## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-ST-DW-0001-D01 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-0100 |  |  | Transmital Date:9/18/2021
Document Title: Standard Drawing For Fire Proofing |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0006-HV-TR-0100 |  |  | Transmital Date:9/18/2021
[5 empty] | CRS No:NISOC-CRS-CRS-BK-GNRAL-PEDCO-000-EL-SP-0016-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقطه نظرات پیشین این امور در پاسخ به ترانسمیتال 0033(نامه ی شماره 166216مورخ 1400/05/24) همچنان بر قوت خود باقی است . لذا دقت نظر لازم در خصوص تولید مدارک بکار گرفته شود . |  | 00/2294/210029 | 1400/07/01 | موارد نامبرده در ترنسمیتال قبلی شامل استاندارد مرجع مربوطه در مدارک ( در قسمت Reference Drawing ) و مشخصات مربوط به بتن و فلزات ( در قسمت Note نقشه ) در Revision D01 اعمال گردیده اند .
2 | مدرک Native ارسالی فاقد Title Block است ، لذا اصلاح شود . |  | 00/2294/210029 | 1400/07/01 | اصلاح گردید .
3 | سایز آرماتور آجدار مصرفی در مقاطع مشخص گردد. نوع آرماتور نیز باید AIII لحاظ گردد. |  | 00/2294/210029 | 1400/07/01 | نوع آرماتور در Note شماره 11 و سایز آرماتورهای مصرفی نیز در Note های شماره 8و9 مشخص گردیده اند . شایان ذکراست که نوع آرماتور S400 می باشد که با آرماتور مورد نظر کارفرمای محترم (AIII) منطبق می باشد .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: