## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-ST-DW-0017 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-0625 |  |  | Transmital Date:02/22/2022
Document Title: Standard Derawing For Septic Tank |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ST-TR-0625 |  |  | Transmital Date:02/22/2022
[5 empty] | CRS No:NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 00/2294/425598 | 1400/12/07 | اصلاح گردید
2 |  |  | 00/2294/425598 | 1400/12/07 | سازه بتن مسلح در نظر گرفته شد
3 |  |  | 00/2294/425598 | 1400/12/07 | اضافه گردید
4 |  |  | 00/2294/425598 | 1400/12/07 | مقادیرپارامتر C برابر است با : 200-(E+D) و واتراستاپ در محل اتصال دیوار به کف در نظر گرفته شد
5 |  |  | 00/2294/425598 | 1400/12/07 | با توجه به پارامتری بودن ابعاد ، جداول فوق توسط دفتر فنی درکارگاه تهیه می گردد.
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: