## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-DT-0005_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0749 |  |  | Transmital Date: 27 Mar 2022
Document Title: Data Sheets For Pressure & Safety Relief Valves |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-0749 |  |  | Transmital Date: 27 Mar 2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0005_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument Comments
1 | ليست مدارك مرجع در ديتا شيت اضافه گردد. |  | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | اضافه گردید.
2 | در قسمت PURCHASE عبارت will be finalized later اضافه گردد. |  | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | اضافه گردید.
3 | متريال spring مطابق با مدرك specification for PSV در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | اعمال گردید.
4 | با توجه به مغايرت بين اطلاعات خط در P&ID و ديتاشيت، اطلاعات مربوط به متريال بر اساس آخرين مستندات مجددا مورد بازنگري قرار گيرد. |  | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | اعمال گردید.
5 | تست ها مانند Hydro test و seat leakage test در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | اعمال گردید.
6 | با توجه به مغايرت بين اطلاعات خط در P&ID و ديتاشيت، اطلاعات مربوط به متريال بر اساس آخرين مستندات مجددا مورد بازنگري قرار گيرد. |  | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | اعمال گردید.
Process Comments
7 | شماره خط با آخرين ويرايش P&ID مطابقت ندارد. |  | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | اعمال گردید.
8 | نهايي سازي مدرك منوط به تاييد محاسبات مربوطه مي باشد. |  | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | ملاحظه گردید.
9 | فشار طراحي و ساير اطلاعات فرايندي مجدد مورد بازبيني قرار گيرد. |  | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | اعمال گردید.
Piping Comments
10 | ويرايش P&ID مشخص شود |  | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | ملاحظه گردید.
11 | شماره خط مطابق با P&ID مشخص شود. |  | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | اعمال گردید.
12 | سايز مطابق با P&ID مشخص شود. |  | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 16 Apr 2022 |  |  |  |  | Date: