## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GNRAL-PEDCO-000-IN-SP-0010 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-0029 |  |  | Transmittal Date: 04 ـAug 2021
Document Title:Specification For Instrument and F&G cables |  |  |  |  | PEDCO Tr. No.:BK-HD-PEDCO-T-0029 |  |  | Transmittal Date: 04 ـAug 2021
[5 empty] | CRS No:NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0010-D00 |  |  | CRS Status:
Item |  |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدارک زیر به بخش مراجع افزوده گردند. |  | 1400/2294/320793 | 1401/09/26 | مطابق خواست کارفرمای محترم اضافه شد.
2 | بخش Abbreviation کامل شود. |  | 00/2294/320793 | 1401/09/26 | نواقص برطرف گردید.
3 | بخشی به نام Order of Precedence جهت تعیین اولویت با هدف رفع اختلافات میان مدارک و استانداردها اضافه شود. |  | 00/2294/320793 | 1401/09/26 | مطابق خواست کارفرمای محترم اضافه شد.
4 | توضیحات بخشهای زیر اضافه شوند. Cable Tray and Conduit Support Junction Boxes Guarantee |  | 00/2294/320793 | 1401/09/26 | بغیر از Guarantee که بر اساس توافق با کارفرمای محترم به مدارک MR منتقل شده بقیه موارد اضافه گردید.
5 | بخشی بعنوان Terms and Definition اضافه شود. |  | 00/2294/320793 | 1401/09/26 | در قسمت 1 تحت نام General Definition ذکر شده است.
6 | عناوین، عبارات و توضیحات فارسی از مدرک حذف گردند. |  | 00/2294/320793 | 1401/09/26 | بجز عبارات فارسی موجود در Header که مطابق فرمت نهایی شده است عبارت فارسی دیگری یافت نگردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and inculpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 10 Jan 2022 |  |  |  |  | Date: