## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GNRAL-PEDCO-000-IN-SP-0010 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-0029 |  |  | Transmittal Date: 04 ـAug 2021
Document Title: Specification For Instrument/F&G Cables |  |  |  |  | PEDCO Tr. No.:BK-HD-PEDCO-T-0029 |  |  | Transmittal Date: 04 ـAug 2021
[5 empty] | CRS No:NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0010-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Control and instrumentation Design Creiteria shall be considered. |  | BK-SUR-ENG-INS-00-01341 | 2021-08-15 | all document are compatible with each other
2 | Please concider following items in standard section: IPS-M-IN-100 IPS-G-IN-220 IPS-C-IN-190 |  | BK-SUR-ENG-INS-00-01341 | 2021-08-15 | Implemented
3 | Below note shall be added end of standard section: "Vendor shall state the additional Codes and Standards if necessary." |  | BK-SUR-ENG-INS-00-01341 | 2021-08-15 | Implemented
4 | applicable items related to the specification shall be mentioned in Abbreviation section . (for example BDV,UV and other cases shall be deleted) |  | BK-SUR-ENG-INS-00-01341 | 2021-08-15 | Implemented
5 | its recommended to specify environment condition (for area and rack room) in addition of reffer to Process Basis of Design” Doc. No. “BK-GNRAL-PEDCO- 000-PR-BD-0001 |  | BK-SUR-ENG-INS-00-01341 | 2021-08-15 | Due to prevent constrating to reissue all documents in case of any modification in environment data we suggest you to avoid data duplicating in documents if acclicable and accept referenced data.
6 | Priority of Documents shall be specified. |  | BK-SUR-ENG-INS-00-01341 | 2021-08-15 | Implemented
7 | Below note or same as that shall be mentioned: "1-Cable sample: When specified in the requisition, VENDOR shall provide CLIENT / EPC CONTRACTOR with a 300mm length of each type of cable, clearly marked with its Type No, to enable glands to be checked. 2-Cable Code Identification" |  | BK-SUR-ENG-INS-00-01341 | 2021-08-15 | Implemented
8 | Spare parts and special tools shall be checked according to Client procedure and contract. |  | BK-SUR-ENG-INS-00-01341 | 2021-08-15 | Implemented
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and inculpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 15 Aug 2021 |  |  |  |  | Date: