## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0582 |  |  | Transmital Date: 13/Feb/2022
Document Title: PMR For Gas Compressors |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-ME-TR-0582 |  |  | Transmital Date: 13/Feb/2022
[5 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به نامه شماره BK-PEDCO-NISOC-0011-ME-LT-25575 مورخ 1400/11/25 به اطلاع می رساند مدارک MR پس از تولید و نهایی شدن کلیه مدارک مهندسی تفصیلی مربوطه می بایست تولید گردد، چرا که تمامی مدارک در مئرد هر پکیج خرید می بایست با درج ویرایش نهایی و عنوان آن در متن ضمیمه MR شود. از آنجایی که مدارک مهندسی تفصیلی پیش نیاز تاکنون نهایی نشده اند لذا این مدرک در این برهه ناقص به شمار می آید. |  | 00/2294/430723 | 1400/12/10 | با توجه به اینکه تجهیز مربوطه در مرحله خرید می باشد لذا مدرک MR کمپرسور با ویرایش جدید می بایست در اختیار سازندگان قرار گیرد. همچنین به اطلاع کارفرمای محترم می رساند که مدارک مهندسی تفصیلی مربوطه با درج آخرین ویرایش و ضمیمه آن ها به مدرک MR ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: 3/5/2022 |  |  |  |  | Date: 05/30/2022