## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-TB-0002-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0759 |  |  | Transmittal Date: 28/Mar /2022
Document Title: TBE FOR Gas Dehydration Package |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-ME-TR-0759 |  |  | Transmital Date: 28/Mar /2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-TB-0002-D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Mechanical comments
1 | Technical detail for the "Delham" offer to be filled out. There are too many details to provided after P.O., which makes the technical comparison ineffective. |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | Noted.
2 | Hazardous Area Classification to be unified for all vendors. |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | Noted.
3 | "Gastech" offer package capacity is not in accordance with others. |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | Noted.
4 | BMS Logic requirement shall be unified for all offers |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | Noted.
5 | Fireproofing requirement shall be unified for all vendors |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | Noted.
6 | Anchor bolt requirement shall be unified for all vendors |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | Noted.
7 | Supply of Industrial Computer shall be unified for all vendors |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | There is no PC in vendor scope of work. Package control moded is type B and all control activities will be done through plant DCS/ESD.
8 | Please clarify why performance guarantee status for "Gastech" and "TJ" offers is "No", and "NA", respectively. |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | Gastech and Tehran Javan' s performance guarantee are conditional and It is not acceptable.
9 | Vendors offered materials and C.A. are inconsistent (e.g. 3mm C.A. for SS316L), this matter shall be solved. |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | Noted.
10 | Solely "Gastech" considered the service to be 'Lethal", please clarify whether this assumption is a must or not. If so, all other vendors shall do the same; otherwise, "Gastech" shall revise the offer accordingly. |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | Noted.
| Instrument comments |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25
| - لازم است كه موارد Deviation براي تمامي شركت ها در يك فايل ورد جمع بندي گردد. |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | Noted.
| - Recommendation مربوط به vendor براي انتخاب نوع كنترل پنل ارائه گردد. |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | There is no panel in vendor scope of work. Package control moded is type B and all control activities will be done through plant DCS/ESD
| - با توجه به جدول ارائه شده مورد مربوط به B1 توسط وندورها بصورت واضح مشخص شود. |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | modified
| - ميزان Ingress Protection for outdoor instrumentations براي تمامي وندورها در جدول مشخص گردد. |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | modified
| - بر اساس اين TBE محدوده كاري، كابل كشي از Jb داخل فيلد تا اتاق كنترل مشخص گردد |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | modified
| - براي شفاف سازي بهتر پيشهناد مي گردد كه proposal offer TCL ارائه گردد. |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | Noted.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M.ESMAEILI | Signature | H.naserizadeh |  |  | Clarified By: | Signature
| Date: 4/25/2022 |  |  |  |  | Date: