## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No: BK-GNRAL-HD-000-PM-PR-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PM-TT-0608 |  |  |  | Transmital Date: | 2022-02-20
Document Title: PROJECT COORDINATION PROCEDURE |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PM-TR-0608 |  |  |  | Transmital Date: | 2022-02-20
[5 empty] | CRS No: PEDCO-BK-GNRAL-HD-000-PM-PR-0001_G03 |  |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion
1 | چارت سازمانی به روز گردد |  | MOM | 2021-05-30 | اعمال گردید
2 | جدول کلاس مدارک اضافه گردد |  | MOM | 2021-05-30 | اعمال گردید
3
4
5
6
7
8
9
10
11
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: