## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DW-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0709 |  |  | Transmital Date: 3/9/2022
Document Title: Typical Instrument Installation Drawing |  |  |  |  | PEDCO Tr. No.: BK-GCS-PEDCO-120-IN-DW-0001-0709 |  |  | Transmital Date: 3/9/2022
[5 empty] | CRS No: NISCO-CRS-BK-GCS-PEDCO-120-IN-DW-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
3 | فهرست مدارک مرجع اضافه گردد. |  | 1401/2294/9656 | 1401/01/15 | اعمال گردید.
| به ابتدای مدرک صفحه ای تحت عنوان فهرست اضافه گردد. |  | 1401/2294/9656 | 1401/01/15 | اعمال گردید.
| این مدرک می بایستی براساس استانداردهای نصب IPS (از جمله IPS-D-IN-106 ) تکمیل گردد. |  | 1401/2294/9656 | 1401/01/15 | این مدرک مطابق با پروژه های قبلی مناطق نفتی جنوب و براساس حداقل های IPS-D-IN-106 (این حداقل ها شامل ابعاد ، اندازه و متریال ) برآورده شده است همچنین نحوه نصب بسیاری تجهیزات از جمله jb در این استاندارد وجود ندارد که مطابق با همان پروژه های قبلی تهیه گردیده است.
| ابعاد و اندازه ها و همچنین متریال ‌های ارائه شده مطابق با استاندارد مطابق با استاندارد IPS مورد بازنگری قرار گیرد. |  | 1401/2294/9656 | 1401/01/15 | این مدرک مطابق با پروژه های قبلی مناطق نفتی جنوب و براساس حداقل های IPS-D-IN-106 (این حداقل ها شامل ابعاد ، اندازه و متریال ) برآورده شده است همچنین نحوه نصب بسیاری تجهیزات از جمله jb در این استاندارد وجود ندارد که مطابق با همان پروژه های قبلی تهیه گردیده است.
4 | نمونه نصب تجهیزات ابزاردقیق، برای همه ی تجهیزات ابزاردقیق مورد استفاده در بسته کاری نمایش داده شود. |  | 1401/2294/9656 | 1401/01/15 | نمونه نصب در این مدرک نمایش داده می شود همچنین برای تجهیزاتی که روی پایپ می‌باشد می بایست به مدرک HOOKUP مراجعه گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 7 Feb 2022 |  |  |  |  | Date: