## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W018S-PEDCO-110-CV-MR-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0768 |  |  | Transmital Date: 3/Apr/2022
Document Title: PMR For Geomembrane - W018S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-0768 |  |  | Transmital Date: 3/Apr/2022
[5 empty] | CRS No: NISOC-CRS-BK-W018S-PEDCO-110-CV-MR-0001_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در صفحه 5 از 18 - بخش GENERAL 2.0 ردیف 3، TABLE1-2 ، حجم اعلام شده فقط جهت اطلاع کارفرما تلقی می شود. |  | 01/2294/13822 | 1401/01/18 | -
2 | در صفحه 11 از 18 - بخش GUARANTEE AND WARRANTY 12.0 - مقتضی است با مراجعه به شرح قرارداد-تسهیلات احداث و تعمیر چاه ها-عملیات سیویل و جاده های دسترسی - 1-4-10- خدمات اجرایی سیویل-که به ارائه گارانتی حداق 10 ساله عایق ژئوممبران اشاره شده است- این ردیف از مدرک ارسالی، مطابق با شرح پیمان اصلاح گردد. |  | 01/2294/13822 | 1401/01/18 | مطابق با پیوست 10 کلی "بند 10-11-2 در خصوص بسته‏های‏ کاری در بخش سطح الارض و تحت الارض، دوره زمانی گارانتی مربوط به کالا/ تجهیزات به مدت 18 ماه از زمان تحویل کامل و یا 12 ماه از تاریخ نصب هر فقره از کالا/تجهیزات است"، لذا گارانتی حداقل 10 ساله برای ژئوممبرین چاه ها (که مراقبت و حفاظت به خصوصی از آنها نمیشود) قطعا توسط هیچ سازنده ای پذیرفتنی نیست
3 | در رابطه با تست های الزامی پس از انجام عملیات اجرایی، هیچگونه اشاره ای نشده است، لذا اقدام گردد. |  | 01/2294/13822 | 1401/01/18 | با توجه به اینکه مدرک PMR مربوط به خرید کالا می باشد تست های پس از اجرا در مدرک ITP for civil work در بخش مربوط به ژئوممبران لحاظ شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature | M.Fakharian
Date:10/04/2022