## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W018S-PEDCO-110-CV-MR-0002_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0768 |  |  | Transmital Date: 3/Apr/2022
Document Title: PMR For Geotextile - W018S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-0768 |  |  | Transmital Date: 3/Apr/2022
[5 empty] | CRS No: NISOC-CRS-BK-W018S-PEDCO-110-CV-MR-0002_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در صفحه 5 از 17 - بخش GENERAL 2.0 ردیف 3، TABLE1-2 ، حجم اعلام شده فقط جهت اطلاع کارفرما تلقی می شود. |  | 01/2294/13822 | 1401/01/18 | -
2 | در صفحه 5 از 17 - بخش GENERAL 2.0-ردیف 2، 2- اشاره به (HDPE) GEOMEMBRANE MATERIAL شده ، که مقتضی است این موضوع به مصالح ژئوتکستایل تغییر و اصلاح گردد. |  | 01/2294/13822 | 1401/01/18 | اصلاحات مقتضی اعمال گردید
3 | در رابطه با تست های الزامی پس از انجام عملیات اجرایی، هیچگونه اشاره ای نشده است، لذا اقدام گردد. |  | 01/2294/13822 | 1401/01/18 | با توجه به اینکه مدرک PMR مربوط به خرید کالا می باشد تست های پس از اجرا در مدرک ITP for civil work در بخش مربوط به ژئوتکستایل لحاظ شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature | M.Fakharian
Date:10/04/2022