## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W018S-PEDCO-110-CV-MR-0002_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0768 |  |  | Transmital Date: 3/Apr/2022
Document Title: PMR For Getextile - W018S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-0768 |  |  | Transmital Date: 3/Apr/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W018S-PEDCO-110-CV-MR-0001_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بند 2.2، عبارت "High Density PolyEthylene (HDPE) Geomembrae" به "nonwoven Geotextile" تغيير يابد. |  | BK-SUR-ENG-CIV-01-03846 | 11.04.2022 | اصلاحات مقتضی اعمال گردید
2 | در بند 5.1.1 عبارت QA Organization به QA/QC Organization Chart تغییر یابد. |  | BK-SUR-ENG-CIV-01-03846 | 11.04.2022 | اصلاحات مقتضی اعمال گردید
3 | در جدول Attachment 1(List of Reference/Applicable Documents): 1-دستورالعمل FDB Requirements اضافه گردد. 2- دستورالعمل Packing, Marking, Transportation Procedure اضافه شود. 3-نام "دستورالعمل بازرسي" به "دستورالعمل بازرسي خريد و ساخت كالا" تغيير يابد. |  | BK-SUR-ENG-CIV-01-03846 | 11.04.2022 | اصلاحات مقتضی اعمال گردید
4 | برخي از مدارك Attachment 2 براي Geotextile كاريردي نيست. جدول براي اين نوع كالا اصلاح گردد. |  | BK-SUR-ENG-CIV-01-03846 | 11.04.2022 | اصلاحات مقتضی اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature | M.Fakharian
Date:10/04/2022