## برق
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-GNRAL-PEDCO-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PI-TT-0001 |  |  |  | Transmital Date: |  | 2021-07-07
Document Title: Master Document Identification List (MDL) |  |  |  |  | PEDCO Tr. No.: - |  |  |  | Transmital Date: -
[5 empty] | CRS No: BK-PEDCO-NISOC-CRS-0002 |  |  |  | CRS Status:
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No:BK-GNRAL-PEDEC-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0211 |  |  | Transmital Date: 11/7/2021
Document Title: Master Document List (MDL) & Updating |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-GE-TR-0211 |  |  | Transmital Date:11/7/2021
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion | Clarification (By EPC Contractor)
1 | According to our telephone conversation following documents shall be added or modified for "Service to Company (Camp Documents): -MTO for electrical -Earthing & Lightning calculation -Lighting Calculation -Single Line Diagram (Sahll be submitted for each building separately) -Lighting Layout (Sahll be submitted for each building separately) *Diesel sizing shall be considered in Load List |  | BK-SUR-ENG-GEN-00-02026 | 2021-11-16 | با توجه به اینکه ، تمامی فعالیتهای ساخت این مجموعه توسط فروشنده انجام خواهد گردید، مدارک خواسته شده توسط سازنده ساندویچ پنلها تهیه و با تایید کارفرمای محترم خواهد رسید، لذا نیازی به اضافه نمودن مدارک در MDL نیست. |  |  | اعمال نگردید
2 | Telecomm comments |  | BK-SUR-ENG-GEN-00-02027 | 2021-11-16 | نقطه نظرات دریافتی مربوط به پروژه بینک نبود لذا از دید این پیمانکار لیست مدارک ارسالی نهایی فرض می گردد. |  |  | اعمال نگردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 07.Aug.2021

## سیویل
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-GNRAL-PEDCO-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PI-TT-0001 |  |  |  | Transmital Date: |  | 2021-07-07
Document Title: Master Document Identification List (MDL) |  |  |  |  | PEDCO Tr. No.: - |  |  |  | Transmital Date: -
[5 empty] | CRS No: BK-PEDCO-NISOC-CRS-0002 |  |  |  | CRS Status:
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No:BK-GNRAL-PEDEC-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0211 |  |  | Transmital Date: 11/7/2021
Document Title: Master Document List (MDL) & Updating |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-GE-TR-0211 |  |  | Transmital Date:11/7/2021
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion | Clarification (By EPC Contractor)
1 | با توجه به جلسه قبلي با مديريت مهندسي پروژه بينك ، مقرر شده بود تا مداركي كه خارج از ليست مدارك مهندسي درج شده بودند تعيين تكليف/حذف گردند( بطور مثال : Technical/Site Queries و As-Built Document Bookletsو Final Engineering Dossier و ...) ولي در ليست جديد مجدد ارائه شده اند. با توجه به اينكه از جمع بندي تيم پروژه با كارفرما اطلاعي در دست نمي باشد به نظر ضروري است تا اين موارد شفاف سازي شود |  | BK-SUR-ENG-GEN-00-02026 | 2021-11-16 | موارد مذکور عینا مطابق با نظامنامه و ساختار شکست شرکت نفت خیز جنوب بوده و می بایست در نظر گرفته شود. |  |  | اعمال نگردید
2 | در خصوص مدارك كمپ نيز آيا تصميم به ارائه مدارك در ليست اصلي بوده و يا مي بايست مجزا در نظر گرفته شوند |  | BK-SUR-ENG-GEN-00-02026 | 2021-11-16 | مطابق با نقطه نظر ذینفع اصلی ، می بایست درلیست اصلی مدرک ارائه گردد. |  |  | اعمال نگردید
3 | پيمانكار ملزم شود تا تغييرات و جابجايي مدارك را درج نمايد تا قابل رديابي باشد. |  | BK-SUR-ENG-GEN-00-02026 | 2021-11-16 | موارد تغییر یافته در ستون Add/Modify نشان داده شده اند. |  |  | اعمال نگردید
4 | نقطه نظرات اعلامی روی فایل اکسل پیوست شده |  | BK-SUR-ENG-GEN-00-02026 | 2021-11-16 | نقطه نظرات دریافتی برروی فایل اکسل نیز بصورت زیر اعمال گردیده است:
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 07.Aug.2021

## QC
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No:BK-GNRAL-PEDEC-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0211 |  |  | Transmital Date: 11/7/2021
Document Title: Master Document List (MDL) & Updating |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-GE-TR-0211 |  |  | Transmital Date:11/7/2021
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion | Clarification (By EPC Contractor)
1 | مدرك Criticality Assessment Procedure اضافه گردد |  | طبق صورت جلسه مورخ 20/6/1400 | 20/6/1400 | قبلا دیده شده است. |  |  |  | Closed | Closed
2 | مدرك Non Conformance Control Procedure اضافه گردد |  | طبق صورت جلسه مورخ 20/6/1400 | 20/6/1400 | اعمال گردید |  |  |  | Closed | Closed
3 | مدرك Corrective Action Procedure اضافه گردد |  | طبق صورت جلسه مورخ 20/6/1400 | 20/6/1400 | اعمال گردید |  |  |  | Closed | Closed
4 | مدرك Final Data Book (FDB) Requirements اضافه گردد |  | طبق صورت جلسه مورخ 20/6/1400 | 20/6/1400 | قبلا دیده شده است. |  |  |  | Closed | Closed
5 | مدرك Material Reciving, Storage, Handling Procedure اضافه گردد |  | طبق صورت جلسه مورخ 20/6/1400 | 20/6/1400 | اعمال گردید |  |  |  | Closed | Closed
6 | مدرك Packing, Marking, Transportation Procedure اضافه گردد |  | طبق صورت جلسه مورخ 20/6/1400 | 20/6/1400 | اعمال گردید |  |  |  | Closed | Closed
7 | طبق صورتجلسه مورخ 20/6/1400 عناوين شامل Management Document و General QC Document و ... درج شده و زير مجموعه هر بخش در ذيل عناوين درج گردد |  | طبق صورت جلسه مورخ 20/6/1400 | 20/6/1400 | اعمال گردید |  |  |  | Closed | Closed
8 | مدرك Pressure Test Procedure اضافه شود. |  | طبق صورت جلسه مورخ 20/6/1400 | 19/10/1400 |  |  |  |  | مدرك فوق اضافه نشده است. | اضافه گردید
9 | مدرك Field Joint Coating Procedure for Pipeline دو بار در رديفهاي 1.3.15.2.2.9 و 1.3.15.2.2.11 تكرار شده است. يكي از رديفها حذف گردد. |  |  | 19/10/1400 |  |  |  |  | ‍Closed | Closed
10 | مدارك Project Quality Plan و Technical Query Procedure به بخش مدارك Management انتقال يابد. |  |  | 19/10/1400 |  |  |  |  | Closed | Closed
11 | مدرك Field Joint Coating Procedure for Pipeline به ديسيپلين Pipeline انتقال يابد. |  |  | 19/10/1400 |  |  |  |  | منتقل نشده است. | منتقل گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 07.Aug.2021

## ابزار دقیق
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-GNRAL-PEDCO-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PI-TT-0001 |  |  |  | Transmital Date: |  | 2021-07-07
Document Title: Master Document Identification List (MDL) |  |  |  |  | PEDCO Tr. No.: - |  |  |  | Transmital Date: -
[5 empty] | CRS No: BK-PEDCO-NISOC-CRS-0002 |  |  |  | CRS Status:
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No:BK-GNRAL-PEDEC-000-GE-DN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0397 |  |  | Transmital Date: 12/28/2021
Document Title: Master Document List (MDL) & Updating |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-GE-TR-0397 |  |  | Transmital Date: 12/28/2021
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G05 |  |  | CRS Status: | AP
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion | Clarification (By EPC Contractor)
1 | مدرک Delay Analysis Report به لیست مدارک اضافه گردد در این مقطع نقطه نظر خاصی مطرح نمی باشد |  | س ط ب /27286 | 2022-03-05 | براساس تغییرات مورد نیاز پروزه به روز رسانی گردید کلیه کدهای مربوط به کلاس مدارک و POI براساس ایمیل دریافتی از آن کارفرما اصلاح گردید. با توجه به تغییرات زیاد به وجود آمده در لیست مدارک، اوزان پس از نهایی سازی و تهیه WBS مربوطه اعمال خواهد شد.
2
3
4
5
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 07.Aug.2021