## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-SSGRL-PEDCO-110-ME-DT-0001-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0790 |  |  | Transmital Date: 09/Apr/2022
Document Title: DATA SHEETS FOR FUEL OIL STORAGE DRUM OF WELL PADS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-ME-TR-0790 |  |  | Transmital Date: 09/Apr/2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-ME-DT-0001-D01 |  |  | CRS Status:
item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همان گونه که بارها متذکر گردید ضروری است دلایل بروز تغیییرات جدیدی که مد نظر این امور نبوده است مشخص گردد. در این راستا ارائه Reply Sheet از اهمیت فراوان برخوردار است. |  | 01/2294/43245 | 1401-02-09 | نقطه نظر کارفرمای محترم مدنظر قرار خواهد گرفت.
2 | دلایل تغییر نوع فلنج از WN به SO بیان گردد. |  | 01/2294/43245 | 1401-02-09 | تجهیز مد نظر بر اساس استاندارد BS-EN12282 (طراحی و ساخت تانک های اتمسفریک )طراحی میشود و در این استاندارد الزامی برای نوع فلنج وجود ندارد و میتوان از فلنج SO استفاده کرد.
3 | مبنای محاسبه میزان مصرف گازوئیل جه بوده است؟ به مدرک مربوطه ارجاع داده شود. |  | 01/2294/43245 | 1401-02-09 | میزان مصرف گازوئیل بر مبنای مدرک Consumption List, Doc. No. BK-SSGRL-PEDCO-110-PR-LI-0001 و با در نظر گرفتن چهارده روز بوده است که در مدرک نیز ارجاع داده شد. در فایل اصلاحی مبنای محاسبات به 36 ساعت کاهش یافته است و ابعاد مخزن نیز اصلاح شده است.
4 | Sample P&ID, instrumentation |  |  |  | مطابق نظر کارفرما، برای چاه های تعمیراتی، مدرک P&ID حذف خواهد شد و بنابراین شماره مدرک P&ID برای این چاه ها وجود ندارد و برای نمونه مشابه به مدرک دو چاه W007S, W046S ارجاع داده شده است و تجهیزات ابزار دقیق نیز در حیطه کاری وندور خواهد بود.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date: 4/13/2022 |  |  |  |  | Date: 6/6/2022