## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-TB-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0676 |  |  | Transmital Date: 02/Feb/2022
Document Title: TBE FOR GAS COMPRESSORS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-ME-TR-0676 |  |  | Transmital Date: 02/Feb/2022
[5 empty] | CRS No: NISOC-CRS- BK-GCS-PEDCO-120-ME-TB-0001_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به نامه شماره BK-PEDCO-NISOC-0012-ME-LT-27306 مورخ 15/12/1400 (شماره وصول 34346) به اطلاع می رساند همانطور که مطلع هستید مذاکرات و جلسات متعددی در خصوص نوع روغنکاری و خنک کاری انجام شده و نهایتا ویرایش 5 داده برگ فنی کمپرسورهای پروژه طی نامه شماره 01/2294/43097 مورد تایید کارفرما قرار گرفته است. از انجا که پیمانکار طی نامه شماره BK-PEDCO-NISOC-0102-GE-LT-2496 انحرافات بهینه را نسبت به طراحی بیان نموده است از اینرو بررسی TBE ویرایش D01 در این مقطع موضوعیت نداشته و پس از دریافت ویرایش و نسخه جدید پیشنهادات فنی ، در اولین فرصت مطالعه و پاسخ ارایه خواهد شد. |  | 01/2294/47400 | 1401/02/11 | به اطلاع کارفرمای محترم می رساند، مدرک TBE با ویرایش D02 بر اساس پیشنهادات جدید سازندگان و مکانیکال دیتاشیت اصلاح شده با ویرایش D06 تهیه شده است. ضمنا پیشنهادات جدید سازندگان به پیوست تقدیم حضور می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: |  |  |  |  | Date: 06/11/2022