## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-TB-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0676 |  |  | Transmital Date: 02/Feb/2022
Document Title: TBE FOR GAS COMPRESSORS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-ME-TR-0676 |  |  | Transmital Date: 02/Feb/2022
[5 empty] | CRS No: PEDCO-CRS- BK-GCS-PEDCO-120-ME-TB-0001_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | 1-All the previous comments are still valid. 2- LMF is chinese manufacturer, so it shall be review and accepted bby end-user 3-Somi Mfg is rejected because of deviation. 4- Hirgan shall provide 3 accepted and approved technical offers. |  | BK-SUR-ENG-MEC-00-03608 | 2022-03-15 | 1. Refer to Hirgan Reply on your previous comments. 2. If there is any limitation for using chinese manufacturer (as per contract) please inform. 3. It is replaced with an other manufacturer( SBW). 4. Already submitted for your review.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M.ESMAEILI | Signature | H.naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: 25/27/2022 |  |  |  |  | Date: 06/11/2022