## SHEET 1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-IN-LI-0005_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0587 |  |  | Transmital Date: 13 Feb 2022
Document Title: Panels & Junction Box List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0011-IN-TR-0587 |  |  | Transmital Date: 13 Feb 2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0005_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | شماره مدرک مطابق با MDL اصلاح گردد. |  | 00/2294/432761 | 1400/12/12 | کامنت کارفرمای محترم اعمال گردید.
2 | تعداد I.O ها در صفحه سوم مدرک مورد بازبینی قرار گیرد و در صورت نیاز اصلاح گردد. |  | 00/2294/432761 | 1400/12/12 | تعداد i.o ها با مدارک مرجع ( DSC & ESD & F&G I.O LISTS ) بازنگری شد.
3 | نحوه کددهی junction box نیز بایستی تشریح گردد. |  | 00/2294/432761 | 1400/12/12 | نحوه کددهی JB ها در مدارک مرجع از قبیل Main Instrument Cable List for Field Instruments و Termination Diagram قید شده است
4 | شماره تگ های مربوط به JB های آنالوگ سیستم F&G بایستی در هماهنگی با مدرک Instrument & F&G Junction Box & Termination Diagram باشد. تمامی تناقضات اینچنینی برطرف گردند. |  | 00/2294/432761 | 1400/12/12 | مدرک حاضر با مدارک مرجع همسان سازی شد.
5 | حداکثر تعداد کابل های وروردی JBE-A-1009 مطابق مدرک Instrument & F&G Junction Box & Termination اصلاح گردد. |  | 00/2294/432761 | 1400/12/12 | مدرک حاضر با مدارک مرجع همسان سازی شد.
6 | آیتم Input Cable Plug NO. * Size مربوط به JBF-D-1006 بایستی در هماهنگی با مدرک Instrument & F&G Junction Box & Termination Diagram باشد. تمامی تناقضات اینچنینی برطرف گردند. |  | 00/2294/432761 | 1400/12/12 | مدرک حاضر با مدارک مرجع همسان سازی شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 26 Feb 2022 |  |  |  |  | Date: