## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-SSGRL-PEDCO-110-IN-DG-0002 |  |  |  |  | NISOC Contractor Tr. No.:BK-HD-PEDCO-T-0369 |  |  | Transmittal Date: 20 Dec 2021
Document Title:WHCP Hydraulic Diagrams - Wellheads |  |  |  |  | NISOC Tr. No.: BK-PEDCO-NISOC-0008-IN-TR-0369 |  |  | Transmital Date: 20 Dec 2021
[5 empty] | CRS No:PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پیرو نامه های شماره 200192 مورخ 1400/6/24 و 283484 مورخ 1400/6/30 اعلان می گردد، مدارک مرجع از جمله مدرک Instrumentation & control system design criteria نهایی/ تولید نشده اند. |  | 1400-2294-352438 | 1400/10/16 | این مدرک مطابق آخرین نسخه از مدارک مرجع , پیشنهادات سازندگان بروز رسانی گردید، لازم به ذکر است مدرک Instrument & Control System Design Criteria تولید شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: