## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-IN-DT-0006_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0695 |  |  | Transmital Date: 7 Mar 2022
Document Title: Data Sheets For Control/Regulator valves - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-IN-TR-0695 |  |  | Transmital Date: 7 Mar 2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0006_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مقدار H2S صفر ذکر شده که اشتباه است |  | 1400-2294-453218 | 1400/12/25 | اصلاح گردید .
2 | درصد آب همراه می بایست اصلاح گردد. |  | 01/2294/25145 | 1401/01/27 | اصلاح گردید .
3 | میزان CO2 اصلاح شود. |  | 01/2294/25145 | 1401/01/27 | اصلاح گردید .
|  |  | 1400-2294-453218 | 1400/12/25 | لازم به توضیح است نظر به تغییرات مدرک P&ID، این مدرک بر اساس آخرین رویژن P&ID به روز رسانی شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 14 Mar 2022 |  |  |  |  | Date: