## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0668 |  |  | Transmital Date: 3/5/2022
Document Title: P&ID - Gas Compression Inlet Gas Pipeline (Golkhari) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0668 |  |  | Transmital Date: 3/5/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات عمومی |  | 1401-2294-23096 | 1401/01/26 | پاسخ کلیه‌ نظرات عمومی در پاسخنامه به شماره NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D02 موجود است.
2 | با توجه به عدم تغییر شرایط فرآیندی به طور قابل ملاحظه، علت تغییر سایز قبل و بعد FCV-2102 چیست؟ |  | 1401-2294-23096 | 1401/01/26 | تغییر سایز مربوط به جریان Slug بوده که توضیحات مربوطه در بند 4 موارد عمومی ارائه گردید.و با توجه به نتایج مهندسی ارزش این مورد اصلاح گردید.
3 | شیر مزبور نمی تواند در محل تغییر سایز خط قرار داده شود و این موضوع می بایست اصلاح گردد. |  | 1401-2294-23096 | 1401/01/26 | اصلاح گردید.
4 | تغییر سایز مزبور می تواند مشخصات فرآیندی را دستخوش تغییر نماید که درPFD متناظر نمایش داده نشده است. |  | 1401-2294-23096 | 1401/01/26 | اصلاح گردید.
5 | استفاده از لوله ۱۴ اینچ به دلیل مشکلات تامین لوله و اتصالات و نیز مشکلات تعمیراتی حادث از این موضوع توصیه نمی گردد. |  | 1401-2294-23096 | 1401/01/26 | اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: