## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0009 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0668 |  |  | Transmital Date: 3/5/2022
Document Title: P&ID - 2nd Stage Gas Compression Suction Drums |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0668 |  |  | Transmital Date: 3/5/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات عمومی |  | 1401-2294-23096 | 1401/01/26 | پاسخ کلیه‌ نظرات عمومی در پاسخنامه به شماره NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D02 موجود است.
2 | تخلیه مایعات مخزن مطابق اسناد پایه از طریق مکانیزم کنترلی انجام گردد. شایان ذکر است که این نقشه ها در هماهنگی با تجهیزات واحد موجود در زمان مطالعات مهندسی طراحی گردیده و تجربه عملی در خصوص صحت عملکرد انتخابی وجود دارد. |  | 1401-2294-23096 | 1401/01/26 | مخازن مذکور جهت قطره گیری گاز ورودی کمپرسور میباشد و با توجه به این که مایعات همراه پیشتر در مخازن slug catcher و inlet k.o drum جدا شده است. میزان تجمع مایعات این مخازن به صورت دوره ای بوده و بسیار ناچیز است. از این رو نیاز به استفاده از شیر کنترلی نمیباشد و تخلیه به صورت on/off صورت میگیرد.
3 | دمای طراحی بازنگری گردد. |  | 1401-2294-23096 | 1401/01/26 | دمای طراحی صحیح میباشد. و بر اساس 20% natural draft کولر محاسبه شده است.
4 | استفاده از شیر برقی XV (ON/OFF) برای کنترل مایعات مخازن V-2102A/B/C با توجه به فاصله کم بین سطح (LLL) و سطح زیاد مایع (HLL) در مخزن ذکر شده (30 سانتی متر) ممکن است مرتب باعث باز و بسته شدن شیر برقی یاد شده گردد. لذا پیشنهاد می گردد در این خصوص بررسی های لازم به عمل آمده و در صورت صلاحدید از شیرهای LCV استفاده گردد. |  | 1401-2294-23096 | 1401/01/26 | با توجه به اینکه کمپرسور به صورت تندم میباشد فشار مابین دو کمپرسور توسط UCP کنترل شده و در این مسیر شیر ON/OFF دیگری وجود ندارد تا باعث افزایش فشار گردد و نیازی به این شیر نمیباشد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: