## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0668 |  |  | Transmital Date: 05.Mar.2022
Document Title: P&ID - 1st Stage Gas Compression Suction Drums |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0668 |  |  | Transmital Date: 05.Mar.2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بصورت عمومي در تمام PID ها در جلسه 27-11-1400 مقرر گرديد كه نمايش نوع اتصال شيرها (فلنجي/ جوشي و...) نمايش داده شود كه اين مهم در اين ويرايش انجام نپذيرفته است. |  | BK-SUR-ENG-PCS-01-03755 | 09.Apr.2022 | اعمال گردید.
2 | نهايي سازي خطوط فلر منوط به ارسال محاسبات قابل قبول مي باشد. |  | BK-SUR-ENG-PCS-01-03755 | 09.Apr.2022 | در حال حاضر سایز خطوط بر اساس اخرین ویرایش محاسبات شبکه فلر در نظر گرفته شده است و در صورت تغییر در چیدمان و سایز خطوط در مدرک اعمال میگردد.
3 | فلنج هاي مرتبط با ادوات ابزار دقيق متصل به مخزن مشخص گردد. |  | BK-SUR-ENG-PCS-01-03755 | 09.Apr.2022 | اعمال گردید.
4 | نهايي سازي ابعاد ظرف پس از تاييد محاسبات مربوطه امكان پذير مي باشد. |  | BK-SUR-ENG-PCS-01-03755 | 09.Apr.2022 | مورد تایید است.
5 | ابزاردقيق: با توجه به اينكه كانكشن فرآيندي براي ادوات دما بر روي تفكيك گرها بعضا 1 1/2" و يا 2" در نظر گرفته شده است. براي همسان سازي براي تمامي ادوات دما بر روي تفكيك گرها 2" در نظر گرفته شود در غير اين صورت در مورد مغايرت كانكشن ها شفاف سازي صورت پذيرد. |  | BK-SUR-ENG-PCS-01-03755 | 09.Apr.2022 | اعمال گردید.
6 | RS مشخص گردد. |  | BK-SUR-ENG-PCS-01-03755 | 09.Apr.2022 | در مدرک SYMBOL &LEGEND مشخص گردیده است.
7 | لازم است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-01-03755 | 09.Apr.2022 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021