## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0009 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0668 |  |  | Transmital Date: 05.Mar.2022
Document Title: P&ID - 2nd Stage Gas Compression Suction Drums |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0668 |  |  | Transmital Date: 05.Mar.2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بصورت عمومي در تمام PID ها در جلسه 27-11-1400 مقرر گرديد كه نمايش نوع اتصال شيرها (فلنجي/ جوشي و...) نمايش داده شود كه اين مهم در اين ويرايش انجام نپذيرفته است. |  | BK-SUR-ENG-PCS-01-03755 | 09.Apr.2022 | اعمال گردید
2 | كلاس CS00 براي خط خروجي از كولر استفاده شده كه دماي طراحي آن با توجه به Criteria با مدرك PMS مطابقت ندارد. |  | BK-SUR-ENG-PCS-01-03755 | 09.Apr.2022 | مطابق نتایج مطالعات خوردگی در نظر گرفته شده و در صورت نیاز مدرک pms بازنگری میگردد.
3 | شماره خط بالادست BDV درج گردد. |  | BK-SUR-ENG-PCS-01-03755 | 09.Apr.2022 | اعمال گردید
4 | پايپينگ: شيب خط مشخص گردد. |  | BK-SUR-ENG-PCS-01-03755 | 09.Apr.2022 | اعمال گردید
5 | پايپينگ: اتصال فلنجي به مخزن نشان داده شود. |  | BK-SUR-ENG-PCS-01-03755 | 09.Apr.2022 | اعمال گردید
6 | ابزاردقيق: با توجه به اينكه كانكشن فرآيندي براي ادوات دما بر روي تفكيك گرها بعضا 1 1/2" و يا 2" در نظر گرفته شده است. براي همسان سازي براي تمامي ادوات دما بر روي تفكيك گرها 2" در نظر گرفته شود در غير اين صورت در مورد مغايرت كانكشن ها شفاف سازي صورت پذيرد. |  | BK-SUR-ENG-PCS-01-03755 | 09.Apr.2022 | اعمال گردید
7 | لازم است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-01-03755 | 09.Apr.2022 | اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021