## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0012 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0669 |  |  | Transmital Date: 3/5/2022
Document Title: P&ID - 2nd Stage Gas Compression Discharge Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0669 |  |  | Transmital Date: 3/5/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات عمومی |  | 1401-2294-31443 | 1401/01/30 | پاسخ کلیه‌ نظرات عمومی در پاسخنامه به شماره NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D02 موجود است.
2 | تخلیه مایعات مخزن مطابق اسناد پایه از طریق مکانیزم کنترلی انجام گردد. شایان ذکر است که این نقشه ها در هماهنگی با تجهیزات واحد موجود در زمان مطالعات مهندسی طراحی گردیده و تجربه عملی در خصوص صحت عملکرد انتخابی وجود دارد. |  | 1401-2294-31443 | 1401/01/30 | مطابق توضیحات ارئه شده در جلسه PID review میزان تجمع مایعات این مخازن به صورت دوره ای بوده و بسیار ناچیز است. از این رو نیاز به استفاده از شیر کنترلی نمیباشد و تخلیه به صورت on/off صورت میگیرد.
3 | دمای طراحی مطابق اسناد پیمان بازنگری گردد. |  | 1401-2294-31443 | 1401/01/30 | دمای طراحی بر اساس نتایج شبیه سازی و معیار های عموان شده در مدرک design criteria محاسبه شده و صحیح میباشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: