## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0015 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-TR-0669 |  |  | Transmital Date: 3/5/2022
Document Title: P&ID - Instrument & Plant Air System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0669 |  |  | Transmital Date: 3/5/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات عمومی |  | 1401-2294-31443 | 1401/01/30 | پاسخ کلیه‌ نظرات عمومی در پاسخنامه به شماره NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D02 موجود است.
2 | نقشه خشک کننده های هوا به گونه ای نمایش داده شود که دوقلو بودن و بسترهای خشک کن قابل برداشت باشد. |  | 00/2294/401008 | 1400/11/18 | اعمال گردید.
3 | شایان ذکر است بر اساس اسناد پیمان، در مدرک Duty Spec به وضوح به اینکه هر پکیج خشک کن می بایست دارای دو بستر خشک کن باشد، اشاره گردیده است و پاسخ شماره ۷ مورد قبول نمی باشد. مزید اطلاع است که این مدرک نیز تمام آن مطابق با مفاد استاندارد IPS-G-IN-200 و علی الخصوص بخش 8 این استاندارد میباشد. |  | 00/2294/401008 | 1400/11/18 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: