## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0016 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0669 |  |  | Transmital Date: 3/5/2022
Document Title: P&ID - Nitrogen Generation System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0669 |  |  | Transmital Date: 3/5/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات عمومی |  | 1401-2294-31443 | 1401/01/30 | پاسخ کلیه‌ نظرات عمومی در پاسخنامه به شماره NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D02 موجود است.
2 | کلیه آنالیزور ها و تجهیزات در نظر گرفته شده در اسناد پیمان می بایست با توجه به تاکیدات مکرر این امور در این پکیج لحاظ گردد و پاسخ های پیمانکار در این خصوص مورد قبول نیست. |  | 00/2294/401008 | 1400/11/18 | اعمال گردید.
3 | 21- علت در نظر گرفتن سیستم قطع اضطراری voting برای نیتروژن توضیح داده شود همانگونه که قبلا نیز اشاره شده پیمانکار می بایست تغییرات نسبت به پیمان را مطابق رویه تغییرات مورد توافق پیگیری نمایند و هرگونه ادعای تغییرات خارج از این رویه و در آینده مورد قبول واقع نخواهد شد |  | 00/2294/401008 | 1400/11/18 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: