## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0017 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0669 |  |  | Transmital Date: 3/5/2022
Document Title: P&ID - Close Drain System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0669 |  |  | Transmital Date:3/5/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات عمومی |  | 1401-2294-31443 | 1401/01/30 | پاسخ کلیه‌ نظرات عمومی در پاسخنامه به شماره NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D02 موجود است.
2 | پاسخ شماره ۳، نامربوط به نقطه نظر مطرح شده می باشد |  | 00/2294/401008 | 1400/11/18 | اعمال گردید.
3 | شماره پنج مورد قبول نبوده و تجهیز مزبور می بایست مطابق اسناد پیمان در نظر گرفته شود.. |  | 00/2294/401008 | 1400/11/18 | اعمال گردید.
4 | پاسخ شماره ۱۰ مورد قبول نمی باشد و می بایست مطابق اسناد پیمان تجهیز ارسال سیگنال قطع اضطراری فشار در ورودی پمپ در نظر گرفته شود |  | 00/2294/401008 | 1400/11/18 | اعمال گردید و تجهیز کنترل سطح حذف گردید.
5 | برای هدر و مخزن تخلیه بسته، خط گاز purge در نظر گرفته شود. |  | 00/2294/401008 | 1400/11/18 | بر روی هدر خط مذکور اضافه گردید. در خصوص مخزن از مسیر utility connection استفاده می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: