## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0021 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-TR-0670 |  |  | Transmital Date: 3/5/2022
Document Title: P&ID - Oily Water Sewer |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0670 |  |  | Transmital Date: 3/5/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات عمومی |  | 1401-2294-33690 | 1401/02/01 | پاسخ کلیه‌ نظرات عمومی در پاسخنامه به شماره NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D02 موجود است.
2 | جریاناتی که برای ورودی حوضچه روغن در نظر گرفته شده است با سناریو طراحی آن تطابق ندارد و میبایست اصلاح گردد |  | 1401-2294-33690 | 1401/02/01 | مطابق توافقات صورت گرفته جریانات ورودی به حوضچه از Open Drain تجهیزات به کانال جمع آاوری آبهای سطحی و سپس به حوضچه منتقل میگردد.
3 | - میزان حد مجاز خوردگی لوله های ورودی به حوضچه بسیار کم در نظر گرفته شده است. |  | 1401-2294-33690 | 1401/02/01 | مطابق مدرک PMS پروژه در نظر گرفته شده است.
4 | - یک NOTE در مورد LIT-2273 آورده شود که در آن نوع و نیاز یا عدم نیاز به مش، پایپ و ... ذکر گردد. |  | 1401-2294-33690 | 1401/02/01 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: