## 1
جدول شماره 1 : شناسنامه پروژه
عنوان: مهندسی، تامین کالا و تجهیزات، ساختمان و نصب و راه اندازی (EPCC) ابنیه تحت الارض و تاسیسات سطح الارضی طرح نگهداشت و افزایش تولید میدان بینک
شماره قرارداد: BK-00-CO-0001
كارفرما: شرکت توسعه پتروایران
مجري طرح: منصور مهرشاد
مديريت طرح (مشاور):
پيمانكار: مشارکت "هیرگان انرژی- طرح و بازرسی"
مدير پروژه پيمانكار: محمد فخاریان
موضوع: بخش سطح الارض پروژه نگهداشت و افزایش تولید میدان نفتی بینک (بسته بینک) را در قالب پیمان EPCC
محل: میدان نفتی بينك در استان بوشهر در فاصله 20 كيلومتري شمال غربي شهرستان گناوه، واقع شده است
وضعيت: ساير£ متوقف/تعليق£ پايان مدت پيمان£ تكميل پروژه£ پيمان خاتمه داده شده£ در حال اجرا¢
پيشرفت فيزيكي تا پايان مدت ارائه لايحه تاخيرات 2/48 % درصد
مبلغ اوليه قرارداد (ميليون ريال): - |  | مبلغ اوليه قرارداد (يورو): 35,909,880
تعديل قرارداد دارد£ ندارد¢ |  | مدت تعليق قرارداد: -
مدت اوليه (ماه): 24 ماه |  | تاريخ خاتمه مدت اوليه: 1402/04/02
مدت تمديدهاي پيشين (ماه):- |  | تاريخ خاتمه:-
تاخيرات مجاز پيشين (ماه):-
تاريخ امضا قرارداد |  | تاريخ ابلاغ شروع به كار: | 1400/04/02
تاريخ تحويل موقت (بخشي-كلي) |  | تاريخ تحويل قطعي:

## 2
جدول شماره 2 : خلاصه لايحه تاخيرات پروژه
عنوان طرح: | طرح نگهداشت و افزایش تولید میدان بینک |  |  |  | شماره قرارداد : | BK-00-CO-0001
شماره لایحه تاخیرات : | 1 |  |  |  | تاریخ تنظیم لایحه تاخیرات: | 1401/03/23
نام مشاور : | -
نام پیمانکار : | مشارکت "هیرگان انرژی- طرح و بازرسی"
مبلغ پیمان : | - |  | ميليون ريال |  | 35909880.0474 | يورو
مدت اولیه پیمان (ماه): | 24 | تاریخ شروع: 1400/04/02 |  |  | تاریخ پايان اسمي: | 1402/04/02
تاریخ تحویل زمین: |  | مدت تمدیدهاي پیشین (ماه) : | - |  | تاریخ پایان برنامه ریزي شده: | -
تاریخ تحویل موقت: (بخشي و كلي) |  | مدت دوره تضمین (ماه): | 18 ماه |  | تاریخ تحویل قطعی: | -
تاخیرات (روز) | نوع |  | مجاز
| فني قراردادي |  | 183
| مالي |  | 75
| غير مترقبه |  | 0
| جمع كل* |  | 183
*جمع کل حاصل از همپوشانی است و حاصل از جمع جبري سه ردیف تأخیرات فنی-قراردادي، مالی و غيرمترقبه (ساير) نمی باشد.
مهر و امضاء پیمانکار |  |  |  | مهر و امضاء كارفرما

## 3
جدول شماره 3 : مستندات آيتم هاي تاخير
كد آيتم تاخير |  | عنوان علل تاخير | [8 empty] | نتيجه
رديف | مستندات |  |  | NISOC Date |  | PEDCO Date |  | Hirgan Date |  | شرح درخواست
| نوع | موضوع |  | تاريخ | شماره | تاريخ | شماره | تاريخ | شماره
1 | مالي | تاخير در پرداخت قسط اول پيش پرداخت 2% | [5 empty] | 2021-06-28 | 2 | قسط اول پيش پرداخت در تاريخ 00/06/20 واريز گرديد
2 | فني | تاخير در آغاز عمليات حفاري چاه ها و بالتبع عدم امكان عملياتي شدن خريد كالاهاي پروژه به دليل گارانتي محدود كالاها و همين طور عدم امكان فعاليت هايي اجرايي سطح الارضي
3 | فني | درخواست رفع ابهامات طراحی سیستم های ایمنی و اتصال خط مایعت گازی به کلاستر بینک ایستگاه گاز | [5 empty] | 2021-09-07 | 76 75و | همچنین طی نامه 80 مورخ 00/06/17 نیز درخواست جلسه با کارفرما در تاریخ 00/06/20 به عمل می اید
4 | فني | درخواست رفع ابهامات اطلاعات فرآیندی ایستگاه گاز | [5 empty] | 2021-09-19 | 99
5 | فني | دریافت پاسخ کارفرما بر روی ابهامات طراحی سیستم های ایمنی و اتصال خط مایعت گازی به کلاستر بینک ایستگاه گاز (پاسخ 75) |  | 2021-09-20 | 206337 | 2021-09-26 | 13340
6 | فني | دریافت پاسخ کارفرما بر روی ابهامات طراحی سیستم های ایمنی و اتصال خط مایعت گازی به کلاستر بینک ایستگاه گاز (پاسخ 76) |  | 2021-09-15 | 200607 | 2021-09-28 | 13423 |  |  | به دلیل عدم حل موضوع، در تاریخ 00/07/06 از سایت بازدید به عمل امد
7 | فني | دریافت پاسخ کارفرما بر روی ابهامات اطلاعات فرآیندی ایستگاه گاز (پاسخ 99) |  |  |  | 2021-10-04 | 13901
8 | فني | درخواست رفع ابهامات اطلاعات فرآیندی ایستگاه گاز | [5 empty] | 2021-10-10 | 133
9 | فني | عدم نهایی سازي اطلاعات فرآیندی ایستگاه گاز از سوي كارفرما-تغییر دبی ورود به ایستگاه گاز |  | 2021-10-25 | 247891 |  |  |  |  | مدارک مهم فرآیندی، مکانیک، پایپینگ از ابتدا می بایست تهیه شوند.
10 | فني | پیگیری درخواست جلسه پیرو موارد فرایندی و ابزار دقیقی ایستگاه گاز | [5 empty] | 2021-11-07 | 170
11 | فني | دریافت پاسخ کارفرما پیرو ابهامات و موارد فرایندی و ابزار دقیقی ایستگاه گاز (پاسخ 170) |  | 2021-11-14 | 275271 | 2021-11-20 | 17661
12 | فني | دریافت نحوه اختصاص و میزان دبی جریان از واحدهای کلاستر گلخاری و بینک |  | 2021-11-10 | 270410 | 2021-11-15 | 17218
13 | فني | درخواست اطلاعات مورد نیاز خط لوله گاز ورودی از کلاستر گلخاری 3 | [5 empty] | 2021-12-01 | 197 | درخواست بازید از سایت 00/09/23 و 00/09/22
14 | فني | عدم نهایی سازي اطلاعات فرآیندی ایستگاه گاز از سوي كارفرما-تغییر دمای خط ورودی به ایستگاه گاز از سمت تفکیک گر گلخاری |  | 2021-11-28 | 294976 | 2021-12-06 | 1920 |  |  | مدارک مهم فرآیندی، مکانیک، پایپینگ از ابتدا می بایست تهیه شوند.
15 | فني | اعلام تبعات مترتب از تغییر مشخصات فرآیندی ایستگاه گاز | [5 empty] | 2021-12-11 | 213
16 | فني | عدم وجود اطلاعات فرايندي در چاه ها در اسناد مناقصه-دريافت فشار، دما، دبي چاه ها در حالت عملياتي |  |  |  | 2021-09-13 | 12194 | 2021-08-09 | 44 | مدارک مهم فرآیندی، مکانیک، پایپینگ از ابتدا می بایست تهیه شوند.
17 | فني | عدم وجود اطلاعات فرايندي در چاه ها در اسناد مناقصه- دريافت اطلاعات فرآيندي فشار جرياني چاه ها قبل كاهنده |  | 2021-10-06 | 223853 | 2021-10-13 | 14622 |  |  | مدارک مهم فرآیندی، مکانیک، پایپینگ از ابتدا می بایست تهیه شوند.
18 | فني | عدم وجود اطلاعات فرايندي در چاه ها در اسناد مناقصه-دريافت اطلاعات جریانی خروجی از چاه ها |  |  |  | 2021-11-15 | 17216 |  |  | * در پاسخ به نامه شماره 44 * مدارک مهم فرآیندی، مکانیک، پایپینگ از ابتدا می بایست تهیه شوند.
19 | فني | تناقض اطلاعات دریافتی با مدارک پایه |  |  |  | 2021-12-26 | 21018 | 2021-11-23 | 192 | * در پاسخ به نامه شماره 44 * مدارک مهم فرآیندی، مکانیک، پایپینگ از ابتدا می بایست تهیه شوند.
20 | فني | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه- دريافت اطلاعات مديريت پسماند چاه 18 كه با توجه به نيمه ساخته بودن لوكيشن در قالب نقشه هاي سيويل مكاتبه و نهايي شد. |  | 2021-09-15 | 200540 |  |  | 2021-10-04 | 125 | عدم امكان نهايي سازي مدارك سيويل سرچاهي و تعيين تكليف فعاليت هاي اجرايي و برگزاری جلسه مشترک در تاریخ 00/07/19 به منظور رفع ابهامات
21 | فني | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه- دريافت اطلاعات مديريت پسماند چاه 18 كه با توجه به نيمه ساخته بودن لوكيشن در قالب نقشه هاي سيويل مكاتبه و نهايي شد. |  |  |  | 2021-12-01 | س ط ب / 18835 |  |  | تعیین تکلیف نهایی موضوع
22 | فني | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه- دريافت اطلاعات تغيير يافته مديريت پسماند چاه 18 كه بعد از تاييد نقشه سيويل چاه 18 (شامل طرح پسماند) در اين جلسه مجددا اصلاحاتي از سمت كارفرما جهت اعمال مطرح شد |  | 2022-01-25 | صورتجلسه | 2022-01-25 |  |  |  | عدم امكان نهايي سازي مدارك سيويل سرچاهي و تعيين تكليف فعاليت هاي اجرايي
23 | فني | عدم وجود اطلاعات طرح مديريت پسماند در اسناد مناقصه- دريافت اطلاعات مديريت پسماند ساير چاه ها |  | 2022-01-30 | 387966 | 2022-01-30 |  |  |  | عدم امكان نهايي سازي مدارك سيويل سرچاهي و تعيين تكليف فعاليت هاي اجرايي
24 | فني | انجام مطالعات پایه در فاز مطالعات Detail به دلیل اصرار کارفرما به انجام مطالعات خوردگي - عدم وجود مدرك Corrossion Study در اسناد مناقصه و اضافه شدن مدرك به MDL |  | 2021-09-13 | MDL | 2021-09-13 |  |  |  | منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي كه نهايتا در MDL ويرايش G02 اضافه می گردد
25 | فني | انجام مطالعات پایه در فاز مطالعات Detail به دلیل اصرار کارفرما به انجام مطالعات خوردگي -برگزاري جلسه در 00/10/19 و منوط شدن نهايي شدن موضوع به دريافت اطلاعات توليد آب از چاه ها |  | 2022-01-26 | 382258 | 2022-01-30 | 24325 |  |  | منوط شدن نهايي شدن مدارک مهم فرآیندی، مکانیک، پایپینگ به نهايي سازي مطالعات خوردگي
26 | مديريتي | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي |  | 2021-09-03 | 182921 | 2021-09-05 | 11561 | 2021-08-15 | 53 | *اعلام گزارش به کارفرما از یک سازنده داخلی توانمند جهت ساخت لوله ها و درخواست خرید از خارج در تاریخ 00/05/24 *برگزاری جلسه مشترک در تاریخ 00/06/02 *دریافت پاسخ کارفرما مبنی بر استعلام از سایر سازندگان و همچنین ثبت در سامانه توان ایران
27 | مديريتي | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي | [5 empty] | 2021-09-26 | 112 | ارسال گزارش جامع اول: -اعلام انصراف شرکت اسفراین در تاریخ 00/05/12 ، -گروه صنعتی فولاد در 00/06/22 - همچنین ثبت در سامانه توان ایران در تاریخ 00/06/17 و 00/06/22
28 | مديريتي | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي |  |  |  | 2021-10-03 | 13825 | 2021-10-27 | 145 | ارسال گزارش جامع دوم و اعلام انصراف شرکت ها: - ضرورت انجام تغییرات در ثبت سامانه توان ایران پیرو نامه 13825 شرکت پترو ایران -انچام تغییرات در سایت توان ایران در تاریخ 00/07/18 -اعلام انصراف شرکت کوثر در تاریخ 00/06/22 ، -اعلام انصراف شرکت خدمات فنی آسماری 00/06/27 -اعلام انصراف شرکت سپنتا اهواز 00/07/26 - دریافت انصراف غیررسمی فولادنور، کالوپ لوله و سازه های فلزی نوین پارسیان جنوب
29 | مديريتي | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي |  |  |  | 2021-10-03 | 13825 | 2021-12-08 | 206 | ارسال گزارش جامع سوم، بازدید از لوله سازی ها و نتیجه گیری در خصوص ناگزیر بودن پیمانکار به تامین لوله ها از خارج از کشور: - بازدید از لوله سازی اهواز در تاریخ 00/08/24 -بازدید از گروه صنعتی فولاد در تاریخ 00/08/25 -بازدید از لوله و نورد ساوه در تاریخ 00/09/09 -دریافت پیشنهاد از اسفراین در تاریخ 00/09/16 --دریافت توضیحات تکمیلی فولاد مبارکه در خصوص انحرافات از IPS-M-PI-190 ویرایش 4 --بازدید از فولاد مبارکه در تاریخ 00/09/23
30 | مديريتي | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي |  | 2021-12-20 | 327355 | 2021-12-22 | 20803 |  |  | تاکید کارفرما بر ادامه فرایند مذاکره با سازندگان داخلی و عدم نتیجه گیری به منظور سفارش گذاری (توضیح آنکه سازندگان داخلي توانمندي ساخت داخل لوله ها طبق مشخصات فني پروژه (مطابق با استاندارد IPS-M-PI-190-4) نداشتند و جلسات و مذاكرات متعددي جهت ايجاد انعطاف در معيارهاي سخت گيرانه در اين IPS با سازندگان، سازندگان متريال خام اوليه (فولاد مباركه اصفهان) و كارفرمايان برگزار گرديد و در نهايت از منظر ارزياب هاي اقتصادي و زمان تحويل سازندگان داخلي قادر به رقابت با سازندگان خارجي نشدند)
31 | اجرايي | تاخير در دريافت مجوز نقشه برداري هوايي |  | 2021-09-21 | 208118 | 2021-09-20 | 19846 | 2021-09-11 | 85 | معرفی گروه از طرف پیمانکار و درخواست کارفرما درخصوص اطلاعات تکمیلی
32 | اجرايي | تاخير در دريافت مجوز نقشه برداري هوايي |  |  |  | 2021-11-15 | 17208 | 2021-09-25 | 108 | ارسال اطلاعات تکمیلی
33 | اجرايي | تاخير در دريافت مجوز نقشه برداري هوايي |  |  |  | 2021-12-01 | 18860 | 2021-11-20 | 187 | دریافت مجوز نهایی
* كليه مستندات هر كدام از آيتم هاي تاخير مندرج در جدول شماره 3 در اين جدول مرتب و ارائه مي گردد.
مهر و امضاء پیمانکار | [5 empty] | مهر و امضاء كارفرما
Formulas:
PEDCO Date = [NISOC Date]

## 4
2021-06-23 | 2022-05-25 |  |  |  | جدول شماره 4 : ليست علل تأخير پروژه |  |  |  |  | 2021-06-23 |  |  | 3 |  | 5 | 11 |  | 13 | 19 |  | 21 | 27 |  | 29 | 35 |  | 37 | 43 |  | 45 | 2021-12-23 | 183
| Code | كد | پایان | عنوان علل تاخيرات | شرح | دوره طبق واقعيت |  |  | نوع علل |  |  |  | 0 |  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5
| Code |  |  | عنوان علل تاخيرات |  | مدت (روز) | شروع | پايان |  | plan-Start |  | plan-Finish | Actual-Start |  | Actual-Finish | Actual-Start |  | Actual-Finish | Actual-Start |  | Actual-Finish | Actual-Start |  | Actual-Finish | Actual-Start |  | Actual-Finish | Actual-Start |  | Actual-Finish
| F | F01 |  | تاخير در دريافت پيش پرداخت | تاخير در دريافت 2% پيش پرداخت با ضريب تاثير 0.9 | 75 | 2021-06-28 | 2021-09-03 12:00 | مالي | 2021-06-28 | 75 | 2021-09-11
| I | I01 |  | تاخير در آغاز عمليات حفاري چاه ها | تاخير در آغاز عمليات حفاري چاه ها و بالتبع عدم امكان عملياتي شدن خريد كالاهاي پروژه به دليل گارانتي محدود كالاها و همين طور عدم امكان فعاليت هايي اجرايي سطح الارضي | - | 2021-10-23 | - | فصول مشترک | 2021-10-23 | 120 | 2022-02-20
BK-GCS-PEDCO-120-PR-PF-0001 | E | E01 | Process Flow Diagram (PFD) | عدم نهایی سازي اطلاعات فرآیندی ایستگاه گاز | عدم نهایی سازي اطلاعات فرآیندی ایستگاه گاز از سوي كارفرما و بالتبع اثرات آن بر روی نهایی نشدن PFD ایستگاه گاز | 166 | 2021-06-23 | 2021-12-06 | فنی
BK-GCS-PEDCO-120-PR-DT-0030 | E | E02 | Process Data Sheets For Gas Compressors Packages | عدم نهایی سازي ديتاشيت فرآيندي پكيج هاي كمپرسور |  | 199 | 2021-11-07 | 2022-05-25 | فنی | 2021-07-31 | 43 | 2021-09-12 | 2021-11-07 | 199 | 2022-05-25
BK-GCS-PEDCO-120-ME-DT-0031 | E | E03 | Mechanical Data Sheets For Gas Compressors Packages | عدم نهایی سازي ديتاشيت مكانيك پكيج هاي كمپرسور |  | 238 | 2021-09-12 | 2022-05-08 | فنی | 2021-08-12 | 48 | 2021-09-29 | 2021-09-12 | 238 | 2022-05-08
BK-GCS-PEDCO-120-ME-TB-0001 | E | E04 | TBE For Gas Compressors | عدم نهايي سازي TBE كمپرسورها |  | 31 | 2022-02-02 | 2022-03-05 | فنی | 2021-08-16 | 44 | 2021-09-29 | 2022-02-02 | 31 | 2022-03-05
BK-GCS-PEDCO-120-ME-MR-0001 | E | E05 | PMR For Gas Compressors | عدم نهايي سازي MR كمپرسورها |  | 77 | 2021-11-28 | 2022-02-13 | فنی | 2021-09-03 | 10 | 2021-09-13 | 2021-11-28 | 77 | 2022-02-13
| P | P01 | Tendering & Selection For Gas Compressors | عدم انتخاب سازنده كمپرسورها |  | 18 | 2022-02-26 | 2022-03-16 | کالا | 2021-08-11 | 59 | 2021-10-09 | 2022-02-26 | 18 | 2022-03-16
| P | P02 | Contract Effectiveness / PO For Gas Compressors | عدم عقد قرارداد براي تامين كمپرسورها |  | 70 | 2022-03-16 | 2022-05-25 | کالا | 2021-10-10 | 29 | 2021-11-08 | 0 |  | 0
BK-W018S-PEDCO-110-PR-PF-0001 | E | E06 | Process Flow Diagram - W018S | عدم نهایی سازي اطلاعات فرآیندی چاه ها -چاه 18 | عدم نهایی سازي اطلاعات فرآیندی چاه ها از سوي كارفرما و مطالعات خوردگي و بالتبع اثرات آن بر روی نهایی نشدن PFD و P&ID چاه ها- چاه 18 به عنوان نماينده چاه هاي دكل A اورده شده است | 112 | 2021-06-23 | 2021-10-13 | فنی | 2021-07-23 | 44 | 2021-09-05 | 2021-08-04 | 294 | 2022-05-25
BK-W028-PEDCO-110-PR-PF-0001 | E | E07 | Process Flow Diagram - W028 | عدم نهایی سازي اطلاعات فرآیندی چاه ها -چاه 28 | عدم نهایی سازي اطلاعات فرآیندی چاه ها از سوي كارفرما و مطالعات خوردگي و بالتبع اثرات آن بر روی نهایی نشدن PFD و P&ID چاه ها- چاه 28 به عنوان نماينده چاه هاي دكل B اورده شده است | 284 | 2021-08-14 | 2022-05-25 | فنی | 2021-07-23 | 39 | 2021-08-31 | 2021-08-14 | 284 | 2022-05-25
BK-SSGRL-PEDCO-110-PL-RT-0001 | E | E08 | Pipeline Corrosion Study & Material Selection Report-W018S | انجام مطالعات پایه در فاز مطالعات Detail به دلیل اصرار کارفرما به انجام مطالعات خوردگي و تطويل آن به دليل نبود اطلاعات آب چاه 18 | اضافه شدن دير هنگام مدرك مطالعات خوردگي به MDL و تطويل در نهايي شدن آن به دليل عدم دريافت اطلاعات مربوط به چاه ها و منوط شدن نهايي شدن مدارك كليدي بخش فرايند ، مكانيك، ابزار دقيق و پايپينگ به مدرك مذكور-چاه 18 به عنوان نماينده كليه چاه هاي مربوط به دكل A اورده شده است | 135 | 2021-09-13 | 2022-01-26 | فنی
BK-SSGRL-PEDCO-110-PL-RT-0001 | E | E09 | Pipeline Corrosion Study & Material Selection Report - W028 | انجام مطالعات پایه در فاز مطالعات Detail به دلیل اصرار کارفرما به انجام مطالعات خوردگي و تطويل آن به دليل نبود اطلاعات آب چاه 28 | اضافه شدن دير هنگام مدرك مطالعات خوردگي به MDL و تطويل در نهايي شدن آن به دليل عدم دريافت اطلاعات مربوط به چاه ها و منوط شدن نهايي شدن مدارك كليدي بخش فرايند ، مكانيك، ابزار دقيق و پايپينگ به مدرك مذكور-چاه 28 به عنوان نماينده كليه چاه هاي مربوط به دكل B اورده شده است | 135 | 2021-09-13 | 2022-01-26 | فنی
BK-GNRAL-PEDCO-000-PI-SP-0017 | E | E10 | Piping Material Specification-W018S | عدم نهايي سازي PMS-چاه 18 | چاه 28 به عنوان نماينده كليه چاه هاي مربوط به دكل B اورده شده است | 113 | 2021-08-24 | 2021-12-15 | فنی | 2021-08-02 | 29 | 2021-08-31 | 2021-08-24 | 113 | 2021-12-15
BK-SSGRL-PEDCO-110-PI-SP-0001 | E | E11 | Piping Material Specification - W028 | عدم نهايي سازي PMS چاه 28 | چاه 28 به عنوان نماينده كليه چاه هاي مربوط به دكل B اورده شده است | 178 | 2021-11-28 | 2022-05-25 | فنی | 2021-10-22 | 63 | 2021-12-24 | 2021-11-28 | 178 | 2022-05-25
BK-W018S-PEDCO-110-PL-MR-0001 | E | E12 | PMR For Line Pipes - W018S | عدم نهايي سازي مدارك خريد براي لوله هاي جرياني- چاه 18 | چاه 18 به عنوان نماينده كليه چاه هاي مربوط به دكل A اورده شده است | 9 | 2021-12-06 | 2021-12-15 | فنی | 2021-10-06 | 4 | 2021-10-10 | 2021-12-06 | 9 | 2021-12-15
BK-W028-PEDCO-110-PL-MR-0001 | E | E13 | PMR For Line Pipes - W028 | عدم نهايي سازي مدارك خريد براي لوله هاي جرياني- چاه 28 | چاه 28 به عنوان نماينده كليه چاه هاي مربوط به دكل B اورده شده است | 9 | 2021-12-06 | 2021-12-15 | فنی | 2021-07-30 | 9 | 2021-08-08 | 2021-12-06 | 9 | 2021-12-15
| P | P03 | Tendering & Selection- W018S- Line pipe | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي-چاه 18 | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي | 336 | 2021-06-23 | 2022-05-25 | کالا | 2021-10-01 | 6 | 2021-10-07 | 0 | 0 | 0
| P | P04 | Tendering & Selection- W028 - Line pipe | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي-چاه 28 | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي | 336 | 2021-06-23 | 2022-05-25 | کالا | 2021-08-19 | 6 | 2021-08-25
| P | P05 | Contract Effectiveness / PO- W018S-Line pipe | عدم امکان عقد قرارداد با سازنده لوله های جریانی-چاه 18 |  | 336 | 2021-06-23 | 2022-05-25 | کالا | 2021-10-08 | 4 | 2021-10-12 | 0 | 0 | 0
| P | P06 | Contract Effectiveness / PO- W028 - Line pipe | عدم امکان عقد قرارداد با سازنده لوله های جریانی-چاه 28 |  | 336 | 2021-06-23 | 2022-05-25 | کالا | 2021-08-26 | 4 | 2021-08-30 | 0 | 0 | 0
| P | P07 | Manufacturing / Fabrication / Supply- W018S-Line pipe | عدم امکان آغاز ساخت لوله های جریانی-چاه 18 |  | 336 | 2021-06-23 | 2022-05-25 | کالا | 2021-10-13 | 69 | 2021-12-21 | 0 | 0 | 0
| P | P08 | Manufacturing / Fabrication / Supply- W028 - Line pipe | عدم امکان آغاز ساخت لوله های جریانی-چاه 28 |  | 336 | 2021-06-23 | 2022-05-25 | کالا | 2021-08-31 | 109 | 2021-12-18 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-IN-SP-0001 | E | E14 | Specification For WHCP/HPU-W018S | نهايي نشدن Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | نهايي نشدن Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي از بخش حفاري كارفرما-چاه 18 به عنوان نماينده چاه هاي دكل A اورده شده است | 231 | 2021-08-08 | 2022-03-27 | فنی | 2021-07-23 | 37 | 2021-08-29 | 2021-08-08 | 231 | 2022-03-27
BK-SSGRL-PEDCO-110-IN-SP-0001 | E | E15 | Specification For WHCP/HPU - W028 | نهايي نشدن Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | نهايي نشدن Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي از بخش حفاري كارفرما-چاه 28 به عنوان نماينده چاه هاي دكل B اورده شده است | 231 | 2021-08-08 | 2022-03-27 | فنی | 2021-07-23 | 37 | 2021-08-29 | 2021-08-08 | 231 | 2022-03-27
BK-SSGRL-PEDCO-110-IN-DT-0001 | E | E16 | Data Sheets For WHCP/HPU - Wellheads-W018S | نهايي نشدن ديتاشيت WHCP | نهايي نشدن ديتاشيت WHCP به دليل نهايي نشدن Spec ، نهايي نشدن اطلاعات فرآيندي چاه ها و عدم دريافت داده برگ SSV و SSSV شيرهاي سرچاهي از بخش حفاري كارفرما-چاه 18 به عنوان نماينده چاه هاي دكل A اورده شده است | 276 | 2021-08-22 | 2022-05-25 | فنی | 2021-08-02 | 29 | 2021-08-31 | 2021-08-22 | 276 | 2022-05-25
BK-SSGRL-PEDCO-110-IN-DT-0001 | E | E17 | Data Sheets For WHCP/HPU - Wellheads - W028 | نهايي نشدن ديتاشيت WHCP | نهايي نشدن ديتاشيت WHCP به دليل نهايي نشدن Spec ، نهايي نشدن اطلاعات فرآيندي چاه ها و عدم دريافت داده برگ SSV و SSSV شيرهاي سرچاهي از بخش حفاري كارفرما-چاه 28 به عنوان نماينده چاه هاي دكل B اورده شده است | 276 | 2021-08-22 | 2022-05-25 | فنی | 2021-08-12 | 48 | 2021-09-29 | 2021-08-22 | 276 | 2022-05-25
BK-W018S-PEDCO-110-IN-MR-0001 | E | E18 | PMR For WHCP/HPU - W018S | عدم نهايي سازي MR برای WHCP-چاه 18 |  | 62 | 2021-11-15 | 2022-01-16 | فنی | 2021-08-30 | 6 | 2021-09-05 | 2021-11-15 | 62 | 2022-01-16
BK-W028-PEDCO-110-IN-MR-0001 | E | E19 | PMR For WHCP/HPU - W028 | عدم نهايي سازي MR برای WHCP-چاه 28 |  | 62 | 2021-11-15 | 2022-01-16 | فنی | 2021-09-01 | 9 | 2021-09-10 | 2021-11-15 | 62 | 2022-01-16
| P | P09 | Tendering & Selection- W018S-WHCP | عدم امکان انتخاب سازنده برای WHCP-چاه 18 |  | 71 | 2022-03-15 | 2022-05-25 | کالا | 2021-09-23 | 9 | 2021-10-02 | 2022-03-15 | 71 | 2022-05-25
| P | P10 | Tendering & Selection- W028 - WHCP | عدم امکان انتخاب سازنده برای WHCP-چاه 28 |  | 71 | 2022-03-15 | 2022-05-25 | کالا | 2021-09-23 | 9 | 2021-10-02 | 2022-03-15 | 71 | 2022-05-25
| P | P11 | Contract Effectiveness / PO- W018S- WHCP | عدم امکان عقد قرارداد با سازنده برای WHCP-چاه 18 |  | 71 | 2022-03-15 | 2022-05-25 | کالا | 2021-10-03 | 4 | 2021-10-07 | 0 | 0 | 0
| P | P12 | Contract Effectiveness / PO- W028 - WHCP | عدم امکان عقد قرارداد با سازنده برای WHCP-چاه 28 |  | 71 | 2022-03-15 | 2022-05-25 | کالا | 2021-10-03 | 4 | 2021-10-07 | 0 | 0 | 0
| P | P13 | Manufacturing / Fabrication / Supply- W018S-WHCP | عدم امکان ساخت WHCP-چاه 18 |  | 71 | 2022-03-15 | 2022-05-25 | کالا | 2021-10-08 | 89 | 2022-01-05 | 0 | 0 | 0
| P | P14 | Manufacturing / Fabrication / Supply- W028 - WHCP | عدم امکان ساخت WHCP-چاه 18 |  | 71 | 2022-03-15 | 2022-05-25 | کالا | 2021-10-08 | 89 | 2022-01-05 | 0 | 0 | 0
BK-W018S-PEDCO-110-CV-PY-0001 | E | E20 | General Civil Layout - W018S | عدم نهايي سازي طرح مديريت پسماند چاه 18 | عدم نهايي سازي طرح مديريت پسماند چاه 18 و بالتبع عدم نهايي سازي مدارك Civil سرچاهي-چاه 18 به عنوان نماينده چاه هاي دكل A اورده شده است | 152 | 2021-07-28 | 2021-12-27 | فنی | 2021-08-12 | 19 | 2021-08-31 | 2021-07-28 | 152 | 2021-12-27
BK-W018S-PEDCO-110-CV-DW-0001 | E | E21 | Rough Grading Plans -W018S | عدم نهايي سازي مدرک RG- چاه 18 |  | 220 | 2021-07-28 | 2022-03-05 | فنی | 2021-08-07 | 39 | 2021-09-15 | 2021-07-28 | 220 | 2022-03-05
BK-W018S-PEDCO-110-CV-PY-0002 | E | E22 | Civil and Structural drawings - W018S | عدم نهايي سازي نقشه های سیویل و سازه ای چاه- چاه 18 |  | 228 | 2021-07-28 | 2022-03-13 | فنی | 2021-07-28 | 39 | 2021-09-05 | 2021-07-28 | 228 | 2022-03-13
BK-W028-PEDCO-110-CV-PY-0001 | E | E23 | General Civil Layout -W028 | عدم نهايي سازي طرح مديريت پسماند ساير چاه ها | عدم نهايي سازي طرح مديريت پسماند ساير چاه ها و بالتبع عدم نهايي سازي مدارك Civil سرچاهي (در تاريخ 00/12/01 نهايي گرديد) | 218 | 2021-10-19 | 2022-05-25 | فنی | 2021-07-23 | 24 | 2021-08-16 | 2021-10-19 | 218 | 2022-05-25
BK-W028-PEDCO-110-CV-DW-0001 | E | E24 | Rough Grading Plans -W028 | عدم نهايي سازي مدرک RG- چاه 28 |  | 181 | 2021-10-11 | 2022-04-10 | فنی | 2021-07-23 | 24 | 2021-08-16 | 2021-10-11 | 181 | 2022-04-10
BK-W028-PEDCO-110-CV-PY-0002 | E | E25 | Civil and Structural drawings -W028 | عدم نهايي سازي نقشه های سیویل و سازه ای چاه- چاه 28 |  | 218 | 2021-10-19 | 2022-05-25 | فنی | 2021-07-23 | 44 | 2021-09-05 | 2021-10-19 | 218 | 2022-05-25
| C | C03 |  | تاخير در دريافت مجوزها | تاخير در دريافت مجوز نقشه برداري هوايي | 70 | 2021-09-11 | 2021-11-20 | اجرايي | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
BK-GNRAL-PEDCO-000-PM-RT-0001 | M | M01 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Endorsement Report For Basic Design & Scope of Work | 47 |  |  | مديريتي |  |  |  | 2021-08-14 | 24 | 2021-09-07 | 2021-10-03 | 23 | 2021-10-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-GCS-PEDCO-120-PR-PF-0001 |  | M02 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Process Flow Diagram (PFD) | 108 |  |  | مديريتي |  |  |  | 2021-08-28 | 9 | 2021-09-06 | 2021-10-31 | 14 | 2021-11-14 | 2021-12-14 | 19 | 2022-01-02 | 2022-01-22 | 31 | 2022-02-22 | 2022-03-26 | 35 | 2022-04-30 | 0 | 0 | 0
BK-GCS-PEDCO-120-PR-DT-0030 |  | M03 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Process Data Sheets For Gas Compressors Packages | 49 |  |  | مديريتي |  |  |  | 2021-11-21 | 6 | 2021-11-27 | 2022-01-15 | 14 | 2022-01-29 | 2022-04-09 | 29 | 2022-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-GCS-PEDCO-120-ME-DT-0031 |  | M04 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Mechanical Data Sheets For Gas Compressors Packages | 76 |  |  | مديريتي |  |  |  | 2021-09-26 | 15 | 2021-10-11 | 2021-10-31 | 8 | 2021-11-08 | 2021-11-28 | 22 | 2021-12-20 | 2022-01-26 | 27 | 2022-02-22 | 2022-03-19 | 7 | 2022-03-26 | 2022-05-04 | -3 | 2022-05-01
BK-GCS-PEDCO-120-ME-TB-0001 |  | M05 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | TBE For Gas Compressors | 60 |  |  | مديريتي |  |  |  | 2022-02-16 | 11 | 2022-02-27 | 2022-03-19 | 49 | 2022-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-GCS-PEDCO-120-ME-MR-0001 |  | M06 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | PMR For Gas Compressors | 21 |  |  | مديريتي |  |  |  | 2021-12-12 | 3 | 2021-12-15 | 2022-01-18 | 12 | 2022-01-30 | 2022-02-27 | 6 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W018S-PEDCO-110-PR-PF-0001 |  | M07 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Process Flow Diagram - W018S | -44496 |  |  | مديريتي |  |  |  | 2021-08-18 | 20 | 2021-09-07 | 2021-11-16 | -44516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W018S-PEDCO-110-PI-PY-0001 |  | M08 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Plot Plan Drawing - W018S | 56 |  |  | مديريتي |  |  |  | 2021-09-05 | 24 | 2021-09-29 | 2021-11-29 | 13 | 2021-12-12 | 2022-02-14 | 19 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-IN-SP-0001 |  | M09 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Specification For WHCP/HPU-W018S | 114 |  |  | مديريتي |  |  |  | 2021-08-22 | 23 | 2021-09-14 | 2021-10-24 | 70 | 2022-01-02 | 2022-01-24 | 6 | 2022-01-30 | 2022-04-10 | 15 | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0
BK-W018S-PEDCO-110-CV-DW-0001 |  | M10 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Rough Grading Plans -W018S | -25 |  |  | مديريتي |  |  |  | 2021-08-11 | -4 | 2021-08-07 | 2021-11-13 | -7 | 2021-11-06 | 2022-01-29 | -7 | 2022-01-22 | 2022-03-12 | -7 | 2022-03-05 | 2022-03-27 | 0 | 2022-03-27 | 0 | 0 | 0
BK-W018S-PEDCO-110-PR-PI-0001 |  | M11 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | P&ID - W018S | 79 |  |  | مديريتي |  |  |  | 2021-08-23 | 14 | 2021-09-06 | 2021-11-15 | 12 | 2021-11-27 | 2021-12-29 | 5 | 2022-01-03 | 2022-03-14 | 48 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0
BK-GNRAL-PEDCO-000-PI-SP-0017 |  | M12 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Piping Material Specification-W018S | -44531 |  |  | مديريتي |  |  |  | 2021-09-07 | 7 | 2021-09-14 | 2021-10-18 | 21 | 2021-11-08 | 2021-12-29 | -44559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-IN-DT-0001 |  | M13 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Data Sheets For WHCP/HPU - Wellheads-W018S | 23 |  |  | مديريتي |  |  |  | 2021-09-05 | 15 | 2021-09-20 | 2021-11-23 | 4 | 2021-11-27 | 2022-01-04 | 4 | 2022-01-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W018S-PEDCO-110-CV-PY-0002 |  | M14 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Civil and Structural drawings - W018S | -44650 |  |  | مديريتي |  |  |  | 2021-08-11 | -4 | 2021-08-07 | 2022-01-18 | -7 | 2022-01-11 | 2022-03-19 | -44639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W018S-PEDCO-110-CV-PY-0001 |  | M15 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | General Civil Layout - W018S | -39 |  |  | مديريتي |  |  |  | 2021-08-11 | -4 | 2021-08-07 | 2021-09-11 | -7 | 2021-09-04 | 2021-09-27 | -9 | 2021-09-18 | 2021-11-06 | -4 | 2021-11-02 | 2021-12-04 | -7 | 2021-11-27 | 2022-01-10 | -8 | 2022-01-02
BK-SSGRL-PEDCO-110-PL-RT-0001 |  | M16 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Pipeline Corrosion Study & Material Selection Report-W018S | -44519 |  |  | مديريتي |  |  |  | 2021-11-10 | 11 | 2021-11-21 | 2021-12-18 | -44548 | 0 | 2022-03-14 | 18 | 2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W018S-PEDCO-110-IN-MR-0001 |  | M17 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | PMR For WHCP/HPU - W018S | 10 |  |  | مديريتي |  |  |  | 2021-11-29 | 8 | 2021-12-07 | 2022-01-30 | 2 | 2022-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W018S-PEDCO-110-PL-MR-0001 |  | M18 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | PMR For Line pipes - W018S | -5 |  |  | مديريتي |  |  |  | 2021-12-20 | -5 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W028-PEDCO-110-PR-PF-0001 |  | M19 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Process Flow Diagram - W028 | -44507 |  |  | مديريتي |  |  |  | 2021-08-28 | 9 | 2021-09-06 | 2021-11-16 | -44516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W028-PEDCO-110-PI-DW-0001 |  | M20 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Plot Plan Drawing - W028 | 68 |  |  | مديريتي |  |  |  | 2022-02-16 | 68 | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-IN-SP-0001 |  | M21 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Specification For WHCP/HPU-W018S | 114 |  |  | مديريتي |  |  |  | 2021-08-22 | 23 | 2021-09-14 | 2021-10-24 | 70 | 2022-01-02 | 2022-01-24 | 6 | 2022-01-30 | 2022-04-10 | 15 | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0
BK-W028-PEDCO-110-CV-PY-0001 |  | M22 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | General Civil Layout -W028 | 19 |  |  | مديريتي |  |  |  | 2021-11-02 | 20 | 2021-11-22 | 2022-03-26 | -1 | 2022-03-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W028-PEDCO-110-CV-PY-0002 |  | M23 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Civil and Structural drawings -W028 | -44499 |  |  | مديريتي |  |  |  | 2021-11-02 | -44502 | 0 | 2021-12-04 | -3 | 2021-12-01 | 2022-03-28 | 6 | 2022-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W028-PEDCO-110-CV-DW-0001 |  | M24 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Rough Grading Plans -W028 | -44684 |  |  | مديريتي |  |  |  | 2021-10-25 | -7 | 2021-10-18 | 2022-02-20 | -8 | 2022-02-12 | 2022-03-28 | 6 | 2022-04-03 | 2022-04-24 | -44675 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W028-PEDCO-110-PL-MR-0001 |  | M25 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | PMR For Line Pipes - W028 | -5 |  |  | مديريتي |  |  |  | 2021-12-20 | -5 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W028-PEDCO-110-PR-PI-0001 |  | M26 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | P&ID - W028 | 68 |  |  | مديريتي |  |  |  | 2021-09-05 | 3 | 2021-09-08 | 2021-11-15 | 12 | 2021-11-27 | 2021-12-29 | 5 | 2022-01-03 | 2022-03-14 | 48 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-IN-DT-0001 |  | M27 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Data Sheets For WHCP/HPU - Wellheads-W018S | 23 |  |  | مديريتي |  |  |  | 2021-09-05 | 15 | 2021-09-20 | 2021-11-23 | 4 | 2021-11-27 | 2022-01-04 | 4 | 2022-01-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-PL-RT-0001 |  | M28 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Pipeline Corrosion Study & Material Selection Report-W018S | -44519 |  |  | مديريتي |  |  |  | 2021-11-10 | 11 | 2021-11-21 | 2021-12-18 | -44548 | 0 | 2022-03-14 | 18 | 2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-W028-PEDCO-110-IN-MR-0001 |  | M29 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | PMR For WHCP/HPU - W028 | 10 |  |  | مديريتي |  |  |  | 2021-11-29 | 8 | 2021-12-07 | 2022-01-30 | 2 | 2022-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BK-SSGRL-PEDCO-110-PI-SP-0001 |  | M30 |  | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | Piping Material Specification - W028 | -44650 |  |  | مديريتي |  |  |  | 2021-12-12 | 14 | 2021-12-26 | 2022-04-13 | -44664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | مهر و امضاء پیمانکار |  |  |  | مهر و امضاء كارفرما

## S&F (hidden)
Description | Doc. No. |  | Actual Start Date | Actual Finish Date
Procurement & Services Contracting Plan | BK-GNRAL-HD-000-PM-CG-0001 | BK-GNRAL-HD-000-PM-CG-0001Procurement & Services Contracting Plan |  | 2022-05-25
Master Document List (MDL) & Updating | BK-GNRAL-PEDCO-000-GE-DN-0001 | BK-GNRAL-PEDCO-000-GE-DN-0001Master Document List (MDL) & Updating | 2021-07-07 | 2021-12-28
EPC HSE Plan | BK-GNRAL-HD-000-PM-HP-0001 | BK-GNRAL-HD-000-PM-HP-0001EPC HSE Plan | 2021-07-28 | 2022-05-22
Project Emergency Response Plan (ERP) | BK-GNRAL-HD-000-PM-HP-0002 | BK-GNRAL-HD-000-PM-HP-0002Project Emergency Response Plan (ERP) | 2022-02-12 | 2022-05-25
Guideline on Permit To Work System(PTWS) | BK-GNRAL-HD-000-PM-HP-0003 | BK-GNRAL-HD-000-PM-HP-0003Guideline on Permit To Work System(PTWS) | 2021-12-01 | 2021-12-01
HSE Operation Control Procedure | BK-GNRAL-HD-000-PM-HP-0004 | BK-GNRAL-HD-000-PM-HP-0004HSE Operation Control Procedure |  | 2022-05-25
Environmental Management Plan (EMP) | BK-GNRAL-HD-000-PM-HP-0005 | BK-GNRAL-HD-000-PM-HP-0005Environmental Management Plan (EMP) | 2022-02-21 | 2022-05-10
Detailed Schedule & Updating | BK-GNRAL-HD-000-PM-SH-0001 | BK-GNRAL-HD-000-PM-SH-0001Detailed Schedule & Updating | 2021-12-08 | 2022-05-09
Work Breakdown Structure (WBS) | BK-GNRAL-HD-000-PM-WB-0001 | BK-GNRAL-HD-000-PM-WB-0001Work Breakdown Structure (WBS) | 2021-11-16 | 2022-02-02
Cost Breakdown Structure (CBS) | BK-GNRAL-HD-000-PM-WB-0002 | BK-GNRAL-HD-000-PM-WB-0002Cost Breakdown Structure (CBS) | 2021-11-16 | 2022-02-02
Material Equipment & Control Index (MCI) | BK-GNRAL-HD-000-PM-FO-0001 | BK-GNRAL-HD-000-PM-FO-0001Material Equipment & Control Index (MCI) |  | 2022-05-25
Progress S-curves & Updating | BK-GNRAL-HD-000-PM-PG-0001 | BK-GNRAL-HD-000-PM-PG-0001Progress S-curves & Updating | 2022-02-20 | 2022-05-25
Production Capacity Realization Plan | BK-GNRAL-PEDCO-000-PM-PS-0001 | BK-GNRAL-PEDCO-000-PM-PS-0001Production Capacity Realization Plan |  | 2022-05-25
Cash Flow Plan | BK-GNRAL-HD-000-PM-CP-0001 | BK-GNRAL-HD-000-PM-CP-0001Cash Flow Plan |  | 2022-05-25
Quality Plan | BK-GNRAL-PEDCO-000-PM-QP-0001 | BK-GNRAL-PEDCO-000-PM-QP-0001Quality Plan |  | 2022-05-25
Project Organization Charts | BK-GNRAL-HD-000-PM-CH-0001 | BK-GNRAL-HD-000-PM-CH-0001Project Organization Charts |  | 2022-05-25
Specification for Medical Services | BK-GNRAL-HD-000-PM-SP-0001 | BK-GNRAL-HD-000-PM-SP-0001Specification for Medical Services |  | 2022-05-25
Project Coordination Procedure | BK-GNRAL-HD-000-PM-PR-0001 | BK-GNRAL-HD-000-PM-PR-0001Project Coordination Procedure | 2021-07-11 | 2022-02-20
Project Control Procedure (WBS, PMS,Invoicing) | BK-GNRAL-HD-000-PM-PR-0002 | BK-GNRAL-HD-000-PM-PR-0002Project Control Procedure (WBS, PMS,Invoicing) | 2021-07-24 | 2022-05-25
Progress Measurement Procedure | BK-GNRAL-HD-000-PM-PR-0014 | BK-GNRAL-HD-000-PM-PR-0014Progress Measurement Procedure | 2021-11-20 | 2022-05-25
Document Numbering Procedure | BK-GNRAL-HD-000-PM-PR-0003 | BK-GNRAL-HD-000-PM-PR-0003Document Numbering Procedure |  | 2022-05-25
Change Control Procedure | BK-GNRAL-HD-000-PM-PR-0004 | BK-GNRAL-HD-000-PM-PR-0004Change Control Procedure | 2021-07-24 | 2022-05-25
Invoicing Procedure | BK-GNRAL-HD-000-PM-PR-0005 | BK-GNRAL-HD-000-PM-PR-0005Invoicing Procedure | 2021-12-07 | 2022-05-25
Correspondence Procedure | BK-GNRAL-HD-000-PM-PR-0006 | BK-GNRAL-HD-000-PM-PR-0006Correspondence Procedure |  | 2022-05-25
Meeting Procedure | BK-GNRAL-HD-000-PM-PR-0007 | BK-GNRAL-HD-000-PM-PR-0007Meeting Procedure |  | 2022-05-25
Reporting Procedure | BK-GNRAL-HD-000-PM-PR-0008 | BK-GNRAL-HD-000-PM-PR-0008Reporting Procedure |  | 2022-05-25
Procurement & Services Contracting Procedure | BK-GNRAL-HD-000-PM-PR-0009 | BK-GNRAL-HD-000-PM-PR-0009Procurement & Services Contracting Procedure | 2021-11-22 | 2021-12-29
Eng. Document Control Procedure | BK-GNRAL-HD-000-PM-PR-0010 | BK-GNRAL-HD-000-PM-PR-0010Eng. Document Control Procedure |  | 2022-05-25
Material Control Procedure | BK-GNRAL-HD-000-PM-PR-0011 | BK-GNRAL-HD-000-PM-PR-0011Material Control Procedure |  | 2022-05-25
Completion & Handover Procedure | BK-GNRAL-HD-000-PM-PR-0012 | BK-GNRAL-HD-000-PM-PR-0012Completion & Handover Procedure |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0001 | BK-GNRAL-HD-000-GE-RT-0001Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0002 | BK-GNRAL-HD-000-GE-RT-0002Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0003 | BK-GNRAL-HD-000-GE-RT-0003Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0004 | BK-GNRAL-HD-000-GE-RT-0004Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0005 | BK-GNRAL-HD-000-GE-RT-0005Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0006 | BK-GNRAL-HD-000-GE-RT-0006Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0007 | BK-GNRAL-HD-000-GE-RT-0007Monthly Progress Report | 2022-01-11 | 2022-01-11
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0008 | BK-GNRAL-HD-000-GE-RT-0008Monthly Progress Report | 2022-02-13 | 2022-02-13
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0009 | BK-GNRAL-HD-000-GE-RT-0009Monthly Progress Report | 2022-03-13 | 2022-03-13
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0010 | BK-GNRAL-HD-000-GE-RT-0010Monthly Progress Report | 2022-04-11 | 2022-04-11
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0011 | BK-GNRAL-HD-000-GE-RT-0011Monthly Progress Report | 2022-05-14 | 2022-05-14
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0012 | BK-GNRAL-HD-000-GE-RT-0012Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0013 | BK-GNRAL-HD-000-GE-RT-0013Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0014 | BK-GNRAL-HD-000-GE-RT-0014Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0015 | BK-GNRAL-HD-000-GE-RT-0015Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0016 | BK-GNRAL-HD-000-GE-RT-0016Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0017 | BK-GNRAL-HD-000-GE-RT-0017Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0018 | BK-GNRAL-HD-000-GE-RT-0018Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0019 | BK-GNRAL-HD-000-GE-RT-0019Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0020 | BK-GNRAL-HD-000-GE-RT-0020Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0021 | BK-GNRAL-HD-000-GE-RT-0021Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0022 | BK-GNRAL-HD-000-GE-RT-0022Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0023 | BK-GNRAL-HD-000-GE-RT-0023Monthly Progress Report |  | 2022-05-25
Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0024 | BK-GNRAL-HD-000-GE-RT-0024Monthly Progress Report |  | 2022-05-25
Delay Analysis Report | BK-GNRAL-HD-000-GE-RT-0050 | BK-GNRAL-HD-000-GE-RT-0050Delay Analysis Report |  | 2022-05-25
Delay Analysis Report | BK-GNRAL-HD-000-GE-RT-0051 | BK-GNRAL-HD-000-GE-RT-0051Delay Analysis Report |  | 2022-05-25
Delay Analysis Report | BK-GNRAL-HD-000-GE-RT-0052 | BK-GNRAL-HD-000-GE-RT-0052Delay Analysis Report |  | 2022-05-25
Delay Analysis Report | BK-GNRAL-HD-000-GE-RT-0053 | BK-GNRAL-HD-000-GE-RT-0053Delay Analysis Report |  | 2022-05-25
Plumbing & Sewage Piping Layout | BK-GNRAL-PEDCO-220-HV-PY-0001 | BK-GNRAL-PEDCO-220-HV-PY-0001Plumbing & Sewage Piping Layout | 2022-05-21 | 2022-05-25
HVAC System Layout | BK-GNRAL-PEDCO-220-HV-PY-0002 | BK-GNRAL-PEDCO-220-HV-PY-0002HVAC System Layout | 2022-05-14 | 2022-05-25
HVAC Equipment Schedule | BK-GNRAL-PEDCO-220-HV-LI-0001 | BK-GNRAL-PEDCO-220-HV-LI-0001 HVAC Equipment Schedule |  | 2022-05-25
Safety & Fire Fighting Equipment Location Layout | BK-GNRAL-PEDCO-220-SA-PY-0001 | BK-GNRAL-PEDCO-220-SA-PY-0001Safety & Fire Fighting Equipment Location Layout | 2022-02-02 | 2022-05-25
Lighting & Small Power Layout For Camp Area | BK-GNRAL-PEDCO-220-EL-PY-0001 | BK-GNRAL-PEDCO-220-EL-PY-0001Lighting & Small Power Layout For Camp Area | 2022-01-01 | 2022-05-25
Earthing & Lightning Layout For Camp Area | BK-GNRAL-PEDCO-220-EL-PY-0002 | BK-GNRAL-PEDCO-220-EL-PY-0002Earthing & Lightning Layout For Camp Area |  | 2022-05-25
Cable Route for For Camp Area | BK-GNRAL-PEDCO-220-EL-DW-0001 | BK-GNRAL-PEDCO-220-EL-DW-0001Cable Route for For Camp Area | 2022-01-04 | 2022-05-25
Electrical Load List | BK-GNRAL-PEDCO-220-EL-LI-0001 | BK-GNRAL-PEDCO-220-EL-LI-0001Electrical Load List | 2022-05-18 | 2022-05-25
Architectural Drawing For NISOC Office Building | BK-GNRAL-PEDCO-220-AR-DW-0001 | BK-GNRAL-PEDCO-220-AR-DW-0001Architectural Drawing For NISOC Office Building | 2021-07-24 | 2022-03-12
Architectural Drawing For NISOC Residental Building | BK-GNRAL-PEDCO-220-AR-DW-0002 | BK-GNRAL-PEDCO-220-AR-DW-0002Architectural Drawing For NISOC Residental Building | 2021-10-13 | T-0929
Architectural Drawing For Petro Iran Office Building | BK-GNRAL-PEDCO-220-AR-DW-0003 | BK-GNRAL-PEDCO-220-AR-DW-0003Architectural Drawing For Petro Iran Office Building | 2021-06-28 | 2022-02-20
Architectural Drawing For Petro Iran Residental Building | BK-GNRAL-PEDCO-220-AR-DW-0007 | BK-GNRAL-PEDCO-220-AR-DW-0007Architectural Drawing For Petro Iran Residental Building | 2021-06-28 | 2022-02-12
Architectural Drawing For Petro Iran/Contractor Restaurant | BK-GNRAL-PEDCO-220-AR-DW-0004 | BK-GNRAL-PEDCO-220-AR-DW-0004Architectural Drawing For Petro Iran/Contractor Restaurant | 2021-08-22 | 2022-02-26
Architectural Drawing For Warehouse of Site Mobilization | BK-GNRAL-PEDCO-220-AR-DW-0005 | BK-GNRAL-PEDCO-220-AR-DW-0005Architectural Drawing For Warehouse of Site Mobilization | 2021-08-22 | 2022-02-02
Architectural Drawing For Drivers Rest Room | BK-GNRAL-PEDCO-220-AR-DW-0006 | BK-GNRAL-PEDCO-220-AR-DW-0006Architectural Drawing For Drivers Rest Room | 2021-06-28 | 2022-03-02
Overall Layout for Camp Area | BK-GNRAL-PEDCO-220-CV-PY-0001 | BK-GNRAL-PEDCO-220-CV-PY-0001Overall Layout for Camp Area | 2021-07-24 | 2021-12-12
Rough Grading Plan For Camp Area | BK-GNRAL-PEDCO-220-CV-DW-0001 | BK-GNRAL-PEDCO-220-CV-DW-0001Rough Grading Plan For Camp Area | 2021-09-20 | 2021-12-12
Foundation Location Drawing For Camp Area | BK-GNRAL-PEDCO-220-ST-DW-0001 | BK-GNRAL-PEDCO-220-ST-DW-0001Foundation Location Drawing For Camp Area | 2022-02-12 | 2022-05-25
Structural Drawing For NISOC Residental Building | BK-GNRAL-PEDCO-220-ST-DW-0002 | BK-GNRAL-PEDCO-220-ST-DW-0002Structural Drawing For NISOC Residental Building | 2021-11-10 | 2022-05-15
Structural Drawing For Warehouse | BK-GNRAL-PEDCO-220-ST-DW-0003 | BK-GNRAL-PEDCO-220-ST-DW-0003Structural Drawing For Warehouse | 2021-11-10 | 2022-05-25
Endorsement Report For Basic Design & Scope of Work | BK-GNRAL-PEDCO-000-PM-RT-0001 | BK-GNRAL-PEDCO-000-PM-RT-0001Endorsement Report For Basic Design & Scope of Work | 2021-07-31 | 2021-09-19
Process Design Criteria | BK-GNRAL-PEDCO-000-PR-DC-0001 | BK-GNRAL-PEDCO-000-PR-DC-0001Process Design Criteria | 2021-07-27 | 2022-01-01
Process Basis Of Design | BK-GNRAL-PEDCO-000-PR-DB-0001 | BK-GNRAL-PEDCO-000-PR-DB-0001Process Basis Of Design | 2021-07-27 | 2022-05-25
Drainage Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0001 | BK-GNRAL-PEDCO-000-PR-PH-0001Drainage Philosophy | 2021-07-27 | 2022-05-25
Control Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0002 | BK-GNRAL-PEDCO-000-PR-PH-0002Control Philosophy | 2021-07-27 | 2022-05-25
Flare,Blow Down And Relief Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0003 | BK-GNRAL-PEDCO-000-PR-PH-0003Flare,Blow Down And Relief Philosophy | 2021-07-27 | 2022-05-25
Isolation Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0004 | BK-GNRAL-PEDCO-000-PR-PH-0004Isolation Philosophy | 2021-07-27 | 2022-05-25
ESD Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0005 | BK-GNRAL-PEDCO-000-PR-PH-0005ESD Philosophy | 2021-07-27 | 2022-05-25
Symbol & Legend For PFD and P&ID | BK-GNRAL-PEDCO-000-PR-PI-0001 | BK-GNRAL-PEDCO-000-PR-PI-0001Symbol & Legend For PFD and P&ID | 2021-08-04 | 2022-05-25
Mechanical Design Criteria | BK-GNRAL-PEDCO-000-ME-DC-0001 | BK-GNRAL-PEDCO-000-ME-DC-0001Mechanical Design Criteria | 2021-07-28 | 2022-05-25
Specification For Pressure Vessels | BK-GNRAL-PEDCO-000-ME-SP-0001 | BK-GNRAL-PEDCO-000-ME-SP-0001Specification For Pressure Vessels | 2021-07-28 | 2022-05-25
Specification For Atmospheric Above Ground Welded Steel Tanks | BK-GNRAL-PEDCO-000-ME-SP-0002 | BK-GNRAL-PEDCO-000-ME-SP-0002Specification For Atmospheric Above Ground Welded Steel Tanks | 2021-07-28 | 2022-05-25
Standard Detail Drawing For Pressure Vessels and Heat Exchangers | BK-GNRAL-PEDCO-000-ME-DW-0001 | BK-GNRAL-PEDCO-000-ME-DW-0001Standard Detail Drawing For Pressure Vessels and Heat Exchangers | 2021-07-28 | 2021-07-28
Standard Detail Drawing For Storage Tanks | BK-GNRAL-PEDCO-000-ME-DW-0002 | BK-GNRAL-PEDCO-000-ME-DW-0002Standard Detail Drawing For Storage Tanks | 2021-07-28 | 2021-07-28
HVAC & Plumbing Design Criteria | BK-GNRAL-PEDCO-000-HV-DC-0001 | BK-GNRAL-PEDCO-000-HV-DC-0001HVAC & Plumbing Design Criteria | 2021-07-24 | 2022-02-22
Specification For HVAC Equipment | BK-GNRAL-PEDCO-000-HV-SP-0001 | BK-GNRAL-PEDCO-000-HV-SP-0001Specification For HVAC Equipment | 2021-07-24 | 2021-10-10
Specification For Duct Work & Pipe Work | BK-GNRAL-PEDCO-000-HV-SP-0002 | BK-GNRAL-PEDCO-000-HV-SP-0002Specification For Duct Work & Pipe Work | 2021-07-24 | 2021-10-10
Standard Drawing For HVAC & Plumbing | BK-GNRAL-PEDCO-000-HV-DW-0001 | BK-GNRAL-PEDCO-000-HV-DW-0001Standard Drawing For HVAC & Plumbing | 2021-07-24 | 2021-10-10
Symbol & Legend For HVAC & Plumbing | BK-GNRAL-PEDCO-000-HV-DW-0002 | BK-GNRAL-PEDCO-000-HV-DW-0002Symbol & Legend For HVAC & Plumbing | 2021-08-22 | 2022-05-25
Piping Design Criteria | BK-GNRAL-PEDCO-000-PI-DC-0001 | BK-GNRAL-PEDCO-000-PI-DC-0001Piping Design Criteria | 2021-07-24 | 2022-01-16
Specification For Color Coding and Marking | BK-GNRAL-PEDCO-000-PI-SP-0001 | BK-GNRAL-PEDCO-000-PI-SP-0001Specification For Color Coding and Marking | 2021-08-09 | 2022-05-25
Specification For Transportation, Handling, Storage of pipes | BK-GNRAL-PEDCO-000-PI-SP-0002 | BK-GNRAL-PEDCO-000-PI-SP-0002Specification For Transportation, Handling, Storage of pipes | 2021-12-12 | 2022-05-25
Specification For the Design of Piping in Mechanical Packages | BK-GNRAL-PEDCO-000-PI-SP-0003 | BK-GNRAL-PEDCO-000-PI-SP-0003Specification For the Design of Piping in Mechanical Packages | 2021-08-09 | 2022-05-25
Specification For Metallic Pipes | BK-GNRAL-PEDCO-000-PI-SP-0004 | BK-GNRAL-PEDCO-000-PI-SP-0004Specification For Metallic Pipes | 2021-07-24 | 2022-05-25
Specification For Fittings, Flanges, Gaskets and Bolts | BK-GNRAL-PEDCO-000-PI-SP-0005 | BK-GNRAL-PEDCO-000-PI-SP-0005Specification For Fittings, Flanges, Gaskets and Bolts | 2021-07-24 | 2021-11-07
Specification For Painting | BK-GNRAL-PEDCO-000-PI-SP-0006 | BK-GNRAL-PEDCO-000-PI-SP-0006Specification For Painting | 2021-07-24 | 2022-01-04
Specification For Lining (Internal Protection of Equipment by Painting) | BK-GNRAL-PEDCO-000-PI-SP-0007 | BK-GNRAL-PEDCO-000-PI-SP-0007Specification For Lining (Internal Protection of Equipment by Painting) | 2021-08-09 | 2022-05-25
Specification For Material Requirements in Sour service | BK-GNRAL-PEDCO-000-PI-SP-0008 | BK-GNRAL-PEDCO-000-PI-SP-0008Specification For Material Requirements in Sour service | 2021-08-09 | 2022-05-25
Specification For Manual Valves | BK-GNRAL-PEDCO-000-PI-SP-0009 | BK-GNRAL-PEDCO-000-PI-SP-0009Specification For Manual Valves | 2021-08-09 | 2022-05-25
Specification For Plant Piping Systems Pressure Testing | BK-GNRAL-PEDCO-000-PI-SP-0010 | BK-GNRAL-PEDCO-000-PI-SP-0010Specification For Plant Piping Systems Pressure Testing | 2021-08-09 | 2022-05-25
Specification For Welding of Plant Piping System | BK-GNRAL-PEDCO-000-PI-SP-0011 | BK-GNRAL-PEDCO-000-PI-SP-0011Specification For Welding of Plant Piping System | 2021-08-09 | 2022-05-25
Specification For Flexibility Analysis | BK-GNRAL-PEDCO-000-PI-SP-0012 | BK-GNRAL-PEDCO-000-PI-SP-0012Specification For Flexibility Analysis | 2021-08-09 | 2022-05-25
Specification For Coating Of Underground Piping | BK-GNRAL-PEDCO-000-PI-SP-0013 | BK-GNRAL-PEDCO-000-PI-SP-0013Specification For Coating Of Underground Piping | 2021-07-24 | 2022-02-23
Specification For Pipe Support | BK-GNRAL-PEDCO-000-PI-SP-0014 | BK-GNRAL-PEDCO-000-PI-SP-0014Specification For Pipe Support | 2021-08-09 | 2022-05-25
Specification For Piping Construction, Fabrication & Erection | BK-GNRAL-PEDCO-000-PI-SP-0015 | BK-GNRAL-PEDCO-000-PI-SP-0015Specification For Piping Construction, Fabrication & Erection | 2021-08-09 | 2022-05-25
Specification For Piping Design & Plant Layout | BK-GNRAL-PEDCO-000-PI-SP-0016 | BK-GNRAL-PEDCO-000-PI-SP-0016Specification For Piping Design & Plant Layout | 2021-08-09 | 2022-05-25
Specification For Cleaning and Flushing | BK-GNRAL-PEDCO-000-PI-SP-0017 | BK-GNRAL-PEDCO-000-PI-SP-0017Specification For Cleaning and Flushing | 2021-08-24 | 2021-12-15
Specification For HDPE Pipes | BK-GNRAL-PEDCO-000-PI-SP-0018 | BK-GNRAL-PEDCO-000-PI-SP-0018Specification For HDPE Pipes | 2021-08-24 | 2022-03-05
Specification For Insulation | BK-GNRAL-PEDCO-000-PI-SP-0019 | BK-GNRAL-PEDCO-000-PI-SP-0019Specification For Insulation | 2021-08-24 | 2021-11-07
3D-Model (PDMS) Review Procedure | BK-GNRAL-PEDCO-000-PI-PR-0001 | BK-GNRAL-PEDCO-000-PI-PR-00013D-Model (PDMS) Review Procedure | 2021-07-24 | 2022-01-16
Piping Hydrostatic Test Diagram - Sub Surface | BK-GNRAL-PEDCO-000-PI-PR-0002 | BK-GNRAL-PEDCO-000-PI-PR-0002Piping Hydrostatic Test Diagram - Sub Surface |  | 2022-05-25
Pipeline Design Criteria | BK-GNRAL-PEDCO-000-PL-DC-0001 | BK-GNRAL-PEDCO-000-PL-DC-0001Pipeline Design Criteria | 2021-08-28 | 2022-02-02
Specification For Line Pipes | BK-GNRAL-PEDCO-000-PL-SP-0002 | BK-GNRAL-PEDCO-000-PL-SP-0002Specification For Line Pipes | 2021-07-24 | 2021-12-07
Specification For Pipeline Cold Bending | BK-GNRAL-PEDCO-000-PL-SP-0003 | BK-GNRAL-PEDCO-000-PL-SP-0003Specification For Pipeline Cold Bending | 2021-08-28 | 2022-05-25
Specification For Barred Tee | BK-GNRAL-PEDCO-000-PL-SP-0004 | BK-GNRAL-PEDCO-000-PL-SP-0004Specification For Barred Tee | 2021-08-28 | 2022-03-26
Specification For Fittings, Flanges, Gaskets and Bolts | BK-GNRAL-PEDCO-000-PL-SP-0005 | BK-GNRAL-PEDCO-000-PL-SP-0005Specification For Fittings, Flanges, Gaskets and Bolts | 2021-07-24 | 2021-12-07
Specification For Pipeline Valves | BK-GNRAL-PEDCO-000-PL-SP-0006 | BK-GNRAL-PEDCO-000-PL-SP-0006Specification For Pipeline Valves | 2021-08-28 | 2022-05-25
Specification For Pipeline Coating | BK-GNRAL-PEDCO-000-PL-SP-0007 | BK-GNRAL-PEDCO-000-PL-SP-0007Specification For Pipeline Coating | 2021-07-24 | 2021-12-07
Specification For Pipeline Flushing, Cleaning And Hydrostatic Testing | BK-GNRAL-PEDCO-000-PL-SP-0008 | BK-GNRAL-PEDCO-000-PL-SP-0008Specification For Pipeline Flushing, Cleaning And Hydrostatic Testing | 2021-07-24 | 2021-12-07
Specification For Welding of Transportation Pipeline | BK-GNRAL-PEDCO-000-PL-SP-0009 | BK-GNRAL-PEDCO-000-PL-SP-0009Specification For Welding of Transportation Pipeline | 2021-12-12 | 2022-05-25
Specification For Pipeline Stress Analysis | BK-GNRAL-PEDCO-000-PL-SP-0010 | BK-GNRAL-PEDCO-000-PL-SP-0010Specification For Pipeline Stress Analysis | 2021-07-24 | 2022-05-25
Specification For Pipeline Insulation Joint | BK-GNRAL-PEDCO-000-PL-SP-0011 | BK-GNRAL-PEDCO-000-PL-SP-0011Specification For Pipeline Insulation Joint | 2021-07-24 | 2021-12-07
Specification For Pipeline Construction | BK-GNRAL-PEDCO-000-PL-SP-0012 | BK-GNRAL-PEDCO-000-PL-SP-0012Specification For Pipeline Construction | 2022-01-25 | 2022-05-25
Specification For Pipeline Cleaning and Flushing | BK-GNRAL-PEDCO-000-PL-SP-0013 | BK-GNRAL-PEDCO-000-PL-SP-0013Specification For Pipeline Cleaning and Flushing | 2021-07-24 | 2022-05-25
Specification For Anchor Flanges | BK-GNRAL-PEDCO-000-PL-SP-0014 | BK-GNRAL-PEDCO-000-PL-SP-0014Specification For Anchor Flanges | 2021-08-28 | 2022-05-25
Specification For Pigs | BK-GNRAL-PEDCO-000-PL-SP-0015 | BK-GNRAL-PEDCO-000-PL-SP-0015Specification For Pigs | 2021-08-28 | 2022-05-25
Specification For LBV | BK-GNRAL-PEDCO-000-PL-SP-0016 | BK-GNRAL-PEDCO-000-PL-SP-0016Specification For LBV | 2021-10-06 | 2022-05-25
Pipeline Standard Drawing For Line Marker Post and Cathodic Protection System | BK-GNRAL-PEDCO-000-PL-DW-0001 | BK-GNRAL-PEDCO-000-PL-DW-0001Pipeline Standard Drawing For Line Marker Post and Cathodic Protection System | 2021-09-18 | 2022-05-25
Standard Drawing For Above Ground Pipeline Construction R.O.W | BK-GNRAL-PEDCO-000-PL-DW-0002 | BK-GNRAL-PEDCO-000-PL-DW-0002Standard Drawing For Above Ground Pipeline Construction R.O.W | 2021-11-27 | 2022-03-28
Standard Drawing For Under Ground Pipeline Construction R.O.W | BK-GNRAL-PEDCO-000-PL-DW-0003 | BK-GNRAL-PEDCO-000-PL-DW-0003Standard Drawing For Under Ground Pipeline Construction R.O.W | 2021-12-04 | 2022-02-02
Pipeline Standard Drawing For Anchor Support | BK-GNRAL-PEDCO-000-PL-DW-0004 | BK-GNRAL-PEDCO-000-PL-DW-0004Pipeline Standard Drawing For Anchor Support | 2021-12-22 | 2022-05-25
Standard Drawing For A/G Pipeline Road Crossing | BK-GNRAL-PEDCO-000-PL-DW-0005 | BK-GNRAL-PEDCO-000-PL-DW-0005Standard Drawing For A/G Pipeline Road Crossing | 2021-12-05 | 2022-05-16
Standard Drawing For Existing Pipeline Crossing | BK-GNRAL-PEDCO-000-PL-DW-0006 | BK-GNRAL-PEDCO-000-PL-DW-0006Standard Drawing For Existing Pipeline Crossing | 2021-12-18 | 2022-05-25
Pipeline Standard Drawing For Irish Crossing | BK-GNRAL-PEDCO-000-PL-DW-0007 | BK-GNRAL-PEDCO-000-PL-DW-0007Pipeline Standard Drawing For Irish Crossing | 2021-12-04 | 2022-05-18
Pipeline Standard Drawing For Water - Way Crossing | BK-GNRAL-PEDCO-000-PL-DW-0008 | BK-GNRAL-PEDCO-000-PL-DW-0008Pipeline Standard Drawing For Water - Way Crossing | 2021-11-22 | 2022-05-15
Pipeline Standard Drawing For Pig Signaller Concrete Pit | BK-GNRAL-PEDCO-000-PL-DW-0009 | BK-GNRAL-PEDCO-000-PL-DW-0009Pipeline Standard Drawing For Pig Signaller Concrete Pit | 2021-11-27 | 2022-05-21
Pipeline Standard Drawing For H-Pipe Support | BK-GNRAL-PEDCO-000-PL-DW-0010 | BK-GNRAL-PEDCO-000-PL-DW-0010Pipeline Standard Drawing For H-Pipe Support | 2021-11-27 | 2022-01-31
Pipeline Standard Drawing For Vent Valve Pre-cast Concrete Box | BK-GNRAL-PEDCO-000-PL-DW-0011 | BK-GNRAL-PEDCO-000-PL-DW-0011Pipeline Standard Drawing For Vent Valve Pre-cast Concrete Box | 2021-11-27 | 2022-05-25
Pipeline Standard Drawing For Cover Slabs And Set-On-Weight | BK-GNRAL-PEDCO-000-PL-DW-0013 | BK-GNRAL-PEDCO-000-PL-DW-0013Pipeline Standard Drawing For Cover Slabs And Set-On-Weight | 2021-12-21 | 2022-05-25
Pipeline Standard Drawing For River Crossing | BK-GNRAL-PEDCO-000-PL-DW-0014 | BK-GNRAL-PEDCO-000-PL-DW-0014Pipeline Standard Drawing For River Crossing | 2021-12-15 | 2022-05-25
Specification For Instrumentation | BK-GNRAL-PEDCO-000-IN-SP-0001 | BK-GNRAL-PEDCO-000-IN-SP-0001Specification For Instrumentation | 2021-07-26 | 2022-02-02
Specification For Control System | BK-GNRAL-PEDCO-000-IN-SP-0002 | BK-GNRAL-PEDCO-000-IN-SP-0002Specification For Control System | 2021-07-28 | 2022-05-25
Specification For ESD System | BK-GNRAL-PEDCO-000-IN-SP-0003 | BK-GNRAL-PEDCO-000-IN-SP-0003Specification For ESD System | 2021-07-28 | 2022-05-25
Specification For Instrument and Control of Package Unit System (PU) | BK-GNRAL-PEDCO-000-IN-SP-0004 | BK-GNRAL-PEDCO-000-IN-SP-0004Specification For Instrument and Control of Package Unit System (PU) | 2021-08-04 | 2022-05-25
Specification For Control Valves | BK-GNRAL-PEDCO-000-IN-SP-0005 | BK-GNRAL-PEDCO-000-IN-SP-0005Specification For Control Valves | 2021-07-24 | 2022-05-25
Specification For On-off /Shut Down Valves(ESDV/MOV) | BK-GNRAL-PEDCO-000-IN-SP-0006 | BK-GNRAL-PEDCO-000-IN-SP-0006Specification For On-off /Shut Down Valves(ESDV/MOV) | 2021-07-24 | 2022-05-25
Specification For Pressure Safety Valves(PSV) | BK-GNRAL-PEDCO-000-IN-SP-0007 | BK-GNRAL-PEDCO-000-IN-SP-0007Specification For Pressure Safety Valves(PSV) | 2021-07-24 | 2022-02-26
Specification For Fire & Gas Sensor and Devices | BK-GNRAL-PEDCO-000-IN-SP-0009 | BK-GNRAL-PEDCO-000-IN-SP-0009Specification For Fire & Gas Sensor and Devices | 2021-07-26 | 2022-05-25
Specification For Instrument/F&G Cables | BK-GNRAL-PEDCO-000-IN-SP-0010 | BK-GNRAL-PEDCO-000-IN-SP-0010Specification For Instrument/F&G Cables | 2021-08-04 | 2022-05-25
Specification For Control Panels and System Cabinets | BK-GNRAL-PEDCO-000-IN-SP-0011 | BK-GNRAL-PEDCO-000-IN-SP-0011Specification For Control Panels and System Cabinets | 2021-07-24 | 2022-05-25
Specification For Fire & Gas System | BK-GNRAL-PEDCO-000-IN-SP-0012 | BK-GNRAL-PEDCO-000-IN-SP-0012Specification For Fire & Gas System | 2021-07-28 | 2022-03-06
Specification For LBV | BK-GNRAL-PEDCO-000-IN-SP-0013 | BK-GNRAL-PEDCO-000-IN-SP-0013Specification For LBV | 2021-08-10 | 2022-05-25
Specification For CCTV | BK-GNRAL-PEDCO-000-IN-SP-0014 | BK-GNRAL-PEDCO-000-IN-SP-0014Specification For CCTV | 2021-09-25 | 2022-05-25
CCTV Typical Installation Details & Notes | BK-GNRAL-PEDCO-000-IN-DW-0001 | BK-GNRAL-PEDCO-000-IN-DW-0001CCTV Typical Installation Details & Notes | 2021-09-25 | 2022-05-25
Specification For Fire Fighting Equipment | BK-GNRAL-PEDCO-000-SA-SP-0001 | BK-GNRAL-PEDCO-000-SA-SP-0001Specification For Fire Fighting Equipment | 2021-08-29 | 2021-12-29
Specification For Hazardous Area Classification | BK-GNRAL-PEDCO-000-SA-SP-0002 | BK-GNRAL-PEDCO-000-SA-SP-0002Specification For Hazardous Area Classification | 2021-07-24 | 2022-01-09
Specification For Fire Water System | BK-GNRAL-PEDCO-000-SA-SP-0003 | BK-GNRAL-PEDCO-000-SA-SP-0003Specification For Fire Water System | 2021-07-24 | 2022-05-25
Specification For Environmental Job | BK-GNRAL-PEDCO-000-SA-SP-0004 | BK-GNRAL-PEDCO-000-SA-SP-0004Specification For Environmental Job | 2021-08-11 | 2022-05-25
Specification For Total Flooding System | BK-GNRAL-PEDCO-000-SA-SP-0005 | BK-GNRAL-PEDCO-000-SA-SP-0005Specification For Total Flooding System | 2021-07-24 | 2022-02-26
Specification For Safety Equipment | BK-GNRAL-PEDCO-000-SA-SP-0006 | BK-GNRAL-PEDCO-000-SA-SP-0006Specification For Safety Equipment | 2021-08-29 | 2021-12-06
Specification For passive Fire protection | BK-GNRAL-PEDCO-000-SA-SP-0007 | BK-GNRAL-PEDCO-000-SA-SP-0007Specification For passive Fire protection | 2021-07-24 | 2022-03-05
Specification For Safety Signs | BK-GNRAL-PEDCO-000-SA-SP-0008 | BK-GNRAL-PEDCO-000-SA-SP-0008Specification For Safety Signs | 2021-07-24 | 2022-01-09
Typical Installation Detail for Safety & Fire Fighting Equipment | BK-GNRAL-PEDCO-000-SA-DW-0002 | BK-GNRAL-PEDCO-000-SA-DW-0002Typical Installation Detail for Safety & Fire Fighting Equipment | 2021-12-29 | 2021-12-29
Symbol & Legend For Safety & Firefighting Systems | BK-GNRAL-PEDCO-000-SA-DW-0003 | BK-GNRAL-PEDCO-000-SA-DW-0003Symbol & Legend For Safety & Firefighting Systems | 2021-08-29 | 2021-12-08
Material Safety Data Sheets | BK-GNRAL-PEDCO-000-SA-DT-0001 | BK-GNRAL-PEDCO-000-SA-DT-0001Material Safety Data Sheets | 2021-09-21 | 2022-05-25
Electrical System Design Criteria | BK-GNRAL-PEDCO-000-EL-DC-0001 | BK-GNRAL-PEDCO-000-EL-DC-0001Electrical System Design Criteria | 2021-08-03 | 2022-05-25
Specification For LV Switchgear & Motor Control Centers | BK-GNRAL-PEDCO-000-EL-SP-0001 | BK-GNRAL-PEDCO-000-EL-SP-0001Specification For LV Switchgear & Motor Control Centers | 2021-07-24 | 2022-02-13
Specification For MV Switchgear | BK-GNRAL-PEDCO-000-EL-SP-0002 | BK-GNRAL-PEDCO-000-EL-SP-0002Specification For MV Switchgear | 2021-07-24 | 2022-02-13
Specification For UPS System | BK-GNRAL-PEDCO-000-EL-SP-0003 | BK-GNRAL-PEDCO-000-EL-SP-0003Specification For UPS System | 2021-08-04 | 2022-02-13
Specification For Transformers | BK-GNRAL-PEDCO-000-EL-SP-0004 | BK-GNRAL-PEDCO-000-EL-SP-0004Specification For Transformers | 2021-07-24 | 2022-03-08
Specification For DC Charger | BK-GNRAL-PEDCO-000-EL-SP-0005 | BK-GNRAL-PEDCO-000-EL-SP-0005Specification For DC Charger | 2021-08-04 | 2021-12-07
Specification For Earthing & Lightning System | BK-GNRAL-PEDCO-000-EL-SP-0006 | BK-GNRAL-PEDCO-000-EL-SP-0006Specification For Earthing & Lightning System | 2021-07-28 | 2022-05-25
Specification For Lighting & Small Power System | BK-GNRAL-PEDCO-000-EL-SP-0007 | BK-GNRAL-PEDCO-000-EL-SP-0007Specification For Lighting & Small Power System | 2021-07-28 | 2022-05-25
Specification For Bulk Materials | BK-GNRAL-PEDCO-000-EL-SP-0008 | BK-GNRAL-PEDCO-000-EL-SP-0008Specification For Bulk Materials | 2021-07-24 | 2022-03-07
Specification For Diesel Generator | BK-GNRAL-PEDCO-000-EL-SP-0009 | BK-GNRAL-PEDCO-000-EL-SP-0009Specification For Diesel Generator | 2021-07-28 | 2022-05-25
Specification For LV Induction Motors | BK-GNRAL-PEDCO-000-EL-SP-0010 | BK-GNRAL-PEDCO-000-EL-SP-0010Specification For LV Induction Motors | 2021-07-24 | 2022-02-13
Specification For Electrical Requirements of Packaged Units | BK-GNRAL-PEDCO-000-EL-SP-0011 | BK-GNRAL-PEDCO-000-EL-SP-0011Specification For Electrical Requirements of Packaged Units | 2021-07-28 | 2022-05-25
Specification For Capacitor Bank | BK-GNRAL-PEDCO-000-EL-SP-0012 | BK-GNRAL-PEDCO-000-EL-SP-0012Specification For Capacitor Bank | 2021-07-24 | 2022-02-13
Specification For Distribution & Lighting Panels | BK-GNRAL-PEDCO-000-EL-SP-0013 | BK-GNRAL-PEDCO-000-EL-SP-0013Specification For Distribution & Lighting Panels | 2021-07-28 | 2022-05-25
Specification For Power & Control Cables | BK-GNRAL-PEDCO-000-EL-SP-0014 | BK-GNRAL-PEDCO-000-EL-SP-0014Specification For Power & Control Cables | 2021-07-24 | 2022-02-13
Specification For Cathodic Protection System | BK-GNRAL-PEDCO-000-EL-SP-0016 | BK-GNRAL-PEDCO-000-EL-SP-0016Specification For Cathodic Protection System | 2021-07-31 | 2021-12-07
Specification For MV Induction Motors | BK-GNRAL-PEDCO-000-EL-SP-0017 | BK-GNRAL-PEDCO-000-EL-SP-0017Specification For MV Induction Motors | 2021-07-24 | 2022-02-13
Specification For NGR | BK-GNRAL-PEDCO-000-EL-SP-0018 | BK-GNRAL-PEDCO-000-EL-SP-0018Specification For NGR | 2021-07-24 | 2022-02-13
Specification For Overhead Transmission Lines | BK-GNRAL-PEDCO-000-EL-SP-0019 | BK-GNRAL-PEDCO-000-EL-SP-0019Specification For Overhead Transmission Lines | 2021-07-28 | 2022-02-13
Electrical Legend and Symbols | BK-GNRAL-PEDCO-000-EL-DW-0001 | BK-GNRAL-PEDCO-000-EL-DW-0001Electrical Legend and Symbols | 2021-08-09 | 2021-12-08
Typical Installation Details & Notes For Earthing and Lightning Protection System | BK-GNRAL-PEDCO-000-EL-DW-0002 | BK-GNRAL-PEDCO-000-EL-DW-0002Typical Installation Details & Notes For Earthing and Lightning Protection System | 2021-08-25 | 2021-11-28
Typical Installation Details & Notes For Lighting System | BK-GNRAL-PEDCO-000-EL-DW-0003 | BK-GNRAL-PEDCO-000-EL-DW-0003Typical Installation Details & Notes For Lighting System | 2021-08-25 | 2021-10-25
Typical Installation Details & Notes For Power System | BK-GNRAL-PEDCO-000-EL-DW-0004 | BK-GNRAL-PEDCO-000-EL-DW-0004Typical Installation Details & Notes For Power System | 2021-08-25 | 2021-11-28
Installation Details & Notes For Cathodic Protection Systems | BK-GNRAL-PEDCO-000-EL-DW-0005 | BK-GNRAL-PEDCO-000-EL-DW-0005Installation Details & Notes For Cathodic Protection Systems | 2021-08-25 | 2022-02-13
Telecom. Design Criteria | BK-GNRAL-PEDCO-000-TE-DC-0001 | BK-GNRAL-PEDCO-000-TE-DC-0001Telecom. Design Criteria | 2021-07-28 | 2021-12-07
Specification For CCTV | BK-GNRAL-PEDCO-000-TE-SP-0001 | BK-GNRAL-PEDCO-000-TE-SP-0001Specification For CCTV | 2021-08-10 | 2022-05-25
Specification For PABX | BK-GNRAL-PEDCO-000-TE-SP-0002 | BK-GNRAL-PEDCO-000-TE-SP-0002Specification For PABX | 2021-08-04 | 2021-12-07
Specification For PAGA | BK-GNRAL-PEDCO-000-TE-SP-0003 | BK-GNRAL-PEDCO-000-TE-SP-0003Specification For PAGA | 2021-08-04 | 2022-05-25
Specification For Radio | BK-GNRAL-PEDCO-000-TE-SP-0004 | BK-GNRAL-PEDCO-000-TE-SP-0004Specification For Radio | 2021-08-04 | 2022-02-22
Specification For Telecommunication Tower | BK-GNRAL-PEDCO-000-TE-SP-0005 | BK-GNRAL-PEDCO-000-TE-SP-0005Specification For Telecommunication Tower | 2021-08-04 | 2022-05-25
Specification For Telecom. Cable | BK-GNRAL-PEDCO-000-TE-SP-0006 | BK-GNRAL-PEDCO-000-TE-SP-0006Specification For Telecom. Cable | 2021-08-09 | 2021-12-08
Telecom Systems Legend and Symbols | BK-GNRAL-PEDCO-000-TE-DW-0001 | BK-GNRAL-PEDCO-000-TE-DW-0001Telecom Systems Legend and Symbols | 2021-08-01 | 2022-05-25
Telecom Typical Installation Details & Notes | BK-GNRAL-PEDCO-000-TE-DW-0002 | BK-GNRAL-PEDCO-000-TE-DW-0002Telecom Typical Installation Details & Notes | 2021-08-01 | 2021-08-01
CCTV Typical Installation Details & Notes | BK-GNRAL-PEDCO-000-TE-DW-0003 | BK-GNRAL-PEDCO-000-TE-DW-0003CCTV Typical Installation Details & Notes | 2021-08-22 | 2022-05-25
Architectural Design Criteria | BK-GNRAL-PEDCO-000-AR-DC-0001 | BK-GNRAL-PEDCO-000-AR-DC-0001Architectural Design Criteria | 2022-02-08 | 2022-05-25
Buildings General Specification | BK-GNRAL-PEDCO-000-AR-SP-0001 | BK-GNRAL-PEDCO-000-AR-SP-0001 Buildings General Specification | 2022-04-06 | 2022-05-25
Standard Drawing for Architectural Details | BK-GNRAL-PEDCO-000-AR-DW-0001 | BK-GNRAL-PEDCO-000-AR-DW-0001Standard Drawing for Architectural Details | 2021-12-18 | 2022-05-25
Civil Design Criteria | BK-GNRAL-PEDCO-000-CV-DC-0001 | BK-GNRAL-PEDCO-000-CV-DC-0001Civil Design Criteria | 2022-02-13 | 2022-05-25
Design Criteria for Sewerage & Drainage | BK-GNRAL-PEDCO-000-CV-DC-0002 | BK-GNRAL-PEDCO-000-CV-DC-0002Design Criteria for Sewerage & Drainage |  | 2022-05-25
Specification For Civil Works | BK-GNRAL-PEDCO-000-CV-SP-0001 | BK-GNRAL-PEDCO-000-CV-SP-0001Specification For Civil Works |  | 2022-05-25
Specification For Road & Paving | BK-GNRAL-PEDCO-000-CV-SP-0002 | BK-GNRAL-PEDCO-000-CV-SP-0002Specification For Road & Paving | 2021-08-09 | 2022-05-22
Specification For Fence & Gate | BK-GNRAL-PEDCO-000-CV-SP-0003 | BK-GNRAL-PEDCO-000-CV-SP-0003Specification For Fence & Gate | 2021-09-18 | 2021-12-26
Specification For Earth Work | BK-GNRAL-PEDCO-000-CV-SP-0004 | BK-GNRAL-PEDCO-000-CV-SP-0004Specification For Earth Work | 2021-08-09 | 2022-04-25
Specification For Sewerage & Drainage | BK-GNRAL-PEDCO-000-CV-SP-0005 | BK-GNRAL-PEDCO-000-CV-SP-0005Specification For Sewerage & Drainage | 2021-08-09 | 2022-03-12
Specification For Geological & Geotechnical Survey | BK-GNRAL-PEDCO-000-CV-SP-0006 | BK-GNRAL-PEDCO-000-CV-SP-0006Specification For Geological & Geotechnical Survey | 2022-03-26 | 2022-05-25
Standard Drawing For Civil Works | BK-GNRAL-PEDCO-000-CV-DW-0001 | BK-GNRAL-PEDCO-000-CV-DW-0001Standard Drawing For Civil Works |  | 2022-05-25
Standard Drawing For Slope Protection Details | BK-GNRAL-PEDCO-000-CV-DW-0002 | BK-GNRAL-PEDCO-000-CV-DW-0002Standard Drawing For Slope Protection Details | 2021-08-22 | 2022-05-25
Standard Drawing For Roads | BK-GNRAL-PEDCO-000-CV-DW-0003 | BK-GNRAL-PEDCO-000-CV-DW-0003Standard Drawing For Roads | 2021-08-22 | 2022-05-21
Standard Drawing For Electrical Cable Trench | BK-GNRAL-PEDCO-000-CV-DW-0004 | BK-GNRAL-PEDCO-000-CV-DW-0004Standard Drawing For Electrical Cable Trench | 2021-08-22 | 2022-05-25
Standard Drawing For Manholes | BK-GNRAL-PEDCO-000-CV-DW-0005 | BK-GNRAL-PEDCO-000-CV-DW-0005Standard Drawing For Manholes | 2021-08-22 | 2022-05-25
Standard Drawing For Catch Basins | BK-GNRAL-PEDCO-000-CV-DW-0006 | BK-GNRAL-PEDCO-000-CV-DW-0006Standard Drawing For Catch Basins | 2021-08-22 | 2022-05-25
Standard Drawing For Sewerage & Drainage Details | BK-GNRAL-PEDCO-000-CV-DW-0007 | BK-GNRAL-PEDCO-000-CV-DW-0007Standard Drawing For Sewerage & Drainage Details | 2022-02-02 | 2022-05-25
Standard Drawing For Civil Underground Crossings | BK-GNRAL-PEDCO-000-CV-DW-0008 | BK-GNRAL-PEDCO-000-CV-DW-0008Standard Drawing For Civil Underground Crossings | 2022-02-07 | 2022-05-25
Standard Drawing For Fence & Gate Details | BK-GNRAL-PEDCO-000-CV-DW-0009 | BK-GNRAL-PEDCO-000-CV-DW-0009Standard Drawing For Fence & Gate Details | 2021-09-18 | 2022-02-28
Standard Drawing For Concrete Continues Weight | BK-GNRAL-PEDCO-000-CV-DW-0010 | BK-GNRAL-PEDCO-000-CV-DW-0010Standard Drawing For Concrete Continues Weight | 2021-08-08 | 2022-05-25
Standard Drawing For Major Floodway Crossing | BK-GNRAL-PEDCO-000-CV-DW-0012 | BK-GNRAL-PEDCO-000-CV-DW-0012Standard Drawing For Major Floodway Crossing |  | 2022-05-25
Standard Drawing For Culvert & Details | BK-GNRAL-PEDCO-000-CV-DW-0014 | BK-GNRAL-PEDCO-000-CV-DW-0014 Standard Drawing For Culvert & Details | 2021-09-25 | 2021-11-15
Standard Drawing For Valve Box | BK-GNRAL-PEDCO-000-CV-DW-0016 | BK-GNRAL-PEDCO-000-CV-DW-0016Standard Drawing For Valve Box | 2022-01-12 | 2022-01-12
Standard Drawing For Fire Hydrant PAD | BK-GNRAL-PEDCO-000-CV-DW-0018 | BK-GNRAL-PEDCO-000-CV-DW-0018Standard Drawing For Fire Hydrant PAD | 2022-03-13 | 2022-05-25
Standard Drawing For Cable Pull Pit | BK-GNRAL-PEDCO-000-CV-DW-0020 | BK-GNRAL-PEDCO-000-CV-DW-0020Standard Drawing For Cable Pull Pit | 2022-04-11 | 2022-05-25
Standard Drawing For Pavings | BK-GNRAL-PEDCO-000-CV-DW-0035 | BK-GNRAL-PEDCO-000-CV-DW-0035Standard Drawing For Pavings | 2022-01-08 | 2022-05-25
Standard Drawing For Earth Pit | BK-GNRAL-PEDCO-000-CV-DW-0037 | BK-GNRAL-PEDCO-000-CV-DW-0037Standard Drawing For Earth Pit | 2022-02-13 | 2022-05-25
Standard Detail For Pipe Bedding | BK-GNRAL-PEDCO-000-CV-DW-0039 | BK-GNRAL-PEDCO-000-CV-DW-0039Standard Detail For Pipe Bedding | 2021-08-22 | 2022-05-25
Standard Details of Miscellaneous Items | BK-GNRAL-PEDCO-000-CV-DW-0040 | BK-GNRAL-PEDCO-000-CV-DW-0040Standard Details of Miscellaneous Items | 2022-03-06 | 2022-05-22
Typical Drawing For A/G Pipeline Road Crossing | BK-GNRAL-PEDCO-000-CV-DW-0025 | BK-GNRAL-PEDCO-000-CV-DW-0025Typical Drawing For A/G Pipeline Road Crossing | 2021-08-08 | 2022-05-25
Pipeline Typical Drawing For Irish Crossing | BK-GNRAL-PEDCO-000-CV-DW-0027 | BK-GNRAL-PEDCO-000-CV-DW-0027Pipeline Typical Drawing For Irish Crossing | 2021-08-08 | 2022-05-25
Pipeline Typical Drawing For Water - Way Crossing | BK-GNRAL-PEDCO-000-CV-DW-0028 | BK-GNRAL-PEDCO-000-CV-DW-0028Pipeline Typical Drawing For Water - Way Crossing | 2021-08-08 | 2022-05-25
Pipeline Typical Drawing For Pig Signaller Concrete Pit | BK-GNRAL-PEDCO-000-CV-DW-0029 | BK-GNRAL-PEDCO-000-CV-DW-0029Pipeline Typical Drawing For Pig Signaller Concrete Pit | 2021-08-08 | 2022-05-25
Pipeline Typical Drawing For H-Pipe Support | BK-GNRAL-PEDCO-000-CV-DW-0030 | BK-GNRAL-PEDCO-000-CV-DW-0030Pipeline Typical Drawing For H-Pipe Support | 2021-08-08 | 2022-05-25
Pipeline Typical Drawing For Vent Valve Pre-cast Concrete Box | BK-GNRAL-PEDCO-000-CV-DW-0031 | BK-GNRAL-PEDCO-000-CV-DW-0031Pipeline Typical Drawing For Vent Valve Pre-cast Concrete Box | 2021-08-08 | 2022-05-25
Standard Detail curbed Stone Bounded Area | BK-GNRAL-PEDCO-000-CV-DW-0038 | BK-GNRAL-PEDCO-000-CV-DW-0038Standard Detail curbed Stone Bounded Area | 2021-08-22 | 2022-05-25
Design Criteria For Concrete Works | BK-GNRAL-PEDCO-000-ST-DC-0001 | BK-GNRAL-PEDCO-000-ST-DC-0001Design Criteria For Concrete Works |  | 2022-05-25
Specification For Concrete Work | BK-GNRAL-PEDCO-000-ST-SP-0001 | BK-GNRAL-PEDCO-000-ST-SP-0001Specification For Concrete Work | 2021-08-14 | 2022-05-25
Specification For Storage Tank Foundation | BK-GNRAL-PEDCO-000-ST-SP-0002 | BK-GNRAL-PEDCO-000-ST-SP-0002Specification For Storage Tank Foundation | 2021-11-23 | 2022-03-09
Specification for Fabrication of Steel Structures | BK-GNRAL-PEDCO-000-ST-SP-0003 | BK-GNRAL-PEDCO-000-ST-SP-0003Specification for Fabrication of Steel Structures | 2022-01-24 | 2022-02-28
Specification For Grouting | BK-GNRAL-PEDCO-000-ST-SP-0004 | BK-GNRAL-PEDCO-000-ST-SP-0004Specification For Grouting | 2021-08-14 | 2022-01-18
Specification for Erection of Steel Structures | BK-GNRAL-PEDCO-000-ST-SP-0005 | BK-GNRAL-PEDCO-000-ST-SP-0005Specification for Erection of Steel Structures | 2022-01-24 | 2022-02-28
Specification for Fireproofing | BK-GNRAL-PEDCO-000-ST-SP-0006 | BK-GNRAL-PEDCO-000-ST-SP-0006Specification for Fireproofing | 2021-09-18 | 2021-12-26
Specification for Design of Blast Resistant Buildings | BK-GNRAL-PEDCO-000-ST-SP-0007 | BK-GNRAL-PEDCO-000-ST-SP-0007Specification for Design of Blast Resistant Buildings | 2021-12-12 | 2022-05-25
Specification For Steel Structural Works | BK-GNRAL-PEDCO-000-ST-SP-0008 | BK-GNRAL-PEDCO-000-ST-SP-0008Specification For Steel Structural Works |  | 2022-05-25
Standard Drawing For Fire Proofing | BK-GNRAL-PEDCO-000-ST-DW-0001 | BK-GNRAL-PEDCO-000-ST-DW-0001Standard Drawing For Fire Proofing | 2021-08-08 | 2022-01-18
Standard Drawing For Anchor Bolts | BK-GNRAL-PEDCO-000-ST-DW-0002 | BK-GNRAL-PEDCO-000-ST-DW-0002Standard Drawing For Anchor Bolts | 2021-12-15 | 2022-02-12
Standard Drawing For Steel Stairs | BK-GNRAL-PEDCO-000-ST-DW-0003 | BK-GNRAL-PEDCO-000-ST-DW-0003Standard Drawing For Steel Stairs | 2021-12-18 | 2022-02-13
Standard Drawing For Operating Platform | BK-GNRAL-PEDCO-000-ST-DW-0005 | BK-GNRAL-PEDCO-000-ST-DW-0005Standard Drawing For Operating Platform | 2021-12-27 | 2022-03-12
Standard Drawing For Handrail | BK-GNRAL-PEDCO-000-ST-DW-0006 | BK-GNRAL-PEDCO-000-ST-DW-0006Standard Drawing For Handrail | 2021-12-18 | 2022-02-09
Standard Drawing For Insert Plates in Concrete | BK-GNRAL-PEDCO-000-ST-DW-0007 | BK-GNRAL-PEDCO-000-ST-DW-0007Standard Drawing For Insert Plates in Concrete | 2021-08-08 | 2022-01-24
Standard Details For Ladder & Safety Cage | BK-GNRAL-PEDCO-000-ST-DW-0009 | BK-GNRAL-PEDCO-000-ST-DW-0009Standard Details For Ladder & Safety Cage | 2021-12-15 | 2022-02-16
Standard Drawing For Lighting pole foundation Plan & Details | BK-GNRAL-PEDCO-000-ST-DW-0010 | BK-GNRAL-PEDCO-000-ST-DW-0010Standard Drawing For Lighting pole foundation Plan & Details | 2022-01-29 | 2022-05-25
General Notes - Steel Structures | BK-GNRAL-PEDCO-000-ST-DW-0011 | BK-GNRAL-PEDCO-000-ST-DW-0011General Notes - Steel Structures | 2022-01-25 | 2022-03-12
General Notes - Reinforced Concrete Structures | BK-GNRAL-PEDCO-000-ST-DW-0012 | BK-GNRAL-PEDCO-000-ST-DW-0012General Notes - Reinforced Concrete Structures | 2021-12-20 | 2022-02-16
Standard Drawing For Structural Built-up Sections | BK-GNRAL-PEDCO-000-ST-DW-0014 | BK-GNRAL-PEDCO-000-ST-DW-0014Standard Drawing For Structural Built-up Sections | 2021-12-04 | 2022-05-23
Standard Drawing For Steel Flooring, Grating and Chequered Plate | BK-GNRAL-PEDCO-000-ST-DW-0015 | BK-GNRAL-PEDCO-000-ST-DW-0015Standard Drawing For Steel Flooring, Grating and Chequered Plate | 2022-01-05 | 2022-02-12
Concrete Reinforcement Shape Code | BK-GNRAL-PEDCO-000-ST-DW-0016 | BK-GNRAL-PEDCO-000-ST-DW-0016Concrete Reinforcement Shape Code |  | 2022-05-25
Standard Drawing For Septic Tank | BK-GNRAL-PEDCO-000-ST-DW-0017 | BK-GNRAL-PEDCO-000-ST-DW-0017Standard Drawing For Septic Tank | 2022-01-22 | 2022-05-25
EPC Waste Management Plan | BK-GNRAL-HD-000-SA-HP-0001 | BK-GNRAL-HD-000-SA-HP-0001EPC Waste Management Plan |  | 2022-05-25
HAZOP Study Procedure | BK-GNRAL-PEDCO-000-GE-PR-0001 | BK-GNRAL-PEDCO-000-GE-PR-0001HAZOP Study Procedure | 2021-10-25 | 2022-03-02
HAZID Study Procedure | BK-GNRAL-PEDCO-000-GE-PR-0002 | BK-GNRAL-PEDCO-000-GE-PR-0002HAZID Study Procedure | 2021-09-05 | 2021-10-27
SIL Study Procedure | BK-GNRAL-PEDCO-000-GE-PR-0003 | BK-GNRAL-PEDCO-000-GE-PR-0003SIL Study Procedure | 2021-10-25 | 2022-03-07
Crisis Management Plan | BK-GNRAL-HD-000-GE-PR-0004 | BK-GNRAL-HD-000-GE-PR-0004Crisis Management Plan |  | 2022-05-25
EPC FMEA report | BK-GNRAL-HD-000-GE-PR-0005 | BK-GNRAL-HD-000-GE-PR-0005EPC FMEA report | 2021-12-28 | 2022-05-22
PSSR Procedure | BK-GNRAL-HD-000-GE-PR-0006 | BK-GNRAL-HD-000-GE-PR-0006PSSR Procedure |  | 2022-05-25
Pigging Safety Requirement | BK-GNRAL-PEDCO-000-GE-PR-0007 | BK-GNRAL-PEDCO-000-GE-PR-0007Pigging Safety Requirement | 2022-04-09 | 2022-05-25
Project Quality Plan | BK-GNRAL-PEDCO-000-QC-PR-0001 | BK-GNRAL-PEDCO-000-QC-PR-0001Project Quality Plan | 2021-12-08 | 2022-05-25
Project Audit Procedure | BK-GNRAL-PEDCO-000-QC-PR-0003 | BK-GNRAL-PEDCO-000-QC-PR-0003Project Audit Procedure |  | 2022-05-25
Non Conformance Control Procedure | BK-GNRAL-PEDCO-000-QC-PR-0042 | BK-GNRAL-PEDCO-000-QC-PR-0042Non Conformance Control Procedure | 2022-04-10 | 2022-05-25
Corrective Action Procedure | BK-GNRAL-PEDCO-000-QC-PR-0043 | BK-GNRAL-PEDCO-000-QC-PR-0043Corrective Action Procedure |  | 2022-05-25
Material Reciving, Storage, Handling Procedure | BK-GNRAL-PEDCO-000-QC-PR-0044 | BK-GNRAL-PEDCO-000-QC-PR-0044Material Reciving, Storage, Handling Procedure | 2022-02-20 | 2022-05-25
Packing, Marking, Transportation Procedure | BK-GNRAL-PEDCO-000-QC-PR-0045 | BK-GNRAL-PEDCO-000-QC-PR-0045Packing, Marking, Transportation Procedure | 2022-04-24 | 2022-05-25
Criticality Assessment Procedure | BK-GNRAL-PEDCO-000-PM-PR-0013 | BK-GNRAL-PEDCO-000-PM-PR-0013Criticality Assessment Procedure |  | 2022-05-25
Specification For Final Data Book (FDB) Requirements | BK-GNRAL-PEDCO-000-QC-PR-0022 | BK-GNRAL-PEDCO-000-QC-PR-0022Specification For Final Data Book (FDB) Requirements | 2022-04-03 | 2022-05-25
Technical Query Procedure | BK-GNRAL-PEDCO-000-QC-PR-0014 | BK-GNRAL-PEDCO-000-QC-PR-0014Technical Query Procedure | 2022-04-03 | 2022-05-25
Quality Control Plan (QCP) | BK-GNRAL-PEDCO-000-QC-PR-0002 | BK-GNRAL-PEDCO-000-QC-PR-0002Quality Control Plan (QCP) | 2021-11-28 | 2022-05-25
Specification for Welding Procedure | BK-GNRAL-PEDCO-000-QC-PR-0015 | BK-GNRAL-PEDCO-000-QC-PR-0015Specification for Welding Procedure | 2022-04-16 | 2022-05-25
Heat Treatment Procedure (Pre Heating , PWHT) | BK-GNRAL-PEDCO-000-QC-PR-0016 | BK-GNRAL-PEDCO-000-QC-PR-0016Heat Treatment Procedure (Pre Heating , PWHT) |  | 2022-05-25
Welder Performance Qualification Test (WQT) Procedure | BK-GNRAL-PEDCO-000-QC-PR-0017 | BK-GNRAL-PEDCO-000-QC-PR-0017Welder Performance Qualification Test (WQT) Procedure | 2022-04-04 | 2022-05-25
NDT Procedure | BK-GNRAL-PEDCO-000-QC-PR-0018 | BK-GNRAL-PEDCO-000-QC-PR-0018NDT Procedure |  | 2022-05-25
Surface Preparation and Coating/Painting Procedure | BK-GNRAL-PEDCO-000-QC-PR-0019 | BK-GNRAL-PEDCO-000-QC-PR-0019Surface Preparation and Coating/Painting Procedure |  | 2022-05-25
Control of Inspection Measuring and Test Equipment Procedure | BK-GNRAL-PEDCO-000-QC-PR-0021 | BK-GNRAL-PEDCO-000-QC-PR-0021Control of Inspection Measuring and Test Equipment Procedure | 2022-04-10 | 2022-05-25
Field Joint Coating Procedure For Pipeline | BK-GNRAL-PEDCO-000-QC-PR-0035 | BK-GNRAL-PEDCO-000-QC-PR-0035Field Joint Coating Procedure For Pipeline |  | 2022-05-25
ITP For Piping Works | BK-GNRAL-PEDCO-000-QC-PR-0004 | BK-GNRAL-PEDCO-000-QC-PR-0004ITP For Piping Works | 2022-04-10 | 2022-05-25
PIPING PWPS (Preliminary Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0023 | BK-GNRAL-PEDCO-000-QC-PR-0023PIPING PWPS (Preliminary Welding Procedure Specification) |  | 2022-05-25
PIPING WPS (Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0024 | BK-GNRAL-PEDCO-000-QC-PR-0024PIPING WPS (Welding Procedure Specification) |  | 2022-05-25
PIPING PQR (Procedure Qualification Record) | BK-GNRAL-PEDCO-000-QC-PR-0025 | BK-GNRAL-PEDCO-000-QC-PR-0025PIPING PQR (Procedure Qualification Record) |  | 2022-05-25
PIPING PWPS (Preliminary Welding Procedure Specification) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0026 | BK-GNRAL-PEDCO-000-QC-PR-0026PIPING PWPS (Preliminary Welding Procedure Specification) for Repair Welding |  | 2022-05-25
PIPING WPS (Preliminary Welding Procedure Specification) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0027 | BK-GNRAL-PEDCO-000-QC-PR-0027PIPING WPS (Preliminary Welding Procedure Specification) for Repair Welding |  | 2022-05-25
PIPING PQR (Procedure Qualification Record) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0028 | BK-GNRAL-PEDCO-000-QC-PR-0028PIPING PQR (Procedure Qualification Record) for Repair Welding |  | 2022-05-25
ITP For Telecommunication Installation | BK-GNRAL-PEDCO-000-QC-PR-0012 | BK-GNRAL-PEDCO-000-QC-PR-0012ITP For Telecommunication Installation |  | 2022-05-25
ITP For Safety Installation | BK-GNRAL-PEDCO-000-QC-PR-0013 | BK-GNRAL-PEDCO-000-QC-PR-0013ITP For Safety Installation |  | 2022-05-25
ITP For Architectural Works | BK-GNRAL-PEDCO-000-QC-PR-0008 | BK-GNRAL-PEDCO-000-QC-PR-0008ITP For Architectural Works |  | 2022-05-25
ITP For Mechanical Installation | BK-GNRAL-PEDCO-000-QC-PR-0009 | BK-GNRAL-PEDCO-000-QC-PR-0009ITP For Mechanical Installation |  | 2022-05-25
ITP For Steel Structural Works | BK-GNRAL-PEDCO-000-QC-PR-0007 | BK-GNRAL-PEDCO-000-QC-PR-0007ITP For Steel Structural Works | 2022-05-21 | 2022-05-25
Steel Structure WPS (Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0036 | BK-GNRAL-PEDCO-000-QC-PR-0036Steel Structure WPS (Welding Procedure Specification) |  | 2022-05-25
Steel Structure PQR (Procedure Qualification Record) | BK-GNRAL-PEDCO-000-QC-PR-0037 | BK-GNRAL-PEDCO-000-QC-PR-0037Steel Structure PQR (Procedure Qualification Record) |  | 2022-05-25
Steel Structure WPS (Welding Procedure Specification) For Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0038 | BK-GNRAL-PEDCO-000-QC-PR-0038Steel Structure WPS (Welding Procedure Specification) For Repair Welding |  | 2022-05-25
Steel Structure PQR (Procedure Qualification Record) For Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0039 | BK-GNRAL-PEDCO-000-QC-PR-0039Steel Structure PQR (Procedure Qualification Record) For Repair Welding |  | 2022-05-25
Weld Map For Steel Structures | BK-GNRAL-PEDCO-000-QC-PR-0040 | BK-GNRAL-PEDCO-000-QC-PR-0040Weld Map For Steel Structures |  | 2022-05-25
NDT Plan For steel Structures | BK-GNRAL-PEDCO-000-QC-PR-0041 | BK-GNRAL-PEDCO-000-QC-PR-0041NDT Plan For steel Structures |  | 2022-05-25
ITP For I&C Installation | BK-GNRAL-PEDCO-000-QC-PR-0011 | BK-GNRAL-PEDCO-000-QC-PR-0011ITP For I&C Installation |  | 2022-05-25
ITP For Pipeline | BK-GNRAL-PEDCO-000-QC-PR-0005 | BK-GNRAL-PEDCO-000-QC-PR-0005ITP For Pipeline | 2022-01-16 | 2022-05-25
PIPELINE PWPS (Preliminary Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0029 | BK-GNRAL-PEDCO-000-QC-PR-0029PIPELINE PWPS (Preliminary Welding Procedure Specification) | 2022-02-23 | 2022-05-25
PIPELINE WPS (Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0030 | BK-GNRAL-PEDCO-000-QC-PR-0030PIPELINE WPS (Welding Procedure Specification) |  | 2022-05-25
PIPELINE PQR (Procedure Qualification Record) | BK-GNRAL-PEDCO-000-QC-PR-0031 | BK-GNRAL-PEDCO-000-QC-PR-0031PIPELINE PQR (Procedure Qualification Record) |  | 2022-05-25
PIPELINE PWPS (Preliminary Welding Procedure Specification) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0032 | BK-GNRAL-PEDCO-000-QC-PR-0032PIPELINE PWPS (Preliminary Welding Procedure Specification) for Repair Welding |  | 2022-05-25
PIPELINE WPS (Preliminary Welding Procedure Specification) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0033 | BK-GNRAL-PEDCO-000-QC-PR-0033PIPELINE WPS (Preliminary Welding Procedure Specification) for Repair Welding |  | 2022-05-25
PIPELINE PQR (Procedure Qualification Record) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0034 | BK-GNRAL-PEDCO-000-QC-PR-0034PIPELINE PQR (Procedure Qualification Record) for Repair Welding |  | 2022-05-25
ITP For Civil Works | BK-GNRAL-PEDCO-000-QC-PR-0006 | BK-GNRAL-PEDCO-000-QC-PR-0006ITP For Civil Works | 2021-09-20 | 2022-05-25
ITP For Electrical Installation | BK-GNRAL-PEDCO-000-QC-PR-0010 | BK-GNRAL-PEDCO-000-QC-PR-0010ITP For Electrical Installation |  | 2022-05-25
Endorsement Report For Basic Design & Scope of Work | BK-SSGRL-PEDCO-110-GE-RT-0001 | BK-SSGRL-PEDCO-110-GE-RT-0001Endorsement Report For Basic Design & Scope of Work | 2021-07-31 | 2022-05-25
Value Engineering Study Report | BK-SSGRL-PEDCO-110-GE-RT-0002 | BK-SSGRL-PEDCO-110-GE-RT-0002Value Engineering Study Report | 2022-02-01 | 2022-05-25
HAZID Report For WHF & Flow lines | BK-SSGRL-PEDCO-110-GE-RT-0003 | BK-SSGRL-PEDCO-110-GE-RT-0003HAZID Report For WHF & Flow lines |  | 2022-05-25
HAZOP Report For Binak B/C Manifold Extension | BK-SSGRL-PEDCO-110-GE-RT-0004 | BK-SSGRL-PEDCO-110-GE-RT-0004HAZOP Report For Binak B/C Manifold Extension |  | 2022-05-25
SIL Report For Binak B/C Manifold Extension | BK-SSGRL-PEDCO-110-GE-RT-0005 | BK-SSGRL-PEDCO-110-GE-RT-0005SIL Report For Binak B/C Manifold Extension |  | 2022-05-25
Drainage Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0001 | BK-SSGRL-PEDCO-110-PR-PH-0001Drainage Philosophy | 2022-03-26 | 2022-05-10
Control Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0002 | BK-SSGRL-PEDCO-110-PR-PH-0002Control Philosophy | 2022-05-09 | 2022-05-25
Flare,Blow Down And Relief Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0003 | BK-SSGRL-PEDCO-110-PR-PH-0003Flare,Blow Down And Relief Philosophy | 2022-03-26 | 2022-05-10
Isolation Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0004 | BK-SSGRL-PEDCO-110-PR-PH-0004Isolation Philosophy | 2021-11-21 | 2022-05-25
ESD Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0005 | BK-SSGRL-PEDCO-110-PR-PH-0005ESD Philosophy | 2022-05-09 | 2022-05-25
Symbol & Legend For PFD and P&ID | BK-SSGRL-PEDCO-110-PR-PI-0001 | BK-SSGRL-PEDCO-110-PR-PI-0001Symbol & Legend For PFD and P&ID | 2021-10-30 | 2022-05-25
Consumption List | BK-SSGRL-PEDCO-110-PR-LI-0001 | BK-SSGRL-PEDCO-110-PR-LI-0001Consumption List | 2022-02-23 | 2022-05-25
Data Sheets For FUEL Oil Storage Drum of Well Pads | BK-SSGRL-PEDCO-110-ME-DT-0001 | BK-SSGRL-PEDCO-110-ME-DT-0001Data Sheets For FUEL Oil Storage Drum of Well Pads | 2022-01-16 | 2022-05-25
Data Sheets For Potable Water Tank of Well Pads | BK-SSGRL-PEDCO-110-ME-DT-0002 | BK-SSGRL-PEDCO-110-ME-DT-0002Data Sheets For Potable Water Tank of Well Pads | 2022-02-09 | 2022-05-25
Piping Material Specification | BK-SSGRL-PEDCO-110-PI-SP-0001 | BK-SSGRL-PEDCO-110-PI-SP-0001Piping Material Specification | 2021-11-28 | 2022-05-25
Data Sheets For Stone Trap | BK-SSGRL-PEDCO-110-PI-DT-0001 | BK-SSGRL-PEDCO-110-PI-DT-0001Data Sheets For Stone Trap | 2021-12-27 | 2022-05-25
Standard Pipe Support Drawings | BK-SSGRL-PEDCO-110-PI-DW-0001 | BK-SSGRL-PEDCO-110-PI-DW-0001Standard Pipe Support Drawings | 2022-02-19 | 2022-02-19
Piping Assembly Drawing | BK-SSGRL-PEDCO-110-PI-DW-0002 | BK-SSGRL-PEDCO-110-PI-DW-0002Piping Assembly Drawing |  | 2022-05-25
Piping Hydrostatic Test Diagram - Sub Surface | BK-SSGRL-PEDCO-110-PI-DW-0003 | BK-SSGRL-PEDCO-110-PI-DW-0003Piping Hydrostatic Test Diagram - Sub Surface |  | 2022-05-25
Piping Wall Thickness Calculation | BK-SSGRL-PEDCO-110-PI-CN-0001 | BK-SSGRL-PEDCO-110-PI-CN-0001Piping Wall Thickness Calculation | 2021-11-28 | 2022-05-25
Piping Corrosion Study & Material Selection Report | BK-SSGRL-PEDCO-110-PI-RT-0001 | BK-SSGRL-PEDCO-110-PI-RT-0001Piping Corrosion Study & Material Selection Report | 2021-11-28 | 2022-05-25
Pipeline Material Specification | BK-SSGRL-PEDCO-110-PL-SP-0001 | BK-SSGRL-PEDCO-110-PL-SP-0001Pipeline Material Specification | 2021-10-27 | 2022-05-25
Pipeline Standard Support Drawings | BK-SSGRL-PEDCO-110-PL-DW-0001 | BK-SSGRL-PEDCO-110-PL-DW-0001Pipeline Standard Support Drawings | 2021-07-27 | 2022-01-05
Pipeline Hydrostatic Test Diagram - Sub Surface | BK-SSGRL-PEDCO-110-PL-DG-0001 | BK-SSGRL-PEDCO-110-PL-DG-0001Pipeline Hydrostatic Test Diagram - Sub Surface |  | 2022-05-25
Pipeline Wall Thickness Calculation | BK-SSGRL-PEDCO-110-PL-CN-0001 | BK-SSGRL-PEDCO-110-PL-CN-0001Pipeline Wall Thickness Calculation | 2021-10-27 | 2022-05-25
Pipeline Corrosion Study & Material Selection Report | BK-SSGRL-PEDCO-110-PL-RT-0001 | BK-SSGRL-PEDCO-110-PL-RT-0001Pipeline Corrosion Study & Material Selection Report | 2021-10-27 | 2022-05-25
Instrument & Control System Design Criteria | BK-SSGRL-PEDCO-110-IN-DC-0002 | BK-SSGRL-PEDCO-110-IN-DC-0002Instrument & Control System Design Criteria | 2022-01-03 | 2022-05-25
Fire & Gas Detection Design Criteria | BK-SSGRL-PEDCO-110-IN-DC-0001 | BK-SSGRL-PEDCO-110-IN-DC-0001Fire & Gas Detection Design Criteria | 2021-08-14 | 2022-01-01
Instrument & Control System Basis of Design | BK-SSGRL-PEDCO-110-IN-DB-0001 | BK-SSGRL-PEDCO-110-IN-DB-0001Instrument & Control System Basis of Design | 2021-08-22 | 2022-05-25
Specification For WHCP/HPU | BK-SSGRL-PEDCO-110-IN-SP-0001 | BK-SSGRL-PEDCO-110-IN-SP-0001Specification For WHCP/HPU | 2021-08-08 | 2022-03-27
Data Sheets For WHCP/HPU - Wellheads | BK-SSGRL-PEDCO-110-IN-DT-0001 | BK-SSGRL-PEDCO-110-IN-DT-0001Data Sheets For WHCP/HPU - Wellheads | 2021-08-22 | 2022-05-25
Data Sheets For Pressure Gauge - Wellheads | BK-SSGRL-PEDCO-110-IN-DT-0002 | BK-SSGRL-PEDCO-110-IN-DT-0002Data Sheets For Pressure Gauge - Wellheads | 2021-12-07 | 2022-05-25
Data Sheets For Temperature Gauge - Wellheads | BK-SSGRL-PEDCO-110-IN-DT-0003 | BK-SSGRL-PEDCO-110-IN-DT-0003Data Sheets For Temperature Gauge - Wellheads | 2021-12-07 | 2022-05-25
Instrument Hook-up Diagram - Wellheads | BK-SSGRL-PEDCO-110-IN-DG-0001 | BK-SSGRL-PEDCO-110-IN-DG-0001Instrument Hook-up Diagram - Wellheads | 2021-11-14 | 2022-05-25
WHCP HYDRAULIC\PNEUMATIC DIAGRAMS-WELLHEADS | BK-SSGRL-PEDCO-110-IN-DG-0002 | BK-SSGRL-PEDCO-110-IN-DG-0002WHCP HYDRAULIC\PNEUMATIC DIAGRAMS-WELLHEADS | 2021-08-22 | 2021-12-20
Instrument Index For New Wells & Manifold Extension | BK-SSGRL-PEDCO-110-IN-LI-0001 | BK-SSGRL-PEDCO-110-IN-LI-0001Instrument Index For New Wells & Manifold Extension | 2021-11-10 | 2022-05-25
Active Fire Protection and Safety Concept | BK-SSGRL-PEDCO-110-SA-DC-0001 | BK-SSGRL-PEDCO-110-SA-DC-0001Active Fire Protection and Safety Concept | 2021-08-29 | 2021-12-06
Data Sheets For Fire Fighting Equipment | BK-SSGRL-PEDCO-110-SA-DT-0001 | BK-SSGRL-PEDCO-110-SA-DT-0001Data Sheets For Fire Fighting Equipment | 2021-12-08 | 2022-04-06
Data Sheets For Safety Equipment | BK-SSGRL-PEDCO-110-SA-DT-0002 | BK-SSGRL-PEDCO-110-SA-DT-0002Data Sheets For Safety Equipment | 2021-12-08 | 2022-01-09
Data Sheets For Safety Sign | BK-SSGRL-PEDCO-110-SA-DT-0003 | BK-SSGRL-PEDCO-110-SA-DT-0003Data Sheets For Safety Sign | 2021-12-08 | 2022-01-09
Calculation Note For Lighting System of Well Pads Switchgear Building | BK-SSGRL-PEDCO-110-EL-CN-0002 | BK-SSGRL-PEDCO-110-EL-CN-0002Calculation Note For Lighting System of Well Pads Switchgear Building | 2022-05-11 | 2022-05-25
Calculation Note For Lighting System of Well Pads Security Building | BK-SSGRL-PEDCO-110-EL-CN-0003 | BK-SSGRL-PEDCO-110-EL-CN-0003Calculation Note For Lighting System of Well Pads Security Building | 2022-04-30 | 2022-05-25
Calculation Note For Lighting System of Well Pads Area | BK-SSGRL-PEDCO-110-EL-CN-0004 | BK-SSGRL-PEDCO-110-EL-CN-0004Calculation Note For Lighting System of Well Pads Area | 2022-05-14 | 2022-05-25
Calculation Note For Cable Sizing of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0005 | BK-SSGRL-PEDCO-110-EL-CN-0005Calculation Note For Cable Sizing of Well Pads | 2021-11-02 | 2022-05-25
Calculation Note For UPS System of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0006 | BK-SSGRL-PEDCO-110-EL-CN-0006Calculation Note For UPS System of Well Pads |  | 2022-05-25
Calculation Note For Earthing & Lightning System of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0007 | BK-SSGRL-PEDCO-110-EL-CN-0007Calculation Note For Earthing & Lightning System of Well Pads | 2022-05-01 | 2022-05-25
Calculation Note For Diesel Generator Sizing of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0008 | BK-SSGRL-PEDCO-110-EL-CN-0008Calculation Note For Diesel Generator Sizing of Well Pads | 2022-01-26 | 2022-05-25
Calculation Note For DC Charger of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0009 | BK-SSGRL-PEDCO-110-EL-CN-0009Calculation Note For DC Charger of Well Pads | 2022-01-26 | 2022-05-25
Calculation Note For LV Capacitor Bank of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0010 | BK-SSGRL-PEDCO-110-EL-CN-0010Calculation Note For LV Capacitor Bank of Well Pads | 2022-01-29 | 2022-05-25
Calculation Note For 11 KV Over Head Line Sag and Tension | BK-SSGRL-PEDCO-110-EL-CN-0011 | BK-SSGRL-PEDCO-110-EL-CN-0011Calculation Note For 11 KV Over Head Line Sag and Tension | 2021-10-13 | 2022-05-25
Calculation Note For 33 KV Over Head Line Sag and Tension | BK-SSGRL-PEDCO-110-EL-CN-0012 | BK-SSGRL-PEDCO-110-EL-CN-0012Calculation Note For 33 KV Over Head Line Sag and Tension | 2021-10-11 | 2022-05-25
Data Sheets For UPS of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0002 | BK-SSGRL-PEDCO-110-EL-DT-0002Data Sheets For UPS of Well Pads |  | 2022-05-25
Data Sheets For DC Charger of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0003 | BK-SSGRL-PEDCO-110-EL-DT-0003Data Sheets For DC Charger of Well Pads | 2022-01-29 | 2022-05-25
Data Sheets For Diesel Generator of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0004 | BK-SSGRL-PEDCO-110-EL-DT-0004Data Sheets For Diesel Generator of Well Pads | 2021-09-20 | 2022-05-25
Data Sheets For Local Control Stations (LCS) of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0005 | BK-SSGRL-PEDCO-110-EL-DT-0005Data Sheets For Local Control Stations (LCS) of Well Pads | 2021-08-30 | 2022-05-25
Data Sheets For LV Capacitor Bank of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0006 | BK-SSGRL-PEDCO-110-EL-DT-0006Data Sheets For LV Capacitor Bank of Well Pads | 2021-09-12 | 2022-05-25
Data Sheets For LV Switchgear of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0008 | BK-SSGRL-PEDCO-110-EL-DT-0008Data Sheets For LV Switchgear of Well Pads | 2022-02-19 | 2022-05-25
Data Sheets For Power & Control Cables of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0009 | BK-SSGRL-PEDCO-110-EL-DT-0009Data Sheets For Power & Control Cables of Well Pads | 2021-09-13 | 2022-05-25
Data Sheets For Power Transformers of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0010 | BK-SSGRL-PEDCO-110-EL-DT-0010Data Sheets For Power Transformers of Well Pads | 2021-09-15 | 2022-05-25
Data Sheets For Distribution & Lighting Panels of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0011 | BK-SSGRL-PEDCO-110-EL-DT-0011Data Sheets For Distribution & Lighting Panels of Well Pads | 2021-09-12 | 2022-05-25
Data Sheets For 11 KV Over Head Line Equipment | BK-SSGRL-PEDCO-110-EL-DT-0012 | BK-SSGRL-PEDCO-110-EL-DT-0012Data Sheets For 11 KV Over Head Line Equipment | 2021-11-10 | 2022-05-25
Data Sheets For 33 KV Over Head Line Equipment | BK-SSGRL-PEDCO-110-EL-DT-0013 | BK-SSGRL-PEDCO-110-EL-DT-0013Data Sheets For 33 KV Over Head Line Equipment | 2021-11-10 | 2022-05-25
Typical Installation Details For Over Head Line Equipment | BK-SSGRL-PEDCO-110-EL-DW-0001 | BK-SSGRL-PEDCO-110-EL-DW-0001Typical Installation Details For Over Head Line Equipment | 2021-08-22 | 2021-11-07
Installation Detail & Notes for Connection OHL to Gantries for Wells | BK-SSGRL-PEDCO-110-EL-DW-0002 | BK-SSGRL-PEDCO-110-EL-DW-0002Installation Detail & Notes for Connection OHL to Gantries for Wells | 2022-03-06 | 2022-05-25
Electrical Typical Schematic Diagrams For LV Panels of Well Pads | BK-SSGRL-PEDCO-110-EL-DG-0001 | BK-SSGRL-PEDCO-110-EL-DG-0001Electrical Typical Schematic Diagrams For LV Panels of Well Pads | 2021-08-30 | 2022-05-21
Control Logic Diagram For LV Incomers of Well Pads | BK-SSGRL-PEDCO-110-EL-LD-0001 | BK-SSGRL-PEDCO-110-EL-LD-0001Control Logic Diagram For LV Incomers of Well Pads | 2021-08-30 | 2022-05-25
Earthing Layout For Electrical Tower (Gantry) of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0001 | BK-SSGRL-PEDCO-110-EL-PY-0001Earthing Layout For Electrical Tower (Gantry) of Well Pads |  | 2022-05-25
Cable Route Layout For Electrical Tower (Gantry) of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0002 | BK-SSGRL-PEDCO-110-EL-PY-0002Cable Route Layout For Electrical Tower (Gantry) of Well Pads |  | 2022-05-25
Overall Single Line Diagram of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0001 | BK-SSGRL-PEDCO-110-EL-SL-0001Overall Single Line Diagram of Well Pads | 2022-03-02 | 2022-05-25
Single Line Diagram For LV Switchgear of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0002 | BK-SSGRL-PEDCO-110-EL-SL-0002Single Line Diagram For LV Switchgear of Well Pads | 2022-02-08 | 2022-05-25
Single Line Diagram For LV Power Distribution Panel of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0003 | BK-SSGRL-PEDCO-110-EL-SL-0003Single Line Diagram For LV Power Distribution Panel of Well Pads | 2022-05-14 | 2022-05-25
Single Line Diagram For DC Charger of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0004 | BK-SSGRL-PEDCO-110-EL-SL-0004Single Line Diagram For DC Charger of Well Pads | 2022-02-06 | 2022-05-25
Single Line Diagram For Capacitor Banks of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0005 | BK-SSGRL-PEDCO-110-EL-SL-0005Single Line Diagram For Capacitor Banks of Well Pads | 2022-02-02 | 2022-05-25
Interconnection Wiring Diagram of Well Pads | BK-SSGRL-PEDCO-110-EL-DG-0002 | BK-SSGRL-PEDCO-110-EL-DG-0002Interconnection Wiring Diagram of Well Pads |  | 2022-05-25
Area Lighting & Small Power Layout of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0003 | BK-SSGRL-PEDCO-110-EL-PY-0003Area Lighting & Small Power Layout of Well Pads | 2022-05-14 | 2022-05-25
Lighting & Small Power Layout For Switchgear Building of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0004 | BK-SSGRL-PEDCO-110-EL-PY-0004Lighting & Small Power Layout For Switchgear Building of Well Pads | 2022-05-11 | 2022-05-25
Lighting & Small Power Layout For Security Building of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0005 | BK-SSGRL-PEDCO-110-EL-PY-0005Lighting & Small Power Layout For Security Building of Well Pads | 2022-05-07 | 2022-05-25
Area Electrical Cable Route & Section Layout of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0006 | BK-SSGRL-PEDCO-110-EL-PY-0006Area Electrical Cable Route & Section Layout of Well Pads |  | 2022-05-25
Electrical Cable Route & Section Layout For Switchgear Building of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0007 | BK-SSGRL-PEDCO-110-EL-PY-0007Electrical Cable Route & Section Layout For Switchgear Building of Well Pads |  | 2022-05-25
Electrical Equipment Arrangement Layout For Switchgear Building of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0008 | BK-SSGRL-PEDCO-110-EL-PY-0008Electrical Equipment Arrangement Layout For Switchgear Building of Well Pads | 2022-05-23 | 2022-05-25
Earthing & Lightning Layout for well pads | BK-SSGRL-PEDCO-110-EL-PY-0010 | BK-SSGRL-PEDCO-110-EL-PY-0010Earthing & Lightning Layout for well pads |  | 2022-05-25
Electrical Load List of Well Pads | BK-SSGRL-PEDCO-110-EL-LI-0001 | BK-SSGRL-PEDCO-110-EL-LI-0001Electrical Load List of Well Pads | 2022-01-25 | 2022-05-25
Electrical Power & Control Cable List of Well Pads | BK-SSGRL-PEDCO-110-EL-LI-0002 | BK-SSGRL-PEDCO-110-EL-LI-0002Electrical Power & Control Cable List of Well Pads |  | 2022-05-25
Cable Drum Schedule and Cutting List of Well Pads | BK-SSGRL-PEDCO-110-EL-LI-0003 | BK-SSGRL-PEDCO-110-EL-LI-0003Cable Drum Schedule and Cutting List of Well Pads |  | 2022-05-25
Electrical Network (Load Flow, Motor Starting & Short Circuit) Study Report of Well Pads | BK-SSGRL-PEDCO-110-EL-RT-0002 | BK-SSGRL-PEDCO-110-EL-RT-0002Electrical Network (Load Flow, Motor Starting & Short Circuit) Study Report of Well Pads |  | 2022-05-25
Relay Coordination & Setting Study Report of Well Pads | BK-SSGRL-PEDCO-110-EL-RT-0003 | BK-SSGRL-PEDCO-110-EL-RT-0003Relay Coordination & Setting Study Report of Well Pads |  | 2022-05-25
11KV Over Head Line Study Report | BK-SSGRL-PEDCO-110-EL-RT-0004 | BK-SSGRL-PEDCO-110-EL-RT-000411KV Over Head Line Study Report | 2022-03-29 | 2022-05-25
33KV Over Head Line Study Report | BK-SSGRL-PEDCO-110-EL-RT-0005 | BK-SSGRL-PEDCO-110-EL-RT-000533KV Over Head Line Study Report | 2022-03-29 | 2022-05-25
BINAK Oil Field Project Overall Well Location/Facilities Layout | BK-SSGRL-PEDCO-110-CV-PY-0001 | BK-SSGRL-PEDCO-110-CV-PY-0001BINAK Oil Field Project Overall Well Location/Facilities Layout | 2022-04-06 | 2022-05-25
Calculation Note For Flood Control | BK-SSGRL-PEDCO-110-CV-CN-0001 | BK-SSGRL-PEDCO-110-CV-CN-0001Calculation Note For Flood Control | 2021-12-05 | 2022-05-25
Typical Drawing For Rig Foundation Plan & Details | BK-SSGRL-PEDCO-110-ST-DW-0003 | BK-SSGRL-PEDCO-110-ST-DW-0003Typical Drawing For Rig Foundation Plan & Details
Geotechnical Investigation Plan for Well Pads | BK-SSGRL-PEDCO-110-GT-PR-0001 | BK-SSGRL-PEDCO-110-GT-PR-0001Geotechnical Investigation Plan for Well Pads | 2021-08-11 | 2021-10-25
Process Flow Diagram - W018S | BK-W018S-PEDCO-110-PR-PF-0001 | BK-W018S-PEDCO-110-PR-PF-0001Process Flow Diagram - W018S | 2021-08-04 | 2022-05-25
P&ID - W018S | BK-W018S-PEDCO-110-PR-PI-0001 | BK-W018S-PEDCO-110-PR-PI-0001P&ID - W018S | 2021-08-09 | 2022-05-25
Line List - W018S | BK-W018S-PEDCO-110-PR-LI-0001 | BK-W018S-PEDCO-110-PR-LI-0001Line List - W018S | 2021-08-09 | 2022-05-25
Flow line Hydraulic Calculation Report | BK-W018S-PEDCO-110-PR-RT-0001 | BK-W018S-PEDCO-110-PR-RT-0001Flow line Hydraulic Calculation Report | 2021-10-30 | 2022-05-25
Process Data Sheets For Instrument Devices - W018S | BK-W018S-PEDCO-110-PR-DT-0001 | BK-W018S-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - W018S | 2022-04-12 | 2022-05-25
Plot Plan Drawing - W018S | BK-W018S-PEDCO-110-PI-PY-0001 | BK-W018S-PEDCO-110-PI-PY-0001Plot Plan Drawing - W018S | 2021-08-22 | 2022-05-25
Piping Plan - W018S | BK-W018S-PEDCO-110-PI-DW-0001 | BK-W018S-PEDCO-110-PI-DW-0001Piping Plan - W018S |  | 2022-05-25
Isometric Drawings - W018S | BK-W018S-PEDCO-110-PI-DW-0002 | BK-W018S-PEDCO-110-PI-DW-0002Isometric Drawings - W018S |  | 2022-05-25
Material Flow Diagram - W018S | BK-W018S-PEDCO-110-PI-DG-0001 | BK-W018S-PEDCO-110-PI-DG-0001Material Flow Diagram - W018S | 2021-11-08 | 2022-05-25
Piping Support List - W018S | BK-W018S-PEDCO-110-PI-LI-0001 | BK-W018S-PEDCO-110-PI-LI-0001Piping Support List - W018S |  | 2022-05-25
Critical Line List - W018S | BK-W018S-PEDCO-110-PI-LI-0002 | BK-W018S-PEDCO-110-PI-LI-0002Critical Line List - W018S | 2022-04-27 | 2022-05-25
PDMS Model Review Report (60%) - W018S | BK-W018S-PEDCO-110-PI-RT-0001 | BK-W018S-PEDCO-110-PI-RT-0001PDMS Model Review Report (60%) - W018S | 2022-04-04 | 2022-05-25
PDMS Model Review Report (90%) - W018S | BK-W018S-PEDCO-110-PI-RT-0002 | BK-W018S-PEDCO-110-PI-RT-0002PDMS Model Review Report (90%) - W018S |  | 2022-05-25
MTO For Pipes - W018S | BK-W018S-PEDCO-110-PI-MT-0001 | BK-W018S-PEDCO-110-PI-MT-0001MTO For Pipes - W018S | 2021-12-04 | 2022-04-17
MTO For Fittings - W018S | BK-W018S-PEDCO-110-PI-MT-0002 | BK-W018S-PEDCO-110-PI-MT-0002MTO For Fittings - W018S | 2021-12-20 | 2022-04-16
MTO For Flanges - W018S | BK-W018S-PEDCO-110-PI-MT-0003 | BK-W018S-PEDCO-110-PI-MT-0003MTO For Flanges - W018S | 2021-12-20 | 2022-04-16
MTO For Manual Valves - W018S | BK-W018S-PEDCO-110-PI-MT-0004 | BK-W018S-PEDCO-110-PI-MT-0004MTO For Manual Valves - W018S | 2021-12-20 | 2022-04-16
MTO For Gaskets - W018S | BK-W018S-PEDCO-110-PI-MT-0005 | BK-W018S-PEDCO-110-PI-MT-0005MTO For Gaskets - W018S | 2021-12-20 | 2022-04-16
MTO For Bolt & Nuts - W018S | BK-W018S-PEDCO-110-PI-MT-0006 | BK-W018S-PEDCO-110-PI-MT-0006MTO For Bolt & Nuts - W018S | 2021-12-20 | 2022-04-16
Flow line Transversal Drawings - W018S | BK-W018S-PEDCO-110-PL-DW-0002 | BK-W018S-PEDCO-110-PL-DW-0002Flow line Transversal Drawings - W018S |  | 2022-05-25
Road Crossing Location List | BK-W018S-PEDCO-110-PL-LI-0001 | BK-W018S-PEDCO-110-PL-LI-0001Road Crossing Location List |  | 2022-05-25
MTO For Line Pipes (Flow lines) - W018S | BK-W018S-PEDCO-110-PL-MT-0001 | BK-W018S-PEDCO-110-PL-MT-0001MTO For Line Pipes (Flow lines) - W018S | 2021-08-22 | 2021-08-22
Instrument Location Layout Drawing - W018S | BK-W018S-PEDCO-110-IN-PY-0001 | BK-W018S-PEDCO-110-IN-PY-0001Instrument Location Layout Drawing - W018S | 2022-02-23 | 2022-05-25
MTO For Instrument Tube and Fitting - W018S | BK-W018S-PEDCO-110-IN-MT-0001 | BK-W018S-PEDCO-110-IN-MT-0001MTO For Instrument Tube and Fitting - W018S | 2021-11-14 | 2022-01-12
MTO For Instrument Cable Tray - W018S | BK-W018S-PEDCO-110-IN-MT-0002 | BK-W018S-PEDCO-110-IN-MT-0002MTO For Instrument Cable Tray - W018S | 2021-11-14 | 2022-01-12
Hazardous Area Classification Layout - W018S | BK-W018S-PEDCO-110-SA-PY-0001 | BK-W018S-PEDCO-110-SA-PY-0001Hazardous Area Classification Layout - W018S | 2021-11-15 | 2022-05-01
Safety & Fire Fighting Equipment Location Layout - W018S | BK-W018S-PEDCO-110-SA-PY-0002 | BK-W018S-PEDCO-110-SA-PY-0002Safety & Fire Fighting Equipment Location Layout - W018S | 2021-09-07 | 2022-04-19
Escape Route & Safety Sign Layout - W018S | BK-W018S-PEDCO-110-SA-PY-0003 | BK-W018S-PEDCO-110-SA-PY-0003Escape Route & Safety Sign Layout - W018S | 2021-11-15 | 2022-05-16
Hazard Source List - W018S | BK-W018S-PEDCO-110-SA-LI-0001 | BK-W018S-PEDCO-110-SA-LI-0001Hazard Source List - W018S | 2021-11-09 | 2022-05-25
MTO For Fire Fighting & Safety Equipment - W018S | BK-W018S-PEDCO-110-SA-MT-0001 | BK-W018S-PEDCO-110-SA-MT-0001MTO For Fire Fighting & Safety Equipment - W018S | 2021-11-15 | 2021-11-15
MTO For Safety Sign - W018S | BK-W018S-PEDCO-110-SA-MT-0002 | BK-W018S-PEDCO-110-SA-MT-0002MTO For Safety Sign - W018S | 2021-11-15 | 2021-11-15
Architectural Drawing For WHCP/HPU Shelter of Well Pads - W018 | BK-W018S-PEDCO-110-AR-DW-0001 | BK-W018S-PEDCO-110-AR-DW-0001Architectural Drawing For WHCP/HPU Shelter of Well Pads - W018 | 2022-02-21 | 2022-05-25
General Civil Layout - W018S | BK-W018S-PEDCO-110-CV-PY-0001 | BK-W018S-PEDCO-110-CV-PY-0001General Civil Layout - W018S | 2021-07-28 | 2021-12-27
Civil and Structural drawings - W018S | BK-W018S-PEDCO-110-CV-PY-0002 | BK-W018S-PEDCO-110-CV-PY-0002Civil and Structural drawings - W018S | 2021-07-28 | 2022-03-05
Rough Grading Plans -W018S | BK-W018S-PEDCO-110-CV-DW-0001 | BK-W018S-PEDCO-110-CV-DW-0001Rough Grading Plans -W018S | 2021-07-28 | 2022-03-13
Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W018S | BK-W018S-PEDCO-110-CV-CN-0001 | BK-W018S-PEDCO-110-CV-CN-0001Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W018S | 2022-02-19 | 2022-05-25
MTO For Civil Works - W018S | BK-W018S-PEDCO-110-CV-MT-0001 | BK-W018S-PEDCO-110-CV-MT-0001MTO For Civil Works - W018S | 2022-05-15 | 2022-05-15
Structure Drawing For WHCP/HPU Shelter - W018S | BK-W018S-PEDCO-110-ST-DW-0001 | BK-W018S-PEDCO-110-ST-DW-0001Structure Drawing For WHCP/HPU Shelter - W018S | 2022-03-27 | T-0961
Platform Structure Drawing - W018S | BK-W018S-PEDCO-110-ST-DW-0002 | BK-W018S-PEDCO-110-ST-DW-0002Platform Structure Drawing - W018S | 2022-02-02 | 2022-05-25
CALCULATION NOTE WHCP/ HPU SHELTER | BK-W018S-PEDCO-110-ST-CN-0003 | BK-W018S-PEDCO-110-ST-CN-0003 CALCULATION NOTE WHCP/ HPU SHELTER | 2022-05-01 | T-0961
MTO For Structural Works - W018S | BK-W018S-PEDCO-110-ST-MT-0001 | BK-W018S-PEDCO-110-ST-MT-0001MTO For Structural Works - W018S | 2022-05-02 | 2022-05-02
Geotechnical Investigation Report - W018S | BK-W018S-PEDCO-110-GT-RT-0001 | BK-W018S-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - W018S | 2022-02-26 | 2022-05-25
Flow line Plan & Profile Drawings - W018S | BK-W018S-PEDCO-110-SU-DW-0001 | BK-W018S-PEDCO-110-SU-DW-0001Flow line Plan & Profile Drawings - W018S | 2022-02-26 | 2022-05-25
PMR For Pipes - W018S | BK-W018S-PEDCO-110-PI-MR-0001 | BK-W018S-PEDCO-110-PI-MR-0001PMR For Pipes - W018S | 2021-12-06 | 2021-12-06
TBE For Pipes - W018S | BK-W018S-PEDCO-110-PI-TB-0001 | BK-W018S-PEDCO-110-PI-TB-0001TBE For Pipes - W018S |  | 2022-05-25
PMR For Fittings - W018S | BK-W018S-PEDCO-110-PI-MR-0002 | BK-W018S-PEDCO-110-PI-MR-0002PMR For Fittings - W018S | 2022-04-16 | 2022-04-16
TBE For Fitting - W018S | BK-W018S-PEDCO-110-PI-TB-0002 | BK-W018S-PEDCO-110-PI-TB-0002TBE For Fitting - W018S |  | 2022-05-25
PMR For Flanges - W018S | BK-W018S-PEDCO-110-PI-MR-0003 | BK-W018S-PEDCO-110-PI-MR-0003PMR For Flanges - W018S | 2022-04-16 | 2022-04-16
TBE For Flanges - W018S | BK-W018S-PEDCO-110-PI-TB-0003 | BK-W018S-PEDCO-110-PI-TB-0003TBE For Flanges - W018S | 2022-02-13 | 2022-02-13
PMR For Manual Valves - W018S | BK-W018S-PEDCO-110-PI-MR-0004 | BK-W018S-PEDCO-110-PI-MR-0004PMR For Manual Valves - W018S | 2022-04-16 | 2022-04-16
TBE For Manual Valves - W018S | BK-W018S-PEDCO-110-PI-TB-0004 | BK-W018S-PEDCO-110-PI-TB-0004TBE For Manual Valves - W018S | 2022-02-13 | 2022-02-13
PMR For Gaskets - W018S | BK-W018S-PEDCO-110-PI-MR-0005 | BK-W018S-PEDCO-110-PI-MR-0005PMR For Gaskets - W018S | 2022-04-16 | 2022-04-16
TBE For Gaskets - W018S | BK-W018S-PEDCO-110-PI-TB-0005 | BK-W018S-PEDCO-110-PI-TB-0005TBE For Gaskets - W018S | 2022-02-13 | 2022-02-13
PMR For Bolt/Nuts - W018S | BK-W018S-PEDCO-110-PI-MR-0006 | BK-W018S-PEDCO-110-PI-MR-0006PMR For Bolt/Nuts - W018S | 2022-04-16 | 2022-04-16
TBE For Bolt/Nuts - W018S | BK-W018S-PEDCO-110-PI-TB-0006 | BK-W018S-PEDCO-110-PI-TB-0006TBE For Bolt/Nuts - W018S |  | 2022-05-25
PMR For Sampling Connection Set - W018S | BK-W018S-PEDCO-110-PI-MR-0007 | BK-W018S-PEDCO-110-PI-MR-0007PMR For Sampling Connection Set - W018S | 2022-02-20 | 2022-02-20
TBE For Sampling Connection | BK-W018S-PEDCO-110-PI-TB-0007 | BK-W018S-PEDCO-110-PI-TB-0007TBE For Sampling Connection |  | 2022-05-25
PMR For Stone Trap - W018S | BK-W018S-PEDCO-110-PI-MR-0008 | BK-W018S-PEDCO-110-PI-MR-0008PMR For Stone Trap - W018S | 2022-04-27 | 2022-04-27
TBE For Stone Trap - W018S | BK-W018S-PEDCO-110-PI-TB-0008 | BK-W018S-PEDCO-110-PI-TB-0008TBE For Stone Trap - W018S | 2022-05-24 | 2022-05-24
PMR For Pipe Support - W018S | BK-W018S-PEDCO-110-PI-MR-0010 | BK-W018S-PEDCO-110-PI-MR-0010PMR For Pipe Support - W018S |  | 2022-05-25
TBE For Pipe Support - W018S | BK-W018S-PEDCO-110-PI-TB-0010 | BK-W018S-PEDCO-110-PI-TB-0010TBE For Pipe Support - W018S |  | 2022-05-25
PMR For Line Pipes - W018S | BK-W018S-PEDCO-110-PL-MR-0001 | BK-W018S-PEDCO-110-PL-MR-0001PMR For Line Pipes - W018S | 2021-12-06 | 2021-12-15
TBE For Line Pipes - W018S | BK-W018S-PEDCO-110-PL-TB-0001 | BK-W018S-PEDCO-110-PL-TB-0001TBE For Line Pipes - W018S | 2022-02-19 | 2022-05-14
PMR For Flow Line Support - W018S | BK-W018S-PEDCO-110-PL-MR-0002 | BK-W018S-PEDCO-110-PL-MR-0002PMR For Flow Line Support - W018S |  | 2022-05-25
TBE For Flow Line Support - W018S | BK-W018S-PEDCO-110-PL-TB-0002 | BK-W018S-PEDCO-110-PL-TB-0002TBE For Flow Line Support - W018S |  | 2022-05-25
PMR For WHCP/HPU - W018S | BK-W018S-PEDCO-110-IN-MR-0001 | BK-W018S-PEDCO-110-IN-MR-0001PMR For WHCP/HPU - W018S | 2021-11-15 | 2022-01-16
TBE/TBA For WHCP/HPU - W018S | BK-W018S-PEDCO-110-IN-TB-0001 | BK-W018S-PEDCO-110-IN-TB-0001TBE/TBA For WHCP/HPU - W018S | 2021-11-30 | 2022-02-19
PMR For Field Instrumentations - W018S | BK-W018S-PEDCO-110-IN-MR-0002 | BK-W018S-PEDCO-110-IN-MR-0002PMR For Field Instrumentations - W018S | 2021-12-13 | 2021-12-13
TBE/TBA For Field Instrumentations - W018S | BK-W018S-PEDCO-110-IN-TB-0002 | BK-W018S-PEDCO-110-IN-TB-0002TBE/TBA For Field Instrumentations - W018S |  | 2022-05-25
PMR For Instrument Bulk Items - W018S | BK-W018S-PEDCO-110-IN-MR-0003 | BK-W018S-PEDCO-110-IN-MR-0003PMR For Instrument Bulk Items - W018S | 2022-01-18 | 2022-01-18
TBE/TBA For Instrument Bulk Items - W018S | BK-W018S-PEDCO-110-IN-TB-0003 | BK-W018S-PEDCO-110-IN-TB-0003TBE/TBA For Instrument Bulk Items - W018S | 2022-02-02 | 2022-02-02
PMR For Fire Fighting and Safety Equipment - W018S | BK-W018S-PEDCO-110-SA-MR-0001 | BK-W018S-PEDCO-110-SA-MR-0001PMR For Fire Fighting and Safety Equipment - W018S | 2021-12-08 | 2022-05-11
TBE For Fire Fighting and Safety Equipment - W018S | BK-W018S-PEDCO-110-SA-TB-0001 | BK-W018S-PEDCO-110-SA-TB-0001TBE For Fire Fighting and Safety Equipment - W018S | 2022-03-12 | 2022-03-12
PMR For Fire Safety Sign - W018S | BK-W018S-PEDCO-110-SA-MR-0002 | BK-W018S-PEDCO-110-SA-MR-0002PMR For Fire Safety Sign - W018S | 2021-12-08 | 2021-12-08
TBE For Fire Safety Sign - W018S | BK-W018S-PEDCO-110-SA-TB-0002 | BK-W018S-PEDCO-110-SA-TB-0002TBE For Fire Safety Sign - W018S | 2022-03-12 | 2022-03-12
PMR For Steel Structure Items - W018S | BK-W018S-PEDCO-110-ST-MR-0001 | BK-W018S-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - W018S |  | 2022-05-25
TBE For Steel Structure Items - W018S | BK-W018S-PEDCO-110-ST-TB-0001 | BK-W018S-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - W018S |  | 2022-05-25
PMR For Anchor Bolts - W018S | BK-W018S-PEDCO-110-ST-MR-0002 | BK-W018S-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - W018S |  | 2022-05-25
TBE For Anchor Bolts - W018S | BK-W018S-PEDCO-110-ST-TB-0002 | BK-W018S-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - W018S |  | 2022-05-25
PMR For Geomembrane - W018S | BK-W018S-PEDCO-110-CV-MR-0001 | BK-W018S-PEDCO-110-CV-MR-0001PMR For Geomembrane - W018S | 2022-04-03 | 2022-04-03
TBE For Geomembrane - W018S | BK-W018S-PEDCO-110-CV-TB-0001 | BK-W018S-PEDCO-110-CV-TB-0001TBE For Geomembrane - W018S |  | 2022-05-25
PMR For Geotextile - W018S | BK-W018S-PEDCO-110-CV-MR-0002 | BK-W018S-PEDCO-110-CV-MR-0002PMR For Geotextile - W018S | 2022-04-03 | 2022-04-03
TBE For Geotextile - W018S | BK-W018S-PEDCO-110-CV-TB-0002 | BK-W018S-PEDCO-110-CV-TB-0002TBE For Geotextile - W018S |  | 2022-05-25
Pre-Commissioning, Commissioning & Startup Procedure - W018S | BK-W018S-PEDCO-110-CO-PR-0001 | BK-W018S-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - W018S |  | 2022-05-25
Technical/Site Queries | BK-W018S-PEDCO-110-GE-TQ-0001 | BK-W018S-PEDCO-110-GE-TQ-0001Technical/Site Queries |  | 2022-05-25
As-Built Document Booklets - W018S | BK-W018S-PEDCO-110-GE-DO-0001 | BK-W018S-PEDCO-110-GE-DO-0001As-Built Document Booklets - W018S |  | 2022-05-25
Operating Manual - W018S | BK-W018S-PEDCO-110-GE-ML-0001 | BK-W018S-PEDCO-110-GE-ML-0001Operating Manual - W018S |  | 2022-05-25
As-Built Document Booklets - W018S | BK-W018S-PEDCO-110-GE-DO-0001 | BK-W018S-PEDCO-110-GE-DO-0001As-Built Document Booklets - W018S |  | 2022-05-25
Final Engineering Dossier - W018S | BK-W018S-PEDCO-110-GE-DO-0002 | BK-W018S-PEDCO-110-GE-DO-0002Final Engineering Dossier - W018S |  | 2022-05-25
Process Flow Diagram - W028 | BK-W028-PEDCO-110-PR-PF-0001 | BK-W028-PEDCO-110-PR-PF-0001Process Flow Diagram - W028 | 2021-08-14 | 2022-05-25
P&ID - W028 | BK-W028-PEDCO-110-PR-PI-0001 | BK-W028-PEDCO-110-PR-PI-0001P&ID - W028 | 2021-08-22 | 2022-05-25
Line List - W028 | BK-W028-PEDCO-110-PR-LI-0001 | BK-W028-PEDCO-110-PR-LI-0001Line List - W028 | 2021-08-22 | 2022-05-25
Flow line Hydraulic Calculation Report | BK-W028-PEDCO-110-PR-RT-0001 | BK-W028-PEDCO-110-PR-RT-0001Flow line Hydraulic Calculation Report | 2021-10-30 | 2022-05-25
Process Data Sheets For Instrument Devices - W028 | BK-W028-PEDCO-110-PR-DT-0001 | BK-W028-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - W028 | 2022-04-12 | 2022-05-25
Plot Plan Drawing - W028 | BK-W028-PEDCO-110-PI-DW-0001 | BK-W028-PEDCO-110-PI-DW-0001Plot Plan Drawing - W028 | 2022-02-02 | 2022-05-25
Piping Plan - W028 | BK-W028-PEDCO-110-PI-DW-0002 | BK-W028-PEDCO-110-PI-DW-0002Piping Plan - W028 |  | 2022-05-25
Isometric Drawings - W028 | BK-W028-PEDCO-110-PI-DW-0003 | BK-W028-PEDCO-110-PI-DW-0003Isometric Drawings - W028 |  | 2022-05-25
Material Flow Diagram - W028 | BK-W028-PEDCO-110-PI-DG-0001 | BK-W028-PEDCO-110-PI-DG-0001Material Flow Diagram - W028 | 2021-11-08 | 2022-05-25
Piping Support List - W028 | BK-W028-PEDCO-110-PI-LI-0001 | BK-W028-PEDCO-110-PI-LI-0001Piping Support List - W028 |  | 2022-05-25
Critical Line List - W028 | BK-W028-PEDCO-110-PI-LI-0002 | BK-W028-PEDCO-110-PI-LI-0002Critical Line List - W028 | 2022-05-02 | 2022-05-25
PDMS Model Review Report (60%) - W028 | BK-W028-PEDCO-110-PI-RT-0001 | BK-W028-PEDCO-110-PI-RT-0001PDMS Model Review Report (60%) - W028 |  | 2022-05-25
PDMS Model Review Report (90%) - W028 | BK-W028-PEDCO-110-PI-RT-0002 | BK-W028-PEDCO-110-PI-RT-0002PDMS Model Review Report (90%) - W028 |  | 2022-05-25
MTO For Pipes - W028 | BK-W028-PEDCO-110-PI-MT-0001 | BK-W028-PEDCO-110-PI-MT-0001MTO For Pipes - W028 | 2021-12-04 | 2022-04-17
MTO For Fittings - W028 | BK-W028-PEDCO-110-PI-MT-0002 | BK-W028-PEDCO-110-PI-MT-0002MTO For Fittings - W028 | 2021-12-20 | 2022-04-16
MTO For Flanges - W028 | BK-W028-PEDCO-110-PI-MT-0003 | BK-W028-PEDCO-110-PI-MT-0003MTO For Flanges - W028 | 2021-12-20 | 2022-04-16
MTO For Manual Valves - W028 | BK-W028-PEDCO-110-PI-MT-0004 | BK-W028-PEDCO-110-PI-MT-0004MTO For Manual Valves - W028 | 2021-12-20 | 2022-04-16
MTO For Gaskets - W028 | BK-W028-PEDCO-110-PI-MT-0005 | BK-W028-PEDCO-110-PI-MT-0005MTO For Gaskets - W028 | 2021-12-20 | 2022-04-16
MTO For Bolt & Nuts - W028 | BK-W028-PEDCO-110-PI-MT-0006 | BK-W028-PEDCO-110-PI-MT-0006MTO For Bolt & Nuts - W028 | 2021-12-20 | 2022-04-16
Flow line Transversal Drawings - W028 | BK-W028-PEDCO-110-PL-DW-0002 | BK-W028-PEDCO-110-PL-DW-0002Flow line Transversal Drawings - W028 |  | 2022-05-25
Road Crossing Location List | BK-W028-PEDCO-110-PL-LI-0001 | BK-W028-PEDCO-110-PL-LI-0001Road Crossing Location List |  | 2022-05-25
MTO For Line Pipes (Flow lines) - W028 | BK-W028-PEDCO-110-PL-MT-0001 | BK-W028-PEDCO-110-PL-MT-0001MTO For Line Pipes (Flow lines) - W028 | 2021-08-22 | 2021-08-22
Instrument Location Layout Drawing - W028 | BK-W028-PEDCO-110-IN-PY-0001 | BK-W028-PEDCO-110-IN-PY-0001Instrument Location Layout Drawing - W028 | 2022-05-16 | 2022-05-25
MTO For Instrument Tube and Fitting - W028 | BK-W028-PEDCO-110-IN-MT-0001 | BK-W028-PEDCO-110-IN-MT-0001MTO For Instrument Tube and Fitting - W028 | 2021-11-14 | 2022-01-12
MTO For Instrument Cable Tray - W028 | BK-W028-PEDCO-110-IN-MT-0002 | BK-W028-PEDCO-110-IN-MT-0002MTO For Instrument Cable Tray - W028 | 2021-11-14 | 2022-01-12
Hazardous Area Classification Layout - W028 | BK-W028-PEDCO-110-SA-PY-0001 | BK-W028-PEDCO-110-SA-PY-0001Hazardous Area Classification Layout - W028 | 2022-05-07 | 2022-05-25
Safety & Fire Fighting Equipment Location Layout - W028 | BK-W028-PEDCO-110-SA-PY-0002 | BK-W028-PEDCO-110-SA-PY-0002Safety & Fire Fighting Equipment Location Layout - W028 | 2022-04-16 | 2022-05-25
Escape Route & Safety Sign Layout - W028 | BK-W028-PEDCO-110-SA-PY-0003 | BK-W028-PEDCO-110-SA-PY-0003Escape Route & Safety Sign Layout - W028 | 2022-04-17 | 2022-05-25
Hazard Source List - W028 | BK-W028-PEDCO-110-SA-LI-0001 | BK-W028-PEDCO-110-SA-LI-0001Hazard Source List - W028 | 2021-11-09 | 2022-05-25
MTO For Fire Fighting & Safety Equipment - W028 | BK-W028-PEDCO-110-SA-MT-0001 | BK-W028-PEDCO-110-SA-MT-0001MTO For Fire Fighting & Safety Equipment - W028 | 2021-12-08 | 2021-12-08
MTO For Safety Sign - W028 | BK-W028-PEDCO-110-SA-MT-0002 | BK-W028-PEDCO-110-SA-MT-0002MTO For Safety Sign - W028 | 2021-12-08 | 2021-12-08
Architectural Drawing For WHCP/HPU Shelter of Well Pads - W028 | BK-W028-PEDCO-110-AR-DW-0001 | BK-W028-PEDCO-110-AR-DW-0001Architectural Drawing For WHCP/HPU Shelter of Well Pads - W028 | 2022-02-26 | 2022-05-25
General Civil Layout -W028 | BK-W028-PEDCO-110-CV-PY-0001 | BK-W028-PEDCO-110-CV-PY-0001General Civil Layout -W028 | 2021-10-19 | 2022-05-25
Civil and Structural drawings -W028 | BK-W028-PEDCO-110-CV-PY-0002 | BK-W028-PEDCO-110-CV-PY-0002Civil and Structural drawings -W028 | 2021-10-19 | 2022-05-25
Rough Grading Plans -W028 | BK-W028-PEDCO-110-CV-DW-0001 | BK-W028-PEDCO-110-CV-DW-0001Rough Grading Plans -W028 | 2021-10-11 | 2022-04-10
Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W028 | BK-W028-PEDCO-110-CV-CN-0001 | BK-W028-PEDCO-110-CV-CN-0001Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W028 | 2021-12-05 | 2022-05-25
MTO For Civil Works - W028 | BK-W028-PEDCO-110-CV-MT-0001 | BK-W028-PEDCO-110-CV-MT-0001MTO For Civil Works - W028 | 2022-05-09 | 2022-05-09
Platform Structure Drawing - W028 | BK-W028-PEDCO-110-ST-DW-0002 | BK-W028-PEDCO-110-ST-DW-0002Platform Structure Drawing - W028 |  | 2022-05-25
MTO For Structural Works - W028 | BK-W028-PEDCO-110-ST-MT-0001 | BK-W028-PEDCO-110-ST-MT-0001MTO For Structural Works - W028 | 2022-05-02 | 2022-05-02
Geotechnical Investigation Report - W028 | BK-W028-PEDCO-110-GT-RT-0001 | BK-W028-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - W028 | 2022-05-17 | 2022-05-25
Flow line Plan & Profile Drawings - W028 | BK-W028-PEDCO-110-SU-DW-0001 | BK-W028-PEDCO-110-SU-DW-0001Flow line Plan & Profile Drawings - W028 |  | 2022-05-25
PMR For Pipes - W028 | BK-W028-PEDCO-110-PI-MR-0001 | BK-W028-PEDCO-110-PI-MR-0001PMR For Pipes - W028 | 2021-12-06 | 2021-12-06
TBE For Pipes - W028 | BK-W028-PEDCO-110-PI-TB-0001 | BK-W028-PEDCO-110-PI-TB-0001TBE For Pipes - W028 |  | 2022-05-25
PMR For Fittings - W028 | BK-W028-PEDCO-110-PI-MR-0002 | BK-W028-PEDCO-110-PI-MR-0002PMR For Fittings - W028 | 2022-04-16 | 2022-04-16
TBE For Fitting - W028 | BK-W028-PEDCO-110-PI-TB-0002 | BK-W028-PEDCO-110-PI-TB-0002TBE For Fitting - W028 |  | 2022-05-25
PMR For Flanges - W028 | BK-W028-PEDCO-110-PI-MR-0003 | BK-W028-PEDCO-110-PI-MR-0003PMR For Flanges - W028 | 2022-04-16 | 2022-04-16
TBE For Flanges - W028 | BK-W028-PEDCO-110-PI-TB-0003 | BK-W028-PEDCO-110-PI-TB-0003TBE For Flanges - W028 | 2022-02-13 | 2022-02-13
PMR For Manual Valves - W028 | BK-W028-PEDCO-110-PI-MR-0004 | BK-W028-PEDCO-110-PI-MR-0004PMR For Manual Valves - W028 | 2022-04-16 | 2022-04-16
TBE For Manual Valves - W028 | BK-W028-PEDCO-110-PI-TB-0004 | BK-W028-PEDCO-110-PI-TB-0004TBE For Manual Valves - W028 | 2022-02-13 | 2022-02-13
PMR For Gaskets - W028 | BK-W028-PEDCO-110-PI-MR-0005 | BK-W028-PEDCO-110-PI-MR-0005PMR For Gaskets - W028 | 2022-04-16 | 2022-04-16
TBE For Gaskets - W028 | BK-W028-PEDCO-110-PI-TB-0005 | BK-W028-PEDCO-110-PI-TB-0005TBE For Gaskets - W028 | 2022-02-13 | 2022-02-13
PMR For Bolt/Nuts - W028 | BK-W028-PEDCO-110-PI-MR-0006 | BK-W028-PEDCO-110-PI-MR-0006PMR For Bolt/Nuts - W028 | 2022-04-16 | 2022-04-16
TBE For Bolt/Nuts - W028 | BK-W028-PEDCO-110-PI-TB-0006 | BK-W028-PEDCO-110-PI-TB-0006TBE For Bolt/Nuts - W028 |  | 2022-05-25
PMR For Sampling Connection Set - W028 | BK-W028-PEDCO-110-PI-MR-0007 | BK-W028-PEDCO-110-PI-MR-0007PMR For Sampling Connection Set - W028 | 2022-02-20 | 2022-02-20
TBE For Sampling Connection Set - W028 | BK-W028-PEDCO-110-PI-TB-0007 | BK-W028-PEDCO-110-PI-TB-0007TBE For Sampling Connection Set - W028 |  | 2022-05-25
PMR For Stone Trap - W028 | BK-W028-PEDCO-110-PI-MR-0008 | BK-W028-PEDCO-110-PI-MR-0008PMR For Stone Trap - W028 | 2022-04-27 | 2022-04-27
TBE For Stone Trap - W028 | BK-W028-PEDCO-110-PI-TB-0008 | BK-W028-PEDCO-110-PI-TB-0008TBE For Stone Trap - W028 | 2022-05-24 | 2022-05-24
PMR For Pipe Support - W028 | BK-W028-PEDCO-110-PI-MR-0009 | BK-W028-PEDCO-110-PI-MR-0009PMR For Pipe Support - W028 |  | 2022-05-25
TBE For Pipe Support - W028 | BK-W028-PEDCO-110-PI-TB-0009 | BK-W028-PEDCO-110-PI-TB-0009TBE For Pipe Support - W028 |  | 2022-05-25
PMR For Line Pipes - W028 | BK-W028-PEDCO-110-PL-MR-0001 | BK-W028-PEDCO-110-PL-MR-0001PMR For Line Pipes - W028 | 2021-12-06 | 2021-12-15
TBE For Line Pipes - W028 | BK-W028-PEDCO-110-PL-TB-0001 | BK-W028-PEDCO-110-PL-TB-0001TBE For Line Pipes - W028 | 2022-02-19 | 2022-05-14
PMR For Flow Line Support - W028 | BK-W028-PEDCO-110-PL-MR-0002 | BK-W028-PEDCO-110-PL-MR-0002PMR For Flow Line Support - W028 |  | 2022-05-25
TBE For Flow Line Support - W028 | BK-W028-PEDCO-110-PL-TB-0002 | BK-W028-PEDCO-110-PL-TB-0002TBE For Flow Line Support - W028 |  | 2022-05-25
PMR For WHCP/HPU - W028 | BK-W028-PEDCO-110-IN-MR-0001 | BK-W028-PEDCO-110-IN-MR-0001PMR For WHCP/HPU - W028 | 2021-11-15 | 2022-01-16
TBE/TBA For WHCP/HPU - W028 | BK-W028-PEDCO-110-IN-TB-0001 | BK-W028-PEDCO-110-IN-TB-0001TBE/TBA For WHCP/HPU - W028 | 2021-12-01 | 2022-02-19
PMR For Field Instrumentations - W028 | BK-W028-PEDCO-110-IN-MR-0002 | BK-W028-PEDCO-110-IN-MR-0002PMR For Field Instrumentations - W028 | 2021-12-13 | 2021-12-13
TBE/TBA For Field Instrumentations - W028 | BK-W028-PEDCO-110-IN-TB-0002 | BK-W028-PEDCO-110-IN-TB-0002TBE/TBA For Field Instrumentations - W028 |  | 2022-05-25
PMR For Instrument Bulk Items - W028 | BK-W028-PEDCO-110-IN-MR-0003 | BK-W028-PEDCO-110-IN-MR-0003PMR For Instrument Bulk Items - W028 | 2022-01-16 | 2022-01-16
TBE/TBA For Instrument Bulk Items - W028 | BK-W028-PEDCO-110-IN-TB-0003 | BK-W028-PEDCO-110-IN-TB-0003TBE/TBA For Instrument Bulk Items - W028 | 2022-02-02 | 2022-02-02
PMR For Fire Fighting and Safety Equipment - W028 | BK-W028-PEDCO-110-SA-MR-0001 | BK-W028-PEDCO-110-SA-MR-0001PMR For Fire Fighting and Safety Equipment - W028 | 2021-12-08 | 2021-12-08
TBE For Fire Fighting and Safety Equipment - W028 | BK-W028-PEDCO-110-SA-TB-0001 | BK-W028-PEDCO-110-SA-TB-0001TBE For Fire Fighting and Safety Equipment - W028 |  | 2022-05-25
PMR For Fire Safety Sign - W028 | BK-W028-PEDCO-110-SA-MR-0002 | BK-W028-PEDCO-110-SA-MR-0002PMR For Fire Safety Sign - W028 | 2021-12-08 | 2021-12-08
TBE For Fire Safety Sign - W028 | BK-W028-PEDCO-110-SA-TB-0002 | BK-W028-PEDCO-110-SA-TB-0002TBE For Fire Safety Sign - W028 |  | 2022-05-25
PMR For Steel Structure Items - W028 | BK-W028-PEDCO-110-ST-MR-0001 | BK-W028-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - W028 |  | 2022-05-25
TBE For Steel Structure Items - W028 | BK-W028-PEDCO-110-ST-TB-0001 | BK-W028-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - W028 |  | 2022-05-25
PMR For Anchor Bolts - W028 | BK-W028-PEDCO-110-ST-MR-0002 | BK-W028-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - W028 |  | 2022-05-25
TBE For Anchor Bolts - W028 | BK-W028-PEDCO-110-ST-TB-0002 | BK-W028-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - W028 |  | 2022-05-25
PMR For Geomembrane - W028 | BK-W028-PEDCO-110-CV-MR-0001 | BK-W028-PEDCO-110-CV-MR-0001PMR For Geomembrane - W028 | 2022-04-13 | 2022-05-22
TBE For Geomembrane - W028 | BK-W028-PEDCO-110-CV-TB-0001 | BK-W028-PEDCO-110-CV-TB-0001TBE For Geomembrane - W028 |  | 2022-05-25
PMR For Geotextile - W028 | BK-W028-PEDCO-110-CV-MR-0002 | BK-W028-PEDCO-110-CV-MR-0002PMR For Geotextile - W028 | 2022-04-13 | 2022-05-22
TBE For Geotextile - W028 | BK-W028-PEDCO-110-CV-TB-0002 | BK-W028-PEDCO-110-CV-TB-0002TBE For Geotextile - W028 |  | 2022-05-25
Pre-Commissioning, Commissioning & Startup Procedure - W028 | BK-W028-PEDCO-110-CO-PR-0001 | BK-W028-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - W028 |  | 2022-05-25
Technical/Site Queries | BK-W028-PEDCO-110-GE-TQ-0001 | BK-W028-PEDCO-110-GE-TQ-0001Technical/Site Queries |  | 2022-05-25
As-Built Document Booklets - W028 | BK-W028-PEDCO-110-GE-DO-0001 | BK-W028-PEDCO-110-GE-DO-0001As-Built Document Booklets - W028 |  | 2022-05-25
Operating Manual - W028 | BK-W028-PEDCO-110-GE-ML-0001 | BK-W028-PEDCO-110-GE-ML-0001Operating Manual - W028 |  | 2022-05-25
As-Built Document Booklets - W028 | BK-W028-PEDCO-110-GE-DO-0001 | BK-W028-PEDCO-110-GE-DO-0001As-Built Document Booklets - W028 |  | 2022-05-25
Final Engineering Dossier - W028 | BK-W028-PEDCO-110-GE-DO-0002 | BK-W028-PEDCO-110-GE-DO-0002Final Engineering Dossier - W028 |  | 2022-05-25
Process Flow Diagram - W0046S | BK-W046S-PEDCO-110-PR-PF-0001 | BK-W046S-PEDCO-110-PR-PF-0001Process Flow Diagram - W0046S | 2021-08-24 | 2022-03-13
P&ID - W0046S | BK-W046S-PEDCO-110-PR-PI-0001 | BK-W046S-PEDCO-110-PR-PI-0001P&ID - W0046S | 2021-08-24 | 2022-05-25
P&ID for Diesel Oil Drum- W0046S | BK-W046S-PEDCO-110-PR-PI-0002 | BK-W046S-PEDCO-110-PR-PI-0002P&ID for Diesel Oil Drum- W0046S | 2021-11-16 | 2022-05-25
P&ID for Potable Water Tank - W0046S | BK-W046S-PEDCO-110-PR-PI-0003 | BK-W046S-PEDCO-110-PR-PI-0003P&ID for Potable Water Tank - W0046S | 2021-11-16 | 2022-05-25
Line List - W0046S | BK-W046S-PEDCO-110-PR-LI-0001 | BK-W046S-PEDCO-110-PR-LI-0001Line List - W0046S | 2021-08-24 | 2022-05-25
Flow line Hydraulic Calculation Report | BK-W046S-PEDCO-110-PR-RT-0001 | BK-W046S-PEDCO-110-PR-RT-0001Flow line Hydraulic Calculation Report | 2021-10-30 | 2022-05-25
Process Data Sheets For Instrument Devices - W046S | BK-W046S-PEDCO-110-PR-DT-0001 | BK-W046S-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - W046S | 2022-04-12 | 2022-05-25
HVAC Calculation Note For Switchgear Building - W046S | BK-W046S-PEDCO-110-HV-CN-0001 | BK-W046S-PEDCO-110-HV-CN-0001HVAC Calculation Note For Switchgear Building - W046S | 2022-03-14 | 2022-05-25
HVAC Calculation Note For Security Building - W046S | BK-W046S-PEDCO-110-HV-CN-0002 | BK-W046S-PEDCO-110-HV-CN-0002HVAC Calculation Note For Security Building - W046S |  | 2022-05-25
Data Sheets For Main HVAC Equipment - W046S | BK-W046S-PEDCO-110-HV-DT-0001 | BK-W046S-PEDCO-110-HV-DT-0001Data Sheets For Main HVAC Equipment - W046S |  | 2022-05-25
HVAC System Layout For Switchgear Building - W046S | BK-W046S-PEDCO-110-HV-PY-0001 | BK-W046S-PEDCO-110-HV-PY-0001HVAC System Layout For Switchgear Building - W046S | 2022-04-19 | 2022-05-25
HVAC System Layout For Security Building - W046S | BK-W046S-PEDCO-110-HV-PY-0002 | BK-W046S-PEDCO-110-HV-PY-0002HVAC System Layout For Security Building - W046S |  | 2022-05-25
Plumbing & Sewage Piping Layout For Switchgear Building - W046S | BK-W046S-PEDCO-110-HV-PY-0003 | BK-W046S-PEDCO-110-HV-PY-0003Plumbing & Sewage Piping Layout For Switchgear Building - W046S |  | 2022-05-25
Plumbing & Sewage Piping Layout For Security Building - W046S | BK-W046S-PEDCO-110-HV-PY-0004 | BK-W046S-PEDCO-110-HV-PY-0004Plumbing & Sewage Piping Layout For Security Building - W046S |  | 2022-05-25
MTO For Building HVAC & Plumbing Systems - W046S | BK-W046S-PEDCO-110-HV-MT-0001 | BK-W046S-PEDCO-110-HV-MT-0001MTO For Building HVAC & Plumbing Systems - W046S |  | 2022-05-25
Plot Plan Drawing - W046S | BK-W046S-PEDCO-110-PI-DW-0001 | BK-W046S-PEDCO-110-PI-DW-0001Plot Plan Drawing - W046S | 2022-05-09 | 2022-05-25
Piping Plan - W046S | BK-W046S-PEDCO-110-PI-DW-0002 | BK-W046S-PEDCO-110-PI-DW-0002Piping Plan - W046S |  | 2022-05-25
Isometric Drawings - W046S | BK-W046S-PEDCO-110-PI-DW-0003 | BK-W046S-PEDCO-110-PI-DW-0003Isometric Drawings - W046S |  | 2022-05-25
Material Flow Diagram - W046S | BK-W046S-PEDCO-110-PI-DG-0001 | BK-W046S-PEDCO-110-PI-DG-0001Material Flow Diagram - W046S | 2021-11-08 | 2022-05-25
Piping Support List - W046S | BK-W046S-PEDCO-110-PI-LI-0001 | BK-W046S-PEDCO-110-PI-LI-0001Piping Support List - W046S |  | 2022-05-25
Critical Line List - W046S | BK-W046S-PEDCO-110-PI-LI-0002 | BK-W046S-PEDCO-110-PI-LI-0002Critical Line List - W046S |  | 2022-05-25
PDMS Model Review Report (30%) - W046S | BK-W046S-PEDCO-110-PI-RT-0001 | BK-W046S-PEDCO-110-PI-RT-0001PDMS Model Review Report (30%) - W046S |  | 2022-05-25
PDMS Model Review Report (60%) - W046S | BK-W046S-PEDCO-110-PI-RT-0002 | BK-W046S-PEDCO-110-PI-RT-0002PDMS Model Review Report (60%) - W046S |  | 2022-05-25
PDMS Model Review Report (90%) - W046S | BK-W046S-PEDCO-110-PI-RT-0003 | BK-W046S-PEDCO-110-PI-RT-0003PDMS Model Review Report (90%) - W046S |  | 2022-05-25
MTO For Pipes - W046S | BK-W046S-PEDCO-110-PI-MT-0001 | BK-W046S-PEDCO-110-PI-MT-0001MTO For Pipes - W046S |  | 2022-05-25
MTO For Fittings - W046S | BK-W046S-PEDCO-110-PI-MT-0002 | BK-W046S-PEDCO-110-PI-MT-0002MTO For Fittings - W046S |  | 2022-05-25
MTO For Flanges - W046S | BK-W046S-PEDCO-110-PI-MT-0003 | BK-W046S-PEDCO-110-PI-MT-0003MTO For Flanges - W046S |  | 2022-05-25
MTO For Manual Valves - W046S | BK-W046S-PEDCO-110-PI-MT-0004 | BK-W046S-PEDCO-110-PI-MT-0004MTO For Manual Valves - W046S |  | 2022-05-25
MTO For Gaskets - W046S | BK-W046S-PEDCO-110-PI-MT-0005 | BK-W046S-PEDCO-110-PI-MT-0005MTO For Gaskets - W046S |  | 2022-05-25
MTO For Bolt & Nuts - W046S | BK-W046S-PEDCO-110-PI-MT-0006 | BK-W046S-PEDCO-110-PI-MT-0006MTO For Bolt & Nuts - W046S |  | 2022-05-25
Flow line Transversal Drawings - W046S | BK-W046S-PEDCO-110-PL-DW-0002 | BK-W046S-PEDCO-110-PL-DW-0002Flow line Transversal Drawings - W046S |  | 2022-05-25
Road Crossing Location List | BK-W046S-PEDCO-110-PL-LI-0001 | BK-W046S-PEDCO-110-PL-LI-0001Road Crossing Location List |  | 2022-05-25
MTO For Line Pipes (Flow lines) - W046S | BK-W046S-PEDCO-110-PL-MT-0001 | BK-W046S-PEDCO-110-PL-MT-0001MTO For Line Pipes (Flow lines) - W046S | 2021-08-22 | 2021-08-22
Instrument Location Layout Drawing - W046S | BK-W046S-PEDCO-110-IN-PY-0001 | BK-W046S-PEDCO-110-IN-PY-0001Instrument Location Layout Drawing - W046S | 2022-05-16 | 2022-05-25
MTO For Instrument Tube and Fitting - W046S | BK-W046S-PEDCO-110-IN-MT-0001 | BK-W046S-PEDCO-110-IN-MT-0001MTO For Instrument Tube and Fitting - W046S | 2021-12-18 | 2022-01-29
Hazardous Area Classification Layout - W046S | BK-W046S-PEDCO-110-SA-PY-0001 | BK-W046S-PEDCO-110-SA-PY-0001Hazardous Area Classification Layout - W046S |  | 2022-05-25
Safety & Fire Fighting Equipment Location Layout - W046S | BK-W046S-PEDCO-110-SA-PY-0002 | BK-W046S-PEDCO-110-SA-PY-0002Safety & Fire Fighting Equipment Location Layout - W046S |  | 2022-05-25
Escape Route & Safety Sign Layout - W046S | BK-W046S-PEDCO-110-SA-PY-0003 | BK-W046S-PEDCO-110-SA-PY-0003Escape Route & Safety Sign Layout - W046S |  | 2022-05-25
Hazard Source List - W046S | BK-W046S-PEDCO-110-SA-LI-0001 | BK-W046S-PEDCO-110-SA-LI-0001Hazard Source List - W046S | 2021-11-09 | 2022-05-25
MTO For Fire Fighting & Safety Equipment - W046S | BK-W046S-PEDCO-110-SA-MT-0001 | BK-W046S-PEDCO-110-SA-MT-0001MTO For Fire Fighting & Safety Equipment - W046S |  | 2022-05-25
MTO For Safety Sign - W046S | BK-W046S-PEDCO-110-SA-MT-0002 | BK-W046S-PEDCO-110-SA-MT-0002MTO For Safety Sign - W046S |  | 2022-05-25
MTO For Transmission Over Head Line - W046S | BK-W046S-PEDCO-110-EL-MT-0001 | BK-W046S-PEDCO-110-EL-MT-0001MTO For Transmission Over Head Line - W046S |  | 2022-05-25
MTO For Earthing & Lightning Systems - W046S | BK-W046S-PEDCO-110-EL-MT-0002 | BK-W046S-PEDCO-110-EL-MT-0002MTO For Earthing & Lightning Systems - W046S |  | 2022-05-25
MTO For Lighting & Small Powers - W046S | BK-W046S-PEDCO-110-EL-MT-0003 | BK-W046S-PEDCO-110-EL-MT-0003MTO For Lighting & Small Powers - W046S | 2022-05-18 | 2022-05-18
MTO For Power & Control Cables - W046S | BK-W046S-PEDCO-110-EL-MT-0004 | BK-W046S-PEDCO-110-EL-MT-0004MTO For Power & Control Cables - W046S |  | 2022-05-25
MTO For Tray/Ladder and Accessories - W046S | BK-W046S-PEDCO-110-EL-MT-0005 | BK-W046S-PEDCO-110-EL-MT-0005MTO For Tray/Ladder and Accessories - W046S |  | 2022-05-25
MTO For Electrical Bulk Items - W046S | BK-W046S-PEDCO-110-EL-MT-0006 | BK-W046S-PEDCO-110-EL-MT-0006MTO For Electrical Bulk Items - W046S |  | 2022-05-25
Architectural Drawing For Diesel Generator Shelter of Well Pads - W046S | BK-W046S-PEDCO-110-AR-DW-0001 | BK-W046S-PEDCO-110-AR-DW-0001Architectural Drawing For Diesel Generator Shelter of Well Pads - W046S | 2022-05-01 | 2022-05-25
Architectural Drawing For WHCP/HPU Shelter of Well Pads - W046S | BK-W046S-PEDCO-110-AR-DW-0002 | BK-W046S-PEDCO-110-AR-DW-0002Architectural Drawing For WHCP/HPU Shelter of Well Pads - W046S |  | 2022-05-25
Architectural Drawing For Switchgear Building of Well Pads - W046S | BK-W046S-PEDCO-110-AR-DW-0003 | BK-W046S-PEDCO-110-AR-DW-0003Architectural Drawing For Switchgear Building of Well Pads - W046S | 2022-03-02 | 2022-05-25
Architectural Drawing For Security Building of Well Pads - W046S | BK-W046S-PEDCO-110-AR-DW-0004 | BK-W046S-PEDCO-110-AR-DW-0004Architectural Drawing For Security Building of Well Pads - W046S | 2022-05-01 | 2022-05-25
MTO For Architectural Works - W0046S | BK-W046S-PEDCO-110-AR-MT-0001 | BK-W046S-PEDCO-110-AR-MT-0001MTO For Architectural Works - W0046S |  | 2022-05-25
General Civil Layout -W046S | BK-W046S-PEDCO-110-CV-PY-0001 | BK-W046S-PEDCO-110-CV-PY-0001General Civil Layout -W046S | 2022-05-02 | 2022-05-25
Civil and Structural drawings -W046S | BK-W046S-PEDCO-110-CV-PY-0002 | BK-W046S-PEDCO-110-CV-PY-0002Civil and Structural drawings -W046S | 2022-05-22 | 2022-05-25
Rough Grading Plans -W046S | BK-W046S-PEDCO-110-CV-DW-0001 | BK-W046S-PEDCO-110-CV-DW-0001Rough Grading Plans -W046S | 2021-12-12 | 2022-05-25
Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W046S | BK-W046S-PEDCO-110-CV-CN-0001 | BK-W046S-PEDCO-110-CV-CN-0001Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W046S |  | 2022-05-25
MTO For Civil Works - W046S | BK-W046S-PEDCO-110-CV-MT-0001 | BK-W046S-PEDCO-110-CV-MT-0001MTO For Civil Works - W046S |  | 2022-05-25
Fuel Oil Storage Drum Detail Drawing For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0003 | BK-W046S-PEDCO-110-ST-DW-0003Fuel Oil Storage Drum Detail Drawing For Well Pads - W046S |  | 2022-05-25
Foundation Drawing For Security Building For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0004 | BK-W046S-PEDCO-110-ST-DW-0004Foundation Drawing For Security Building For Well Pads - W046S |  | 2022-05-25
Structural Drawing For Security Building For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0005 | BK-W046S-PEDCO-110-ST-DW-0005Structural Drawing For Security Building For Well Pads - W046S |  | 2022-05-25
Foundation Drawing For Switchgear Building For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0006 | BK-W046S-PEDCO-110-ST-DW-0006Foundation Drawing For Switchgear Building For Well Pads - W046S |  | 2022-05-25
Structural Drawing For Switchgear Building For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0007 | BK-W046S-PEDCO-110-ST-DW-0007Structural Drawing For Switchgear Building For Well Pads - W046S |  | 2022-05-25
Foundation Drawing For Potable Water Tank For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0008 | BK-W046S-PEDCO-110-ST-DW-0008Foundation Drawing For Potable Water Tank For Well Pads - W046S |  | 2022-05-25
Foundation Drawing For Diesel Generator Shelter For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0009 | BK-W046S-PEDCO-110-ST-DW-0009Foundation Drawing For Diesel Generator Shelter For Well Pads - W046S |  | 2022-05-25
Structural Drawing For Diesel Generator Shelter For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0010 | BK-W046S-PEDCO-110-ST-DW-0010Structural Drawing For Diesel Generator Shelter For Well Pads - W046S |  | 2022-05-25
Platform Structure Drawing - W046S | BK-W046S-PEDCO-110-ST-DW-0012 | BK-W046S-PEDCO-110-ST-DW-0012Platform Structure Drawing - W046S |  | 2022-05-25
Foundation Drawing For Transmission Line Tower - W046S | BK-W046S-PEDCO-110-ST-DW-0013 | BK-W046S-PEDCO-110-ST-DW-0013Foundation Drawing For Transmission Line Tower - W046S |  | 2022-05-25
MTO For Structural Works - W046S | BK-W046S-PEDCO-110-ST-MT-0001 | BK-W046S-PEDCO-110-ST-MT-0001MTO For Structural Works - W046S |  | 2022-05-25
Geotechnical Investigation Report - W046S | BK-W046S-PEDCO-110-GT-RT-0001 | BK-W046S-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - W046S |  | 2022-05-25
Flow line Plan & Profile Drawings - W046S | BK-W046S-PEDCO-110-SU-DW-0001 | BK-W046S-PEDCO-110-SU-DW-0001Flow line Plan & Profile Drawings - W046S |  | 2022-05-25
Over Head Line Plan and Profile - W046S | BK-W046S-PEDCO-110-SU-DW-0002 | BK-W046S-PEDCO-110-SU-DW-0002Over Head Line Plan and Profile - W046S | 2022-03-26 | 2022-05-25
PMR For Pipes - W046S | BK-W046S-PEDCO-110-PI-MR-0001 | BK-W046S-PEDCO-110-PI-MR-0001PMR For Pipes - W046S |  | 2022-05-25
TBE For Pipes - W046S | BK-W046S-PEDCO-110-PI-TB-0001 | BK-W046S-PEDCO-110-PI-TB-0001TBE For Pipes - W046S |  | 2022-05-25
PMR For Fittings - W046S | BK-W046S-PEDCO-110-PI-MR-0002 | BK-W046S-PEDCO-110-PI-MR-0002PMR For Fittings - W046S |  | 2022-05-25
TBE For Fitting - W046S | BK-W046S-PEDCO-110-PI-TB-0002 | BK-W046S-PEDCO-110-PI-TB-0002TBE For Fitting - W046S |  | 2022-05-25
PMR For Flanges - W046S | BK-W046S-PEDCO-110-PI-MR-0003 | BK-W046S-PEDCO-110-PI-MR-0003PMR For Flanges - W046S |  | 2022-05-25
TBE For Flanges - W046S | BK-W046S-PEDCO-110-PI-TB-0003 | BK-W046S-PEDCO-110-PI-TB-0003TBE For Flanges - W046S |  | 2022-05-25
PMR For Manual Valves - W046S | BK-W046S-PEDCO-110-PI-MR-0004 | BK-W046S-PEDCO-110-PI-MR-0004PMR For Manual Valves - W046S |  | 2022-05-25
TBE For Manual Valves - W046S | BK-W046S-PEDCO-110-PI-TB-0004 | BK-W046S-PEDCO-110-PI-TB-0004TBE For Manual Valves - W046S |  | 2022-05-25
PMR For Gaskets - W046S | BK-W046S-PEDCO-110-PI-MR-0005 | BK-W046S-PEDCO-110-PI-MR-0005PMR For Gaskets - W046S |  | 2022-05-25
TBE For Gaskets - W046S | BK-W046S-PEDCO-110-PI-TB-0005 | BK-W046S-PEDCO-110-PI-TB-0005TBE For Gaskets - W046S |  | 2022-05-25
PMR For Bolt/Nuts - W046S | BK-W046S-PEDCO-110-PI-MR-0006 | BK-W046S-PEDCO-110-PI-MR-0006PMR For Bolt/Nuts - W046S |  | 2022-05-25
TBE For Bolt/Nuts - W046S | BK-W046S-PEDCO-110-PI-TB-0006 | BK-W046S-PEDCO-110-PI-TB-0006TBE For Bolt/Nuts - W046S |  | 2022-05-25
PMR For Sampling Connection Set - W046S | BK-W046S-PEDCO-110-PI-MR-0007 | BK-W046S-PEDCO-110-PI-MR-0007PMR For Sampling Connection Set - W046S |  | 2022-05-25
TBE For Sampling Connection - W046S | BK-W046S-PEDCO-110-PI-TB-0007 | BK-W046S-PEDCO-110-PI-TB-0007TBE For Sampling Connection - W046S |  | 2022-05-25
PMR For Stone Trap - W046S | BK-W046S-PEDCO-110-PI-MR-0008 | BK-W046S-PEDCO-110-PI-MR-0008PMR For Stone Trap - W046S |  | 2022-05-25
TBE For Stone Trap - W046S | BK-W046S-PEDCO-110-PI-TB-0008 | BK-W046S-PEDCO-110-PI-TB-0008TBE For Stone Trap - W046S |  | 2022-05-25
PMR For Pipe Support - W046S | BK-W046S-PEDCO-110-PI-MR-0009 | BK-W046S-PEDCO-110-PI-MR-0009PMR For Pipe Support - W046S |  | 2022-05-25
TBE For Pipe Support - W046S | BK-W046S-PEDCO-110-PI-TB-0009 | BK-W046S-PEDCO-110-PI-TB-0009TBE For Pipe Support - W046S |  | 2022-05-25
PMR For Main HVAC Equipment - W046S | BK-W046S-PEDCO-110-HV-MR-0001 | BK-W046S-PEDCO-110-HV-MR-0001PMR For Main HVAC Equipment - W046S |  | 2022-05-25
TBE For Main HVAC Equipment - W046S | BK-W046S-PEDCO-110-HV-TB-0001 | BK-W046S-PEDCO-110-HV-TB-0001TBE For Main HVAC Equipment - W046S |  | 2022-05-25
PMR For Line Pipes - W046S | BK-W046S-PEDCO-110-PL-MR-0001 | BK-W046S-PEDCO-110-PL-MR-0001PMR For Line Pipes - W046S |  | 2022-05-25
TBE For Line Pipes - W046S | BK-W046S-PEDCO-110-PL-TB-0001 | BK-W046S-PEDCO-110-PL-TB-0001TBE For Line Pipes - W046S | 2022-02-19 | 2022-05-14
PMR For Flow Line Support - W046S | BK-W046S-PEDCO-110-PL-MR-0002 | BK-W046S-PEDCO-110-PL-MR-0002PMR For Flow Line Support - W046S |  | 2022-05-25
TBE For Flow Line Support - W046S | BK-W046S-PEDCO-110-PL-TB-0002 | BK-W046S-PEDCO-110-PL-TB-0002TBE For Flow Line Support - W046S |  | 2022-05-25
PMR For Field Instrumentations - W046S | BK-W046S-PEDCO-110-IN-MR-0002 | BK-W046S-PEDCO-110-IN-MR-0002PMR For Field Instrumentations - W046S | 2021-12-13 | 2021-12-13
TBE/TBA For Field Instrumentations - W046S | BK-W046S-PEDCO-110-IN-TB-0002 | BK-W046S-PEDCO-110-IN-TB-0002TBE/TBA For Field Instrumentations - W046S |  | 2022-05-25
PMR For Instrument Bulk Items - W046S | BK-W046S-PEDCO-110-IN-MR-0003 | BK-W046S-PEDCO-110-IN-MR-0003PMR For Instrument Bulk Items - W046S | 2022-01-16 | 2022-01-16
TBE/TBA For Instrument Bulk Items - W046S | BK-W046S-PEDCO-110-IN-TB-0003 | BK-W046S-PEDCO-110-IN-TB-0003TBE/TBA For Instrument Bulk Items - W046S | 2022-02-02 | 2022-02-02
PMR For Fire Fighting and Safety Equipment - W046S | BK-W046S-PEDCO-110-SA-MR-0001 | BK-W046S-PEDCO-110-SA-MR-0001PMR For Fire Fighting and Safety Equipment - W046S |  | 2022-05-25
TBE For Fire Fighting and Safety Equipment - W046S | BK-W046S-PEDCO-110-SA-TB-0001 | BK-W046S-PEDCO-110-SA-TB-0001TBE For Fire Fighting and Safety Equipment - W046S |  | 2022-05-25
PMR For Fire Safety Sign - W046S | BK-W046S-PEDCO-110-SA-MR-0002 | BK-W046S-PEDCO-110-SA-MR-0002PMR For Fire Safety Sign - W046S |  | 2022-05-25
TBE For Fire Safety Sign - W046S | BK-W046S-PEDCO-110-SA-TB-0002 | BK-W046S-PEDCO-110-SA-TB-0002TBE For Fire Safety Sign - W046S |  | 2022-05-25
PMR For Transformers - W046S | BK-W046S-PEDCO-110-EL-MR-0001 | BK-W046S-PEDCO-110-EL-MR-0001PMR For Transformers - W046S |  | 2022-05-25
TBE For Transformers - W046S | BK-W046S-PEDCO-110-EL-TB-0001 | BK-W046S-PEDCO-110-EL-TB-0001TBE For Transformers - W046S |  | 2022-05-25
PMR For LV Switchgear & MCC - W046S | BK-W046S-PEDCO-110-EL-MR-0002 | BK-W046S-PEDCO-110-EL-MR-0002PMR For LV Switchgear & MCC - W046S |  | 2022-05-25
TBE For LV Switchgear & MCC - W046S | BK-W046S-PEDCO-110-EL-TB-0002 | BK-W046S-PEDCO-110-EL-TB-0002TBE For LV Switchgear & MCC - W046S |  | 2022-05-25
PMR For Emergency Diesel Generator - W046S | BK-W046S-PEDCO-110-EL-MR-0003 | BK-W046S-PEDCO-110-EL-MR-0003PMR For Emergency Diesel Generator - W046S |  | 2022-05-25
TBE For Emergency Diesel Generator - W046S | BK-W046S-PEDCO-110-EL-TB-0003 | BK-W046S-PEDCO-110-EL-TB-0003TBE For Emergency Diesel Generator - W046S |  | 2022-05-25
PMR For UPS System - W046S | BK-W046S-PEDCO-110-EL-MR-0004 | BK-W046S-PEDCO-110-EL-MR-0004PMR For UPS System - W046S |  | 2022-05-25
TBE For UPS System - W046S | BK-W046S-PEDCO-110-EL-TB-0004 | BK-W046S-PEDCO-110-EL-TB-0004TBE For UPS System - W046S |  | 2022-05-25
PMR For DC Charger - W046S | BK-W046S-PEDCO-110-EL-MR-0005 | BK-W046S-PEDCO-110-EL-MR-0005PMR For DC Charger - W046S | 2022-04-26 | 2022-04-26
TBE For DC Charger - W046S | BK-W046S-PEDCO-110-EL-TB-0005 | BK-W046S-PEDCO-110-EL-TB-0005TBE For DC Charger - W046S |  | 2022-05-25
PMR For Capacitor Bank - W046S | BK-W046S-PEDCO-110-EL-MR-0006 | BK-W046S-PEDCO-110-EL-MR-0006PMR For Capacitor Bank - W046S |  | 2022-05-25
TBE For Capacitor Bank - W046S | BK-W046S-PEDCO-110-EL-TB-0006 | BK-W046S-PEDCO-110-EL-TB-0006TBE For Capacitor Bank - W046S |  | 2022-05-25
PMR For Lighting & Distribution Main Panels - W046S | BK-W046S-PEDCO-110-EL-MR-0007 | BK-W046S-PEDCO-110-EL-MR-0007PMR For Lighting & Distribution Main Panels - W046S |  | 2022-05-25
TBE For Lighting & Distribution Main Panels - W046S | BK-W046S-PEDCO-110-EL-TB-0007 | BK-W046S-PEDCO-110-EL-TB-0007TBE For Lighting & Distribution Main Panels - W046S |  | 2022-05-25
PMR For Earthing & Lightning System - W046S | BK-W046S-PEDCO-110-EL-MR-0008 | BK-W046S-PEDCO-110-EL-MR-0008PMR For Earthing & Lightning System - W046S |  | 2022-05-25
TBE For Earthing & Lightning System - W046S | BK-W046S-PEDCO-110-EL-TB-0008 | BK-W046S-PEDCO-110-EL-TB-0008TBE For Earthing & Lightning System - W046S |  | 2022-05-25
PMR For Lighting and Small Power Equipment - W046S | BK-W046S-PEDCO-110-EL-MR-0009 | BK-W046S-PEDCO-110-EL-MR-0009PMR For Lighting and Small Power Equipment - W046S |  | 2022-05-25
TBE For Lighting and Small Power Equipment - W046S | BK-W046S-PEDCO-110-EL-TB-0009 | BK-W046S-PEDCO-110-EL-TB-0009TBE For Lighting and Small Power Equipment - W046S |  | 2022-05-25
PMR For Tray/Ladder and Accessories - W046S | BK-W046S-PEDCO-110-EL-MR-0010 | BK-W046S-PEDCO-110-EL-MR-0010PMR For Tray/Ladder and Accessories - W046S |  | 2022-05-25
TBE For Tray/Ladder and Accessories - W046S | BK-W046S-PEDCO-110-EL-TB-0010 | BK-W046S-PEDCO-110-EL-TB-0010TBE For Tray/Ladder and Accessories - W046S |  | 2022-05-25
PMR For Power & Control Cables - W046S | BK-W046S-PEDCO-110-EL-MR-0011 | BK-W046S-PEDCO-110-EL-MR-0011PMR For Power & Control Cables - W046S |  | 2022-05-25
TBE For Power & Control Cables - W046S | BK-W046S-PEDCO-110-EL-TB-0011 | BK-W046S-PEDCO-110-EL-TB-0011TBE For Power & Control Cables - W046S |  | 2022-05-25
PMR For Electrical Bulk Items - W046S | BK-W046S-PEDCO-110-EL-MR-0012 | BK-W046S-PEDCO-110-EL-MR-0012PMR For Electrical Bulk Items - W046S |  | 2022-05-25
TBE For Electrical Bulk Items - W046S | BK-W046S-PEDCO-110-EL-TB-0012 | BK-W046S-PEDCO-110-EL-TB-0012TBE For Electrical Bulk Items - W046S |  | 2022-05-25
PMR For Transmission Over head Line - W046S | BK-W046S-PEDCO-110-EL-MR-0013 | BK-W046S-PEDCO-110-EL-MR-0013PMR For Transmission Over head Line - W046S |  | 2022-05-25
TBE For Transmission Over head Line - W046S | BK-W046S-PEDCO-110-EL-TB-0013 | BK-W046S-PEDCO-110-EL-TB-0013TBE For Transmission Over head Line - W046S |  | 2022-05-25
PMR For Steel Structure Items - W046S | BK-W046S-PEDCO-110-ST-MR-0001 | BK-W046S-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - W046S |  | 2022-05-25
TBE For Steel Structure Items - W046S | BK-W046S-PEDCO-110-ST-TB-0001 | BK-W046S-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - W046S |  | 2022-05-25
PMR For Anchor Bolts - W046S | BK-W046S-PEDCO-110-ST-MR-0002 | BK-W046S-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - W046S |  | 2022-05-25
TBE For Anchor Bolts - W046S | BK-W046S-PEDCO-110-ST-TB-0002 | BK-W046S-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - W046S |  | 2022-05-25
PMR For Blast Proof Doors - W046S | BK-W046S-PEDCO-110-ST-MR-0003 | BK-W046S-PEDCO-110-ST-MR-0003PMR For Blast Proof Doors - W046S |  | 2022-05-25
TBE For Blast Proof Doors - W046S | BK-W046S-PEDCO-110-ST-TB-0003 | BK-W046S-PEDCO-110-ST-TB-0003TBE For Blast Proof Doors - W046S |  | 2022-05-25
PMR For Geomembrane - W046S | BK-W046S-PEDCO-110-CV-MR-0001 | BK-W046S-PEDCO-110-CV-MR-0001PMR For Geomembrane - W046S |  | 2022-05-25
TBE For Geomembrane - W046S | BK-W046S-PEDCO-110-CV-TB-0001 | BK-W046S-PEDCO-110-CV-TB-0001TBE For Geomembrane - W046S |  | 2022-05-25
PMR For Geotextile - W046S | BK-W046S-PEDCO-110-CV-MR-0002 | BK-W046S-PEDCO-110-CV-MR-0002PMR For Geotextile - W046S |  | 2022-05-25
TBE For Geotextile - W046S | BK-W046S-PEDCO-110-CV-TB-0002 | BK-W046S-PEDCO-110-CV-TB-0002TBE For Geotextile - W046S |  | 2022-05-25
Pre-Commissioning, Commissioning & Startup Procedure - W046S | BK-W046S-PEDCO-110-CO-PR-0001 | BK-W046S-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - W046S |  | 2022-05-25
Technical/Site Queries | BK-W046S-PEDCO-110-GE-TQ-0001 | BK-W046S-PEDCO-110-GE-TQ-0001Technical/Site Queries |  | 2022-05-25
As-Built Document Booklets - W046S | BK-W046S-PEDCO-110-GE-DO-0001 | BK-W046S-PEDCO-110-GE-DO-0001As-Built Document Booklets - W046S |  | 2022-05-25
Operating Manual - W046S | BK-W046S-PEDCO-110-GE-ML-0001 | BK-W046S-PEDCO-110-GE-ML-0001Operating Manual - W046S |  | 2022-05-25
As-Built Document Booklets - W046S | BK-W046S-PEDCO-110-GE-DO-0001 | BK-W046S-PEDCO-110-GE-DO-0001As-Built Document Booklets - W046S
Final Engineering Dossier - W046S | BK-W046S-PEDCO-110-GE-DO-0002 | BK-W046S-PEDCO-110-GE-DO-0002Final Engineering Dossier - W046S |  | 2022-05-25
Process Flow Diagram - W035 | BK-W035-PEDCO-110-PR-PF-0001 | BK-W035-PEDCO-110-PR-PF-0001Process Flow Diagram - W035 | 2021-08-22 | 2022-05-25
P&ID - W035 | BK-W035-PEDCO-110-PR-PI-0001 | BK-W035-PEDCO-110-PR-PI-0001P&ID - W035 | 2021-08-22 | 2022-05-25
Line List - W035 | BK-W035-PEDCO-110-PR-LI-0001 | BK-W035-PEDCO-110-PR-LI-0001Line List - W035 | 2021-08-22 | 2022-05-25
Flow line Hydraulic Calculation Report | BK-W035-PEDCO-110-PR-RT-0001 | BK-W035-PEDCO-110-PR-RT-0001Flow line Hydraulic Calculation Report | 2021-10-30 | 2022-05-25
Process Data Sheets For Instrument Devices - W035 | BK-W035-PEDCO-110-PR-DT-0001 | BK-W035-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - W035 | 2022-04-12 | 2022-05-25
Plot Plan Drawing - W035 | BK-W035-PEDCO-110-PI-DW-0001 | BK-W035-PEDCO-110-PI-DW-0001Plot Plan Drawing - W035 |  | 2022-05-25
Piping Plan - W035 | BK-W035-PEDCO-110-PI-DW-0002 | BK-W035-PEDCO-110-PI-DW-0002Piping Plan - W035 |  | 2022-05-25
Isometric Drawings - W035 | BK-W035-PEDCO-110-PI-DW-0003 | BK-W035-PEDCO-110-PI-DW-0003Isometric Drawings - W035 |  | 2022-05-25
Material Flow Diagram - W035 | BK-W035-PEDCO-110-PI-DG-0001 | BK-W035-PEDCO-110-PI-DG-0001Material Flow Diagram - W035 | 2021-11-08 | 2022-05-25
Piping Support List - W035 | BK-W035-PEDCO-110-PI-LI-0001 | BK-W035-PEDCO-110-PI-LI-0001Piping Support List - W035 |  | 2022-05-25
Critical Line List - W035 | BK-W035-PEDCO-110-PI-LI-0002 | BK-W035-PEDCO-110-PI-LI-0002Critical Line List - W035 |  | 2022-05-25
PDMS Model Review Report (60%) - W035 | BK-W035-PEDCO-110-PI-RT-0001 | BK-W035-PEDCO-110-PI-RT-0001PDMS Model Review Report (60%) - W035 |  | 2022-05-25
PDMS Model Review Report (90%) - W035 | BK-W035-PEDCO-110-PI-RT-0002 | BK-W035-PEDCO-110-PI-RT-0002PDMS Model Review Report (90%) - W035 |  | 2022-05-25
MTO For Pipes - W035 | BK-W035-PEDCO-110-PI-MT-0001 | BK-W035-PEDCO-110-PI-MT-0001MTO For Pipes - W035 |  | 2022-05-25
MTO For Fittings - W035 | BK-W035-PEDCO-110-PI-MT-0002 | BK-W035-PEDCO-110-PI-MT-0002MTO For Fittings - W035 |  | 2022-05-25
MTO For Flanges - W035 | BK-W035-PEDCO-110-PI-MT-0003 | BK-W035-PEDCO-110-PI-MT-0003MTO For Flanges - W035 |  | 2022-05-25
MTO For Manual Valves - W035 | BK-W035-PEDCO-110-PI-MT-0004 | BK-W035-PEDCO-110-PI-MT-0004MTO For Manual Valves - W035 |  | 2022-05-25
MTO For Gaskets - W035 | BK-W035-PEDCO-110-PI-MT-0005 | BK-W035-PEDCO-110-PI-MT-0005MTO For Gaskets - W035 |  | 2022-05-25
MTO For Bolt & Nuts - W035 | BK-W035-PEDCO-110-PI-MT-0006 | BK-W035-PEDCO-110-PI-MT-0006MTO For Bolt & Nuts - W035 |  | 2022-05-25
Flow line Transversal Drawings - W035 | BK-W035-PEDCO-110-PL-DW-0002 | BK-W035-PEDCO-110-PL-DW-0002Flow line Transversal Drawings - W035 |  | 2022-05-25
Road Crossing Location List | BK-W035-PEDCO-110-PL-LI-0001 | BK-W035-PEDCO-110-PL-LI-0001Road Crossing Location List |  | 2022-05-25
MTO For Line Pipes (Flow lines) - W035 | BK-W035-PEDCO-110-PL-MT-0001 | BK-W035-PEDCO-110-PL-MT-0001MTO For Line Pipes (Flow lines) - W035 | 2021-08-22 | 2021-08-22
Instrument Location Layout Drawing - W035 | BK-W035-PEDCO-110-IN-PY-0001 | BK-W035-PEDCO-110-IN-PY-0001Instrument Location Layout Drawing - W035 |  | 2022-05-25
MTO For Instrument Tube and Fitting - W035 | BK-W035-PEDCO-110-IN-MT-0001 | BK-W035-PEDCO-110-IN-MT-0001MTO For Instrument Tube and Fitting - W035 | 2021-11-14 | 2022-01-12
MTO For Instrument Cable Tray - W035 | BK-W035-PEDCO-110-IN-MT-0002 | BK-W035-PEDCO-110-IN-MT-0002MTO For Instrument Cable Tray - W035 | 2021-11-14 | 2022-01-12
Hazardous Area Classification Layout - W035 | BK-W035-PEDCO-110-SA-PY-0001 | BK-W035-PEDCO-110-SA-PY-0001Hazardous Area Classification Layout - W035 |  | 2022-05-25
Safety & Fire Fighting Equipment Location Layout - W035 | BK-W035-PEDCO-110-SA-PY-0002 | BK-W035-PEDCO-110-SA-PY-0002Safety & Fire Fighting Equipment Location Layout - W035 |  | 2022-05-25
Escape Route & Safety Sign Layout - W035 | BK-W035-PEDCO-110-SA-PY-0003 | BK-W035-PEDCO-110-SA-PY-0003Escape Route & Safety Sign Layout - W035 |  | 2022-05-25
Hazard Source List - W035 | BK-W035-PEDCO-110-SA-LI-0001 | BK-W035-PEDCO-110-SA-LI-0001Hazard Source List - W035 | 2021-11-09 | 2022-05-25
MTO For Fire Fighting & Safety Equipment - W035 | BK-W035-PEDCO-110-SA-MT-0001 | BK-W035-PEDCO-110-SA-MT-0001MTO For Fire Fighting & Safety Equipment - W035 |  | 2022-05-25
MTO For Safety Sign - W035 | BK-W035-PEDCO-110-SA-MT-0002 | BK-W035-PEDCO-110-SA-MT-0002MTO For Safety Sign - W035 |  | 2022-05-25
Architectural Drawing For WHCP/HPU Shelter of Well Pads - W035 | BK-W035-PEDCO-110-AR-DW-0001 | BK-W035-PEDCO-110-AR-DW-0001Architectural Drawing For WHCP/HPU Shelter of Well Pads - W035 | 2022-02-26 | 2022-05-25
General Civil Layout -W035 | BK-W035-PEDCO-110-CV-PY-0001 | BK-W035-PEDCO-110-CV-PY-0001General Civil Layout -W035 |  | 2022-05-25
Civil and Structural drawings -W035 | BK-W035-PEDCO-110-CV-PY-0002 | BK-W035-PEDCO-110-CV-PY-0002Civil and Structural drawings -W035 |  | 2022-05-25
Rough Grading Plans -W035 | BK-W035-PEDCO-110-CV-DW-0001 | BK-W035-PEDCO-110-CV-DW-0001Rough Grading Plans -W035 | 2021-12-15 | 2022-05-25
Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W035 | BK-W035-PEDCO-110-CV-CN-0001 | BK-W035-PEDCO-110-CV-CN-0001Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W035 |  | 2022-05-25
MTO For Civil Works - W035 | BK-W035-PEDCO-110-CV-MT-0001 | BK-W035-PEDCO-110-CV-MT-0001MTO For Civil Works - W035 |  | 2022-05-25
Platform Structure Drawing - W035 | BK-W035-PEDCO-110-ST-DW-0002 | BK-W035-PEDCO-110-ST-DW-0002Platform Structure Drawing - W035 |  | 2022-05-25
MTO For Structural Works - W035 | BK-W035-PEDCO-110-ST-MT-0001 | BK-W035-PEDCO-110-ST-MT-0001MTO For Structural Works - W035 |  | 2022-05-25
Geotechnical Investigation Report - W035 | BK-W035-PEDCO-110-GT-RT-0001 | BK-W035-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - W035 |  | 2022-05-25
Flow line Plan & Profile Drawings - W035 | BK-W035-PEDCO-110-SU-DW-0001 | BK-W035-PEDCO-110-SU-DW-0001Flow line Plan & Profile Drawings - W035 |  | 2022-05-25
PMR For Pipes - W035 | BK-W035-PEDCO-110-PI-MR-0001 | BK-W035-PEDCO-110-PI-MR-0001PMR For Pipes - W035 |  | 2022-05-25
TBE For Pipes - W035 | BK-W035-PEDCO-110-PI-TB-0001 | BK-W035-PEDCO-110-PI-TB-0001TBE For Pipes - W035 |  | 2022-05-25
PMR For Fittings - W035 | BK-W035-PEDCO-110-PI-MR-0002 | BK-W035-PEDCO-110-PI-MR-0002PMR For Fittings - W035 |  | 2022-05-25
TBE For Fitting - W035 | BK-W035-PEDCO-110-PI-TB-0002 | BK-W035-PEDCO-110-PI-TB-0002TBE For Fitting - W035 |  | 2022-05-25
PMR For Flanges - W035 | BK-W035-PEDCO-110-PI-MR-0003 | BK-W035-PEDCO-110-PI-MR-0003PMR For Flanges - W035 |  | 2022-05-25
TBE For Flanges - W035 | BK-W035-PEDCO-110-PI-TB-0003 | BK-W035-PEDCO-110-PI-TB-0003TBE For Flanges - W035 |  | 2022-05-25
PMR For Manual Valves - W035 | BK-W035-PEDCO-110-PI-MR-0004 | BK-W035-PEDCO-110-PI-MR-0004PMR For Manual Valves - W035 |  | 2022-05-25
TBE For Manual Valves - W035 | BK-W035-PEDCO-110-PI-TB-0004 | BK-W035-PEDCO-110-PI-TB-0004TBE For Manual Valves - W035 |  | 2022-05-25
PMR For Gaskets - W035 | BK-W035-PEDCO-110-PI-MR-0005 | BK-W035-PEDCO-110-PI-MR-0005PMR For Gaskets - W035 |  | 2022-05-25
TBE For Gaskets - W035 | BK-W035-PEDCO-110-PI-TB-0005 | BK-W035-PEDCO-110-PI-TB-0005TBE For Gaskets - W035 |  | 2022-05-25
PMR For Bolt/Nuts - W035 | BK-W035-PEDCO-110-PI-MR-0006 | BK-W035-PEDCO-110-PI-MR-0006PMR For Bolt/Nuts - W035 |  | 2022-05-25
TBE For Bolt/Nuts - W035 | BK-W035-PEDCO-110-PI-TB-0006 | BK-W035-PEDCO-110-PI-TB-0006TBE For Bolt/Nuts - W035 |  | 2022-05-25
PMR For Sampling Connection Set - W035 | BK-W035-PEDCO-110-PI-MR-0007 | BK-W035-PEDCO-110-PI-MR-0007PMR For Sampling Connection Set - W035 |  | 2022-05-25
TBE For Sampling Connection Set - W035 | BK-W035-PEDCO-110-PI-TB-0007 | BK-W035-PEDCO-110-PI-TB-0007TBE For Sampling Connection Set - W035 |  | 2022-05-25
PMR For Stone Trap - W035 | BK-W035-PEDCO-110-PI-MR-0008 | BK-W035-PEDCO-110-PI-MR-0008PMR For Stone Trap - W035 |  | 2022-05-25
TBE For Stone Trap - W035 | BK-W035-PEDCO-110-PI-TB-0008 | BK-W035-PEDCO-110-PI-TB-0008TBE For Stone Trap - W035 |  | 2022-05-25
PMR For Pipe Support - W035 | BK-W035-PEDCO-110-PI-MR-0009 | BK-W035-PEDCO-110-PI-MR-0009PMR For Pipe Support - W035 |  | 2022-05-25
TBE For Pipe Support - W035 | BK-W035-PEDCO-110-PI-TB-0009 | BK-W035-PEDCO-110-PI-TB-0009TBE For Pipe Support - W035 |  | 2022-05-25
PMR For Line Pipes - W035 | BK-W035-PEDCO-110-PL-MR-0001 | BK-W035-PEDCO-110-PL-MR-0001PMR For Line Pipes - W035 |  | 2022-05-25
TBE For Line Pipes - W035 | BK-W035-PEDCO-110-PL-TB-0001 | BK-W035-PEDCO-110-PL-TB-0001TBE For Line Pipes - W035 | 2022-02-19 | 2022-05-14
PMR For Flow Line Support - W035 | BK-W035-PEDCO-110-PL-MR-0002 | BK-W035-PEDCO-110-PL-MR-0002PMR For Flow Line Support - W035 |  | 2022-05-25
TBE For Flow Line Support - W035 | BK-W035-PEDCO-110-PL-TB-0002 | BK-W035-PEDCO-110-PL-TB-0002TBE For Flow Line Support - W035 |  | 2022-05-25
PMR For WHCP/HPU - W035 | BK-W035-PEDCO-110-IN-MR-0001 | BK-W035-PEDCO-110-IN-MR-0001PMR For WHCP/HPU - W035 | 2021-11-15 | 2022-01-16
TBE/TBA For WHCP/HPU - W035 | BK-W035-PEDCO-110-IN-TB-0001 | BK-W035-PEDCO-110-IN-TB-0001TBE/TBA For WHCP/HPU - W035 | 2021-12-01 | 2022-02-19
PMR For Field Instrumentations - W035 | BK-W035-PEDCO-110-IN-MR-0002 | BK-W035-PEDCO-110-IN-MR-0002PMR For Field Instrumentations - W035 | 2021-12-13 | 2021-12-13
TBE/TBA For Field Instrumentations - W035 | BK-W035-PEDCO-110-IN-TB-0002 | BK-W035-PEDCO-110-IN-TB-0002TBE/TBA For Field Instrumentations - W035 |  | 2022-05-25
PMR For Instrument Bulk Items - W035 | BK-W035-PEDCO-110-IN-MR-0003 | BK-W035-PEDCO-110-IN-MR-0003PMR For Instrument Bulk Items - W035 | 2022-01-16 | 2022-01-16
TBE/TBA For Instrument Bulk Items - W035 | BK-W035-PEDCO-110-IN-TB-0003 | BK-W035-PEDCO-110-IN-TB-0003TBE/TBA For Instrument Bulk Items - W035 | 2022-02-02 | 2022-02-02
PMR For Fire Fighting and Safety Equipment - W035 | BK-W035-PEDCO-110-SA-MR-0001 | BK-W035-PEDCO-110-SA-MR-0001PMR For Fire Fighting and Safety Equipment - W035 |  | 2022-05-25
TBE For Fire Fighting and Safety Equipment - W035 | BK-W035-PEDCO-110-SA-TB-0001 | BK-W035-PEDCO-110-SA-TB-0001TBE For Fire Fighting and Safety Equipment - W035 |  | 2022-05-25
PMR For Fire Safety Sign - W035 | BK-W035-PEDCO-110-SA-MR-0002 | BK-W035-PEDCO-110-SA-MR-0002PMR For Fire Safety Sign - W035 |  | 2022-05-25
TBE For Fire Safety Sign - W035 | BK-W035-PEDCO-110-SA-TB-0002 | BK-W035-PEDCO-110-SA-TB-0002TBE For Fire Safety Sign - W035 |  | 2022-05-25
PMR For Steel Structure Items - W035 | BK-W035-PEDCO-110-ST-MR-0001 | BK-W035-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - W035 |  | 2022-05-25
TBE For Steel Structure Items - W035 | BK-W035-PEDCO-110-ST-TB-0001 | BK-W035-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - W035 |  | 2022-05-25
PMR For Anchor Bolts - W035 | BK-W035-PEDCO-110-ST-MR-0002 | BK-W035-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - W035 |  | 2022-05-25
TBE For Anchor Bolts - W035 | BK-W035-PEDCO-110-ST-TB-0002 | BK-W035-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - W035 |  | 2022-05-25
PMR For Geomembrane - W035 | BK-W035-PEDCO-110-CV-MR-0001 | BK-W035-PEDCO-110-CV-MR-0001PMR For Geomembrane - W035 |  | 2022-05-25
TBE For Geomembrane - W035 | BK-W035-PEDCO-110-CV-TB-0001 | BK-W035-PEDCO-110-CV-TB-0001TBE For Geomembrane - W035 |  | 2022-05-25
PMR For Geotextile - W035 | BK-W035-PEDCO-110-CV-MR-0002 | BK-W035-PEDCO-110-CV-MR-0002PMR For Geotextile - W035 |  | 2022-05-25
TBE For Geotextile - W035 | BK-W035-PEDCO-110-CV-TB-0002 | BK-W035-PEDCO-110-CV-TB-0002TBE For Geotextile - W035 |  | 2022-05-25
Pre-Commissioning, Commissioning & Startup Procedure - W035 | BK-W035-PEDCO-110-CO-PR-0001 | BK-W035-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - W035 |  | 2022-05-25
Technical/Site Queries | BK-W035-PEDCO-110-GE-TQ-0001 | BK-W035-PEDCO-110-GE-TQ-0001Technical/Site Queries |  | 2022-05-25
As-Built Document Booklets - W035 | BK-W035-PEDCO-110-GE-DO-0001 | BK-W035-PEDCO-110-GE-DO-0001As-Built Document Booklets - W035 |  | 2022-05-25
Operating Manual - W035 | BK-W035-PEDCO-110-GE-ML-0001 | BK-W035-PEDCO-110-GE-ML-0001Operating Manual - W035 |  | 2022-05-25
As-Built Document Booklets - W035 | BK-W035-PEDCO-110-GE-DO-0001 | BK-W035-PEDCO-110-GE-DO-0001As-Built Document Booklets - W035
Final Engineering Dossier - W035 | BK-W035-PEDCO-110-GE-DO-0002 | BK-W035-PEDCO-110-GE-DO-0002Final Engineering Dossier - W035 |  | 2022-05-25
Process Flow Diagram - W008N | BK-W008N-PEDCO-110-PR-PF-0001 | BK-W008N-PEDCO-110-PR-PF-0001Process Flow Diagram - W008N | 2021-08-22 | 2022-05-25
P&ID - W008N | BK-W008N-PEDCO-110-PR-PI-0001 | BK-W008N-PEDCO-110-PR-PI-0001P&ID - W008N | 2021-08-22 | 2022-05-25
Line List - W008N | BK-W008N-PEDCO-110-PR-LI-0001 | BK-W008N-PEDCO-110-PR-LI-0001Line List - W008N | 2021-08-22 | 2022-05-25
Flow line Hydraulic Calculation Report | BK-W008N-PEDCO-110-PR-RT-0001 | BK-W008N-PEDCO-110-PR-RT-0001Flow line Hydraulic Calculation Report | 2021-10-30 | 2022-05-25
Process Data Sheets For Instrument Devices - W008N | BK-W008N-PEDCO-110-PR-DT-0001 | BK-W008N-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - W008N | 2022-04-12 | 2022-05-25
Plot Plan Drawing - W008N | BK-W008N-PEDCO-110-PI-DW-0001 | BK-W008N-PEDCO-110-PI-DW-0001Plot Plan Drawing - W008N |  | 2022-05-25
Piping Plan - W008N | BK-W008N-PEDCO-110-PI-DW-0002 | BK-W008N-PEDCO-110-PI-DW-0002Piping Plan - W008N |  | 2022-05-25
Isometric Drawings - W008N | BK-W008N-PEDCO-110-PI-DW-0003 | BK-W008N-PEDCO-110-PI-DW-0003Isometric Drawings - W008N |  | 2022-05-25
Material Flow Diagram - W008N | BK-W008N-PEDCO-110-PI-DG-0001 | BK-W008N-PEDCO-110-PI-DG-0001Material Flow Diagram - W008N | 2021-11-08 | 2022-05-25
Piping Support List - W008N | BK-W008N-PEDCO-110-PI-LI-0001 | BK-W008N-PEDCO-110-PI-LI-0001Piping Support List - W008N |  | 2022-05-25
Critical Line List - W008N | BK-W008N-PEDCO-110-PI-LI-0002 | BK-W008N-PEDCO-110-PI-LI-0002Critical Line List - W008N |  | 2022-05-25
PDMS Model Review Report (60%) - W008N | BK-W008N-PEDCO-110-PI-RT-0001 | BK-W008N-PEDCO-110-PI-RT-0001PDMS Model Review Report (60%) - W008N |  | 2022-05-25
PDMS Model Review Report (90%) - W008N | BK-W008N-PEDCO-110-PI-RT-0002 | BK-W008N-PEDCO-110-PI-RT-0002PDMS Model Review Report (90%) - W008N |  | 2022-05-25
MTO For Pipes - W008N | BK-W008N-PEDCO-110-PI-MT-0001 | BK-W008N-PEDCO-110-PI-MT-0001MTO For Pipes - W008N |  | 2022-05-25
MTO For Fittings - W008N | BK-W008N-PEDCO-110-PI-MT-0002 | BK-W008N-PEDCO-110-PI-MT-0002MTO For Fittings - W008N |  | 2022-05-25
MTO For Flanges - W008N | BK-W008N-PEDCO-110-PI-MT-0003 | BK-W008N-PEDCO-110-PI-MT-0003MTO For Flanges - W008N |  | 2022-05-25
MTO For Manual Valves - W008N | BK-W008N-PEDCO-110-PI-MT-0004 | BK-W008N-PEDCO-110-PI-MT-0004MTO For Manual Valves - W008N |  | 2022-05-25
MTO For Gaskets - W008N | BK-W008N-PEDCO-110-PI-MT-0005 | BK-W008N-PEDCO-110-PI-MT-0005MTO For Gaskets - W008N |  | 2022-05-25
MTO For Bolt & Nuts - W008N | BK-W008N-PEDCO-110-PI-MT-0006 | BK-W008N-PEDCO-110-PI-MT-0006MTO For Bolt & Nuts - W008N |  | 2022-05-25
Flow line Transversal Drawings - W008N | BK-W008N-PEDCO-110-PL-DW-0002 | BK-W008N-PEDCO-110-PL-DW-0002Flow line Transversal Drawings - W008N |  | 2022-05-25
Road Crossing Location List | BK-W008N-PEDCO-110-PL-LI-0001 | BK-W008N-PEDCO-110-PL-LI-0001Road Crossing Location List |  | 2022-05-25
MTO For Line Pipes (Flow lines) - W008N | BK-W008N-PEDCO-110-PL-MT-0001 | BK-W008N-PEDCO-110-PL-MT-0001MTO For Line Pipes (Flow lines) - W008N | 2021-08-22 | 2021-08-22
Instrument Location Layout Drawing - W008N | BK-W008N-PEDCO-110-IN-PY-0001 | BK-W008N-PEDCO-110-IN-PY-0001Instrument Location Layout Drawing - W008N |  | 2022-05-25
MTO For Instrument Tube and Fitting - W008N | BK-W008N-PEDCO-110-IN-MT-0001 | BK-W008N-PEDCO-110-IN-MT-0001MTO For Instrument Tube and Fitting - W008N | 2021-11-14 | 2022-01-12
MTO For Instrument Cable Tray - W008N | BK-W008N-PEDCO-110-IN-MT-0002 | BK-W008N-PEDCO-110-IN-MT-0002MTO For Instrument Cable Tray - W008N | 2021-11-14 | 2022-01-12
Hazardous Area Classification Layout - W008N | BK-W008N-PEDCO-110-SA-PY-0001 | BK-W008N-PEDCO-110-SA-PY-0001Hazardous Area Classification Layout - W008N |  | 2022-05-25
Safety & Fire Fighting Equipment Location Layout - W008N | BK-W008N-PEDCO-110-SA-PY-0002 | BK-W008N-PEDCO-110-SA-PY-0002Safety & Fire Fighting Equipment Location Layout - W008N |  | 2022-05-25
Escape Route & Safety Sign Layout - W008N | BK-W008N-PEDCO-110-SA-PY-0003 | BK-W008N-PEDCO-110-SA-PY-0003Escape Route & Safety Sign Layout - W008N |  | 2022-05-25
Hazard Source List - W008N | BK-W008N-PEDCO-110-SA-LI-0001 | BK-W008N-PEDCO-110-SA-LI-0001Hazard Source List - W008N | 2021-11-09 | 2022-05-25
MTO For Fire Fighting & Safety Equipment - W008N | BK-W008N-PEDCO-110-SA-MT-0001 | BK-W008N-PEDCO-110-SA-MT-0001MTO For Fire Fighting & Safety Equipment - W008N |  | 2022-05-25
MTO For Safety Sign - W008N | BK-W008N-PEDCO-110-SA-MT-0002 | BK-W008N-PEDCO-110-SA-MT-0002MTO For Safety Sign - W008N |  | 2022-05-25
Architectural Drawing For WHCP/HPU Shelter of Well Pads - W008N | BK-W008N-PEDCO-110-AR-DW-0001 | BK-W008N-PEDCO-110-AR-DW-0001Architectural Drawing For WHCP/HPU Shelter of Well Pads - W008N | 2022-02-26 | 2022-05-25
General Civil Layout -W008N | BK-W008N-PEDCO-110-CV-PY-0001 | BK-W008N-PEDCO-110-CV-PY-0001General Civil Layout -W008N |  | 2022-05-25
Civil and Structural drawings -W008N | BK-W008N-PEDCO-110-CV-PY-0002 | BK-W008N-PEDCO-110-CV-PY-0002Civil and Structural drawings -W008N |  | 2022-05-25
Rough Grading Plans -W008N | BK-W008N-PEDCO-110-CV-DW-0001 | BK-W008N-PEDCO-110-CV-DW-0001Rough Grading Plans -W008N |  | 2022-05-25
Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W008N | BK-W008N-PEDCO-110-CV-CN-0001 | BK-W008N-PEDCO-110-CV-CN-0001Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W008N |  | 2022-05-25
MTO For Civil Works | BK-W008N-PEDCO-110-CV-MT-0001 | BK-W008N-PEDCO-110-CV-MT-0001MTO For Civil Works |  | 2022-05-25
Platform Structure Drawing - W008N | BK-W008N-PEDCO-110-ST-DW-0002 | BK-W008N-PEDCO-110-ST-DW-0002Platform Structure Drawing - W008N |  | 2022-05-25
MTO For Structural Works - W008N | BK-W008N-PEDCO-110-ST-MT-0001 | BK-W008N-PEDCO-110-ST-MT-0001MTO For Structural Works - W008N |  | 2022-05-25
Geotechnical Investigation Report - W008N | BK-W008N-PEDCO-110-GT-RT-0001 | BK-W008N-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - W008N |  | 2022-05-25
Flow line Plan & Profile Drawings - W008N | BK-W008N-PEDCO-110-SU-DW-0001 | BK-W008N-PEDCO-110-SU-DW-0001Flow line Plan & Profile Drawings - W008N |  | 2022-05-25
PMR For Pipes - W008N | BK-W008N-PEDCO-110-PI-MR-0001 | BK-W008N-PEDCO-110-PI-MR-0001PMR For Pipes - W008N |  | 2022-05-25
TBE For Pipes - W008N | BK-W008N-PEDCO-110-PI-TB-0001 | BK-W008N-PEDCO-110-PI-TB-0001TBE For Pipes - W008N |  | 2022-05-25
PMR For Fittings - W008N | BK-W008N-PEDCO-110-PI-MR-0002 | BK-W008N-PEDCO-110-PI-MR-0002PMR For Fittings - W008N |  | 2022-05-25
TBE For Fitting - W008N | BK-W008N-PEDCO-110-PI-TB-0002 | BK-W008N-PEDCO-110-PI-TB-0002TBE For Fitting - W008N |  | 2022-05-25
PMR For Flanges - W008N | BK-W008N-PEDCO-110-PI-MR-0003 | BK-W008N-PEDCO-110-PI-MR-0003PMR For Flanges - W008N |  | 2022-05-25
TBE For Flanges - W008N | BK-W008N-PEDCO-110-PI-TB-0003 | BK-W008N-PEDCO-110-PI-TB-0003TBE For Flanges - W008N |  | 2022-05-25
PMR For Manual Valves - W008N | BK-W008N-PEDCO-110-PI-MR-0004 | BK-W008N-PEDCO-110-PI-MR-0004PMR For Manual Valves - W008N |  | 2022-05-25
TBE For Manual Valves - W008N | BK-W008N-PEDCO-110-PI-TB-0004 | BK-W008N-PEDCO-110-PI-TB-0004TBE For Manual Valves - W008N |  | 2022-05-25
PMR For Gaskets - W008N | BK-W008N-PEDCO-110-PI-MR-0005 | BK-W008N-PEDCO-110-PI-MR-0005PMR For Gaskets - W008N |  | 2022-05-25
TBE For Gaskets - W008N | BK-W008N-PEDCO-110-PI-TB-0005 | BK-W008N-PEDCO-110-PI-TB-0005TBE For Gaskets - W008N |  | 2022-05-25
PMR For Bolt/Nuts - W008N | BK-W008N-PEDCO-110-PI-MR-0006 | BK-W008N-PEDCO-110-PI-MR-0006PMR For Bolt/Nuts - W008N |  | 2022-05-25
TBE For Bolt/Nuts - W008N | BK-W008N-PEDCO-110-PI-TB-0006 | BK-W008N-PEDCO-110-PI-TB-0006TBE For Bolt/Nuts - W008N |  | 2022-05-25
PMR For Sampling Connection Set - W008N | BK-W008N-PEDCO-110-PI-MR-0007 | BK-W008N-PEDCO-110-PI-MR-0007PMR For Sampling Connection Set - W008N |  | 2022-05-25
TBE For Sampling Connection Set - W008N | BK-W008N-PEDCO-110-PI-TB-0007 | BK-W008N-PEDCO-110-PI-TB-0007TBE For Sampling Connection Set - W008N |  | 2022-05-25
PMR For Stone Trap - W008N | BK-W008N-PEDCO-110-PI-MR-0008 | BK-W008N-PEDCO-110-PI-MR-0008PMR For Stone Trap - W008N |  | 2022-05-25
TBE For Stone Trap - W008N | BK-W008N-PEDCO-110-PI-TB-0008 | BK-W008N-PEDCO-110-PI-TB-0008TBE For Stone Trap - W008N | 2022-05-24 | 2022-05-24
PMR For Pipe Support - W008N | BK-W008N-PEDCO-110-PI-MR-0009 | BK-W008N-PEDCO-110-PI-MR-0009PMR For Pipe Support - W008N |  | 2022-05-25
TBE For Pipe Support - W008N | BK-W008N-PEDCO-110-PI-TB-0009 | BK-W008N-PEDCO-110-PI-TB-0009TBE For Pipe Support - W008N |  | 2022-05-25
PMR For Line Pipes - W008N | BK-W008N-PEDCO-110-PL-MR-0001 | BK-W008N-PEDCO-110-PL-MR-0001PMR For Line Pipes - W008N |  | 2022-05-25
TBE For Line Pipes - W008N | BK-W008N-PEDCO-110-PL-TB-0001 | BK-W008N-PEDCO-110-PL-TB-0001TBE For Line Pipes - W008N | 2022-02-19 | 2022-05-14
PMR For Flow Line Support - W008N | BK-W008N-PEDCO-110-PL-MR-0002 | BK-W008N-PEDCO-110-PL-MR-0002PMR For Flow Line Support - W008N |  | 2022-05-25
TBE For Flow Line Support - W008N | BK-W008N-PEDCO-110-PL-TB-0002 | BK-W008N-PEDCO-110-PL-TB-0002TBE For Flow Line Support - W008N |  | 2022-05-25
PMR For WHCP/HPU - W008N | BK-W008N-PEDCO-110-IN-MR-0001 | BK-W008N-PEDCO-110-IN-MR-0001PMR For WHCP/HPU - W008N | 2021-11-15 | 2022-01-16
TBE/TBA For WHCP/HPU - W008N | BK-W008N-PEDCO-110-IN-TB-0001 | BK-W008N-PEDCO-110-IN-TB-0001TBE/TBA For WHCP/HPU - W008N | 2021-12-01 | 2022-02-19
PMR For Field Instrumentations - W008N | BK-W008N-PEDCO-110-IN-MR-0002 | BK-W008N-PEDCO-110-IN-MR-0002PMR For Field Instrumentations - W008N | 2021-12-13 | 2021-12-13
TBE/TBA For Field Instrumentations - W008N | BK-W008N-PEDCO-110-IN-TB-0002 | BK-W008N-PEDCO-110-IN-TB-0002TBE/TBA For Field Instrumentations - W008N |  | 2022-05-25
PMR For Instrument Bulk Items - W008N | BK-W008N-PEDCO-110-IN-MR-0003 | BK-W008N-PEDCO-110-IN-MR-0003PMR For Instrument Bulk Items - W008N | 2022-01-16 | 2022-01-16
TBE/TBA For Instrument Bulk Items-W008N | BK-W008N-PEDCO-110-IN-TB-0003 | BK-W008N-PEDCO-110-IN-TB-0003TBE/TBA For Instrument Bulk Items-W008N | 2022-02-02 | 2022-02-02
PMR For Fire Fighting and Safety Equipment - W008N | BK-W008N-PEDCO-110-SA-MR-0001 | BK-W008N-PEDCO-110-SA-MR-0001PMR For Fire Fighting and Safety Equipment - W008N |  | 2022-05-25
TBE For Fire Fighting and Safety Equipment - W008N | BK-W008N-PEDCO-110-SA-TB-0001 | BK-W008N-PEDCO-110-SA-TB-0001TBE For Fire Fighting and Safety Equipment - W008N |  | 2022-05-25
PMR For Fire Safety Sign - W008N | BK-W008N-PEDCO-110-SA-MR-0002 | BK-W008N-PEDCO-110-SA-MR-0002PMR For Fire Safety Sign - W008N |  | 2022-05-25
TBE For Fire Safety Sign - W008N | BK-W008N-PEDCO-110-SA-TB-0002 | BK-W008N-PEDCO-110-SA-TB-0002TBE For Fire Safety Sign - W008N |  | 2022-05-25
PMR For Steel Structure Items - W008N | BK-W008N-PEDCO-110-ST-MR-0001 | BK-W008N-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - W008N |  | 2022-05-25
TBE For Steel Structure Items - W008N | BK-W008N-PEDCO-110-ST-TB-0001 | BK-W008N-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - W008N |  | 2022-05-25
PMR For Anchor Bolts - W008N | BK-W008N-PEDCO-110-ST-MR-0002 | BK-W008N-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - W008N |  | 2022-05-25
TBE For Anchor Bolts - W008N | BK-W008N-PEDCO-110-ST-TB-0002 | BK-W008N-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - W008N |  | 2022-05-25
PMR For Geomembrane - W008N | BK-W008N-PEDCO-110-CV-MR-0001 | BK-W008N-PEDCO-110-CV-MR-0001PMR For Geomembrane - W008N |  | 2022-05-25
TBE For Geomembrane - W008N | BK-W008N-PEDCO-110-CV-TB-0001 | BK-W008N-PEDCO-110-CV-TB-0001TBE For Geomembrane - W008N |  | 2022-05-25
PMR For Geotextile - W008N | BK-W008N-PEDCO-110-CV-MR-0002 | BK-W008N-PEDCO-110-CV-MR-0002PMR For Geotextile - W008N |  | 2022-05-25
TBE For Geotextile - W008N | BK-W008N-PEDCO-110-CV-TB-0002 | BK-W008N-PEDCO-110-CV-TB-0002TBE For Geotextile - W008N |  | 2022-05-25
Pre-Commissioning, Commissioning & Startup Procedure - W008N | BK-W008N-PEDCO-110-CO-PR-0001 | BK-W008N-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - W008N |  | 2022-05-25
Technical/Site Queries | BK-W008N-PEDCO-110-GE-TQ-0001 | BK-W008N-PEDCO-110-GE-TQ-0001Technical/Site Queries |  | 2022-05-25
As-Built Document Booklets - W008N | BK-W008N-PEDCO-110-GE-DO-0001 | BK-W008N-PEDCO-110-GE-DO-0001As-Built Document Booklets - W008N |  | 2022-05-25
Operating Manual - W008N | BK-W008N-PEDCO-110-GE-ML-0001 | BK-W008N-PEDCO-110-GE-ML-0001Operating Manual - W008N |  | 2022-05-25
As-Built Document Booklets - W008N | BK-W008N-PEDCO-110-GE-DO-0001 | BK-W008N-PEDCO-110-GE-DO-0001As-Built Document Booklets - W008N
Final Engineering Dossier - W008N | BK-W008N-PEDCO-110-GE-DO-0002 | BK-W008N-PEDCO-110-GE-DO-0002Final Engineering Dossier - W008N |  | 2022-05-25
Process Description - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-DP-0001 | BK-W007S-PEDCO-110-PR-DP-0001Process Description - Extension of Binak B/C Manifold |  | 2022-05-25
Calculation book for (CV,PSV,Pump & Line sizing) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-CN-0001 | BK-W007S-PEDCO-110-PR-CN-0001Calculation book for (CV,PSV,Pump & Line sizing) - Extension of Binak B/C Manifold | 2022-02-23 | 2022-05-25
ESD Block Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-DG-0001 | BK-W007S-PEDCO-110-PR-DG-0001ESD Block Diagram - Extension of Binak B/C Manifold |  | 2022-05-25
Process Flow Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-PF-0001 | BK-W007S-PEDCO-110-PR-PF-0001Process Flow Diagram - Extension of Binak B/C Manifold | 2021-08-09 | 2022-05-25
P&ID - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-PI-0001 | BK-W007S-PEDCO-110-PR-PI-0001P&ID - Extension of Binak B/C Manifold | 2021-10-26 | 2022-05-25
Cause & Effect Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-DG-0002 | BK-W007S-PEDCO-110-PR-DG-0002Cause & Effect Diagram - Extension of Binak B/C Manifold |  | 2022-05-25
Process Flow Diagram - W007S | BK-W007S-PEDCO-110-PR-PF-0002 | BK-W007S-PEDCO-110-PR-PF-0002Process Flow Diagram - W007S | 2021-08-24 | 2022-05-25
P&ID - W007S | BK-W007S-PEDCO-110-PR-PI-0002 | BK-W007S-PEDCO-110-PR-PI-0002P&ID - W007S | 2021-08-24 | 2022-05-25
P&ID for Diesel Oil Drum- W007S | BK-W007S-PEDCO-110-PR-PI-0003 | BK-W007S-PEDCO-110-PR-PI-0003P&ID for Diesel Oil Drum- W007S | 2021-11-16 | 2022-05-25
P&ID for Potable Water Tank - W007S | BK-W007S-PEDCO-110-PR-PI-0004 | BK-W007S-PEDCO-110-PR-PI-0004P&ID for Potable Water Tank - W007S | 2021-11-16 | 2022-05-25
Line List - W007S & Manifold Extension | BK-W007S-PEDCO-110-PR-LI-0001 | BK-W007S-PEDCO-110-PR-LI-0001Line List - W007S & Manifold Extension | 2022-04-20 | 2022-05-25
Tie-In List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-LI-0002 | BK-W007S-PEDCO-110-PR-LI-0002Tie-In List - Extension of Binak B/C Manifold | 2022-04-20 | 2022-05-25
Line List - W007S | BK-W007S-PEDCO-110-PR-LI-0003 | BK-W007S-PEDCO-110-PR-LI-0003Line List - W007S | 2021-08-24 | 2022-05-25
Flow line Hydraulic Calculation Report | BK-W007S-PEDCO-110-PR-RT-0001 | BK-W007S-PEDCO-110-PR-RT-0001Flow line Hydraulic Calculation Report | 2021-10-30 | 2022-05-25
Process Data Sheets For Instrument Devices - W007S & Extension Manifold | BK-W007S-PEDCO-110-PR-DT-0001 | BK-W007S-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - W007S & Extension Manifold | 2022-04-12 | 2022-05-25
Specification For Positive Displacement Rotary Pumps | BK-W007S-PEDCO-110-ME-SP-0001 | BK-W007S-PEDCO-110-ME-SP-0001Specification For Positive Displacement Rotary Pumps | 2022-02-21 | 2022-05-25
Data Sheets For Oil Sump Pump - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ME-DT-0001 | BK-W007S-PEDCO-110-ME-DT-0001Data Sheets For Oil Sump Pump - Extension of Binak B/C Manifold | 2022-03-14 | 2022-05-25
HVAC Calculation Note For Switchgear Building - W007S | BK-W007S-PEDCO-110-HV-CN-0001 | BK-W007S-PEDCO-110-HV-CN-0001HVAC Calculation Note For Switchgear Building - W007S | 2022-04-04 | 2022-05-25
HVAC Calculation Note For Security Building - W007S | BK-W007S-PEDCO-110-HV-CN-0002 | BK-W007S-PEDCO-110-HV-CN-0002HVAC Calculation Note For Security Building - W007S |  | 2022-05-25
Data Sheets For Main HVAC Equipment - W007S | BK-W007S-PEDCO-110-HV-DT-0001 | BK-W007S-PEDCO-110-HV-DT-0001Data Sheets For Main HVAC Equipment - W007S |  | 2022-05-25
HVAC System Layout For Switchgear Building - W007S | BK-W007S-PEDCO-110-HV-PY-0001 | BK-W007S-PEDCO-110-HV-PY-0001HVAC System Layout For Switchgear Building - W007S | 2022-04-19 | 2022-05-25
HVAC System Layout For Security Building - W007S | BK-W007S-PEDCO-110-HV-PY-0002 | BK-W007S-PEDCO-110-HV-PY-0002HVAC System Layout For Security Building - W007S |  | 2022-05-25
Plumbing & Sewage Piping Layout For Switchgear Building - W007S | BK-W007S-PEDCO-110-HV-PY-0003 | BK-W007S-PEDCO-110-HV-PY-0003Plumbing & Sewage Piping Layout For Switchgear Building - W007S |  | 2022-05-25
Plumbing & Sewage Piping Layout For Security Building - W007S | BK-W007S-PEDCO-110-HV-PY-0004 | BK-W007S-PEDCO-110-HV-PY-0004Plumbing & Sewage Piping Layout For Security Building - W007S |  | 2022-05-25
MTO For Building HVAC & Plumbing Systems - W007S | BK-W007S-PEDCO-110-HV-MT-0001 | BK-W007S-PEDCO-110-HV-MT-0001MTO For Building HVAC & Plumbing Systems - W007S |  | 2022-05-25
Plot Plan Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-PY-0001 | BK-W007S-PEDCO-110-PI-PY-0001Plot Plan Drawing - Extension of Binak B/C Manifold | 2022-01-15 | 2022-05-25
Piping Plan Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-DW-0001 | BK-W007S-PEDCO-110-PI-DW-0001Piping Plan Drawing - Extension of Binak B/C Manifold |  | 2022-05-25
Isometric Drawings - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-DW-0002 | BK-W007S-PEDCO-110-PI-DW-0002Isometric Drawings - Extension of Binak B/C Manifold |  | 2022-05-25
Plot Plan Drawing - W007S | BK-W007S-PEDCO-110-PI-PY-0002 | BK-W007S-PEDCO-110-PI-PY-0002Plot Plan Drawing - W007S |  | 2022-05-25
Piping Plan - W007S | BK-W007S-PEDCO-110-PI-DW-0003 | BK-W007S-PEDCO-110-PI-DW-0003Piping Plan - W007S |  | 2022-05-25
Isometric Drawings - W007S | BK-W007S-PEDCO-110-PI-DW-0004 | BK-W007S-PEDCO-110-PI-DW-0004Isometric Drawings - W007S |  | 2022-05-25
Material Flow Diagram - W007S | BK-W007S-PEDCO-110-PI-DG-0001 | BK-W007S-PEDCO-110-PI-DG-0001Material Flow Diagram - W007S | 2021-11-08 | 2022-05-25
Material Flow Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-DG-0002 | BK-W007S-PEDCO-110-PI-DG-0002Material Flow Diagram - Extension of Binak B/C Manifold | 2022-05-11 | 2022-05-25
Critical Line List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-LI-0001 | BK-W007S-PEDCO-110-PI-LI-0001Critical Line List - Extension of Binak B/C Manifold |  | 2022-05-25
Piping Tie-In List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-LI-0002 | BK-W007S-PEDCO-110-PI-LI-0002Piping Tie-In List - Extension of Binak B/C Manifold |  | 2022-05-25
Piping Support List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-LI-0003 | BK-W007S-PEDCO-110-PI-LI-0003Piping Support List - Extension of Binak B/C Manifold |  | 2022-05-25
Piping Support List - W007S | BK-W007S-PEDCO-110-PI-LI-0004 | BK-W007S-PEDCO-110-PI-LI-0004Piping Support List - W007S |  | 2022-05-25
Critical Line List - W007S | BK-W007S-PEDCO-110-PI-LI-0005 | BK-W007S-PEDCO-110-PI-LI-0005Critical Line List - W007S |  | 2022-05-25
PDMS Model Review Report (30%) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-RT-0001 | BK-W007S-PEDCO-110-PI-RT-0001PDMS Model Review Report (30%) - Extension of Binak B/C Manifold | 2022-04-09 | 2022-05-25
PDMS Model Review Report (60%) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-RT-0002 | BK-W007S-PEDCO-110-PI-RT-0002PDMS Model Review Report (60%) - Extension of Binak B/C Manifold |  | 2022-05-25
PDMS Model Review Report (90%) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-RT-0003 | BK-W007S-PEDCO-110-PI-RT-0003PDMS Model Review Report (90%) - Extension of Binak B/C Manifold |  | 2022-05-25
PDMS Model Review Report | BK-W007S-PEDCO-110-PI-RT-0004 | BK-W007S-PEDCO-110-PI-RT-0004PDMS Model Review Report |  | 2022-05-25
PDMS Model Review Report (60%) - W007S | BK-W007S-PEDCO-110-PI-RT-0005 | BK-W007S-PEDCO-110-PI-RT-0005PDMS Model Review Report (60%) - W007S |  | 2022-05-25
PDMS Model Review Report (90%) - W007S | BK-W007S-PEDCO-110-PI-RT-0006 | BK-W007S-PEDCO-110-PI-RT-0006PDMS Model Review Report (90%) - W007S |  | 2022-05-25
Stress Analysis Calculations Report For Manifold area | BK-W007S-PEDCO-110-PI-RT-0007 | BK-W007S-PEDCO-110-PI-RT-0007Stress Analysis Calculations Report For Manifold area |  | 2022-05-25
MTO For Pipes - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0001 | BK-W007S-PEDCO-110-PI-MT-0001MTO For Pipes - Manifold & W007S |  | 2022-05-25
MTO For Fittings - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0002 | BK-W007S-PEDCO-110-PI-MT-0002MTO For Fittings - Manifold & W007S |  | 2022-05-25
MTO For Flanges - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0003 | BK-W007S-PEDCO-110-PI-MT-0003MTO For Flanges - Manifold & W007S |  | 2022-05-25
MTO For Manual Valves - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0004 | BK-W007S-PEDCO-110-PI-MT-0004MTO For Manual Valves - Manifold & W007S |  | 2022-05-25
MTO For Gaskets - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0005 | BK-W007S-PEDCO-110-PI-MT-0005MTO For Gaskets - Manifold & W007S |  | 2022-05-25
MTO For Bolt & Nuts - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0006 | BK-W007S-PEDCO-110-PI-MT-0006MTO For Bolt & Nuts - Manifold & W007S |  | 2022-05-25
Flow line Transversal Drawings - W007S | BK-W007S-PEDCO-110-PL-DW-0002 | BK-W007S-PEDCO-110-PL-DW-0002Flow line Transversal Drawings - W007S |  | 2022-05-25
Road Crossing Location List | BK-W007S-PEDCO-110-PL-LI-0001 | BK-W007S-PEDCO-110-PL-LI-0001Road Crossing Location List |  | 2022-05-25
MTO For Line Pipes (Flow lines) - W007S | BK-W007S-PEDCO-110-PL-MT-0001 | BK-W007S-PEDCO-110-PL-MT-0001MTO For Line Pipes (Flow lines) - W007S | 2021-08-22 | 2021-08-22
Data Sheets For Temperature Gauge - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0001 | BK-W007S-PEDCO-110-IN-DT-0001Data Sheets For Temperature Gauge - Extension of Binak B/C Manifold | 2021-12-07 | 2022-05-25
Data Sheets For Pressure & Diff. Pressure Gauge - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0002 | BK-W007S-PEDCO-110-IN-DT-0002Data Sheets For Pressure & Diff. Pressure Gauge - Extension of Binak B/C Manifold | 2021-12-07 | 2022-05-25
Data Sheets For Pressure Transmitter - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0003 | BK-W007S-PEDCO-110-IN-DT-0003Data Sheets For Pressure Transmitter - Extension of Binak B/C Manifold | 2021-12-07 | 2022-05-25
Data Sheets For Pressure & Safety Relief Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0004 | BK-W007S-PEDCO-110-IN-DT-0004Data Sheets For Pressure & Safety Relief Valves - Extension of Binak B/C Manifold |  | 2022-05-25
Data Sheets For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0005 | BK-W007S-PEDCO-110-IN-DT-0005Data Sheets For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold | 2022-03-09 | 2022-05-25
Data Sheets For Control/Regulator valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0006 | BK-W007S-PEDCO-110-IN-DT-0006Data Sheets For Control/Regulator valves - Extension of Binak B/C Manifold | 2022-03-07 | 2022-05-25
Data Sheets For Flow Transmitter/Diff. Pressure Transmitter - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0007 | BK-W007S-PEDCO-110-IN-DT-0007Data Sheets For Flow Transmitter/Diff. Pressure Transmitter - Extension of Binak B/C Manifold | 2021-12-07 | 2022-05-25
Data Sheets For Orifice Plate/Restriction Orifice - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0008 | BK-W007S-PEDCO-110-IN-DT-0008Data Sheets For Orifice Plate/Restriction Orifice - Extension of Binak B/C Manifold |  | 2022-05-25
Data Sheets For Corrosion Coupon/ Probe - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0009 | BK-W007S-PEDCO-110-IN-DT-0009Data Sheets For Corrosion Coupon/ Probe - Extension of Binak B/C Manifold | 2022-03-09 | 2022-05-25
Data Sheets For F&G Devices - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0010 | BK-W007S-PEDCO-110-IN-DT-0010Data Sheets For F&G Devices - Extension of Binak B/C Manifold |  | 2022-05-25
Data Sheets For Pressure Switch and Differential Pressure Switch - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0011 | BK-W007S-PEDCO-110-IN-DT-0011Data Sheets For Pressure Switch and Differential Pressure Switch - Extension of Binak B/C Manifold |  | 2022-05-25
DATA SHEETS FOR DISPLACER LEVEL TRANSMITTER - EXTENSION OF BINAK BC MANIFOLD | BK-W007S-PEDCO-110-IN-DT-0012 | BK-W007S-PEDCO-110-IN-DT-0012DATA SHEETS FOR DISPLACER LEVEL TRANSMITTER - EXTENSION OF BINAK BC MANIFOLD | 2022-01-01 | 2022-05-25
Typical Instrument Installation Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DW-0001 | BK-W007S-PEDCO-110-IN-DW-0001Typical Instrument Installation Drawing - Extension of Binak B/C Manifold | 2022-03-09 | 2022-05-11
Block Diagram Configuration For Control/ESD/F&G System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0001 | BK-W007S-PEDCO-110-IN-DG-0001Block Diagram Configuration For Control/ESD/F&G System - Extension of Binak B/C Manifold | 2021-09-01 | 2022-05-25
Instrument Earthing Typical Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0002 | BK-W007S-PEDCO-110-IN-DG-0002Instrument Earthing Typical Diagram - Extension of Binak B/C Manifold | 2022-01-01 | 2022-04-20
Instrument Hook-up Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0003 | BK-W007S-PEDCO-110-IN-DG-0003Instrument Hook-up Diagram - Extension of Binak B/C Manifold |  | 2022-05-25
ESD Level Hierarchy - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0004 | BK-W007S-PEDCO-110-IN-DG-0004ESD Level Hierarchy - Extension of Binak B/C Manifold | 2022-04-24 | 2022-05-25
ESD System Loop Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0005 | BK-W007S-PEDCO-110-IN-DG-0005ESD System Loop Diagram - Extension of Binak B/C Manifold |  | 2022-05-25
Control System Loop Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0006 | BK-W007S-PEDCO-110-IN-DG-0006Control System Loop Diagram - Extension of Binak B/C Manifold |  | 2022-05-25
F&G System Loop Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0007 | BK-W007S-PEDCO-110-IN-DG-0007F&G System Loop Diagram - Extension of Binak B/C Manifold |  | 2022-05-25
Instrument Air Piping and Air Header Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0008 | BK-W007S-PEDCO-110-IN-DG-0008Instrument Air Piping and Air Header Diagram - Extension of Binak B/C Manifold |  | 2022-05-25
Instrument & F&G Junction Box Termination Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0009 | BK-W007S-PEDCO-110-IN-DG-0009Instrument & F&G Junction Box Termination Diagram - Extension of Binak B/C Manifold | 2022-05-14 | 2022-05-25
F&G Cause and Effect Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0010 | BK-W007S-PEDCO-110-IN-DG-0010F&G Cause and Effect Diagram - Extension of Binak B/C Manifold |  | 2022-05-25
Control System Logic Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LD-0001 | BK-W007S-PEDCO-110-IN-LD-0001Control System Logic Diagram - Extension of Binak B/C Manifold | 2022-04-10 | 2022-05-25
ESD Logic Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LD-0002 | BK-W007S-PEDCO-110-IN-LD-0002ESD Logic Diagram - Extension of Binak B/C Manifold |  | 2022-05-25
Control Room Layout & Arrangement Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0001 | BK-W007S-PEDCO-110-IN-PY-0001Control Room Layout & Arrangement Drawing - Extension of Binak B/C Manifold | 2022-05-11 | 2022-05-25
Control Room Cable Route Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0002 | BK-W007S-PEDCO-110-IN-PY-0002Control Room Cable Route Layout - Extension of Binak B/C Manifold |  | 2022-05-25
Instrument Location Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0003 | BK-W007S-PEDCO-110-IN-PY-0003Instrument Location Layout - Extension of Binak B/C Manifold | 2022-05-17 | 2022-05-25
Instrument/F&G Cable Trench/Route Layout Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0004 | BK-W007S-PEDCO-110-IN-PY-0004Instrument/F&G Cable Trench/Route Layout Drawing - Extension of Binak B/C Manifold |  | 2022-05-25
F&G Location Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0005 | BK-W007S-PEDCO-110-IN-PY-0005F&G Location Layout - Extension of Binak B/C Manifold |  | 2022-05-25
Instrument Location Layout Drawing - W007S | BK-W007S-PEDCO-110-IN-PY-0006 | BK-W007S-PEDCO-110-IN-PY-0006Instrument Location Layout Drawing - W007S |  | 2022-05-25
Wiring Diagram; Interposing Relay Panel (IRP) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0011 | BK-W007S-PEDCO-110-IN-DG-0011Wiring Diagram; Interposing Relay Panel (IRP) - Extension of Binak B/C Manifold |  | 2022-05-25
I/O List For Control System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0002 | BK-W007S-PEDCO-110-IN-LI-0002I/O List For Control System - Extension of Binak B/C Manifold | 2021-11-03 | 2022-05-25
I/O List For ESD Systems - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0003 | BK-W007S-PEDCO-110-IN-LI-0003I/O List For ESD Systems - Extension of Binak B/C Manifold | 2021-11-03 | 2022-05-25
I/O List For F&G Systems - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0004 | BK-W007S-PEDCO-110-IN-LI-0004I/O List For F&G Systems - Extension of Binak B/C Manifold |  | 2022-05-25
Panels & Junction Box List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0005 | BK-W007S-PEDCO-110-IN-LI-0005Panels & Junction Box List - Extension of Binak B/C Manifold |  | 2022-05-25
Set Point & Alarm List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0006 | BK-W007S-PEDCO-110-IN-LI-0006Set Point & Alarm List - Extension of Binak B/C Manifold |  | 2022-05-25
I&C Power Consumption Summary - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0007 | BK-W007S-PEDCO-110-IN-LI-0007I&C Power Consumption Summary - Extension of Binak B/C Manifold | 2022-02-28 | 2022-05-25
F&G Detector List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0008 | BK-W007S-PEDCO-110-IN-LI-0008F&G Detector List - Extension of Binak B/C Manifold |  | 2022-05-25
Instrument /F&G Cable List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0009 | BK-W007S-PEDCO-110-IN-LI-0009Instrument /F&G Cable List - Extension of Binak B/C Manifold |  | 2022-05-25
MTO for Bulk Item and Installation Accessories - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0001 | BK-W007S-PEDCO-110-IN-MT-0001MTO for Bulk Item and Installation Accessories - W007S & Manifold |  | 2022-05-25
MTO For Instrument/F&G Cable - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0002 | BK-W007S-PEDCO-110-IN-MT-0002MTO For Instrument/F&G Cable - W007S & Manifold |  | 2022-05-25
MTO For Instrument/F&G Junction box and Gland - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0003 | BK-W007S-PEDCO-110-IN-MT-0003MTO For Instrument/F&G Junction box and Gland - W007S & Manifold |  | 2022-05-25
MTO For Instrument Tube and Fitting - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0004 | BK-W007S-PEDCO-110-IN-MT-0004MTO For Instrument Tube and Fitting - W007S & Manifold |  | 2022-05-25
MTO For Instrument Cable Tray/Ladder - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0005 | BK-W007S-PEDCO-110-IN-MT-0005MTO For Instrument Cable Tray/Ladder - W007S & Manifold |  | 2022-05-25
Hazardous Area Classification Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-SA-PY-0001 | BK-W007S-PEDCO-110-SA-PY-0001Hazardous Area Classification Layout - Extension of Binak B/C Manifold | 2022-03-12 | 2022-05-25
Safety & Fire Fighting Equipment Location Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-SA-PY-0002 | BK-W007S-PEDCO-110-SA-PY-0002Safety & Fire Fighting Equipment Location Layout - Extension of Binak B/C Manifold | 2022-04-17 | 2022-05-25
Escape Route & Safety Sign Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-SA-PY-0003 | BK-W007S-PEDCO-110-SA-PY-0003Escape Route & Safety Sign Layout - Extension of Binak B/C Manifold | 2022-04-17 | 2022-05-25
Hazardous Area Classification Layout - W007S | BK-W007S-PEDCO-110-SA-PY-0004 | BK-W007S-PEDCO-110-SA-PY-0004Hazardous Area Classification Layout - W007S |  | 2022-05-25
Safety & Fire Fighting Equipment Location Layout - W007S | BK-W007S-PEDCO-110-SA-PY-0005 | BK-W007S-PEDCO-110-SA-PY-0005Safety & Fire Fighting Equipment Location Layout - W007S |  | 2022-05-25
Escape Route & Safety Sign Layout - W007S | BK-W007S-PEDCO-110-SA-PY-0006 | BK-W007S-PEDCO-110-SA-PY-0006Escape Route & Safety Sign Layout - W007S |  | 2022-05-25
Hazard Source List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-SA-LI-0001 | BK-W007S-PEDCO-110-SA-LI-0001Hazard Source List - Extension of Binak B/C Manifold | 2021-11-09 | 2022-05-25
Hazard Source List - W007S | BK-W007S-PEDCO-110-SA-LI-0002 | BK-W007S-PEDCO-110-SA-LI-0002Hazard Source List - W007S | 2021-11-09 | 2022-05-25
MTO For Fire Fighting & Safety Equipment - Manifold & W007S | BK-W007S-PEDCO-110-SA-MT-0002 | BK-W007S-PEDCO-110-SA-MT-0002MTO For Fire Fighting & Safety Equipment - Manifold & W007S |  | 2022-05-25
MTO For Safety Sign - W007S | BK-W007S-PEDCO-110-SA-MT-0003 | BK-W007S-PEDCO-110-SA-MT-0003MTO For Safety Sign - W007S |  | 2022-05-25
Earthing Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-PY-0001 | BK-W007S-PEDCO-110-EL-PY-0001Earthing Layout - Extension of Binak B/C Manifold |  | 2022-05-25
LV Switchgear/MCC Expansion SLD - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-SL-0001 | BK-W007S-PEDCO-110-EL-SL-0001LV Switchgear/MCC Expansion SLD - Extension of Binak B/C Manifold |  | 2022-05-25
UPS Single Line Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-SL-0002 | BK-W007S-PEDCO-110-EL-SL-0002UPS Single Line Diagram - Extension of Binak B/C Manifold | 2022-03-26 | 2022-05-25
DC Charger Single Line Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-SL-0003 | BK-W007S-PEDCO-110-EL-SL-0003DC Charger Single Line Diagram - Extension of Binak B/C Manifold | 2022-03-26 | 2022-05-25
Interconnection Wiring Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-DG-0001 | BK-W007S-PEDCO-110-EL-DG-0001Interconnection Wiring Diagram - Extension of Binak B/C Manifold |  | 2022-05-25
Area Electrical Cable Route & Section Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-PY-0002 | BK-W007S-PEDCO-110-EL-PY-0002Area Electrical Cable Route & Section Layout - Extension of Binak B/C Manifold |  | 2022-05-25
Electrical Equipment Arrangement Layout In Switchgear Building - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-PY-0003 | BK-W007S-PEDCO-110-EL-PY-0003Electrical Equipment Arrangement Layout In Switchgear Building - Extension of Binak B/C Manifold |  | 2022-05-25
Earthing & Lightning Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-PY-0004 | BK-W007S-PEDCO-110-EL-PY-0004Earthing & Lightning Layout - Extension of Binak B/C Manifold |  | 2022-05-25
Electrical Load List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-LI-0001 | BK-W007S-PEDCO-110-EL-LI-0001Electrical Load List - Extension of Binak B/C Manifold | 2022-03-07 | 2022-05-25
Electrical Power & Control Cable List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-LI-0002 | BK-W007S-PEDCO-110-EL-LI-0002Electrical Power & Control Cable List - Extension of Binak B/C Manifold |  | 2022-05-25
MTO For Earthing & Lightning Systems - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0001 | BK-W007S-PEDCO-110-EL-MT-0001MTO For Earthing & Lightning Systems - Manifold & W007S |  | 2022-05-25
MTO For Lighting & Small Powers - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0002 | BK-W007S-PEDCO-110-EL-MT-0002MTO For Lighting & Small Powers - Manifold & W007S | 2022-05-18 | 2022-05-18
MTO For Power & Control Cables - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0003 | BK-W007S-PEDCO-110-EL-MT-0003MTO For Power & Control Cables - Manifold & W007S |  | 2022-05-25
MTO For Tray/Ladder and Accessories - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0004 | BK-W007S-PEDCO-110-EL-MT-0004MTO For Tray/Ladder and Accessories - Manifold & W007S |  | 2022-05-25
MTO For Electrical Bulk Items - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0005 | BK-W007S-PEDCO-110-EL-MT-0005MTO For Electrical Bulk Items - Manifold & W007S |  | 2022-05-25
MTO For Transmission Over Head Line - W007S | BK-W007S-PEDCO-110-EL-MT-0006 | BK-W007S-PEDCO-110-EL-MT-0006MTO For Transmission Over Head Line - W007S |  | 2022-05-25
Architectural Drawing For Diesel Generator Shelter of Well Pads - W007S | BK-W007S-PEDCO-110-AR-DW-0001 | BK-W007S-PEDCO-110-AR-DW-0001Architectural Drawing For Diesel Generator Shelter of Well Pads - W007S | 2022-05-01 | 2022-05-25
Architectural Drawing For WHCP/HPU Shelter of Well Pads - W007S | BK-W007S-PEDCO-110-AR-DW-0002 | BK-W007S-PEDCO-110-AR-DW-0002Architectural Drawing For WHCP/HPU Shelter of Well Pads - W007S |  | 2022-05-25
Architectural Drawing For Switchgear Building of Well Pads - W007S | BK-W007S-PEDCO-110-AR-DW-0003 | BK-W007S-PEDCO-110-AR-DW-0003Architectural Drawing For Switchgear Building of Well Pads - W007S | 2022-03-09 | 2022-05-25
Architectural Drawing For Security Building of Well Pads - W007S | BK-W007S-PEDCO-110-AR-DW-0004 | BK-W007S-PEDCO-110-AR-DW-0004Architectural Drawing For Security Building of Well Pads - W007S | 2022-05-01 | 2022-05-25
MTO For Architectural Works - W007S | BK-W007S-PEDCO-110-AR-MT-0001 | BK-W007S-PEDCO-110-AR-MT-0001MTO For Architectural Works - W007S |  | 2022-05-25
General Civil Layout - W007S | BK-W007S-PEDCO-110-CV-PY-0001 | BK-W007S-PEDCO-110-CV-PY-0001General Civil Layout - W007S |  | 2022-05-25
Civil and Structural drawings - W007S | BK-W007S-PEDCO-110-CV-PY-0002 | BK-W007S-PEDCO-110-CV-PY-0002Civil and Structural drawings - W007S |  | 2022-05-25
Rough Grading Plans -W007S | BK-W007S-PEDCO-110-CV-DW-0001 | BK-W007S-PEDCO-110-CV-DW-0001Rough Grading Plans -W007S |  | 2022-05-25
Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W007S | BK-W007S-PEDCO-110-CV-CN-0001 | BK-W007S-PEDCO-110-CV-CN-0001Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W007S |  | 2022-05-25
MTO For Civil Works - W007S | BK-W007S-PEDCO-110-CV-MT-0001 | BK-W007S-PEDCO-110-CV-MT-0001MTO For Civil Works - W007S |  | 2022-05-25
SITE VISIT REPORT - MANIFOLD EXTENSION | BK-W007S-PEDCO-110-CV-RT-0001 | BK-W007S-PEDCO-110-CV-RT-0001SITE VISIT REPORT - MANIFOLD EXTENSION | 2022-04-18 | 2022-05-25
Pipe Supports Foundation Drawing For Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ST-DW-0001 | BK-W007S-PEDCO-110-ST-DW-0001Pipe Supports Foundation Drawing For Extension of Binak B/C Manifold |  | 2022-05-25
Pipe Supports Structure Drawing For Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ST-DW-0002 | BK-W007S-PEDCO-110-ST-DW-0002Pipe Supports Structure Drawing For Extension of Binak B/C Manifold |  | 2022-05-25
Access Platforms Structure Plan & Details For Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ST-DW-0003 | BK-W007S-PEDCO-110-ST-DW-0003Access Platforms Structure Plan & Details For Extension of Binak B/C Manifold |  | 2022-05-25
Access Platforms Foundation Drawing For Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ST-DW-0004 | BK-W007S-PEDCO-110-ST-DW-0004Access Platforms Foundation Drawing For Extension of Binak B/C Manifold |  | 2022-05-25
Fuel Oil Storage Drum Detail Drawing For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0007 | BK-W007S-PEDCO-110-ST-DW-0007Fuel Oil Storage Drum Detail Drawing For Well Pads - W007S |  | 2022-05-25
Foundation Drawing For Security Building For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0008 | BK-W007S-PEDCO-110-ST-DW-0008Foundation Drawing For Security Building For Well Pads - W007S |  | 2022-05-25
Structural Drawing For Security Building For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0009 | BK-W007S-PEDCO-110-ST-DW-0009Structural Drawing For Security Building For Well Pads - W007S |  | 2022-05-25
Foundation Drawing For Switchgear Building For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0010 | BK-W007S-PEDCO-110-ST-DW-0010Foundation Drawing For Switchgear Building For Well Pads - W007S |  | 2022-05-25
Structural Drawing For Switchgear Building For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0011 | BK-W007S-PEDCO-110-ST-DW-0011Structural Drawing For Switchgear Building For Well Pads - W007S |  | 2022-05-25
Foundation Drawing For Potable Water Tank For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0012 | BK-W007S-PEDCO-110-ST-DW-0012Foundation Drawing For Potable Water Tank For Well Pads - W007S |  | 2022-05-25
Foundation Drawing For Diesel Generator Shelter For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0013 | BK-W007S-PEDCO-110-ST-DW-0013Foundation Drawing For Diesel Generator Shelter For Well Pads - W007S |  | 2022-05-25
Structural Drawing For Diesel Generator Shelter For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0014 | BK-W007S-PEDCO-110-ST-DW-0014Structural Drawing For Diesel Generator Shelter For Well Pads - W007S |  | 2022-05-25
Platform Structure Drawing - W007S | BK-W007S-PEDCO-110-ST-DW-0016 | BK-W007S-PEDCO-110-ST-DW-0016Platform Structure Drawing - W007S |  | 2022-05-25
Foundation Drawing For Oil Pump | BK-W007S-PEDCO-110-ST-DW-0018 | BK-W007S-PEDCO-110-ST-DW-0018Foundation Drawing For Oil Pump |  | 2022-05-25
Sump Pit Structural Drawing for Oil Pump | BK-W007S-PEDCO-110-ST-DW-0019 | BK-W007S-PEDCO-110-ST-DW-0019Sump Pit Structural Drawing for Oil Pump |  | 2022-05-25
Foundation Drawing For Transmission Line Tower - W007S | BK-W007S-PEDCO-110-ST-DW-0020 | BK-W007S-PEDCO-110-ST-DW-0020Foundation Drawing For Transmission Line Tower - W007S |  | 2022-05-25
MTO For Structural Works - W007S & Manifold Extension | BK-W007S-PEDCO-110-ST-MT-0001 | BK-W007S-PEDCO-110-ST-MT-0001MTO For Structural Works - W007S & Manifold Extension |  | 2022-05-25
Geotechnical Investigation Report - W007S | BK-W007S-PEDCO-110-GT-RT-0001 | BK-W007S-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - W007S |  | 2022-05-25
Flow line Plan & Profile Drawings - W007S | BK-W007S-PEDCO-110-SU-DW-0001 | BK-W007S-PEDCO-110-SU-DW-0001Flow line Plan & Profile Drawings - W007S |  | 2022-05-25
Over Head Line Plan and Profile - W007S | BK-W007S-PEDCO-110-SU-DW-0002 | BK-W007S-PEDCO-110-SU-DW-0002Over Head Line Plan and Profile - W007S |  | 2022-05-25
PMR For Pumps - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ME-MR-0001 | BK-W007S-PEDCO-110-ME-MR-0001PMR For Pumps - Extension of Binak B/C Manifold |  | 2022-05-25
TBE For Pumps - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ME-TB-0001 | BK-W007S-PEDCO-110-ME-TB-0001TBE For Pumps - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For Drums - W007S | BK-W007S-PEDCO-110-ME-MR-0002 | BK-W007S-PEDCO-110-ME-MR-0002PMR For Drums - W007S |  | 2022-05-25
TBE For Drums - W007S | BK-W007S-PEDCO-110-ME-TB-0002 | BK-W007S-PEDCO-110-ME-TB-0002TBE For Drums - W007S |  | 2022-05-25
PMR For Potable Tanks - W007S | BK-W007S-PEDCO-110-ME-MR-0003 | BK-W007S-PEDCO-110-ME-MR-0003PMR For Potable Tanks - W007S |  | 2022-05-25
TBE For Potable Tanks - W007S | BK-W007S-PEDCO-110-ME-TB-0003 | BK-W007S-PEDCO-110-ME-TB-0003TBE For Potable Tanks - W007S |  | 2022-05-25
PMR For Main HVAC Equipment - W007S | BK-W007S-PEDCO-110-HV-MR-0001 | BK-W007S-PEDCO-110-HV-MR-0001PMR For Main HVAC Equipment - W007S |  | 2022-05-25
TBE For Main HVAC Equipment - W007S | BK-W007S-PEDCO-110-HV-TB-0001 | BK-W007S-PEDCO-110-HV-TB-0001TBE For Main HVAC Equipment - W007S |  | 2022-05-25
PMR For Pipes - W007S | BK-W007S-PEDCO-110-PI-MR-0001 | BK-W007S-PEDCO-110-PI-MR-0001PMR For Pipes - W007S |  | 2022-05-25
TBE For Pipes - W007S | BK-W007S-PEDCO-110-PI-TB-0001 | BK-W007S-PEDCO-110-PI-TB-0001TBE For Pipes - W007S |  | 2022-05-25
PMR For Fittings - W007S | BK-W007S-PEDCO-110-PI-MR-0002 | BK-W007S-PEDCO-110-PI-MR-0002PMR For Fittings - W007S |  | 2022-05-25
TBE For Fitting - W007S | BK-W007S-PEDCO-110-PI-TB-0002 | BK-W007S-PEDCO-110-PI-TB-0002TBE For Fitting - W007S |  | 2022-05-25
PMR For Flanges - W007S | BK-W007S-PEDCO-110-PI-MR-0003 | BK-W007S-PEDCO-110-PI-MR-0003PMR For Flanges - W007S |  | 2022-05-25
TBE For Flanges - W007S | BK-W007S-PEDCO-110-PI-TB-0003 | BK-W007S-PEDCO-110-PI-TB-0003TBE For Flanges - W007S |  | 2022-05-25
PMR For Manual Valves - W007S | BK-W007S-PEDCO-110-PI-MR-0004 | BK-W007S-PEDCO-110-PI-MR-0004PMR For Manual Valves - W007S |  | 2022-05-25
TBE For Manual Valves - W007S | BK-W007S-PEDCO-110-PI-TB-0004 | BK-W007S-PEDCO-110-PI-TB-0004TBE For Manual Valves - W007S |  | 2022-05-25
PMR For Gaskets - W007S | BK-W007S-PEDCO-110-PI-MR-0005 | BK-W007S-PEDCO-110-PI-MR-0005PMR For Gaskets - W007S |  | 2022-05-25
TBE For Gaskets - W007S | BK-W007S-PEDCO-110-PI-TB-0005 | BK-W007S-PEDCO-110-PI-TB-0005TBE For Gaskets - W007S |  | 2022-05-25
PMR For Bolt/Nuts - W007S | BK-W007S-PEDCO-110-PI-MR-0006 | BK-W007S-PEDCO-110-PI-MR-0006PMR For Bolt/Nuts - W007S |  | 2022-05-25
TBE For Bolt/Nuts - W007S | BK-W007S-PEDCO-110-PI-TB-0006 | BK-W007S-PEDCO-110-PI-TB-0006TBE For Bolt/Nuts - W007S |  | 2022-05-25
PMR For Sampling Connection Set - W007S | BK-W007S-PEDCO-110-PI-MR-0007 | BK-W007S-PEDCO-110-PI-MR-0007PMR For Sampling Connection Set - W007S |  | 2022-05-25
TBE For Sampling Connection - W007S | BK-W007S-PEDCO-110-PI-TB-0007 | BK-W007S-PEDCO-110-PI-TB-0007TBE For Sampling Connection - W007S |  | 2022-05-25
PMR For Stone Trap - W007S | BK-W007S-PEDCO-110-PI-MR-0008 | BK-W007S-PEDCO-110-PI-MR-0008PMR For Stone Trap - W007S |  | 2022-05-25
TBE For Stone Trap - W007S | BK-W007S-PEDCO-110-PI-TB-0008 | BK-W007S-PEDCO-110-PI-TB-0008TBE For Stone Trap - W007S | 2022-05-24 | 2022-05-24
PMR For Pipe Support - W007S | BK-W007S-PEDCO-110-PI-MR-0009 | BK-W007S-PEDCO-110-PI-MR-0009PMR For Pipe Support - W007S |  | 2022-05-25
TBE For Pipe Support - W007S | BK-W007S-PEDCO-110-PI-TB-0009 | BK-W007S-PEDCO-110-PI-TB-0009TBE For Pipe Support - W007S |  | 2022-05-25
PMR For Line Pipes - W007S | BK-W007S-PEDCO-110-PL-MR-0001 | BK-W007S-PEDCO-110-PL-MR-0001PMR For Line Pipes - W007S |  | 2022-05-25
TBE FOR LINE PIPES – W007S | BK-W007S-PEDCO-110-PL-TB-0001 | BK-W007S-PEDCO-110-PL-TB-0001TBE FOR LINE PIPES – W007S | 2022-02-19 | 2022-05-14
PMR For Flow Line Support - W007S | BK-W007S-PEDCO-110-PL-MR-0002 | BK-W007S-PEDCO-110-PL-MR-0002PMR For Flow Line Support - W007S |  | 2022-05-25
TBE For Flow Line Support - W007S | BK-W007S-PEDCO-110-PL-TB-0002 | BK-W007S-PEDCO-110-PL-TB-0002TBE For Flow Line Support - W007S |  | 2022-05-25
PMR For Control System/Console/Furniture - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0001 | BK-W007S-PEDCO-110-IN-MR-0001PMR For Control System/Console/Furniture - Extension of Binak B/C Manifold |  | 2022-05-25
TBE/TBA For Control System/Console/Furniture - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0001 | BK-W007S-PEDCO-110-IN-TB-0001TBE/TBA For Control System/Console/Furniture - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For ESD System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0002 | BK-W007S-PEDCO-110-IN-MR-0002PMR For ESD System - Extension of Binak B/C Manifold |  | 2022-05-25
TBE/TBA For ESD System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0002 | BK-W007S-PEDCO-110-IN-TB-0002TBE/TBA For ESD System - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For F&G System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0003 | BK-W007S-PEDCO-110-IN-MR-0003PMR For F&G System - Extension of Binak B/C Manifold |  | 2022-05-25
TBE/TBA For F&G System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0003 | BK-W007S-PEDCO-110-IN-TB-0003TBE/TBA For F&G System - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0004 | BK-W007S-PEDCO-110-IN-MR-0004PMR For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold | 2022-03-26 | 2022-03-26
TBE/TBA For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0004 | BK-W007S-PEDCO-110-IN-TB-0004TBE/TBA For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For Control Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0005 | BK-W007S-PEDCO-110-IN-MR-0005PMR For Control Valves - Extension of Binak B/C Manifold | 2022-03-14 | 2022-03-14
TBE/TBA For Control Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0005 | BK-W007S-PEDCO-110-IN-TB-0005TBE/TBA For Control Valves - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For Pressure Safety Valves (PSV) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0006 | BK-W007S-PEDCO-110-IN-MR-0006PMR For Pressure Safety Valves (PSV) - Extension of Binak B/C Manifold |  | 2022-05-25
TBE/TBA For Pressure Safety Valves (PSV) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0006 | BK-W007S-PEDCO-110-IN-TB-0006TBE/TBA For Pressure Safety Valves (PSV) - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For F&G Detector - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0007 | BK-W007S-PEDCO-110-IN-MR-0007PMR For F&G Detector - Extension of Binak B/C Manifold |  | 2022-05-25
TBE/TBA For F&G Detector - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0007 | BK-W007S-PEDCO-110-IN-TB-0007TBE/TBA For F&G Detector - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For Orifice and Restriction Orifice Plate - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0008 | BK-W007S-PEDCO-110-IN-MR-0008PMR For Orifice and Restriction Orifice Plate - Extension of Binak B/C Manifold |  | 2022-05-25
TBE/TBA For Orifice and Restriction Orifice Plate - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0008 | BK-W007S-PEDCO-110-IN-TB-0008TBE/TBA For Orifice and Restriction Orifice Plate - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For Corrosion Coupon/Probe - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0009 | BK-W007S-PEDCO-110-IN-MR-0009PMR For Corrosion Coupon/Probe - Extension of Binak B/C Manifold |  | 2022-05-25
TBE/TBA For Corrosion Coupon/Probe - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0009 | BK-W007S-PEDCO-110-IN-TB-0009TBE/TBA For Corrosion Coupon/Probe - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For Pressure Transmitter/Pressure Switch - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0010 | BK-W007S-PEDCO-110-IN-MR-0010PMR For Pressure Transmitter/Pressure Switch - Extension of Binak B/C Manifold | 2022-01-16 | 2022-01-16
TBE/TBA For Pressure Transmitter/Pressure Switch - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0010 | BK-W007S-PEDCO-110-IN-TB-0010TBE/TBA For Pressure Transmitter/Pressure Switch - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For Flow Transmitter/ Diff. Pressure Transmitter - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0011 | BK-W007S-PEDCO-110-IN-MR-0011PMR For Flow Transmitter/ Diff. Pressure Transmitter - Extension of Binak B/C Manifold | 2022-01-16 | 2022-01-16
TBE/TBA For Flow Transmitter/ Diff. Pressure Transmitter - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0011 | BK-W007S-PEDCO-110-IN-TB-0011TBE/TBA For Flow Transmitter/ Diff. Pressure Transmitter - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For Instrument/F&G Cable - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0012 | BK-W007S-PEDCO-110-IN-MR-0012PMR For Instrument/F&G Cable - Extension of Binak B/C Manifold |  | 2022-05-25
TBE/TBA For Instrument/F&G Cable - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0012 | BK-W007S-PEDCO-110-IN-TB-0012TBE/TBA For Instrument/F&G Cable - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For Instrument/F&G Junction box and Gland - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0013 | BK-W007S-PEDCO-110-IN-MR-0013PMR For Instrument/F&G Junction box and Gland - Extension of Binak B/C Manifold |  | 2022-05-25
TBE/TBA For Instrument/F&G Junction box and Gland - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0013 | BK-W007S-PEDCO-110-IN-TB-0013TBE/TBA For Instrument/F&G Junction box and Gland - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For Bulk Item and Installation Accessories - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0014 | BK-W007S-PEDCO-110-IN-MR-0014PMR For Bulk Item and Installation Accessories - Extension of Binak B/C Manifold |  | 2022-05-25
TBE/TBA For Bulk Item and Installation Accessories - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0014 | BK-W007S-PEDCO-110-IN-TB-0014TBE/TBA For Bulk Item and Installation Accessories - Extension of Binak B/C Manifold |  | 2022-05-25
PMR For Differential Pressure/Pressure Gauge - Manifold & W007S | BK-W007S-PEDCO-110-IN-MR-0015 | BK-W007S-PEDCO-110-IN-MR-0015PMR For Differential Pressure/Pressure Gauge - Manifold & W007S | 2022-01-16 | 2022-01-16
TBE/TBA For Differential Pressure/Pressure Gauge - Manifold & W007S | BK-W007S-PEDCO-110-IN-TB-0015 | BK-W007S-PEDCO-110-IN-TB-0015TBE/TBA For Differential Pressure/Pressure Gauge - Manifold & W007S |  | 2022-05-25
PMR For Temperature Gauge - Manifold & W007S | BK-W007S-PEDCO-110-IN-MR-0016 | BK-W007S-PEDCO-110-IN-MR-0016PMR For Temperature Gauge - Manifold & W007S | 2022-01-16 | 2022-01-16
TBE/TBA For Temperature Gauge - Manifold & W007S | BK-W007S-PEDCO-110-IN-TB-0016 | BK-W007S-PEDCO-110-IN-TB-0016TBE/TBA For Temperature Gauge - Manifold & W007S |  | 2022-05-25
PMR For Instrument Tube and Fitting - Manifold & W007S | BK-W007S-PEDCO-110-IN-MR-0017 | BK-W007S-PEDCO-110-IN-MR-0017PMR For Instrument Tube and Fitting - Manifold & W007S |  | 2022-05-25
TBE/TBA For Instrument Tube and Fitting - Manifold & W007S | BK-W007S-PEDCO-110-IN-TB-0017 | BK-W007S-PEDCO-110-IN-TB-0017TBE/TBA For Instrument Tube and Fitting - Manifold & W007S |  | 2022-05-25
PMR For Instrument Cable Tray/Ladder - Manifold & W007S | BK-W007S-PEDCO-110-IN-MR-0018 | BK-W007S-PEDCO-110-IN-MR-0018PMR For Instrument Cable Tray/Ladder - Manifold & W007S |  | 2022-05-25
TBE/TBA For Instrument Cable Tray/Ladder - Manifold & W007S | BK-W007S-PEDCO-110-IN-TB-0018 | BK-W007S-PEDCO-110-IN-TB-0018TBE/TBA For Instrument Cable Tray/Ladder - Manifold & W007S |  | 2022-05-25
PMR For Fire Fighting and Safety Equipment - Manifold & W007S | BK-W007S-PEDCO-110-SA-MR-0001 | BK-W007S-PEDCO-110-SA-MR-0001PMR For Fire Fighting and Safety Equipment - Manifold & W007S |  | 2022-05-25
TBE For Fire Fighting and Safety Equipment - Manifold & W007S | BK-W007S-PEDCO-110-SA-TB-0001 | BK-W007S-PEDCO-110-SA-TB-0001TBE For Fire Fighting and Safety Equipment - Manifold & W007S |  | 2022-05-25
PMR For Fire Safety Sign - Manifold & W007S | BK-W007S-PEDCO-110-SA-MR-0002 | BK-W007S-PEDCO-110-SA-MR-0002PMR For Fire Safety Sign - Manifold & W007S |  | 2022-05-25
TBE For Fire Safety Sign - Manifold & W007S | BK-W007S-PEDCO-110-SA-TB-0002 | BK-W007S-PEDCO-110-SA-TB-0002TBE For Fire Safety Sign - Manifold & W007S |  | 2022-05-25
PMR For LV Switchgear & MCC - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0001 | BK-W007S-PEDCO-110-EL-MR-0001PMR For LV Switchgear & MCC - Manifold & W007S |  | 2022-05-25
TBE For LV Switchgear & MCC - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0001 | BK-W007S-PEDCO-110-EL-TB-0001TBE For LV Switchgear & MCC - Manifold & W007S |  | 2022-05-25
PMR For UPS System - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0002 | BK-W007S-PEDCO-110-EL-MR-0002PMR For UPS System - Manifold & W007S |  | 2022-05-25
TBE For UPS System - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0002 | BK-W007S-PEDCO-110-EL-TB-0002TBE For UPS System - Manifold & W007S |  | 2022-05-25
PMR For DC Charger - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0003 | BK-W007S-PEDCO-110-EL-MR-0003PMR For DC Charger - Manifold & W007S |  | 2022-05-25
TBE For DC Charger - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0003 | BK-W007S-PEDCO-110-EL-TB-0003TBE For DC Charger - Manifold & W007S |  | 2022-05-25
PMR For Earthing & Lightning System - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0004 | BK-W007S-PEDCO-110-EL-MR-0004PMR For Earthing & Lightning System - Manifold & W007S |  | 2022-05-25
TBE For Earthing & Lightning System - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0004 | BK-W007S-PEDCO-110-EL-TB-0004TBE For Earthing & Lightning System - Manifold & W007S |  | 2022-05-25
PMR For Power & Control Cables - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0005 | BK-W007S-PEDCO-110-EL-MR-0005PMR For Power & Control Cables - Manifold & W007S |  | 2022-05-25
TBE For Power & Control Cables - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0005 | BK-W007S-PEDCO-110-EL-TB-0005TBE For Power & Control Cables - Manifold & W007S |  | 2022-05-25
PMR For Tray/Ladder and Accessories - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0006 | BK-W007S-PEDCO-110-EL-MR-0006PMR For Tray/Ladder and Accessories - Manifold & W007S |  | 2022-05-25
TBE For Tray/Ladder and Accessories - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0006 | BK-W007S-PEDCO-110-EL-TB-0006TBE For Tray/Ladder and Accessories - Manifold & W007S |  | 2022-05-25
PMR For Electrical Bulk Items - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0007 | BK-W007S-PEDCO-110-EL-MR-0007PMR For Electrical Bulk Items - Manifold & W007S |  | 2022-05-25
TBE For Electrical Bulk Items - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0007 | BK-W007S-PEDCO-110-EL-TB-0007TBE For Electrical Bulk Items - Manifold & W007S |  | 2022-05-25
PMR For Transformers - W007S | BK-W007S-PEDCO-110-EL-MR-0008 | BK-W007S-PEDCO-110-EL-MR-0008PMR For Transformers - W007S |  | 2022-05-25
TBE For Transformers - W007S | BK-W007S-PEDCO-110-EL-TB-0008 | BK-W007S-PEDCO-110-EL-TB-0008TBE For Transformers - W007S |  | 2022-05-25
PMR For Emergency Diesel Generator - W007S | BK-W007S-PEDCO-110-EL-MR-0009 | BK-W007S-PEDCO-110-EL-MR-0009PMR For Emergency Diesel Generator - W007S |  | 2022-05-25
TBE For Emergency Diesel Generator - W007S | BK-W007S-PEDCO-110-EL-TB-0009 | BK-W007S-PEDCO-110-EL-TB-0009TBE For Emergency Diesel Generator - W007S |  | 2022-05-25
PMR For Lighting & Distribution Main Panels - W007S | BK-W007S-PEDCO-110-EL-MR-0010 | BK-W007S-PEDCO-110-EL-MR-0010PMR For Lighting & Distribution Main Panels - W007S |  | 2022-05-25
TBE For Lighting & Distribution Main Panels - W007S | BK-W007S-PEDCO-110-EL-TB-0010 | BK-W007S-PEDCO-110-EL-TB-0010TBE For Lighting & Distribution Main Panels - W007S |  | 2022-05-25
PMR For Lighting and Small Power Equipment - W007S | BK-W007S-PEDCO-110-EL-MR-0011 | BK-W007S-PEDCO-110-EL-MR-0011PMR For Lighting and Small Power Equipment - W007S |  | 2022-05-25
TBE For Lighting and Small Power Equipment - W007S | BK-W007S-PEDCO-110-EL-TB-0011 | BK-W007S-PEDCO-110-EL-TB-0011TBE For Lighting and Small Power Equipment - W007S |  | 2022-05-25
PMR For Capacitor Bank - W007S | BK-W007S-PEDCO-110-EL-MR-0012 | BK-W007S-PEDCO-110-EL-MR-0012PMR For Capacitor Bank - W007S |  | 2022-05-25
TBE For Capacitor Bank - W007S | BK-W007S-PEDCO-110-EL-TB-0012 | BK-W007S-PEDCO-110-EL-TB-0012TBE For Capacitor Bank - W007S |  | 2022-05-25
PMR For Transmission Over head Line Equipment - W007S | BK-W007S-PEDCO-110-EL-MR-0013 | BK-W007S-PEDCO-110-EL-MR-0013PMR For Transmission Over head Line Equipment - W007S |  | 2022-05-25
TBE For Transmission Over head Line Equipment - W007S | BK-W007S-PEDCO-110-EL-TB-0013 | BK-W007S-PEDCO-110-EL-TB-0013TBE For Transmission Over head Line Equipment - W007S |  | 2022-05-25
PMR For Steel Structure Items - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-MR-0001 | BK-W007S-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - W007S/Manifold Extension |  | 2022-05-25
TBE For Steel Structure Items - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-TB-0001 | BK-W007S-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - W007S/Manifold Extension |  | 2022-05-25
PMR For Anchor Bolts - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-MR-0002 | BK-W007S-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - W007S/Manifold Extension |  | 2022-05-25
TBE For Anchor Bolts - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-TB-0002 | BK-W007S-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - W007S/Manifold Extension |  | 2022-05-25
PMR For Blast Proof Doors - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-MR-0003 | BK-W007S-PEDCO-110-ST-MR-0003PMR For Blast Proof Doors - W007S/Manifold Extension |  | 2022-05-25
TBE For Blast Proof Doors - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-TB-0003 | BK-W007S-PEDCO-110-ST-TB-0003TBE For Blast Proof Doors - W007S/Manifold Extension |  | 2022-05-25
PMR For Geomembrane - W007S | BK-W007S-PEDCO-110-CV-MR-0001 | BK-W007S-PEDCO-110-CV-MR-0001PMR For Geomembrane - W007S |  | 2022-05-25
TBE For Geomembrane - W007S | BK-W007S-PEDCO-110-CV-TB-0001 | BK-W007S-PEDCO-110-CV-TB-0001TBE For Geomembrane - W007S |  | 2022-05-25
PMR For Geotextile - W007S | BK-W007S-PEDCO-110-CV-MR-0002 | BK-W007S-PEDCO-110-CV-MR-0002PMR For Geotextile - W007S |  | 2022-05-25
TBE For Geotextile - W007S | BK-W007S-PEDCO-110-CV-TB-0002 | BK-W007S-PEDCO-110-CV-TB-0002TBE For Geotextile - W007S |  | 2022-05-25
Pre-Commissioning, Commissioning & Startup Procedure - Manifold & W007S | BK-W007S-PEDCO-110-CO-PR-0001 | BK-W007S-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - Manifold & W007S |  | 2022-05-25
Technical/Site Queries | BK-W007S-PEDCO-110-GE-TQ-0001 | BK-W007S-PEDCO-110-GE-TQ-0001Technical/Site Queries |  | 2022-05-25
As-Built Document Booklets - Manifold & W007S | BK-W007S-PEDCO-110-GE-DO-0001 | BK-W007S-PEDCO-110-GE-DO-0001As-Built Document Booklets - Manifold & W007S |  | 2022-05-25
Operating Manual - Manifold & W007S | BK-W007S-PEDCO-110-GE-ML-0001 | BK-W007S-PEDCO-110-GE-ML-0001Operating Manual - Manifold & W007S |  | 2022-05-25
As-Built Document Booklets - Manifold & W007S | BK-W007S-PEDCO-110-GE-DO-0001 | BK-W007S-PEDCO-110-GE-DO-0001As-Built Document Booklets - Manifold & W007S |  | 2022-05-25
Final Engineering Dossier - Manifold & W007S | BK-W007S-PEDCO-110-GE-DO-0002 | BK-W007S-PEDCO-110-GE-DO-0002Final Engineering Dossier - Manifold & W007S |  | 2022-05-25
P&ID for Diesel Oil Drum- BK14 | BK-BK14-PEDCO-110-PR-PI-0001 | BK-BK14-PEDCO-110-PR-PI-0001P&ID for Diesel Oil Drum- BK14 | 2021-11-15 | 2022-05-25
P&ID for Potable Water Tank - BK14 | BK-BK14-PEDCO-110-PR-PI-0002 | BK-BK14-PEDCO-110-PR-PI-0002P&ID for Potable Water Tank - BK14 | 2021-11-15 | 2022-05-25
Line List - BK14 | BK-BK14-PEDCO-110-PR-LI-0001 | BK-BK14-PEDCO-110-PR-LI-0001Line List - BK14 | 2022-02-27 | 2022-05-25
Process Data Sheets For Instrument Devices - BK14 | BK-BK14-PEDCO-110-PR-DT-0001 | BK-BK14-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - BK14 | 2022-04-12 | 2022-05-25
HVAC Calculation Note For Switchgear Building - BK14 | BK-BK14-PEDCO-110-HV-CN-0001 | BK-BK14-PEDCO-110-HV-CN-0001HVAC Calculation Note For Switchgear Building - BK14 |  | 2022-05-25
HVAC Calculation Note For Security Building - BK14 | BK-BK14-PEDCO-110-HV-CN-0002 | BK-BK14-PEDCO-110-HV-CN-0002HVAC Calculation Note For Security Building - BK14 |  | 2022-05-25
Data Sheets For Main HVAC Equipment - BK14 | BK-BK14-PEDCO-110-HV-DT-0001 | BK-BK14-PEDCO-110-HV-DT-0001Data Sheets For Main HVAC Equipment - BK14 |  | 2022-05-25
HVAC System Layout For Switchgear Building - BK14 | BK-BK14-PEDCO-110-HV-PY-0001 | BK-BK14-PEDCO-110-HV-PY-0001HVAC System Layout For Switchgear Building - BK14 |  | 2022-05-25
HVAC System Layout For Security Building - BK14 | BK-BK14-PEDCO-110-HV-PY-0002 | BK-BK14-PEDCO-110-HV-PY-0002HVAC System Layout For Security Building - BK14 |  | 2022-05-25
Plumbing & Sewage Piping Layout For Switchgear Building - BK14 | BK-BK14-PEDCO-110-HV-PY-0003 | BK-BK14-PEDCO-110-HV-PY-0003Plumbing & Sewage Piping Layout For Switchgear Building - BK14 |  | 2022-05-25
Plumbing & Sewage Piping Layout For Security Building - BK14 | BK-BK14-PEDCO-110-HV-PY-0004 | BK-BK14-PEDCO-110-HV-PY-0004Plumbing & Sewage Piping Layout For Security Building - BK14 |  | 2022-05-25
MTO For Building HVAC & Plumbing Systems - BK14 | BK-BK14-PEDCO-110-HV-MT-0001 | BK-BK14-PEDCO-110-HV-MT-0001MTO For Building HVAC & Plumbing Systems - BK14 |  | 2022-05-25
MTO For Pipes - BK14 | BK-BK14-PEDCO-110-PI-MT-0001 | BK-BK14-PEDCO-110-PI-MT-0001MTO For Pipes - BK14 |  | 2022-05-25
MTO For Transmission Over Head Line - BK14 | BK-BK14-PEDCO-110-EL-MT-0001 | BK-BK14-PEDCO-110-EL-MT-0001MTO For Transmission Over Head Line - BK14 |  | 2022-05-25
MTO For Lighting & Small Powers - BK14 | BK-BK14-PEDCO-110-EL-MT-0002 | BK-BK14-PEDCO-110-EL-MT-0002MTO For Lighting & Small Powers - BK14 | 2022-05-18 | 2022-05-18
MTO For Power & Control Cables - BK14 | BK-BK14-PEDCO-110-EL-MT-0003 | BK-BK14-PEDCO-110-EL-MT-0003MTO For Power & Control Cables - BK14 |  | 2022-05-25
MTO For Tray/Ladder and Accessories - BK14 | BK-BK14-PEDCO-110-EL-MT-0004 | BK-BK14-PEDCO-110-EL-MT-0004MTO For Tray/Ladder and Accessories - BK14 |  | 2022-05-25
MTO For Electrical Bulk Items - BK14 | BK-BK14-PEDCO-110-EL-MT-0005 | BK-BK14-PEDCO-110-EL-MT-0005MTO For Electrical Bulk Items - BK14 |  | 2022-05-25
MTO For Earthing & Lightning Systems - BK14 | BK-BK14-PEDCO-110-EL-MT-0006 | BK-BK14-PEDCO-110-EL-MT-0006MTO For Earthing & Lightning Systems - BK14 |  | 2022-05-25
Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-14 | BK-BK14-PEDCO-110-AR-DW-0001 | BK-BK14-PEDCO-110-AR-DW-0001Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-14 | 2022-05-01 | 2022-05-25
Architectural Drawing For Switchgear Building of Well Pads - BK-14 | BK-BK14-PEDCO-110-AR-DW-0002 | BK-BK14-PEDCO-110-AR-DW-0002Architectural Drawing For Switchgear Building of Well Pads - BK-14 | 2022-03-09 | 2022-05-25
Architectural Drawing For Security Building of Well Pads - BK-14 | BK-BK14-PEDCO-110-AR-DW-0003 | BK-BK14-PEDCO-110-AR-DW-0003Architectural Drawing For Security Building of Well Pads - BK-14 | 2022-05-01 | 2022-05-25
MTO For Architectural Works - BK14 | BK-BK14-PEDCO-110-AR-MT-0001 | BK-BK14-PEDCO-110-AR-MT-0001MTO For Architectural Works - BK14 |  | 2022-05-25
Civil and Structural drawings - BK14 | BK-BK14-PEDCO-110-CV-DW-0001 | BK-BK14-PEDCO-110-CV-DW-0001Civil and Structural drawings - BK14 |  | 2022-05-25
General Civil Layout - BK14 | BK-BK14-PEDCO-110-CV-PY-0001 | BK-BK14-PEDCO-110-CV-PY-0001General Civil Layout - BK14 |  | 2022-05-25
Rough Grading Plans -BK14 | BK-BK14-PEDCO-110-CV-PY-0003 | BK-BK14-PEDCO-110-CV-PY-0003Rough Grading Plans -BK14 |  | 2022-05-25
Site Visit Report (Civil Work) - BK14 | BK-BK14-PEDCO-110-CV-RT-0001 | BK-BK14-PEDCO-110-CV-RT-0001Site Visit Report (Civil Work) - BK14 | 2021-11-09 | 2022-05-25
MTO For Civil Works - BK14 | BK-BK14-PEDCO-110-CV-MT-0001 | BK-BK14-PEDCO-110-CV-MT-0001MTO For Civil Works - BK14 |  | 2022-05-25
Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0001 | BK-BK14-PEDCO-110-ST-DW-0001Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-14 |  | 2022-05-25
Foundation Drawing For Security Building For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0002 | BK-BK14-PEDCO-110-ST-DW-0002Foundation Drawing For Security Building For Well Pads - BK-14 |  | 2022-05-25
Structural Drawing For Security Building For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0003 | BK-BK14-PEDCO-110-ST-DW-0003Structural Drawing For Security Building For Well Pads - BK-14 |  | 2022-05-25
Foundation Drawing For Switchgear Building For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0004 | BK-BK14-PEDCO-110-ST-DW-0004Foundation Drawing For Switchgear Building For Well Pads - BK-14 |  | 2022-05-25
Structural Drawing For Switchgear Building For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0005 | BK-BK14-PEDCO-110-ST-DW-0005Structural Drawing For Switchgear Building For Well Pads - BK-14 |  | 2022-05-25
Foundation Drawing For Potable Water Tank For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0006 | BK-BK14-PEDCO-110-ST-DW-0006Foundation Drawing For Potable Water Tank For Well Pads - BK-14 |  | 2022-05-25
Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0007 | BK-BK14-PEDCO-110-ST-DW-0007Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-14 |  | 2022-05-25
Structural Drawing For Diesel Generator Shelter For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0008 | BK-BK14-PEDCO-110-ST-DW-0008Structural Drawing For Diesel Generator Shelter For Well Pads - BK-14 |  | 2022-05-25
MTO For Structural Works - BK14 | BK-BK14-PEDCO-110-ST-MT-0001 | BK-BK14-PEDCO-110-ST-MT-0001MTO For Structural Works - BK14 |  | 2022-05-25
Geotechnical Investigation Report - BK14 | BK-BK14-PEDCO-110-GT-RT-0001 | BK-BK14-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - BK14 |  | 2022-05-25
Over Head Line Plan and Profile - BK14 | BK-BK14-PEDCO-110-SU-DW-0001 | BK-BK14-PEDCO-110-SU-DW-0001Over Head Line Plan and Profile - BK14 | 2022-02-21 | 2022-05-25
PMR For Pipes - BK14 | BK-BK14-PEDCO-110-PI-MR-0001 | BK-BK14-PEDCO-110-PI-MR-0001PMR For Pipes - BK14 |  | 2022-05-25
TBE For Pipes - BK14 | BK-BK14-PEDCO-110-PI-TB-0001 | BK-BK14-PEDCO-110-PI-TB-0001TBE For Pipes - BK14 |  | 2022-05-25
PMR For Pipe Support - BK14 | BK-BK14-PEDCO-110-PI-MR-0002 | BK-BK14-PEDCO-110-PI-MR-0002PMR For Pipe Support - BK14 |  | 2022-05-25
TBE For Pipe Support - BK14 | BK-BK14-PEDCO-110-PI-TB-0002 | BK-BK14-PEDCO-110-PI-TB-0002TBE For Pipe Support - BK14 |  | 2022-05-25
PMR For Main HVAC Equipment - BK14 | BK-BK14-PEDCO-110-HV-MR-0001 | BK-BK14-PEDCO-110-HV-MR-0001PMR For Main HVAC Equipment - BK14 |  | 2022-05-25
TBE For Main HVAC Equipment - BK14 | BK-BK14-PEDCO-110-HV-TB-0001 | BK-BK14-PEDCO-110-HV-TB-0001TBE For Main HVAC Equipment - BK14 |  | 2022-05-25
PMR For Transformers - BK14 | BK-BK14-PEDCO-110-EL-MR-0001 | BK-BK14-PEDCO-110-EL-MR-0001PMR For Transformers - BK14 |  | 2022-05-25
TBE For Transformers - BK14 | BK-BK14-PEDCO-110-EL-TB-0001 | BK-BK14-PEDCO-110-EL-TB-0001TBE For Transformers - BK14 |  | 2022-05-25
PMR For LV Switchgear & MCC - BK14 | BK-BK14-PEDCO-110-EL-MR-0002 | BK-BK14-PEDCO-110-EL-MR-0002PMR For LV Switchgear & MCC - BK14 |  | 2022-05-25
TBE For LV Switchgear & MCC - BK14 | BK-BK14-PEDCO-110-EL-TB-0002 | BK-BK14-PEDCO-110-EL-TB-0002TBE For LV Switchgear & MCC - BK14 |  | 2022-05-25
PMR For Emergency Diesel Generator - BK14 | BK-BK14-PEDCO-110-EL-MR-0003 | BK-BK14-PEDCO-110-EL-MR-0003PMR For Emergency Diesel Generator - BK14 |  | 2022-05-25
TBE For Emergency Diesel Generator - BK14 | BK-BK14-PEDCO-110-EL-TB-0003 | BK-BK14-PEDCO-110-EL-TB-0003TBE For Emergency Diesel Generator - BK14 |  | 2022-05-25
PMR For UPS System - BK14 | BK-BK14-PEDCO-110-EL-MR-0004 | BK-BK14-PEDCO-110-EL-MR-0004PMR For UPS System - BK14 |  | 2022-05-25
TBE For UPS System - BK14 | BK-BK14-PEDCO-110-EL-TB-0004 | BK-BK14-PEDCO-110-EL-TB-0004TBE For UPS System - BK14 |  | 2022-05-25
PMR For DC Charger - BK14 | BK-BK14-PEDCO-110-EL-MR-0005 | BK-BK14-PEDCO-110-EL-MR-0005PMR For DC Charger - BK14 | 2022-04-26 | 2022-04-26
TBE For DC Charger - BK14 | BK-BK14-PEDCO-110-EL-TB-0005 | BK-BK14-PEDCO-110-EL-TB-0005TBE For DC Charger - BK14 |  | 2022-05-25
PMR For Capacitor Bank - BK14 | BK-BK14-PEDCO-110-EL-MR-0006 | BK-BK14-PEDCO-110-EL-MR-0006PMR For Capacitor Bank - BK14 |  | 2022-05-25
TBE For Capacitor Bank - BK14 | BK-BK14-PEDCO-110-EL-TB-0006 | BK-BK14-PEDCO-110-EL-TB-0006TBE For Capacitor Bank - BK14 |  | 2022-05-25
PMR For Lighting & Distribution Main Panels - BK14 | BK-BK14-PEDCO-110-EL-MR-0007 | BK-BK14-PEDCO-110-EL-MR-0007PMR For Lighting & Distribution Main Panels - BK14 |  | 2022-05-25
TBE For Lighting & Distribution Main Panels - BK14 | BK-BK14-PEDCO-110-EL-TB-0007 | BK-BK14-PEDCO-110-EL-TB-0007TBE For Lighting & Distribution Main Panels - BK14 |  | 2022-05-25
PMR For Earthing & Lightning System - BK14 | BK-BK14-PEDCO-110-EL-MR-0008 | BK-BK14-PEDCO-110-EL-MR-0008PMR For Earthing & Lightning System - BK14 |  | 2022-05-25
TBE For Earthing & Lightning System - BK14 | BK-BK14-PEDCO-110-EL-TB-0008 | BK-BK14-PEDCO-110-EL-TB-0008TBE For Earthing & Lightning System - BK14 |  | 2022-05-25
PMR For Lighting and Small Power Equipment - BK14 | BK-BK14-PEDCO-110-EL-MR-0009 | BK-BK14-PEDCO-110-EL-MR-0009PMR For Lighting and Small Power Equipment - BK14 |  | 2022-05-25
TBE For Lighting and Small Power Equipment - BK14 | BK-BK14-PEDCO-110-EL-TB-0009 | BK-BK14-PEDCO-110-EL-TB-0009TBE For Lighting and Small Power Equipment - BK14 |  | 2022-05-25
PMR For Tray/Ladder and Accessories - BK14 | BK-BK14-PEDCO-110-EL-MR-0010 | BK-BK14-PEDCO-110-EL-MR-0010PMR For Tray/Ladder and Accessories - BK14 |  | 2022-05-25
TBE For Tray/Ladder and Accessories - BK14 | BK-BK14-PEDCO-110-EL-TB-0010 | BK-BK14-PEDCO-110-EL-TB-0010TBE For Tray/Ladder and Accessories - BK14 |  | 2022-05-25
PMR For Power & Control Cables - BK14 | BK-BK14-PEDCO-110-EL-MR-0011 | BK-BK14-PEDCO-110-EL-MR-0011PMR For Power & Control Cables - BK14 |  | 2022-05-25
TBE For Power & Control Cables - BK14 | BK-BK14-PEDCO-110-EL-TB-0011 | BK-BK14-PEDCO-110-EL-TB-0011TBE For Power & Control Cables - BK14 |  | 2022-05-25
PMR For Electrical Bulk Items - BK14 | BK-BK14-PEDCO-110-EL-MR-0012 | BK-BK14-PEDCO-110-EL-MR-0012PMR For Electrical Bulk Items - BK14 |  | 2022-05-25
TBE For Electrical Bulk Items - BK14 | BK-BK14-PEDCO-110-EL-TB-0012 | BK-BK14-PEDCO-110-EL-TB-0012TBE For Electrical Bulk Items - BK14 |  | 2022-05-25
PMR For Transmission Over head Line - BK14 | BK-BK14-PEDCO-110-EL-MR-0013 | BK-BK14-PEDCO-110-EL-MR-0013PMR For Transmission Over head Line - BK14 |  | 2022-05-25
TBE For Transmission Over head Line - BK14 | BK-BK14-PEDCO-110-EL-TB-0013 | BK-BK14-PEDCO-110-EL-TB-0013TBE For Transmission Over head Line - BK14 |  | 2022-05-25
PMR For Steel Structure Items - BK14 | BK-BK14-PEDCO-110-ST-MR-0001 | BK-BK14-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - BK14 |  | 2022-05-25
TBE For Steel Structure Items - BK14 | BK-BK14-PEDCO-110-ST-TB-0001 | BK-BK14-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - BK14 |  | 2022-05-25
PMR For Anchor Bolts - BK14 | BK-BK14-PEDCO-110-ST-MR-0002 | BK-BK14-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - BK14 |  | 2022-05-25
TBE For Anchor Bolts - BK14 | BK-BK14-PEDCO-110-ST-TB-0002 | BK-BK14-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - BK14 |  | 2022-05-25
PMR For Blast Proof Doors - BK14 | BK-BK14-PEDCO-110-ST-MR-0003 | BK-BK14-PEDCO-110-ST-MR-0003PMR For Blast Proof Doors - BK14 |  | 2022-05-25
TBE For Blast Proof Doors - BK14 | BK-BK14-PEDCO-110-ST-TB-0003 | BK-BK14-PEDCO-110-ST-TB-0003TBE For Blast Proof Doors - BK14 |  | 2022-05-25
PMR For Geomembrane - BK14 | BK-BK14-PEDCO-110-CV-MR-0001 | BK-BK14-PEDCO-110-CV-MR-0001PMR For Geomembrane - BK14 |  | 2022-05-25
TBE For Geomembrane - BK14 | BK-BK14-PEDCO-110-CV-TB-0001 | BK-BK14-PEDCO-110-CV-TB-0001TBE For Geomembrane - BK14 |  | 2022-05-25
PMR For Geotextile - BK14 | BK-BK14-PEDCO-110-CV-MR-0002 | BK-BK14-PEDCO-110-CV-MR-0002PMR For Geotextile - BK14 |  | 2022-05-25
TBE For Geotextile - BK14 | BK-BK14-PEDCO-110-CV-TB-0002 | BK-BK14-PEDCO-110-CV-TB-0002TBE For Geotextile - BK14 |  | 2022-05-25
Pre-Commissioning, Commissioning & Startup Procedure - BK14 | BK-BK14-PEDCO-110-CO-PR-0001 | BK-BK14-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - BK14 |  | 2022-05-25
Technical/Site Queries | BK-BK14-PEDCO-110-GE-TQ-0001 | BK-BK14-PEDCO-110-GE-TQ-0001Technical/Site Queries |  | 2022-05-25
As-Built Document Booklets - BK14 | BK-BK14-PEDCO-110-GE-DO-0001 | BK-BK14-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK14 |  | 2022-05-25
Operating Manual - BK14 | BK-BK14-PEDCO-110-GE-ML-0001 | BK-BK14-PEDCO-110-GE-ML-0001Operating Manual - BK14 |  | 2022-05-25
As-Built Document Booklets - BK14 | BK-BK14-PEDCO-110-GE-DO-0001 | BK-BK14-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK14
Final Engineering Dossier - BK14 | BK-BK14-PEDCO-110-GE-DO-0002 | BK-BK14-PEDCO-110-GE-DO-0002Final Engineering Dossier - BK14 |  | 2022-05-25
P&ID for Diesel Oil Drum- BK12 | BK-BK12-PEDCO-110-PR-PI-0001 | BK-BK12-PEDCO-110-PR-PI-0001P&ID for Diesel Oil Drum- BK12 | 2021-11-15 | 2022-05-25
P&ID for Potable Water Tank - BK12 | BK-BK12-PEDCO-110-PR-PI-0002 | BK-BK12-PEDCO-110-PR-PI-0002P&ID for Potable Water Tank - BK12 | 2021-11-15 | 2022-05-25
Line List - BK12 | BK-BK12-PEDCO-110-PR-LI-0001 | BK-BK12-PEDCO-110-PR-LI-0001Line List - BK12 | 2022-02-27 | 2022-05-25
Process Data Sheets For Instrument Devices - BK12 | BK-BK12-PEDCO-110-PR-DT-0001 | BK-BK12-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - BK12 | 2022-04-12 | 2022-05-25
HVAC Calculation Note For Switchgear Building - BK12 | BK-BK12-PEDCO-110-HV-CN-0001 | BK-BK12-PEDCO-110-HV-CN-0001HVAC Calculation Note For Switchgear Building - BK12 |  | 2022-05-25
HVAC Calculation Note For Security Building - BK12 | BK-BK12-PEDCO-110-HV-CN-0002 | BK-BK12-PEDCO-110-HV-CN-0002HVAC Calculation Note For Security Building - BK12 |  | 2022-05-25
Data Sheets For Main HVAC Equipment - BK12 | BK-BK12-PEDCO-110-HV-DT-0001 | BK-BK12-PEDCO-110-HV-DT-0001Data Sheets For Main HVAC Equipment - BK12 |  | 2022-05-25
HVAC System Layout For Switchgear Building - BK12 | BK-BK12-PEDCO-110-HV-PY-0001 | BK-BK12-PEDCO-110-HV-PY-0001HVAC System Layout For Switchgear Building - BK12 |  | 2022-05-25
HVAC System Layout For Security Building - BK12 | BK-BK12-PEDCO-110-HV-PY-0002 | BK-BK12-PEDCO-110-HV-PY-0002HVAC System Layout For Security Building - BK12 |  | 2022-05-25
Plumbing & Sewage Piping Layout For Switchgear Building - BK12 | BK-BK12-PEDCO-110-HV-PY-0003 | BK-BK12-PEDCO-110-HV-PY-0003Plumbing & Sewage Piping Layout For Switchgear Building - BK12 |  | 2022-05-25
Plumbing & Sewage Piping Layout For Security Building - BK12 | BK-BK12-PEDCO-110-HV-PY-0004 | BK-BK12-PEDCO-110-HV-PY-0004Plumbing & Sewage Piping Layout For Security Building - BK12 |  | 2022-05-25
MTO For Building HVAC & Plumbing Systems - BK12 | BK-BK12-PEDCO-110-HV-MT-0001 | BK-BK12-PEDCO-110-HV-MT-0001MTO For Building HVAC & Plumbing Systems - BK12 |  | 2022-05-25
MTO For Pipes - BK12 | BK-BK12-PEDCO-110-PI-MT-0001 | BK-BK12-PEDCO-110-PI-MT-0001MTO For Pipes - BK12 |  | 2022-05-25
MTO For Transmission Over Head Line - BK12 | BK-BK12-PEDCO-110-EL-MT-0001 | BK-BK12-PEDCO-110-EL-MT-0001MTO For Transmission Over Head Line - BK12 |  | 2022-05-25
MTO For Lighting & Small Powers - BK12 | BK-BK12-PEDCO-110-EL-MT-0002 | BK-BK12-PEDCO-110-EL-MT-0002MTO For Lighting & Small Powers - BK12 | 2022-05-18 | 2022-05-18
MTO For Power & Control Cables - BK12 | BK-BK12-PEDCO-110-EL-MT-0003 | BK-BK12-PEDCO-110-EL-MT-0003MTO For Power & Control Cables - BK12 |  | 2022-05-25
MTO For Tray/Ladder and Accessories - BK12 | BK-BK12-PEDCO-110-EL-MT-0004 | BK-BK12-PEDCO-110-EL-MT-0004MTO For Tray/Ladder and Accessories - BK12 |  | 2022-05-25
MTO For Electrical Bulk Items - BK12 | BK-BK12-PEDCO-110-EL-MT-0005 | BK-BK12-PEDCO-110-EL-MT-0005MTO For Electrical Bulk Items - BK12 |  | 2022-05-25
MTO For Earthing & Lightning Systems - BK12 | BK-BK12-PEDCO-110-EL-MT-0006 | BK-BK12-PEDCO-110-EL-MT-0006MTO For Earthing & Lightning Systems - BK12 |  | 2022-05-25
Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-12 | BK-BK12-PEDCO-110-AR-DW-0001 | BK-BK12-PEDCO-110-AR-DW-0001Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-12 | 2022-05-01 | 2022-05-25
Architectural Drawing For Switchgear Building of Well Pads - BK-12 | BK-BK12-PEDCO-110-AR-DW-0002 | BK-BK12-PEDCO-110-AR-DW-0002Architectural Drawing For Switchgear Building of Well Pads - BK-12 | 2022-03-09 | 2022-05-25
Architectural Drawing For Security Building of Well Pads - BK-12 | BK-BK12-PEDCO-110-AR-DW-0003 | BK-BK12-PEDCO-110-AR-DW-0003Architectural Drawing For Security Building of Well Pads - BK-12 | 2022-05-01 | 2022-05-25
MTO For Architectural Works - BK12 | BK-BK12-PEDCO-110-AR-MT-0001 | BK-BK12-PEDCO-110-AR-MT-0001MTO For Architectural Works - BK12 |  | 2022-05-25
Civil and Structural drawings - BK12 | BK-BK12-PEDCO-110-CV-DW-0001 | BK-BK12-PEDCO-110-CV-DW-0001Civil and Structural drawings - BK12 |  | 2022-05-25
General Civil Layout - BK12 | BK-BK12-PEDCO-110-CV-PY-0001 | BK-BK12-PEDCO-110-CV-PY-0001General Civil Layout - BK12 |  | 2022-05-25
Rough Grading Plans -BK12 | BK-BK12-PEDCO-110-CV-PY-0003 | BK-BK12-PEDCO-110-CV-PY-0003Rough Grading Plans -BK12 |  | 2022-05-25
Site Visit Report (Civil Work) - BK12 | BK-BK12-PEDCO-110-CV-RT-0001 | BK-BK12-PEDCO-110-CV-RT-0001Site Visit Report (Civil Work) - BK12 |  | 2022-05-25
MTO For Civil Works - BK12 | BK-BK12-PEDCO-110-CV-MT-0001 | BK-BK12-PEDCO-110-CV-MT-0001MTO For Civil Works - BK12 |  | 2022-05-25
Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0001 | BK-BK12-PEDCO-110-ST-DW-0001Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-12 |  | 2022-05-25
Foundation Drawing For Security Building For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0002 | BK-BK12-PEDCO-110-ST-DW-0002Foundation Drawing For Security Building For Well Pads - BK-12 |  | 2022-05-25
Structural Drawing For Security Building For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0003 | BK-BK12-PEDCO-110-ST-DW-0003Structural Drawing For Security Building For Well Pads - BK-12 |  | 2022-05-25
Foundation Drawing For Switchgear Building For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0004 | BK-BK12-PEDCO-110-ST-DW-0004Foundation Drawing For Switchgear Building For Well Pads - BK-12 |  | 2022-05-25
Structural Drawing For Switchgear Building For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0005 | BK-BK12-PEDCO-110-ST-DW-0005Structural Drawing For Switchgear Building For Well Pads - BK-12 |  | 2022-05-25
Foundation Drawing For Potable Water Tank For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0006 | BK-BK12-PEDCO-110-ST-DW-0006Foundation Drawing For Potable Water Tank For Well Pads - BK-12 |  | 2022-05-25
Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0007 | BK-BK12-PEDCO-110-ST-DW-0007Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-12 |  | 2022-05-25
Structural Drawing For Diesel Generator Shelter For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0008 | BK-BK12-PEDCO-110-ST-DW-0008Structural Drawing For Diesel Generator Shelter For Well Pads - BK-12 |  | 2022-05-25
MTO For Structural Works - BK12 | BK-BK12-PEDCO-110-ST-MT-0001 | BK-BK12-PEDCO-110-ST-MT-0001MTO For Structural Works - BK12 |  | 2022-05-25
Geotechnical Investigation Report - BK12 | BK-BK12-PEDCO-110-GT-RT-0001 | BK-BK12-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - BK12 |  | 2022-05-25
Over Head Line Plan and Profile - BK12 | BK-BK12-PEDCO-110-SU-DW-0001 | BK-BK12-PEDCO-110-SU-DW-0001Over Head Line Plan and Profile - BK12 | 2022-05-16 | 2022-05-25
PMR For Pipes - BK12 | BK-BK12-PEDCO-110-PI-MR-0001 | BK-BK12-PEDCO-110-PI-MR-0001PMR For Pipes - BK12 |  | 2022-05-25
TBE For Pipes - BK12 | BK-BK12-PEDCO-110-PI-TB-0001 | BK-BK12-PEDCO-110-PI-TB-0001TBE For Pipes - BK12 |  | 2022-05-25
PMR For Pipe Support - BK12 | BK-BK12-PEDCO-110-PI-MR-0002 | BK-BK12-PEDCO-110-PI-MR-0002PMR For Pipe Support - BK12 |  | 2022-05-25
TBE For Pipe Support - BK12 | BK-BK12-PEDCO-110-PI-TB-0002 | BK-BK12-PEDCO-110-PI-TB-0002TBE For Pipe Support - BK12 |  | 2022-05-25
PMR For Main HVAC Equipment - BK12 | BK-BK12-PEDCO-110-HV-MR-0001 | BK-BK12-PEDCO-110-HV-MR-0001PMR For Main HVAC Equipment - BK12 |  | 2022-05-25
TBE For Main HVAC Equipment - BK12 | BK-BK12-PEDCO-110-HV-TB-0001 | BK-BK12-PEDCO-110-HV-TB-0001TBE For Main HVAC Equipment - BK12 |  | 2022-05-25
PMR For Transformers - BK12 | BK-BK12-PEDCO-110-EL-MR-0001 | BK-BK12-PEDCO-110-EL-MR-0001PMR For Transformers - BK12 |  | 2022-05-25
TBE For Transformers - BK12 | BK-BK12-PEDCO-110-EL-TB-0001 | BK-BK12-PEDCO-110-EL-TB-0001TBE For Transformers - BK12 |  | 2022-05-25
PMR For LV Switchgear & MCC - BK12 | BK-BK12-PEDCO-110-EL-MR-0002 | BK-BK12-PEDCO-110-EL-MR-0002PMR For LV Switchgear & MCC - BK12 |  | 2022-05-25
TBE For LV Switchgear & MCC - BK12 | BK-BK12-PEDCO-110-EL-TB-0002 | BK-BK12-PEDCO-110-EL-TB-0002TBE For LV Switchgear & MCC - BK12 |  | 2022-05-25
PMR For Emergency Diesel Generator - BK12 | BK-BK12-PEDCO-110-EL-MR-0003 | BK-BK12-PEDCO-110-EL-MR-0003PMR For Emergency Diesel Generator - BK12 |  | 2022-05-25
TBE For Emergency Diesel Generator - BK12 | BK-BK12-PEDCO-110-EL-TB-0003 | BK-BK12-PEDCO-110-EL-TB-0003TBE For Emergency Diesel Generator - BK12 |  | 2022-05-25
PMR For UPS System - BK12 | BK-BK12-PEDCO-110-EL-MR-0004 | BK-BK12-PEDCO-110-EL-MR-0004PMR For UPS System - BK12 |  | 2022-05-25
TBE For UPS System - BK12 | BK-BK12-PEDCO-110-EL-TB-0004 | BK-BK12-PEDCO-110-EL-TB-0004TBE For UPS System - BK12 |  | 2022-05-25
PMR For DC Charger - BK12 | BK-BK12-PEDCO-110-EL-MR-0005 | BK-BK12-PEDCO-110-EL-MR-0005PMR For DC Charger - BK12 | 2022-04-26 | 2022-04-26
TBE For DC Charger - BK12 | BK-BK12-PEDCO-110-EL-TB-0005 | BK-BK12-PEDCO-110-EL-TB-0005TBE For DC Charger - BK12 |  | 2022-05-25
PMR For Capacitor Bank - BK12 | BK-BK12-PEDCO-110-EL-MR-0006 | BK-BK12-PEDCO-110-EL-MR-0006PMR For Capacitor Bank - BK12 |  | 2022-05-25
TBE For Capacitor Bank - BK12 | BK-BK12-PEDCO-110-EL-TB-0006 | BK-BK12-PEDCO-110-EL-TB-0006TBE For Capacitor Bank - BK12 |  | 2022-05-25
PMR For Lighting & Distribution Main Panels - BK12 | BK-BK12-PEDCO-110-EL-MR-0007 | BK-BK12-PEDCO-110-EL-MR-0007PMR For Lighting & Distribution Main Panels - BK12 |  | 2022-05-25
TBE For Lighting & Distribution Main Panels - BK12 | BK-BK12-PEDCO-110-EL-TB-0007 | BK-BK12-PEDCO-110-EL-TB-0007TBE For Lighting & Distribution Main Panels - BK12 |  | 2022-05-25
PMR For Earthing & Lightning System - BK12 | BK-BK12-PEDCO-110-EL-MR-0008 | BK-BK12-PEDCO-110-EL-MR-0008PMR For Earthing & Lightning System - BK12 |  | 2022-05-25
TBE For Earthing & Lightning System - BK12 | BK-BK12-PEDCO-110-EL-TB-0008 | BK-BK12-PEDCO-110-EL-TB-0008TBE For Earthing & Lightning System - BK12 |  | 2022-05-25
PMR For Lighting and Small Power Equipment - BK12 | BK-BK12-PEDCO-110-EL-MR-0009 | BK-BK12-PEDCO-110-EL-MR-0009PMR For Lighting and Small Power Equipment - BK12 |  | 2022-05-25
TBE For Lighting and Small Power Equipment - BK12 | BK-BK12-PEDCO-110-EL-TB-0009 | BK-BK12-PEDCO-110-EL-TB-0009TBE For Lighting and Small Power Equipment - BK12 |  | 2022-05-25
PMR For Tray/Ladder and Accessories - BK12 | BK-BK12-PEDCO-110-EL-MR-0010 | BK-BK12-PEDCO-110-EL-MR-0010PMR For Tray/Ladder and Accessories - BK12 |  | 2022-05-25
TBE For Tray/Ladder and Accessories - BK12 | BK-BK12-PEDCO-110-EL-TB-0010 | BK-BK12-PEDCO-110-EL-TB-0010TBE For Tray/Ladder and Accessories - BK12 |  | 2022-05-25
PMR For Power & Control Cables - BK12 | BK-BK12-PEDCO-110-EL-MR-0011 | BK-BK12-PEDCO-110-EL-MR-0011PMR For Power & Control Cables - BK12 |  | 2022-05-25
TBE For Power & Control Cables - BK12 | BK-BK12-PEDCO-110-EL-TB-0011 | BK-BK12-PEDCO-110-EL-TB-0011TBE For Power & Control Cables - BK12 |  | 2022-05-25
PMR For Electrical Bulk Items - BK12 | BK-BK12-PEDCO-110-EL-MR-0012 | BK-BK12-PEDCO-110-EL-MR-0012PMR For Electrical Bulk Items - BK12 |  | 2022-05-25
TBE For Electrical Bulk Items - BK12 | BK-BK12-PEDCO-110-EL-TB-0012 | BK-BK12-PEDCO-110-EL-TB-0012TBE For Electrical Bulk Items - BK12 |  | 2022-05-25
PMR For Transmission Over head Line - BK12 | BK-BK12-PEDCO-110-EL-MR-0013 | BK-BK12-PEDCO-110-EL-MR-0013PMR For Transmission Over head Line - BK12 |  | 2022-05-25
TBE For Transmission Over head Line - BK12 | BK-BK12-PEDCO-110-EL-TB-0013 | BK-BK12-PEDCO-110-EL-TB-0013TBE For Transmission Over head Line - BK12 |  | 2022-05-25
PMR For Steel Structure Items - BK12 | BK-BK12-PEDCO-110-ST-MR-0001 | BK-BK12-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - BK12 |  | 2022-05-25
TBE For Steel Structure Items - BK12 | BK-BK12-PEDCO-110-ST-TB-0001 | BK-BK12-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - BK12 |  | 2022-05-25
PMR For Anchor Bolts - BK12 | BK-BK12-PEDCO-110-ST-MR-0002 | BK-BK12-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - BK12 |  | 2022-05-25
TBE For Anchor Bolts - BK12 | BK-BK12-PEDCO-110-ST-TB-0002 | BK-BK12-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - BK12 |  | 2022-05-25
PMR For Blast Proof Doors - BK12 | BK-BK12-PEDCO-110-ST-MR-0003 | BK-BK12-PEDCO-110-ST-MR-0003PMR For Blast Proof Doors - BK12 |  | 2022-05-25
TBE For Blast Proof Doors - BK12 | BK-BK12-PEDCO-110-ST-TB-0003 | BK-BK12-PEDCO-110-ST-TB-0003TBE For Blast Proof Doors - BK12 |  | 2022-05-25
Pre-Commissioning, Commissioning & Startup Procedure - BK12 | BK-BK12-PEDCO-110-CO-PR-0001 | BK-BK12-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - BK12 |  | 2022-05-25
Technical/Site Queries | BK-BK12-PEDCO-110-GE-TQ-0001 | BK-BK12-PEDCO-110-GE-TQ-0001Technical/Site Queries |  | 2022-05-25
As-Built Document Booklets - BK12 | BK-BK12-PEDCO-110-GE-DO-0001 | BK-BK12-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK12 |  | 2022-05-25
Operating Manual - BK12 | BK-BK12-PEDCO-110-GE-ML-0001 | BK-BK12-PEDCO-110-GE-ML-0001Operating Manual - BK12 |  | 2022-05-25
As-Built Document Booklets - BK12 | BK-BK12-PEDCO-110-GE-DO-0001 | BK-BK12-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK12
Final Engineering Dossier - BK12 | BK-BK12-PEDCO-110-GE-DO-0002 | BK-BK12-PEDCO-110-GE-DO-0002Final Engineering Dossier - BK12 |  | 2022-05-25
P&ID for Diesel Oil Drum- BK15 | BK-BK15-PEDCO-110-PR-PI-0001 | BK-BK15-PEDCO-110-PR-PI-0001P&ID for Diesel Oil Drum- BK15 | 2021-11-15 | 2022-05-25
P&ID for Potable Water Tank - BK15 | BK-BK15-PEDCO-110-PR-PI-0002 | BK-BK15-PEDCO-110-PR-PI-0002P&ID for Potable Water Tank - BK15 | 2021-11-15 | 2022-05-25
Line List - BK15 | BK-BK15-PEDCO-110-PR-LI-0001 | BK-BK15-PEDCO-110-PR-LI-0001Line List - BK15 | 2022-02-27 | 2022-05-25
Process Data Sheets For Instrument Devices - BK15 | BK-BK15-PEDCO-110-PR-DT-0001 | BK-BK15-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - BK15 | 2022-04-12 | 2022-05-25
HVAC Calculation Note For Switchgear Building - BK15 | BK-BK15-PEDCO-110-HV-CN-0001 | BK-BK15-PEDCO-110-HV-CN-0001HVAC Calculation Note For Switchgear Building - BK15 |  | 2022-05-25
HVAC Calculation Note For Security Building - BK15 | BK-BK15-PEDCO-110-HV-CN-0002 | BK-BK15-PEDCO-110-HV-CN-0002HVAC Calculation Note For Security Building - BK15 |  | 2022-05-25
Data Sheets For Main HVAC Equipment - BK15 | BK-BK15-PEDCO-110-HV-DT-0001 | BK-BK15-PEDCO-110-HV-DT-0001Data Sheets For Main HVAC Equipment - BK15 |  | 2022-05-25
HVAC System Layout For Switchgear Building - BK15 | BK-BK15-PEDCO-110-HV-PY-0001 | BK-BK15-PEDCO-110-HV-PY-0001HVAC System Layout For Switchgear Building - BK15 |  | 2022-05-25
HVAC System Layout For Security Building - BK15 | BK-BK15-PEDCO-110-HV-PY-0002 | BK-BK15-PEDCO-110-HV-PY-0002HVAC System Layout For Security Building - BK15 |  | 2022-05-25
Plumbing & Sewage Piping Layout For Switchgear Building - BK15 | BK-BK15-PEDCO-110-HV-PY-0003 | BK-BK15-PEDCO-110-HV-PY-0003Plumbing & Sewage Piping Layout For Switchgear Building - BK15 |  | 2022-05-25
Plumbing & Sewage Piping Layout For Security Building - BK15 | BK-BK15-PEDCO-110-HV-PY-0004 | BK-BK15-PEDCO-110-HV-PY-0004Plumbing & Sewage Piping Layout For Security Building - BK15 |  | 2022-05-25
MTO For Building HVAC & Plumbing Systems - BK15 | BK-BK15-PEDCO-110-HV-MT-0001 | BK-BK15-PEDCO-110-HV-MT-0001MTO For Building HVAC & Plumbing Systems - BK15 |  | 2022-05-25
MTO For Pipes - BK15 | BK-BK15-PEDCO-110-PI-MT-0001 | BK-BK15-PEDCO-110-PI-MT-0001MTO For Pipes - BK15 |  | 2022-05-25
MTO For Transmission Over Head Line - BK15 | BK-BK15-PEDCO-110-EL-MT-0001 | BK-BK15-PEDCO-110-EL-MT-0001MTO For Transmission Over Head Line - BK15 |  | 2022-05-25
MTO For Lighting & Small Powers - BK15 | BK-BK15-PEDCO-110-EL-MT-0002 | BK-BK15-PEDCO-110-EL-MT-0002MTO For Lighting & Small Powers - BK15 | 2022-05-18 | 2022-05-18
MTO For Power & Control Cables - BK15 | BK-BK15-PEDCO-110-EL-MT-0003 | BK-BK15-PEDCO-110-EL-MT-0003MTO For Power & Control Cables - BK15 |  | 2022-05-25
MTO For Tray/Ladder and Accessories - BK15 | BK-BK15-PEDCO-110-EL-MT-0004 | BK-BK15-PEDCO-110-EL-MT-0004MTO For Tray/Ladder and Accessories - BK15 |  | 2022-05-25
MTO For Electrical Bulk Items - BK15 | BK-BK15-PEDCO-110-EL-MT-0005 | BK-BK15-PEDCO-110-EL-MT-0005MTO For Electrical Bulk Items - BK15 |  | 2022-05-25
MTO For Earthing & Lightning Systems - BK15 | BK-BK15-PEDCO-110-EL-MT-0006 | BK-BK15-PEDCO-110-EL-MT-0006MTO For Earthing & Lightning Systems - BK15 |  | 2022-05-25
Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-15 | BK-BK15-PEDCO-110-AR-DW-0001 | BK-BK15-PEDCO-110-AR-DW-0001Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-15 | 2022-05-01 | 2022-05-25
Architectural Drawing For Switchgear Building of Well Pads - BK-15 | BK-BK15-PEDCO-110-AR-DW-0002 | BK-BK15-PEDCO-110-AR-DW-0002Architectural Drawing For Switchgear Building of Well Pads - BK-15 | 2022-03-09 | 2022-05-25
Architectural Drawing For Security Building of Well Pads - BK-15 | BK-BK15-PEDCO-110-AR-DW-0003 | BK-BK15-PEDCO-110-AR-DW-0003Architectural Drawing For Security Building of Well Pads - BK-15 | 2022-05-01 | 2022-05-25
MTO For Architectural Works - BK15 | BK-BK15-PEDCO-110-AR-MT-0001 | BK-BK15-PEDCO-110-AR-MT-0001MTO For Architectural Works - BK15 |  | 2022-05-25
Civil and Structural drawings - BK15 | BK-BK15-PEDCO-110-CV-DW-0001 | BK-BK15-PEDCO-110-CV-DW-0001Civil and Structural drawings - BK15 |  | 2022-05-25
General Civil Layout - BK15 | BK-BK15-PEDCO-110-CV-PY-0001 | BK-BK15-PEDCO-110-CV-PY-0001General Civil Layout - BK15 |  | 2022-05-25
Rough Grading Plans -BK15 | BK-BK15-PEDCO-110-CV-PY-0003 | BK-BK15-PEDCO-110-CV-PY-0003Rough Grading Plans -BK15 |  | 2022-05-25
Site Visit Report (Civil Work) - BK15 | BK-BK15-PEDCO-110-CV-RT-0001 | BK-BK15-PEDCO-110-CV-RT-0001Site Visit Report (Civil Work) - BK15 |  | 2022-05-25
MTO For Civil Works - BK15 | BK-BK15-PEDCO-110-CV-MT-0001 | BK-BK15-PEDCO-110-CV-MT-0001MTO For Civil Works - BK15 |  | 2022-05-25
Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0001 | BK-BK15-PEDCO-110-ST-DW-0001Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-15 |  | 2022-05-25
Foundation Drawing For Security Building For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0002 | BK-BK15-PEDCO-110-ST-DW-0002Foundation Drawing For Security Building For Well Pads - BK-15 |  | 2022-05-25
Structural Drawing For Security Building For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0003 | BK-BK15-PEDCO-110-ST-DW-0003Structural Drawing For Security Building For Well Pads - BK-15 |  | 2022-05-25
Foundation Drawing For Switchgear Building For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0004 | BK-BK15-PEDCO-110-ST-DW-0004Foundation Drawing For Switchgear Building For Well Pads - BK-15 |  | 2022-05-25
Structural Drawing For Switchgear Building For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0005 | BK-BK15-PEDCO-110-ST-DW-0005Structural Drawing For Switchgear Building For Well Pads - BK-15 |  | 2022-05-25
Foundation Drawing For Potable Water Tank For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0006 | BK-BK15-PEDCO-110-ST-DW-0006Foundation Drawing For Potable Water Tank For Well Pads - BK-15 |  | 2022-05-25
Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0007 | BK-BK15-PEDCO-110-ST-DW-0007Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-15 |  | 2022-05-25
Structural Drawing For Diesel Generator Shelter For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0008 | BK-BK15-PEDCO-110-ST-DW-0008Structural Drawing For Diesel Generator Shelter For Well Pads - BK-15 |  | 2022-05-25
MTO For Structural Works - BK15 | BK-BK15-PEDCO-110-ST-MT-0001 | BK-BK15-PEDCO-110-ST-MT-0001MTO For Structural Works - BK15 |  | 2022-05-25
Geotechnical Investigation Report - BK15 | BK-BK15-PEDCO-110-GT-RT-0001 | BK-BK15-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - BK15 |  | 2022-05-25
Over Head Line Plan and Profile - BK15 | BK-BK15-PEDCO-110-SU-DW-0001 | BK-BK15-PEDCO-110-SU-DW-0001Over Head Line Plan and Profile - BK15 | 2022-05-16 | 2022-05-25
PMR For Pipes - BK15 | BK-BK15-PEDCO-110-PI-MR-0001 | BK-BK15-PEDCO-110-PI-MR-0001PMR For Pipes - BK15 |  | 2022-05-25
TBE For Pipes - BK15 | BK-BK15-PEDCO-110-PI-TB-0001 | BK-BK15-PEDCO-110-PI-TB-0001TBE For Pipes - BK15 |  | 2022-05-25
PMR For Pipe Support - BK15 | BK-BK15-PEDCO-110-PI-MR-0002 | BK-BK15-PEDCO-110-PI-MR-0002PMR For Pipe Support - BK15 |  | 2022-05-25
TBE For Pipe Support - BK15 | BK-BK15-PEDCO-110-PI-TB-0002 | BK-BK15-PEDCO-110-PI-TB-0002TBE For Pipe Support - BK15 |  | 2022-05-25
PMR For Main HVAC Equipment - BK15 | BK-BK15-PEDCO-110-HV-MR-0001 | BK-BK15-PEDCO-110-HV-MR-0001PMR For Main HVAC Equipment - BK15 |  | 2022-05-25
TBE For Main HVAC Equipment - BK15 | BK-BK15-PEDCO-110-HV-TB-0001 | BK-BK15-PEDCO-110-HV-TB-0001TBE For Main HVAC Equipment - BK15 |  | 2022-05-25
PMR For Transformers - BK15 | BK-BK15-PEDCO-110-EL-MR-0001 | BK-BK15-PEDCO-110-EL-MR-0001PMR For Transformers - BK15 |  | 2022-05-25
TBE For Transformers - BK15 | BK-BK15-PEDCO-110-EL-TB-0001 | BK-BK15-PEDCO-110-EL-TB-0001TBE For Transformers - BK15 |  | 2022-05-25
PMR For LV Switchgear & MCC - BK15 | BK-BK15-PEDCO-110-EL-MR-0002 | BK-BK15-PEDCO-110-EL-MR-0002PMR For LV Switchgear & MCC - BK15 |  | 2022-05-25
TBE For LV Switchgear & MCC - BK15 | BK-BK15-PEDCO-110-EL-TB-0002 | BK-BK15-PEDCO-110-EL-TB-0002TBE For LV Switchgear & MCC - BK15 |  | 2022-05-25
PMR For Emergency Diesel Generator - BK15 | BK-BK15-PEDCO-110-EL-MR-0003 | BK-BK15-PEDCO-110-EL-MR-0003PMR For Emergency Diesel Generator - BK15 |  | 2022-05-25
TBE For Emergency Diesel Generator - BK15 | BK-BK15-PEDCO-110-EL-TB-0003 | BK-BK15-PEDCO-110-EL-TB-0003TBE For Emergency Diesel Generator - BK15 |  | 2022-05-25
PMR For UPS System - BK15 | BK-BK15-PEDCO-110-EL-MR-0004 | BK-BK15-PEDCO-110-EL-MR-0004PMR For UPS System - BK15 |  | 2022-05-25
TBE For UPS System - BK15 | BK-BK15-PEDCO-110-EL-TB-0004 | BK-BK15-PEDCO-110-EL-TB-0004TBE For UPS System - BK15 |  | 2022-05-25
PMR For DC Charger - BK15 | BK-BK15-PEDCO-110-EL-MR-0005 | BK-BK15-PEDCO-110-EL-MR-0005PMR For DC Charger - BK15 | 2022-04-27 | 2022-04-27
TBE For DC Charger - BK15 | BK-BK15-PEDCO-110-EL-TB-0005 | BK-BK15-PEDCO-110-EL-TB-0005TBE For DC Charger - BK15 |  | 2022-05-25
PMR For Capacitor Bank - BK15 | BK-BK15-PEDCO-110-EL-MR-0006 | BK-BK15-PEDCO-110-EL-MR-0006PMR For Capacitor Bank - BK15 |  | 2022-05-25
TBE For Capacitor Bank - BK15 | BK-BK15-PEDCO-110-EL-TB-0006 | BK-BK15-PEDCO-110-EL-TB-0006TBE For Capacitor Bank - BK15 |  | 2022-05-25
PMR For Lighting & Distribution Main Panels - BK15 | BK-BK15-PEDCO-110-EL-MR-0007 | BK-BK15-PEDCO-110-EL-MR-0007PMR For Lighting & Distribution Main Panels - BK15 |  | 2022-05-25
TBE For Lighting & Distribution Main Panels - BK15 | BK-BK15-PEDCO-110-EL-TB-0007 | BK-BK15-PEDCO-110-EL-TB-0007TBE For Lighting & Distribution Main Panels - BK15 |  | 2022-05-25
PMR For Earthing & Lightning System - BK15 | BK-BK15-PEDCO-110-EL-MR-0008 | BK-BK15-PEDCO-110-EL-MR-0008PMR For Earthing & Lightning System - BK15 |  | 2022-05-25
TBE For Earthing & Lightning System - BK15 | BK-BK15-PEDCO-110-EL-TB-0008 | BK-BK15-PEDCO-110-EL-TB-0008TBE For Earthing & Lightning System - BK15 |  | 2022-05-25
PMR For Lighting and Small Power Equipment - BK15 | BK-BK15-PEDCO-110-EL-MR-0009 | BK-BK15-PEDCO-110-EL-MR-0009PMR For Lighting and Small Power Equipment - BK15 |  | 2022-05-25
TBE For Lighting and Small Power Equipment - BK15 | BK-BK15-PEDCO-110-EL-TB-0009 | BK-BK15-PEDCO-110-EL-TB-0009TBE For Lighting and Small Power Equipment - BK15 |  | 2022-05-25
PMR For Tray/Ladder and Accessories - BK15 | BK-BK15-PEDCO-110-EL-MR-0010 | BK-BK15-PEDCO-110-EL-MR-0010PMR For Tray/Ladder and Accessories - BK15 |  | 2022-05-25
TBE For Tray/Ladder and Accessories - BK15 | BK-BK15-PEDCO-110-EL-TB-0010 | BK-BK15-PEDCO-110-EL-TB-0010TBE For Tray/Ladder and Accessories - BK15 |  | 2022-05-25
PMR For Power & Control Cables - BK15 | BK-BK15-PEDCO-110-EL-MR-0011 | BK-BK15-PEDCO-110-EL-MR-0011PMR For Power & Control Cables - BK15 |  | 2022-05-25
TBE For Power & Control Cables - BK15 | BK-BK15-PEDCO-110-EL-TB-0011 | BK-BK15-PEDCO-110-EL-TB-0011TBE For Power & Control Cables - BK15 |  | 2022-05-25
PMR For Electrical Bulk Items - BK15 | BK-BK15-PEDCO-110-EL-MR-0012 | BK-BK15-PEDCO-110-EL-MR-0012PMR For Electrical Bulk Items - BK15 |  | 2022-05-25
TBE For Electrical Bulk Items - BK15 | BK-BK15-PEDCO-110-EL-TB-0012 | BK-BK15-PEDCO-110-EL-TB-0012TBE For Electrical Bulk Items - BK15 |  | 2022-05-25
PMR For Transmission Over head Line - BK15 | BK-BK15-PEDCO-110-EL-MR-0013 | BK-BK15-PEDCO-110-EL-MR-0013PMR For Transmission Over head Line - BK15 |  | 2022-05-25
TBE For Transmission Over head Line - BK15 | BK-BK15-PEDCO-110-EL-TB-0013 | BK-BK15-PEDCO-110-EL-TB-0013TBE For Transmission Over head Line - BK15 |  | 2022-05-25
PMR For Steel Structure Items - BK15 | BK-BK15-PEDCO-110-ST-MR-0001 | BK-BK15-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - BK15 |  | 2022-05-25
TBE For Steel Structure Items - BK15 | BK-BK15-PEDCO-110-ST-TB-0001 | BK-BK15-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - BK15 |  | 2022-05-25
PMR For Anchor Bolts - BK15 | BK-BK15-PEDCO-110-ST-MR-0002 | BK-BK15-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - BK15 |  | 2022-05-25
TBE For Anchor Bolts - BK15 | BK-BK15-PEDCO-110-ST-TB-0002 | BK-BK15-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - BK15 |  | 2022-05-25
PMR For Blast Proof Doors - BK15 | BK-BK15-PEDCO-110-ST-MR-0003 | BK-BK15-PEDCO-110-ST-MR-0003PMR For Blast Proof Doors - BK15 |  | 2022-05-25
TBE For Blast Proof Doors - BK15 | BK-BK15-PEDCO-110-ST-TB-0003 | BK-BK15-PEDCO-110-ST-TB-0003TBE For Blast Proof Doors - BK15 |  | 2022-05-25
Pre-Commissioning, Commissioning & Startup Procedure - BK15 | BK-BK15-PEDCO-110-CO-PR-0001 | BK-BK15-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - BK15 |  | 2022-05-25
Technical/Site Queries | BK-BK15-PEDCO-110-GE-TQ-0001 | BK-BK15-PEDCO-110-GE-TQ-0001Technical/Site Queries |  | 2022-05-25
As-Built Document Booklets - BK15 | BK-BK15-PEDCO-110-GE-DO-0001 | BK-BK15-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK15 |  | 2022-05-25
Operating Manual - BK15 | BK-BK15-PEDCO-110-GE-ML-0001 | BK-BK15-PEDCO-110-GE-ML-0001Operating Manual - BK15 |  | 2022-05-25
As-Built Document Booklets - BK15 | BK-BK15-PEDCO-110-GE-DO-0001 | BK-BK15-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK15
Final Engineering Dossier - BK15 | BK-BK15-PEDCO-110-GE-DO-0002 | BK-BK15-PEDCO-110-GE-DO-0002Final Engineering Dossier - BK15 |  | 2022-05-25
P&ID for Diesel Oil Drum- BK05 | BK-BK05-PEDCO-110-PR-PI-0001 | BK-BK05-PEDCO-110-PR-PI-0001P&ID for Diesel Oil Drum- BK05 | 2021-11-15 | 2022-05-25
P&ID for Potable Water Tank - BK05 | BK-BK05-PEDCO-110-PR-PI-0002 | BK-BK05-PEDCO-110-PR-PI-0002P&ID for Potable Water Tank - BK05 | 2021-11-15 | 2022-05-25
Line List - BK05 | BK-BK05-PEDCO-110-PR-LI-0001 | BK-BK05-PEDCO-110-PR-LI-0001Line List - BK05 | 2022-02-27 | 2022-05-25
Process Data Sheets For Instrument Devices - BK05 | BK-BK05-PEDCO-110-PR-DT-0001 | BK-BK05-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices - BK05 | 2022-04-12 | 2022-05-25
HVAC Calculation Note For Switchgear Building - BK05 | BK-BK05-PEDCO-110-HV-CN-0001 | BK-BK05-PEDCO-110-HV-CN-0001HVAC Calculation Note For Switchgear Building - BK05 |  | 2022-05-25
HVAC Calculation Note For Security Building - BK05 | BK-BK05-PEDCO-110-HV-CN-0002 | BK-BK05-PEDCO-110-HV-CN-0002HVAC Calculation Note For Security Building - BK05 |  | 2022-05-25
Data Sheets For Main HVAC Equipment - BK05 | BK-BK05-PEDCO-110-HV-DT-0001 | BK-BK05-PEDCO-110-HV-DT-0001Data Sheets For Main HVAC Equipment - BK05 |  | 2022-05-25
HVAC System Layout For Switchgear Building - BK05 | BK-BK05-PEDCO-110-HV-PY-0001 | BK-BK05-PEDCO-110-HV-PY-0001HVAC System Layout For Switchgear Building - BK05 |  | 2022-05-25
HVAC System Layout For Security Building - BK05 | BK-BK05-PEDCO-110-HV-PY-0002 | BK-BK05-PEDCO-110-HV-PY-0002HVAC System Layout For Security Building - BK05 |  | 2022-05-25
Plumbing & Sewage Piping Layout For Switchgear Building - BK05 | BK-BK05-PEDCO-110-HV-PY-0003 | BK-BK05-PEDCO-110-HV-PY-0003Plumbing & Sewage Piping Layout For Switchgear Building - BK05 |  | 2022-05-25
Plumbing & Sewage Piping Layout For Security Building - BK05 | BK-BK05-PEDCO-110-HV-PY-0004 | BK-BK05-PEDCO-110-HV-PY-0004Plumbing & Sewage Piping Layout For Security Building - BK05 |  | 2022-05-25
MTO For Building HVAC & Plumbing Systems - BK05 | BK-BK05-PEDCO-110-HV-MT-0001 | BK-BK05-PEDCO-110-HV-MT-0001MTO For Building HVAC & Plumbing Systems - BK05 |  | 2022-05-25
MTO For Pipes - BK05 | BK-BK05-PEDCO-110-PI-MT-0001 | BK-BK05-PEDCO-110-PI-MT-0001MTO For Pipes - BK05 |  | 2022-05-25
MTO For Transmission Over Head Line - BK05 | BK-BK05-PEDCO-110-EL-MT-0001 | BK-BK05-PEDCO-110-EL-MT-0001MTO For Transmission Over Head Line - BK05 |  | 2022-05-25
MTO For Lighting & Small Powers - BK05 | BK-BK05-PEDCO-110-EL-MT-0002 | BK-BK05-PEDCO-110-EL-MT-0002MTO For Lighting & Small Powers - BK05 | 2022-05-18 | 2022-05-18
MTO For Power & Control Cables - BK05 | BK-BK05-PEDCO-110-EL-MT-0003 | BK-BK05-PEDCO-110-EL-MT-0003MTO For Power & Control Cables - BK05 |  | 2022-05-25
MTO For Tray/Ladder and Accessories - BK05 | BK-BK05-PEDCO-110-EL-MT-0004 | BK-BK05-PEDCO-110-EL-MT-0004MTO For Tray/Ladder and Accessories - BK05 |  | 2022-05-25
MTO For Electrical Bulk Items - BK05 | BK-BK05-PEDCO-110-EL-MT-0005 | BK-BK05-PEDCO-110-EL-MT-0005MTO For Electrical Bulk Items - BK05 |  | 2022-05-25
MTO For Earthing & Lightning Systems - BK05 | BK-BK05-PEDCO-110-EL-MT-0006 | BK-BK05-PEDCO-110-EL-MT-0006MTO For Earthing & Lightning Systems - BK05 |  | 2022-05-25
Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-05 | BK-BK05-PEDCO-110-AR-DW-0001 | BK-BK05-PEDCO-110-AR-DW-0001Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-05 | 2022-05-01 | 2022-05-25
Architectural Drawing For Switchgear Building of Well Pads - BK-05 | BK-BK05-PEDCO-110-AR-DW-0002 | BK-BK05-PEDCO-110-AR-DW-0002Architectural Drawing For Switchgear Building of Well Pads - BK-05 | 2022-03-09 | 2022-05-25
Architectural Drawing For Security Building of Well Pads - BK-05 | BK-BK05-PEDCO-110-AR-DW-0003 | BK-BK05-PEDCO-110-AR-DW-0003Architectural Drawing For Security Building of Well Pads - BK-05 | 2022-05-01 | 2022-05-25
MTO For Architectural Works - BK05 | BK-BK05-PEDCO-110-AR-MT-0001 | BK-BK05-PEDCO-110-AR-MT-0001MTO For Architectural Works - BK05 |  | 2022-05-25
Civil and Structural drawings - BK05 | BK-BK05-PEDCO-110-CV-DW-0001 | BK-BK05-PEDCO-110-CV-DW-0001Civil and Structural drawings - BK05 |  | 2022-05-25
General Civil Layout - BK05 | BK-BK05-PEDCO-110-CV-PY-0001 | BK-BK05-PEDCO-110-CV-PY-0001General Civil Layout - BK05 |  | 2022-05-25
Rough Grading Plans -BK05 | BK-BK05-PEDCO-110-CV-PY-0003 | BK-BK05-PEDCO-110-CV-PY-0003Rough Grading Plans -BK05 |  | 2022-05-25
Site Visit Report (Civil Work) - BK05 | BK-BK05-PEDCO-110-CV-RT-0001 | BK-BK05-PEDCO-110-CV-RT-0001Site Visit Report (Civil Work) - BK05 |  | 2022-05-25
MTO For Civil Works - BK05 | BK-BK05-PEDCO-110-CV-MT-0001 | BK-BK05-PEDCO-110-CV-MT-0001MTO For Civil Works - BK05 |  | 2022-05-25
Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0001 | BK-BK05-PEDCO-110-ST-DW-0001Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-05 |  | 2022-05-25
Foundation Drawing For Security Building For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0002 | BK-BK05-PEDCO-110-ST-DW-0002Foundation Drawing For Security Building For Well Pads - BK-05 |  | 2022-05-25
Structural Drawing For Security Building For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0003 | BK-BK05-PEDCO-110-ST-DW-0003Structural Drawing For Security Building For Well Pads - BK-05 |  | 2022-05-25
Foundation Drawing For Switchgear Building For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0004 | BK-BK05-PEDCO-110-ST-DW-0004Foundation Drawing For Switchgear Building For Well Pads - BK-05 |  | 2022-05-25
Structural Drawing For Switchgear Building For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0005 | BK-BK05-PEDCO-110-ST-DW-0005Structural Drawing For Switchgear Building For Well Pads - BK-05 |  | 2022-05-25
Foundation Drawing For Potable Water Tank For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0006 | BK-BK05-PEDCO-110-ST-DW-0006Foundation Drawing For Potable Water Tank For Well Pads - BK-05 |  | 2022-05-25
Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0007 | BK-BK05-PEDCO-110-ST-DW-0007Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-05 |  | 2022-05-25
Structural Drawing For Diesel Generator Shelter For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0008 | BK-BK05-PEDCO-110-ST-DW-0008Structural Drawing For Diesel Generator Shelter For Well Pads - BK-05 |  | 2022-05-25
MTO For Structural Works - BK05 | BK-BK05-PEDCO-110-ST-MT-0001 | BK-BK05-PEDCO-110-ST-MT-0001MTO For Structural Works - BK05 |  | 2022-05-25
Geotechnical Investigation Report - BK05 | BK-BK05-PEDCO-110-GT-RT-0001 | BK-BK05-PEDCO-110-GT-RT-0001Geotechnical Investigation Report - BK05 |  | 2022-05-25
Over Head Line Plan and Profile - BK05 | BK-BK05-PEDCO-110-SU-DW-0001 | BK-BK05-PEDCO-110-SU-DW-0001Over Head Line Plan and Profile - BK05 | 2022-05-18 | 2022-05-25
PMR For Pipes - BK05 | BK-BK05-PEDCO-110-PI-MR-0001 | BK-BK05-PEDCO-110-PI-MR-0001PMR For Pipes - BK05 |  | 2022-05-25
TBE For Pipes - BK05 | BK-BK05-PEDCO-110-PI-TB-0001 | BK-BK05-PEDCO-110-PI-TB-0001TBE For Pipes - BK05 |  | 2022-05-25
PMR For Pipe Support - BK05 | BK-BK05-PEDCO-110-PI-MR-0002 | BK-BK05-PEDCO-110-PI-MR-0002PMR For Pipe Support - BK05 |  | 2022-05-25
TBE For Pipe Support - BK05 | BK-BK05-PEDCO-110-PI-TB-0002 | BK-BK05-PEDCO-110-PI-TB-0002TBE For Pipe Support - BK05 |  | 2022-05-25
PMR For Main HVAC Equipment - BK05 | BK-BK05-PEDCO-110-HV-MR-0001 | BK-BK05-PEDCO-110-HV-MR-0001PMR For Main HVAC Equipment - BK05 |  | 2022-05-25
TBE For Main HVAC Equipment - BK05 | BK-BK05-PEDCO-110-HV-TB-0001 | BK-BK05-PEDCO-110-HV-TB-0001TBE For Main HVAC Equipment - BK05 |  | 2022-05-25
PMR For Transformers - BK05 | BK-BK05-PEDCO-110-EL-MR-0001 | BK-BK05-PEDCO-110-EL-MR-0001PMR For Transformers - BK05 |  | 2022-05-25
TBE For Transformers - BK05 | BK-BK05-PEDCO-110-EL-TB-0001 | BK-BK05-PEDCO-110-EL-TB-0001TBE For Transformers - BK05 |  | 2022-05-25
PMR For LV Switchgear & MCC - BK05 | BK-BK05-PEDCO-110-EL-MR-0002 | BK-BK05-PEDCO-110-EL-MR-0002PMR For LV Switchgear & MCC - BK05 |  | 2022-05-25
TBE For LV Switchgear & MCC - BK05 | BK-BK05-PEDCO-110-EL-TB-0002 | BK-BK05-PEDCO-110-EL-TB-0002TBE For LV Switchgear & MCC - BK05 |  | 2022-05-25
PMR For Emergency Diesel Generator - BK05 | BK-BK05-PEDCO-110-EL-MR-0003 | BK-BK05-PEDCO-110-EL-MR-0003PMR For Emergency Diesel Generator - BK05 |  | 2022-05-25
TBE For Emergency Diesel Generator - BK05 | BK-BK05-PEDCO-110-EL-TB-0003 | BK-BK05-PEDCO-110-EL-TB-0003TBE For Emergency Diesel Generator - BK05 |  | 2022-05-25
PMR For UPS System - BK05 | BK-BK05-PEDCO-110-EL-MR-0004 | BK-BK05-PEDCO-110-EL-MR-0004PMR For UPS System - BK05 |  | 2022-05-25
TBE For UPS System - BK05 | BK-BK05-PEDCO-110-EL-TB-0004 | BK-BK05-PEDCO-110-EL-TB-0004TBE For UPS System - BK05 |  | 2022-05-25
PMR For DC Charger - BK05 | BK-BK05-PEDCO-110-EL-MR-0005 | BK-BK05-PEDCO-110-EL-MR-0005PMR For DC Charger - BK05 | 2022-04-27 | 2022-04-27
TBE For DC Charger - BK05 | BK-BK05-PEDCO-110-EL-TB-0005 | BK-BK05-PEDCO-110-EL-TB-0005TBE For DC Charger - BK05 |  | 2022-05-25
PMR For Capacitor Bank - BK05 | BK-BK05-PEDCO-110-EL-MR-0006 | BK-BK05-PEDCO-110-EL-MR-0006PMR For Capacitor Bank - BK05 |  | 2022-05-25
TBE For Capacitor Bank - BK05 | BK-BK05-PEDCO-110-EL-TB-0006 | BK-BK05-PEDCO-110-EL-TB-0006TBE For Capacitor Bank - BK05 |  | 2022-05-25
PMR For Lighting & Distribution Main Panels - BK05 | BK-BK05-PEDCO-110-EL-MR-0007 | BK-BK05-PEDCO-110-EL-MR-0007PMR For Lighting & Distribution Main Panels - BK05 |  | 2022-05-25
TBE For Lighting & Distribution Main Panels - BK05 | BK-BK05-PEDCO-110-EL-TB-0007 | BK-BK05-PEDCO-110-EL-TB-0007TBE For Lighting & Distribution Main Panels - BK05 |  | 2022-05-25
PMR For Earthing & Lightning System - BK05 | BK-BK05-PEDCO-110-EL-MR-0008 | BK-BK05-PEDCO-110-EL-MR-0008PMR For Earthing & Lightning System - BK05 |  | 2022-05-25
TBE For Earthing & Lightning System - BK05 | BK-BK05-PEDCO-110-EL-TB-0008 | BK-BK05-PEDCO-110-EL-TB-0008TBE For Earthing & Lightning System - BK05 |  | 2022-05-25
PMR For Lighting and Small Power Equipment - BK05 | BK-BK05-PEDCO-110-EL-MR-0009 | BK-BK05-PEDCO-110-EL-MR-0009PMR For Lighting and Small Power Equipment - BK05 |  | 2022-05-25
TBE For Lighting and Small Power Equipment - BK05 | BK-BK05-PEDCO-110-EL-TB-0009 | BK-BK05-PEDCO-110-EL-TB-0009TBE For Lighting and Small Power Equipment - BK05 |  | 2022-05-25
PMR For Tray/Ladder and Accessories - BK05 | BK-BK05-PEDCO-110-EL-MR-0010 | BK-BK05-PEDCO-110-EL-MR-0010PMR For Tray/Ladder and Accessories - BK05 |  | 2022-05-25
TBE For Tray/Ladder and Accessories - BK05 | BK-BK05-PEDCO-110-EL-TB-0010 | BK-BK05-PEDCO-110-EL-TB-0010TBE For Tray/Ladder and Accessories - BK05 |  | 2022-05-25
PMR For Power & Control Cables - BK05 | BK-BK05-PEDCO-110-EL-MR-0011 | BK-BK05-PEDCO-110-EL-MR-0011PMR For Power & Control Cables - BK05 |  | 2022-05-25
TBE For Power & Control Cables - BK05 | BK-BK05-PEDCO-110-EL-TB-0011 | BK-BK05-PEDCO-110-EL-TB-0011TBE For Power & Control Cables - BK05 |  | 2022-05-25
PMR For Electrical Bulk Items - BK05 | BK-BK05-PEDCO-110-EL-MR-0012 | BK-BK05-PEDCO-110-EL-MR-0012PMR For Electrical Bulk Items - BK05 |  | 2022-05-25
TBE For Electrical Bulk Items - BK05 | BK-BK05-PEDCO-110-EL-TB-0012 | BK-BK05-PEDCO-110-EL-TB-0012TBE For Electrical Bulk Items - BK05 |  | 2022-05-25
PMR For Transmission Over head Line - BK05 | BK-BK05-PEDCO-110-EL-MR-0013 | BK-BK05-PEDCO-110-EL-MR-0013PMR For Transmission Over head Line - BK05 |  | 2022-05-25
TBE For Transmission Over head Line - BK05 | BK-BK05-PEDCO-110-EL-TB-0013 | BK-BK05-PEDCO-110-EL-TB-0013TBE For Transmission Over head Line - BK05 |  | 2022-05-25
PMR For Steel Structure Items - BK05 | BK-BK05-PEDCO-110-ST-MR-0001 | BK-BK05-PEDCO-110-ST-MR-0001PMR For Steel Structure Items - BK05 |  | 2022-05-25
TBE For Steel Structure Items - BK05 | BK-BK05-PEDCO-110-ST-TB-0001 | BK-BK05-PEDCO-110-ST-TB-0001TBE For Steel Structure Items - BK05 |  | 2022-05-25
PMR For Anchor Bolts - BK05 | BK-BK05-PEDCO-110-ST-MR-0002 | BK-BK05-PEDCO-110-ST-MR-0002PMR For Anchor Bolts - BK05 |  | 2022-05-25
TBE For Anchor Bolts - BK05 | BK-BK05-PEDCO-110-ST-TB-0002 | BK-BK05-PEDCO-110-ST-TB-0002TBE For Anchor Bolts - BK05 |  | 2022-05-25
PMR For Blast Proof Doors - BK05 | BK-BK05-PEDCO-110-ST-MR-0003 | BK-BK05-PEDCO-110-ST-MR-0003PMR For Blast Proof Doors - BK05 |  | 2022-05-25
TBE For Blast Proof Doors - BK05 | BK-BK05-PEDCO-110-ST-TB-0003 | BK-BK05-PEDCO-110-ST-TB-0003TBE For Blast Proof Doors - BK05 |  | 2022-05-25
Pre-Commissioning, Commissioning & Startup Procedure - BK05 | BK-BK05-PEDCO-110-CO-PR-0001 | BK-BK05-PEDCO-110-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure - BK05 |  | 2022-05-25
Technical/Site Queries | BK-BK05-PEDCO-110-GE-TQ-0001 | BK-BK05-PEDCO-110-GE-TQ-0001Technical/Site Queries |  | 2022-05-25
As-Built Document Booklets - BK05 | BK-BK05-PEDCO-110-GE-DO-0001 | BK-BK05-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK05 |  | 2022-05-25
Operating Manual - BK05 | BK-BK05-PEDCO-110-GE-ML-0001 | BK-BK05-PEDCO-110-GE-ML-0001Operating Manual - BK05 |  | 2022-05-25
As-Built Document Booklets - BK05 | BK-BK05-PEDCO-110-GE-DO-0001 | BK-BK05-PEDCO-110-GE-DO-0001As-Built Document Booklets - BK05 |  | 2022-05-25
Final Engineering Dossier - BK05 | BK-BK05-PEDCO-110-GE-DO-0002 | BK-BK05-PEDCO-110-GE-DO-0002Final Engineering Dossier - BK05 |  | 2022-05-25
Endorsement Report For Basic Design & Scope of Work | BK-PPL-PEDCO-320-GE-RT-0001 | BK-PPL-PEDCO-320-GE-RT-0001Endorsement Report For Basic Design & Scope of Work | 2021-07-31 | 2022-05-25
Value Engineering Study Report | BK-PPL-PEDCO-320-GE-RT-0002 | BK-PPL-PEDCO-320-GE-RT-0002Value Engineering Study Report | 2022-02-01 | 2022-05-25
HAZID Report For Pipeline | BK-PPL-PEDCO-320-GE-RT-0003 | BK-PPL-PEDCO-320-GE-RT-0003HAZID Report For Pipeline |  | 2022-05-25
HAZOP Report For Pipeline | BK-PPL-PEDCO-320-GE-RT-0004 | BK-PPL-PEDCO-320-GE-RT-0004HAZOP Report For Pipeline |  | 2022-05-25
Drainage Philosophy | BK-PPL-PEDCO-320-PR-PH-0001 | BK-PPL-PEDCO-320-PR-PH-0001Drainage Philosophy | 2022-01-31 | 2022-05-25
Control Philosophy | BK-PPL-PEDCO-320-PR-PH-0002 | BK-PPL-PEDCO-320-PR-PH-0002Control Philosophy | 2022-05-09 | 2022-05-25
Flare,Blow Down And Relief Philosophy | BK-PPL-PEDCO-320-PR-PH-0003 | BK-PPL-PEDCO-320-PR-PH-0003Flare,Blow Down And Relief Philosophy | 2022-02-06 | 2022-05-25
Isolation Philosophy | BK-PPL-PEDCO-320-PR-PH-0004 | BK-PPL-PEDCO-320-PR-PH-0004Isolation Philosophy | 2021-11-21 | 2022-05-25
ESD Philosophy | BK-PPL-PEDCO-320-PR-PH-0005 | BK-PPL-PEDCO-320-PR-PH-0005ESD Philosophy | 2022-05-09 | 2022-05-25
Process Description | BK-PPL-PEDCO-320-PR-DP-0001 | BK-PPL-PEDCO-320-PR-DP-0001Process Description | 2022-02-19 | 2022-05-25
Calculation Note For PSV Sizing | BK-PPL-PEDCO-320-PR-CN-0001 | BK-PPL-PEDCO-320-PR-CN-0001Calculation Note For PSV Sizing | 2022-02-19 | 2022-05-25
Symbol & Legend For PFD and P&ID | BK-PPL-PEDCO-320-PR-PI-0003 | BK-PPL-PEDCO-320-PR-PI-0003Symbol & Legend For PFD and P&ID | 2022-01-24 | 2022-05-25
Process Flow Diagram For pipelines | BK-PPL-PEDCO-320-PR-PF-0001 | BK-PPL-PEDCO-320-PR-PF-0001Process Flow Diagram For pipelines | 2021-11-17 | 2022-05-25
P&ID - Gas Pipeline (to Siahmakan G.I. Station) | BK-PPL-PEDCO-320-PR-PI-0001 | BK-PPL-PEDCO-320-PR-PI-0001P&ID - Gas Pipeline (to Siahmakan G.I. Station) | 2021-11-17 | 2022-05-25
P&ID - Condensate Pipeline (to Binak PU) | BK-PPL-PEDCO-320-PR-PI-0002 | BK-PPL-PEDCO-320-PR-PI-0002P&ID - Condensate Pipeline (to Binak PU) | 2021-11-17 | 2022-05-25
ESD Block Diagram | BK-PPL-PEDCO-320-PR-BD-0001 | BK-PPL-PEDCO-320-PR-BD-0001ESD Block Diagram |  | 2022-05-25
Cause & Effect Diagram | BK-PPL-PEDCO-320-PR-CE-0001 | BK-PPL-PEDCO-320-PR-CE-0001Cause & Effect Diagram |  | 2022-05-25
Pipelines Hydraulic Calculation Report | BK-PPL-PEDCO-320-PR-RT-0001 | BK-PPL-PEDCO-320-PR-RT-0001Pipelines Hydraulic Calculation Report | 2021-11-17 | 2022-05-25
Equipment List | BK-PPL-PEDCO-320-PR-LI-0001 | BK-PPL-PEDCO-320-PR-LI-0001Equipment List | 2022-02-19 | 2022-05-25
Line List | BK-PPL-PEDCO-320-PR-LI-0002 | BK-PPL-PEDCO-320-PR-LI-0002Line List | 2022-02-16 | 2022-05-25
Relief Load Summary | BK-PPL-PEDCO-320-PR-LI-0003 | BK-PPL-PEDCO-320-PR-LI-0003Relief Load Summary | 2022-04-12 | 2022-05-25
Tie in list | BK-PPL-PEDCO-320-PR-LI-0004 | BK-PPL-PEDCO-320-PR-LI-0004Tie in list | 2022-02-19 | 2022-05-25
Process Data Sheets For Instrument Devices | BK-PPL-PEDCO-110-PR-DT-0001 | BK-PPL-PEDCO-110-PR-DT-0001Process Data Sheets For Instrument Devices | 2022-04-12 | 2022-05-25
Specification For Pig Traps | BK-PPL-PEDCO-320-ME-SP-0001 | BK-PPL-PEDCO-320-ME-SP-0001Specification For Pig Traps | 2021-09-04 | 2022-01-31
Data Sheets For Pig Traps | BK-PPL-PEDCO-320-ME-DT-0001 | BK-PPL-PEDCO-320-ME-DT-0001Data Sheets For Pig Traps | 2021-12-13 | 2022-05-25
Piping Material Specification | BK-PPL-PEDCO-320-PI-SP-0001 | BK-PPL-PEDCO-320-PI-SP-0001Piping Material Specification | 2021-12-12 | 2022-05-25
Unit Plot Plan For Pig Receiver Area (in Siahmakan G.I. Station) | BK-PPL-PEDCO-320-PI-PY-0001 | BK-PPL-PEDCO-320-PI-PY-0001Unit Plot Plan For Pig Receiver Area (in Siahmakan G.I. Station) |  | 2022-05-25
A/G Piping Plan | BK-PPL-PEDCO-320-PI-DW-0001 | BK-PPL-PEDCO-320-PI-DW-0001A/G Piping Plan |  | 2022-05-25
A/G Piping Isometric | BK-PPL-PEDCO-320-PI-DW-0002 | BK-PPL-PEDCO-320-PI-DW-0002A/G Piping Isometric |  | 2022-05-25
Unit Plot Plan For Binak Production Unit | BK-PPL-PEDCO-320-PI-PY-0002 | BK-PPL-PEDCO-320-PI-PY-0002Unit Plot Plan For Binak Production Unit |  | 2022-05-25
Piping Hydrostatic Test Diagram - PPL | BK-PPL-PEDCO-320-PI-PR-0001 | BK-PPL-PEDCO-320-PI-PR-0001Piping Hydrostatic Test Diagram - PPL |  | 2022-05-25
Corrosion Study & Material Selection Report | BK-PPL-PEDCO-320-PI-RT-0001 | BK-PPL-PEDCO-320-PI-RT-0001Corrosion Study & Material Selection Report | 2021-12-12 | 2022-05-25
Wall Thickness Calculation Report | BK-PPL-PEDCO-320-PI-RT-0002 | BK-PPL-PEDCO-320-PI-RT-0002Wall Thickness Calculation Report | 2021-12-12 | 2022-05-25
Stress Analysis Calculations Report | BK-PPL-PEDCO-320-PI-RT-0003 | BK-PPL-PEDCO-320-PI-RT-0003Stress Analysis Calculations Report |  | 2022-05-25
PDMS Model Review Report (30%) | BK-PPL-PEDCO-320-PI-RT-0004 | BK-PPL-PEDCO-320-PI-RT-0004PDMS Model Review Report (30%) |  | 2022-05-25
PDMS Model Review Report (60%) | BK-PPL-PEDCO-320-PI-RT-0005 | BK-PPL-PEDCO-320-PI-RT-0005PDMS Model Review Report (60%) |  | 2022-05-25
PDMS Model Review Report (90%) | BK-PPL-PEDCO-320-PI-RT-0006 | BK-PPL-PEDCO-320-PI-RT-0006PDMS Model Review Report (90%) |  | 2022-05-25
Pipe Support List | BK-PPL-PEDCO-320-PI-LI-0001 | BK-PPL-PEDCO-320-PI-LI-0001Pipe Support List |  | 2022-05-25
Piping Tie-In List | BK-PPL-PEDCO-320-PI-LI-0002 | BK-PPL-PEDCO-320-PI-LI-0002Piping Tie-In List |  | 2022-05-25
MTO For Pipes | BK-PPL-PEDCO-320-PI-MT-0001 | BK-PPL-PEDCO-320-PI-MT-0001MTO For Pipes |  | 2022-05-25
MTO For Fittings | BK-PPL-PEDCO-320-PI-MT-0002 | BK-PPL-PEDCO-320-PI-MT-0002MTO For Fittings |  | 2022-05-25
MTO For Flanges | BK-PPL-PEDCO-320-PI-MT-0003 | BK-PPL-PEDCO-320-PI-MT-0003MTO For Flanges |  | 2022-05-25
MTO For Manual Valves | BK-PPL-PEDCO-320-PI-MT-0004 | BK-PPL-PEDCO-320-PI-MT-0004MTO For Manual Valves |  | 2022-05-25
MTO For Gaskets | BK-PPL-PEDCO-320-PI-MT-0005 | BK-PPL-PEDCO-320-PI-MT-0005MTO For Gaskets |  | 2022-05-25
MTO For Bolt & Nuts | BK-PPL-PEDCO-320-PI-MT-0006 | BK-PPL-PEDCO-320-PI-MT-0006MTO For Bolt & Nuts |  | 2022-05-25
MTO For Insulation Joints | BK-PPL-PEDCO-320-PI-MT-0007 | BK-PPL-PEDCO-320-PI-MT-0007MTO For Insulation Joints
MTO For Insulation | BK-PPL-PEDCO-320-PI-MT-0008 | BK-PPL-PEDCO-320-PI-MT-0008MTO For Insulation |  | 2022-05-25
MTO For Painting | BK-PPL-PEDCO-320-PI-MT-0009 | BK-PPL-PEDCO-320-PI-MT-0009MTO For Painting |  | 2022-05-25
MTO For Coating of Underground Piping | BK-PPL-PEDCO-320-PI-MT-0010 | BK-PPL-PEDCO-320-PI-MT-0010MTO For Coating of Underground Piping |  | 2022-05-25
Pipeline Material Specification | BK-PPL-PEDCO-320-PL-SP-0001 | BK-PPL-PEDCO-320-PL-SP-0001Pipeline Material Specification | 2021-12-12 | 2022-05-25
Calculation Note For Pipeline Wall Thickness | BK-PPL-PEDCO-320-PL-CN-0001 | BK-PPL-PEDCO-320-PL-CN-0001Calculation Note For Pipeline Wall Thickness | 2021-12-12 | 2022-05-25
Data Sheets For Anchor Flanges | BK-PPL-PEDCO-320-PL-DT-0001 | BK-PPL-PEDCO-320-PL-DT-0001Data Sheets For Anchor Flanges |  | 2022-05-25
Data Sheets For Barred Tee | BK-PPL-PEDCO-320-PL-DT-0002 | BK-PPL-PEDCO-320-PL-DT-0002Data Sheets For Barred Tee | 2022-03-27 | 2022-05-25
Data Sheets For Insulation Joints | BK-PPL-PEDCO-320-PL-DT-0003 | BK-PPL-PEDCO-320-PL-DT-0003Data Sheets For Insulation Joints |  | 2022-05-25
Data Sheets For Rock Shield | BK-PPL-PEDCO-320-PL-DT-0004 | BK-PPL-PEDCO-320-PL-DT-0004Data Sheets For Rock Shield |  | 2022-05-25
Standard Support Drawings | BK-PPL-PEDCO-320-PL-DW-0001 | BK-PPL-PEDCO-320-PL-DW-0001Standard Support Drawings |  | 2022-05-25
Pipeline Standard Drawings | BK-PPL-PEDCO-320-PL-DW-0006 | BK-PPL-PEDCO-320-PL-DW-0006Pipeline Standard Drawings |  | 2022-05-25
Pipeline Hydrostatic Test Diagram - PPL | BK-PPL-PEDCO-320-PL-PR-0001 | BK-PPL-PEDCO-320-PL-PR-0001Pipeline Hydrostatic Test Diagram - PPL |  | 2022-05-25
Stress Analysis Calculations Report For Pipelines | BK-PPL-PEDCO-320-PL-RT-0001 | BK-PPL-PEDCO-320-PL-RT-0001Stress Analysis Calculations Report For Pipelines |  | 2022-05-25
MTO For Line Pipe | BK-PPL-PEDCO-320-PL-MT-0001 | BK-PPL-PEDCO-320-PL-MT-0001MTO For Line Pipe | 2021-08-22 | 2021-08-22
MTO For Pipeline Field Joints Coating | BK-PPL-PEDCO-320-PL-MT-0002 | BK-PPL-PEDCO-320-PL-MT-0002MTO For Pipeline Field Joints Coating |  | 2022-05-25
MTO For Pipeline Flange, Fittings, Gasket and Bolt | BK-PPL-PEDCO-320-PL-MT-0003 | BK-PPL-PEDCO-320-PL-MT-0003MTO For Pipeline Flange, Fittings, Gasket and Bolt |  | 2022-05-25
Instrument & Control System Basis of Design | BK-PPL-PEDCO-320-IN-DB-0001 | BK-PPL-PEDCO-320-IN-DB-0001Instrument & Control System Basis of Design | 2021-08-22 | 2022-05-25
Instrument & Control System Design Criteria | BK-PPL-PEDCO-320-IN-DC-0001 | BK-PPL-PEDCO-320-IN-DC-0001Instrument & Control System Design Criteria | 2022-01-03 | 2022-05-25
Fire & Gas Detection Design Criteria | BK-PPL-PEDCO-320-IN-DC-0002 | BK-PPL-PEDCO-320-IN-DC-0002Fire & Gas Detection Design Criteria |  | 2022-05-25
Data Sheets For Pressure & Diff. Pressure Gauge | BK-PPL-PEDCO-320-IN-DT-0001 | BK-PPL-PEDCO-320-IN-DT-0001Data Sheets For Pressure & Diff. Pressure Gauge | 2022-02-02 | 2022-05-25
Data Sheets For Temperature Gauge | BK-PPL-PEDCO-320-IN-DT-0002 | BK-PPL-PEDCO-320-IN-DT-0002Data Sheets For Temperature Gauge | 2022-02-05 | 2022-05-25
Data Sheets For Pressure/Diff. Pressure Transmitter | BK-PPL-PEDCO-320-IN-DT-0003 | BK-PPL-PEDCO-320-IN-DT-0003Data Sheets For Pressure/Diff. Pressure Transmitter | 2022-02-13 | 2022-05-25
Data Sheets For Pressure & Safety Relief Valves | BK-PPL-PEDCO-320-IN-DT-0005 | BK-PPL-PEDCO-320-IN-DT-0005Data Sheets For Pressure & Safety Relief Valves | 2022-03-27 | 2022-05-25
Data Sheets For ON/OFF & Shutdown Valves | BK-PPL-PEDCO-320-IN-DT-0006 | BK-PPL-PEDCO-320-IN-DT-0006Data Sheets For ON/OFF & Shutdown Valves |  | 2022-05-25
Data Sheets For Corrosion Coupon/ Probe | BK-PPL-PEDCO-320-IN-DT-0009 | BK-PPL-PEDCO-320-IN-DT-0009Data Sheets For Corrosion Coupon/ Probe | 2022-02-02 | 2022-05-25
Data Sheets For Pig Signaler | BK-PPL-PEDCO-320-IN-DT-0010 | BK-PPL-PEDCO-320-IN-DT-0010Data Sheets For Pig Signaler | 2022-02-02 | 2022-05-25
Data Sheets For F&G Detectors & Equipment | BK-PPL-PEDCO-320-IN-DT-0011 | BK-PPL-PEDCO-320-IN-DT-0011Data Sheets For F&G Detectors & Equipment |  | 2022-05-25
Data Sheets For LBV | BK-PPL-PEDCO-320-IN-DT-0012 | BK-PPL-PEDCO-320-IN-DT-0012Data Sheets For LBV | 2022-03-27 | 2022-05-25
Typical Instrument Installation Drawing | BK-PPL-PEDCO-320-IN-DW-0001 | BK-PPL-PEDCO-320-IN-DW-0001Typical Instrument Installation Drawing |  | 2022-05-25
Block Diagram Configuration For Control/ESD/F&G System | BK-PPL-PEDCO-320-IN-BD-0001 | BK-PPL-PEDCO-320-IN-BD-0001Block Diagram Configuration For Control/ESD/F&G System | 2021-09-01 | 2022-05-25
Instrument Earthing Typical Diagram | BK-PPL-PEDCO-320-IN-DG-0001 | BK-PPL-PEDCO-320-IN-DG-0001Instrument Earthing Typical Diagram | 2021-12-29 | 2022-04-17
Instrument Hook-up Diagram | BK-PPL-PEDCO-320-IN-DG-0002 | BK-PPL-PEDCO-320-IN-DG-0002Instrument Hook-up Diagram |  | 2022-05-25
ESD Level Hierarchy | BK-PPL-PEDCO-320-IN-DG-0003 | BK-PPL-PEDCO-320-IN-DG-0003ESD Level Hierarchy |  | 2022-05-25
ESD System Loop Diagram | BK-PPL-PEDCO-320-IN-DG-0004 | BK-PPL-PEDCO-320-IN-DG-0004ESD System Loop Diagram |  | 2022-05-25
Control System Loop Diagram | BK-PPL-PEDCO-320-IN-DG-0005 | BK-PPL-PEDCO-320-IN-DG-0005Control System Loop Diagram |  | 2022-05-25
Instrument Air Piping and Air Header Diagram | BK-PPL-PEDCO-320-IN-DG-0006 | BK-PPL-PEDCO-320-IN-DG-0006Instrument Air Piping and Air Header Diagram |  | 2022-05-25
Instrument & F&G Junction Box Termination Diagram | BK-PPL-PEDCO-320-IN-DG-0007 | BK-PPL-PEDCO-320-IN-DG-0007Instrument & F&G Junction Box Termination Diagram |  | 2022-05-25
Control System Logic Diagram | BK-PPL-PEDCO-320-IN-LD-0001 | BK-PPL-PEDCO-320-IN-LD-0001Control System Logic Diagram |  | 2022-05-25
ESD Logic Diagram | BK-PPL-PEDCO-320-IN-LD-0002 | BK-PPL-PEDCO-320-IN-LD-0002ESD Logic Diagram |  | 2022-05-25
Control Room Cable Route Layout | BK-PPL-PEDCO-320-IN-PY-0001 | BK-PPL-PEDCO-320-IN-PY-0001Control Room Cable Route Layout |  | 2022-05-25
Instrument Location Layout | BK-PPL-PEDCO-320-IN-PY-0002 | BK-PPL-PEDCO-320-IN-PY-0002Instrument Location Layout |  | 2022-05-25
Instrument Cable Trench/Route Layout Drawing | BK-PPL-PEDCO-320-IN-PY-0003 | BK-PPL-PEDCO-320-IN-PY-0003Instrument Cable Trench/Route Layout Drawing |  | 2022-05-25
Control Room Arrangement Layout | BK-PPL-PEDCO-320-IN-PY-0006 | BK-PPL-PEDCO-320-IN-PY-0006Control Room Arrangement Layout |  | 2022-05-25
F&G System Loop Diagram | BK-PPL-PEDCO-320-IN-PY-0007 | BK-PPL-PEDCO-320-IN-PY-0007F&G System Loop Diagram
F&G Cause and Effect Diagram | BK-PPL-PEDCO-320-IN-PY-0008 | BK-PPL-PEDCO-320-IN-PY-0008F&G Cause and Effect Diagram
F&G Location Layout For Process Area | BK-PPL-PEDCO-320-IN-PY-0009 | BK-PPL-PEDCO-320-IN-PY-0009F&G Location Layout For Process Area |  | 2022-05-25
Instrument Index | BK-PPL-PEDCO-320-IN-LI-0001 | BK-PPL-PEDCO-320-IN-LI-0001Instrument Index | 2022-02-02 | 2022-05-25
I/O List For Control System | BK-PPL-PEDCO-320-IN-LI-0002 | BK-PPL-PEDCO-320-IN-LI-0002I/O List For Control System |  | 2022-05-25
I/O List For ESD /F&G System | BK-PPL-PEDCO-320-IN-LI-0003 | BK-PPL-PEDCO-320-IN-LI-0003I/O List For ESD /F&G System |  | 2022-05-25
Panels & Junction Box List | BK-PPL-PEDCO-320-IN-LI-0004 | BK-PPL-PEDCO-320-IN-LI-0004Panels & Junction Box List |  | 2022-05-25
Set Point & Alarm List | BK-PPL-PEDCO-320-IN-LI-0005 | BK-PPL-PEDCO-320-IN-LI-0005Set Point & Alarm List |  | 2022-05-25
I&C Power Consumption Summary | BK-PPL-PEDCO-320-IN-LI-0006 | BK-PPL-PEDCO-320-IN-LI-0006I&C Power Consumption Summary |  | 2022-05-25
Instrument and F&G Cable List | BK-PPL-PEDCO-320-IN-LI-0007 | BK-PPL-PEDCO-320-IN-LI-0007Instrument and F&G Cable List |  | 2022-05-25
F&G Detector List | BK-PPL-PEDCO-320-IN-LI-0008 | BK-PPL-PEDCO-320-IN-LI-0008F&G Detector List |  | 2022-05-25
MTO for Bulk Item and Installation Accessories | BK-PPL-PEDCO-320-IN-MT-0001 | BK-PPL-PEDCO-320-IN-MT-0001MTO for Bulk Item and Installation Accessories |  | 2022-05-25
MTO For Instrument/F&G Cable | BK-PPL-PEDCO-320-IN-MT-0002 | BK-PPL-PEDCO-320-IN-MT-0002MTO For Instrument/F&G Cable |  | 2022-05-25
MTO For Instrument/F&G Junction box and Gland | BK-PPL-PEDCO-320-IN-MT-0003 | BK-PPL-PEDCO-320-IN-MT-0003MTO For Instrument/F&G Junction box and Gland |  | 2022-05-25
MTO For Instrument Tube and Fitting | BK-PPL-PEDCO-320-IN-MT-0004 | BK-PPL-PEDCO-320-IN-MT-0004MTO For Instrument Tube and Fitting |  | 2022-05-25
MTO For Instrument Cable Tray/Ladder | BK-PPL-PEDCO-320-IN-MT-0005 | BK-PPL-PEDCO-320-IN-MT-0005MTO For Instrument Cable Tray/Ladder |  | 2022-05-25
MTO For Safety Sign | BK-PPL-PEDCO-320-SA-MT-0002 | BK-PPL-PEDCO-320-SA-MT-0002MTO For Safety Sign |  | 2022-05-25
Active Fire Protection and Safety Concept | BK-PPL-PEDCO-320-SA-DB-0001 | BK-PPL-PEDCO-320-SA-DB-0001Active Fire Protection and Safety Concept | 2021-11-16 | 2022-05-25
Data Sheets For Safety Equipment | BK-PPL-PEDCO-320-SA-DT-0002 | BK-PPL-PEDCO-320-SA-DT-0002Data Sheets For Safety Equipment |  | 2022-05-25
Data Sheets For fire fighting Equipment | BK-PPL-PEDCO-320-SA-DT-0003 | BK-PPL-PEDCO-320-SA-DT-0003Data Sheets For fire fighting Equipment |  | 2022-05-25
Data Sheets For safety sign | BK-PPL-PEDCO-320-SA-DT-0004 | BK-PPL-PEDCO-320-SA-DT-0004Data Sheets For safety sign |  | 2022-05-25
Hazardous Area Classification Layout | BK-PPL-PEDCO-320-SA-PY-0001 | BK-PPL-PEDCO-320-SA-PY-0001Hazardous Area Classification Layout |  | 2022-05-25
Safety & Fire Fighting Equipment Location Layout | BK-PPL-PEDCO-320-SA-PY-0002 | BK-PPL-PEDCO-320-SA-PY-0002Safety & Fire Fighting Equipment Location Layout |  | 2022-05-25
Escape Route & Safety Sign Layout | BK-PPL-PEDCO-320-SA-PY-0003 | BK-PPL-PEDCO-320-SA-PY-0003Escape Route & Safety Sign Layout |  | 2022-05-25
QRA Report | BK-PPL-PEDCO-320-SA-RT-0003 | BK-PPL-PEDCO-320-SA-RT-0003QRA Report |  | 2022-05-25
Hazard Source List | BK-PPL-PEDCO-320-SA-LI-0001 | BK-PPL-PEDCO-320-SA-LI-0001Hazard Source List | 2021-11-16 | 2022-05-25
MTO For Safety & Fire Fighting Equipment | BK-PPL-PEDCO-320-SA-MT-0001 | BK-PPL-PEDCO-320-SA-MT-0001MTO For Safety & Fire Fighting Equipment |  | 2022-05-25
Calculation Note For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-CN-0001 | BK-PPL-PEDCO-320-EL-CN-0001Calculation Note For Cathodic Protection System for Siahmakan Gas Injection |  | 2022-05-25
Data Sheets For Expansion of LV Switchgear in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-DT-0001 | BK-PPL-PEDCO-320-EL-DT-0001Data Sheets For Expansion of LV Switchgear in Siahmakan Gas Injection |  | 2022-05-25
Data Sheets For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-DT-0002 | BK-PPL-PEDCO-320-EL-DT-0002Data Sheets For Cathodic Protection System for Siahmakan Gas Injection |  | 2022-05-25
Single Line Diagram For Expansion Of Upstream LV Switchgear in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-SL-0001 | BK-PPL-PEDCO-320-EL-SL-0001Single Line Diagram For Expansion Of Upstream LV Switchgear in Siahmakan Gas Injection |  | 2022-05-25
Interconnection Wiring Diagram in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-DG-0002 | BK-PPL-PEDCO-320-EL-DG-0002Interconnection Wiring Diagram in Siahmakan Gas Injection |  | 2022-05-25
Interconnection Wiring Diagrams For Cathodic Protection Systems for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-DG-0003 | BK-PPL-PEDCO-320-EL-DG-0003Interconnection Wiring Diagrams For Cathodic Protection Systems for Siahmakan Gas Injection |  | 2022-05-25
Area Earthing Layout in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-PY-0001 | BK-PPL-PEDCO-320-EL-PY-0001Area Earthing Layout in Siahmakan Gas Injection |  | 2022-05-25
Area Electrical Cable Route & Section Layout in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-PY-0002 | BK-PPL-PEDCO-320-EL-PY-0002Area Electrical Cable Route & Section Layout in Siahmakan Gas Injection |  | 2022-05-25
Layout For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-PY-0003 | BK-PPL-PEDCO-320-EL-PY-0003Layout For Cathodic Protection System for Siahmakan Gas Injection | 2022-05-02 | 2022-05-25
Electrical Load List in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-LI-0001 | BK-PPL-PEDCO-320-EL-LI-0001Electrical Load List in Siahmakan Gas Injection |  | 2022-05-25
Electrical Power & Control Cable List in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-LI-0002 | BK-PPL-PEDCO-320-EL-LI-0002Electrical Power & Control Cable List in Siahmakan Gas Injection |  | 2022-05-25
Cable Schedule For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-LI-0003 | BK-PPL-PEDCO-320-EL-LI-0003Cable Schedule For Cathodic Protection System for Siahmakan Gas Injection |  | 2022-05-25
MTO For Earthing & Lightning Systems in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0001 | BK-PPL-PEDCO-320-EL-MT-0001MTO For Earthing & Lightning Systems in Siahmakan Gas Injection |  | 2022-05-25
MTO For Power & Control Cables in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0002 | BK-PPL-PEDCO-320-EL-MT-0002MTO For Power & Control Cables in Siahmakan Gas Injection |  | 2022-05-25
MTO For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0003 | BK-PPL-PEDCO-320-EL-MT-0003MTO For Cathodic Protection System for Siahmakan Gas Injection |  | 2022-05-25
MTO For Electrical Bulk Items in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0004 | BK-PPL-PEDCO-320-EL-MT-0004MTO For Electrical Bulk Items in Siahmakan Gas Injection |  | 2022-05-25
MTO For Lighting & Small Powers in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0006 | BK-PPL-PEDCO-320-EL-MT-0006MTO For Lighting & Small Powers in Siahmakan Gas Injection |  | 2022-05-25
Civil Layout For Pig Receiver Area (In Siahmakan G.I. Station) | BK-PPL-PEDCO-320-CV-PY-0001 | BK-PPL-PEDCO-320-CV-PY-0001Civil Layout For Pig Receiver Area (In Siahmakan G.I. Station) |  | 2022-05-25
Civil Layout For LBV Stations | BK-PPL-PEDCO-320-CV-PY-0002 | BK-PPL-PEDCO-320-CV-PY-0002Civil Layout For LBV Stations |  | 2022-05-25
Site Visit Report (Civil Work) - 8" & 4" Pipelines | BK-PPL-PEDCO-110-CV-RT-0001 | BK-PPL-PEDCO-110-CV-RT-0001Site Visit Report (Civil Work) - 8" & 4" Pipelines |  | 2022-05-25
Foundation Drawing For Pig Receiver (PL-3101 In Siahmakan G.I. Station) | BK-PPL-PEDCO-320-ST-DW-0001 | BK-PPL-PEDCO-320-ST-DW-0001Foundation Drawing For Pig Receiver (PL-3101 In Siahmakan G.I. Station) |  | 2022-05-25
Structural Drawing For LBV Pits | BK-PPL-PEDCO-320-ST-DW-0002 | BK-PPL-PEDCO-320-ST-DW-0002Structural Drawing For LBV Pits |  | 2022-05-25
Geotechnical Investigation Plan for Pipelines | BK-PPL-PEDCO-320-GT-PR-0001 | BK-PPL-PEDCO-320-GT-PR-0001Geotechnical Investigation Plan for Pipelines | 2021-08-11 | 2021-10-25
Geotechnical Investigation Report for Pipelines | BK-PPL-PEDCO-320-GT-RT-0001 | BK-PPL-PEDCO-320-GT-RT-0001Geotechnical Investigation Report for Pipelines |  | 2022-05-25
Plan & Profile Drawings For Gas Pipeline (to Siahmakan) | BK-PPL-PEDCO-320-SU-DW-0001 | BK-PPL-PEDCO-320-SU-DW-0001Plan & Profile Drawings For Gas Pipeline (to Siahmakan) |  | 2022-05-25
Plan & Profile Drawings For Condensate Pipeline (to Binak PU) | BK-PPL-PEDCO-320-SU-DW-0002 | BK-PPL-PEDCO-320-SU-DW-0002Plan & Profile Drawings For Condensate Pipeline (to Binak PU) |  | 2022-05-25
PMR For Pig Traps | BK-PPL-PEDCO-320-ME-MR-0001 | BK-PPL-PEDCO-320-ME-MR-0001PMR For Pig Traps | 2022-02-21 | 2022-02-21
TBE For Pig Traps | BK-PPL-PEDCO-320-ME-TB-0001 | BK-PPL-PEDCO-320-ME-TB-0001TBE For Pig Traps |  | 2022-05-25
PMR For Line Pipe | BK-PPL-PEDCO-320-PL-MR-0001 | BK-PPL-PEDCO-320-PL-MR-0001PMR For Line Pipe | 2021-12-06 | 2021-12-06
TBE For Line Pipe | BK-PPL-PEDCO-320-PL-TB-0001 | BK-PPL-PEDCO-320-PL-TB-0001TBE For Line Pipe |  | 2022-05-25
PMR For Line Insulation Joints | BK-PPL-PEDCO-320-PL-MR-0002 | BK-PPL-PEDCO-320-PL-MR-0002PMR For Line Insulation Joints |  | 2022-05-25
TBE For Line Insulation Joints | BK-PPL-PEDCO-320-PL-TB-0002 | BK-PPL-PEDCO-320-PL-TB-0002TBE For Line Insulation Joints |  | 2022-05-25
PMR For Anchor Flanges | BK-PPL-PEDCO-320-PL-MR-0003 | BK-PPL-PEDCO-320-PL-MR-0003PMR For Anchor Flanges |  | 2022-05-25
TBE For Anchor Flanges | BK-PPL-PEDCO-320-PL-TB-0003 | BK-PPL-PEDCO-320-PL-TB-0003TBE For Anchor Flanges |  | 2022-05-25
PMR For Pipeline Flange, Fittings, Gasket and Bolt | BK-PPL-PEDCO-320-PL-MR-0004 | BK-PPL-PEDCO-320-PL-MR-0004PMR For Pipeline Flange, Fittings, Gasket and Bolt |  | 2022-05-25
TBE For Pipeline Flange, Fittings, Gasket and Bolt | BK-PPL-PEDCO-320-PL-TB-0004 | BK-PPL-PEDCO-320-PL-TB-0004TBE For Pipeline Flange, Fittings, Gasket and Bolt |  | 2022-05-25
PMR For Pipeline Rock Shield | BK-PPL-PEDCO-320-PL-MR-0005 | BK-PPL-PEDCO-320-PL-MR-0005PMR For Pipeline Rock Shield |  | 2022-05-25
TBE For Pipeline Rock Shield | BK-PPL-PEDCO-320-PL-TB-0005 | BK-PPL-PEDCO-320-PL-TB-0005TBE For Pipeline Rock Shield |  | 2022-05-25
PMR For Control System/Console/Furniture | BK-PPL-PEDCO-320-IN-MR-0001 | BK-PPL-PEDCO-320-IN-MR-0001PMR For Control System/Console/Furniture |  | 2022-05-25
TBE For Control System/Console/Furniture | BK-PPL-PEDCO-320-IN-TB-0001 | BK-PPL-PEDCO-320-IN-TB-0001TBE For Control System/Console/Furniture |  | 2022-05-25
PMR For ESD System | BK-PPL-PEDCO-320-IN-MR-0002 | BK-PPL-PEDCO-320-IN-MR-0002PMR For ESD System |  | 2022-05-25
TBE For ESD System | BK-PPL-PEDCO-320-IN-TB-0002 | BK-PPL-PEDCO-320-IN-TB-0002TBE For ESD System |  | 2022-05-25
PMR For Corrosion Probe/Coupon | BK-PPL-PEDCO-320-IN-MR-0003 | BK-PPL-PEDCO-320-IN-MR-0003PMR For Corrosion Probe/Coupon |  | 2022-05-25
TBE For Corrosion Probe/Coupon | BK-PPL-PEDCO-320-IN-TB-0003 | BK-PPL-PEDCO-320-IN-TB-0003TBE For Corrosion Probe/Coupon |  | 2022-05-25
PMR For ON/OFF & Shutdown Valves | BK-PPL-PEDCO-320-IN-MR-0004 | BK-PPL-PEDCO-320-IN-MR-0004PMR For ON/OFF & Shutdown Valves |  | 2022-05-25
TBE For ON/OFF & Shutdown Valves | BK-PPL-PEDCO-320-IN-TB-0004 | BK-PPL-PEDCO-320-IN-TB-0004TBE For ON/OFF & Shutdown Valves |  | 2022-05-25
PMR For Pressure Safety Valves (PSV) | BK-PPL-PEDCO-320-IN-MR-0006 | BK-PPL-PEDCO-320-IN-MR-0006PMR For Pressure Safety Valves (PSV) |  | 2022-05-25
TBE For Pressure Safety Valves (PSV) | BK-PPL-PEDCO-320-IN-TB-0006 | BK-PPL-PEDCO-320-IN-TB-0006TBE For Pressure Safety Valves (PSV) |  | 2022-05-25
PMR For Differential Pressure/Pressure Gauge | BK-PPL-PEDCO-320-IN-MR-0008 | BK-PPL-PEDCO-320-IN-MR-0008PMR For Differential Pressure/Pressure Gauge |  | 2022-05-25
TBE For Differential Pressure/Pressure Gauge | BK-PPL-PEDCO-320-IN-TB-0008 | BK-PPL-PEDCO-320-IN-TB-0008TBE For Differential Pressure/Pressure Gauge |  | 2022-05-25
PMR For Pressure/Diff. Pressure Transmitter | BK-PPL-PEDCO-320-IN-MR-0009 | BK-PPL-PEDCO-320-IN-MR-0009PMR For Pressure/Diff. Pressure Transmitter |  | 2022-05-25
TBE For Pressure/Diff. Pressure Transmitter | BK-PPL-PEDCO-320-IN-TB-0009 | BK-PPL-PEDCO-320-IN-TB-0009TBE For Pressure/Diff. Pressure Transmitter |  | 2022-05-25
PMR For Temperature Gauge | BK-PPL-PEDCO-320-IN-MR-0010 | BK-PPL-PEDCO-320-IN-MR-0010PMR For Temperature Gauge |  | 2022-05-25
TBE For Temperature Gauge | BK-PPL-PEDCO-320-IN-TB-0010 | BK-PPL-PEDCO-320-IN-TB-0010TBE For Temperature Gauge |  | 2022-05-25
PMR For Pig Signaler | BK-PPL-PEDCO-320-IN-MR-0013 | BK-PPL-PEDCO-320-IN-MR-0013PMR For Pig Signaler |  | 2022-05-25
TBE For Pig Signaler | BK-PPL-PEDCO-320-IN-TB-0013 | BK-PPL-PEDCO-320-IN-TB-0013TBE For Pig Signaler |  | 2022-05-25
PMR For Instrument Installation Accessories | BK-PPL-PEDCO-320-IN-MR-0014 | BK-PPL-PEDCO-320-IN-MR-0014PMR For Instrument Installation Accessories |  | 2022-05-25
TBE For Instrument Installation Accessories | BK-PPL-PEDCO-320-IN-TB-0014 | BK-PPL-PEDCO-320-IN-TB-0014TBE For Instrument Installation Accessories |  | 2022-05-25
PMR For Instrument Cable Tray | BK-PPL-PEDCO-320-IN-MR-0015 | BK-PPL-PEDCO-320-IN-MR-0015PMR For Instrument Cable Tray |  | 2022-05-25
TBE For Instrument Cable Tray | BK-PPL-PEDCO-320-IN-TB-0015 | BK-PPL-PEDCO-320-IN-TB-0015TBE For Instrument Cable Tray |  | 2022-05-25
PMR For Instrument and F&G Junction box and Gland | BK-PPL-PEDCO-320-IN-MR-0016 | BK-PPL-PEDCO-320-IN-MR-0016PMR For Instrument and F&G Junction box and Gland |  | 2022-05-25
TBE For Instrument and F&G Junction box and Gland | BK-PPL-PEDCO-320-IN-TB-0016 | BK-PPL-PEDCO-320-IN-TB-0016TBE For Instrument and F&G Junction box and Gland |  | 2022-05-25
PMR For Instrument Tube and Fitting | BK-PPL-PEDCO-320-IN-MR-0017 | BK-PPL-PEDCO-320-IN-MR-0017PMR For Instrument Tube and Fitting |  | 2022-05-25
TBE For Instrument Tube and Fitting | BK-PPL-PEDCO-320-IN-TB-0017 | BK-PPL-PEDCO-320-IN-TB-0017TBE For Instrument Tube and Fitting |  | 2022-05-25
PMR For Instrument and F&G Cable | BK-PPL-PEDCO-320-IN-MR-0018 | BK-PPL-PEDCO-320-IN-MR-0018PMR For Instrument and F&G Cable |  | 2022-05-25
TBE For Instrument and F&G Cable | BK-PPL-PEDCO-320-IN-TB-0018 | BK-PPL-PEDCO-320-IN-TB-0018TBE For Instrument and F&G Cable |  | 2022-05-25
PMR For F&G Devices | BK-PPL-PEDCO-320-IN-MR-0019 | BK-PPL-PEDCO-320-IN-MR-0019PMR For F&G Devices |  | 2022-05-25
TBE For F&G Devices | BK-PPL-PEDCO-320-IN-TB-0019 | BK-PPL-PEDCO-320-IN-TB-0019TBE For F&G Devices |  | 2022-05-25
PMR For LBV | BK-PPL-PEDCO-320-IN-MR-0020 | BK-PPL-PEDCO-320-IN-MR-0020PMR For LBV |  | 2022-05-25
TBE For LBV | BK-PPL-PEDCO-320-IN-TB-0020 | BK-PPL-PEDCO-320-IN-TB-0020TBE For LBV |  | 2022-05-25
PMR For Safety Equipment | BK-PPL-PEDCO-320-SA-MR-0001 | BK-PPL-PEDCO-320-SA-MR-0001PMR For Safety Equipment |  | 2022-05-25
TBE For Safety Equipment | BK-PPL-PEDCO-320-SA-TB-0001 | BK-PPL-PEDCO-320-SA-TB-0001TBE For Safety Equipment |  | 2022-05-25
PMR For Fire Fighting Equipment | BK-PPL-PEDCO-320-SA-MR-0002 | BK-PPL-PEDCO-320-SA-MR-0002PMR For Fire Fighting Equipment |  | 2022-05-25
TBE For Fire Fighting Equipment | BK-PPL-PEDCO-320-SA-TB-0002 | BK-PPL-PEDCO-320-SA-TB-0002TBE For Fire Fighting Equipment |  | 2022-05-25
PMR For Safety Signs | BK-PPL-PEDCO-320-SA-MR-0003 | BK-PPL-PEDCO-320-SA-MR-0003PMR For Safety Signs |  | 2022-05-25
TBE For Safety Signs | BK-PPL-PEDCO-320-SA-TB-0003 | BK-PPL-PEDCO-320-SA-TB-0003TBE For Safety Signs |  | 2022-05-25
PMR For Expansion Of LV Switchgear in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MR-0001 | BK-PPL-PEDCO-320-EL-MR-0001PMR For Expansion Of LV Switchgear in Siahmakan Gas Injection |  | 2022-05-25
TBE For Expansion Of LV Switchgear in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-TB-0001 | BK-PPL-PEDCO-320-EL-TB-0001TBE For Expansion Of LV Switchgear in Siahmakan Gas Injection |  | 2022-05-25
PMR For Power & Control Cables in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MR-0002 | BK-PPL-PEDCO-320-EL-MR-0002PMR For Power & Control Cables in Siahmakan Gas Injection |  | 2022-05-25
TBE For Power & Control Cables in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-TB-0002 | BK-PPL-PEDCO-320-EL-TB-0002TBE For Power & Control Cables in Siahmakan Gas Injection |  | 2022-05-25
PMR For Cathodic Protection System | BK-PPL-PEDCO-320-EL-MR-0003 | BK-PPL-PEDCO-320-EL-MR-0003PMR For Cathodic Protection System |  | 2022-05-25
TBE For Cathodic Protection System | BK-PPL-PEDCO-320-EL-TB-0003 | BK-PPL-PEDCO-320-EL-TB-0003TBE For Cathodic Protection System |  | 2022-05-25
PMR For Electrical Bulk Items in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MR-0004 | BK-PPL-PEDCO-320-EL-MR-0004PMR For Electrical Bulk Items in Siahmakan Gas Injection |  | 2022-05-25
TBE For Electrical Bulk Items in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-TB-0004 | BK-PPL-PEDCO-320-EL-TB-0004TBE For Electrical Bulk Items in Siahmakan Gas Injection |  | 2022-05-25
Pre-Commissioning, Commissioning & Startup Procedure | BK-PPL-PEDCO-320-CO-PR-0001 | BK-PPL-PEDCO-320-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure |  | 2022-05-25
Technical/Site Queries | BK-PPL-PEDCO-320-GE-TQ-0001 | BK-PPL-PEDCO-320-GE-TQ-0001Technical/Site Queries |  | 2022-05-25
As-Built Document Booklets | BK-PPL-PEDCO-320-GE-DO-0001 | BK-PPL-PEDCO-320-GE-DO-0001As-Built Document Booklets |  | 2022-05-25
Operating Manual | BK-PPL-PEDCO-320-GE-ML-0001 | BK-PPL-PEDCO-320-GE-ML-0001Operating Manual |  | 2022-05-25
As-Built Document Booklets | BK-PPL-PEDCO-320-GE-DO-0001 | BK-PPL-PEDCO-320-GE-DO-0001As-Built Document Booklets |  | 2022-05-25
Final Engineering Dossier | BK-PPL-PEDCO-320-GE-DO-0002 | BK-PPL-PEDCO-320-GE-DO-0002Final Engineering Dossier |  | 2022-05-25
Endorsement Report For Basic Design & Scope of Work | BK-GCS-PEDCO-120-GE-RT-0001 | BK-GCS-PEDCO-120-GE-RT-0001Endorsement Report For Basic Design & Scope of Work | 2021-07-31 | 2022-05-25
Value Engineering Study Report | BK-GCS-PEDCO-120-GE-RT-0002 | BK-GCS-PEDCO-120-GE-RT-0002Value Engineering Study Report | 2022-02-01 | 2022-05-25
HAZID Report For Compressor Station | BK-GCS-PEDCO-120-GE-RT-0003 | BK-GCS-PEDCO-120-GE-RT-0003HAZID Report For Compressor Station |  | 2022-05-25
HAZOP Report For Compressor Station | BK-GCS-PEDCO-120-GE-RT-0004 | BK-GCS-PEDCO-120-GE-RT-0004HAZOP Report For Compressor Station |  | 2022-05-25
SIL Report For Compressor Station | BK-GCS-PEDCO-120-GE-RT-0005 | BK-GCS-PEDCO-120-GE-RT-0005SIL Report For Compressor Station |  | 2022-05-25
Drainage Philosophy | BK-GCS-PEDCO-120-PR-PH-0001 | BK-GCS-PEDCO-120-PR-PH-0001Drainage Philosophy | 2021-11-21 | 2022-05-25
Control Philosophy | BK-GCS-PEDCO-120-PR-PH-0002 | BK-GCS-PEDCO-120-PR-PH-0002Control Philosophy | 2022-02-20 | 2022-05-25
Flare,Blow Down And Relief Philosophy | BK-GCS-PEDCO-120-PR-PH-0003 | BK-GCS-PEDCO-120-PR-PH-0003Flare,Blow Down And Relief Philosophy | 2021-11-21 | 2022-05-25
Isolation Philosophy | BK-GCS-PEDCO-120-PR-PH-0004 | BK-GCS-PEDCO-120-PR-PH-0004Isolation Philosophy | 2021-11-21 | 2022-05-22
ESD Philosophy | BK-GCS-PEDCO-120-PR-PH-0005 | BK-GCS-PEDCO-120-PR-PH-0005ESD Philosophy | 2022-02-20 | 2022-05-25
Chemical Regeneration Procedure | BK-GCS-PEDCO-120-PR-PR-0001 | BK-GCS-PEDCO-120-PR-PR-0001Chemical Regeneration Procedure |  | 2022-05-25
Startup And Shutdown Procedure | BK-GCS-PEDCO-120-PR-PR-0002 | BK-GCS-PEDCO-120-PR-PR-0002Startup And Shutdown Procedure |  | 2022-05-25
Process & Utility Description | BK-GCS-PEDCO-120-PR-DP-0001 | BK-GCS-PEDCO-120-PR-DP-0001Process & Utility Description | 2022-02-20 | 2022-05-25
Duty Specification For Gas Dehydration Package | BK-GCS-PEDCO-120-PR-SP-0001 | BK-GCS-PEDCO-120-PR-SP-0001Duty Specification For Gas Dehydration Package | 2021-08-22 | 2022-05-25
Duty Specification for Instrument/Plant Air & Nitrogen Packages | BK-GCS-PEDCO-120-PR-SP-0002 | BK-GCS-PEDCO-120-PR-SP-0002Duty Specification for Instrument/Plant Air & Nitrogen Packages | 2021-12-28 | 2022-05-25
Duty Specification for LP Flare Package | BK-GCS-PEDCO-120-PR-SP-0003 | BK-GCS-PEDCO-120-PR-SP-0003Duty Specification for LP Flare Package | 2022-03-09 | 2022-05-25
Duty Specification for Chemical Injection Package | BK-GCS-PEDCO-120-PR-SP-0004 | BK-GCS-PEDCO-120-PR-SP-0004Duty Specification for Chemical Injection Package | 2022-03-09 | 2022-05-25
Calculation Note For Pumps | BK-GCS-PEDCO-120-PR-CN-0001 | BK-GCS-PEDCO-120-PR-CN-0001Calculation Note For Pumps | 2021-12-13 | 2022-05-25
Calculation Note For Drum Sizing | BK-GCS-PEDCO-120-PR-CN-0002 | BK-GCS-PEDCO-120-PR-CN-0002Calculation Note For Drum Sizing | 2021-09-26 | 2022-05-25
Calculation Note For Flow Element Sizing | BK-GCS-PEDCO-120-PR-CN-0003 | BK-GCS-PEDCO-120-PR-CN-0003Calculation Note For Flow Element Sizing |  | 2022-05-25
Calculation Note For PSV Sizing | BK-GCS-PEDCO-120-PR-CN-0004 | BK-GCS-PEDCO-120-PR-CN-0004Calculation Note For PSV Sizing | 2021-09-26 | 2022-05-25
Calculation Note For Line Sizing | BK-GCS-PEDCO-120-PR-CN-0005 | BK-GCS-PEDCO-120-PR-CN-0005Calculation Note For Line Sizing | 2021-09-26 | 2022-05-25
Calculation Note For Control Valve Sizing | BK-GCS-PEDCO-120-PR-CN-0006 | BK-GCS-PEDCO-120-PR-CN-0006Calculation Note For Control Valve Sizing | 2021-09-26 | 2022-05-25
Calculation Note For Depressurizing (Min. Design Temperature ) | BK-GCS-PEDCO-120-PR-CN-0007 | BK-GCS-PEDCO-120-PR-CN-0007Calculation Note For Depressurizing (Min. Design Temperature ) | 2021-12-13 | 2022-05-25
Process Data Sheets For Inlet Gas K.O. Drum | BK-GCS-PEDCO-120-PR-DT-0001 | BK-GCS-PEDCO-120-PR-DT-0001Process Data Sheets For Inlet Gas K.O. Drum | 2021-11-10 | 2022-05-25
Process Data Sheets For 1st Stage G.C. Suction Drums | BK-GCS-PEDCO-120-PR-DT-0002 | BK-GCS-PEDCO-120-PR-DT-0002Process Data Sheets For 1st Stage G.C. Suction Drums | 2021-11-10 | 2022-05-25
Process Data Sheets For 1st Stage Gas Air Coolers | BK-GCS-PEDCO-120-PR-DT-0003 | BK-GCS-PEDCO-120-PR-DT-0003Process Data Sheets For 1st Stage Gas Air Coolers | 2021-11-07 | 2022-05-25
Process Data Sheets For 2nd Stage G.C. Suction Drums | BK-GCS-PEDCO-120-PR-DT-0004 | BK-GCS-PEDCO-120-PR-DT-0004Process Data Sheets For 2nd Stage G.C. Suction Drums | 2021-11-10 | 2022-05-25
Process Data Sheets For 2nd Stage Gas Air Coolers | BK-GCS-PEDCO-120-PR-DT-0005 | BK-GCS-PEDCO-120-PR-DT-0005Process Data Sheets For 2nd Stage Gas Air Coolers | 2021-11-07 | 2022-05-25
Process Data Sheets For Discharge Gas K.O. Drum | BK-GCS-PEDCO-120-PR-DT-0006 | BK-GCS-PEDCO-120-PR-DT-0006Process Data Sheets For Discharge Gas K.O. Drum | 2021-11-10 | 2022-05-25
Process Data Sheets For Diesel Oil Drum | BK-GCS-PEDCO-120-PR-DT-0007 | BK-GCS-PEDCO-120-PR-DT-0007Process Data Sheets For Diesel Oil Drum | 2021-11-10 | 2022-05-25
Process Data Sheets For Instrument Air Receiver | BK-GCS-PEDCO-120-PR-DT-0008 | BK-GCS-PEDCO-120-PR-DT-0008Process Data Sheets For Instrument Air Receiver | 2021-11-10 | 2022-05-25
Process Data Sheets For Nitrogen Receiver | BK-GCS-PEDCO-120-PR-DT-0009 | BK-GCS-PEDCO-120-PR-DT-0009Process Data Sheets For Nitrogen Receiver | 2021-11-10 | 2022-05-25
Process Data Sheets For Close Drain Drum | BK-GCS-PEDCO-120-PR-DT-0010 | BK-GCS-PEDCO-120-PR-DT-0010Process Data Sheets For Close Drain Drum | 2021-11-10 | 2022-05-25
Process Data Sheets For Elevated Potable Water Tank | BK-GCS-PEDCO-120-PR-DT-0011 | BK-GCS-PEDCO-120-PR-DT-0011Process Data Sheets For Elevated Potable Water Tank | 2021-11-10 | 2022-05-25
Process Data Sheets For Flare K.O. Drum | BK-GCS-PEDCO-120-PR-DT-0012 | BK-GCS-PEDCO-120-PR-DT-0012Process Data Sheets For Flare K.O. Drum | 2021-11-10 | 2022-05-25
Process Data Sheets For Fuel Gas K.O. Drum | BK-GCS-PEDCO-120-PR-DT-0013 | BK-GCS-PEDCO-120-PR-DT-0013Process Data Sheets For Fuel Gas K.O. Drum | 2021-11-10 | 2022-05-25
Process Data Sheets For Slug Catcher | BK-GCS-PEDCO-120-PR-DT-0014 | BK-GCS-PEDCO-120-PR-DT-0014Process Data Sheets For Slug Catcher | 2021-11-10 | 2022-05-25
Process Data Sheets For Degassing Vessel | BK-GCS-PEDCO-120-PR-DT-0015 | BK-GCS-PEDCO-120-PR-DT-0015Process Data Sheets For Degassing Vessel | 2021-11-10 | 2022-05-25
Process Data Sheets For Lean Glycol Storage Tank | BK-GCS-PEDCO-120-PR-DT-0016 | BK-GCS-PEDCO-120-PR-DT-0016Process Data Sheets For Lean Glycol Storage Tank | 2021-11-27 | 2022-05-25
Process Data Sheets For Slug Storage Tank | BK-GCS-PEDCO-120-PR-DT-0018 | BK-GCS-PEDCO-120-PR-DT-0018Process Data Sheets For Slug Storage Tank | 2021-11-27 | 2022-05-25
Process Data Sheets For Glycol Sump Drum | BK-GCS-PEDCO-120-PR-DT-0019 | BK-GCS-PEDCO-120-PR-DT-0019Process Data Sheets For Glycol Sump Drum | 2021-12-28 | 2022-05-25
Process Data Sheets For Slug Pumps | BK-GCS-PEDCO-120-PR-DT-0020 | BK-GCS-PEDCO-120-PR-DT-0020Process Data Sheets For Slug Pumps | 2021-11-28 | 2022-05-25
Process Data Sheets For Glycol Transfer Pumps | BK-GCS-PEDCO-120-PR-DT-0021 | BK-GCS-PEDCO-120-PR-DT-0021Process Data Sheets For Glycol Transfer Pumps | 2021-11-28 | 2022-05-25
Process Data Sheets For Glycol Manual Pump | BK-GCS-PEDCO-120-PR-DT-0022 | BK-GCS-PEDCO-120-PR-DT-0022Process Data Sheets For Glycol Manual Pump | 2021-11-28 | 2022-05-25
Process Data Sheets For Closed Drain Pumps | BK-GCS-PEDCO-120-PR-DT-0023 | BK-GCS-PEDCO-120-PR-DT-0023Process Data Sheets For Closed Drain Pumps | 2021-11-28 | 2022-05-25
Process Data Sheets For Sump Pumps | BK-GCS-PEDCO-120-PR-DT-0024 | BK-GCS-PEDCO-120-PR-DT-0024Process Data Sheets For Sump Pumps | 2021-11-28 | 2022-05-25
Process Data Sheets For Flare KO Drum Pumps | BK-GCS-PEDCO-120-PR-DT-0025 | BK-GCS-PEDCO-120-PR-DT-0025Process Data Sheets For Flare KO Drum Pumps | 2021-11-28 | 2022-05-25
Process Data Sheets For Potable Water Pump | BK-GCS-PEDCO-120-PR-DT-0026 | BK-GCS-PEDCO-120-PR-DT-0026Process Data Sheets For Potable Water Pump | 2021-11-28 | 2022-05-25
Process Data Sheets For Glycol Sump Pumps | BK-GCS-PEDCO-120-PR-DT-0027 | BK-GCS-PEDCO-120-PR-DT-0027Process Data Sheets For Glycol Sump Pumps | 2021-11-28 | 2022-05-25
Process Data Sheets For Glycol Drain Pump | BK-GCS-PEDCO-120-PR-DT-0028 | BK-GCS-PEDCO-120-PR-DT-0028Process Data Sheets For Glycol Drain Pump | 2021-11-28 | 2022-05-25
Process Data Sheets of Diesel Pump | BK-GCS-PEDCO-120-PR-DT-0028 | BK-GCS-PEDCO-120-PR-DT-0028Process Data Sheets of Diesel Pump | 2021-11-28 | 2022-05-25
Process Data Sheets For Gas Compressors Packages | BK-GCS-PEDCO-120-PR-DT-0030 | BK-GCS-PEDCO-120-PR-DT-0030Process Data Sheets For Gas Compressors Packages | 2021-11-07 | 2022-05-25
Process Data Sheets For Chemical Injection Packages | BK-GCS-PEDCO-120-PR-DT-0031 | BK-GCS-PEDCO-120-PR-DT-0031Process Data Sheets For Chemical Injection Packages | 2022-05-09 | 2022-05-25
Process Data Sheets For Instrument Devices | BK-GCS-PEDCO-120-PR-DT-0032 | BK-GCS-PEDCO-120-PR-DT-0032Process Data Sheets For Instrument Devices | 2022-04-20 | 2022-05-25
Process Flow Diagram (PFD) | BK-GCS-PEDCO-120-PR-PF-0001 | BK-GCS-PEDCO-120-PR-PF-0001Process Flow Diagram (PFD) | 2021-08-14 | 2022-05-25
Utility Flow Diagrams (UFD) | BK-GCS-PEDCO-120-PR-UF-0001 | BK-GCS-PEDCO-120-PR-UF-0001Utility Flow Diagrams (UFD) | 2021-10-18 | 2022-05-25
Symbol & Legend For PFD and P&ID | BK-GCS-PEDCO-120-PR-PI-0001 | BK-GCS-PEDCO-120-PR-PI-0001Symbol & Legend For PFD and P&ID | 2021-10-04 | 2022-05-25
P&ID - Gas Compression Inlet Gas Pipeline (Binak) | BK-GCS-PEDCO-120-PR-PI-0002 | BK-GCS-PEDCO-120-PR-PI-0002P&ID - Gas Compression Inlet Gas Pipeline (Binak) | 2021-09-26 | 2022-05-25
P&ID - Gas Compression Inlet Gas Pipeline (Golkhari) | BK-GCS-PEDCO-120-PR-PI-0003 | BK-GCS-PEDCO-120-PR-PI-0003P&ID - Gas Compression Inlet Gas Pipeline (Golkhari) | 2021-09-26 | 2022-05-25
P&ID - Slug Catcher System | BK-GCS-PEDCO-120-PR-PI-0004 | BK-GCS-PEDCO-120-PR-PI-0004P&ID - Slug Catcher System | 2021-09-26 | 2022-05-25
P&ID - Gas Compression Inlet Knock Out Drum | BK-GCS-PEDCO-120-PR-PI-0005 | BK-GCS-PEDCO-120-PR-PI-0005P&ID - Gas Compression Inlet Knock Out Drum | 2021-09-26 | 2022-05-25
P&ID - 1st Stage Gas Compression Suction Drums | BK-GCS-PEDCO-120-PR-PI-0006 | BK-GCS-PEDCO-120-PR-PI-0006P&ID - 1st Stage Gas Compression Suction Drums | 2021-09-26 | 2022-05-25
P&ID - 1st Stage Gas Compression Compressors | BK-GCS-PEDCO-120-PR-PI-0007 | BK-GCS-PEDCO-120-PR-PI-0007P&ID - 1st Stage Gas Compression Compressors | 2021-09-26 | 2022-05-25
P&ID - 1st Stage Gas Compression Air Coolers | BK-GCS-PEDCO-120-PR-PI-0008 | BK-GCS-PEDCO-120-PR-PI-0008P&ID - 1st Stage Gas Compression Air Coolers | 2021-09-26 | 2022-05-25
P&ID - 2nd Stage Gas Compression Suction Drums | BK-GCS-PEDCO-120-PR-PI-0009 | BK-GCS-PEDCO-120-PR-PI-0009P&ID - 2nd Stage Gas Compression Suction Drums | 2021-09-26 | 2022-05-25
P&ID - 2nd Stage Gas Compression Compressors | BK-GCS-PEDCO-120-PR-PI-0010 | BK-GCS-PEDCO-120-PR-PI-0010P&ID - 2nd Stage Gas Compression Compressors | 2021-09-26 | 2022-05-25
P&ID - 2nd Stage Gas Compression Air Coolers | BK-GCS-PEDCO-120-PR-PI-0011 | BK-GCS-PEDCO-120-PR-PI-0011P&ID - 2nd Stage Gas Compression Air Coolers | 2021-09-26 | 2022-05-25
P&ID - 2nd Stage Gas Compression Discharge Drum | BK-GCS-PEDCO-120-PR-PI-0012 | BK-GCS-PEDCO-120-PR-PI-0012P&ID - 2nd Stage Gas Compression Discharge Drum | 2021-09-26 | 2022-05-25
P&ID - Gas Compression Dehydration Package | BK-GCS-PEDCO-120-PR-PI-0013 | BK-GCS-PEDCO-120-PR-PI-0013P&ID - Gas Compression Dehydration Package | 2021-09-26 | 2022-05-25
P&ID - Lean Glycol Storage Tank | BK-GCS-PEDCO-120-PR-PI-0014 | BK-GCS-PEDCO-120-PR-PI-0014P&ID - Lean Glycol Storage Tank | 2021-09-26 | 2022-05-25
P&ID - Instrument & Plant Air System | BK-GCS-PEDCO-120-PR-PI-0015 | BK-GCS-PEDCO-120-PR-PI-0015P&ID - Instrument & Plant Air System | 2021-10-18 | 2022-05-25
P&ID - Nitrogen Generation System | BK-GCS-PEDCO-120-PR-PI-0016 | BK-GCS-PEDCO-120-PR-PI-0016P&ID - Nitrogen Generation System | 2021-10-18 | 2022-05-25
P&ID - Close Drain System | BK-GCS-PEDCO-120-PR-PI-0017 | BK-GCS-PEDCO-120-PR-PI-0017P&ID - Close Drain System | 2021-10-18 | 2022-05-25
P&ID - Corrosion Inhibitor Package | BK-GCS-PEDCO-120-PR-PI-0018 | BK-GCS-PEDCO-120-PR-PI-0018P&ID - Corrosion Inhibitor Package | 2021-10-18 | 2022-05-25
P&ID - Methanol Injection Package | BK-GCS-PEDCO-120-PR-PI-0019 | BK-GCS-PEDCO-120-PR-PI-0019P&ID - Methanol Injection Package | 2021-10-18 | 2022-05-25
P&ID - LP Flare System | BK-GCS-PEDCO-120-PR-PI-0020 | BK-GCS-PEDCO-120-PR-PI-0020P&ID - LP Flare System | 2021-10-18 | 2022-05-25
P&ID - Oily Water Sewer | BK-GCS-PEDCO-120-PR-PI-0021 | BK-GCS-PEDCO-120-PR-PI-0021P&ID - Oily Water Sewer | 2021-10-18 | 2022-05-25
P&ID - Fuel Gas System | BK-GCS-PEDCO-120-PR-PI-0022 | BK-GCS-PEDCO-120-PR-PI-0022P&ID - Fuel Gas System | 2021-10-18 | 2022-05-25
P&ID - Diesel Oil System | BK-GCS-PEDCO-120-PR-PI-0023 | BK-GCS-PEDCO-120-PR-PI-0023P&ID - Diesel Oil System | 2021-10-18 | 2022-05-25
P&ID - Potable Water System | BK-GCS-PEDCO-120-PR-PI-0024 | BK-GCS-PEDCO-120-PR-PI-0024P&ID - Potable Water System | 2021-10-18 | 2022-05-25
P&ID - Glycol Sump Drum | BK-GCS-PEDCO-120-PR-PI-0025 | BK-GCS-PEDCO-120-PR-PI-0025P&ID - Glycol Sump Drum | 2021-09-26 | 2022-05-25
ESD Block Diagram | BK-GCS-PEDCO-120-PR-BD-0001 | BK-GCS-PEDCO-120-PR-BD-0001ESD Block Diagram |  | 2022-05-25
Cause & Effect Diagram | BK-GCS-PEDCO-120-PR-CE-0001 | BK-GCS-PEDCO-120-PR-CE-0001Cause & Effect Diagram |  | 2022-05-25
Chemical Injection Points Diagram | BK-GCS-PEDCO-120-PR-DG-0001 | BK-GCS-PEDCO-120-PR-DG-0001Chemical Injection Points Diagram |  | 2022-05-25
Process Main Equipment List | BK-GCS-PEDCO-120-PR-LI-0001 | BK-GCS-PEDCO-120-PR-LI-0001Process Main Equipment List | 2022-02-20 | 2022-05-25
Process Electrical Load List | BK-GCS-PEDCO-120-PR-LI-0002 | BK-GCS-PEDCO-120-PR-LI-0002Process Electrical Load List | 2022-01-19 | 2022-05-25
Tie in list | BK-GCS-PEDCO-120-PR-LI-0003 | BK-GCS-PEDCO-120-PR-LI-0003Tie in list | 2022-02-20 | 2022-05-25
Line List | BK-GCS-PEDCO-120-PR-LI-0004 | BK-GCS-PEDCO-120-PR-LI-0004Line List | 2022-04-30 | 2022-05-25
Chemical Consumption List | BK-GCS-PEDCO-120-PR-LI-0005 | BK-GCS-PEDCO-120-PR-LI-0005Chemical Consumption List | 2022-03-09 | 2022-05-25
Utility Consumption List | BK-GCS-PEDCO-120-PR-LI-0006 | BK-GCS-PEDCO-120-PR-LI-0006Utility Consumption List | 2021-12-28 | 2022-05-25
Emission and Effluent Summary | BK-GCS-PEDCO-120-PR-LI-0007 | BK-GCS-PEDCO-120-PR-LI-0007Emission and Effluent Summary |  | 2022-05-25
Relief Load Summery | BK-GCS-PEDCO-120-PR-LI-0008 | BK-GCS-PEDCO-120-PR-LI-0008Relief Load Summery | 2022-01-26 | 2022-05-25
Flare Network Study Report | BK-GCS-PEDCO-120-PR-RT-0001 | BK-GCS-PEDCO-120-PR-RT-0001Flare Network Study Report | 2022-01-05 | 2022-05-25
Flare Radiation & Dispersion Study Report | BK-GCS-PEDCO-120-PR-RT-0002 | BK-GCS-PEDCO-120-PR-RT-0002Flare Radiation & Dispersion Study Report | 2022-01-05 | 2022-05-25
Process Simulation Report | BK-GCS-PEDCO-120-PR-RT-0003 | BK-GCS-PEDCO-120-PR-RT-0003Process Simulation Report | 2021-10-17 | 2022-05-25
Specification For Air Cooled Heat Exchangers | BK-GCS-PEDCO-120-ME-SP-0001 | BK-GCS-PEDCO-120-ME-SP-0001Specification For Air Cooled Heat Exchangers | 2021-08-14 | 2022-05-25
Specification For Large Welded Low Pressure Storage Tanks | BK-GCS-PEDCO-120-ME-SP-0010 | BK-GCS-PEDCO-120-ME-SP-0010Specification For Large Welded Low Pressure Storage Tanks | 2021-08-24 | 2022-01-31
Specification For Reciprocating Compressor (API 618) | BK-GCS-PEDCO-120-ME-SP-0002 | BK-GCS-PEDCO-120-ME-SP-0002Specification For Reciprocating Compressor (API 618) | 2021-08-14 | 2022-03-07
Specification For Centrifugal Pumps For Process Services (API610) | BK-GCS-PEDCO-120-ME-SP-0003 | BK-GCS-PEDCO-120-ME-SP-0003Specification For Centrifugal Pumps For Process Services (API610) | 2021-08-22 | 2022-04-19
Specification For Centrifugal Pumps For General Services | BK-GCS-PEDCO-120-ME-SP-0004 | BK-GCS-PEDCO-120-ME-SP-0004Specification For Centrifugal Pumps For General Services | 2021-08-14 | 2022-05-25
Specification For Fire Water Pumps | BK-GCS-PEDCO-120-ME-SP-0005 | BK-GCS-PEDCO-120-ME-SP-0005Specification For Fire Water Pumps | 2021-08-22 | 2022-04-19
Specification For Overhead Travelling Cranes | BK-GCS-PEDCO-120-ME-SP-0009 | BK-GCS-PEDCO-120-ME-SP-0009Specification For Overhead Travelling Cranes | 2021-08-14 | 2022-05-25
Specification for Control Volume Pump (API 675) | BK-GCS-PEDCO-120-ME-SP-0011 | BK-GCS-PEDCO-120-ME-SP-0011Specification for Control Volume Pump (API 675) | 2021-08-24 | 2022-04-19
Specification For Diesel Engines | BK-GCS-PEDCO-120-ME-SP-0012 | BK-GCS-PEDCO-120-ME-SP-0012Specification For Diesel Engines | 2021-08-24 | 2022-03-06
Specification For Air Compressor Package | BK-GCS-PEDCO-120-ME-SP-0006 | BK-GCS-PEDCO-120-ME-SP-0006Specification For Air Compressor Package | 2021-08-14 | 2022-03-07
Specification For Air Dryer Package | BK-GCS-PEDCO-120-ME-SP-0007 | BK-GCS-PEDCO-120-ME-SP-0007Specification For Air Dryer Package | 2021-08-14 | 2022-05-25
Specification For Chemical Injection Package | BK-GCS-PEDCO-120-ME-SP-0008 | BK-GCS-PEDCO-120-ME-SP-0008Specification For Chemical Injection Package | 2021-08-22 | 2022-05-25
Specification For Flare Package | BK-GCS-PEDCO-120-ME-SP-0013 | BK-GCS-PEDCO-120-ME-SP-0013Specification For Flare Package | 2021-08-24 | 2022-03-09
Specification For Nitrogen Package | BK-GCS-PEDCO-120-ME-SP-0014 | BK-GCS-PEDCO-120-ME-SP-0014Specification For Nitrogen Package | 2021-08-24 | 2022-05-25
Mechanical Data Sheets For Inlet Gas K.O. Drum | BK-GCS-PEDCO-120-ME-DT-0001 | BK-GCS-PEDCO-120-ME-DT-0001Mechanical Data Sheets For Inlet Gas K.O. Drum | 2021-12-07 | 2022-05-25
Mechanical Data Sheets For 1st Stage G.C. Suction Drums | BK-GCS-PEDCO-120-ME-DT-0002 | BK-GCS-PEDCO-120-ME-DT-0002Mechanical Data Sheets For 1st Stage G.C. Suction Drums | 2021-12-13 | 2022-05-25
Mechanical Data Sheets For 1st Stage Gas Air Coolers | BK-GCS-PEDCO-120-ME-DT-0003 | BK-GCS-PEDCO-120-ME-DT-0003Mechanical Data Sheets For 1st Stage Gas Air Coolers | 2021-12-29 | 2022-05-25
Mechanical Data Sheets For 2nd Stage G.C. Suction Drums | BK-GCS-PEDCO-120-ME-DT-0004 | BK-GCS-PEDCO-120-ME-DT-0004Mechanical Data Sheets For 2nd Stage G.C. Suction Drums | 2021-12-13 | 2022-05-25
Mechanical Data Sheets For 2nd Stage Gas Air Coolers | BK-GCS-PEDCO-120-ME-DT-0005 | BK-GCS-PEDCO-120-ME-DT-0005Mechanical Data Sheets For 2nd Stage Gas Air Coolers | 2021-12-29 | 2022-05-25
Mechanical Data Sheets For Discharge Gas K.O. Drum | BK-GCS-PEDCO-120-ME-DT-0006 | BK-GCS-PEDCO-120-ME-DT-0006Mechanical Data Sheets For Discharge Gas K.O. Drum | 2021-12-27 | 2022-05-25
Mechanical Data Sheets For Diesel Oil Drum | BK-GCS-PEDCO-120-ME-DT-0007 | BK-GCS-PEDCO-120-ME-DT-0007Mechanical Data Sheets For Diesel Oil Drum | 2021-12-13 | 2022-05-25
Mechanical Data Sheets For Instrument Air Receiver | BK-GCS-PEDCO-120-ME-DT-0008 | BK-GCS-PEDCO-120-ME-DT-0008Mechanical Data Sheets For Instrument Air Receiver | 2021-12-07 | 2022-05-25
Mechanical Data Sheets For Nitrogen Receiver | BK-GCS-PEDCO-120-ME-DT-0009 | BK-GCS-PEDCO-120-ME-DT-0009Mechanical Data Sheets For Nitrogen Receiver | 2021-11-27 | 2022-05-25
Mechanical Data Sheets For Close Drain Drum | BK-GCS-PEDCO-120-ME-DT-0010 | BK-GCS-PEDCO-120-ME-DT-0010Mechanical Data Sheets For Close Drain Drum | 2021-12-13 | 2022-05-25
Mechanical Data Sheets For Elevated Potable Water Tank | BK-GCS-PEDCO-120-ME-DT-0011 | BK-GCS-PEDCO-120-ME-DT-0011Mechanical Data Sheets For Elevated Potable Water Tank | 2021-11-27 | 2022-05-25
Mechanical Data Sheets For Flare K.O. Drum | BK-GCS-PEDCO-120-ME-DT-0012 | BK-GCS-PEDCO-120-ME-DT-0012Mechanical Data Sheets For Flare K.O. Drum | 2022-01-03 | 2022-05-25
Mechanical Data Sheets For Fuel Gas K.O. Drum | BK-GCS-PEDCO-120-ME-DT-0013 | BK-GCS-PEDCO-120-ME-DT-0013Mechanical Data Sheets For Fuel Gas K.O. Drum | 2021-12-13 | 2022-05-25
Mechanical Data Sheets For Slug Catcher | BK-GCS-PEDCO-120-ME-DT-0014 | BK-GCS-PEDCO-120-ME-DT-0014Mechanical Data Sheets For Slug Catcher | 2021-12-28 | 2022-05-25
Mechanical Data Sheets For Degassing Vessel | BK-GCS-PEDCO-120-ME-DT-0015 | BK-GCS-PEDCO-120-ME-DT-0015Mechanical Data Sheets For Degassing Vessel | 2022-03-06 | 2022-05-25
Mechanical Data Sheets For Lean Glycol Storage Tank | BK-GCS-PEDCO-120-ME-DT-0016 | BK-GCS-PEDCO-120-ME-DT-0016Mechanical Data Sheets For Lean Glycol Storage Tank | 2021-11-28 | 2022-05-25
Mechanical Data Sheets For Fire Water Storage Tank | BK-GCS-PEDCO-120-ME-DT-0017 | BK-GCS-PEDCO-120-ME-DT-0017Mechanical Data Sheets For Fire Water Storage Tank |  | 2022-05-25
Mechanical Data Sheets For Slug Storage Tank | BK-GCS-PEDCO-120-ME-DT-0018 | BK-GCS-PEDCO-120-ME-DT-0018Mechanical Data Sheets For Slug Storage Tank | 2021-12-14 | 2022-05-25
Mechanical Data Sheets For Slug Pumps | BK-GCS-PEDCO-120-ME-DT-0019 | BK-GCS-PEDCO-120-ME-DT-0019Mechanical Data Sheets For Slug Pumps | 2021-12-07 | 2022-04-12
Mechanical Data Sheets For Glycol Transfer Pumps | BK-GCS-PEDCO-120-ME-DT-0020 | BK-GCS-PEDCO-120-ME-DT-0020Mechanical Data Sheets For Glycol Transfer Pumps | 2021-11-27 | 2022-04-12
Mechanical Data Sheets For Glycol Manual Pump | BK-GCS-PEDCO-120-ME-DT-0021 | BK-GCS-PEDCO-120-ME-DT-0021Mechanical Data Sheets For Glycol Manual Pump | 2021-11-27 | 2022-04-12
Mechanical Data Sheets For Closed Drain Pumps | BK-GCS-PEDCO-120-ME-DT-0022 | BK-GCS-PEDCO-120-ME-DT-0022Mechanical Data Sheets For Closed Drain Pumps | 2021-11-27 | 2022-05-25
Mechanical Data Sheets For Sump Pumps | BK-GCS-PEDCO-120-ME-DT-0023 | BK-GCS-PEDCO-120-ME-DT-0023Mechanical Data Sheets For Sump Pumps | 2021-12-07 | 2022-03-27
Mechanical Data Sheets For Flare KO Drum Pumps | BK-GCS-PEDCO-120-ME-DT-0024 | BK-GCS-PEDCO-120-ME-DT-0024Mechanical Data Sheets For Flare KO Drum Pumps | 2021-11-27 | 2022-05-25
Mechanical Data Sheets For Potable Water Pump | BK-GCS-PEDCO-120-ME-DT-0025 | BK-GCS-PEDCO-120-ME-DT-0025Mechanical Data Sheets For Potable Water Pump | 2021-12-07 | 2022-03-26
Mechanical Data Sheets For Diesel Pump | BK-GCS-PEDCO-120-ME-DT-0026 | BK-GCS-PEDCO-120-ME-DT-0026Mechanical Data Sheets For Diesel Pump | 2021-11-27 | 2022-04-12
Mechanical Data Sheets For Overhead Traveling Cranes | BK-GCS-PEDCO-120-ME-DT-0027 | BK-GCS-PEDCO-120-ME-DT-0027Mechanical Data Sheets For Overhead Traveling Cranes | 2022-02-13 | 2022-05-25
Mechanical Data Sheets For Fire Water Jockey Pumps | BK-GCS-PEDCO-120-ME-DT-0028 | BK-GCS-PEDCO-120-ME-DT-0028Mechanical Data Sheets For Fire Water Jockey Pumps | 2022-02-21 | 2022-05-25
Mechanical Data Sheets For Fire Water Main Pumps - Elect. Motor Driven | BK-GCS-PEDCO-120-ME-DT-0029 | BK-GCS-PEDCO-120-ME-DT-0029Mechanical Data Sheets For Fire Water Main Pumps - Elect. Motor Driven | 2022-02-21 | 2022-05-25
Mechanical Data Sheets For Fire Water Main Pumps - Diesel Engine Driven | BK-GCS-PEDCO-120-ME-DT-0030 | BK-GCS-PEDCO-120-ME-DT-0030Mechanical Data Sheets For Fire Water Main Pumps - Diesel Engine Driven | 2022-02-16 | 2022-05-25
Mechanical Data Sheets For Gas Compressors Packages | BK-GCS-PEDCO-120-ME-DT-0031 | BK-GCS-PEDCO-120-ME-DT-0031Mechanical Data Sheets For Gas Compressors Packages | 2021-09-12 | 2022-05-08
Mechanical Data Sheets For Glycol Sump Pumps | BK-GCS-PEDCO-120-ME-DT-0034 | BK-GCS-PEDCO-120-ME-DT-0034Mechanical Data Sheets For Glycol Sump Pumps | 2021-12-08 | 2022-05-25
Mechanical Data Sheets For Glycol Drain Pump | BK-GCS-PEDCO-120-ME-DT-0035 | BK-GCS-PEDCO-120-ME-DT-0035Mechanical Data Sheets For Glycol Drain Pump | 2021-12-08 | 2022-05-25
Mechanical Data Sheets For Glycol Sump Drum | BK-GCS-PEDCO-120-ME-DT-0036 | BK-GCS-PEDCO-120-ME-DT-0036Mechanical Data Sheets For Glycol Sump Drum | 2022-01-05 | 2022-05-25
HVAC Calculation Note For Control Building | BK-GCS-PEDCO-120-HV-CN-0001 | BK-GCS-PEDCO-120-HV-CN-0001HVAC Calculation Note For Control Building | 2022-03-30 | 2022-05-25
HVAC Calculation Note For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-CN-0002 | BK-GCS-PEDCO-120-HV-CN-0002HVAC Calculation Note For Extension of Existing Elect. Building |  | 2022-05-25
Data Sheets For Main HVAC Equipment of Control Building | BK-GCS-PEDCO-120-HV-DT-0001 | BK-GCS-PEDCO-120-HV-DT-0001Data Sheets For Main HVAC Equipment of Control Building |  | 2022-05-25
Data Sheets For Main HVAC Equipment of Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-DT-0002 | BK-GCS-PEDCO-120-HV-DT-0002Data Sheets For Main HVAC Equipment of Extension of Existing Elect. Building |  | 2022-05-25
Plumbing & Sewage Piping Layout For Control Building | BK-GCS-PEDCO-120-HV-PY-0001 | BK-GCS-PEDCO-120-HV-PY-0001Plumbing & Sewage Piping Layout For Control Building |  | 2022-05-25
HVAC Flow Diagram For Control Building | BK-GCS-PEDCO-120-HV-DG-0001 | BK-GCS-PEDCO-120-HV-DG-0001HVAC Flow Diagram For Control Building |  | 2022-05-25
HVAC Room Layout & Section For Control Building | BK-GCS-PEDCO-120-HV-PY-0002 | BK-GCS-PEDCO-120-HV-PY-0002HVAC Room Layout & Section For Control Building |  | 2022-05-25
HVAC System Duct Plan For Control Building | BK-GCS-PEDCO-120-HV-PY-0003 | BK-GCS-PEDCO-120-HV-PY-0003HVAC System Duct Plan For Control Building |  | 2022-05-25
HVAC System Roof Layout For Control Building | BK-GCS-PEDCO-120-HV-PY-0004 | BK-GCS-PEDCO-120-HV-PY-0004HVAC System Roof Layout For Control Building |  | 2022-05-25
HVAC I&C Diagram For Control Building | BK-GCS-PEDCO-120-HV-DG-0002 | BK-GCS-PEDCO-120-HV-DG-0002HVAC I&C Diagram For Control Building |  | 2022-05-25
Plumbing & Sewage Piping Layout For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-PY-0005 | BK-GCS-PEDCO-120-HV-PY-0005Plumbing & Sewage Piping Layout For Extension of Existing Elect. Building |  | 2022-05-25
HVAC Flow Diagram For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-DG-0003 | BK-GCS-PEDCO-120-HV-DG-0003HVAC Flow Diagram For Extension of Existing Elect. Building |  | 2022-05-25
HVAC System Layout & Section For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-PY-0006 | BK-GCS-PEDCO-120-HV-PY-0006HVAC System Layout & Section For Extension of Existing Elect. Building |  | 2022-05-25
HVAC System Duct Plan For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-PY-0007 | BK-GCS-PEDCO-120-HV-PY-0007HVAC System Duct Plan For Extension of Existing Elect. Building |  | 2022-05-25
HVAC System Roof Layout For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-PY-0008 | BK-GCS-PEDCO-120-HV-PY-0008HVAC System Roof Layout For Extension of Existing Elect. Building |  | 2022-05-25
HVAC I&C Diagram For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-DG-0004 | BK-GCS-PEDCO-120-HV-DG-0004HVAC I&C Diagram For Extension of Existing Elect. Building |  | 2022-05-25
MTO For HVAC & Plumbing For Control Building | BK-GCS-PEDCO-120-HV-MT-0001 | BK-GCS-PEDCO-120-HV-MT-0001MTO For HVAC & Plumbing For Control Building |  | 2022-05-25
MTO For HVAC & Plumbing For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-MT-0002 | BK-GCS-PEDCO-120-HV-MT-0002MTO For HVAC & Plumbing For Extension of Existing Elect. Building |  | 2022-05-25
Piping Material Specification | BK-GCS-PEDCO-120-PI-SP-0001 | BK-GCS-PEDCO-120-PI-SP-0001Piping Material Specification | 2021-12-06 | 2022-05-25
Data Sheets For Strainers | BK-GCS-PEDCO-120-PI-DT-0001 | BK-GCS-PEDCO-120-PI-DT-0001Data Sheets For Strainers |  | 2022-05-25
Data Sheets For Manual valves | BK-GCS-PEDCO-120-PI-DT-0002 | BK-GCS-PEDCO-120-PI-DT-0002Data Sheets For Manual valves |  | 2022-05-25
Data Sheets and MTO For Piping Special Items | BK-GCS-PEDCO-120-PI-DT-0003 | BK-GCS-PEDCO-120-PI-DT-0003Data Sheets and MTO For Piping Special Items |  | 2022-05-25
Data Sheets For Special Pipe Supports | BK-GCS-PEDCO-120-PI-DT-0004 | BK-GCS-PEDCO-120-PI-DT-0004Data Sheets For Special Pipe Supports |  | 2022-05-25
Data Sheets For Piping Insulation Joints | BK-GCS-PEDCO-120-PI-DT-0005 | BK-GCS-PEDCO-120-PI-DT-0005Data Sheets For Piping Insulation Joints |  | 2022-05-25
Data Sheets For Expansion Joints | BK-GCS-PEDCO-120-PI-DT-0006 | BK-GCS-PEDCO-120-PI-DT-0006Data Sheets For Expansion Joints |  | 2022-05-25
Unit Plot Plan Drawing | BK-GCS-PEDCO-120-PI-PY-0001 | BK-GCS-PEDCO-120-PI-PY-0001Unit Plot Plan Drawing | 2021-09-12 | 2022-05-25
Standard Pipe Support Drawings | BK-GCS-PEDCO-120-PI-DW-0001 | BK-GCS-PEDCO-120-PI-DW-0001Standard Pipe Support Drawings |  | 2022-05-25
Piping Assembly Drawing | BK-GCS-PEDCO-120-PI-DW-0002 | BK-GCS-PEDCO-120-PI-DW-0002Piping Assembly Drawing |  | 2022-05-25
Piping Key Plan | BK-GCS-PEDCO-120-PI-DW-0003 | BK-GCS-PEDCO-120-PI-DW-0003Piping Key Plan |  | 2022-05-25
A/G Piping Plan | BK-GCS-PEDCO-120-PI-DW-0004 | BK-GCS-PEDCO-120-PI-DW-0004A/G Piping Plan |  | 2022-05-25
U/G Piping Plan | BK-GCS-PEDCO-120-PI-DW-0005 | BK-GCS-PEDCO-120-PI-DW-0005U/G Piping Plan |  | 2022-05-25
A/G Piping Isometric | BK-GCS-PEDCO-120-PI-DW-0006 | BK-GCS-PEDCO-120-PI-DW-0006A/G Piping Isometric |  | 2022-05-25
U/G Piping Isometric | BK-GCS-PEDCO-120-PI-DW-0007 | BK-GCS-PEDCO-120-PI-DW-0007U/G Piping Isometric |  | 2022-05-25
Overall Plot Plan Drawing | BK-GCS-PEDCO-120-PI-DW-0008 | BK-GCS-PEDCO-120-PI-DW-0008Overall Plot Plan Drawing |  | 2022-05-25
Special Pipe Support Drawings | BK-GCS-PEDCO-120-PI-DW-0009 | BK-GCS-PEDCO-120-PI-DW-0009Special Pipe Support Drawings |  | 2022-05-25
Material flow Diagram | BK-GCS-PEDCO-120-PI-DG-0001 | BK-GCS-PEDCO-120-PI-DG-0001Material flow Diagram | 2022-05-11 | 2022-05-25
Piping Hydrostatic Test Diagram - GCS | BK-GCS-PEDCO-120-PI-DW-0010 | BK-GCS-PEDCO-120-PI-DW-0010Piping Hydrostatic Test Diagram - GCS |  | 2022-05-25
Critical Line List | BK-GCS-PEDCO-120-PI-LI-0001 | BK-GCS-PEDCO-120-PI-LI-0001Critical Line List |  | 2022-05-25
Pipe Support List | BK-GCS-PEDCO-120-PI-LI-0002 | BK-GCS-PEDCO-120-PI-LI-0002Pipe Support List |  | 2022-05-25
Piping Tie-In Schedule List | BK-GCS-PEDCO-120-PI-LI-0003 | BK-GCS-PEDCO-120-PI-LI-0003Piping Tie-In Schedule List |  | 2022-05-25
Piping Corrosion Study & Material Selection Report | BK-GCS-PEDCO-120-PI-RT-0001 | BK-GCS-PEDCO-120-PI-RT-0001Piping Corrosion Study & Material Selection Report | 2021-12-06 | 2022-05-25
Stress Analysis Calculations Report | BK-GCS-PEDCO-120-PI-RT-0002 | BK-GCS-PEDCO-120-PI-RT-0002Stress Analysis Calculations Report |  | 2022-05-25
PDMS Model Review Report (30%) | BK-GCS-PEDCO-120-PI-RT-0003 | BK-GCS-PEDCO-120-PI-RT-0003PDMS Model Review Report (30%) | 2022-03-26 | 2022-05-25
PDMS Model Review Report (60%) | BK-GCS-PEDCO-120-PI-RT-0004 | BK-GCS-PEDCO-120-PI-RT-0004PDMS Model Review Report (60%) |  | 2022-05-25
PDMS Model Review Report (90%) | BK-GCS-PEDCO-120-PI-RT-0005 | BK-GCS-PEDCO-120-PI-RT-0005PDMS Model Review Report (90%) |  | 2022-05-25
Wall Thickness Calculation Report | BK-GCS-PEDCO-120-PI-RT-0006 | BK-GCS-PEDCO-120-PI-RT-0006Wall Thickness Calculation Report | 2021-12-06 | 2022-05-25
MTO For Pipes | BK-GCS-PEDCO-120-PI-MT-0001 | BK-GCS-PEDCO-120-PI-MT-0001MTO For Pipes |  | 2022-05-25
MTO For Fittings | BK-GCS-PEDCO-120-PI-MT-0002 | BK-GCS-PEDCO-120-PI-MT-0002MTO For Fittings |  | 2022-05-25
MTO For Flanges | BK-GCS-PEDCO-120-PI-MT-0003 | BK-GCS-PEDCO-120-PI-MT-0003MTO For Flanges |  | 2022-05-25
MTO For Manual Valves | BK-GCS-PEDCO-120-PI-MT-0004 | BK-GCS-PEDCO-120-PI-MT-0004MTO For Manual Valves |  | 2022-05-25
MTO For Gaskets | BK-GCS-PEDCO-120-PI-MT-0005 | BK-GCS-PEDCO-120-PI-MT-0005MTO For Gaskets |  | 2022-05-25
MTO For Bolt & Nuts | BK-GCS-PEDCO-120-PI-MT-0006 | BK-GCS-PEDCO-120-PI-MT-0006MTO For Bolt & Nuts |  | 2022-05-25
MTO For Insulation | BK-GCS-PEDCO-120-PI-MT-0008 | BK-GCS-PEDCO-120-PI-MT-0008MTO For Insulation |  | 2022-05-25
MTO For Painting | BK-GCS-PEDCO-120-PI-MT-0009 | BK-GCS-PEDCO-120-PI-MT-0009MTO For Painting |  | 2022-05-25
MTO For Coating of Underground Piping | BK-GCS-PEDCO-120-PI-MT-0010 | BK-GCS-PEDCO-120-PI-MT-0010MTO For Coating of Underground Piping |  | 2022-05-25
Instrument & Control System Basis of Design | BK-GCS-PEDCO-120-IN-DB-0001 | BK-GCS-PEDCO-120-IN-DB-0001Instrument & Control System Basis of Design | 2021-08-22 | 2022-05-25
Fire & Gas Detection Design Criteria | BK-GCS-PEDCO-120-IN-DC-0001 | BK-GCS-PEDCO-120-IN-DC-0001Fire & Gas Detection Design Criteria | 2021-08-30 | 2022-05-25
Instrument & Control System Design Criteria | BK-GCS-PEDCO-120-IN-DC-0002 | BK-GCS-PEDCO-120-IN-DC-0002Instrument & Control System Design Criteria | 2022-01-03 | 2022-05-25
Data Sheets For Pressure & Diff. Pressure Gauge | BK-GCS-PEDCO-120-IN-DT-0001 | BK-GCS-PEDCO-120-IN-DT-0001Data Sheets For Pressure & Diff. Pressure Gauge | 2022-03-27 | 2022-05-25
Data Sheets For Temperature Gauge | BK-GCS-PEDCO-120-IN-DT-0002 | BK-GCS-PEDCO-120-IN-DT-0002Data Sheets For Temperature Gauge | 2022-03-27 | 2022-05-25
Data Sheets For Level Gauges | BK-GCS-PEDCO-120-IN-DT-0003 | BK-GCS-PEDCO-120-IN-DT-0003Data Sheets For Level Gauges | 2022-04-05 | 2022-05-25
Data Sheets For Pressure/Diff. Pressure Transmitter | BK-GCS-PEDCO-120-IN-DT-0004 | BK-GCS-PEDCO-120-IN-DT-0004Data Sheets For Pressure/Diff. Pressure Transmitter | 2022-04-10 | 2022-05-25
Data Sheets For Temperature Transmitter/Switch | BK-GCS-PEDCO-120-IN-DT-0005 | BK-GCS-PEDCO-120-IN-DT-0005Data Sheets For Temperature Transmitter/Switch | 2022-03-27 | 2022-05-25
Data Sheets For Displacer Level Transmitter | BK-GCS-PEDCO-120-IN-DT-0006 | BK-GCS-PEDCO-120-IN-DT-0006Data Sheets For Displacer Level Transmitter | 2022-04-05 | 2022-05-25
Data Sheets For Pressure/ Differential Pressure Switch | BK-GCS-PEDCO-120-IN-DT-0007 | BK-GCS-PEDCO-120-IN-DT-0007Data Sheets For Pressure/ Differential Pressure Switch |  | 2022-05-25
Data Sheets For Level Switch | BK-GCS-PEDCO-120-IN-DT-0008 | BK-GCS-PEDCO-120-IN-DT-0008Data Sheets For Level Switch | 2022-04-10 | 2022-05-25
Data Sheets For Pressure & Safety Relief Valves | BK-GCS-PEDCO-120-IN-DT-0009 | BK-GCS-PEDCO-120-IN-DT-0009Data Sheets For Pressure & Safety Relief Valves | 2022-05-17 | 2022-05-25
Data Sheets For ON/OFF & Shutdown Valves | BK-GCS-PEDCO-120-IN-DT-0010 | BK-GCS-PEDCO-120-IN-DT-0010Data Sheets For ON/OFF & Shutdown Valves | 2022-05-08 | 2022-05-25
Data Sheets For Control/Regulator Valves | BK-GCS-PEDCO-120-IN-DT-0011 | BK-GCS-PEDCO-120-IN-DT-0011Data Sheets For Control/Regulator Valves |  | 2022-05-25
Data Sheets For Diff. Pressure Flow Transmitter | BK-GCS-PEDCO-120-IN-DT-0012 | BK-GCS-PEDCO-120-IN-DT-0012Data Sheets For Diff. Pressure Flow Transmitter | 2022-04-05 | 2022-05-25
Data Sheets For Orifice Plate/Restriction Orifice | BK-GCS-PEDCO-120-IN-DT-0013 | BK-GCS-PEDCO-120-IN-DT-0013Data Sheets For Orifice Plate/Restriction Orifice |  | 2022-05-25
Data Sheets For Corrosion Coupon/ Probe | BK-GCS-PEDCO-120-IN-DT-0014 | BK-GCS-PEDCO-120-IN-DT-0014Data Sheets For Corrosion Coupon/ Probe | 2022-03-27 | 2022-05-25
Data Sheets For F&G Detectors & Equipment | BK-GCS-PEDCO-120-IN-DT-0016 | BK-GCS-PEDCO-120-IN-DT-0016Data Sheets For F&G Detectors & Equipment | 2022-05-09 | 2022-05-25
Data Sheets For ESD Console/F&G Matrix Panel | BK-GCS-PEDCO-120-IN-DT-0017 | BK-GCS-PEDCO-120-IN-DT-0017Data Sheets For ESD Console/F&G Matrix Panel | 2022-04-30 | 2022-05-25
Data Sheets For Rotameter | BK-GCS-PEDCO-120-IN-DT-0018 | BK-GCS-PEDCO-120-IN-DT-0018Data Sheets For Rotameter | 2022-04-05 | 2022-05-25
Data Sheets For Diff. Pressure Type Level Transmitter | BK-GCS-PEDCO-120-IN-DT-0019 | BK-GCS-PEDCO-120-IN-DT-0019Data Sheets For Diff. Pressure Type Level Transmitter | 2022-04-05 | 2022-05-25
Data Sheets For CCTV | BK-GCS-PEDCO-120-IN-DT-0020 | BK-GCS-PEDCO-120-IN-DT-0020Data Sheets For CCTV | 2021-10-13 | 2022-05-25
Data Sheets For IRP Panel | BK-GCS-PEDCO-120-IN-DT-0021 | BK-GCS-PEDCO-120-IN-DT-0021Data Sheets For IRP Panel |  | 2022-05-25
Typical Instrument Installation Drawing | BK-GCS-PEDCO-120-IN-DW-0001 | BK-GCS-PEDCO-120-IN-DW-0001Typical Instrument Installation Drawing | 2022-03-09 | 2022-03-09
Control/ESD/F&G System Block Diagram Configuration | BK-GCS-PEDCO-120-IN-BD-0001 | BK-GCS-PEDCO-120-IN-BD-0001Control/ESD/F&G System Block Diagram Configuration | 2021-08-30 | 2022-05-25
Instrument Earthing Typical Diagram | BK-GCS-PEDCO-120-IN-DG-0001 | BK-GCS-PEDCO-120-IN-DG-0001Instrument Earthing Typical Diagram | 2021-12-29 | 2022-04-17
Instrument Hook-up Diagram | BK-GCS-PEDCO-120-IN-DG-0002 | BK-GCS-PEDCO-120-IN-DG-0002Instrument Hook-up Diagram | 2022-03-02 | 2022-05-25
ESD Level Hierarchy | BK-GCS-PEDCO-120-IN-DG-0003 | BK-GCS-PEDCO-120-IN-DG-0003ESD Level Hierarchy |  | 2022-05-25
ESD System Loop Diagram | BK-GCS-PEDCO-120-IN-DG-0004 | BK-GCS-PEDCO-120-IN-DG-0004ESD System Loop Diagram |  | 2022-05-25
Control System Loop Diagram | BK-GCS-PEDCO-120-IN-DG-0005 | BK-GCS-PEDCO-120-IN-DG-0005Control System Loop Diagram |  | 2022-05-25
F&G System Loop Diagram | BK-GCS-PEDCO-120-IN-DG-0006 | BK-GCS-PEDCO-120-IN-DG-0006F&G System Loop Diagram |  | 2022-05-25
Instrument Air Piping and Air Header Diagram | BK-GCS-PEDCO-120-IN-DG-0007 | BK-GCS-PEDCO-120-IN-DG-0007Instrument Air Piping and Air Header Diagram |  | 2022-05-25
Instrument & F&G Junction Box Termination Diagram | BK-GCS-PEDCO-120-IN-DG-0008 | BK-GCS-PEDCO-120-IN-DG-0008Instrument & F&G Junction Box Termination Diagram | 2022-02-13 | 2022-05-25
F&G Cause and Effect Diagram For Process Area | BK-GCS-PEDCO-120-IN-DG-0009 | BK-GCS-PEDCO-120-IN-DG-0009F&G Cause and Effect Diagram For Process Area |  | 2022-05-25
F&G Cause and Effect Diagram For Buildings | BK-GCS-PEDCO-120-IN-DG-0010 | BK-GCS-PEDCO-120-IN-DG-0010F&G Cause and Effect Diagram For Buildings |  | 2022-05-25
Control System Logic Diagram | BK-GCS-PEDCO-120-IN-LD-0001 | BK-GCS-PEDCO-120-IN-LD-0001Control System Logic Diagram |  | 2022-05-25
ESD Logic Diagram | BK-GCS-PEDCO-120-IN-LD-0002 | BK-GCS-PEDCO-120-IN-LD-0002ESD Logic Diagram |  | 2022-05-25
Control Room Layout & Arrangement Drawing | BK-GCS-PEDCO-120-IN-PY-0001 | BK-GCS-PEDCO-120-IN-PY-0001Control Room Layout & Arrangement Drawing | 2022-02-02 | 2022-05-25
Control Room Cable Route Layout | BK-GCS-PEDCO-120-IN-PY-0002 | BK-GCS-PEDCO-120-IN-PY-0002Control Room Cable Route Layout | 2022-05-23 | 2022-05-25
Instrument Location Layout | BK-GCS-PEDCO-120-IN-PY-0003 | BK-GCS-PEDCO-120-IN-PY-0003Instrument Location Layout |  | 2022-05-25
Instrument/F&G Cable Trench/Route Layout Drawing | BK-GCS-PEDCO-120-IN-PY-0004 | BK-GCS-PEDCO-120-IN-PY-0004Instrument/F&G Cable Trench/Route Layout Drawing | 2022-01-25 | 2022-05-25
F&G Location Layout For Process Area | BK-GCS-PEDCO-120-IN-PY-0005 | BK-GCS-PEDCO-120-IN-PY-0005F&G Location Layout For Process Area | 2022-02-07 | 2022-05-25
F&G Location Layout For Buildings | BK-GCS-PEDCO-120-IN-PY-0006 | BK-GCS-PEDCO-120-IN-PY-0006F&G Location Layout For Buildings | 2022-04-18 | 2022-05-25
Block Diagram For CCTV | BK-GCS-PEDCO-120-IN-BD-0002 | BK-GCS-PEDCO-120-IN-BD-0002Block Diagram For CCTV |  | 2022-05-25
Block Diagram For CCTV in Binak DU | BK-GCS-PEDCO-120-IN-BD-0003 | BK-GCS-PEDCO-120-IN-BD-0003Block Diagram For CCTV in Binak DU |  | 2022-05-25
CCTV Equipment Layout for GCS Area | BK-GCS-PEDCO-120-IN-PY-0007 | BK-GCS-PEDCO-120-IN-PY-0007 CCTV Equipment Layout for GCS Area | 2022-04-09 | 2022-05-25
CCTV Equipment Layout For Desalting Unit Area | BK-GCS-PEDCO-120-IN-PY-0008 | BK-GCS-PEDCO-120-IN-PY-0008CCTV Equipment Layout For Desalting Unit Area |  | 2022-05-25
Wiring Diagram For Interposing Relay Panel (IRP) | BK-GCS-PEDCO-120-EL-DG-0011 | BK-GCS-PEDCO-120-EL-DG-0011Wiring Diagram For Interposing Relay Panel (IRP) |  | 2022-05-25
Instrument Index | BK-GCS-PEDCO-120-IN-LI-0001 | BK-GCS-PEDCO-120-IN-LI-0001Instrument Index | 2022-04-27 | 2022-05-25
I/O List For Control System | BK-GCS-PEDCO-120-IN-LI-0002 | BK-GCS-PEDCO-120-IN-LI-0002I/O List For Control System | 2022-01-25 | 2022-05-25
I/O List For ESD Systems | BK-GCS-PEDCO-120-IN-LI-0003 | BK-GCS-PEDCO-120-IN-LI-0003I/O List For ESD Systems | 2022-01-25 | 2022-05-25
I/O List For F&G Systems | BK-GCS-PEDCO-120-IN-LI-0004 | BK-GCS-PEDCO-120-IN-LI-0004I/O List For F&G Systems | 2022-02-07 | 2022-05-25
Panels & Junction Box List | BK-GCS-PEDCO-120-IN-LI-0005 | BK-GCS-PEDCO-120-IN-LI-0005Panels & Junction Box List | 2022-02-13 | 2022-05-25
Set Point & Alarm List | BK-GCS-PEDCO-120-IN-LI-0006 | BK-GCS-PEDCO-120-IN-LI-0006Set Point & Alarm List | 2022-05-09 | 2022-05-25
I&C Power Consumption Summary | BK-GCS-PEDCO-120-IN-LI-0007 | BK-GCS-PEDCO-120-IN-LI-0007I&C Power Consumption Summary | 2022-02-23 | 2022-05-25
F&G Detector List | BK-GCS-PEDCO-120-IN-LI-0008 | BK-GCS-PEDCO-120-IN-LI-0008F&G Detector List | 2022-02-07 | 2022-05-25
Instrument /F&G Cable List | BK-GCS-PEDCO-120-IN-LI-0009 | BK-GCS-PEDCO-120-IN-LI-0009Instrument /F&G Cable List | 2022-02-13 | 2022-05-25
Cable Schedule For CCTV | BK-GCS-PEDCO-120-IN-LI-0010 | BK-GCS-PEDCO-120-IN-LI-0010Cable Schedule For CCTV |  | 2022-05-25
Cable Schedule For CCTV in Binak DU Area | BK-GCS-PEDCO-120-IN-LI-0011 | BK-GCS-PEDCO-120-IN-LI-0011Cable Schedule For CCTV in Binak DU Area |  | 2022-05-25
MTO for Bulk Item and Installation Accessories | BK-GCS-PEDCO-120-IN-MT-0001 | BK-GCS-PEDCO-120-IN-MT-0001MTO for Bulk Item and Installation Accessories |  | 2022-05-25
MTO For Instrument/F&G Cable | BK-GCS-PEDCO-120-IN-MT-0002 | BK-GCS-PEDCO-120-IN-MT-0002MTO For Instrument/F&G Cable |  | 2022-05-25
MTO For Instrument/F&G Junction box and Gland | BK-GCS-PEDCO-120-IN-MT-0003 | BK-GCS-PEDCO-120-IN-MT-0003MTO For Instrument/F&G Junction box and Gland |  | 2022-05-25
MTO For Instrument Tube and Fitting | BK-GCS-PEDCO-120-IN-MT-0004 | BK-GCS-PEDCO-120-IN-MT-0004MTO For Instrument Tube and Fitting |  | 2022-05-25
MTO For Instrument Cable Tray/Ladder | BK-GCS-PEDCO-120-IN-MT-0005 | BK-GCS-PEDCO-120-IN-MT-0005MTO For Instrument Cable Tray/Ladder |  | 2022-05-25
MTO For CCTV | BK-GCS-PEDCO-120-IN-MT-0006 | BK-GCS-PEDCO-120-IN-MT-0006MTO For CCTV | 2021-12-12 | 2022-02-12
MTO For CCTV in Binak DU Area | BK-GCS-PEDCO-120-IN-MT-0007 | BK-GCS-PEDCO-120-IN-MT-0007MTO For CCTV in Binak DU Area | 2021-12-13 | 2022-05-02
Active Fire Protection and Safety Concept | BK-GCS-PEDCO-120-SA-DB-0001 | BK-GCS-PEDCO-120-SA-DB-0001Active Fire Protection and Safety Concept | 2021-09-14 | 2022-05-25
Calculation Note For Total Flooding Demand For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-SA-CN-0001 | BK-GCS-PEDCO-120-SA-CN-0001Calculation Note For Total Flooding Demand For Extension of Existing Elect. Building | 2022-01-16 | 2022-03-09
Calculation Note For Fire Water Demand | BK-GCS-PEDCO-120-SA-CN-0002 | BK-GCS-PEDCO-120-SA-CN-0002Calculation Note For Fire Water Demand | 2021-12-13 | 2022-05-25
Fire Water Hydraulic Calculation Note | BK-GCS-PEDCO-120-SA-CN-0003 | BK-GCS-PEDCO-120-SA-CN-0003Fire Water Hydraulic Calculation Note | 2022-05-22 | 2022-05-25
Data Sheets For Safety Equipment | BK-GCS-PEDCO-120-SA-DT-0002 | BK-GCS-PEDCO-120-SA-DT-0002Data Sheets For Safety Equipment | 2022-04-19 | 2022-05-25
Data Sheets For Fire Fighting Equipment | BK-GCS-PEDCO-120-SA-DT-0003 | BK-GCS-PEDCO-120-SA-DT-0003Data Sheets For Fire Fighting Equipment | 2022-04-18 | 2022-05-25
Data Sheets For Deluge valves | BK-GCS-PEDCO-120-SA-DT-0004 | BK-GCS-PEDCO-120-SA-DT-0004Data Sheets For Deluge valves | 2022-01-16 | 2022-05-25
Data Sheets For Water Spray Nozzles | BK-GCS-PEDCO-120-SA-DT-0005 | BK-GCS-PEDCO-120-SA-DT-0005Data Sheets For Water Spray Nozzles | 2022-05-22 | 2022-05-25
Data Sheets For Safety Sign | BK-GCS-PEDCO-120-SA-DT-0006 | BK-GCS-PEDCO-120-SA-DT-0006Data Sheets For Safety Sign | 2021-09-20 | 2022-05-25
PFD - Fire Water System | BK-GCS-PEDCO-120-SA-PF-0001 | BK-GCS-PEDCO-120-SA-PF-0001PFD - Fire Water System | 2021-12-13 | 2022-05-25
P&ID - Fire Water Network | BK-GCS-PEDCO-120-SA-PI-0001 | BK-GCS-PEDCO-120-SA-PI-0001P&ID - Fire Water Network | 2022-02-12 | 2022-05-25
P&ID - Total Flooding System For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-SA-PI-0002 | BK-GCS-PEDCO-120-SA-PI-0002P&ID - Total Flooding System For Extension of Existing Elect. Building | 2022-01-16 | 2022-05-25
Fire Water Network Layout | BK-GCS-PEDCO-120-SA-PY-0001 | BK-GCS-PEDCO-120-SA-PY-0001Fire Water Network Layout | 2021-12-13 | 2022-05-25
Hazardous Area Classification Layout | BK-GCS-PEDCO-120-SA-PY-0002 | BK-GCS-PEDCO-120-SA-PY-0002Hazardous Area Classification Layout | 2022-03-12 | 2022-05-25
Fire Proofing Zone Layout | BK-GCS-PEDCO-120-SA-PY-0003 | BK-GCS-PEDCO-120-SA-PY-0003Fire Proofing Zone Layout | 2022-05-22 | 2022-05-25
Safety & Fire Fighting Equipment Location Layout | BK-GCS-PEDCO-120-SA-PY-0004 | BK-GCS-PEDCO-120-SA-PY-0004Safety & Fire Fighting Equipment Location Layout | 2022-02-12 | 2022-05-25
Escape Route & Safety Sign Layout | BK-GCS-PEDCO-120-SA-PY-0005 | BK-GCS-PEDCO-120-SA-PY-0005Escape Route & Safety Sign Layout | 2022-05-10 | 2022-05-25
Hazard Source List | BK-GCS-PEDCO-120-SA-LI-0001 | BK-GCS-PEDCO-120-SA-LI-0001Hazard Source List | 2022-02-23 | 2022-05-25
Fire Fighting Line List | BK-GCS-PEDCO-120-SA-LI-0002 | BK-GCS-PEDCO-120-SA-LI-0002Fire Fighting Line List |  | 2022-05-25
Consequence Modeling Report | BK-GCS-PEDCO-120-SA-RT-0003 | BK-GCS-PEDCO-120-SA-RT-0003Consequence Modeling Report | 2021-11-21 | 2022-05-25
MTO For Safety & Fire Fighting Equipment | BK-GCS-PEDCO-120-SA-MT-0001 | BK-GCS-PEDCO-120-SA-MT-0001MTO For Safety & Fire Fighting Equipment | 2022-05-22 | 2022-05-22
MTO For Safety Sign | BK-GCS-PEDCO-120-SA-MT-0002 | BK-GCS-PEDCO-120-SA-MT-0002MTO For Safety Sign | 2022-05-15 | 2022-05-15
Calculation Note For Outdoor Area Lighting System | BK-GCS-PEDCO-120-EL-CN-0001 | BK-GCS-PEDCO-120-EL-CN-0001Calculation Note For Outdoor Area Lighting System |  | 2022-05-25
Calculation Note For Indoor Area Lighting System | BK-GCS-PEDCO-120-EL-CN-0002 | BK-GCS-PEDCO-120-EL-CN-0002Calculation Note For Indoor Area Lighting System | 2022-04-27 | 2022-05-25
Calculation Note For Cable Sizing | BK-GCS-PEDCO-120-EL-CN-0003 | BK-GCS-PEDCO-120-EL-CN-0003Calculation Note For Cable Sizing |  | 2022-05-25
Calculation Note For UPS System | BK-GCS-PEDCO-120-EL-CN-0004 | BK-GCS-PEDCO-120-EL-CN-0004Calculation Note For UPS System | 2021-11-22 | 2022-05-25
Calculation Note For DC Charger System | BK-GCS-PEDCO-120-EL-CN-0005 | BK-GCS-PEDCO-120-EL-CN-0005Calculation Note For DC Charger System | 2021-12-15 | 2022-05-25
Calculation Note For Earthing & Lightning System | BK-GCS-PEDCO-120-EL-CN-0006 | BK-GCS-PEDCO-120-EL-CN-0006Calculation Note For Earthing & Lightning System | 2022-04-30 | 2022-05-25
Calculation Note For Diesel Generator Sizing | BK-GCS-PEDCO-120-EL-CN-0007 | BK-GCS-PEDCO-120-EL-CN-0007Calculation Note For Diesel Generator Sizing | 2021-11-16 | 2022-05-25
Calculation Note For Cathodic Protection System | BK-GCS-PEDCO-120-EL-CN-0008 | BK-GCS-PEDCO-120-EL-CN-0008Calculation Note For Cathodic Protection System | 2022-05-01 | 2022-05-25
Calculation Note For NGR Sizing | BK-GCS-PEDCO-120-EL-CN-0009 | BK-GCS-PEDCO-120-EL-CN-0009Calculation Note For NGR Sizing | 2022-04-11 | 2022-05-25
Calculation Note for UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-CN-0010 | BK-GCS-PEDCO-120-EL-CN-0010Calculation Note for UPS of CCTV in Desalting, Production & CS Unit |  | 2022-05-25
Calculation Note for Capacitor Banks | BK-GCS-PEDCO-120-EL-CN-0011 | BK-GCS-PEDCO-120-EL-CN-0011Calculation Note for Capacitor Banks | 2021-11-22 | 2022-05-25
Data Sheets For UPS | BK-GCS-PEDCO-120-EL-DT-0001 | BK-GCS-PEDCO-120-EL-DT-0001Data Sheets For UPS | 2021-12-26 | 2022-05-25
Data Sheets For DC Charger | BK-GCS-PEDCO-120-EL-DT-0002 | BK-GCS-PEDCO-120-EL-DT-0002Data Sheets For DC Charger | 2021-12-19 | 2022-05-25
Data Sheets For Diesel Generator | BK-GCS-PEDCO-120-EL-DT-0003 | BK-GCS-PEDCO-120-EL-DT-0003Data Sheets For Diesel Generator |  | 2022-05-25
Data Sheets For Expansion of MV Switchgear | BK-GCS-PEDCO-120-EL-DT-0004 | BK-GCS-PEDCO-120-EL-DT-0004Data Sheets For Expansion of MV Switchgear | 2022-01-22 | 2022-05-25
Data Sheets For LV Switchgear | BK-GCS-PEDCO-120-EL-DT-0005 | BK-GCS-PEDCO-120-EL-DT-0005Data Sheets For LV Switchgear | 2022-02-19 | 2022-05-25
Data Sheets For Local Control Stations (LCS) | BK-GCS-PEDCO-120-EL-DT-0006 | BK-GCS-PEDCO-120-EL-DT-0006Data Sheets For Local Control Stations (LCS) | 2022-02-06 | 2022-05-25
Data Sheets For Capacitor Bank | BK-GCS-PEDCO-120-EL-DT-0007 | BK-GCS-PEDCO-120-EL-DT-0007Data Sheets For Capacitor Bank | 2022-02-27 | 2022-05-25
Data Sheets For LV Induction Motors | BK-GCS-PEDCO-120-EL-DT-0008 | BK-GCS-PEDCO-120-EL-DT-0008Data Sheets For LV Induction Motors | 2021-09-12 | 2022-05-25
Data Sheets For MV Induction Motors | BK-GCS-PEDCO-120-EL-DT-0009 | BK-GCS-PEDCO-120-EL-DT-0009Data Sheets For MV Induction Motors | 2021-09-12 | 2022-05-25
Data Sheets For Power & Control Cables | BK-GCS-PEDCO-120-EL-DT-0010 | BK-GCS-PEDCO-120-EL-DT-0010Data Sheets For Power & Control Cables | 2022-02-19 | 2022-05-25
Data Sheets For Power Transformers | BK-GCS-PEDCO-120-EL-DT-0011 | BK-GCS-PEDCO-120-EL-DT-0011Data Sheets For Power Transformers | 2022-02-02 | 2022-05-25
Data Sheets For Cathodic Protection System | BK-GCS-PEDCO-120-EL-DT-0012 | BK-GCS-PEDCO-120-EL-DT-0012Data Sheets For Cathodic Protection System |  | 2022-05-25
Data Sheets For NGR | BK-GCS-PEDCO-120-EL-DT-0013 | BK-GCS-PEDCO-120-EL-DT-0013Data Sheets For NGR | 2022-04-11 | 2022-05-25
Data Sheets For Remote Control Panel | BK-GCS-PEDCO-120-EL-DT-0015 | BK-GCS-PEDCO-120-EL-DT-0015Data Sheets For Remote Control Panel |  | 2022-05-25
Data Sheets For Distribution & Lighting Panels | BK-GCS-PEDCO-120-EL-DT-0016 | BK-GCS-PEDCO-120-EL-DT-0016Data Sheets For Distribution & Lighting Panels | 2022-05-17 | 2022-05-25
Data Sheet for UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-DT-0017 | BK-GCS-PEDCO-120-EL-DT-0017Data Sheet for UPS of CCTV in Desalting, Production & CS Unit | 2022-03-02 | 2022-05-25
Electrical Overall Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0001 | BK-GCS-PEDCO-120-EL-SL-0001Electrical Overall Single Line Diagram | 2022-01-24 | 2022-05-25
LV Switchgear/MCC Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0002 | BK-GCS-PEDCO-120-EL-SL-0002LV Switchgear/MCC Single Line Diagram | 2021-12-27 | 2022-05-25
Existent MV Switchgear Expansion Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0003 | BK-GCS-PEDCO-120-EL-SL-0003Existent MV Switchgear Expansion Single Line Diagram | 2022-01-12 | 2022-05-25
Distribution and Lighting Panels Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0004 | BK-GCS-PEDCO-120-EL-SL-0004Distribution and Lighting Panels Single Line Diagram |  | 2022-05-25
UPS Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0005 | BK-GCS-PEDCO-120-EL-SL-0005UPS Single Line Diagram | 2021-12-26 | 2022-05-25
DC Charger Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0006 | BK-GCS-PEDCO-120-EL-SL-0006DC Charger Single Line Diagram | 2021-12-18 | 2022-05-25
Electrical Typical Schematic Diagrams For MV panel | BK-GCS-PEDCO-120-EL-DG-0001 | BK-GCS-PEDCO-120-EL-DG-0001Electrical Typical Schematic Diagrams For MV panel | 2022-01-12 | 2022-04-30
Electrical Typical Schematic Diagrams For LV panel | BK-GCS-PEDCO-120-EL-DG-0002 | BK-GCS-PEDCO-120-EL-DG-0002Electrical Typical Schematic Diagrams For LV panel | 2021-12-13 | 2022-05-15
Interconnection Wiring Diagram | BK-GCS-PEDCO-120-EL-DG-0003 | BK-GCS-PEDCO-120-EL-DG-0003Interconnection Wiring Diagram |  | 2022-05-25
Wiring Diagram For Remote Control Panel (RCP) | BK-GCS-PEDCO-120-EL-DG-0005 | BK-GCS-PEDCO-120-EL-DG-0005Wiring Diagram For Remote Control Panel (RCP) |  | 2022-05-25
Wiring Diagrams For Cathodic Protection Systems | BK-GCS-PEDCO-120-EL-DG-0006 | BK-GCS-PEDCO-120-EL-DG-0006Wiring Diagrams For Cathodic Protection Systems |  | 2022-05-25
Control Logic Diagram For LV Incomers and bus tie | BK-GCS-PEDCO-120-EL-LD-0001 | BK-GCS-PEDCO-120-EL-LD-0001Control Logic Diagram For LV Incomers and bus tie | 2022-01-16 | 2022-05-25
Overall Earthing Layout | BK-GCS-PEDCO-120-EL-PY-0001 | BK-GCS-PEDCO-120-EL-PY-0001Overall Earthing Layout |  | 2022-05-25
Earthing & Lightning Layout For Building & Shelter | BK-GCS-PEDCO-120-EL-PY-0002 | BK-GCS-PEDCO-120-EL-PY-0002Earthing & Lightning Layout For Building & Shelter |  | 2022-05-25
Area Lighting & Small Power Layout | BK-GCS-PEDCO-120-EL-PY-0003 | BK-GCS-PEDCO-120-EL-PY-0003Area Lighting & Small Power Layout |  | 2022-05-25
Lighting & Small Power Layout For Building & Shelter | BK-GCS-PEDCO-120-EL-PY-0004 | BK-GCS-PEDCO-120-EL-PY-0004Lighting & Small Power Layout For Building & Shelter | 2022-05-15 | 2022-05-25
Area Electrical Cable Route & Section Layout | BK-GCS-PEDCO-120-EL-PY-0005 | BK-GCS-PEDCO-120-EL-PY-0005Area Electrical Cable Route & Section Layout |  | 2022-05-25
Electrical Cable Route & Section Layout For Building & Shelter | BK-GCS-PEDCO-120-EL-PY-0006 | BK-GCS-PEDCO-120-EL-PY-0006Electrical Cable Route & Section Layout For Building & Shelter |  | 2022-05-25
HVAC Power Cabling Arrangement Layout For Building | BK-GCS-PEDCO-120-EL-PY-0007 | BK-GCS-PEDCO-120-EL-PY-0007HVAC Power Cabling Arrangement Layout For Building |  | 2022-05-25
Electrical Equipment Arrangement Layout For Building | BK-GCS-PEDCO-120-EL-PY-0008 | BK-GCS-PEDCO-120-EL-PY-0008Electrical Equipment Arrangement Layout For Building | 2022-05-09 | 2022-05-25
Cathodic Protection System Layout | BK-GCS-PEDCO-120-EL-PY-0009 | BK-GCS-PEDCO-120-EL-PY-0009Cathodic Protection System Layout |  | 2022-05-25
Capacitor Banks Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0007 | BK-GCS-PEDCO-120-EL-SL-0007Capacitor Banks Single Line Diagram | 2022-03-02 | 2022-05-25
Power & Control Cables Termination Diagrams | BK-GCS-PEDCO-120-EL-DG-0007 | BK-GCS-PEDCO-120-EL-DG-0007Power & Control Cables Termination Diagrams |  | 2022-05-25
Single Line Diagram for UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-SL-0009 | BK-GCS-PEDCO-120-EL-SL-0009Single Line Diagram for UPS of CCTV in Desalting, Production & CS Unit |  | 2022-05-25
SLD for Supplying UPS of CCTV Panel in Desalting Unit | BK-GCS-PEDCO-120-EL-SL-0008 | BK-GCS-PEDCO-120-EL-SL-0008SLD for Supplying UPS of CCTV Panel in Desalting Unit |  | 2022-05-25
SLD for Supplying UPS of CCTV Panel in Production Unit | BK-GCS-PEDCO-120-EL-SL-0010 | BK-GCS-PEDCO-120-EL-SL-0010SLD for Supplying UPS of CCTV Panel in Production Unit |  | 2022-05-25
Equipment Arrangement Layout for UPS of CCTV in Desalting Unit | BK-GCS-PEDCO-120-EL-PY-0010 | BK-GCS-PEDCO-120-EL-PY-0010Equipment Arrangement Layout for UPS of CCTV in Desalting Unit |  | 2022-05-25
Equipment Arrangement Layout for UPS of CCTV in Production Unit | BK-GCS-PEDCO-120-EL-PY-0011 | BK-GCS-PEDCO-120-EL-PY-0011Equipment Arrangement Layout for UPS of CCTV in Production Unit |  | 2022-05-25
Cable Route Layout for Desalting Unit | BK-GCS-PEDCO-120-EL-PY-0012 | BK-GCS-PEDCO-120-EL-PY-0012Cable Route Layout for Desalting Unit |  | 2022-05-25
Cable Route layout for Production Unit | BK-GCS-PEDCO-120-EL-PY-0013 | BK-GCS-PEDCO-120-EL-PY-0013Cable Route layout for Production Unit |  | 2022-05-25
Earthing Layout for Desalting Unit | BK-GCS-PEDCO-120-EL-PY-0014 | BK-GCS-PEDCO-120-EL-PY-0014Earthing Layout for Desalting Unit |  | 2022-05-25
Earthing Layout for Production Unit | BK-GCS-PEDCO-120-EL-PY-0015 | BK-GCS-PEDCO-120-EL-PY-0015Earthing Layout for Production Unit |  | 2022-05-25
Electrical Load List | BK-GCS-PEDCO-120-EL-LI-0001 | BK-GCS-PEDCO-120-EL-LI-0001Electrical Load List | 2021-11-16 | 2022-05-25
Electrical Power & Control Cable Schedule | BK-GCS-PEDCO-120-EL-LI-0002 | BK-GCS-PEDCO-120-EL-LI-0002Electrical Power & Control Cable Schedule |  | 2022-05-25
Electrical Power & Control Drum Schedule & Cutting List | BK-GCS-PEDCO-120-EL-LI-0003 | BK-GCS-PEDCO-120-EL-LI-0003Electrical Power & Control Drum Schedule & Cutting List |  | 2022-05-25
Cable Schedule For Cathodic Protection System | BK-GCS-PEDCO-120-EL-LI-0004 | BK-GCS-PEDCO-120-EL-LI-0004Cable Schedule For Cathodic Protection System |  | 2022-05-25
Electrical I/O Signal List | BK-GCS-PEDCO-120-EL-LI-0005 | BK-GCS-PEDCO-120-EL-LI-0005Electrical I/O Signal List |  | 2022-05-25
Electrical Network (Load Flow, Motor Starting & Short Circuit) Study Report | BK-GCS-PEDCO-120-EL-RT-0001 | BK-GCS-PEDCO-120-EL-RT-0001Electrical Network (Load Flow, Motor Starting & Short Circuit) Study Report |  | 2022-05-25
Relay Coordination & Setting Study Report | BK-GCS-PEDCO-120-EL-RT-0002 | BK-GCS-PEDCO-120-EL-RT-0002Relay Coordination & Setting Study Report |  | 2022-05-25
MTO For Earthing & Lightning Systems | BK-GCS-PEDCO-120-EL-MT-0001 | BK-GCS-PEDCO-120-EL-MT-0001MTO For Earthing & Lightning Systems |  | 2022-05-25
MTO For Lighting & Small Powers | BK-GCS-PEDCO-120-EL-MT-0002 | BK-GCS-PEDCO-120-EL-MT-0002MTO For Lighting & Small Powers |  | 2022-05-25
MTO For Power & Control Cables | BK-GCS-PEDCO-120-EL-MT-0003 | BK-GCS-PEDCO-120-EL-MT-0003MTO For Power & Control Cables |  | 2022-05-25
MTO For Tray/Ladder and Accessories | BK-GCS-PEDCO-120-EL-MT-0004 | BK-GCS-PEDCO-120-EL-MT-0004MTO For Tray/Ladder and Accessories |  | 2022-05-25
MTO For Cathodic Protection System | BK-GCS-PEDCO-120-EL-MT-0005 | BK-GCS-PEDCO-120-EL-MT-0005MTO For Cathodic Protection System | 2022-05-01 | 2022-05-01
MTO For Electrical Bulk Items | BK-GCS-PEDCO-120-EL-MT-0006 | BK-GCS-PEDCO-120-EL-MT-0006MTO For Electrical Bulk Items |  | 2022-05-25
Data Sheets For CCTV | BK-GCS-PEDCO-120-TE-DT-0001 | BK-GCS-PEDCO-120-TE-DT-0001Data Sheets For CCTV
Data Sheets For PABX | BK-GCS-PEDCO-120-TE-DT-0002 | BK-GCS-PEDCO-120-TE-DT-0002Data Sheets For PABX | 2021-10-13 | 2022-02-02
Data Sheets For PAGA | BK-GCS-PEDCO-120-TE-DT-0003 | BK-GCS-PEDCO-120-TE-DT-0003Data Sheets For PAGA | 2021-10-13 | 2022-02-13
Data Sheets For Radio | BK-GCS-PEDCO-120-TE-DT-0004 | BK-GCS-PEDCO-120-TE-DT-0004Data Sheets For Radio | 2021-11-21 | 2022-02-02
Data Sheets For Telecom. Cable | BK-GCS-PEDCO-120-TE-DT-0005 | BK-GCS-PEDCO-120-TE-DT-0005Data Sheets For Telecom. Cable | 2021-10-13 | 2022-02-02
Data Sheets For Telecommunication Tower | BK-GCS-PEDCO-120-TE-DT-0006 | BK-GCS-PEDCO-120-TE-DT-0006Data Sheets For Telecommunication Tower | 2021-10-13 | 2022-02-02
Telecom Overall Block Diagram | BK-GCS-PEDCO-120-TE-BD-0001 | BK-GCS-PEDCO-120-TE-BD-0001Telecom Overall Block Diagram |  | 2022-05-25
Typical Installation Details & Notes For Telecommunication Tower | BK-GCS-PEDCO-120-TE-DW-0001 | BK-GCS-PEDCO-120-TE-DW-0001Typical Installation Details & Notes For Telecommunication Tower |  | 2022-05-25
Block Diagram For CCTV | BK-GCS-PEDCO-120-TE-BD-0002 | BK-GCS-PEDCO-120-TE-BD-0002Block Diagram For CCTV
Block Diagram For CCTV in Binak DU | BK-GCS-PEDCO-120-TE-BD-0003 | BK-GCS-PEDCO-120-TE-BD-0003Block Diagram For CCTV in Binak DU
Block Diagram For PABX | BK-GCS-PEDCO-120-TE-BD-0004 | BK-GCS-PEDCO-120-TE-BD-0004Block Diagram For PABX | 2021-07-28 | 2022-03-08
Block Diagram For PAGA | BK-GCS-PEDCO-120-TE-BD-0005 | BK-GCS-PEDCO-120-TE-BD-0005Block Diagram For PAGA | 2021-07-28 | 2022-03-08
Block Diagram For Radio | BK-GCS-PEDCO-120-TE-BD-0006 | BK-GCS-PEDCO-120-TE-BD-0006Block Diagram For Radio | 2021-07-28 | 2021-09-25
Telecomm. Equipment Layout For Electrical Building | BK-GCS-PEDCO-120-TE-PY-0001 | BK-GCS-PEDCO-120-TE-PY-0001Telecomm. Equipment Layout For Electrical Building | 2022-04-17 | 2022-05-25
Telecomm. Equipment Layout For Control Building | BK-GCS-PEDCO-120-TE-PY-0002 | BK-GCS-PEDCO-120-TE-PY-0002Telecomm. Equipment Layout For Control Building |  | 2022-05-25
CCTV Equipment Layout For Area | BK-GCS-PEDCO-120-TE-PY-0003 | BK-GCS-PEDCO-120-TE-PY-0003CCTV Equipment Layout For Area
CCTV Equipment Layout For Desalting Unit Area | BK-GCS-PEDCO-120-TE-PY-0004 | BK-GCS-PEDCO-120-TE-PY-0004CCTV Equipment Layout For Desalting Unit Area
Telecomm Equipment Layout For Area | BK-GCS-PEDCO-120-TE-PY-0005 | BK-GCS-PEDCO-120-TE-PY-0005Telecomm Equipment Layout For Area | 2022-04-04 | 2022-05-25
PAGA Equipment Layout For Area | BK-GCS-PEDCO-120-TE-PY-0006 | BK-GCS-PEDCO-120-TE-PY-0006PAGA Equipment Layout For Area | 2022-04-06 | 2022-05-25
Cable Schedule For CCTV | BK-GCS-PEDCO-120-TE-LI-0001 | BK-GCS-PEDCO-120-TE-LI-0001Cable Schedule For CCTV
Cable Schedule For PABX | BK-GCS-PEDCO-120-TE-LI-0003 | BK-GCS-PEDCO-120-TE-LI-0003Cable Schedule For PABX |  | 2022-05-25
Cable Schedule For PAGA | BK-GCS-PEDCO-120-TE-LI-0004 | BK-GCS-PEDCO-120-TE-LI-0004Cable Schedule For PAGA |  | 2022-05-25
MTO For CCTV | BK-GCS-PEDCO-120-TE-MT-0001 | BK-GCS-PEDCO-120-TE-MT-0001MTO For CCTV
MTO For CCTV in Binak DU Area | BK-GCS-PEDCO-120-TE-MT-0002 | BK-GCS-PEDCO-120-TE-MT-0002MTO For CCTV in Binak DU Area
MTO For PABX | BK-GCS-PEDCO-120-TE-MT-0003 | BK-GCS-PEDCO-120-TE-MT-0003MTO For PABX |  | 2022-05-25
MTO For PAGA | BK-GCS-PEDCO-120-TE-MT-0004 | BK-GCS-PEDCO-120-TE-MT-0004MTO For PAGA |  | 2022-05-25
MTO For Radio | BK-GCS-PEDCO-120-TE-MT-0005 | BK-GCS-PEDCO-120-TE-MT-0005MTO For Radio | 2021-12-13 | 2022-01-09
MTO For Telecom. Cable | BK-GCS-PEDCO-120-TE-MT-0006 | BK-GCS-PEDCO-120-TE-MT-0006MTO For Telecom. Cable |  | 2022-05-25
Architectural Detail Drawing For Control Building | BK-GCS-PEDCO-120-AR-DW-0001 | BK-GCS-PEDCO-120-AR-DW-0001Architectural Detail Drawing For Control Building | 2021-12-13 | 2022-05-25
Architectural Detail Drawing For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-AR-DW-0002 | BK-GCS-PEDCO-120-AR-DW-0002Architectural Detail Drawing For Extension of Existing Elect. Building | 2022-01-15 | 2022-05-25
Architectural Drawing For Gas Compressors Shelter | BK-GCS-PEDCO-120-AR-DW-0003 | BK-GCS-PEDCO-120-AR-DW-0003Architectural Drawing For Gas Compressors Shelter |  | 2022-05-25
Architectural Drawing For Chemical Inj. Packages/Chemical Storage Shelter | BK-GCS-PEDCO-120-AR-DW-0004 | BK-GCS-PEDCO-120-AR-DW-0004Architectural Drawing For Chemical Inj. Packages/Chemical Storage Shelter |  | 2022-05-25
Architectural Drawing For Utility Shelter | BK-GCS-PEDCO-120-AR-DW-0005 | BK-GCS-PEDCO-120-AR-DW-0005Architectural Drawing For Utility Shelter |  | 2022-05-25
Architectural Drawing For Fire Water Pumps Shelter | BK-GCS-PEDCO-120-AR-DW-0006 | BK-GCS-PEDCO-120-AR-DW-0006Architectural Drawing For Fire Water Pumps Shelter |  | 2022-05-25
Architectural Drawing For Fire Shed | BK-GCS-PEDCO-120-AR-DW-0007 | BK-GCS-PEDCO-120-AR-DW-0007Architectural Drawing For Fire Shed | 2022-05-01 | 2022-05-25
MTO For Architectural Works | BK-GCS-PEDCO-120-AR-MT-0001 | BK-GCS-PEDCO-120-AR-MT-0001MTO For Architectural Works |  | 2022-05-25
MTO For Blast Proof Doors | BK-GCS-PEDCO-120-AR-MT-0002 | BK-GCS-PEDCO-120-AR-MT-0002MTO For Blast Proof Doors |  | 2022-05-25
Site Sewarage System Layout & Details | BK-GCS-PEDCO-120-CV-PY-0001 | BK-GCS-PEDCO-120-CV-PY-0001Site Sewarage System Layout & Details |  | 2022-05-25
Cable Trench and Duct Bank Layout | BK-GCS-PEDCO-120-CV-PY-0002 | BK-GCS-PEDCO-120-CV-PY-0002Cable Trench and Duct Bank Layout |  | 2022-05-25
Oil Contaminated Water System Layout | BK-GCS-PEDCO-120-CV-PY-0003 | BK-GCS-PEDCO-120-CV-PY-0003Oil Contaminated Water System Layout |  | 2022-05-25
Plant Clean Water Drainage System Layout & Details | BK-GCS-PEDCO-120-CV-PY-0004 | BK-GCS-PEDCO-120-CV-PY-0004Plant Clean Water Drainage System Layout & Details |  | 2022-05-25
Road, Paving And Plant Finish Grading Layout & Sections | BK-GCS-PEDCO-120-CV-PY-0005 | BK-GCS-PEDCO-120-CV-PY-0005Road, Paving And Plant Finish Grading Layout & Sections |  | 2022-05-25
Plant Underground Composite Layout | BK-GCS-PEDCO-120-CV-PY-0006 | BK-GCS-PEDCO-120-CV-PY-0006Plant Underground Composite Layout |  | 2022-05-25
Rough Grading Plan and Details | BK-GCS-PEDCO-120-CV-PY-0007 | BK-GCS-PEDCO-120-CV-PY-0007Rough Grading Plan and Details | 2022-05-23 | 2022-05-25
Calculation Note For Inside Surface Water Drainage Channels | BK-GCS-PEDCO-120-CV-CN-0001 | BK-GCS-PEDCO-120-CV-CN-0001Calculation Note For Inside Surface Water Drainage Channels |  | 2022-05-25
Calculation Note for offsite flood control system | BK-GCS-PEDCO-120-CV-CN-0002 | BK-GCS-PEDCO-120-CV-CN-0002Calculation Note for offsite flood control system |  | 2022-05-25
Site Visit Report (Civil Work) - GCS | BK-GCS-PEDCO-110-CV-RT-0001 | BK-GCS-PEDCO-110-CV-RT-0001Site Visit Report (Civil Work) - GCS | 2022-03-13 | 2022-05-25
MTO For Civil Work | BK-GCS-PEDCO-120-CV-MT-0001 | BK-GCS-PEDCO-120-CV-MT-0001MTO For Civil Work |  | 2022-05-25
Structural Calculation Note For Control Building | BK-GCS-PEDCO-120-ST-CN-0002 | BK-GCS-PEDCO-120-ST-CN-0002Structural Calculation Note For Control Building |  | 2022-05-25
Calculation Report for Gas Compressors Shelter | BK-GCS-PEDCO-120-ST-CN-0003 | BK-GCS-PEDCO-120-ST-CN-0003Calculation Report for Gas Compressors Shelter |  | 2022-05-25
Calculation Report for Extension of Existing Elect. Building | BK-GCS-PEDCO-120-ST-CN-0005 | BK-GCS-PEDCO-120-ST-CN-0005Calculation Report for Extension of Existing Elect. Building |  | 2022-05-25
Calculation Note for Gas Compressors Foundation | BK-GCS-PEDCO-120-ST-CN-0006 | BK-GCS-PEDCO-120-ST-CN-0006Calculation Note for Gas Compressors Foundation |  | 2022-05-25
Calculation Note for Tank Foundation (TK-2301 A/B) | BK-GCS-PEDCO-120-ST-CN-0007 | BK-GCS-PEDCO-120-ST-CN-0007Calculation Note for Tank Foundation (TK-2301 A/B) |  | 2022-05-25
Calculation Note for Utility Shelter | BK-GCS-PEDCO-120-ST-CN-0008 | BK-GCS-PEDCO-120-ST-CN-0008Calculation Note for Utility Shelter |  | 2022-05-25
Calculation Note for Fire Water Pump Shelter | BK-GCS-PEDCO-120-ST-CN-0009 | BK-GCS-PEDCO-120-ST-CN-0009Calculation Note for Fire Water Pump Shelter |  | 2022-05-25
Calculation Note for Foundation of Slug Catcher Drum (V-2104) | BK-GCS-PEDCO-120-ST-CN-0010 | BK-GCS-PEDCO-120-ST-CN-0010Calculation Note for Foundation of Slug Catcher Drum (V-2104) |  | 2022-05-25
Calculation Note for Foundation of Dehydration Package (PK-2101) | BK-GCS-PEDCO-120-ST-CN-0011 | BK-GCS-PEDCO-120-ST-CN-0011Calculation Note for Foundation of Dehydration Package (PK-2101) |  | 2022-05-25
Calculation Note for Close Drain Sump Pit (SU-2201 A) | BK-GCS-PEDCO-120-ST-CN-0012 | BK-GCS-PEDCO-120-ST-CN-0012Calculation Note for Close Drain Sump Pit (SU-2201 A) |  | 2022-05-25
Calculation Note for Oily Water Sump Pit (SU-2201 B) | BK-GCS-PEDCO-120-ST-CN-0013 | BK-GCS-PEDCO-120-ST-CN-0013Calculation Note for Oily Water Sump Pit (SU-2201 B) |  | 2022-05-25
Calculation Note For Compressor Area Main Sleepers | BK-GCS-PEDCO-120-ST-CN-0014 | BK-GCS-PEDCO-120-ST-CN-0014Calculation Note For Compressor Area Main Sleepers |  | 2022-05-25
Calculation Note For Flare Area Sleepers | BK-GCS-PEDCO-120-ST-CN-0015 | BK-GCS-PEDCO-120-ST-CN-0015Calculation Note For Flare Area Sleepers |  | 2022-05-25
Calculation Note For Special Pipe Supports | BK-GCS-PEDCO-120-ST-CN-0016 | BK-GCS-PEDCO-120-ST-CN-0016Calculation Note For Special Pipe Supports |  | 2022-05-25
Calculation Note for1st Stage Air Coolers (AE-2101 A/B/C) | BK-GCS-PEDCO-120-ST-CN-0017 | BK-GCS-PEDCO-120-ST-CN-0017Calculation Note for1st Stage Air Coolers (AE-2101 A/B/C) |  | 2022-05-25
Calculation Note for 2nd Stage Air Coolers (AE-2102 A/B/C) | BK-GCS-PEDCO-120-ST-CN-0018 | BK-GCS-PEDCO-120-ST-CN-0018Calculation Note for 2nd Stage Air Coolers (AE-2102 A/B/C) |  | 2022-05-25
Calculation Note for Elevated Potable Water Tank (TK-2209) | BK-GCS-PEDCO-120-ST-CN-0019 | BK-GCS-PEDCO-120-ST-CN-0019Calculation Note for Elevated Potable Water Tank (TK-2209) |  | 2022-05-25
Calculation Note for Lean Glycol Storage Tank (TK-2102) | BK-GCS-PEDCO-120-ST-CN-0020 | BK-GCS-PEDCO-120-ST-CN-0020Calculation Note for Lean Glycol Storage Tank (TK-2102) |  | 2022-05-25
Calculation Note for Nitrogen Package (PK-2204A/B) | BK-GCS-PEDCO-120-ST-CN-0021 | BK-GCS-PEDCO-120-ST-CN-0021Calculation Note for Nitrogen Package (PK-2204A/B) |  | 2022-05-25
Calculation Note for Glycol Sump Pit (SU-2101) | BK-GCS-PEDCO-120-ST-CN-0022 | BK-GCS-PEDCO-120-ST-CN-0022Calculation Note for Glycol Sump Pit (SU-2101) |  | 2022-05-25
Calculation Note for Slug Pumps (P-2101A/B) | BK-GCS-PEDCO-120-ST-CN-0023 | BK-GCS-PEDCO-120-ST-CN-0023Calculation Note for Slug Pumps (P-2101A/B) |  | 2022-05-25
Calculation Note for Utility Area Sleepers | BK-GCS-PEDCO-120-ST-CN-0024 | BK-GCS-PEDCO-120-ST-CN-0024Calculation Note for Utility Area Sleepers |  | 2022-05-25
Calculation Note for Pipe rack | BK-GCS-PEDCO-120-ST-CN-0025 | BK-GCS-PEDCO-120-ST-CN-0025Calculation Note for Pipe rack |  | 2022-05-25
Calculation Note for Chemical Injection and Storage Shelter | BK-GCS-PEDCO-120-ST-CN-0026 | BK-GCS-PEDCO-120-ST-CN-0026Calculation Note for Chemical Injection and Storage Shelter |  | 2022-05-25
Foundation Location Plan | BK-GCS-PEDCO-120-ST-DW-0003 | BK-GCS-PEDCO-120-ST-DW-0003Foundation Location Plan |  | 2022-05-25
Foundation Drawing For 1st Stage Gas Compressor (C-2101A/B/C) | BK-GCS-PEDCO-120-ST-DW-0004 | BK-GCS-PEDCO-120-ST-DW-0004Foundation Drawing For 1st Stage Gas Compressor (C-2101A/B/C) |  | 2022-05-25
Foundation Drawing For 2nd Stage Gas Compressor (C-2102A/B/C) | BK-GCS-PEDCO-120-ST-DW-0005 | BK-GCS-PEDCO-120-ST-DW-0005Foundation Drawing For 2nd Stage Gas Compressor (C-2102A/B/C) |  | 2022-05-25
Foundation Drawing For 1st Stage Air Coolers (AE-2101 A/B/C) | BK-GCS-PEDCO-120-ST-DW-0007 | BK-GCS-PEDCO-120-ST-DW-0007Foundation Drawing For 1st Stage Air Coolers (AE-2101 A/B/C) |  | 2022-05-25
Foundation Drawing For 2nd Stage Air Coolers (AE-2102 A/B/C) | BK-GCS-PEDCO-120-ST-DW-0008 | BK-GCS-PEDCO-120-ST-DW-0008Foundation Drawing For 2nd Stage Air Coolers (AE-2102 A/B/C) |  | 2022-05-25
Foundation Drawing For Inlet Gas K.O. Drum (V-2105) | BK-GCS-PEDCO-120-ST-DW-0009 | BK-GCS-PEDCO-120-ST-DW-0009Foundation Drawing For Inlet Gas K.O. Drum (V-2105) |  | 2022-05-25
Foundation Drawing For For 1st Stage G.C. Suction Drums (V-2101 A/B/C) | BK-GCS-PEDCO-120-ST-DW-0010 | BK-GCS-PEDCO-120-ST-DW-0010Foundation Drawing For For 1st Stage G.C. Suction Drums (V-2101 A/B/C) |  | 2022-05-25
Foundation Drawing For For 2nd Stage G.C. Suction Drums (V-2102 A/B/C) | BK-GCS-PEDCO-120-ST-DW-0011 | BK-GCS-PEDCO-120-ST-DW-0011Foundation Drawing For For 2nd Stage G.C. Suction Drums (V-2102 A/B/C) |  | 2022-05-25
Foundation Drawing For 2nd Stage G.C. Discharge Drum (V-2103) | BK-GCS-PEDCO-120-ST-DW-0012 | BK-GCS-PEDCO-120-ST-DW-0012Foundation Drawing For 2nd Stage G.C. Discharge Drum (V-2103) |  | 2022-05-25
Foundation Drawing For Fuel Oil Drum (V-2206) | BK-GCS-PEDCO-120-ST-DW-0013 | BK-GCS-PEDCO-120-ST-DW-0013Foundation Drawing For Fuel Oil Drum (V-2206) |  | 2022-05-25
Foundation Drawing For Instrument Air Receiver (V-2203) | BK-GCS-PEDCO-120-ST-DW-0014 | BK-GCS-PEDCO-120-ST-DW-0014Foundation Drawing For Instrument Air Receiver (V-2203) |  | 2022-05-25
Foundation Drawing For Elevated Potable Water Tank (TK-2209) | BK-GCS-PEDCO-120-ST-DW-0015 | BK-GCS-PEDCO-120-ST-DW-0015Foundation Drawing For Elevated Potable Water Tank (TK-2209) |  | 2022-05-25
Structural Drawing For Close Drain Sump Pit (SU-2201 A) | BK-GCS-PEDCO-120-ST-DW-0016 | BK-GCS-PEDCO-120-ST-DW-0016Structural Drawing For Close Drain Sump Pit (SU-2201 A) |  | 2022-05-25
Foundation Drawing For Fuel Gas K.O Drum (V-2205) | BK-GCS-PEDCO-120-ST-DW-0017 | BK-GCS-PEDCO-120-ST-DW-0017Foundation Drawing For Fuel Gas K.O Drum (V-2205) |  | 2022-05-25
Foundation Drawing For Slug Catcher Drum (V-2104) | BK-GCS-PEDCO-120-ST-DW-0018 | BK-GCS-PEDCO-120-ST-DW-0018Foundation Drawing For Slug Catcher Drum (V-2104) |  | 2022-05-25
Foundation Drawing For Degassing Drum (V-2106) | BK-GCS-PEDCO-120-ST-DW-0019 | BK-GCS-PEDCO-120-ST-DW-0019Foundation Drawing For Degassing Drum (V-2106) |  | 2022-05-25
Foundation Drawing For Nitrogen Receiver Drum (V-2204) | BK-GCS-PEDCO-120-ST-DW-0020 | BK-GCS-PEDCO-120-ST-DW-0020Foundation Drawing For Nitrogen Receiver Drum (V-2204) |  | 2022-05-25
Structural Drawing For Oily Water Sump Pit (SU-2201 B) | BK-GCS-PEDCO-120-ST-DW-0021 | BK-GCS-PEDCO-120-ST-DW-0021Structural Drawing For Oily Water Sump Pit (SU-2201 B) |  | 2022-05-25
Foundation Drawing For Lean Glycol Storage Tank (TK-2102) | BK-GCS-PEDCO-120-ST-DW-0023 | BK-GCS-PEDCO-120-ST-DW-0023Foundation Drawing For Lean Glycol Storage Tank (TK-2102) |  | 2022-05-25
Foundation Drawing For Fire Water Storage Tanks (TK-2301A/B) | BK-GCS-PEDCO-120-ST-DW-0024 | BK-GCS-PEDCO-120-ST-DW-0024Foundation Drawing For Fire Water Storage Tanks (TK-2301A/B) |  | 2022-05-25
Foundation Drawing For Slug Storage Tank (TK-2101) | BK-GCS-PEDCO-120-ST-DW-0025 | BK-GCS-PEDCO-120-ST-DW-0025Foundation Drawing For Slug Storage Tank (TK-2101) |  | 2022-05-25
Foundation Drawing For Dehydration Package (PK-2101) | BK-GCS-PEDCO-120-ST-DW-0026 | BK-GCS-PEDCO-120-ST-DW-0026Foundation Drawing For Dehydration Package (PK-2101) |  | 2022-05-25
Foundation Drawing For Diesel Generator (PK-2206) | BK-GCS-PEDCO-120-ST-DW-0027 | BK-GCS-PEDCO-120-ST-DW-0027Foundation Drawing For Diesel Generator (PK-2206) |  | 2022-05-25
Foundation Drawing For Instrument & Plant Air Package (PK-C-2203A/B) | BK-GCS-PEDCO-120-ST-DW-0028 | BK-GCS-PEDCO-120-ST-DW-0028Foundation Drawing For Instrument & Plant Air Package (PK-C-2203A/B) |  | 2022-05-25
Foundation Drawing For Corrosion Inhibitor Injection Package (PK-2207) | BK-GCS-PEDCO-120-ST-DW-0029 | BK-GCS-PEDCO-120-ST-DW-0029Foundation Drawing For Corrosion Inhibitor Injection Package (PK-2207) |  | 2022-05-25
Foundation Drawing For Methanol Injection Package (PK-2208) | BK-GCS-PEDCO-120-ST-DW-0030 | BK-GCS-PEDCO-120-ST-DW-0030Foundation Drawing For Methanol Injection Package (PK-2208) |  | 2022-05-25
Foundation Drawing For LP Flare Package (PK-2201) | BK-GCS-PEDCO-120-ST-DW-0031 | BK-GCS-PEDCO-120-ST-DW-0031Foundation Drawing For LP Flare Package (PK-2201) |  | 2022-05-25
Foundation Drawing For Nitrogen Package (PK-2204A/B) | BK-GCS-PEDCO-120-ST-DW-0032 | BK-GCS-PEDCO-120-ST-DW-0032Foundation Drawing For Nitrogen Package (PK-2204A/B) |  | 2022-05-25
Dike Wall Drawing For Lean Glycol Storage Tank (TK-2102) | BK-GCS-PEDCO-120-ST-DW-0033 | BK-GCS-PEDCO-120-ST-DW-0033Dike Wall Drawing For Lean Glycol Storage Tank (TK-2102) |  | 2022-05-25
Dike Wall Drawing For Slug Storage Tank (TK-2101) | BK-GCS-PEDCO-120-ST-DW-0034 | BK-GCS-PEDCO-120-ST-DW-0034Dike Wall Drawing For Slug Storage Tank (TK-2101) |  | 2022-05-25
Foundation Drawing For Glycol Sump Pit (SU-2101) | BK-GCS-PEDCO-120-ST-DW-0035 | BK-GCS-PEDCO-120-ST-DW-0035Foundation Drawing For Glycol Sump Pit (SU-2101) |  | 2022-05-25
Foundation Drawing For Glycol Transfer Pumps (P-2103 A/B) | BK-GCS-PEDCO-120-ST-DW-0036 | BK-GCS-PEDCO-120-ST-DW-0036Foundation Drawing For Glycol Transfer Pumps (P-2103 A/B) |  | 2022-05-25
Foundation Drawing For Glycol Manual Pump (P-2102) | BK-GCS-PEDCO-120-ST-DW-0037 | BK-GCS-PEDCO-120-ST-DW-0037Foundation Drawing For Glycol Manual Pump (P-2102) |  | 2022-05-25
Foundation Drawing For Fire Water Jockey Pumps (P-2302A/B) | BK-GCS-PEDCO-120-ST-DW-0038 | BK-GCS-PEDCO-120-ST-DW-0038Foundation Drawing For Fire Water Jockey Pumps (P-2302A/B) |  | 2022-05-25
Foundation Drawing For Fire Water Electrical Pump (P-2301 A) | BK-GCS-PEDCO-120-ST-DW-0039 | BK-GCS-PEDCO-120-ST-DW-0039Foundation Drawing For Fire Water Electrical Pump (P-2301 A) |  | 2022-05-25
Foundation Drawing For Fire Water Diesel Pumps (P-2302 B/C) | BK-GCS-PEDCO-120-ST-DW-0040 | BK-GCS-PEDCO-120-ST-DW-0040Foundation Drawing For Fire Water Diesel Pumps (P-2302 B/C) |  | 2022-05-25
Foundation Drawing For Potable Water Pump (P-2209) | BK-GCS-PEDCO-120-ST-DW-0041 | BK-GCS-PEDCO-120-ST-DW-0041Foundation Drawing For Potable Water Pump (P-2209) |  | 2022-05-25
Foundation Drawing For Fuel Oil Pump (P-2206) | BK-GCS-PEDCO-120-ST-DW-0042 | BK-GCS-PEDCO-120-ST-DW-0042Foundation Drawing For Fuel Oil Pump (P-2206) |  | 2022-05-25
Foundation Drawing For Slug Pumps (P-2101A/B) | BK-GCS-PEDCO-120-ST-DW-0043 | BK-GCS-PEDCO-120-ST-DW-0043Foundation Drawing For Slug Pumps (P-2101A/B) |  | 2022-05-25
Foundation Drawing For Compressor Area Main Sleepers | BK-GCS-PEDCO-120-ST-DW-0044 | BK-GCS-PEDCO-120-ST-DW-0044Foundation Drawing For Compressor Area Main Sleepers |  | 2022-05-25
Foundation Drawing For Compressor Area Secondary Sleepers | BK-GCS-PEDCO-120-ST-DW-0045 | BK-GCS-PEDCO-120-ST-DW-0045Foundation Drawing For Compressor Area Secondary Sleepers |  | 2022-05-25
Foundation Drawing For Utility Area Sleepers | BK-GCS-PEDCO-120-ST-DW-0046 | BK-GCS-PEDCO-120-ST-DW-0046Foundation Drawing For Utility Area Sleepers |  | 2022-05-25
Foundation Drawing For Flare Area Sleepers | BK-GCS-PEDCO-120-ST-DW-0047 | BK-GCS-PEDCO-120-ST-DW-0047Foundation Drawing For Flare Area Sleepers |  | 2022-05-25
Foundation Drawing For Transformer & Shelters | BK-GCS-PEDCO-120-ST-DW-0048 | BK-GCS-PEDCO-120-ST-DW-0048Foundation Drawing For Transformer & Shelters |  | 2022-05-25
Foundation Drawing For Pipe Supports | BK-GCS-PEDCO-120-ST-DW-0049 | BK-GCS-PEDCO-120-ST-DW-0049Foundation Drawing For Pipe Supports |  | 2022-05-25
Structural Drawing For Special Pipe Supports | BK-GCS-PEDCO-120-ST-DW-0050 | BK-GCS-PEDCO-120-ST-DW-0050Structural Drawing For Special Pipe Supports |  | 2022-05-25
Culvert Detail Drawing | BK-GCS-PEDCO-120-ST-DW-0051 | BK-GCS-PEDCO-120-ST-DW-0051Culvert Detail Drawing |  | 2022-05-25
Foundation Drawing For Access Platforms | BK-GCS-PEDCO-120-ST-DW-0052 | BK-GCS-PEDCO-120-ST-DW-0052Foundation Drawing For Access Platforms |  | 2022-05-25
Structural Drawing For Access Platforms | BK-GCS-PEDCO-120-ST-DW-0053 | BK-GCS-PEDCO-120-ST-DW-0053Structural Drawing For Access Platforms |  | 2022-05-25
Foundation Drawing For Pipe rack | BK-GCS-PEDCO-120-ST-DW-0054 | BK-GCS-PEDCO-120-ST-DW-0054Foundation Drawing For Pipe rack |  | 2022-05-25
Structural Drawing For Pipe rack | BK-GCS-PEDCO-120-ST-DW-0055 | BK-GCS-PEDCO-120-ST-DW-0055Structural Drawing For Pipe rack |  | 2022-05-25
Foundation Drawing For Lighting Poles and Towers | BK-GCS-PEDCO-120-ST-DW-0056 | BK-GCS-PEDCO-120-ST-DW-0056Foundation Drawing For Lighting Poles and Towers |  | 2022-05-25
Foundation Drawing For Chemical Injection and Storage Shelter | BK-GCS-PEDCO-120-ST-DW-0057 | BK-GCS-PEDCO-120-ST-DW-0057Foundation Drawing For Chemical Injection and Storage Shelter |  | 2022-05-25
Structural Drawing For Chemical Injection and Storage Shelter | BK-GCS-PEDCO-120-ST-DW-0058 | BK-GCS-PEDCO-120-ST-DW-0058Structural Drawing For Chemical Injection and Storage Shelter |  | 2022-05-25
Foundation Drawing For Gas Compressor Shelter | BK-GCS-PEDCO-120-ST-DW-0059 | BK-GCS-PEDCO-120-ST-DW-0059Foundation Drawing For Gas Compressor Shelter |  | 2022-05-25
Structural Drawing For Gas Compressor Shelter | BK-GCS-PEDCO-120-ST-DW-0060 | BK-GCS-PEDCO-120-ST-DW-0060Structural Drawing For Gas Compressor Shelter |  | 2022-05-25
Foundation Drawing For Control Building | BK-GCS-PEDCO-120-ST-DW-0061 | BK-GCS-PEDCO-120-ST-DW-0061Foundation Drawing For Control Building |  | 2022-05-25
Structural Drawing For Control Building | BK-GCS-PEDCO-120-ST-DW-0062 | BK-GCS-PEDCO-120-ST-DW-0062Structural Drawing For Control Building |  | 2022-05-25
Foundation Drawing For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-ST-DW-0063 | BK-GCS-PEDCO-120-ST-DW-0063Foundation Drawing For Extension of Existing Elect. Building |  | 2022-05-25
Structural Drawing For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-ST-DW-0064 | BK-GCS-PEDCO-120-ST-DW-0064Structural Drawing For Extension of Existing Elect. Building |  | 2022-05-25
Foundation Drawing For Fire Water Pump Shelter | BK-GCS-PEDCO-120-ST-DW-0065 | BK-GCS-PEDCO-120-ST-DW-0065Foundation Drawing For Fire Water Pump Shelter |  | 2022-05-25
Structural Drawing For Fire Water Pump Shelter | BK-GCS-PEDCO-120-ST-DW-0066 | BK-GCS-PEDCO-120-ST-DW-0066Structural Drawing For Fire Water Pump Shelter |  | 2022-05-25
Foundation Drawing For Utility Shelter | BK-GCS-PEDCO-120-ST-DW-0067 | BK-GCS-PEDCO-120-ST-DW-0067Foundation Drawing For Utility Shelter |  | 2022-05-25
Structural Drawing For Utility Shelter | BK-GCS-PEDCO-120-ST-DW-0068 | BK-GCS-PEDCO-120-ST-DW-0068Structural Drawing For Utility Shelter |  | 2022-05-25
Foundation Drawing For Air Dryer Packages (PK-D-2203A/B) | BK-GCS-PEDCO-120-ST-DW-0069 | BK-GCS-PEDCO-120-ST-DW-0069Foundation Drawing For Air Dryer Packages (PK-D-2203A/B) |  | 2022-05-25
Foundation Drawing For Pig Launcher (PL-3101) | BK-GCS-PEDCO-120-ST-DW-0070 | BK-GCS-PEDCO-120-ST-DW-0070Foundation Drawing For Pig Launcher (PL-3101) |  | 2022-05-25
Foundation Drawing For Ignition Package | BK-GCS-PEDCO-120-ST-DW-0071 | BK-GCS-PEDCO-120-ST-DW-0071Foundation Drawing For Ignition Package |  | 2022-05-25
Foundation Drawing For Fire Shed | BK-GCS-PEDCO-120-ST-DW-0072 | BK-GCS-PEDCO-120-ST-DW-0072Foundation Drawing For Fire Shed | 2022-01-30 | 2022-05-25
Structural Drawing For Fire Shed | BK-GCS-PEDCO-120-ST-DW-0073 | BK-GCS-PEDCO-120-ST-DW-0073Structural Drawing For Fire Shed | 2022-01-30 | 2022-05-25
Structural Drawing For Shelter of Transformers | BK-GCS-PEDCO-120-ST-DW-0074 | BK-GCS-PEDCO-120-ST-DW-0074Structural Drawing For Shelter of Transformers |  | 2022-05-25
MTO For Steel Structures Works | BK-GCS-PEDCO-120-ST-MT-0001 | BK-GCS-PEDCO-120-ST-MT-0001MTO For Steel Structures Works |  | 2022-05-25
MTO For Structural Concrete Works | BK-GCS-PEDCO-120-ST-MT-0002 | BK-GCS-PEDCO-120-ST-MT-0002MTO For Structural Concrete Works |  | 2022-05-25
Topographical Map | BK-GCS-PEDCO-120-SU-MP-0001 | BK-GCS-PEDCO-120-SU-MP-0001Topographical Map | 2022-04-30 | 2022-04-30
Geotechnical Investigation Plan for Compressor Station | BK-GCS-PEDCO-120-GT-PR-0001 | BK-GCS-PEDCO-120-GT-PR-0001Geotechnical Investigation Plan for Compressor Station | 2021-12-19 | 2022-01-18
Geotechnical Investigation Report for Compressor Station | BK-GCS-PEDCO-120-GT-RT-0001 | BK-GCS-PEDCO-120-GT-RT-0001Geotechnical Investigation Report for Compressor Station | 2022-05-17 | 2022-05-25
PMR For Gas Compressors | BK-GCS-PEDCO-120-ME-MR-0001 | BK-GCS-PEDCO-120-ME-MR-0001PMR For Gas Compressors | 2021-11-28 | 2022-02-13
TBE For Gas Compressors | BK-GCS-PEDCO-120-ME-TB-0001 | BK-GCS-PEDCO-120-ME-TB-0001TBE For Gas Compressors | 2022-02-02 | 2022-03-05
PMR For Gas Dehydration Package | BK-GCS-PEDCO-120-ME-MR-0002 | BK-GCS-PEDCO-120-ME-MR-0002PMR For Gas Dehydration Package | 2021-12-19 | 2022-01-26
TBE For Gas Dehydration Package | BK-GCS-PEDCO-120-ME-TB-0002 | BK-GCS-PEDCO-120-ME-TB-0002TBE For Gas Dehydration Package | 2022-03-28 | 2022-03-28
PMR For Pressure Vessels | BK-GCS-PEDCO-120-ME-MR-0003 | BK-GCS-PEDCO-120-ME-MR-0003PMR For Pressure Vessels | 2022-02-22 | 2022-02-22
TBE For Pressure Vessels | BK-GCS-PEDCO-120-ME-TB-0003 | BK-GCS-PEDCO-120-ME-TB-0003TBE For Pressure Vessels |  | 2022-05-25
PMR For Gas Air Coolers | BK-GCS-PEDCO-120-ME-MR-0004 | BK-GCS-PEDCO-120-ME-MR-0004PMR For Gas Air Coolers | 2022-02-19 | 2022-02-19
TBE For Gas Air Coolers | BK-GCS-PEDCO-120-ME-TB-0004 | BK-GCS-PEDCO-120-ME-TB-0004TBE For Gas Air Coolers |  | 2022-05-25
PMR For Storage Tanks | BK-GCS-PEDCO-120-ME-MR-0005 | BK-GCS-PEDCO-120-ME-MR-0005PMR For Storage Tanks | 2022-02-07 | 2022-02-07
TBE For Storage Tanks | BK-GCS-PEDCO-120-ME-TB-0005 | BK-GCS-PEDCO-120-ME-TB-0005TBE For Storage Tanks |  | 2022-05-25
PMR For Instrument/Plant Air & Nitrogen Packages | BK-GCS-PEDCO-120-ME-MR-0006 | BK-GCS-PEDCO-120-ME-MR-0006PMR For Instrument/Plant Air & Nitrogen Packages |  | 2022-05-25
TBE For Instrument/Plant Air & Nitrogen Packages | BK-GCS-PEDCO-120-ME-TB-0006 | BK-GCS-PEDCO-120-ME-TB-0006TBE For Instrument/Plant Air & Nitrogen Packages |  | 2022-05-25
PMR For Chemical Injection Packages | BK-GCS-PEDCO-120-ME-MR-0008 | BK-GCS-PEDCO-120-ME-MR-0008PMR For Chemical Injection Packages |  | 2022-05-25
TBE For Chemical Injection Packages | BK-GCS-PEDCO-120-ME-TB-0008 | BK-GCS-PEDCO-120-ME-TB-0008TBE For Chemical Injection Packages |  | 2022-05-25
PMR For Centrifugal Pumps For Process Services | BK-GCS-PEDCO-120-ME-MR-0009 | BK-GCS-PEDCO-120-ME-MR-0009PMR For Centrifugal Pumps For Process Services | 2022-02-13 | 2022-02-13
TBE For Centrifugal Pumps For Process Services | BK-GCS-PEDCO-120-ME-TB-0009 | BK-GCS-PEDCO-120-ME-TB-0009TBE For Centrifugal Pumps For Process Services |  | 2022-05-25
PMR For Centrifugal Pumps For General Services | BK-GCS-PEDCO-120-ME-MR-0010 | BK-GCS-PEDCO-120-ME-MR-0010PMR For Centrifugal Pumps For General Services | 2022-02-16 | 2022-02-16
TBE For Centrifugal Pumps For General Services | BK-GCS-PEDCO-120-ME-TB-0010 | BK-GCS-PEDCO-120-ME-TB-0010TBE For Centrifugal Pumps For General Services |  | 2022-05-25
PMR For Fire Water Pump | BK-GCS-PEDCO-120-ME-MR-0011 | BK-GCS-PEDCO-120-ME-MR-0011PMR For Fire Water Pump | 2022-02-19 | 2022-02-19
TBE For Fire Water Pump | BK-GCS-PEDCO-120-ME-TB-0011 | BK-GCS-PEDCO-120-ME-TB-0011TBE For Fire Water Pump |  | 2022-05-25
PMR For Flare Packages | BK-GCS-PEDCO-120-ME-MR-0012 | BK-GCS-PEDCO-120-ME-MR-0012PMR For Flare Packages |  | 2022-05-25
TBE For Flare Packages | BK-GCS-PEDCO-120-ME-TB-0012 | BK-GCS-PEDCO-120-ME-TB-0012TBE For Flare Packages |  | 2022-05-25
PMR For Overhead Travelling Cranes | BK-GCS-PEDCO-120-ME-MR-0013 | BK-GCS-PEDCO-120-ME-MR-0013PMR For Overhead Travelling Cranes |  | 2022-05-25
TBE For Overhead Travelling Cranes | BK-GCS-PEDCO-120-ME-TB-0013 | BK-GCS-PEDCO-120-ME-TB-0013TBE For Overhead Travelling Cranes |  | 2022-05-25
PMR For Main HVAC Equipment | BK-GCS-PEDCO-120-HV-MR-0001 | BK-GCS-PEDCO-120-HV-MR-0001PMR For Main HVAC Equipment |  | 2022-05-25
TBE For Main HVAC Equipment | BK-GCS-PEDCO-120-HV-TB-0001 | BK-GCS-PEDCO-120-HV-TB-0001TBE For Main HVAC Equipment |  | 2022-05-25
PMR For Pipes | BK-GCS-PEDCO-120-PI-MR-0001 | BK-GCS-PEDCO-120-PI-MR-0001PMR For Pipes |  | 2022-05-25
TBE For Pipes | BK-GCS-PEDCO-120-PI-TB-0001 | BK-GCS-PEDCO-120-PI-TB-0001TBE For Pipes |  | 2022-05-25
PMR For Fittings | BK-GCS-PEDCO-120-PI-MR-0002 | BK-GCS-PEDCO-120-PI-MR-0002PMR For Fittings |  | 2022-05-25
TBE For Fitting | BK-GCS-PEDCO-120-PI-TB-0002 | BK-GCS-PEDCO-120-PI-TB-0002TBE For Fitting |  | 2022-05-25
PMR For Flanges | BK-GCS-PEDCO-120-PI-MR-0003 | BK-GCS-PEDCO-120-PI-MR-0003PMR For Flanges |  | 2022-05-25
TBE For Flanges | BK-GCS-PEDCO-120-PI-TB-0003 | BK-GCS-PEDCO-120-PI-TB-0003TBE For Flanges |  | 2022-05-25
PMR For Manual Valves | BK-GCS-PEDCO-120-PI-MR-0004 | BK-GCS-PEDCO-120-PI-MR-0004PMR For Manual Valves |  | 2022-05-25
TBE For Manual Valves | BK-GCS-PEDCO-120-PI-TB-0004 | BK-GCS-PEDCO-120-PI-TB-0004TBE For Manual Valves |  | 2022-05-25
PMR For Gaskets | BK-GCS-PEDCO-120-PI-MR-0005 | BK-GCS-PEDCO-120-PI-MR-0005PMR For Gaskets |  | 2022-05-25
TBE For Gaskets | BK-GCS-PEDCO-120-PI-TB-0005 | BK-GCS-PEDCO-120-PI-TB-0005TBE For Gaskets |  | 2022-05-25
PMR For Bolt/Nuts | BK-GCS-PEDCO-120-PI-MR-0006 | BK-GCS-PEDCO-120-PI-MR-0006PMR For Bolt/Nuts |  | 2022-05-25
PMR For Bolt/Nuts | BK-GCS-PEDCO-120-PI-TB-0006 | BK-GCS-PEDCO-120-PI-TB-0006PMR For Bolt/Nuts |  | 2022-05-25
PMR For Insulation Joints | BK-GCS-PEDCO-120-PI-MR-0007 | BK-GCS-PEDCO-120-PI-MR-0007PMR For Insulation Joints |  | 2022-05-25
TBE For Insulation Joints | BK-GCS-PEDCO-120-PI-TB-0007 | BK-GCS-PEDCO-120-PI-TB-0007TBE For Insulation Joints |  | 2022-05-25
PMR For Strainers | BK-GCS-PEDCO-120-PI-MR-0008 | BK-GCS-PEDCO-120-PI-MR-0008PMR For Strainers |  | 2022-05-25
TBE For Strainers | BK-GCS-PEDCO-120-PI-TB-0008 | BK-GCS-PEDCO-120-PI-TB-0008TBE For Strainers |  | 2022-05-25
PMR For Special Pipe Supports | BK-GCS-PEDCO-120-PI-MR-0009 | BK-GCS-PEDCO-120-PI-MR-0009PMR For Special Pipe Supports |  | 2022-05-25
TBE For Special Pipe Supports | BK-GCS-PEDCO-120-PI-TB-0009 | BK-GCS-PEDCO-120-PI-TB-0009TBE For Special Pipe Supports |  | 2022-05-25
PMR For Insulation | BK-GCS-PEDCO-120-PI-MR-0010 | BK-GCS-PEDCO-120-PI-MR-0010PMR For Insulation |  | 2022-05-25
TBE For Insulation | BK-GCS-PEDCO-120-PI-TB-0010 | BK-GCS-PEDCO-120-PI-TB-0010TBE For Insulation |  | 2022-05-25
PMR For Painting | BK-GCS-PEDCO-120-PI-MR-0011 | BK-GCS-PEDCO-120-PI-MR-0011PMR For Painting |  | 2022-05-25
TBE For Painting | BK-GCS-PEDCO-120-PI-TB-0011 | BK-GCS-PEDCO-120-PI-TB-0011TBE For Painting |  | 2022-05-25
PMR For Coating of Underground Piping | BK-GCS-PEDCO-120-PI-MR-0012 | BK-GCS-PEDCO-120-PI-MR-0012PMR For Coating of Underground Piping |  | 2022-05-25
TBE For Coating of Underground Piping | BK-GCS-PEDCO-120-PI-TB-0012 | BK-GCS-PEDCO-120-PI-TB-0012TBE For Coating of Underground Piping |  | 2022-05-25
PMR For Control System/Console/Furniture | BK-GCS-PEDCO-120-IN-MR-0001 | BK-GCS-PEDCO-120-IN-MR-0001PMR For Control System/Console/Furniture |  | 2022-05-25
TBE For Control System/Console/Furniture | BK-GCS-PEDCO-120-IN-TB-0001 | BK-GCS-PEDCO-120-IN-TB-0001TBE For Control System/Console/Furniture |  | 2022-05-25
PMR For ESD System | BK-GCS-PEDCO-120-IN-MR-0002 | BK-GCS-PEDCO-120-IN-MR-0002PMR For ESD System |  | 2022-05-25
TBE For ESD System | BK-GCS-PEDCO-120-IN-TB-0002 | BK-GCS-PEDCO-120-IN-TB-0002TBE For ESD System |  | 2022-05-25
PMR For F&G System | BK-GCS-PEDCO-120-IN-MR-0003 | BK-GCS-PEDCO-120-IN-MR-0003PMR For F&G System |  | 2022-05-25
TBE For F&G System | BK-GCS-PEDCO-120-IN-TB-0003 | BK-GCS-PEDCO-120-IN-TB-0003TBE For F&G System |  | 2022-05-25
PMR For On/off & Shutdown Valves | BK-GCS-PEDCO-120-IN-MR-0004 | BK-GCS-PEDCO-120-IN-MR-0004PMR For On/off & Shutdown Valves |  | 2022-05-25
TBE For On/off & Shutdown Valves | BK-GCS-PEDCO-120-IN-TB-0004 | BK-GCS-PEDCO-120-IN-TB-0004TBE For On/off & Shutdown Valves |  | 2022-05-25
PMR For Control Valves | BK-GCS-PEDCO-120-IN-MR-0005 | BK-GCS-PEDCO-120-IN-MR-0005PMR For Control Valves |  | 2022-05-25
TBE For Control Valves | BK-GCS-PEDCO-120-IN-TB-0005 | BK-GCS-PEDCO-120-IN-TB-0005TBE For Control Valves |  | 2022-05-25
PMR For Pressure Safety Valves (PSV) | BK-GCS-PEDCO-120-IN-MR-0006 | BK-GCS-PEDCO-120-IN-MR-0006PMR For Pressure Safety Valves (PSV) |  | 2022-05-25
TBE For Pressure Safety Valves (PSV) | BK-GCS-PEDCO-120-IN-TB-0006 | BK-GCS-PEDCO-120-IN-TB-0006TBE For Pressure Safety Valves (PSV) |  | 2022-05-25
PMR For F&G Devices | BK-GCS-PEDCO-120-IN-MR-0007 | BK-GCS-PEDCO-120-IN-MR-0007PMR For F&G Devices |  | 2022-05-25
TBE For F&G Devices | BK-GCS-PEDCO-120-IN-TB-0007 | BK-GCS-PEDCO-120-IN-TB-0007TBE For F&G Devices |  | 2022-05-25
PMR For Corrosion Probe/Coupon | BK-GCS-PEDCO-120-IN-MR-0008 | BK-GCS-PEDCO-120-IN-MR-0008PMR For Corrosion Probe/Coupon |  | 2022-05-25
TBE For Corrosion Probe/Coupon | BK-GCS-PEDCO-120-IN-TB-0008 | BK-GCS-PEDCO-120-IN-TB-0008TBE For Corrosion Probe/Coupon |  | 2022-05-25
PMR For Orifice and Restriction Orifice Plate | BK-GCS-PEDCO-120-IN-MR-0009 | BK-GCS-PEDCO-120-IN-MR-0009PMR For Orifice and Restriction Orifice Plate |  | 2022-05-25
TBE For Orifice and Restriction Orifice Plate | BK-GCS-PEDCO-120-IN-TB-0009 | BK-GCS-PEDCO-120-IN-TB-0009TBE For Orifice and Restriction Orifice Plate |  | 2022-05-25
PMR For Differential Pressure/Pressure Gauge | BK-GCS-PEDCO-120-IN-MR-0010 | BK-GCS-PEDCO-120-IN-MR-0010PMR For Differential Pressure/Pressure Gauge |  | 2022-05-25
TBE For Differential Pressure/Pressure Gauge | BK-GCS-PEDCO-120-IN-TB-0010 | BK-GCS-PEDCO-120-IN-TB-0010TBE For Differential Pressure/Pressure Gauge |  | 2022-05-25
PMR For DP Flow /DP Level /Pressure/Diff. Pressure Transmitter | BK-GCS-PEDCO-120-IN-MR-0011 | BK-GCS-PEDCO-120-IN-MR-0011PMR For DP Flow /DP Level /Pressure/Diff. Pressure Transmitter |  | 2022-05-25
TBE For DP Flow /DP Level /Pressure/Diff. Pressure Transmitter" | BK-GCS-PEDCO-120-IN-TB-0011 | BK-GCS-PEDCO-120-IN-TB-0011TBE For DP Flow /DP Level /Pressure/Diff. Pressure Transmitter" |  | 2022-05-25
PMR For Pressure/ Differential Pressure Switch | BK-GCS-PEDCO-120-IN-MR-0012 | BK-GCS-PEDCO-120-IN-MR-0012PMR For Pressure/ Differential Pressure Switch |  | 2022-05-25
TBE For Pressure/ Differential Pressure Switch | BK-GCS-PEDCO-120-IN-TB-0012 | BK-GCS-PEDCO-120-IN-TB-0012TBE For Pressure/ Differential Pressure Switch |  | 2022-05-25
PMR For Temperature Gauge | BK-GCS-PEDCO-120-IN-MR-0013 | BK-GCS-PEDCO-120-IN-MR-0013PMR For Temperature Gauge |  | 2022-05-25
TBE For Temperature Gauge | BK-GCS-PEDCO-120-IN-TB-0013 | BK-GCS-PEDCO-120-IN-TB-0013TBE For Temperature Gauge |  | 2022-05-25
PMR For Temperature Transmitter/Switch | BK-GCS-PEDCO-120-IN-MR-0014 | BK-GCS-PEDCO-120-IN-MR-0014PMR For Temperature Transmitter/Switch |  | 2022-05-25
TBE For Temperature Transmitter/Switch | BK-GCS-PEDCO-120-IN-TB-0014 | BK-GCS-PEDCO-120-IN-TB-0014TBE For Temperature Transmitter/Switch |  | 2022-05-25
PMR For Level Gauge | BK-GCS-PEDCO-120-IN-MR-0015 | BK-GCS-PEDCO-120-IN-MR-0015PMR For Level Gauge |  | 2022-05-25
TBE For Level Gauge | BK-GCS-PEDCO-120-IN-TB-0015 | BK-GCS-PEDCO-120-IN-TB-0015TBE For Level Gauge |  | 2022-05-25
PMR For Level Switch | BK-GCS-PEDCO-120-IN-MR-0016 | BK-GCS-PEDCO-120-IN-MR-0016PMR For Level Switch |  | 2022-05-25
TBE For Level Switch | BK-GCS-PEDCO-120-IN-TB-0016 | BK-GCS-PEDCO-120-IN-TB-0016TBE For Level Switch |  | 2022-05-25
PMR For Displacer Level Transmitter | BK-GCS-PEDCO-120-IN-MR-0017 | BK-GCS-PEDCO-120-IN-MR-0017PMR For Displacer Level Transmitter |  | 2022-05-25
TBE For Displacer Level Transmitter | BK-GCS-PEDCO-120-IN-TB-0017 | BK-GCS-PEDCO-120-IN-TB-0017TBE For Displacer Level Transmitter |  | 2022-05-25
PMR For Rotameter | BK-GCS-PEDCO-120-IN-MR-0019 | BK-GCS-PEDCO-120-IN-MR-0019PMR For Rotameter |  | 2022-05-25
TBE For Rotameter | BK-GCS-PEDCO-120-IN-TB-0019 | BK-GCS-PEDCO-120-IN-TB-0019TBE For Rotameter |  | 2022-05-25
PMR For Instrument/F&G cable | BK-GCS-PEDCO-120-IN-MR-0020 | BK-GCS-PEDCO-120-IN-MR-0020PMR For Instrument/F&G cable |  | 2022-05-25
TBE For Instrument/F&G cable | BK-GCS-PEDCO-120-IN-TB-0020 | BK-GCS-PEDCO-120-IN-TB-0020TBE For Instrument/F&G cable |  | 2022-05-25
PMR For Instrument Cable Tray | BK-GCS-PEDCO-120-IN-MR-0021 | BK-GCS-PEDCO-120-IN-MR-0021PMR For Instrument Cable Tray |  | 2022-05-25
TBE For Instrument Cable Tray | BK-GCS-PEDCO-120-IN-TB-0021 | BK-GCS-PEDCO-120-IN-TB-0021TBE For Instrument Cable Tray |  | 2022-05-25
PMR For Instrument/F&G Junction box and Gland | BK-GCS-PEDCO-120-IN-MR-0022 | BK-GCS-PEDCO-120-IN-MR-0022PMR For Instrument/F&G Junction box and Gland |  | 2022-05-25
TBE For Instrument/F&G Junction box and Gland | BK-GCS-PEDCO-120-IN-TB-0022 | BK-GCS-PEDCO-120-IN-TB-0022TBE For Instrument/F&G Junction box and Gland |  | 2022-05-25
PMR For Instrument Tube and Fitting | BK-GCS-PEDCO-120-IN-MR-0023 | BK-GCS-PEDCO-120-IN-MR-0023PMR For Instrument Tube and Fitting |  | 2022-05-25
TBE For Instrument Tube and Fitting | BK-GCS-PEDCO-120-IN-TB-0023 | BK-GCS-PEDCO-120-IN-TB-0023TBE For Instrument Tube and Fitting |  | 2022-05-25
PMR For Instrument Installation Accessories | BK-GCS-PEDCO-120-IN-MR-0024 | BK-GCS-PEDCO-120-IN-MR-0024PMR For Instrument Installation Accessories |  | 2022-05-25
TBE For Instrument Installation Accessories | BK-GCS-PEDCO-120-IN-TB-0024 | BK-GCS-PEDCO-120-IN-TB-0024TBE For Instrument Installation Accessories |  | 2022-05-25
PMR For CCTV System | BK-GCS-PEDCO-120-IN-MR-0025 | BK-GCS-PEDCO-120-IN-MR-0025PMR For CCTV System | 2021-12-20 | 2022-02-12
TBE For CCTV System | BK-GCS-PEDCO-120-IN-TB-0025 | BK-GCS-PEDCO-120-IN-TB-0025TBE For CCTV System | 2022-05-02 | 2022-05-02
PMR For IRP Panel | BK-GCS-PEDCO-120-IN-MR-0026 | BK-GCS-PEDCO-120-IN-MR-0026PMR For IRP Panel |  | 2022-05-25
TBE For IRP Panel | BK-GCS-PEDCO-120-IN-TB-0026 | BK-GCS-PEDCO-120-IN-TB-0026TBE For IRP Panel |  | 2022-05-25
PMR For Total Flooding System | BK-GCS-PEDCO-120-SA-MR-0001 | BK-GCS-PEDCO-120-SA-MR-0001PMR For Total Flooding System | 2022-05-14 | 2022-05-14
TBE For Total Flooding System | BK-GCS-PEDCO-120-SA-TB-0001 | BK-GCS-PEDCO-120-SA-TB-0001TBE For Total Flooding System |  | 2022-05-25
PMR For Deluge Valve & Water Spray | BK-GCS-PEDCO-120-SA-MR-0002 | BK-GCS-PEDCO-120-SA-MR-0002PMR For Deluge Valve & Water Spray |  | 2022-05-25
TBE For Deluge Valve & Water Spray | BK-GCS-PEDCO-120-SA-TB-0002 | BK-GCS-PEDCO-120-SA-TB-0002TBE For Deluge Valve & Water Spray |  | 2022-05-25
PMR For Safety Equipment | BK-GCS-PEDCO-120-SA-MR-0003 | BK-GCS-PEDCO-120-SA-MR-0003PMR For Safety Equipment |  | 2022-05-25
TBE For Safety Equipment | BK-GCS-PEDCO-120-SA-TB-0003 | BK-GCS-PEDCO-120-SA-TB-0003TBE For Safety Equipment |  | 2022-05-25
PMR For Fire Fighting Equipment | BK-GCS-PEDCO-120-SA-MR-0004 | BK-GCS-PEDCO-120-SA-MR-0004PMR For Fire Fighting Equipment |  | 2022-05-25
TBE For Fire Fighting Equipment | BK-GCS-PEDCO-120-SA-TB-0004 | BK-GCS-PEDCO-120-SA-TB-0004TBE For Fire Fighting Equipment |  | 2022-05-25
PMR For Safety Signs | BK-GCS-PEDCO-120-SA-MR-0005 | BK-GCS-PEDCO-120-SA-MR-0005PMR For Safety Signs |  | 2022-05-25
TBE For Safety Signs | BK-GCS-PEDCO-120-SA-TB-0005 | BK-GCS-PEDCO-120-SA-TB-0005TBE For Safety Signs |  | 2022-05-25
PMR For Transformers | BK-GCS-PEDCO-120-EL-MR-0001 | BK-GCS-PEDCO-120-EL-MR-0001PMR For Transformers |  | 2022-05-25
TBE For Transformers | BK-GCS-PEDCO-120-EL-TB-0001 | BK-GCS-PEDCO-120-EL-TB-0001TBE For Transformers |  | 2022-05-25
PMR For LV Switchgear, MCC | BK-GCS-PEDCO-120-EL-MR-0002 | BK-GCS-PEDCO-120-EL-MR-0002PMR For LV Switchgear, MCC |  | 2022-05-25
TBE For LV Switchgear, MCC | BK-GCS-PEDCO-120-EL-TB-0002 | BK-GCS-PEDCO-120-EL-TB-0002TBE For LV Switchgear, MCC |  | 2022-05-25
PMR For Existent MV Switchgear Expansion & RCP | BK-GCS-PEDCO-120-EL-MR-0003 | BK-GCS-PEDCO-120-EL-MR-0003PMR For Existent MV Switchgear Expansion & RCP |  | 2022-05-25
TBE For Existent MV Switchgear Expansion & RCP | BK-GCS-PEDCO-120-EL-TB-0003 | BK-GCS-PEDCO-120-EL-TB-0003TBE For Existent MV Switchgear Expansion & RCP |  | 2022-05-25
PMR For Emergency Diesel Generator | BK-GCS-PEDCO-120-EL-MR-0004 | BK-GCS-PEDCO-120-EL-MR-0004PMR For Emergency Diesel Generator |  | 2022-05-25
TBE For Emergency Diesel Generator | BK-GCS-PEDCO-120-EL-TB-0004 | BK-GCS-PEDCO-120-EL-TB-0004TBE For Emergency Diesel Generator |  | 2022-05-25
PMR For UPS System | BK-GCS-PEDCO-120-EL-MR-0005 | BK-GCS-PEDCO-120-EL-MR-0005PMR For UPS System |  | 2022-05-25
TBE For UPS System | BK-GCS-PEDCO-120-EL-TB-0005 | BK-GCS-PEDCO-120-EL-TB-0005TBE For UPS System |  | 2022-05-25
PMR For DC Charger | BK-GCS-PEDCO-120-EL-MR-0006 | BK-GCS-PEDCO-120-EL-MR-0006PMR For DC Charger |  | 2022-05-25
TBE For DC Charger | BK-GCS-PEDCO-120-EL-TB-0006 | BK-GCS-PEDCO-120-EL-TB-0006TBE For DC Charger |  | 2022-05-25
PMR For Lighting & Distribution Panels | BK-GCS-PEDCO-120-EL-MR-0007 | BK-GCS-PEDCO-120-EL-MR-0007PMR For Lighting & Distribution Panels |  | 2022-05-25
TBE For Lighting & Distribution Panels | BK-GCS-PEDCO-120-EL-TB-0007 | BK-GCS-PEDCO-120-EL-TB-0007TBE For Lighting & Distribution Panels |  | 2022-05-25
PMR For Lighting and Small Power Equipment | BK-GCS-PEDCO-120-EL-MR-0008 | BK-GCS-PEDCO-120-EL-MR-0008PMR For Lighting and Small Power Equipment |  | 2022-05-25
TBE For Lighting and Small Power Equipment | BK-GCS-PEDCO-120-EL-TB-0008 | BK-GCS-PEDCO-120-EL-TB-0008TBE For Lighting and Small Power Equipment |  | 2022-05-25
PMR For Earthing & Lightning System | BK-GCS-PEDCO-120-EL-MR-0009 | BK-GCS-PEDCO-120-EL-MR-0009PMR For Earthing & Lightning System |  | 2022-05-25
TBE For Earthing & Lightning System | BK-GCS-PEDCO-120-EL-TB-0009 | BK-GCS-PEDCO-120-EL-TB-0009TBE For Earthing & Lightning System |  | 2022-05-25
PMR For Local Control Station (LCS) | BK-GCS-PEDCO-120-EL-MR-0010 | BK-GCS-PEDCO-120-EL-MR-0010PMR For Local Control Station (LCS) |  | 2022-05-25
TBE For Local Control Station (LCS) | BK-GCS-PEDCO-120-EL-TB-0010 | BK-GCS-PEDCO-120-EL-TB-0010TBE For Local Control Station (LCS) |  | 2022-05-25
PMR For Capacitor Bank | BK-GCS-PEDCO-120-EL-MR-0011 | BK-GCS-PEDCO-120-EL-MR-0011PMR For Capacitor Bank |  | 2022-05-25
TBE For Capacitor Bank | BK-GCS-PEDCO-120-EL-TB-0011 | BK-GCS-PEDCO-120-EL-TB-0011TBE For Capacitor Bank |  | 2022-05-25
PMR For NGR | BK-GCS-PEDCO-120-EL-MR-0012 | BK-GCS-PEDCO-120-EL-MR-0012PMR For NGR |  | 2022-05-25
TBE For NGR | BK-GCS-PEDCO-120-EL-TB-0012 | BK-GCS-PEDCO-120-EL-TB-0012TBE For NGR |  | 2022-05-25
PMR For Cathodic Protection System | BK-GCS-PEDCO-120-EL-MR-0013 | BK-GCS-PEDCO-120-EL-MR-0013PMR For Cathodic Protection System |  | 2022-05-25
TBE For Cathodic Protection System | BK-GCS-PEDCO-120-EL-TB-0013 | BK-GCS-PEDCO-120-EL-TB-0013TBE For Cathodic Protection System |  | 2022-05-25
PMR For Power & Control Cables | BK-GCS-PEDCO-120-EL-MR-0014 | BK-GCS-PEDCO-120-EL-MR-0014PMR For Power & Control Cables |  | 2022-05-25
TBE For Power & Control Cables | BK-GCS-PEDCO-120-EL-TB-0014 | BK-GCS-PEDCO-120-EL-TB-0014TBE For Power & Control Cables |  | 2022-05-25
PMR For Tray/Ladder and Accessories | BK-GCS-PEDCO-120-EL-MR-0015 | BK-GCS-PEDCO-120-EL-MR-0015PMR For Tray/Ladder and Accessories |  | 2022-05-25
TBE For Tray/Ladder and Accessories | BK-GCS-PEDCO-120-EL-TB-0015 | BK-GCS-PEDCO-120-EL-TB-0015TBE For Tray/Ladder and Accessories |  | 2022-05-25
PMR For Electrical Bulk Items | BK-GCS-PEDCO-120-EL-MR-0016 | BK-GCS-PEDCO-120-EL-MR-0016PMR For Electrical Bulk Items |  | 2022-05-25
TBE For Electrical Bulk Items | BK-GCS-PEDCO-120-EL-TB-0016 | BK-GCS-PEDCO-120-EL-TB-0016TBE For Electrical Bulk Items |  | 2022-05-25
PMR For UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-MR-0017 | BK-GCS-PEDCO-120-EL-MR-0017PMR For UPS of CCTV in Desalting, Production & CS Unit |  | 2022-05-25
TBE for UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-TB-0017 | BK-GCS-PEDCO-120-EL-TB-0017TBE for UPS of CCTV in Desalting, Production & CS Unit |  | 2022-05-25
PMR For CCTV System | BK-GCS-PEDCO-120-TE-MR-0001 | BK-GCS-PEDCO-120-TE-MR-0001PMR For CCTV System
TBE For CCTV System | BK-GCS-PEDCO-120-TE-TB-0001 | BK-GCS-PEDCO-120-TE-TB-0001TBE For CCTV System
PMR For PAGA System | BK-GCS-PEDCO-120-TE-MR-0002 | BK-GCS-PEDCO-120-TE-MR-0002PMR For PAGA System |  | 2022-05-25
TBE For PAGA System | BK-GCS-PEDCO-120-TE-TB-0002 | BK-GCS-PEDCO-120-TE-TB-0002TBE For PAGA System |  | 2022-05-25
PMR For PABX System | BK-GCS-PEDCO-120-TE-MR-0003 | BK-GCS-PEDCO-120-TE-MR-0003PMR For PABX System |  | 2022-05-25
TBE For PABX System | BK-GCS-PEDCO-120-TE-TB-0003 | BK-GCS-PEDCO-120-TE-TB-0003TBE For PABX System |  | 2022-05-25
PMR For Radio System | BK-GCS-PEDCO-120-TE-MR-0004 | BK-GCS-PEDCO-120-TE-MR-0004PMR For Radio System | 2021-12-20 | 2022-02-12
TBE For Radio System | BK-GCS-PEDCO-120-TE-TB-0004 | BK-GCS-PEDCO-120-TE-TB-0004TBE For Radio System |  | 2022-05-25
PMR For Telecomm. Cable | BK-GCS-PEDCO-120-TE-MR-0005 | BK-GCS-PEDCO-120-TE-MR-0005PMR For Telecomm. Cable |  | 2022-05-25
TBE For Telecomm. Cable | BK-GCS-PEDCO-120-TE-TB-0005 | BK-GCS-PEDCO-120-TE-TB-0005TBE For Telecomm. Cable |  | 2022-05-25
PMR For Telecommunication Tower | BK-GCS-PEDCO-120-TE-MR-0006 | BK-GCS-PEDCO-120-TE-MR-0006PMR For Telecommunication Tower |  | 2022-05-25
TBE For Telecommunication Tower | BK-GCS-PEDCO-120-TE-TB-0006 | BK-GCS-PEDCO-120-TE-TB-0006TBE For Telecommunication Tower |  | 2022-05-25
PMR For Steel Structure Items | BK-GCS-PEDCO-120-ST-MR-0001 | BK-GCS-PEDCO-120-ST-MR-0001PMR For Steel Structure Items |  | 2022-05-25
TBE For Steel Structure Items | BK-GCS-PEDCO-120-ST-TB-0001 | BK-GCS-PEDCO-120-ST-TB-0001TBE For Steel Structure Items |  | 2022-05-25
PMR For Anchor Bolts | BK-GCS-PEDCO-120-ST-MR-0002 | BK-GCS-PEDCO-120-ST-MR-0002PMR For Anchor Bolts |  | 2022-05-25
TBE For Anchor Bolts | BK-GCS-PEDCO-120-ST-TB-0002 | BK-GCS-PEDCO-120-ST-TB-0002TBE For Anchor Bolts |  | 2022-05-25
PMR For Blast Proof Doors | BK-GCS-PEDCO-120-ST-MR-0003 | BK-GCS-PEDCO-120-ST-MR-0003PMR For Blast Proof Doors |  | 2022-05-25
TBE For Blast Proof Doors | BK-GCS-PEDCO-120-ST-TB-0003 | BK-GCS-PEDCO-120-ST-TB-0003TBE For Blast Proof Doors |  | 2022-05-25
Pre-Commissioning, Commissioning & Startup Procedure | BK-GCS-PEDCO-120-CO-PR-0001 | BK-GCS-PEDCO-120-CO-PR-0001Pre-Commissioning, Commissioning & Startup Procedure |  | 2022-05-25
Technical/Site Queries | BK-GCS-PEDCO-120-GE-TQ-0001 | BK-GCS-PEDCO-120-GE-TQ-0001Technical/Site Queries |  | 2022-05-25
As-Built Document Booklets | BK-GCS-PEDCO-120-GE-DO-0001 | BK-GCS-PEDCO-120-GE-DO-0001As-Built Document Booklets |  | 2022-05-25
Operating Manual | BK-GCS-PEDCO-120-GE-ML-0001 | BK-GCS-PEDCO-120-GE-ML-0001Operating Manual |  | 2022-05-25
As-Built Document Booklets | BK-GCS-PEDCO-120-GE-DO-0001 | BK-GCS-PEDCO-120-GE-DO-0001As-Built Document Booklets
Final Engineering Dossier | BK-GCS-PEDCO-120-GE-DO-0002 | BK-GCS-PEDCO-120-GE-DO-0002Final Engineering Dossier |  | 2022-05-25

## 5
|  | جدول شماره 5 : لیست فعالیت هاي اصلی و بحرانی پروژه متاثر از علل تاخيرات | [12 empty] | 2022-05-25 |  | 1 |  |  |  | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24
 | time axis 2021-06-01 to 2023-06-22 12:00
شماره (ID A s) | نام بسته كاري | فاز | برنامه/واقعي | نام فعالیت اصلی | دوره طبق برنامه مصوب |  |  |  | دوره اصلاح شده |  | درصد پیشرفت فیزیکی | دوره طبق واقعیت | time axis 2021-06-01 to 2023-06-22 12:00
[5 empty] | مدت (روز) | شروع | پايان | شناوري | شروع اصلاح شده | پایان اصلاح شده |  | مدت (روز) | شروع | پايان |  | 2021-07-01: شش ماهه اول سال اول; 2021-12-31 09:36: شش ماهه دوم سال اول; 2022-06-30 07:12: شش ماهه اول سال دوم; 2022-12-29 16:48: شش ماهه دوم سال دوم
P12-EPC-E1000 | ايستگاه گاز | E | P | Endorsement Report For Basic Design & Scope of Work | 29 | 2021-06-23 | 2021-07-22 | 0 | 2021-06-23 | 2021-07-22 | 100% | 50 | 2021-07-31 | 2021-09-19 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E1000 | ايستگاه گاز | E | A | Endorsement Report For Basic Design & Scope of Work | 50 | 2021-07-31 | 2021-09-19 | 0 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E1570 | ايستگاه گاز | E | P | Process Flow Diagram (PFD) | 53 | 2021-07-04 | 2021-08-26 | 0 | 2021-07-04 | 2021-08-26 | 80% | 284 | 2021-08-14 | 2022-05-25 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E1570 | ايستگاه گاز | E | A | Process Flow Diagram (PFD) | 284 | 2021-08-14 | 2022-05-25 | 0 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E1540 | ايستگاه گاز | E | P | Process Data Sheets For Gas Compressors Packages | 43 | 2021-07-31 | 2021-09-12 | 0 | 2021-07-31 | 2021-09-12 | 60% | 199 | 2021-11-07 | 2022-05-25 |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E1540 | ايستگاه گاز | E | A | Process Data Sheets For Gas Compressors Packages | 199 | 2021-11-07 | 2022-05-25 | 0 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E2480 | ايستگاه گاز | E | P | Mechanical Data Sheets For Gas Compressors Packages | 48 | 2021-08-12 | 2021-09-29 | 0 | 2021-08-12 | 2021-09-29 | 80% | 238 | 2021-09-12 | 2022-05-08 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E2480 | ايستگاه گاز | E | A | Mechanical Data Sheets For Gas Compressors Packages | 238 | 2021-09-12 | 2022-05-08 | 0 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E7980 | ايستگاه گاز | E | P | TBE For Gas Compressors | 44 | 2021-08-16 | 2021-09-29 | 0 | 2021-08-16 | 2021-09-29 | 0% | 31 | 2022-02-02 | 2022-03-05 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E7980 | ايستگاه گاز | E | A | TBE For Gas Compressors | 31 | 2022-02-02 | 2022-03-05 | 0 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E7970 | ايستگاه گاز | E | P | PMR For Gas Compressors | 10 | 2021-09-03 | 2021-09-13 | 0 | 2021-09-03 | 2021-09-13 | 100% | 77 | 2021-11-28 | 2022-02-13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-E7970 | ايستگاه گاز | E | A | PMR For Gas Compressors | 77 | 2021-11-28 | 2022-02-13 | 0 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-P1000 | ايستگاه گاز | P | P | Tendering & Selection For Gas Compressors | 59 | 2021-08-11 | 2021-10-09 | 0 | 2021-08-11 | 2021-10-09 | 0% | 18 | 2022-02-26 | 2022-03-16 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-P1000 | ايستگاه گاز | P | A | Tendering & Selection For Gas Compressors | 18 | 2022-02-26 | 2022-03-16 | 0 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-P1010 | ايستگاه گاز | P | P | Contract Effectiveness / PO For Gas Compressors | 29 | 2021-10-10 | 2021-11-08 | 0 | 2021-10-10 | 2021-11-08 | 0% |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-P1010 | ايستگاه گاز | P | A | Contract Effectiveness / PO For Gas Compressors |  | 0 | 0 | 0 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-P1020 | ايستگاه گاز | P | P | Manufacturing / Fabrication / Supply For Gas Compressors | 419 | 2021-11-09 | 2023-01-02 | 0 | 2021-11-09 | 2023-01-02 | 0% |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12-EPC-P1020 | ايستگاه گاز | P | A | Manufacturing / Fabrication / Supply For Gas Compressors |  | 0 | 0 | 0 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1060 | چاه شماره 18 | E | P | Process Flow Diagram - W018S | 44 | 2021-07-23 | 2021-09-05 | 39 | 2021-08-31 | 2021-10-14 | 60% | 294 | 2021-08-04 | 2022-05-25 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1060 | چاه شماره 18 | E | A | Process Flow Diagram - W018S | 294 | 2021-08-04 | 2022-05-25 | 39 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1370 | چاه شماره 18 | E | P | Plot Plan Drawing - W018S | 39 | 2021-07-23 | 2021-08-31 | 14 | 2021-08-06 | 2021-09-14 | 80% | 276 | 2021-08-22 | 2022-05-25 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1370 | چاه شماره 18 | E | A | Plot Plan Drawing - W018S | 276 | 2021-08-22 | 2022-05-25 | 14 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1860 | چاه شماره 18 | E | P | Specification For WHCP/HPU-W018S | 37 | 2021-07-23 | 2021-08-29 | 22 | 2021-08-14 | 2021-09-20 | 80% | 231 | 2021-08-08 | 2022-03-27 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1860 | چاه شماره 18 | E | A | Specification For WHCP/HPU-W018S | 231 | 2021-08-08 | 2022-03-27 | 22 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E2470 | چاه شماره 18 | E | P | Rough Grading Plans -W018S | 39 | 2021-07-28 | 2021-09-05 | 9 | 2021-08-06 | 2021-09-14 | 60% | 228 | 2021-07-28 | 2022-03-13 |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E2470 | چاه شماره 18 | E | A | Rough Grading Plans -W018S | 228 | 2021-07-28 | 2022-03-13 | 9 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1070 | چاه شماره 18 | E | P | P&ID - W018S | 44 | 2021-08-02 | 2021-09-15 | 39 | 2021-09-10 | 2021-10-24 | 80% | 289 | 2021-08-09 | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1070 | چاه شماره 18 | E | A | P&ID - W018S | 289 | 2021-08-09 | 2022-05-25 | 39 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1300 | چاه شماره 18 | E | P | Piping Material Specification-W018S | 29 | 2021-08-02 | 2021-08-31 | 153 | 2022-01-02 | 2022-01-31 | 100% | 113 | 2021-08-24 | 2021-12-15 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1300 | چاه شماره 18 | E | A | Piping Material Specification-W018S | 113 | 2021-08-24 | 2021-12-15 | 153 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1870 | چاه شماره 18 | E | P | Data Sheets For WHCP/HPU - Wellheads-W018S | 29 | 2021-08-02 | 2021-08-31 | 22 | 2021-08-24 | 2021-09-22 | 80% | 276 | 2021-08-22 | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1870 | چاه شماره 18 | E | A | Data Sheets For WHCP/HPU - Wellheads-W018S | 276 | 2021-08-22 | 2022-05-25 | 22 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E2460 | چاه شماره 18 | E | P | Civil and Structural drawings - W018S | 39 | 2021-08-07 | 2021-09-15 | 16 | 2021-08-23 | 2021-10-01 | 60% | 220 | 2021-07-28 | 2022-03-05 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E2460 | چاه شماره 18 | E | A | Civil and Structural drawings - W018S | 220 | 2021-07-28 | 2022-03-05 | 16 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E2450 | چاه شماره 18 | E | P | General Civil Layout - W018S | 19 | 2021-08-12 | 2021-08-31 | 14 | 2021-08-26 | 2021-09-14 | 100% | 152 | 2021-07-28 | 2021-12-27 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E2450 | چاه شماره 18 | E | A | General Civil Layout - W018S | 152 | 2021-07-28 | 2021-12-27 | 14 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1810 | چاه شماره 18 | E | P | Pipeline Corrosion Study & Material Selection Report-W018S | 43 | 2021-08-22 | 2021-10-04 | 192 | 2022-03-02 | 2022-04-14 | 0% | 210 | 2021-10-27 | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E1810 | چاه شماره 18 | E | A | Pipeline Corrosion Study & Material Selection Report-W018S | 210 | 2021-10-27 | 2022-05-25 | 192 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E3590 | چاه شماره 18 | E | P | PMR For WHCP/HPU - W018S | 6 | 2021-08-30 | 2021-09-05 | 22 | 2021-09-21 | 2021-09-27 | 100% | 62 | 2021-11-15 | 2022-01-16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E3590 | چاه شماره 18 | E | A | PMR For WHCP/HPU - W018S | 62 | 2021-11-15 | 2022-01-16 | 22 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E3560 | چاه شماره 18 | E | P | PMR For Line pipes - W018S | 4 | 2021-10-06 | 2021-10-10 | 40 | 2021-11-15 | 2021-11-19 | 100% | 9 | 2021-12-06 | 2021-12-15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-E3560 | چاه شماره 18 | E | A | PMR For Line pipes - W018S | 9 | 2021-12-06 | 2021-12-15 | 40 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1670 | چاه شماره 18 | P | P | Tendering & Selection- W018S-WHCP | 9 | 2021-09-23 | 2021-10-02 | 22 | 2021-10-15 | 2021-10-24 | 0% | 71 | 2022-03-15 | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1670 | چاه شماره 18 | P | A | Tendering & Selection- W018S-WHCP | 71 | 2022-03-15 | 2022-05-25 | 22 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1550 | چاه شماره 18 | P | P | Tendering & Selection- W018S- Line pipe | 6 | 2021-10-01 | 2021-10-07 | 26 | 2021-10-27 | 2021-11-02 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1550 | چاه شماره 18 | P | A | Tendering & Selection- W018S- Line pipe | 0 | 0 | 0 | 26 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1680 | چاه شماره 18 | P | P | Contract Effectiveness / PO- W018S- WHCP | 4 | 2021-10-03 | 2021-10-07 | 22 | 2021-10-25 | 2021-10-29 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1680 | چاه شماره 18 | P | A | Contract Effectiveness / PO- W018S- WHCP | 0 | 0 | 0 | 22 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1560 | چاه شماره 18 | P | P | Contract Effectiveness / PO- W018S-Line pipe | 4 | 2021-10-08 | 2021-10-12 | 26 | 2021-11-03 | 2021-11-07 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1560 | چاه شماره 18 | P | A | Contract Effectiveness / PO- W018S-Line pipe | 0 | 0 | 0 | 26 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1690 | چاه شماره 18 | P | P | Manufacturing / Fabrication / Supply- W018S-WHCP | 89 | 2021-10-08 | 2022-01-05 | 22 | 2021-10-30 | 2022-01-27 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1690 | چاه شماره 18 | P | A | Manufacturing / Fabrication / Supply- W018S-WHCP | 0 | 0 | 0 | 22 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1570 | چاه شماره 18 | P | P | Manufacturing / Fabrication / Supply- W018S-Line pipe | 69 | 2021-10-13 | 2021-12-21 | 26 | 2021-11-08 | 2022-01-16 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-P1570 | چاه شماره 18 | P | A | Manufacturing / Fabrication / Supply- W018S-Line pipe | 0 | 0 | 0 | 26 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-C1150 | چاه شماره 18 | C | P | Supply & Installation sealling Layer of Mud pit- W018S | 7 | 2021-09-20 | 2021-09-27 | 12 | 2021-10-02 | 2021-10-09 | 0% | 111 | 2021-08-20 | 2021-12-09 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-C1150 | چاه شماره 18 | C | A | Supply & Installation sealling Layer of Mud pit- W018S | 111 | 2021-08-20 | 2021-12-09 | 12 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-C1330 | چاه شماره 18 | C | P | Construction of Right of Way- W018S | 19 | 2021-10-09 | 2021-10-28 | 94 | 2022-01-11 | 2022-01-30 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-C1330 | چاه شماره 18 | C | A | Construction of Right of Way- W018S | 0 | 0 | 0 | 94 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-C1350 | چاه شماره 18 | C | P | Construction & Installation of Shelter for Wellhead Control Panel-W018S | 14 | 2021-12-20 | 2022-01-03 | 57 | 2022-02-15 | 2022-03-01 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P01-EPC-C1350 | چاه شماره 18 | C | A | Construction & Installation of Shelter for Wellhead Control Panel-W018S | 0 | 0 | 0 | 57 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1060 | چاه شماره 28 | E | P | Process Flow Diagram - W028 | 39 | 2021-07-23 | 2021-08-31 | 44 | 2021-09-05 | 2021-10-14 | 60% | 284 | 2021-08-14 | 2022-05-25 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1060 | چاه شماره 28 | E | A | Process Flow Diagram - W028 | 284 | 2021-08-14 | 2022-05-25 | 44 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1380 | چاه شماره 28 | E | P | Plot Plan Drawing - W028 | 29 | 2021-07-23 | 2021-08-21 | 44 | 2021-09-05 | 2021-10-04 | 0% | 112 | 2022-02-02 | 2022-05-25 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1380 | چاه شماره 28 | E | A | Plot Plan Drawing - W028 | 112 | 2022-02-02 | 2022-05-25 | 44 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1860 | چاه شماره 28 | E | P | Specification For WHCP/HPU - W028 | 37 | 2021-07-23 | 2021-08-29 | 197 | 2022-02-05 | 2022-03-14 | 80% | 231 | 2021-08-08 | 2022-03-27 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1860 | چاه شماره 28 | E | A | Specification For WHCP/HPU - W028 | 231 | 2021-08-08 | 2022-03-27 | 197 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E2460 | چاه شماره 28 | E | P | General Civil Layout -W028 | 24 | 2021-07-23 | 2021-08-16 | 0 | 2021-07-23 | 2021-08-16 | 60% | 218 | 2021-10-19 | 2022-05-25 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E2460 | چاه شماره 28 | E | A | General Civil Layout -W028 | 218 | 2021-10-19 | 2022-05-25 | 0 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E2470 | چاه شماره 28 | E | P | Civil and Structural drawings -W028 | 44 | 2021-07-23 | 2021-09-05 | 181 | 2022-01-20 | 2022-03-05 | 80% | 218 | 2021-10-19 | 2022-05-25 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E2470 | چاه شماره 28 | E | A | Civil and Structural drawings -W028 | 218 | 2021-10-19 | 2022-05-25 | 181 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E2480 | چاه شماره 28 | E | P | Rough Grading Plans -W028 | 24 | 2021-07-23 | 2021-08-16 | 0 | 2021-07-23 | 2021-08-16 | 60% | 181 | 2021-10-11 | 2022-04-10 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E2480 | چاه شماره 28 | E | A | Rough Grading Plans -W028 | 181 | 2021-10-11 | 2022-04-10 | 0 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E3530 | چاه شماره 28 | E | P | PMR For Line Pipes - W028 | 9 | 2021-07-30 | 2021-08-08 | 50 | 2021-09-18 | 2021-09-27 | 100% | 9 | 2021-12-06 | 2021-12-15 |  |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E3530 | چاه شماره 28 | E | A | PMR For Line Pipes - W028 | 9 | 2021-12-06 | 2021-12-15 | 50 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1070 | چاه شماره 28 | E | P | P&ID - W028 | 39 | 2021-08-02 | 2021-09-10 | 44 | 2021-09-15 | 2021-10-24 | 80% | 276 | 2021-08-22 | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1070 | چاه شماره 28 | E | A | P&ID - W028 | 276 | 2021-08-22 | 2022-05-25 | 44 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1880 | چاه شماره 28 | E | P | Data Sheets For WHCP/HPU - Wellheads - W028 | 48 | 2021-08-12 | 2021-09-29 | 197 | 2022-02-25 | 2022-04-14 | 80% | 276 | 2021-08-22 | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1880 | چاه شماره 28 | E | A | Data Sheets For WHCP/HPU - Wellheads - W028 | 276 | 2021-08-22 | 2022-05-25 | 197 |  |  | 80% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1820 | چاه شماره 28 | E | P | Pipeline Corrosion Study & Material Selection Report - W028 | 43 | 2021-08-22 | 2021-10-04 | 192 | 2022-03-02 | 2022-04-14 | 0% | 210 | 2021-10-27 | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1820 | چاه شماره 28 | E | A | Pipeline Corrosion Study & Material Selection Report - W028 | 210 | 2021-10-27 | 2022-05-25 | 192 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E3590 | چاه شماره 28 | E | P | PMR For WHCP/HPU - W028 | 9 | 2021-09-01 | 2021-09-10 | 45 | 2021-10-16 | 2021-10-25 | 100% | 62 | 2021-11-15 | 2022-01-16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E3590 | چاه شماره 28 | E | A | PMR For WHCP/HPU - W028 | 62 | 2021-11-15 | 2022-01-16 | 45 |  |  | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1180 | چاه شماره 28 | E | P | Piping Material Specification - W028 | 63 | 2021-10-22 | 2021-12-24 | 111 | 2022-02-10 | 2022-04-14 | 60% | 178 | 2021-11-28 | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-E1180 | چاه شماره 28 | E | A | Piping Material Specification - W028 | 178 | 2021-11-28 | 2022-05-25 | 111 |  |  | 60% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1550 | چاه شماره 28 | P | P | Tendering & Selection- W028 - Line pipe | 6 | 2021-08-19 | 2021-08-25 | 50 | 2021-10-08 | 2021-10-14 | 0% | 71 | 2022-03-15 | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1550 | چاه شماره 28 | P | A | Tendering & Selection- W028 - Line pipe | 71 | 2022-03-15 | 2022-05-25 | 50 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1560 | چاه شماره 28 | P | P | Contract Effectiveness / PO- W028 - Line pipe | 4 | 2021-08-26 | 2021-08-30 | 50 | 2021-10-15 | 2021-10-19 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1560 | چاه شماره 28 | P | A | Contract Effectiveness / PO- W028 - Line pipe | 0 | 0 | 0 | 50 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1570 | چاه شماره 28 | P | P | Manufacturing / Fabrication / Supply- W028 - Line pipe | 109 | 2021-08-31 | 2021-12-18 | 50 | 2021-10-20 | 2022-02-06 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1570 | چاه شماره 28 | P | A | Manufacturing / Fabrication / Supply- W028 - Line pipe | 0 | 0 | 0 | 50 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1670 | چاه شماره 28 | P | P | Tendering & Selection- W028 - WHCP | 9 | 2021-09-23 | 2021-10-02 | 45 | 2021-11-07 | 2021-11-16 | 0% | 71 | 2022-03-15 | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1670 | چاه شماره 28 | P | A | Tendering & Selection- W028 - WHCP | 71 | 2022-03-15 | 2022-05-25 | 45 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1680 | چاه شماره 28 | P | P | Contract Effectiveness / PO- W028 - WHCP | 4 | 2021-10-03 | 2021-10-07 | 45 | 2021-11-17 | 2021-11-21 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1680 | چاه شماره 28 | P | A | Contract Effectiveness / PO- W028 - WHCP | 0 | 0 | 0 | 45 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1690 | چاه شماره 28 | P | P | Manufacturing / Fabrication / Supply- W028 - WHCP | 89 | 2021-10-08 | 2022-01-05 | 45 | 2021-11-22 | 2022-02-19 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-P1690 | چاه شماره 28 | P | A | Manufacturing / Fabrication / Supply- W028 - WHCP | 0 | 0 | 0 | 45 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1170 | چاه شماره 28 | C | P | Site Preparation W028 | 19 | 2021-08-17 | 2021-09-05 | 0 | 2021-08-17 | 2021-09-05 | 53% | -44454 | 2021-09-15 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1170 | چاه شماره 28 | C | A | Site Preparation W028 | -44454 | 2021-09-15 | 0 | 0 |  |  | 53% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1440 | چاه شماره 28 | C | P | Construction of Right of Way - W028 | 14 | 2021-10-11 | 2021-10-25 | 131 | 2022-02-19 | 2022-03-05 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1440 | چاه شماره 28 | C | A | Construction of Right of Way - W028 | 0 | 0 | 0 | 131 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1240 | چاه شماره 28 | C | P | Excavation of Mud Channel- W028 | 6 | 2021-08-30 | 2021-09-05 | 25 | 2021-09-24 | 2021-09-30 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1240 | چاه شماره 28 | C | A | Excavation of Mud Channel- W028 | 0 | 0 | 0 | 25 |  |  | 0% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1310 | چاه شماره 28 | C | P | Installation sealling Layer of Mud Pit- W028 | 6 | 2021-08-29 | 2021-09-04 | 1900-02-05 | 2021-10-05 | 2021-10-11 | 0% | 25 | 2022-04-30 | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1310 | چاه شماره 28 | C | A | Installation sealling Layer of Mud Pit- W028 | 25 | 2022-04-30 | 2022-05-25 | 1900-02-05 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1460 | چاه شماره 28 | C | P | Construction & Installation of Shelter for Wellhead Control Panel- W028 | 4 | 2021-11-05 | 2021-11-09 | 1900-05-10 | 2022-03-16 | 2022-03-20 | 0% | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02-EPC-C1460 | چاه شماره 28 | C | A | Construction & Installation of Shelter for Wellhead Control Panel- W028 | 0 | 0 | 0 | 1900-05-10 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مهر امضا پيمانكار | [8 empty] | مهر امضاء كارفرما
Formulas:
شروع = IFERROR(VLOOKUP([شماره (ID A s)]&[برنامه/واقعي],Gas!$B:$I,7,0),"")
شروع = [شروع, row below]
پايان = IFERROR(VLOOKUP([شماره (ID A s)]&[برنامه/واقعي],Gas!$B:$I,8,0),"")
پايان = [پايان, row below]
دوره اصلاح شده = [شروع]+[شناوري]
پایان اصلاح شده = [دوره اصلاح شده]+[دوره طبق برنامه مصوب]
شناوري = VLOOKUP([شماره (ID A s)],'Well-28'!A:I,5,0)
درصد پیشرفت فیزیکی = VLOOKUP([شماره (ID A s)],'Well-28'!$A:$M,13,0)

## List of delay (hidden)
شماره (ID A s) | نام بسته كاري | فاز | برنامه/واقعي | نام فعالیت اصلی | دوره طبق برنامه مصوب |  |  |  | دوره اصلاح شده |  | درصد پیشرفت فیزیکی | دوره طبق واقعیت
[5 empty] | مدت (روز) | شروع | پايان | شناوري | شروع اصلاح شده | پایان اصلاح شده |  | مدت (روز) | شروع | پايان
P12-EPC-E1000 | ايستگاه گاز | E | A | Endorsement Report For Basic Design & Scope of Work | 50 | 2021-07-31 | 2021-09-19 | 0 |  |  | 100%
P12-EPC-E1570 | ايستگاه گاز | E | A | Process Flow Diagram (PFD) | 284 | 2021-08-14 | 2022-05-25 | 0 |  |  | 80%
P12-EPC-E1540 | ايستگاه گاز | E | A | Process Data Sheets For Gas Compressors Packages | 199 | 2021-11-07 | 2022-05-25 | 0 |  |  | 60%
P12-EPC-E2480 | ايستگاه گاز | E | A | Mechanical Data Sheets For Gas Compressors Packages | 238 | 2021-09-12 | 2022-05-08 | 0 |  |  | 80%
P12-EPC-E7980 | ايستگاه گاز | E | A | TBE For Gas Compressors | 31 | 2022-02-02 | 2022-03-05 | 0 |  |  | 0%
P12-EPC-E7970 | ايستگاه گاز | E | A | PMR For Gas Compressors | 77 | 2021-11-28 | 2022-02-13 | 0 |  |  | 100%
P12-EPC-P1000 | ايستگاه گاز | P | A | Tendering & Selection For Gas Compressors | #VALUE! |  |  | 0 |  |  | 0%
P12-EPC-P1010 | ايستگاه گاز | P | A | Contract Effectiveness / PO For Gas Compressors | #VALUE! |  |  | 0 |  |  | 0%
P12-EPC-P1020 | ايستگاه گاز | P | A | Manufacturing / Fabrication / Supply For Gas Compressors | #VALUE! |  |  | 0 |  |  | 0%
P01-EPC-E1060 | چاه شماره 18 | E | A | Process Flow Diagram - W018S | 294 | 2021-08-04 | 2022-05-25 | 39 |  |  | 60%
P01-EPC-E1370 | چاه شماره 18 | E | A | Plot Plan Drawing - W018S | 276 | 2021-08-22 | 2022-05-25 | 14 |  |  | 80%
P01-EPC-E1860 | چاه شماره 18 | E | A | Specification For WHCP/HPU-W018S | 231 | 2021-08-08 | 2022-03-27 | 22 |  |  | 80%
P01-EPC-E2470 | چاه شماره 18 | E | A | Rough Grading Plans -W018S | 228 | 2021-07-28 | 2022-03-13 | 9 |  |  | 60%
P01-EPC-E1070 | چاه شماره 18 | E | A | P&ID - W018S | 289 | 2021-08-09 | 2022-05-25 | 39 |  |  | 80%
P01-EPC-E1300 | چاه شماره 18 | E | A | Piping Material Specification-W018S | 113 | 2021-08-24 | 2021-12-15 | 153 |  |  | 100%
P01-EPC-E1870 | چاه شماره 18 | E | A | Data Sheets For WHCP/HPU - Wellheads-W018S | 276 | 2021-08-22 | 2022-05-25 | 22 |  |  | 80%
P01-EPC-E2460 | چاه شماره 18 | E | A | Civil and Structural drawings - W018S | 220 | 2021-07-28 | 2022-03-05 | 16 |  |  | 60%
P01-EPC-E2450 | چاه شماره 18 | E | A | General Civil Layout - W018S | 152 | 2021-07-28 | 2021-12-27 | 14 |  |  | 100%
P01-EPC-E1810 | چاه شماره 18 | E | A | Pipeline Corrosion Study & Material Selection Report-W018S | 210 | 2021-10-27 | 2022-05-25 | 192 |  |  | 0%
P01-EPC-E3590 | چاه شماره 18 | E | A | PMR For WHCP/HPU - W018S | 62 | 2021-11-15 | 2022-01-16 | 22 |  |  | 100%
P01-EPC-E3560 | چاه شماره 18 | E | A | PMR For Flowline Support - W018S | 0 |  |  | 26 |  |  | 100%
P01-EPC-P1670 | چاه شماره 18 | P | A | Tendering & Selection- W018S-WHCP | 0 |  |  | 22 |  |  | 0%
P01-EPC-P1550 | چاه شماره 18 | P | A | Tendering & Selection- W018S- Line pipe | 0 |  |  | 26 |  |  | 0%
P01-EPC-P1680 | چاه شماره 18 | P | A | Contract Effectiveness / PO- W018S- WHCP | 0 |  |  | 22 |  |  | 0%
P01-EPC-P1560 | چاه شماره 18 | P | A | Contract Effectiveness / PO- W018S-Line pipe | 0 |  |  | 26 |  |  | 0%
P01-EPC-P1690 | چاه شماره 18 | P | A | Manufacturing / Fabrication / Supply- W018S-WHCP | 0 |  |  | 22 |  |  | 0%
P01-EPC-P1570 | چاه شماره 18 | P | A | Manufacturing / Fabrication / Supply- W018S-Line pipe | 0 |  |  | 26 |  |  | 0%
P01-EPC-C1150 | چاه شماره 18 | C | A | Supply & Installation sealling Layer of Mud pit- W018S | 0 |  |  | 12 |  |  | 0%
P01-EPC-C1330 | چاه شماره 18 | C | A | Construction of Right of Way- W018S | 0 |  |  | 94 |  |  | 0%
P01-EPC-C1350 | چاه شماره 18 | C | A | Construction & Installation of Shelter for Wellhead Control Panel-W018S | 0 |  |  | 57 |  |  | 0%
P02-EPC-E1060 | چاه شماره 28 | E | A | Process Flow Diagram - W028 | 284 | 2021-08-14 | 2022-05-25 | 44 |  |  | 60%
P02-EPC-E1380 | چاه شماره 28 | E | A | Plot Plan Drawing - W028 | 112 | 2022-02-02 | 2022-05-25 | 44 |  |  | 0%
P02-EPC-E1860 | چاه شماره 28 | E | A | Specification For WHCP/HPU - W028 | 231 | 2021-08-08 | 2022-03-27 | 197 |  |  | 80%
P02-EPC-E2460 | چاه شماره 28 | E | A | General Civil Layout -W028 | 218 | 2021-10-19 | 2022-05-25 | 0 |  |  | 60%
P02-EPC-E2470 | چاه شماره 28 | E | A | Civil and Structural drawings -W028 | 218 | 2021-10-19 | 2022-05-25 | 181 |  |  | 80%
P02-EPC-E2480 | چاه شماره 28 | E | A | Rough Grading Plans -W028 | 181 | 2021-10-11 | 2022-04-10 | 0 |  |  | 60%
P02-EPC-E3530 | چاه شماره 28 | E | A | PMR For Line Pipes - W028 | 0 | 2021-12-06 | 2021-12-06 | 50 |  |  | 100%
P02-EPC-E1070 | چاه شماره 28 | E | A | P&ID - W028 | 276 | 2021-08-22 | 2022-05-25 | 44 |  |  | 80%
P02-EPC-E1880 | چاه شماره 28 | E | A | Data Sheets For WHCP/HPU - Wellheads - W028 | 276 | 2021-08-22 | 2022-05-25 | 197 |  |  | 80%
P02-EPC-E1820 | چاه شماره 28 | E | A | Pipeline Corrosion Study & Material Selection Report - W028 | 210 | 2021-10-27 | 2022-05-25 | 192 |  |  | 0%
P02-EPC-E3590 | چاه شماره 28 | E | A | PMR For WHCP/HPU - W028 | 62 | 2021-11-15 | 2022-01-16 | 45 |  |  | 100%
P02-EPC-E1180 | چاه شماره 28 | E | A | Piping Material Specification - W028 | 178 | 2021-11-28 | 2022-05-25 | 111 |  |  | 60%
P02-EPC-P1550 | چاه شماره 28 | P | A | Tendering & Selection- W028 - Line pipe | #VALUE! |  |  | 50 |  |  | 0%
P02-EPC-P1560 | چاه شماره 28 | P | A | Contract Effectiveness / PO- W028 - Line pipe | #VALUE! |  |  | 50 |  |  | 0%
P02-EPC-P1570 | چاه شماره 28 | P | A | Manufacturing / Fabrication / Supply- W028 - Line pipe | #VALUE! |  |  | 50 |  |  | 0%
P02-EPC-P1670 | چاه شماره 28 | P | A | Tendering & Selection- W028 - WHCP | #VALUE! |  |  | 45 |  |  | 0%
P02-EPC-P1680 | چاه شماره 28 | P | A | Contract Effectiveness / PO- W028 - WHCP | #VALUE! |  |  | 45 |  |  | 0%
P02-EPC-P1690 | چاه شماره 28 | P | A | Manufacturing / Fabrication / Supply- W028 - WHCP | #VALUE! |  |  | 45 |  |  | 0%
P02-EPC-C1170 | چاه شماره 28 | C | A | Site Preparation W028 | #VALUE! |  |  | 0 |  |  | 53%
P02-EPC-C1440 | چاه شماره 28 | C | A | Construction of Right of Way - W028 | #VALUE! |  |  | 131 |  |  | 0%
P02-EPC-C1240 | چاه شماره 28 | C | A | Excavation of Mud Channel- W028 | 0 | 0 | 0 | 25 |  |  | 0%
P02-EPC-C1310 | چاه شماره 28 | C | A | Installation sealling Layer of Mud Pit- W028 | 0 | 0 | 0 | 1900-02-05 |  |  | 0
P02-EPC-C1460 | چاه شماره 28 | C | A | Construction & Installation of Shelter for Wellhead Control Panel- W028 | 0 | 0 | 0 | 1900-05-10 |  |  | 0

## 6
0 |  |  |  | جدول شماره 6 : ماتریس علل تأخیرات پروژه |  |  |  | 12 | 14 | 15 | 17 | 18 | 20 | 21 | 23 | 24 | 26 | 27 | 29 | 1 |  |  |  | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24
| كد فعاليت/بسته (ID A s) | نام فعاليت/بسته | بسته كاري | علل تأخیر متأثر در هر فعالیت |  | شروع | پایان | شروع | پایان | شروع | پایان | شروع | پایان | شروع | پایان | شروع | پایان | شروع | پایان | time axis 2021-07-01 to 2023-06-22 12:00
|  |  |  | كد تاخير (ID D s) | عنوان علل تأخیر | time axis 2021-07-01 to 2023-06-22 12:00
[20 empty] | شش ماهه اول سال اول | [23 empty] | شش ماهه دوم سال اول | [23 empty] | شش ماهه اول سال دوم | [23 empty] | شش ماهه دوم سال دوم
| P12-EPC-E1000 | Endorsement Report For Basic Design & Scope of Work | ايستگاه گاز | M01 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-14 | 2021-09-07 | 2021-10-03 | 2021-10-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-07-22 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-07-31 | 2021-09-19 | 2021-07-31 | 2021-09-19 | 2021-07-31 | 2021-09-19 | 2021-07-31 | 2021-09-19 | 2021-07-31 | 2021-09-19 | 2021-07-31 | 2021-09-19 | 2021-07-31 | 2021-09-19 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | P12-EPC-E1000 | 1P12-EPC-E1000 | ايستگاه گاز | M01-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-09-07 | 2021-06-23 | 2021-09-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-E1570 | Process Flow Diagram (PFD) | ايستگاه گاز | E01 | عدم نهایی سازي اطلاعات فرآیندی ایستگاه گاز | 2021-06-23 | 2021-12-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | M02 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-28 | 2021-09-06 | 2021-10-31 | 2021-11-14 | 2021-12-14 | 2022-01-02 | 2022-01-22 | 2022-02-22 | 2022-03-26 | 2022-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-07-04 | 2021-08-26 | 2021-07-04 | 2021-08-26 | 2021-07-04 | 2021-08-26 | 2021-07-04 | 2021-08-26 | 2021-07-04 | 2021-08-26 | 2021-07-04 | 2021-08-26 | 2021-07-04 | 2021-08-26 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | P12-EPC-E1570 | 2P12-EPC-E1570 | ايستگاه گاز | E01-M02- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-07-04 | 2021-12-06 | 2021-07-04 | 2021-09-06 | 2021-07-04 | 2021-11-14 | 2021-07-04 | 2022-01-02 | 2021-07-04 | 2022-02-22 | 2021-07-04 | 2022-04-30 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-E1540 | Process Data Sheets For Gas Compressors Packages | ايستگاه گاز | M03 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-11-21 | 2021-11-27 | 2022-01-15 | 2022-01-29 | 2022-04-09 | 2022-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E01 | عدم نهایی سازي اطلاعات فرآیندی ایستگاه گاز | 2021-06-23 | 2021-12-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-07-31 | 2021-09-12 | 2021-07-31 | 2021-09-12 | 2021-07-31 | 2021-09-12 | 2021-07-31 | 2021-09-12 | 2021-07-31 | 2021-09-12 | 2021-07-31 | 2021-09-12 | 2021-07-31 | 2021-09-12 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-11-07 | 2022-05-25 | 2021-11-07 | 2022-05-25 | 2021-11-07 | 2022-05-25 | 2021-11-07 | 2022-05-25 | 2021-11-07 | 2022-05-25 | 2021-11-07 | 2022-05-25 | 2021-11-07 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | P12-EPC-E1540 | 3P12-EPC-E1540 | ايستگاه گاز | M03-E01- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-07-31 | 2021-12-06 | 2021-07-31 | 2021-11-27 | 2021-07-31 | 2022-01-29 | 2021-07-31 | 2022-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-E2480 | Mechanical Data Sheets For Gas Compressors Packages | ايستگاه گاز | M04 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-09-26 | 2021-10-11 | 2021-10-31 | 2021-11-08 | 2021-11-28 | 2021-12-20 | 2022-01-26 | 2022-02-22 | 2022-03-19 | 2022-03-26 | 2022-05-04 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E01 | عدم نهایی سازي اطلاعات فرآیندی ایستگاه گاز | 2021-06-23 | 2021-12-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-12 | 2021-09-29 | 2021-08-12 | 2021-09-29 | 2021-08-12 | 2021-09-29 | 2021-08-12 | 2021-09-29 | 2021-08-12 | 2021-09-29 | 2021-08-12 | 2021-09-29 | 2021-08-12 | 2021-09-29 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-09-12 | 2022-05-08 | 2021-09-12 | 2022-05-08 | 2021-09-12 | 2022-05-08 | 2021-09-12 | 2022-05-08 | 2021-09-12 | 2022-05-08 | 2021-09-12 | 2022-05-08 | 2021-09-12 | 2022-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | P12-EPC-E2480 | 4P12-EPC-E2480 | ايستگاه گاز | M04-E01- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-12 | 2021-12-06 | 2021-08-12 | 2021-10-11 | 2021-08-12 | 2021-11-08 | 2021-08-12 | 2021-12-20 | 2021-08-12 | 2022-02-22 | 2021-08-12 | 2022-03-26 | 2021-08-12 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-E7980 | TBE For Gas Compressors | ايستگاه گاز | M05 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2022-02-16 | 2022-02-27 | 2022-03-19 | 2022-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E05 | عدم نهايي سازي MR كمپرسورها | 2021-11-28 | 2022-02-13 | 2021-11-28 | 2022-02-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-16 | 2021-09-29 | 2021-08-16 | 2021-09-29 | 2021-08-16 | 2021-09-29 | 2021-08-16 | 2021-09-29 | 2021-08-16 | 2021-09-29 | 2021-08-16 | 2021-09-29 | 2021-08-16 | 2021-09-29 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-02-02 | 2022-03-05 | 2022-02-02 | 2022-03-05 | 2022-02-02 | 2022-03-05 | 2022-02-02 | 2022-03-05 | 2022-02-02 | 2022-03-05 | 2022-02-02 | 2022-03-05 | 2022-02-02 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | P12-EPC-E7980 | 5P12-EPC-E7980 | ايستگاه گاز | M05-E05- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-16 | 2022-02-13 | 2021-08-16 | 2022-02-27 | 2021-08-16 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-E7970 | PMR For Gas Compressors | ايستگاه گاز | M06 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-12-12 | 2021-12-15 | 2022-01-18 | 2022-01-30 | 2022-02-27 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E02 | عدم نهایی سازي ديتاشيت فرآيندي پكيج هاي كمپرسور | 2021-11-07 | 2022-05-25 | 2021-11-07 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E03 | عدم نهایی سازي ديتاشيت مكانيك پكيج هاي كمپرسور | 2021-09-12 | 2022-05-08 | 2021-09-12 | 2022-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-03 | 2021-09-13 | 2021-09-03 | 2021-09-13 | 2021-09-03 | 2021-09-13 | 2021-09-03 | 2021-09-13 | 2021-09-03 | 2021-09-13 | 2021-09-03 | 2021-09-13 | 2021-09-03 | 2021-09-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-11-28 | 2022-02-13 | 2021-11-28 | 2022-02-13 | 2021-11-28 | 2022-02-13 | 2021-11-28 | 2022-02-13 | 2021-11-28 | 2022-02-13 | 2021-11-28 | 2022-02-13 | 2021-11-28 | 2022-02-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | P12-EPC-E7970 | 6P12-EPC-E7970 | ايستگاه گاز | M06-E02-E03 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-03 | 2022-02-13 | 2021-09-12 | 2022-02-13 | 2021-09-03 | 2022-01-30 | 2021-09-03 | 2022-02-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-P1000 | Tendering & Selection For Gas Compressors | ايستگاه گاز | E04 | عدم نهايي سازي TBE كمپرسورها | 2022-02-02 | 2022-03-05 | 2022-02-02 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-11 | 2021-10-09 | 2021-08-11 | 2021-10-09 | 2021-08-11 | 2021-10-09 | 2021-08-11 | 2021-10-09 | 2021-08-11 | 2021-10-09 | 2021-08-11 | 2021-10-09 | 2021-08-11 | 2021-10-09 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-02-26 | 2022-03-16 | 2022-02-26 | 2022-03-16 | 2022-02-26 | 2022-03-16 | 2022-02-26 | 2022-03-16 | 2022-02-26 | 2022-03-16 | 2022-02-26 | 2022-03-16 | 2022-02-26 | 2022-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | P12-EPC-P1000 | 7P12-EPC-P1000 | ايستگاه گاز | E04-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 0 | 2022-03-05 | 2021-08-11 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-P1010 | Contract Effectiveness / PO For Gas Compressors | ايستگاه گاز | P01 | عدم انتخاب سازنده كمپرسورها | 2022-02-26 | 2022-03-16 | 2022-02-26 | 2022-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F01 | تاخير در دريافت پيش پرداخت | 2021-06-28 | 2021-09-03 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-10 | 2021-11-08 | 2021-10-10 | 2021-11-08 | 2021-10-10 | 2021-11-08 | 2021-10-10 | 2021-11-08 | 2021-10-10 | 2021-11-08 | 2021-10-10 | 2021-11-08 | 2021-10-10 | 2021-11-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | P12-EPC-P1010 | 8P12-EPC-P1010 | ايستگاه گاز | P01-F01- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-10 | 2022-03-16 | 2021-10-10 | 2022-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P12-EPC-P1020 | Manufacturing / Fabrication / Supply For Gas Compressors | ايستگاه گاز | P02 | عدم عقد قرارداد براي تامين كمپرسورها | 2022-03-16 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-11-09 | 2023-01-02 | 2021-11-09 | 2023-01-02 | 2021-11-09 | 2023-01-02 | 2021-11-09 | 2023-01-02 | 2021-11-09 | 2023-01-02 | 2021-11-09 | 2023-01-02 | 2021-11-09 | 2023-01-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | P12-EPC-P1020 | 9P12-EPC-P1020 | ايستگاه گاز | P02-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-11-09 | 2022-05-25 | 2021-11-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E1060 | Process Flow Diagram - W018S | چاه شماره 18 | M07 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-18 | 2021-09-07 | 2021-11-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E06 | عدم نهایی سازي اطلاعات فرآیندی چاه ها -چاه 18 | 2021-06-23 | 2021-10-13 | 2021-08-04 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-31 | 2021-10-14 | 2021-08-31 | 2021-10-14 | 2021-08-31 | 2021-10-14 | 2021-08-31 | 2021-10-14 | 2021-08-31 | 2021-10-14 | 2021-08-31 | 2021-10-14 | 2021-08-31 | 2021-10-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-04 | 2022-05-25 | 2021-08-04 | 2022-05-25 | 2021-08-04 | 2022-05-25 | 2021-08-04 | 2022-05-25 | 2021-08-04 | 2022-05-25 | 2021-08-04 | 2022-05-25 | 2021-08-04 | 2022-05-25 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | P01-EPC-E1060 | 10P01-EPC-E1060 | چاه شماره 18 | M07-E06- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-31 | 2021-10-13 | 2021-08-31 | 2022-05-25 | 2021-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E1370 | Plot Plan Drawing - W018S | چاه شماره 18 | M08 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-09-05 | 2021-09-29 | 2021-11-29 | 2021-12-12 | 2022-02-14 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E20 | عدم نهايي سازي طرح مديريت پسماند چاه 18 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | P01-EPC-E1370 | 11P01-EPC-E1370 | چاه شماره 18 | M08-E20- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-06 | 2021-12-27 | 2021-08-06 | 2021-12-27 | 2021-08-06 | 2021-12-12 | 2021-08-06 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E1860 | Specification For WHCP/HPU-W018S | چاه شماره 18 | M09 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-22 | 2021-09-14 | 2021-10-24 | 2022-01-02 | 2022-01-24 | 2022-01-30 | 2022-04-10 | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E14 | نهايي نشدن Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-14 | 2021-09-20 | 2021-08-14 | 2021-09-20 | 2021-08-14 | 2021-09-20 | 2021-08-14 | 2021-09-20 | 2021-08-14 | 2021-09-20 | 2021-08-14 | 2021-09-20 | 2021-08-14 | 2021-09-20 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | P01-EPC-E1860 | 12P01-EPC-E1860 | چاه شماره 18 | M09-E14- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-14 | 2022-03-27 | 2021-08-14 | 2022-03-27 | 2021-08-14 | 2022-01-02 | 2021-08-14 | 2022-01-30 | 2021-08-14 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E2470 | Rough Grading Plans -W018S | چاه شماره 18 | M10 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-11 | 2021-08-07 | 2021-11-13 | 2021-11-06 | 2022-01-29 | 2022-01-22 | 2022-03-12 | 2022-03-05 | 2022-03-27 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E20 | عدم نهايي سازي طرح مديريت پسماند چاه 18 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 2021-08-06 | 2021-09-14 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-07-28 | 2022-03-13 | 2021-07-28 | 2022-03-13 | 2021-07-28 | 2022-03-13 | 2021-07-28 | 2022-03-13 | 2021-07-28 | 2022-03-13 | 2021-07-28 | 2022-03-13 | 2021-07-28 | 2022-03-13 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | P01-EPC-E2470 | 13P01-EPC-E2470 | چاه شماره 18 | M10-E20- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-06 | 2021-12-27 | 2021-08-06 | 2021-12-27 | 2021-08-06 | 2021-11-06 | 2021-08-06 | 2022-01-22 | 2021-08-06 | 2022-03-05 | 2021-08-06 | 2022-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E1070 | P&ID - W018S | چاه شماره 18 | M11 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-23 | 2021-09-06 | 2021-11-15 | 2021-11-27 | 2021-12-29 | 2022-01-03 | 2022-03-14 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E10 | عدم نهايي سازي PMS-چاه 18 | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-10 | 2021-10-24 | 2021-09-10 | 2021-10-24 | 2021-09-10 | 2021-10-24 | 2021-09-10 | 2021-10-24 | 2021-09-10 | 2021-10-24 | 2021-09-10 | 2021-10-24 | 2021-09-10 | 2021-10-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-09 | 2022-05-25 | 2021-08-09 | 2022-05-25 | 2021-08-09 | 2022-05-25 | 2021-08-09 | 2022-05-25 | 2021-08-09 | 2022-05-25 | 2021-08-09 | 2022-05-25 | 2021-08-09 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | P01-EPC-E1070 | 14P01-EPC-E1070 | چاه شماره 18 | M11-E10- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-10 | 2021-12-15 | 2021-09-10 | 2021-12-15 | 2021-09-10 | 2021-11-27 | 2021-09-10 | 2022-01-03 | 2021-09-10 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E1300 | Piping Material Specification-W018S | چاه شماره 18 | M12 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-09-07 | 2021-09-14 | 2021-10-18 | 2021-11-08 | 2021-12-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E08 | انجام مطالعات پایه در فاز مطالعات Detail به دلیل اصرار کارفرما به انجام مطالعات خوردگي و تطويل آن به دليل نبود اطلاعات آب چاه 18 | 2021-09-13 | 2022-01-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-01-02 | 2022-01-31 | 2022-01-02 | 2022-01-31 | 2022-01-02 | 2022-01-31 | 2022-01-02 | 2022-01-31 | 2022-01-02 | 2022-01-31 | 2022-01-02 | 2022-01-31 | 2022-01-02 | 2022-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | P01-EPC-E1300 | 15P01-EPC-E1300 | چاه شماره 18 | M12-E08- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-01-02 | 2021-12-15 | 2022-01-02 | 2021-09-14 | 2022-01-02 | 2021-11-08 | 2022-01-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E1870 | Data Sheets For WHCP/HPU - Wellheads-W018S | چاه شماره 18 | M13 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-09-05 | 2021-09-20 | 2021-11-23 | 2021-11-27 | 2022-01-04 | 2022-01-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E14 | نهايي نشدن Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-24 | 2021-09-22 | 2021-08-24 | 2021-09-22 | 2021-08-24 | 2021-09-22 | 2021-08-24 | 2021-09-22 | 2021-08-24 | 2021-09-22 | 2021-08-24 | 2021-09-22 | 2021-08-24 | 2021-09-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | P01-EPC-E1870 | 16P01-EPC-E1870 | چاه شماره 18 | M13-E14- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-24 | 2022-03-27 | 2021-08-24 | 2022-03-27 | 2021-08-24 | 2021-11-27 | 2021-08-24 | 2022-01-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E2460 | Civil and Structural drawings - W018S | چاه شماره 18 | M14 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-11 | 2021-08-07 | 2022-01-18 | 2022-01-11 | 2022-03-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E21 | عدم نهايي سازي مدرک RG- چاه 18 | 2021-07-28 | 2022-03-05 | 2021-07-28 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-23 | 2021-10-01 | 2021-08-23 | 2021-10-01 | 2021-08-23 | 2021-10-01 | 2021-08-23 | 2021-10-01 | 2021-08-23 | 2021-10-01 | 2021-08-23 | 2021-10-01 | 2021-08-23 | 2021-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-07-28 | 2022-03-05 | 2021-07-28 | 2022-03-05 | 2021-07-28 | 2022-03-05 | 2021-07-28 | 2022-03-05 | 2021-07-28 | 2022-03-05 | 2021-07-28 | 2022-03-05 | 2021-07-28 | 2022-03-05 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | P01-EPC-E2460 | 17P01-EPC-E2460 | چاه شماره 18 | M14-E21- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-23 | 2022-03-05 | 2021-08-23 | 2022-03-05 | 2021-08-23 | 2022-01-11 | 2021-08-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E2450 | General Civil Layout - W018S | چاه شماره 18 | M15 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-11 | 2021-08-07 | 2021-09-11 | 2021-09-04 | 2021-09-27 | 2021-09-18 | 2021-11-06 | 2021-11-02 | 2021-12-04 | 2021-11-27 | 2022-01-10 | 2022-01-02 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E20 | عدم نهايي سازي طرح مديريت پسماند چاه 18 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-26 | 2021-09-14 | 2021-08-26 | 2021-09-14 | 2021-08-26 | 2021-09-14 | 2021-08-26 | 2021-09-14 | 2021-08-26 | 2021-09-14 | 2021-08-26 | 2021-09-14 | 2021-08-26 | 2021-09-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | P01-EPC-E2450 | 18P01-EPC-E2450 | چاه شماره 18 | M15-E20- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-26 | 2021-12-27 | 2021-08-26 | 2021-12-27 | 2021-08-26 | 2021-09-04 | 2021-08-26 | 2021-09-18 | 2021-08-26 | 2021-11-02 | 2021-08-26 | 2021-11-27 | 2021-08-26 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E1810 | Pipeline Corrosion Study & Material Selection Report-W018S | چاه شماره 18 | M16 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-11-10 | 2021-11-21 | 2021-12-18 | 0 | 2022-03-14 | 2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E08 | انجام مطالعات پایه در فاز مطالعات Detail به دلیل اصرار کارفرما به انجام مطالعات خوردگي و تطويل آن به دليل نبود اطلاعات آب چاه 18 | 2021-09-13 | 2022-01-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-10-27 | 2022-05-25 | 2021-10-27 | 2022-05-25 | 2021-10-27 | 2022-05-25 | 2021-10-27 | 2022-05-25 | 2021-10-27 | 2022-05-25 | 2021-10-27 | 2022-05-25 | 2021-10-27 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | P01-EPC-E1810 | 19P01-EPC-E1810 | چاه شماره 18 | M16-E08- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-03-02 | 2022-01-26 | 2022-03-02 | 2021-11-21 | 2022-03-02 | 0 | 2022-03-02 | 2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E3590 | PMR For WHCP/HPU - W018S | چاه شماره 18 | M17 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-11-29 | 2021-12-07 | 2022-01-30 | 2022-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E16 | نهايي نشدن ديتاشيت WHCP | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-21 | 2021-09-27 | 2021-09-21 | 2021-09-27 | 2021-09-21 | 2021-09-27 | 2021-09-21 | 2021-09-27 | 2021-09-21 | 2021-09-27 | 2021-09-21 | 2021-09-27 | 2021-09-21 | 2021-09-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-11-15 | 2022-01-16 | 2021-11-15 | 2022-01-16 | 2021-11-15 | 2022-01-16 | 2021-11-15 | 2022-01-16 | 2021-11-15 | 2022-01-16 | 2021-11-15 | 2022-01-16 | 2021-11-15 | 2022-01-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | P01-EPC-E3590 | 20P01-EPC-E3590 | چاه شماره 18 | M17-E16- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-21 | 2022-01-16 | 2021-09-21 | 2022-01-16 | 2021-09-21 | 2022-01-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-E3560 | PMR For Flowline Support - W018S | چاه شماره 18 | M18 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-12-20 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E10 | عدم نهايي سازي PMS-چاه 18 | 2021-08-24 | 2021-12-15 | 2021-08-24 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-11-15 | 2021-11-19 | 2021-11-15 | 2021-11-19 | 2021-11-15 | 2021-11-19 | 2021-11-15 | 2021-11-19 | 2021-11-15 | 2021-11-19 | 2021-11-15 | 2021-11-19 | 2021-11-15 | 2021-11-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | P01-EPC-E3560 | 21P01-EPC-E3560 | چاه شماره 18 | M18-E10- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-11-15 | 2021-12-15 | 2021-11-15 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-P1670 | Tendering & Selection- W018S-WHCP | چاه شماره 18 | E18 | عدم نهايي سازي MR برای WHCP-چاه 18 | 2021-11-15 | 2022-01-16 | 2021-11-15 | 2022-01-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E16 | نهايي نشدن ديتاشيت WHCP | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-15 | 2021-10-24 | 2021-10-15 | 2021-10-24 | 2021-10-15 | 2021-10-24 | 2021-10-15 | 2021-10-24 | 2021-10-15 | 2021-10-24 | 2021-10-15 | 2021-10-24 | 2021-10-15 | 2021-10-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | P01-EPC-P1670 | 22P01-EPC-P1670 | چاه شماره 18 | E18-E16- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-15 | 2022-05-25 | 2021-10-15 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-P1550 | Tendering & Selection- W018S- Line pipe | چاه شماره 18 | E12 | عدم نهايي سازي مدارك خريد براي لوله هاي جرياني- چاه 18 | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | P03 | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي-چاه 18 | 2021-06-23 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-27 | 2021-11-02 | 2021-10-27 | 2021-11-02 | 2021-10-27 | 2021-11-02 | 2021-10-27 | 2021-11-02 | 2021-10-27 | 2021-11-02 | 2021-10-27 | 2021-11-02 | 2021-10-27 | 2021-11-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | P01-EPC-P1550 | 23P01-EPC-P1550 | چاه شماره 18 | E12-P03- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-27 | 0 | 2021-10-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-P1680 | Contract Effectiveness / PO- W018S- WHCP | چاه شماره 18 | P09 | عدم امکان انتخاب سازنده برای WHCP-چاه 18 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F01 | تاخير در دريافت پيش پرداخت | 2021-06-28 | 2021-09-03 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-25 | 2021-10-29 | 2021-10-25 | 2021-10-29 | 2021-10-25 | 2021-10-29 | 2021-10-25 | 2021-10-29 | 2021-10-25 | 2021-10-29 | 2021-10-25 | 2021-10-29 | 2021-10-25 | 2021-10-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | P01-EPC-P1680 | 24P01-EPC-P1680 | چاه شماره 18 | P09-F01- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-25 | 0 | 2021-10-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-P1560 | Contract Effectiveness / PO- W018S-Line pipe | چاه شماره 18 | P03 | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي-چاه 18 | 2021-06-23 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F01 | تاخير در دريافت پيش پرداخت | 2021-06-28 | 2021-09-03 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-11-03 | 2021-11-07 | 2021-11-03 | 2021-11-07 | 2021-11-03 | 2021-11-07 | 2021-11-03 | 2021-11-07 | 2021-11-03 | 2021-11-07 | 2021-11-03 | 2021-11-07 | 2021-11-03 | 2021-11-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | P01-EPC-P1560 | 25P01-EPC-P1560 | چاه شماره 18 | P03-F01- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-11-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-P1690 | Manufacturing / Fabrication / Supply- W018S-WHCP | چاه شماره 18 | P11 | عدم امکان عقد قرارداد با سازنده برای WHCP-چاه 18 | 2022-03-15 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-30 | 2022-01-27 | 2021-10-30 | 2022-01-27 | 2021-10-30 | 2022-01-27 | 2021-10-30 | 2022-01-27 | 2021-10-30 | 2022-01-27 | 2021-10-30 | 2022-01-27 | 2021-10-30 | 2022-01-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | P01-EPC-P1690 | 26P01-EPC-P1690 | چاه شماره 18 | P11-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-P1570 | Manufacturing / Fabrication / Supply- W018S-Line pipe | چاه شماره 18 | P05 | عدم امکان عقد قرارداد با سازنده لوله های جریانی-چاه 18 | 2021-06-23 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-11-08 | 2022-01-16 | 2021-11-08 | 2022-01-16 | 2021-11-08 | 2022-01-16 | 2021-11-08 | 2022-01-16 | 2021-11-08 | 2022-01-16 | 2021-11-08 | 2022-01-16 | 2021-11-08 | 2022-01-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | P01-EPC-P1570 | 27P01-EPC-P1570 | چاه شماره 18 | P05-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-11-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-C1150 | Supply & Installation sealling Layer of Mud pit- W018S | چاه شماره 18 | E20 | عدم نهايي سازي طرح مديريت پسماند چاه 18 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E21 | عدم نهايي سازي مدرک RG- چاه 18 | 2021-07-28 | 2022-03-05 | 2021-07-28 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E22 | عدم نهايي سازي نقشه های سیویل و سازه ای چاه- چاه 18 | 2021-07-28 | 2022-03-13 | 2021-07-28 | 2022-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-02 | 2021-10-09 | 2021-10-02 | 2021-10-09 | 2021-10-02 | 2021-10-09 | 2021-10-02 | 2021-10-09 | 2021-10-02 | 2021-10-09 | 2021-10-02 | 2021-10-09 | 2021-10-02 | 2021-10-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-20 | 2021-12-09 | 2021-08-20 | 2021-12-09 | 2021-08-20 | 2021-12-09 | 2021-08-20 | 2021-12-09 | 2021-08-20 | 2021-12-09 | 2021-08-20 | 2021-12-09 | 2021-08-20 | 2021-12-09 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | P01-EPC-C1150 | 28P01-EPC-C1150 | چاه شماره 18 | E20-E21-E22 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-02 | 2021-12-09 | 2021-10-02 | 2021-12-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-C1330 | Construction of Right of Way- W018S | چاه شماره 18 | P07 | عدم امکان آغاز ساخت لوله های جریانی-چاه 18 | 2021-06-23 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-01-11 | 2022-01-30 | 2022-01-11 | 2022-01-30 | 2022-01-11 | 2022-01-30 | 2022-01-11 | 2022-01-30 | 2022-01-11 | 2022-01-30 | 2022-01-11 | 2022-01-30 | 2022-01-11 | 2022-01-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | P01-EPC-C1330 | 29P01-EPC-C1330 | چاه شماره 18 | P07-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-01-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P01-EPC-C1350 | Construction & Installation of Shelter for Wellhead Control Panel-W018S | چاه شماره 18 | P13 | عدم امکان ساخت WHCP-چاه 18 | 2022-03-15 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-02-15 | 2022-03-01 | 2022-02-15 | 2022-03-01 | 2022-02-15 | 2022-03-01 | 2022-02-15 | 2022-03-01 | 2022-02-15 | 2022-03-01 | 2022-02-15 | 2022-03-01 | 2022-02-15 | 2022-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | P01-EPC-C1350 | 30P01-EPC-C1350 | چاه شماره 18 | P13-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-02-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E1060 | Process Flow Diagram - W028 | چاه شماره 28 | M19 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-28 | 2021-09-06 | 2021-11-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E07 | عدم نهایی سازي اطلاعات فرآیندی چاه ها -چاه 28 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-05 | 2021-10-14 | 2021-09-05 | 2021-10-14 | 2021-09-05 | 2021-10-14 | 2021-09-05 | 2021-10-14 | 2021-09-05 | 2021-10-14 | 2021-09-05 | 2021-10-14 | 2021-09-05 | 2021-10-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | P02-EPC-E1060 | 31P02-EPC-E1060 | چاه شماره 28 | M19-E07- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-05 | 2022-05-25 | 2021-09-05 | 2022-05-25 | 2021-09-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E1380 | Plot Plan Drawing - W028 | چاه شماره 28 | M20 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2022-02-16 | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E23 | عدم نهايي سازي طرح مديريت پسماند ساير چاه ها | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-05 | 2021-10-04 | 2021-09-05 | 2021-10-04 | 2021-09-05 | 2021-10-04 | 2021-09-05 | 2021-10-04 | 2021-09-05 | 2021-10-04 | 2021-09-05 | 2021-10-04 | 2021-09-05 | 2021-10-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-02-02 | 2022-05-25 | 2022-02-02 | 2022-05-25 | 2022-02-02 | 2022-05-25 | 2022-02-02 | 2022-05-25 | 2022-02-02 | 2022-05-25 | 2022-02-02 | 2022-05-25 | 2022-02-02 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | P02-EPC-E1380 | 32P02-EPC-E1380 | چاه شماره 28 | M20-E23- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-05 | 2022-05-25 | 2021-09-05 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E1860 | Specification For WHCP/HPU - W028 | چاه شماره 28 | M21 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-08-22 | 2021-09-14 | 2021-10-24 | 2022-01-02 | 2022-01-24 | 2022-01-30 | 2022-04-10 | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E15 | نهايي نشدن Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-02-05 | 2022-03-14 | 2022-02-05 | 2022-03-14 | 2022-02-05 | 2022-03-14 | 2022-02-05 | 2022-03-14 | 2022-02-05 | 2022-03-14 | 2022-02-05 | 2022-03-14 | 2022-02-05 | 2022-03-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | P02-EPC-E1860 | 33P02-EPC-E1860 | چاه شماره 28 | M21-E15- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-02-05 | 2022-03-27 | 2022-02-05 | 2022-03-27 | 2022-02-05 | 2022-01-02 | 2022-02-05 | 2022-01-30 | 2022-02-05 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E2460 | General Civil Layout -W028 | چاه شماره 28 | M22 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-11-02 | 2021-11-22 | 2022-03-26 | 2022-03-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E20 | عدم نهايي سازي طرح مديريت پسماند چاه 18 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | P02-EPC-E2460 | 34P02-EPC-E2460 | چاه شماره 28 | M22-E20- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-07-23 | 2021-12-27 | 2021-07-23 | 2021-12-27 | 2021-07-23 | 2022-03-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E2470 | Civil and Structural drawings -W028 | چاه شماره 28 | M23 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-11-02 | 0 | 2021-12-04 | 2021-12-01 | 2022-03-28 | 2022-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E20 | عدم نهايي سازي طرح مديريت پسماند چاه 18 | 2021-07-28 | 2021-12-27 | 2021-07-28 | 2021-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E21 | عدم نهايي سازي مدرک RG- چاه 18 | 2021-07-28 | 2022-03-05 | 2021-07-28 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-01-20 | 2022-03-05 | 2022-01-20 | 2022-03-05 | 2022-01-20 | 2022-03-05 | 2022-01-20 | 2022-03-05 | 2022-01-20 | 2022-03-05 | 2022-01-20 | 2022-03-05 | 2022-01-20 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | P02-EPC-E2470 | 35P02-EPC-E2470 | چاه شماره 28 | M23-E20-E21 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-01-20 | 2022-03-05 | 2022-01-20 | 2022-03-05 | 2022-01-20 | 2021-12-01 | 2022-01-20 | 2022-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E2480 | Rough Grading Plans -W028 | چاه شماره 28 | M24 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-10-25 | 2021-10-18 | 2022-02-20 | 2022-02-12 | 2022-03-28 | 2022-04-03 | 2022-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E23 | عدم نهايي سازي طرح مديريت پسماند ساير چاه ها | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 2021-07-23 | 2021-08-16 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-10-11 | 2022-04-10 | 2021-10-11 | 2022-04-10 | 2021-10-11 | 2022-04-10 | 2021-10-11 | 2022-04-10 | 2021-10-11 | 2022-04-10 | 2021-10-11 | 2022-04-10 | 2021-10-11 | 2022-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | P02-EPC-E2480 | 36P02-EPC-E2480 | چاه شماره 28 | M24-E23- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-07-23 | 2022-04-10 | 2021-07-23 | 2022-04-10 | 2021-07-23 | 2022-02-12 | 2021-07-23 | 2022-04-03 | 2021-07-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E3530 | PMR For Line Pipes - W028 | چاه شماره 28 | M25 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-12-20 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E11 | عدم نهايي سازي PMS چاه 28 | 2021-11-28 | 2022-05-25 | 2021-11-28 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-18 | 2021-09-27 | 2021-09-18 | 2021-09-27 | 2021-09-18 | 2021-09-27 | 2021-09-18 | 2021-09-27 | 2021-09-18 | 2021-09-27 | 2021-09-18 | 2021-09-27 | 2021-09-18 | 2021-09-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | P02-EPC-E3530 | 37P02-EPC-E3530 | چاه شماره 28 | M25-E11- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-18 | 2021-12-15 | 2021-09-18 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E1070 | P&ID - W028 | چاه شماره 28 | M26 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-09-05 | 2021-09-08 | 2021-11-15 | 2021-11-27 | 2021-12-29 | 2022-01-03 | 2022-03-14 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E11 | عدم نهايي سازي PMS چاه 28 | 2021-11-28 | 2022-05-25 | 2021-11-28 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E07 | عدم نهایی سازي اطلاعات فرآیندی چاه ها -چاه 28 | 2021-08-14 | 2022-05-25 | 2021-08-14 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-15 | 2021-10-24 | 2021-09-15 | 2021-10-24 | 2021-09-15 | 2021-10-24 | 2021-09-15 | 2021-10-24 | 2021-09-15 | 2021-10-24 | 2021-09-15 | 2021-10-24 | 2021-09-15 | 2021-10-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | P02-EPC-E1070 | 38P02-EPC-E1070 | چاه شماره 28 | M26-E11-E07 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-15 | 2022-05-25 | 2021-09-15 | 2022-05-25 | 2021-09-15 | 2021-11-27 | 2021-09-15 | 2022-01-03 | 2021-09-15 | 2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E1880 | Data Sheets For WHCP/HPU - Wellheads - W028 | چاه شماره 28 | M27 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-09-05 | 2021-09-20 | 2021-11-23 | 2021-11-27 | 2022-01-04 | 2022-01-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E15 | نهايي نشدن Spec مربوط به WHCP به دليل عدم دريافت اطلاعات شيرهاي سرچاهي | 2021-08-08 | 2022-03-27 | 2021-08-08 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-02-25 | 2022-04-14 | 2022-02-25 | 2022-04-14 | 2022-02-25 | 2022-04-14 | 2022-02-25 | 2022-04-14 | 2022-02-25 | 2022-04-14 | 2022-02-25 | 2022-04-14 | 2022-02-25 | 2022-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | P02-EPC-E1880 | 39P02-EPC-E1880 | چاه شماره 28 | M27-E15- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-02-25 | 2022-03-27 | 2022-02-25 | 2022-03-27 | 2022-02-25 | 2021-11-27 | 2022-02-25 | 2022-01-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E1820 | Pipeline Corrosion Study & Material Selection Report - W028 | چاه شماره 28 | M28 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-11-10 | 2021-11-21 | 2021-12-18 | 0 | 2022-03-14 | 2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E09 | انجام مطالعات پایه در فاز مطالعات Detail به دلیل اصرار کارفرما به انجام مطالعات خوردگي و تطويل آن به دليل نبود اطلاعات آب چاه 28 | 2021-09-13 | 2022-01-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 2022-03-02 | 2022-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-10-27 | 2022-05-25 | 2021-10-27 | 2022-05-25 | 2021-10-27 | 2022-05-25 | 2021-10-27 | 2022-05-25 | 2021-10-27 | 2022-05-25 | 2021-10-27 | 2022-05-25 | 2021-10-27 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | P02-EPC-E1820 | 40P02-EPC-E1820 | چاه شماره 28 | M28-E09- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-03-02 | 2022-01-26 | 2022-03-02 | 2021-11-21 | 2022-03-02 | 0 | 2022-03-02 | 2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E3590 | PMR For WHCP/HPU - W028 | چاه شماره 28 | M29 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-11-29 | 2021-12-07 | 2022-01-30 | 2022-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E17 | نهايي نشدن ديتاشيت WHCP | 2021-08-22 | 2022-05-25 | 2021-08-22 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-16 | 2021-10-25 | 2021-10-16 | 2021-10-25 | 2021-10-16 | 2021-10-25 | 2021-10-16 | 2021-10-25 | 2021-10-16 | 2021-10-25 | 2021-10-16 | 2021-10-25 | 2021-10-16 | 2021-10-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-11-15 | 2022-01-16 | 2021-11-15 | 2022-01-16 | 2021-11-15 | 2022-01-16 | 2021-11-15 | 2022-01-16 | 2021-11-15 | 2022-01-16 | 2021-11-15 | 2022-01-16 | 2021-11-15 | 2022-01-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | P02-EPC-E3590 | 41P02-EPC-E3590 | چاه شماره 28 | M29-E17- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-16 | 2022-01-16 | 2021-10-16 | 2022-01-16 | 2021-10-16 | 2022-01-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-E1180 | Piping Material Specification - W028 | چاه شماره 28 | M30 | تاخیر کارفرما در پاسخگویی به مدارک مهندسی | 0 | 0 | 2021-12-12 | 2021-12-26 | 2022-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E09 | انجام مطالعات پایه در فاز مطالعات Detail به دلیل اصرار کارفرما به انجام مطالعات خوردگي و تطويل آن به دليل نبود اطلاعات آب چاه 28 | 2021-09-13 | 2022-01-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-02-10 | 2022-04-14 | 2022-02-10 | 2022-04-14 | 2022-02-10 | 2022-04-14 | 2022-02-10 | 2022-04-14 | 2022-02-10 | 2022-04-14 | 2022-02-10 | 2022-04-14 | 2022-02-10 | 2022-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-11-28 | 2022-05-25 | 2021-11-28 | 2022-05-25 | 2021-11-28 | 2022-05-25 | 2021-11-28 | 2022-05-25 | 2021-11-28 | 2022-05-25 | 2021-11-28 | 2022-05-25 | 2021-11-28 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | P02-EPC-E1180 | 42P02-EPC-E1180 | چاه شماره 28 | M30-E09- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-02-10 | 2022-01-26 | 2022-02-10 | 2021-12-26 | 2022-02-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-P1550 | Tendering & Selection- W028 - Line pipe | چاه شماره 28 | E13 | عدم نهايي سازي مدارك خريد براي لوله هاي جرياني- چاه 28 | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | P04 | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي-چاه 28 | 2021-06-23 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-08 | 2021-10-14 | 2021-10-08 | 2021-10-14 | 2021-10-08 | 2021-10-14 | 2021-10-08 | 2021-10-14 | 2021-10-08 | 2021-10-14 | 2021-10-08 | 2021-10-14 | 2021-10-08 | 2021-10-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | P02-EPC-P1550 | 43P02-EPC-P1550 | چاه شماره 28 | E13-P04- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-08 | 2022-05-25 | 2021-10-08 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-P1560 | Contract Effectiveness / PO- W028 - Line pipe | چاه شماره 28 | P04 | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي-چاه 28 | 2021-06-23 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F01 | تاخير در دريافت پيش پرداخت | 2021-06-28 | 2021-09-03 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-15 | 2021-10-19 | 2021-10-15 | 2021-10-19 | 2021-10-15 | 2021-10-19 | 2021-10-15 | 2021-10-19 | 2021-10-15 | 2021-10-19 | 2021-10-15 | 2021-10-19 | 2021-10-15 | 2021-10-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | P02-EPC-P1560 | 44P02-EPC-P1560 | چاه شماره 28 | P04-F01- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-P1570 | Manufacturing / Fabrication / Supply- W028 - Line pipe | چاه شماره 28 | P06 | عدم امکان عقد قرارداد با سازنده لوله های جریانی-چاه 28 | 2021-06-23 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-20 | 2022-02-06 | 2021-10-20 | 2022-02-06 | 2021-10-20 | 2022-02-06 | 2021-10-20 | 2022-02-06 | 2021-10-20 | 2022-02-06 | 2021-10-20 | 2022-02-06 | 2021-10-20 | 2022-02-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | P02-EPC-P1570 | 45P02-EPC-P1570 | چاه شماره 28 | P06-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-P1670 | Tendering & Selection- W028 - WHCP | چاه شماره 28 | P04 | الزام كارفرما به خريد لوله هاي 6 و 8 اينچ از سازندگان داخلي-چاه 28 | 2021-06-23 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-11-07 | 2021-11-16 | 2021-11-07 | 2021-11-16 | 2021-11-07 | 2021-11-16 | 2021-11-07 | 2021-11-16 | 2021-11-07 | 2021-11-16 | 2021-11-07 | 2021-11-16 | 2021-11-07 | 2021-11-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 2022-03-15 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | P02-EPC-P1670 | 46P02-EPC-P1670 | چاه شماره 28 | P04-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-11-07 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-P1680 | Contract Effectiveness / PO- W028 - WHCP | چاه شماره 28 | P06 | عدم امکان عقد قرارداد با سازنده لوله های جریانی-چاه 28 | 2021-06-23 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | F01 | تاخير در دريافت پيش پرداخت | 2021-06-28 | 2021-09-03 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-11-17 | 2021-11-21 | 2021-11-17 | 2021-11-21 | 2021-11-17 | 2021-11-21 | 2021-11-17 | 2021-11-21 | 2021-11-17 | 2021-11-21 | 2021-11-17 | 2021-11-21 | 2021-11-17 | 2021-11-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | P02-EPC-P1680 | 47P02-EPC-P1680 | چاه شماره 28 | P06-F01- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-11-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-P1690 | Manufacturing / Fabrication / Supply- W028 - WHCP | چاه شماره 28 | P06 | عدم امکان عقد قرارداد با سازنده لوله های جریانی-چاه 28 | 2021-06-23 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-11-22 | 2022-02-19 | 2021-11-22 | 2022-02-19 | 2021-11-22 | 2022-02-19 | 2021-11-22 | 2022-02-19 | 2021-11-22 | 2022-02-19 | 2021-11-22 | 2022-02-19 | 2021-11-22 | 2022-02-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | P02-EPC-P1690 | 48P02-EPC-P1690 | چاه شماره 28 | P06-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-11-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-C1170 | Site Preparation W028 | چاه شماره 28 | F01 | تاخير در دريافت پيش پرداخت | 2021-06-28 | 2021-09-03 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-08-17 | 2021-09-05 | 2021-08-17 | 2021-09-05 | 2021-08-17 | 2021-09-05 | 2021-08-17 | 2021-09-05 | 2021-08-17 | 2021-09-05 | 2021-08-17 | 2021-09-05 | 2021-08-17 | 2021-09-05 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2021-09-15 | 0 | 2021-09-15 | 0 | 2021-09-15 | 0 | 2021-09-15 | 0 | 2021-09-15 | 0 | 2021-09-15 | 0 | 2021-09-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | P02-EPC-C1170 | 49P02-EPC-C1170 | چاه شماره 28 | F01-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-08-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-C1440 | Construction of Right of Way - W028 | چاه شماره 28 | P08 | عدم امکان آغاز ساخت لوله های جریانی-چاه 28 | 2021-06-23 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-02-19 | 2022-03-05 | 2022-02-19 | 2022-03-05 | 2022-02-19 | 2022-03-05 | 2022-02-19 | 2022-03-05 | 2022-02-19 | 2022-03-05 | 2022-02-19 | 2022-03-05 | 2022-02-19 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | P02-EPC-C1440 | 50P02-EPC-C1440 | چاه شماره 28 | P08-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-02-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-C1240 | Excavation of Mud Channel- W028 | چاه شماره 28 | E23 | عدم نهايي سازي طرح مديريت پسماند ساير چاه ها | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E24 | عدم نهايي سازي مدرک RG- چاه 28 | 2021-10-11 | 2022-04-10 | 2021-10-11 | 2022-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-09-24 | 2021-09-30 | 2021-09-24 | 2021-09-30 | 2021-09-24 | 2021-09-30 | 2021-09-24 | 2021-09-30 | 2021-09-24 | 2021-09-30 | 2021-09-24 | 2021-09-30 | 2021-09-24 | 2021-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | P02-EPC-C1240 | 51P02-EPC-C1240 | چاه شماره 28 | E23-E24- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-09-24 | 0 | 2021-09-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-C1310 | Installation sealling Layer of Mud Pit- W028 | چاه شماره 28 | E23 | عدم نهايي سازي طرح مديريت پسماند ساير چاه ها | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E24 | عدم نهايي سازي مدرک RG- چاه 28 | 2021-10-11 | 2022-04-10 | 2021-10-11 | 2022-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | E25 | عدم نهايي سازي نقشه های سیویل و سازه ای چاه- چاه 28 | 2021-10-19 | 2022-05-25 | 2021-10-19 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2021-10-05 | 2021-10-11 | 2021-10-05 | 2021-10-11 | 2021-10-05 | 2021-10-11 | 2021-10-05 | 2021-10-11 | 2021-10-05 | 2021-10-11 | 2021-10-05 | 2021-10-11 | 2021-10-05 | 2021-10-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 2022-04-30 | 2022-05-25 | 2022-04-30 | 2022-05-25 | 2022-04-30 | 2022-05-25 | 2022-04-30 | 2022-05-25 | 2022-04-30 | 2022-05-25 | 2022-04-30 | 2022-05-25 | 2022-04-30 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | P02-EPC-C1310 | 52P02-EPC-C1310 | چاه شماره 28 | E23-E24-E25 | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2021-10-11 | 2022-05-25 | 2021-10-11 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P02-EPC-C1460 | Construction & Installation of Shelter for Wellhead Control Panel- W028 | چاه شماره 28 | P14 | عدم امکان ساخت WHCP-چاه 18 | 2022-03-15 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A | دوره وقوع فعاليت | دوره بازبيني شده فعالیت | 2022-03-16 | 2022-03-20 | 2022-03-16 | 2022-03-20 | 2022-03-16 | 2022-03-20 | 2022-03-16 | 2022-03-20 | 2022-03-16 | 2022-03-20 | 2022-03-16 | 2022-03-20 | 2022-03-16 | 2022-03-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #N/A |  | دوره واقعیت فعالیت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | P02-EPC-C1460 | 53P02-EPC-C1460 | چاه شماره 28 | P14-- | دوره وقوع تأخیر مجاز به وقوع پیوسته (دوره تأثیر بر روي اجراي فعالیت) | 2022-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| مهر امضا پيمانكار | [8 empty] | مهر امضاء كارفرما | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Formulas:
عنوان علل تأخیر = IFERROR(VLOOKUP([كد تاخير (ID D s)],'4'!$C:$H,3,0),0)

## 7
|  |  |  | جدول شماره 7 : گانت چارت تأخیرات پروژه | [15 empty] | 1 |  |  |  | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24
رديف | كد تاخير | نوع تاخير | كد فعاليت | عنوان فعاليت/بسته متاثر از تاخيرات | بحراني/ غيربحراني | شروع ميلادي | پايان ميلادي | شروع ميلادي | پايان ميلادي | شروع ميلادي | پايان ميلادي | شروع ميلادي | پايان ميلادي | شروع ميلادي | پايان ميلادي | شروع ميلادي | پايان ميلادي | Total Float | طول دوره تاثير (ماه) | time axis 2021-07-01 to 2023-06-22 12:00
[8 empty] | شماره 1 | شماره 1 | شماره 2 | شماره 2 | شماره 3 | شماره 3 | شماره 4 | شماره 4 | شماره 5 | شماره 5 | time axis 2021-07-01 to 2023-06-22 12:00
[6 empty] | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | time axis 2021-07-01 to 2023-06-22 12:00
1 | M01-- | مديريتي | P12-EPC-E1000 | Endorsement Report For Basic Design & Scope of Work | بحراني | 2021-06-23 | 2021-07-22 | 2021-06-23 | 2021-09-07 | 2021-06-23 | 2021-09-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.377 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | E01-M02- | مديريتي مهندسي | P12-EPC-E1570 | Process Flow Diagram (PFD) | بحراني | 2021-07-04 | 2021-12-06 | 2021-07-04 | 2021-09-06 | 2021-07-04 | 2021-11-14 | 2021-07-04 | 2022-01-02 | 2021-07-04 | 2022-02-22 | 2021-07-04 | 2022-04-30 | 0 | 29.9016 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | M03-E01- | مديريتي مهندسي | P12-EPC-E1540 | Process Data Sheets For Gas Compressors Packages | بحراني | 2021-07-31 | 2021-12-06 | 2021-07-31 | 2021-11-27 | 2021-07-31 | 2022-01-29 | 2021-07-31 | 2022-05-08 | 0 | 0 | 0 | 0 | 0 | 19.082 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | M04-E01- | مديريتي مهندسي | P12-EPC-E2480 | Mechanical Data Sheets For Gas Compressors Packages | بحراني | 2021-08-12 | 2021-12-06 | 2021-08-12 | 2021-10-11 | 2021-08-12 | 2021-11-08 | 2021-08-12 | 2021-12-20 | 2021-08-12 | 2022-02-22 | 2021-08-12 | 2022-03-26 | 0 | 22.8852 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | M05-E05- | مديريتي مهندسي | P12-EPC-E7980 | TBE For Gas Compressors | بحراني | 2021-08-16 | 2022-02-13 | 2021-08-16 | 2022-02-27 | 2021-08-16 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.9836 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | M06-E02-E03 | مديريتي مهندسي | P12-EPC-E7970 | PMR For Gas Compressors | بحراني | 2021-09-03 | 2022-02-13 | 2021-09-12 | 2022-02-13 | 2021-09-03 | 2022-01-30 | 2021-09-03 | 2022-02-13 | 0 | 0 | 0 | 0 | 0 | 15.2787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | E04-- | مهندسي | P12-EPC-P1000 | Tendering & Selection For Gas Compressors | بحراني | 0 | 2022-03-05 | 2021-08-11 | 2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7541 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | P01-F01- | كالا مالي | P12-EPC-P1010 | Contract Effectiveness / PO For Gas Compressors | بحراني | 2021-10-10 | 2022-03-16 | 2021-10-10 | 2022-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | P02-- | كالا | P12-EPC-P1020 | Manufacturing / Fabrication / Supply For Gas Compressors | بحراني | 2021-11-09 | 2022-05-25 | 2021-11-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1459.3115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | M07-E06- | مديريتي مهندسي | P01-EPC-E1060 | Process Flow Diagram - W018S | غير بحراني | 2021-08-31 | 2021-10-13 | 2021-08-31 | 2022-05-25 | 2021-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | -1448.2623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | M08-E20- | مديريتي مهندسي | P01-EPC-E1370 | Plot Plan Drawing - W018S | غير بحراني | 2021-08-06 | 2021-12-27 | 2021-08-06 | 2021-12-27 | 2021-08-06 | 2021-12-12 | 2021-08-06 | 2022-03-05 | 0 | 0 | 0 | 0 | 14 | 15.8033 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | M09-E14- | مديريتي مهندسي | P01-EPC-E1860 | Specification For WHCP/HPU-W018S | غير بحراني | 2021-08-14 | 2022-03-27 | 2021-08-14 | 2022-03-27 | 2021-08-14 | 2022-01-02 | 2021-08-14 | 2022-01-30 | 2021-08-14 | 2022-03-27 | 0 | 0 | 22 | 24.918 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | M10-E20- | مديريتي مهندسي | P01-EPC-E2470 | Rough Grading Plans -W018S | غير بحراني | 2021-08-06 | 2021-12-27 | 2021-08-06 | 2021-12-27 | 2021-08-06 | 2021-11-06 | 2021-08-06 | 2022-01-22 | 2021-08-06 | 2022-03-05 | 2021-08-06 | 2022-03-13 | 9 | 27.3443 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | M11-E10- | مديريتي مهندسي | P01-EPC-E1070 | P&ID - W018S | غير بحراني | 2021-09-10 | 2021-12-15 | 2021-09-10 | 2021-12-15 | 2021-09-10 | 2021-11-27 | 2021-09-10 | 2022-01-03 | 2021-09-10 | 2022-05-01 | 0 | 0 | 39 | 17.1148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | M12-E08- | مديريتي مهندسي | P01-EPC-E1300 | Piping Material Specification-W018S | غير بحراني | 2022-01-02 | 2021-12-15 | 2022-01-02 | 2021-09-14 | 2022-01-02 | 2021-11-08 | 2022-01-02 | 0 | 0 | 0 | 0 | 0 | 153 | -1466.4918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | M13-E14- | مديريتي مهندسي | P01-EPC-E1870 | Data Sheets For WHCP/HPU - Wellheads-W018S | غير بحراني | 2021-08-24 | 2022-03-27 | 2021-08-24 | 2022-03-27 | 2021-08-24 | 2021-11-27 | 2021-08-24 | 2022-01-08 | 0 | 0 | 0 | 0 | 22 | 14.6557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | M14-E21- | مديريتي مهندسي | P01-EPC-E2460 | Civil and Structural drawings - W018S | غير بحراني | 2021-08-23 | 2022-03-05 | 2021-08-23 | 2022-03-05 | 2021-08-23 | 2022-01-11 | 2021-08-23 | 0 | 0 | 0 | 0 | 0 | 16 | -1445.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | M15-E20- | مديريتي مهندسي | P01-EPC-E2450 | General Civil Layout - W018S | غير بحراني | 2021-08-26 | 2021-12-27 | 2021-08-26 | 2021-12-27 | 2021-08-26 | 2021-09-04 | 2021-08-26 | 2021-09-18 | 2021-08-26 | 2021-11-02 | 2021-08-26 | 2021-11-27 | 14 | 10.3607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | M16-E08- | مديريتي مهندسي | P01-EPC-E1810 | Pipeline Corrosion Study & Material Selection Report-W018S | غير بحراني | 2022-03-02 | 2022-01-26 | 2022-03-02 | 2021-11-21 | 2022-03-02 | 0 | 2022-03-02 | 2022-04-01 | 0 | 0 | 0 | 0 | 192 | -1465.3443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | M17-E16- | مديريتي مهندسي | P01-EPC-E3590 | PMR For WHCP/HPU - W018S | غير بحراني | 2021-09-21 | 2022-01-16 | 2021-09-21 | 2022-01-16 | 2021-09-21 | 2022-01-16 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 7.6721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | M18-E10- | مديريتي مهندسي | P01-EPC-E3560 | PMR For Line pipes - W018S | غير بحراني | 2021-11-15 | 2021-12-15 | 2021-11-15 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0.98361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | E18-E16- | مهندسي | P01-EPC-P1670 | Tendering & Selection- W018S-WHCP | غير بحراني | 2021-10-15 | 2022-05-25 | 2021-10-15 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 7.2787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | E12-P03- | مهندسي كالا | P01-EPC-P1550 | Tendering & Selection- W018S- Line pipe | غير بحراني | 2021-10-27 | 0 | 2021-10-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | -1458.8852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | P09-F01- | كالا مالي | P01-EPC-P1680 | Contract Effectiveness / PO- W018S- WHCP | غير بحراني | 2021-10-25 | 0 | 2021-10-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -1458.8197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | P03-F01- | كالا مالي | P01-EPC-P1560 | Contract Effectiveness / PO- W018S-Line pipe | غير بحراني | 2021-11-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | P11-- | كالا | P01-EPC-P1690 | Manufacturing / Fabrication / Supply- W018S-WHCP | غير بحراني | 2021-10-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | P05-- | كالا | P01-EPC-P1570 | Manufacturing / Fabrication / Supply- W018S-Line pipe | غير بحراني | 2021-11-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | E20-E21-E22 | مهندسي | P01-EPC-C1150 | Supply & Installation sealling Layer of Mud pit- W018S | غير بحراني | 2021-10-02 | 2021-12-09 | 2021-10-02 | 2021-12-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 2.2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | P07-- | كالا | P01-EPC-C1330 | Construction of Right of Way- W018S | غير بحراني | 2022-01-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | P13-- | كالا | P01-EPC-C1350 | Construction & Installation of Shelter for Wellhead Control Panel-W018S | غير بحراني | 2022-02-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | M19-E07- | مديريتي مهندسي | P02-EPC-E1060 | Process Flow Diagram - W028 | غير بحراني | 2021-09-05 | 2022-05-25 | 2021-09-05 | 2022-05-25 | 2021-09-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | -1448.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | M20-E23- | مديريتي مهندسي | P02-EPC-E1380 | Plot Plan Drawing - W028 | غير بحراني | 2021-09-05 | 2022-05-25 | 2021-09-05 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 8.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | M21-E15- | مديريتي مهندسي | P02-EPC-E1860 | Specification For WHCP/HPU - W028 | غير بحراني | 2022-02-05 | 2022-03-27 | 2022-02-05 | 2022-03-27 | 2022-02-05 | 2022-01-02 | 2022-02-05 | 2022-01-30 | 2022-02-05 | 2022-03-27 | 0 | 0 | 197 | 1.9672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | M22-E20- | مديريتي مهندسي | P02-EPC-E2460 | General Civil Layout -W028 | بحراني | 2021-07-23 | 2021-12-27 | 2021-07-23 | 2021-12-27 | 2021-07-23 | 2022-03-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.1803 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | M23-E20-E21 | مديريتي مهندسي | P02-EPC-E2470 | Civil and Structural drawings -W028 | غير بحراني | 2022-01-20 | 2022-03-05 | 2022-01-20 | 2022-03-05 | 2022-01-20 | 2021-12-01 | 2022-01-20 | 2022-04-03 | 0 | 0 | 0 | 0 | 181 | 2.1967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | M24-E23- | مديريتي مهندسي | P02-EPC-E2480 | Rough Grading Plans -W028 | بحراني | 2021-07-23 | 2022-04-10 | 2021-07-23 | 2022-04-10 | 2021-07-23 | 2022-02-12 | 2021-07-23 | 2022-04-03 | 2021-07-23 | 0 | 0 | 0 | 0 | -1432.1639 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | M25-E11- | مديريتي مهندسي | P02-EPC-E3530 | PMR For Line Pipes - W028 | غير بحراني | 2021-09-18 | 2021-12-15 | 2021-09-18 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 2.8852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | M26-E11-E07 | مديريتي مهندسي | P02-EPC-E1070 | P&ID - W028 | غير بحراني | 2021-09-15 | 2022-05-25 | 2021-09-15 | 2022-05-25 | 2021-09-15 | 2021-11-27 | 2021-09-15 | 2022-01-03 | 2021-09-15 | 2022-05-01 | 0 | 0 | 44 | 21.7377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | M27-E15- | مديريتي مهندسي | P02-EPC-E1880 | Data Sheets For WHCP/HPU - Wellheads - W028 | غير بحراني | 2022-02-25 | 2022-03-27 | 2022-02-25 | 2022-03-27 | 2022-02-25 | 2021-11-27 | 2022-02-25 | 2022-01-08 | 0 | 0 | 0 | 0 | 197 | -3.541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | M28-E09- | مديريتي مهندسي | P02-EPC-E1820 | Pipeline Corrosion Study & Material Selection Report - W028 | غير بحراني | 2022-03-02 | 2022-01-26 | 2022-03-02 | 2021-11-21 | 2022-03-02 | 0 | 2022-03-02 | 2022-04-01 | 0 | 0 | 0 | 0 | 192 | -1465.3443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | M29-E17- | مديريتي مهندسي | P02-EPC-E3590 | PMR For WHCP/HPU - W028 | غير بحراني | 2021-10-16 | 2022-01-16 | 2021-10-16 | 2022-01-16 | 2021-10-16 | 2022-01-16 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 6.0328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | M30-E09- | مديريتي مهندسي | P02-EPC-E1180 | Piping Material Specification - W028 | غير بحراني | 2022-02-10 | 2022-01-26 | 2022-02-10 | 2021-12-26 | 2022-02-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | -1463.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | E13-P04- | مهندسي كالا | P02-EPC-P1550 | Tendering & Selection- W028 - Line pipe | غير بحراني | 2021-10-08 | 2022-05-25 | 2021-10-08 | 2021-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 2.2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | P04-F01- | كالا مالي | P02-EPC-P1560 | Contract Effectiveness / PO- W028 - Line pipe | غير بحراني | 2021-10-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | P06-- | كالا | P02-EPC-P1570 | Manufacturing / Fabrication / Supply- W028 - Line pipe | غير بحراني | 2021-10-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | P04-- | كالا | P02-EPC-P1670 | Tendering & Selection- W028 - WHCP | غير بحراني | 2021-11-07 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | P06-F01- | كالا مالي | P02-EPC-P1680 | Contract Effectiveness / PO- W028 - WHCP | غير بحراني | 2021-11-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | P06-- | كالا | P02-EPC-P1690 | Manufacturing / Fabrication / Supply- W028 - WHCP | غير بحراني | 2021-11-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | F01-- | مالي | P02-EPC-C1170 | Site Preparation W028 | بحراني | 2021-08-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | P08-- | كالا | P02-EPC-C1440 | Construction of Right of Way - W028 | غير بحراني | 2022-02-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | E23-E24- | مهندسي | P02-EPC-C1240 | Excavation of Mud Channel- W028 | غير بحراني | 2021-09-24 | 0 | 2021-09-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | -1457.8033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | E23-E24-E25 | مهندسي | P02-EPC-C1310 | Installation sealling Layer of Mud Pit- W028 | غير بحراني | 2021-10-11 | 2022-05-25 | 2021-10-11 | 2022-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 7.4098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 |  |  | P02-EPC-C1460 | Construction & Installation of Shelter for Wellhead Control Panel- W028 | غير بحراني | 2022-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
هم پوشاني كل تاخيرات | [18 empty] | 0 | 3 | 3 | 5 | 6 | 8 | 11 | 13 | 15 | 18 | 20 | 22 | 22 | 23 | 28 | 28 | 30 | 30 | 30 | 32 | 30 | 30 | 30 | 27 | 27 | 27 | 27 | 27 | 25 | 26 | 27 | 27 | 26 | 28 | 25 | 22 | 22 | 16 | 13 | 12 | 12 | 11 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مهر امضا پيمانكار | [16 empty] | مهر امضاء كارفرما
Formulas:
شروع ميلادي = VLOOKUP([رديف]&[كد فعاليت],'6'!$C:$T,'7'!H$4,0)
شروع ميلادي = VLOOKUP([رديف]&[كد فعاليت],'6'!$C:$T,'7'!J$4,0)
پايان ميلادي = VLOOKUP([رديف]&[كد فعاليت],'6'!$C:$T,'7'!I$4,0)
پايان ميلادي = VLOOKUP([رديف]&[كد فعاليت],'6'!$C:$T,'7'!K$4,0)

## Delay COde (hidden)
Code | M | مديريتي | I | فصول مشترك | E | مهندسي | P | كالا | C | اجرا | F | مالي | كد نهايي
M01-- | TRUE | مديريتي | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | مديريتي
E01-M02- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M03-E01- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M04-E01- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M05-E05- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M06-E02-E03 | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
E04-- | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مهندسي
P01-F01- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | TRUE | مالي | كالا مالي
P02-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
M07-E06- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M08-E20- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M09-E14- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M10-E20- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M11-E10- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M12-E08- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M13-E14- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M14-E21- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M15-E20- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M16-E08- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M17-E16- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M18-E10- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
E18-E16- | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مهندسي
E12-P03- | FALSE |  | FALSE |  | TRUE | مهندسي | TRUE | كالا | FALSE |  | FALSE |  | مهندسي كالا
P09-F01- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | TRUE | مالي | كالا مالي
P03-F01- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | TRUE | مالي | كالا مالي
P11-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
P05-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
E20-E21-E22 | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مهندسي
P07-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
P13-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
M19-E07- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M20-E23- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M21-E15- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M22-E20- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M23-E20-E21 | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M24-E23- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M25-E11- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M26-E11-E07 | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M27-E15- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M28-E09- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M29-E17- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
M30-E09- | TRUE | مديريتي | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مديريتي مهندسي
E13-P04- | FALSE |  | FALSE |  | TRUE | مهندسي | TRUE | كالا | FALSE |  | FALSE |  | مهندسي كالا
P04-F01- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | TRUE | مالي | كالا مالي
P06-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
P04-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
P06-F01- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | TRUE | مالي | كالا مالي
P06-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
F01-- | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | TRUE | مالي | مالي
P08-- | FALSE |  | FALSE |  | FALSE |  | TRUE | كالا | FALSE |  | FALSE |  | كالا
E23-E24- | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مهندسي
E23-E24-E25 | FALSE |  | FALSE |  | TRUE | مهندسي | FALSE |  | FALSE |  | FALSE |  | مهندسي
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
0 | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
مهر و امضاء پیمانکار

## DCI (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | [58 empty] | Last Status | Last Status | [32 empty] | D00 | Rev. D00 | [32 empty] | D01 | Rev. D01 | [32 empty] | D02 | Rev. D02 | [32 empty] | D03 | Rev. D03 | [32 empty] | D04 | Rev. D04 | [32 empty] | D05 | Rev. D05 | [32 empty] | D06 | Rev. D06 | [32 empty] | D07 | Rev. D07 | [32 empty] | D08 | Rev. D08 | [32 empty] | D09 | Rev. D09 | [32 empty] | D10 | Rev. D10 | [20 empty] | c | [6 empty] | c
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [12 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2 | [16 empty] | PEDCO 's Comment #1 |  |  |  |  | PEDCO 's Comment #2 |  |  |  |  | NISOC 's Comment #1 | [6 empty] | NISOC 's Comment #2
[8 empty] | Description | Doc. No. | Doc. No. | پروژه | بسته کاری | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال | F-Number | Final Status | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | Total Delay | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | Total Delay | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay |  | Actual Start Date | Actual Finish Date |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE (FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE (FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE (FARSI) | NISOC Comment Status | CRS No. | REMARK |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE (FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK |  | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE (FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK | REMARK | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK | REMARK | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK | REMARK | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK | REMARK | Last Rev. | Last POI | Last Transmittal NO. | Issue Date | Issue Date (Farsi) | NISOC Transmittal NO. | NISOC Issue Date | NISOC Issue Date (Farsi) | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | PEDCO Comment No. | PEDCO Comment Date | PEDCO Comment Date (Farsi) | PEDCO Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | NISOC Comment No. | NISOC Comment Date | NISOC Comment Date (Farsi) | EMAIL DATE | EMAIL DATE(FARSI) | NISOC Comment Status | CRS No. | REMARK
1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | GENERAL | [57 empty] | GP | [17 empty] | GP
1 | 1 | 0 | 0 | 0 | 0 | 0 | 1.1 | Project Management | [57 empty] | GP | [17 empty] | GP
1 | 1 | 0 | 0 | 0 | 1 | 0 | 1.1.1 | Project Plans | [57 empty] | GP | [17 empty] | GP
1 | 1 | 0 | 0 | 0 | 1 | 1 | 1.1.1.1 | Procurement & Services Contracting Plan | BK-GNRAL-HD-000-PM-CG-0001 | BK-GNRAL-HD-000-PM-CG-0001 | BK | GNRAL | HD | 000 | PM | CG | 0001 | F0Z-707035 | AFD | IFC | 2022-06-12 | 0 | 0 | -44724 | 0 | -44724 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 1900-01-13 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-29 | 0 |  | G00 | IFC | T-1016 | 2022-05-29 | 1401/03/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-1016 | 2022-05-29 | 1401/03/08
1 | 1 | 0 | 0 | 0 | 1 | 2 | 1.1.1.2 | Master Document List (MDL) & Updating | BK-GNRAL-PEDCO-000-GE-DN-0001 | BK-GNRAL-PEDCO-000-GE-DN-0001 | BK | GNRAL | PEDCO | 000 | GE | DN | 0001 | F0Z-707037 | AFD | IFC | 2021-07-21 | 2021-07-20 | 2021-07-18 | -1 | -2 | -3 | IFA | 2021-08-25 | 2021-09-12 | 0 | 18 | -44451 | -44433 | IFA | 2021-10-02 | 2021-10-11 | 0 | 9 | -44480 | -44471 | IFA | 2021-11-03 | 2021-10-31 | 0 | -3 | -44500 | -44503 | AFD | 2021-11-21 | 2021-12-14 | 0 | 23 | -44544 | -44521 | AFD | 2022-01-11 | 2022-01-21 | 2022-04-01 | 10 | 70 | 80 | Modify | 2021-07-07 | 2021-12-28 |  | G05 | AFD | T-0397 | 2021-12-28 | 1400/10/07 | 0 | 0 | 0 | 27286 | 2022-03-05 | 1400/12/14 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G04 | 0 | 0 | 0 | 0 | 0 | 1400-2294-379373 | 2022-01-21 | 1400/11/04 | 2022-04-01 | 1401/01/14 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0001 | 2021-07-07 | 1400/04/16 |  |  |  | L-8317 | 2021-07-26 | 1400/05/04 | CM |  | MOM-14001005 | 2021-08-03 | 1400/05/12 | CM |  | 1400/2291/136301 | 2021-07-20 | 1400/04/29 | 2021-07-18 | 1400/04/27 | CM | [10 empty] | G01-Rep | IFA | T-0032 | 2021-08-11 | 1400/05/20 |  |  |  | MDR-G01(Civil) | 2021-08-09 | 1400/05/18 | CM |  | MDR-G01(QC) | 2021-08-10 | 1400/05/19 | CM | BK-HD-PEDCO-CRS-0002(QC) | 1400-2290-180615 | 2021-08-31 | 1400/06/09 |  |  | CM | BK-PEDCO-NISOC-CRS-0002 | MOM-1400.06.21 | 2021-09-12 | 1400/06/21 |  |  | CM |  | MOM-QAQC |  | G02 | IFA | T-0097 | 2021-09-18 | 1400/06/27 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDEC-000-GE-DN-0001_G01 | [5 empty] | 1400-2290-225508 | 2021-10-06 | 1400/07/14 |  |  | CM | NISOC-CRS-BK-GNRAL-PEDEC-000-GE-DN-0001_G01 | 1400-2290-230666 | 2021-10-11 | 1400/07/19 |  |  | CM |  |  |  | G03 | IFA | T-0176 | 2021-10-20 | 1400/07/28 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDEC-000-GE-DN-0001_G02 | [5 empty] | صورتجلسه بررسی MDL-G03 (نظرات NISOC) | 2021-10-31 | 1400/08/09 |  |  | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G02 | [9 empty] | G04 | AFD | T-0211 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-GEN-00-02026 | 2021-11-16 | 1400/08/25 | CM | [6 empty] | 1400-2290-278160 | 2021-12-14 | 1400/08/23 |  |  | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G03 | [9 empty] | G05 | AFD | T-0397 | 2021-12-28 | 1400/10/07 |  |  |  | 27286 | 2022-03-05 | 1400/12/14 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-GE-DN-0001_G04 | [5 empty] | 1400-2294-379373 | 2022-01-21 | 1400/11/04 | 2022-04-01 | 1401/01/14 | AP
1 | 1 | 0 | 0 | 0 | 1 | 3 | 1.1.1.3 | EPC HSE Plan | BK-GNRAL-HD-000-PM-HP-0001 | BK-GNRAL-HD-000-PM-HP-0001 | BK | GNRAL | HD | 000 | PM | HP | 0001 | F0Z-707044 | AFC | IFC | 2021-08-11 | 0 | 0 | -44419 | 0 | -44419 | IFC | 2021-12-04 | 0 | 0 | -44534 | 0 | -44534 | IFA | 2022-01-19 | 0 | 0 | -44580 | 0 | -44580 | IFA | 2022-02-19 | 0 | 0 | -44611 | 0 | -44611 | AFC | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-20 | 2022-05-22 |  | G03 | AFC | T-0983 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0022 | 2021-07-28 | 1400/05/06 |  |  |  | L-9878 | 2021-08-11 | 1400/05/20 | C4-RJ | [22 empty] | G00 | IFC | T-0260 | 2021-11-20 | 1400/08/29 |  |  |  | BK-SUR-HSE-HSE-00-02241 | 2021-12-11 | 1400/09/20 | CM-C2 | PEDCO-CRS-BK-HD-PEDCO-CRS-0001-G00 | [21 empty] | G01 | IFA | T-0435 | 2022-01-05 | 1400/10/15 |  |  |  | BK-SUR-HSE-HSE-00-02704 | 2022-01-16 | 1400/10/26 | CM-C2 | PEDCO-CRS-BK-GNRAL-HD-000-PM-HP 0001_G00 | [21 empty] | G02 | IFA | T-0553 | 2022-02-05 | 1400/11/16 |  |  |  | BK-SUR-HSE-HSE-01-04311 | 2022-05-18 | 1401/02/28 | AP | PEDCO-CRS-BK-GNRAL-HD-000-PM-HP 0001_G01 | [21 empty] | G03 | AFC | T-0983 | 2022-05-22 | 1401/03/01
1 | 1 | 0 | 0 | 0 | 1 | 4 | 1.1.1.4 | Project Emergency Response Plan (ERP) | BK-GNRAL-HD-000-PM-HP-0002 | BK-GNRAL-HD-000-PM-HP-0002 | BK | GNRAL | HD | 000 | PM | HP | 0002 | F0Z-707045 | AFC | IFC | 2022-02-26 | 0 | 0 | -44618 | 0 | -44618 | IFA | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-22 | 0 |  | G01 | IFA | T-0984 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-BK-CRS-GNRAL-HD-000-PM-HP-0002_G00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0577 | 2022-02-12 | 1400/11/23 |  |  |  | BK-SUR-HSE-HSE-00-03369 | 2022-03-05 | 1400/12/15 | C4-RJ | [22 empty] | G01 | IFA | T-0984 | 2022-05-22 | 1401/03/01 | [7 empty] | PEDCO-BK-CRS-GNRAL-HD-000-PM-HP-0002_G00
1 | 1 | 0 | 0 | 0 | 1 | 5 | 1.1.1.5 | Guideline on Permit To Work System(PTWS) | BK-GNRAL-HD-000-PM-HP-0003 | BK-GNRAL-HD-000-PM-HP-0003 | BK | GNRAL | HD | 000 | PM | HP | 0003 | F0Z-707046 | IFI | IFI | 2021-12-15 | 0 | 0 | -44545 | 0 | -44545 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-01 | 2021-12-01 |  | D00 | IFI | T-0287 | 2021-12-01 | 1400/09/10 | 0 | 0 | 0 | BK-SUR-HSE-HSE-00-02240 | 2021-12-11 | 1400/09/11 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0287 | 2021-12-01 | 1400/09/10 |  |  |  | BK-SUR-HSE-HSE-00-02240 | 2021-12-11 | 1400/09/11 | AP
1 | 1 | 0 | 0 | 0 | 1 | 6 | 1.1.1.6 | HSE Operation Control Procedure | BK-GNRAL-HD-000-PM-HP-0004 | BK-GNRAL-HD-000-PM-HP-0004 | BK | GNRAL | HD | 000 | PM | HP | 0004 | F0Z-707047 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 1 | 7 | 1.1.1.7 | Environmental Management Plan (EMP) | BK-GNRAL-HD-000-PM-HP-0005 | BK-GNRAL-HD-000-PM-HP-0005 | BK | GNRAL | HD | 000 | PM | HP | 0005 | F0Z-707048 | AFC | IFC | 2022-03-07 | 0 | 0 | -44627 | 0 | -44627 | IFA | 2022-03-27 | 0 | 0 | -44647 | 0 | -44647 | IFA | 2022-04-11 | 0 | 0 | -44662 | 0 | -44662 | AFC | 2022-05-24 | 0 | 0 | -44705 | 0 | -44705 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-21 | 2022-05-10 |  | G03 | AFC | T-0924 | 2022-05-10 | 140102/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0620 | 2022-02-21 | 1400/12/02 |  |  |  | BK-SUR-HSE-HSE-00-03362 | 2022-03-06 | 1400/12/15 | CM-C2 | [22 empty] | G01 | IFA | T-0726 | 2022-03-13 | 1400/12/22 |  |  |  | BK-SUR-HSE-HSE-00-03553 | 2022-03-14 | 1400/12/23 | CM-C3 | PEDCO-BK-CRS-GNRAL-HD-000-PM-HP-0005_G00 | [21 empty] | G02 | IFA | T-0758 | 2022-03-28 | 1401/01/08 |  |  |  | BK-SUR-HSE-HSE-01-03697 | 2022-03-26 | 1401/01/09 | AP | PEDCO-BK-CRS-GNRAL-HD-000-PM-HP-0005_G01 | BK-SUR-HSE-HSE-01-03848 | 2022-04-11 | 1401/01/22 | AP | [17 empty] | G03 | AFC | T-0924 | 2022-05-10 | 140102/20
1 | 1 | 0 | 0 | 0 | 1 | 8 | 1.1.1.8 | Detailed Schedule & Updating | BK-GNRAL-HD-000-PM-SH-0001 | BK-GNRAL-HD-000-PM-SH-0001 | BK | GNRAL | HD | 000 | PM | SH | 0001 | F0Z-707039 | AFD | IFC | 2021-12-22 | 2022-12-04 | 0 | 347 | -44899 | -44552 | IFC | 2022-02-22 | 0 | 0 | -44614 | 0 | -44614 | IFA | 2022-04-10 | 0 | 0 | -44661 | 0 | -44661 | IFA | 2022-05-08 | 0 | 0 | -44689 | 0 | -44689 | AFD | 2022-05-23 | 0 | 0 | -44704 | 0 | -44704 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-08 | 2022-05-09 |  | G03 | AFD | T-0916 | 2022-05-09 | 1401/02/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0321 | 2021-12-08 | 1400/09/17 |  |  |  | BK-SUR-PLN-GEN-00-03227 | 2022-02-26 | 1400/12/07 | CM-C3 | [6 empty] | 19764 | 2021-12-12 | 1400/09/21 |  |  | RJ |  | MOM | 2022-12-04 | 1400/09/13 |  |  | CM |  |  |  | G00 | IFC | T-0567 | 2022-02-08 | 1400/11/19 | [7 empty] | PEDCO-CRS- BK-GNRAL-HD-000-PM-SH-0001_G00 | [21 empty] | G01 | IFA | T-0747 | 2022-03-27 | 1401/01/07 |  |  |  | BK-SUR-PLN-GEN-01-03733 | 2022-04-06 | 1401/01/16 | C4-RJ | PEDCO-CRS- BK-GNRAL-HD-000-PM-SH-0001-G01 | [21 empty] | G02 | IFA | T-0854 | 2022-04-24 | 1401/02/04 |  |  |  | 2406 | 2022-04-26 | 1401/02/06 | AP | PEDCO-CRS- BK-GNRAL-HD-000-PM-SH-0001_G01 | [21 empty] | G03 | AFD | T-0916 | 2022-05-09 | 1401/02/19
1 | 1 | 0 | 0 | 0 | 1 | 9 | 1.1.1.9 | Work Breakdown Structure (WBS) | BK-GNRAL-HD-000-PM-WB-0001 | BK-GNRAL-HD-000-PM-WB-0001 | BK | GNRAL | HD | 000 | PM | WB | 0001 | F0Z-707036 | AFD | IFC | 2021-11-30 | 0 | 0 | -44530 | 0 | -44530 | IFA | 2021-12-11 | 0 | 0 | -44541 | 0 | -44541 | IFA | 2022-01-11 | 0 | 0 | -44572 | 0 | -44572 | IFA | 2022-02-05 | 0 | 0 | -44597 | 0 | -44597 | AFD | 2022-02-16 | 0 | 0 | -44608 | 0 | -44608 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-16 | 2022-02-02 |  | G04 | AFD | T-0548 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | 25017 | 2022-02-08 | 1400/11/19 | AP | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0001_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0249 | 2021-11-16 | 1400/08/25 |  |  |  | Comment Sheets\PEDCO\1-Letters\17815 | 2021-11-22 | 1400/09/01 | CM | [22 empty] | G01 | IFA | T-0274 | 2021-11-27 | 1400/09/06 |  |  |  | Comment Sheets\PEDCO\1-Letters\19703 | 2021-12-12 | 1400/09/21 | CM | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0001-G01 | [21 empty] | G02 | IFA | T-0394 | 2021-12-28 | 1400/10/07 |  |  |  | BK-000-PLN-GEN-00-02632 | 2022-01-11 | 1400/10/21 | CM-C2 | [22 empty] | G03 | IFA | T-0484 | 2022-01-22 | 1400/11/02 | [7 empty] | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0001-G02 | [21 empty] | G04 | AFD | T-0548 | 2022-02-02 | 1400/11/13 |  |  |  | 25017 | 2022-02-08 | 1400/11/19 | AP | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0001_G03
1 | 1 | 0 | 0 | 0 | 1 | 10 | 1.1.1.10 | Cost Breakdown Structure (CBS) | BK-GNRAL-HD-000-PM-WB-0002 | BK-GNRAL-HD-000-PM-WB-0002 | BK | GNRAL | HD | 000 | PM | WB | 0002 | F0Z-707043 | AFD | IFC | 2021-11-30 | 0 | 0 | -44530 | 0 | -44530 | IFA | 2021-12-11 | 0 | 0 | -44541 | 0 | -44541 | IFA | 2022-01-11 | 0 | 0 | -44572 | 0 | -44572 | IFA | 2022-02-05 | 0 | 0 | -44597 | 0 | -44597 | AFD | 2022-02-16 | 0 | 0 | -44608 | 0 | -44608 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-16 | 2022-02-02 |  | G04 | AFD | T-0548 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | 25017 | 2022-02-08 | 1400/11/19 | AP | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0002_G03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0249 | 2021-11-16 | 1400/08/25 | [29 empty] | G01 | IFA | T-0274 | 2021-11-27 | 1400/09/06 | [7 empty] | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0002-G01 | [21 empty] | G02 | IFA | T-0394 | 2021-12-28 | 1400/10/07 |  |  |  | BK-000-PLN-GEN-00-02631 | 2022-01-11 | 1400/10/21 | CM-C2 | [22 empty] | G03 | IFA | T-0484 | 2022-01-22 | 1400/11/02 | [7 empty] | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0002-G02 | [21 empty] | G04 | AFD | T-0548 | 2022-02-02 | 1400/11/13 |  |  |  | 25017 | 2022-02-08 | 1400/11/19 | AP | PEDCO-CRS- BK-GNRAL-HD-000-PM-WB-0002_G03
1 | 1 | 0 | 0 | 0 | 1 | 11 | 1.1.1.11 | Material Equipment & Control Index (MCI) | BK-GNRAL-HD-000-PM-FO-0001 | BK-GNRAL-HD-000-PM-FO-0001 | BK | GNRAL | HD | 000 | PM | FO | 0001 | F0Z-707038 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 1 | 12 | 1.1.1.12 | Progress S-curves & Updating | BK-GNRAL-HD-000-PM-PG-0001 | BK-GNRAL-HD-000-PM-PG-0001 | BK | GNRAL | HD | 000 | PM | PG | 0001 | F0Z-707040 | AFD | IFC | 2022-03-06 | 0 | 0 | -44626 | 0 | -44626 | IFC | 2022-05-24 | 0 | 0 | -44705 | 0 | -44705 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-10 | 0 |  | G01 | IFC | T-0928 | 2022-05-10 | 1401/02/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS- BK-GNRAL-HD-000-PM-PG-0001-G00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0609 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-PLN-GEN-01-03734 | 2022-04-06 | 1401/01/17 | C4-RJ | [22 empty] | G01 | IFC | T-0928 | 2022-05-10 | 1401/02/20 | [7 empty] | PEDCO-CRS- BK-GNRAL-HD-000-PM-PG-0001-G00
1 | 1 | 0 | 0 | 0 | 1 | 13 | 1.1.1.13 | Production Capacity Realization Plan | BK-GNRAL-PEDCO-000-PM-PS-0001 | BK-GNRAL-PEDCO-000-PM-PS-0001 | BK | GNRAL | PEDCO | 000 | PM | PS | 0001 | 0 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 1 | 14 | 1.1.1.14 | Cash Flow Plan | BK-GNRAL-HD-000-PM-CP-0001 | BK-GNRAL-HD-000-PM-CP-0001 | BK | GNRAL | HD | 000 | PM | CP | 0001 | F0Z-707041 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 1 | 15 | 1.1.1.15 | Quality Plan | BK-GNRAL-PEDCO-000-PM-QP-0001 | BK-GNRAL-PEDCO-000-PM-QP-0001 | BK | GNRAL | PEDCO | 000 | PM | QP | 0001 | 0 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 1 | 16 | 1.1.1.16 | Project Organization Charts | BK-GNRAL-HD-000-PM-CH-0001 | BK-GNRAL-HD-000-PM-CH-0001 | BK | GNRAL | HD | 000 | PM | CH | 0001 | F0Z-707042 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 1 | 17 | 1.1.1.17 | Specification for Medical Services | BK-GNRAL-HD-000-PM-SP-0001 | BK-GNRAL-HD-000-PM-SP-0001 | BK | GNRAL | HD | 000 | PM | SP | 0001 | F0Z-707049 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 2 | 0 | 1.1.2 | Project Procedures
1 | 1 | 0 | 0 | 0 | 2 | 1 | 1.1.2.1 | Project Coordination Procedure | BK-GNRAL-HD-000-PM-PR-0001 | BK-GNRAL-HD-000-PM-PR-0001 | BK | GNRAL | HD | 000 | PM | PR | 0001 | F0Z-707055 | AFD | IFC | 2021-07-25 | 0 | 0 | -44402 | 0 | -44402 | IFA | 2021-08-09 | 0 | 0 | -44417 | 0 | -44417 | IFA | 2021-12-04 | 0 | 0 | -44534 | 0 | -44534 | AFD | 2022-03-06 | 0 | 0 | -44626 | 0 | -44626 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-11 | 2022-02-20 |  | G03 | AFD | T-0608 | 2022-02-20 | 1400/12/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0001 | 2021-07-11 | 1400/04/20 |  |  |  | L-8318 | 2021-07-26 | 1400/05/04 | CM | [22 empty] | G01 | IFA | T-0012 | 2021-07-26 | 1400/05/04 |  |  |  | RS-BK-GNRAL-HD-000-PM-PR-0001-G01 | 2021-09-14 | 1400/06/23 | CM | BK-HD-PEDCO-CRS-0001 | [21 empty] | G02 | IFA | T-0259 | 2021-11-20 | 1400/08/29 | [7 empty] | PEDCO -CRS-BK-GNRAL-HD-000-PM-PR-0001_G01 | [21 empty] | G03 | AFD | T-0608 | 2022-02-20 | 1400/12/01
1 | 1 | 0 | 0 | 0 | 2 | 2 | 1.1.2.2 | Project Control Procedure (WBS, PMS,Invoicing) | BK-GNRAL-HD-000-PM-PR-0002 | BK-GNRAL-HD-000-PM-PR-0002 | BK | GNRAL | HD | 000 | PM | PR | 0002 | - | AFD | IFC | 2021-08-07 | 0 | 0 | -44415 | 0 | -44415 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | G00 | IFC | T-0010 | 2021-07-24 | 1400/05/02 | 0 | 0 | 0 | BK-SUR-PLN-GEN-01-03735 | 2022-04-06 | 1401/01/17 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0010 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-PLN-GEN-01-03735 | 2022-04-06 | 1401/01/17 | C4-RJ
1 | 1 | 0 | 0 | 0 | 2 | 3 | 1.1.2.3 | Progress Measurement Procedure | BK-GNRAL-HD-000-PM-PR-0014 | BK-GNRAL-HD-000-PM-PR-0014 | BK | GNRAL | HD | 000 | PM | PR | 0014 | F0Z-707056 | AFD | IFC | 2021-12-04 | 0 | 0 | -44534 | 0 | -44534 | IFC | 2022-05-15 | 0 | 0 | -44696 | 0 | -44696 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-01 | 0 |  | G01 | IFC | T-0889 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | 5026 | 2022-05-29 | 1401/03/09 | AP | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0014_G00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0256 | 2021-11-20 | 1400/08/29 |  |  |  | BK-SUR-PLN-GEN-01-03736 | 2022-04-06 | 1401/01/17 | C4-RJ | [22 empty] | G01 | IFC | T-0889 | 2022-05-01 | 1401/02/11 |  |  |  | 5026 | 2022-05-29 | 1401/03/09 | AP | PEDCO-CRS-BK-GNRAL-HD-000-PM-PR-0014_G00
1 | 1 | 0 | 0 | 0 | 2 | 4 | 1.1.2.4 | Document Numbering Procedure | BK-GNRAL-HD-000-PM-PR-0003 | BK-GNRAL-HD-000-PM-PR-0003 | BK | GNRAL | HD | 000 | PM | PR | 0003 | F0Z-707057 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 2 | 5 | 1.1.2.5 | Change Control Procedure | BK-GNRAL-HD-000-PM-PR-0004 | BK-GNRAL-HD-000-PM-PR-0004 | BK | GNRAL | HD | 000 | PM | PR | 0004 | F0Z-707058 | AFD | IFC | 2021-08-07 | 0 | 0 | -44415 | 0 | -44415 | IFC | 2022-05-15 | 0 | 0 | -44696 | 0 | -44696 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-01 | 0 |  | G01 | IFC | T-0889 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | 5026 | 2022-05-29 | 1401/03/09 | AP | PEDCO-CRS- BK-GNRAL-HD-000-PM-PR-0004_G00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0010 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-PLN-GEN-01-03735 | 2022-04-06 | 1401/01/17 | C4-RJ | [22 empty] | G01 | IFC | T-0889 | 2022-05-01 | 1401/02/11 |  |  |  | 5026 | 2022-05-29 | 1401/03/09 | AP | PEDCO-CRS- BK-GNRAL-HD-000-PM-PR-0004_G00
1 | 1 | 0 | 0 | 0 | 2 | 6 | 1.1.2.6 | Invoicing Procedure | BK-GNRAL-HD-000-PM-PR-0005 | BK-GNRAL-HD-000-PM-PR-0005 | BK | GNRAL | HD | 000 | PM | PR | 0005 | F0Z-707059 | AFD | IFC | 2021-12-21 | 0 | 0 | -44551 | 0 | -44551 | IFA | 2022-05-09 | 0 | 0 | -44690 | 0 | -44690 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-25 | 0 |  | G01 | IFA | T-0859 | 2022-04-25 | 1401/02/06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS- BK-GNRAL-HD-000-PM-PR-0005_G00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFC | T-0301 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-PLN-GEN-01-03737 | 2022-04-06 | 1401/01/17 | C4-RJ | [22 empty] | G01 | IFA | T-0859 | 2022-04-25 | 1401/02/06 | [7 empty] | PEDCO-CRS- BK-GNRAL-HD-000-PM-PR-0005_G00
1 | 1 | 0 | 0 | 0 | 2 | 7 | 1.1.2.7 | Correspondence Procedure | BK-GNRAL-HD-000-PM-PR-0006 | BK-GNRAL-HD-000-PM-PR-0006 | BK | GNRAL | HD | 000 | PM | PR | 0006 | F0Z-707060 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 2 | 8 | 1.1.2.8 | Meeting Procedure | BK-GNRAL-HD-000-PM-PR-0007 | BK-GNRAL-HD-000-PM-PR-0007 | BK | GNRAL | HD | 000 | PM | PR | 0007 | F0Z-707061 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 2 | 9 | 1.1.2.9 | Reporting Procedure | BK-GNRAL-HD-000-PM-PR-0008 | BK-GNRAL-HD-000-PM-PR-0008 | BK | GNRAL | HD | 000 | PM | PR | 0008 | F0Z-707062 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 2 | 10 | 1.1.2.10 | Procurement & Services Contracting Procedure | BK-GNRAL-HD-000-PM-PR-0009 | BK-GNRAL-HD-000-PM-PR-0009 | BK | GNRAL | HD | 000 | PM | PR | 0009 | F0Z-707063 | AFD | IFC | 2021-12-06 | 0 | 0 | -44536 | 0 | -44536 | AFD | 2022-01-12 | 0 | 0 | -44573 | 0 | -44573 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-22 | 2021-12-29 |  | G01 | AFD | T-0402 | 2021-12-29 | 1400/10/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0265 | 2021-11-22 | 1400/09/01 |  |  |  | BK-SUR-ENG-MNG-00-02460 | 2021-12-27 | 1400/10/06 | AP | [22 empty] | G01 | AFD | T-0402 | 2021-12-29 | 1400/10/08
1 | 1 | 0 | 0 | 0 | 2 | 11 | 1.1.2.11 | Eng. Document Control Procedure | BK-GNRAL-HD-000-PM-PR-0010 | BK-GNRAL-HD-000-PM-PR-0010 | BK | GNRAL | HD | 000 | PM | PR | 0010 | F0Z-707064 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 2 | 12 | 1.1.2.12 | Material Control Procedure | BK-GNRAL-HD-000-PM-PR-0011 | BK-GNRAL-HD-000-PM-PR-0011 | BK | GNRAL | HD | 000 | PM | PR | 0011 | F0Z-707065 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 2 | 13 | 1.1.2.13 | Completion & Handover Procedure | BK-GNRAL-HD-000-PM-PR-0012 | BK-GNRAL-HD-000-PM-PR-0012 | BK | GNRAL | HD | 000 | PM | PR | 0012 | F0Z-707066 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 0 | 1.1.3 | Project Performance Report
1 | 1 | 0 | 0 | 0 | 3 | 1 | 1.1.3.1 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0001 | BK-GNRAL-HD-000-GE-RT-0001 | BK | GNRAL | HD | 000 | GE | RT | 0001 | F0Z-707067 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 2 | 1.1.3.2 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0002 | BK-GNRAL-HD-000-GE-RT-0002 | BK | GNRAL | HD | 000 | GE | RT | 0002 | F0Z-707068 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 3 | 1.1.3.3 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0003 | BK-GNRAL-HD-000-GE-RT-0003 | BK | GNRAL | HD | 000 | GE | RT | 0003 | F0Z-707069 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 4 | 1.1.3.4 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0004 | BK-GNRAL-HD-000-GE-RT-0004 | BK | GNRAL | HD | 000 | GE | RT | 0004 | F0Z-707070 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 5 | 1.1.3.5 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0005 | BK-GNRAL-HD-000-GE-RT-0005 | BK | GNRAL | HD | 000 | GE | RT | 0005 | F0Z-707071 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 6 | 1.1.3.6 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0006 | BK-GNRAL-HD-000-GE-RT-0006 | BK | GNRAL | HD | 000 | GE | RT | 0006 | F0Z-707072 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 7 | 1.1.3.7 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0007 | BK-GNRAL-HD-000-GE-RT-0007 | BK | GNRAL | HD | 000 | GE | RT | 0007 | F0Z-707073 | IFI | IFI | 2022-01-25 | 0 | 0 | -44586 | 0 | -44586 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-11 | 2022-01-11 |  | D00 | IFI | T-0449 | 2022-01-11 | 1400/10/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0449 | 2022-01-11 | 1400/10/20
1 | 1 | 0 | 0 | 0 | 3 | 8 | 1.1.3.8 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0008 | BK-GNRAL-HD-000-GE-RT-0008 | BK | GNRAL | HD | 000 | GE | RT | 0008 | F0Z-707074 | IFI | IFI | 2022-02-27 | 0 | 0 | -44619 | 0 | -44619 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-13 | 2022-02-13 |  | G00 | IFI | T-0585 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFI | T-0585 | 2022-02-13 | 1400/11/24
1 | 1 | 0 | 0 | 0 | 3 | 9 | 1.1.3.9 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0009 | BK-GNRAL-HD-000-GE-RT-0009 | BK | GNRAL | HD | 000 | GE | RT | 0009 | F0Z-707075 | IFI | IFI | 2022-03-27 | 0 | 0 | -44647 | 0 | -44647 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-13 | 2022-03-13 |  | G00 | IFI | T-0728 | 2022-03-13 | 1400/12/22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFI | T-0728 | 2022-03-13 | 1400/12/22
1 | 1 | 0 | 0 | 0 | 3 | 10 | 1.1.3.10 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0010 | BK-GNRAL-HD-000-GE-RT-0010 | BK | GNRAL | HD | 000 | GE | RT | 0010 | F0Z-707076 | IFI | IFI | 2022-04-25 | 0 | 0 | -44676 | 0 | -44676 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-11 | 2022-04-11 |  | G00 | IFI | T-0805 | 2022-04-11 | 1401/01/22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFI | T-0805 | 2022-04-11 | 1401/01/22
1 | 1 | 0 | 0 | 0 | 3 | 11 | 1.1.3.11 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0011 | BK-GNRAL-HD-000-GE-RT-0011 | BK | GNRAL | HD | 000 | GE | RT | 0011 | F0Z-707077 | IFI | IFI | 2022-05-28 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-14 | 2022-05-14 |  | G00 | IFI | T-0937 | 2022-05-14 | 1401/02/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | G00 | IFI | T-0937 | 2022-05-14 | 1401/02/24
1 | 1 | 0 | 0 | 0 | 3 | 12 | 1.1.3.12 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0012 | BK-GNRAL-HD-000-GE-RT-0012 | BK | GNRAL | HD | 000 | GE | RT | 0012 | F0Z-707078 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 13 | 1.1.3.13 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0013 | BK-GNRAL-HD-000-GE-RT-0013 | BK | GNRAL | HD | 000 | GE | RT | 0013 | F0Z-707079 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 14 | 1.1.3.14 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0014 | BK-GNRAL-HD-000-GE-RT-0014 | BK | GNRAL | HD | 000 | GE | RT | 0014 | F0Z-707080 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 15 | 1.1.3.15 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0015 | BK-GNRAL-HD-000-GE-RT-0015 | BK | GNRAL | HD | 000 | GE | RT | 0015 | F0Z-707081 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 16 | 1.1.3.16 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0016 | BK-GNRAL-HD-000-GE-RT-0016 | BK | GNRAL | HD | 000 | GE | RT | 0016 | F0Z-707082 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 17 | 1.1.3.17 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0017 | BK-GNRAL-HD-000-GE-RT-0017 | BK | GNRAL | HD | 000 | GE | RT | 0017 | F0Z-707083 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 18 | 1.1.3.18 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0018 | BK-GNRAL-HD-000-GE-RT-0018 | BK | GNRAL | HD | 000 | GE | RT | 0018 | F0Z-707084 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 19 | 1.1.3.19 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0019 | BK-GNRAL-HD-000-GE-RT-0019 | BK | GNRAL | HD | 000 | GE | RT | 0019 | F0Z-707085 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 20 | 1.1.3.20 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0020 | BK-GNRAL-HD-000-GE-RT-0020 | BK | GNRAL | HD | 000 | GE | RT | 0020 | F0Z-707086 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 21 | 1.1.3.21 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0021 | BK-GNRAL-HD-000-GE-RT-0021 | BK | GNRAL | HD | 000 | GE | RT | 0021 | F0Z-707087 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 22 | 1.1.3.22 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0022 | BK-GNRAL-HD-000-GE-RT-0022 | BK | GNRAL | HD | 000 | GE | RT | 0022 | F0Z-707088 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 23 | 1.1.3.23 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0023 | BK-GNRAL-HD-000-GE-RT-0023 | BK | GNRAL | HD | 000 | GE | RT | 0023 | F0Z-707089 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 24 | 1.1.3.24 | Monthly Progress Report | BK-GNRAL-HD-000-GE-RT-0024 | BK-GNRAL-HD-000-GE-RT-0024 | BK | GNRAL | HD | 000 | GE | RT | 0024 | F0Z-707090 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 31 | 1.1.3.31 | Delay Analysis Report | BK-GNRAL-HD-000-GE-RT-0050 | BK-GNRAL-HD-000-GE-RT-0050 | BK | GNRAL | HD | 000 | GE | RT | 0050 | F0Z-707091 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 32 | 1.1.3.32 | Delay Analysis Report | BK-GNRAL-HD-000-GE-RT-0051 | BK-GNRAL-HD-000-GE-RT-0051 | BK | GNRAL | HD | 000 | GE | RT | 0051 | F0Z-707092 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 33 | 1.1.3.33 | Delay Analysis Report | BK-GNRAL-HD-000-GE-RT-0052 | BK-GNRAL-HD-000-GE-RT-0052 | BK | GNRAL | HD | 000 | GE | RT | 0052 | F0Z-707093 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 0 | 0 | 0 | 3 | 34 | 1.1.3.34 | Delay Analysis Report | BK-GNRAL-HD-000-GE-RT-0053 | BK-GNRAL-HD-000-GE-RT-0053 | BK | GNRAL | HD | 000 | GE | RT | 0053 | F0Z-707094 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 1 | 0 | 0 | 0 | 0 | 1.1.1 | Camp Engineering Documents
1 | 1 | 1 | 1 | 0 | 0 | 0 | 1.1.1.1 | HVAC/Plumbing
1 | 1 | 1 | 1 | 0 | 1 | 0 | 1.1.1.1.1 | Drawing/Diagram
1 | 1 | 1 | 1 | 0 | 1 | 1 | 1.1.1.1.1.1 | Plumbing & Sewage Piping Layout | BK-GNRAL-PEDCO-220-HV-PY-0001 | BK-GNRAL-PEDCO-220-HV-PY-0001 | BK | GNRAL | PEDCO | 220 | HV | PY | 0001 | F4B-707095 | AFC | IFC | 2022-06-04 | 0 | 0 | -44716 | 0 | -44716 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-21 | 0 |  | D00 | IFC | T-0978 | 2022-05-21 | 1401/02/31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0978 | 2022-05-21 | 1401/02/31
1 | 1 | 1 | 1 | 0 | 1 | 2 | 1.1.1.1.1.2 | HVAC System Layout | BK-GNRAL-PEDCO-220-HV-PY-0002 | BK-GNRAL-PEDCO-220-HV-PY-0002 | BK | GNRAL | PEDCO | 220 | HV | PY | 0002 | F4B-707096 | AFC | IFC | 2022-05-28 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-14 | 0 |  | D00 | IFC | T-0938 | 2022-05-14 | 1401/02/24 | T-0938 | 2022-05-14 | 1401/02/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0938 | 2022-05-14 | 1401/02/24 | T-0938 | 2022-05-14 | 1401/02/24
1 | 1 | 1 | 1 | 0 | 2 | 0 | 1.1.1.1.2 | List
1 | 1 | 1 | 1 | 0 | 2 | 1 | 1.1.1.1.2.1 | HVAC Equipment Schedule | BK-GNRAL-PEDCO-220-HV-LI-0001 | BK-GNRAL-PEDCO-220-HV-LI-0001 | BK | GNRAL | PEDCO | 220 | HV | LI | 0001 | F0Z-707097 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 1 | 1 | 2 | 0 | 0 | 0 | 1.1.1.2 | Safety & Fire Fighting
1 | 1 | 1 | 2 | 0 | 1 | 0 | 1.1.1.2.1 | Drawing/Diagram
1 | 1 | 1 | 2 | 0 | 1 | 1 | 1.1.1.2.1.1 | Safety & Fire Fighting Equipment Location Layout | BK-GNRAL-PEDCO-220-SA-PY-0001 | BK-GNRAL-PEDCO-220-SA-PY-0001 | BK | GNRAL | PEDCO | 220 | SA | PY | 0001 | F2B-707098 | AFC | IFC | 44608 | 44618 | 44613 | 10 | -5 | 5 | IFA | 44703 | 0 | 0 | -44703 | 0 | -44703 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 0 |  | D01 | IFA | T-0908 | 2022-05-08 | 1401/02/18 | T-0908 | 2022-05-08 | 1401/02/18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-220-SA-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0543 | 2022-02-02 | 1400/11/13 | [13 empty] | 1400-2294-419386 | 2022-02-26 | 1400/12/07 | 2022-02-21 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0908 | 2022-05-08 | 1401/02/18 | T-0908 | 2022-05-08 | 1401/02/18 | [16 empty] | NISOC-CRS-BK-GNRAL-PEDCO-220-SA-PY-0001_D00
1 | 1 | 1 | 3 | 0 | 0 | 0 | 1.1.1.3 | Electrical
1 | 1 | 1 | 3 | 0 | 1 | 0 | 1.1.1.3.1 | Drawing/Diagram
1 | 1 | 1 | 3 | 0 | 1 | 1 | 1.1.1.3.1.1 | Lighting & Small Power Layout For Camp Area | BK-GNRAL-PEDCO-220-EL-PY-0001 | BK-GNRAL-PEDCO-220-EL-PY-0001 | BK | GNRAL | PEDCO | 220 | EL | PY | 0001 | F4P-707101 | AFC | IFC | 2022-01-15 | 2022-03-26 | 2022-04-01 | 70 | 6 | 76 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-01 | 0 |  | D00 | IFC | T-0428 | 2022-01-01 | 1400/10/14 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-02677 | 2022-01-15 | 1400/10/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-5251 | 2022-03-26 | 1401/01/09 | 2022-04-01 | 1401/01/14 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0428 | 2022-01-01 | 1400/10/14 |  |  |  | BK-SUR-ENG-ELE-00-02677 | 2022-01-15 | 1400/10/25 | CM-C2 | [6 empty] | 1401-2294-5251 | 2022-03-26 | 1401/01/09 | 2022-04-01 | 1401/01/14 | AP
1 | 1 | 1 | 3 | 0 | 1 | 2 | 1.1.1.3.1.2 | Earthing & Lightning Layout For Camp Area | BK-GNRAL-PEDCO-220-EL-PY-0002 | BK-GNRAL-PEDCO-220-EL-PY-0002 | BK | GNRAL | PEDCO | 220 | EL | PY | 0002 | F4P-707102 | AFC | IFC | 2022-06-12 | 0 | 0 | -44724 | 0 | -44724 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-29 | 0 |  | D00 | IFC | T-1021 | 2022-05-29 | 1401/03/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1021 | 2022-05-29 | 1401/03/08
1 | 1 | 1 | 3 | 0 | 1 | 3 | 1.1.1.3.1.3 | Cable Route for For Camp Area | BK-GNRAL-PEDCO-220-EL-DW-0001 | BK-GNRAL-PEDCO-220-EL-DW-0001 | BK | GNRAL | PEDCO | 220 | EL | DW | 0001 | F4P-707103 | AFC | IFC | 2022-01-18 | 2022-03-26 | 2022-04-01 | 67 | 6 | 73 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-04 | 0 |  | D00 | IFC | T-0428 | 2022-01-04 | 1400/10/14 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-02677 | 2022-01-15 | 1400/10/25 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-5251 | 2022-03-26 | 1401/01/09 | 2022-04-01 | 1401/01/14 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0428 | 2022-01-04 | 1400/10/14 |  |  |  | BK-SUR-ENG-ELE-00-02677 | 2022-01-15 | 1400/10/25 | CM-C3 | [6 empty] | 1401-2294-5251 | 2022-03-26 | 1401/01/09 | 2022-04-01 | 1401/01/14 | AP
1 | 1 | 1 | 3 | 0 | 2 | 0 | 1.1.1.3.2 | List
1 | 1 | 1 | 3 | 0 | 2 | 1 | 1.1.1.3.2.1 | Electrical Load List | BK-GNRAL-PEDCO-220-EL-LI-0001 | BK-GNRAL-PEDCO-220-EL-LI-0001 | BK | GNRAL | PEDCO | 220 | EL | LI | 0001 | F0Z-707104 | AFC | IFC | 44713 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-18 | 0 |  | D00 | IFC | T-0970 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04485 | 2022-05-29 | 1401/03/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0970 | 2022-05-18 | 1401/02/28 |  |  |  | BK-SUR-ENG-ELE-01-04485 | 2022-05-29 | 1401/03/09 | CM-C3
1 | 1 | 1 | 4 | 0 | 0 | 0 | 1.1.1.4 | Architecture
1 | 1 | 1 | 4 | 0 | 1 | 0 | 1.1.1.4.1 | Drawing/Diagram
1 | 1 | 1 | 4 | 0 | 1 | 1 | 1.1.1.4.1.1 | Architectural Drawing For NISOC Office Building | BK-GNRAL-PEDCO-220-AR-DW-0001 | BK-GNRAL-PEDCO-220-AR-DW-0001 | BK | GNRAL | PEDCO | 220 | AR | DW | 0001 | F4B-707105 | AFC | IFC | 2021-08-07 | 2021-08-04 | 2021-08-07 | -3 | 3 | 0 | IFA | 2021-10-25 | 2021-10-19 | 2021-10-30 | -6 | 11 | 5 | AFC | 2021-11-23 | 2021-11-16 | 2021-11-17 | -7 | 1 | -6 | AFC | 2022-03-26 | 2022-03-14 | 2022-03-26 | -12 | 12 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-03-12 |  | D03 | AFC | T-0714 | 2022-03-12 | 1400/12/21 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-03627 | 2022-03-16 | 1400/12/25 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448452 | 2022-03-14 | 1400/12/23 | 2022-03-26 | 1401/01/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0009 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ARC-00-01223 | 2021-07-31 | 1400/05/09 | CM-C2 | [6 empty] | 1400-2294-153629 | 2021-08-04 | 1400/05/13 | 2021-08-07 | 1400/05/16 | CM | [10 empty] | D01 | IFA | T-0150 | 2021-10-11 | 1400/07/19 |  |  |  | BK-SUR-ENG-ARC-00-01864 | 2021-10-30 | 1400/08/08 | CM-C2 | PEDCO-BK-GNRAL-PEDCO-220-AR-DW-0001_D01 | [5 empty] | 1400-2294-241759 | 2021-10-19 | 1400/07/27 | 2021-10-30 | 1400/08/08 | AP | NISOC-BK-GNRAL-PEDCO-220-AR-DW-0001_D01 | [9 empty] | D02 | AFC | T-0222 | 2021-11-09 | 1400/08/18 |  |  |  | BK-SUR-ENG-ARC-00-02010 | 2021-11-15 | 1400/08/24 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0001_D01 | [5 empty] | 1400-2294-277423 | 2021-11-16 | 1400/08/25 | 2021-11-17 | 1400/08/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-220-AR-DW-0001_D01 | [9 empty] | D03 | AFC | T-0714 | 2022-03-12 | 1400/12/21 |  |  |  | BK-SUR-ENG-ARC-00-03627 | 2022-03-16 | 1400/12/25 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0001_D02 | [5 empty] | 1400-2294-448452 | 2022-03-14 | 1400/12/23 | 2022-03-26 | 1401/01/09 | AP
1 | 1 | 1 | 4 | 0 | 1 | 2 | 1.1.1.4.1.2 | Architectural Drawing For NISOC Residental Building | BK-GNRAL-PEDCO-220-AR-DW-0002 | BK-GNRAL-PEDCO-220-AR-DW-0002 | BK | GNRAL | PEDCO | 220 | AR | DW | 0002 | F4B-707106 | AFC | IFC | 2021-10-27 | 2021-10-19 | 2022-01-22 | -8 | 95 | 87 | IFA | 2022-02-14 | 2022-02-05 | 2022-02-08 | -9 | 3 | -6 | AFC | 2022-02-26 | 2022-03-12 | 2022-03-14 | 14 | 2 | 16 | AFC | 2022-05-25 | 2022-05-21 | 2022-05-23 | -4 | 2 | -2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-13 | 2022-05-11 |  | D03 | AFC | T-0929 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | 1401-2294-69692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0159 | 2021-10-13 | 1400/07/21 |  |  |  | BK-SUR-ENG-ARC-00-02012 | 2021-11-15 | 1400/08/24 | CM-C2 | [6 empty] | 1400-2294-241755 | 2021-10-19 | 1400/07/27 | 2022-01-22 | 1400/11/02 | CM | [10 empty] | D01 | IFA | T-0529 | 2022-01-31 | 1400/11/11 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0002_D00 | [5 empty] | 1400-2294-397250 | 2022-02-05 | 1400/11/16 | 2022-02-08 | 1400/11/08 | AP | NISOC-CRS-BK-GNRAL-PEDCO-220-AR-DW-0002_D00 | [9 empty] | D02 | AFC | T-0570 | 2022-02-12 | 1400/11/23 | [13 empty] | 1400-2294-445206 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | AP | [10 empty] | D03 | AFC | T-0929 | 2022-05-11 | 1401/02/21 | [13 empty] | 1401-2294-69692 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | AP
1 | 1 | 1 | 4 | 0 | 1 | 3 | 1.1.1.4.1.3 | Architectural Drawing For Petro Iran Office Building | BK-GNRAL-PEDCO-220-AR-DW-0003 | BK-GNRAL-PEDCO-220-AR-DW-0003 | BK | GNRAL | PEDCO | 220 | AR | DW | 0003 | F4B-707107 | AFC | IFC | 2021-07-12 | 0 | 0 | -44389 | 0 | -44389 | IFA | 2021-08-14 | 0 | 0 | -44422 | 0 | -44422 | IFA | 2021-08-16 | 2021-08-11 | 0 | -5 | -44419 | -44424 | AFC | 2021-10-18 | 2021-09-14 | 2021-10-18 | -34 | 34 | 0 | AFC | 2021-11-21 | 0 | 0 | -44521 | 0 | -44521 | AFC | 2022-03-06 | 0 | 0 | -44626 | 0 | -44626 | Modify | 2021-06-28 | 2022-02-20 |  | D05 | AFC | T-0611 | 2022-02-20 | 1400/12/01 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03415 | 2022-03-08 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0003_D04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | L-0003 | 2021-06-28 | 1400/04/07 | [29 empty] | D01 | IFA | L-0029 | 2021-07-31 | 1400/05/09 | [29 empty] | D02 | IFA | L-0036 | 2021-08-02 | 1400/05/11 |  |  |  | L-10907 | 2021-08-28 | 1400/06/06 | AP | [6 empty] | 1400-2294-160920 | 2021-08-11 | 1400/05/20 |  |  | AP | [10 empty] | D03 | AFC | T-0136 | 2021-10-04 | 1400/07/12 |  |  |  | BK-SUR-ENG-ARC-00-01757 | 2021-10-18 | 1400/07/26 | CM-C2 | [6 empty] | 1400-2294-234322 | 2021-09-14 | 1400/07/22 | 2021-10-18 | 1400/07/26 | CM | [10 empty] | D04 | AFC | T-0213 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-ARC-00-01951 | 2021-11-08 | 1400/08/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0003_D03 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-220-AR-DW-0003_D03 | [9 empty] | D05 | AFC | T-0611 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-CIV-00-03415 | 2022-03-08 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0003_D04
1 | 1 | 1 | 4 | 0 | 1 | 4 | 1.1.1.4.1.4 | Architectural Drawing For Petro Iran Residental Building | BK-GNRAL-PEDCO-220-AR-DW-0007 | BK-GNRAL-PEDCO-220-AR-DW-0007 | BK | GNRAL | PEDCO | 220 | AR | DW | 0007 | F4B-707111 | AFC | IFC | 2021-07-12 | 0 | 0 | -44389 | 0 | -44389 | IFA | 2021-08-14 | 0 | 0 | -44422 | 0 | -44422 | IFA | 2021-08-16 | 2021-08-11 | 0 | -5 | -44419 | -44424 | AFC | 2021-10-18 | 2021-09-14 | 2021-10-18 | -34 | 34 | 0 | AFC | 2021-11-21 | 0 | 0 | -44521 | 0 | -44521 | AFC | 2022-02-26 | 0 | 0 | -44618 | 0 | -44618 | Modify | 2021-06-28 | 2022-02-12 |  | D05 | AFC | T-0575 | 2022-02-12 | 1400/11/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0007_D04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | L-0003 | 2021-06-28 | 1400/04/07 | [29 empty] | D01 | IFA | L-0029 | 2021-07-31 | 1400/05/09 | [29 empty] | D02 | IFA | L-0036 | 2021-08-02 | 1400/05/11 |  |  |  | L-10907 | 2021-08-28 | 1400/06/06 | AP | [6 empty] | 1400-2294-160920 | 2021-08-11 | 1400/05/20 |  |  | AP | [10 empty] | D03 | AFC | T-0136 | 2021-10-04 | 1400/07/12 |  |  |  | BK-SUR-ENG-ARC-00-01757 | 2021-10-18 | 1400/07/26 | CM-C2 | [6 empty] | 1400-2294-234322 | 2021-09-14 | 1400/07/22 | 2021-10-18 | 1400/07/26 | CM | [10 empty] | D04 | AFC | T-0213 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-ARC-00-01951 | 2021-11-08 | 1400/08/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0007_D03 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-220-AR-DW-0007_D03 | [9 empty] | D05 | AFC | T-0575 | 2022-02-12 | 1400/11/23 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0007_D04
1 | 1 | 1 | 4 | 0 | 1 | 5 | 1.1.1.4.1.5 | Architectural Drawing For Petro Iran/Contractor Restaurant | BK-GNRAL-PEDCO-220-AR-DW-0004 | BK-GNRAL-PEDCO-220-AR-DW-0004 | BK | GNRAL | PEDCO | 220 | AR | DW | 0004 | F4B-707108 | AFC | IFC | 2021-09-05 | 2021-08-11 | 0 | -25 | -44419 | -44444 | AFC | 2021-10-18 | 2021-09-14 | 2021-10-18 | -34 | 34 | 0 | AFC | 2022-03-12 | 2022-03-03 | 2022-03-07 | -9 | 4 | -5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2022-02-26 |  | D02 | AFC | T-0642 | 2022-02-26 | 1400/12/07 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-03414 | 2022-03-08 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0004_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-432759 | 2022-03-03 | 1400/12/12 | 2022-03-07 | 1400/12/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | L-0060 | 2021-08-22 | 1400/05/31 |  |  |  | L-10907 | 2021-08-28 | 1400/06/06 | AP | [6 empty] | 1400-2294-160920 | 2021-08-11 | 1400/05/20 |  |  | AP | [10 empty] | D01 | AFC | T-0136 | 2021-10-04 | 1400/07/12 |  |  |  | BK-SUR-ENG-ARC-00-01757 | 2021-10-18 | 1400/07/26 | CM-C2 | [6 empty] | 1400-2294-234322 | 2021-09-14 | 1400/07/22 | 2021-10-18 | 1400/07/26 | RJ | [10 empty] | D02 | AFC | T-0642 | 2022-02-26 | 1400/12/07 |  |  |  | BK-SUR-ENG-ARC-00-03414 | 2022-03-08 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0004_D01 | [5 empty] | 1400-2294-432759 | 2022-03-03 | 1400/12/12 | 2022-03-07 | 1400/12/16 | CM
1 | 1 | 1 | 4 | 0 | 1 | 6 | 1.1.1.4.1.6 | Architectural Drawing For Warehouse of Site Mobilization | BK-GNRAL-PEDCO-220-AR-DW-0005 | BK-GNRAL-PEDCO-220-AR-DW-0005 | BK | GNRAL | PEDCO | 220 | AR | DW | 0005 | F4B-707109 | AFC | IFC | 2021-09-05 | 2021-08-11 | 0 | -25 | -44419 | -44444 | AFC | 2022-01-12 | 2021-01-02 | 2022-01-04 | -375 | 367 | -8 | AFC | 2022-02-16 | 0 | 0 | -44608 | 0 | -44608 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2022-02-02 |  | D02 | AFC | T-0538 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-220-AR-DW-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | L-0061 | 2021-08-22 | 1400/05/31 |  |  |  | L-10907 | 2021-08-28 | 1400/06/06 | AP | [6 empty] | 1400-2294-160920 | 2021-08-11 | 1400/05/20 |  |  | AP | [10 empty] | D01 | AFC | T-0398 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-ARC-00-02553 | 2022-01-03 | 1400/10/13 | CM-C2 | [6 empty] | 1400-2294-346187 | 2021-01-02 | 1400/10/12 | 2022-01-04 | 1400/10/14 | AP | [10 empty] | D02 | AFC | T-0538 | 2022-02-02 | 1400/11/13 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0005_D01 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-220-AR-DW-0005_D01
1 | 1 | 1 | 4 | 0 | 1 | 7 | 1.1.1.4.1.7 | Architectural Drawing For Drivers Rest Room | BK-GNRAL-PEDCO-220-AR-DW-0006 | BK-GNRAL-PEDCO-220-AR-DW-0006 | BK | GNRAL | PEDCO | 220 | AR | DW | 0006 | F4B-707110 | AFC | IFC | 2021-07-12 | 0 | 0 | -44389 | 0 | -44389 | IFA | 2021-08-14 | 0 | 0 | -44422 | 0 | -44422 | IFA | 2021-08-16 | 2021-08-11 | 0 | -5 | -44419 | -44424 | AFC | 2021-10-18 | 2021-09-14 | 2021-10-18 | -34 | 34 | 0 | AFC | 2022-03-16 | 0 | 0 | -44636 | 0 | -44636 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-06-28 | 2022-03-02 |  | D04 | AFC | T-0659 | 2022-03-02 | 1400/12/11 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03417 | 2022-03-08 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0006_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | L-0003 | 2021-06-28 | 1400/04/07 | [29 empty] | D01 | IFA | L-0029 | 2021-07-31 | 1400/05/09 | [29 empty] | D02 | IFA | L-0036 | 2021-08-02 | 1400/05/11 |  |  |  | L-10907 | 2021-08-28 | 1400/06/06 | AP | [6 empty] | 1400-2294-160920 | 2021-08-11 | 1400/05/20 |  |  | AP | [10 empty] | D03 | AFC | T-0136 | 2021-10-04 | 1400/07/12 |  |  |  | BK-SUR-ENG-ARC-00-01757 | 2021-10-18 | 1400/07/26 | CM-C2 | [6 empty] | 1400-2294-234322 | 2021-09-14 | 1400/07/22 | 2021-10-18 | 1400/07/26 | RJ | [10 empty] | D04 | AFC | T-0659 | 2022-03-02 | 1400/12/11 |  |  |  | BK-SUR-ENG-CIV-00-03417 | 2022-03-08 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-220-AR-DW-0006_D03
1 | 1 | 1 | 5 | 0 | 0 | 0 | 1.1.1.5 | Civil
1 | 1 | 1 | 5 | 0 | 1 | 0 | 1.1.1.5.1 | Drawing/Diagram
1 | 1 | 1 | 5 | 0 | 1 | 1 | 1.1.1.5.1.1 | Overall Layout for Camp Area | BK-GNRAL-PEDCO-220-CV-PY-0001 | BK-GNRAL-PEDCO-220-CV-PY-0001 | BK | GNRAL | PEDCO | 220 | CV | PY | 0001 | F4A-707112 | AFC | IFC | 2021-08-07 | 2021-08-04 | 2021-08-07 | -3 | 3 | 0 | IFA | 2021-10-31 | 2021-10-19 | 2021-10-30 | -12 | 11 | -1 | AFC | 2021-11-29 | 2021-11-18 | 2021-11-21 | -11 | 3 | -8 | AFC | 2021-12-26 | 2021-11-15 | 2021-12-18 | -41 | 33 | -8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2021-12-12 |  | D03 | AFC | T-0325 | 2021-12-12 | 1400/09/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-PY-0001-D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-320633 | 2021-11-15 | 1400/09/24 | 2021-12-18 | 1400/09/27 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0008 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-CIV-00-01222 | 2021-07-31 | 1400/05/09 | CM-C2 | [6 empty] | 1400-2294-153664 | 2021-08-04 | 1400/05/13 | 2021-08-07 | 1400/05/16 | CM | [10 empty] | D01 | IFA | T-0165 | 2021-10-17 | 1400/07/25 |  |  |  | BK-SUR-ENG-CIV-00-01801 | 2021-10-20 | 1400/07/28 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-PY-0001-D00 | [5 empty] | 1400-2294-241712 | 2021-10-19 | 1400/07/27 | 2021-10-30 | 1400/08/08 | AP | NISOC-CRS-BK-GNRAL-PEDCO--220-CV-DW-0001-D00 | [9 empty] | D02 | AFC | T-0244 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-CIV-00-02054 | 2021-11-21 | 1400/08/30 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001-D01 | [5 empty] | 1400-2294-281432 | 2021-11-18 | 1400/08/27 | 2021-11-21 | 1400/08/30 | AP | NISOC-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001-D01 | [9 empty] | D03 | AFC | T-0325 | 2021-12-12 | 1400/09/21 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-PY-0001-D02 | [5 empty] | 1400-2294-320633 | 2021-11-15 | 1400/09/24 | 2021-12-18 | 1400/09/27 | CM
1 | 1 | 1 | 5 | 0 | 1 | 2 | 1.1.1.5.1.2 | Rough Grading Plan For Camp Area | BK-GNRAL-PEDCO-220-CV-DW-0001 | BK-GNRAL-PEDCO-220-CV-DW-0001 | BK | GNRAL | PEDCO | 220 | CV | DW | 0001 | F4S-707113 | AFC | IFC | 2021-10-04 | 2021-09-25 | 2021-09-29 | -9 | 4 | -5 | IFA | 2021-10-23 | 2021-10-14 | 0 | -9 | -44483 | -44492 | AFC | 2021-11-09 | 2021-10-30 | 2021-11-02 | -10 | 3 | -7 | AFC | 2021-11-20 | 2021-11-09 | 2021-11-14 | -11 | 5 | -6 | AFC | 2021-12-26 | 2021-11-15 | 2021-12-18 | -41 | 33 | -8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-20 | 2021-12-12 |  | D04 | AFC | T-0325 | 2021-12-12 | 1400/09/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001_D03 | 0 | 0 | 0 | 0 | 0 | 1400-2294-320633 | 2021-11-15 | 1400/09/24 | 2021-12-18 | 1400/09/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0110 | 2021-09-20 | 1400/06/29 |  |  |  | BK-SUR-ENG-CIV-00-01586 | 2021-09-25 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-212146 | 2021-09-25 | 1400/07/03 | 2021-09-29 | 1400/07/07 | CM | [10 empty] | D01 | IFA | T-0141 | 2021-10-09 | 1400/07/17 |  |  |  | BK-SUR-ENG-CIV-00-01689 | 2021-10-19 | 1400/07/27 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001-D00 | [5 empty] | 1400-2294-234323 | 2021-10-14 | 1400/07/22 |  |  | AP | NISOC-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001-D00 | [9 empty] | D02 | AFC | T-0185 | 2021-10-26 | 1400/08/04 |  |  |  | BK-SUR-ENG-CIV-00-01872 | 2021-10-31 | 1400/08/09 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001_D01 | [5 empty] | 1400-2294-253891 | 2021-10-30 | 1400/08/08 | 2021-11-02 | 1400/08/11 | AP | [10 empty] | D03 | AFC | T-0210 | 2021-11-06 | 1400/08/15 |  |  |  | BK-SUR-ENG-CIV-00-01925 | 2021-11-07 | 1400/08/16 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001_D02 | [5 empty] | 1400-2294-269293 | 2021-11-09 | 1400/08/18 | 2021-11-14 | 1400/08/23 | CM | [10 empty] | D04 | AFC | T-0325 | 2021-12-12 | 1400/09/21 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001_D03 | [5 empty] | 1400-2294-320633 | 2021-11-15 | 1400/09/24 | 2021-12-18 | 1400/09/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-220-CV-DW-0001_D03
1 | 1 | 1 | 6 | 0 | 0 | 0 | 1.1.1.6 | Structure
1 | 1 | 1 | 6 | 0 | 1 | 0 | 1.1.1.6.1 | Drawing/Diagram
1 | 1 | 1 | 6 | 0 | 1 | 1 | 1.1.1.6.1.1 | Foundation Location Drawing For Camp Area | BK-GNRAL-PEDCO-220-ST-DW-0001 | BK-GNRAL-PEDCO-220-ST-DW-0001 | BK | GNRAL | PEDCO | 220 | ST | DW | 0001 | F4Q-707114 | AFC | IFC | 2022-02-26 | 2022-02-16 | 2022-02-21 | -10 | 5 | -5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-12 | 0 |  | D00 | IFC | T-0576 | 2022-02-12 | 1400/11/23 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03160 | 2022-02-21 | 1400/12/02 | cm-c2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-413074 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0576 | 2022-02-12 | 1400/11/23 |  |  |  | BK-SUR-ENG-CIV-00-03160 | 2022-02-21 | 1400/12/02 | cm-c2 | [6 empty] | 1400-2294-413074 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | AP
1 | 1 | 1 | 6 | 0 | 1 | 2 | 1.1.1.6.1.2 | Structural Drawing For NISOC Residental Building | BK-GNRAL-PEDCO-220-ST-DW-0002 | BK-GNRAL-PEDCO-220-ST-DW-0002 | BK | GNRAL | PEDCO | 220 | ST | DW | 0002 | F4M-707115 | AFC | IFC | 2021-11-24 | 2021-11-14 | 2021-11-16 | -10 | 2 | -8 | IFA | 2021-12-26 | 2021-12-15 | 2021-12-18 | -11 | 3 | -8 | AFC | 2022-02-06 | 2022-03-12 | 2022-03-14 | 34 | 2 | 36 | AFC | 2022-05-29 | 2022-05-21 | 2022-05-23 | -8 | 2 | -6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 2022-05-15 |  | D03 | AFC | T-0953 | 2022-05-15 | 1401/02/25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-220-ST-DW-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-69912 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0224 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-STR-00-02017 | 2021-11-15 | 1400/08/24 | CM-C3 | [6 empty] | 1400-2294-275236 | 2021-11-14 | 1400/08/23 | 2021-11-16 | 1400/08/25 | CM | [10 empty] | D01 | IFA | T-0326 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-STR-00-02346 | 2021-12-18 | 1400/09/27 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-ST-DW-0002-D01 | [5 empty] | 1400-2294-320636 | 2021-12-15 | 1400/09/24 | 2021-12-18 | 1400/09/27 | AP | NISOC-CRS-BK-GNRAL-PEDCO-220-ST-DW-0002-D01 | [9 empty] | D02 | AFC | T-0494 | 2022-01-23 | 1400/11/03 |  |  |  | BK-SUR-ENG-STR-00-02861 | 2022-01-30 | 1400/11/10 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-220-ST-DW-0002_D01 | [5 empty] | 1400-2294-445105 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | AP | [10 empty] | D03 | AFC | T-0953 | 2022-05-15 | 1401/02/25 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-220-ST-DW-0002_D02 | [5 empty] | 1401-2294-69912 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | AP
1 | 1 | 1 | 6 | 0 | 1 | 3 | 1.1.1.6.1.3 | Structural Drawing For Warehouse | BK-GNRAL-PEDCO-220-ST-DW-0003 | BK-GNRAL-PEDCO-220-ST-DW-0003 | BK | GNRAL | PEDCO | 220 | ST | DW | 0003 | F4M-707116 | AFC | IFC | 2021-11-24 | 2022-04-10 | 2022-04-11 | 137 | 1 | 138 | IFA | 2022-05-22 | 2022-05-16 | 2022-05-23 | -6 | 7 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D01 | IFA | T-0911 | 2022-05-08 | 1401/02/18 | T-0911 | 2022-05-08 | 1401/02/18 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-220-ST-DW-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-63887 | 2022-05-16 | 1401/02/26 | 2022-05-23 | 1401/03/03 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0349 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-STR-00-01964 | 2021-11-10 | 1400/08/19 | C4-RJ | [6 empty] | 1401-2294-16809 | 2022-04-10 | 1401/01/21 | 2022-04-11 | 1401/01/22 | AP | [10 empty] | D01 | IFA | T-0911 | 2022-05-08 | 1401/02/18 | T-0911 | 2022-05-08 | 1401/02/18 |  |  |  |  | PEDCO-CRS-BK-GNRAL-PEDCO-220-ST-DW-0003_D00 | [5 empty] | 1401-2294-63887 | 2022-05-16 | 1401/02/26 | 2022-05-23 | 1401/03/03 | RJ
1 | 2 | 0 | 0 | 0 | 0 | 0 | 1.2 | Project Common Docs (Eng. & QA/QC)
1 | 2 | 0 | 1 | 0 | 0 | 0 | 1.2.1 | Basic Design Endorsement
1 | 2 | 0 | 1 | 0 | 0 | 1 | 1.2.1.1 | Endorsement Report For Basic Design & Scope of Work | BK-GNRAL-PEDCO-000-PM-RT-0001 | BK-GNRAL-PEDCO-000-PM-RT-0001 | BK | GNRAL | PEDCO | 000 | PM | RT | 0001 | F0Z-707117 | AFD | IFC | 44422 | 44436 | 44446 | 14 | 10 | 24 | AFD | 44472 | 44475 | 44495 | 3 | 20 | 23 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-31 | 2021-09-19 |  | D03 | AFD | T-0102 | 2021-09-19 | 1400/06/28 | 0 | 0 | 0 | BK-SUR-ENG-GEN-00-01620 | 2021-09-28 | 1400/07/06 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2290-223853 | 2021-10-06 | 1400/07/14 | 2021-10-26 | 1400/08/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | B00 | IFC | T-0023 | 2021-07-31 | 1400/05/09 | [13 empty] | 1400/2294/176098 | 2021-08-28 | 1400/06/06 | 2021-09-07 | 1400/06/16 | CM | [8 empty] | B00-Reject |  | D03 | AFD | T-0102 | 2021-09-19 | 1400/06/28 |  |  |  | BK-SUR-ENG-GEN-00-01620 | 2021-09-28 | 1400/07/06 | AP | [6 empty] | 1400-2290-223853 | 2021-10-06 | 1400/07/14 | 2021-10-26 | 1400/08/04 | CM
1 | 2 | 0 | 2 | 0 | 0 | 0 | 1.2.2 | Process
1 | 2 | 0 | 2 | 0 | 1 | 0 | 1.2.2.1 | Basis/Criteria
1 | 2 | 0 | 2 | 0 | 1 | 1 | 1.2.2.1.1 | Process Design Criteria | BK-GNRAL-PEDCO-000-PR-DC-0001 | BK-GNRAL-PEDCO-000-PR-DC-0001 | BK | GNRAL | PEDCO | 000 | PR | DC | 0001 | F0Z-707118 | AFD | IFC | 2021-08-10 | 2021-08-10 | 2021-08-08 | 0 | -2 | -2 | IFA | 2021-10-31 | 2021-11-28 | 2021-11-10 | 28 | -18 | 10 | AFD | 2022-01-15 | 2022-01-17 | 2022-01-19 | 2 | 2 | 4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-27 | 2022-01-01 |  | D02 | AFD | T-0411 | 2022-01-01 | 1400/10/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-368526 | 2022-01-17 | 1400/10/27 | 2022-01-19 | 1400/10/29 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 |  |  |  | L-9966 | 2021-08-15 | 1400/05/24 | CM | [6 empty] | 1400/2294/159308 | 2021-08-10 | 1400/05/19 | 2021-08-08 | 1400/05/17 | CM | [10 empty] | D01 | IFA | T-0160 | 2021-10-17 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01969 | 2021-11-10 | 1400/08/19 | AP | PEDCOCRS-BK-00-HD-000-PR-DC-0001_D00 | [5 empty] | 1400-2294-261463 | 2021-11-04 | 1400/08/13 | 2021-11-10 | 1400/08/19 | AP | NISOC-CRS-BK-00-HD-000-PR-DC-0001_D00 | 1400-2290-294976 | 2021-11-28 | 1400/09/07 |  |  | CM |  |  |  | D02 | AFD | T-0411 | 2022-01-01 | 1400/10/11 | [13 empty] | 1400-2294-368526 | 2022-01-17 | 1400/10/27 | 2022-01-19 | 1400/10/29 | AP
1 | 2 | 0 | 2 | 0 | 1 | 2 | 1.2.2.1.2 | Process Basis Of Design | BK-GNRAL-PEDCO-000-PR-DB-0001 | BK-GNRAL-PEDCO-000-PR-DB-0001 | BK | GNRAL | PEDCO | 000 | PR | DB | 0001 | F0Z-707119 | AFD | IFC | 2021-08-10 | 2021-08-10 | 2021-08-08 | 0 | -2 | -2 | IFA | 2021-10-31 | 2021-11-04 | 2021-11-10 | 4 | 6 | 10 | IFA | 2021-12-14 | 2021-12-30 | 2022-01-02 | 16 | 3 | 19 | IFA | 2022-02-07 | 2022-02-26 | 2022-02-20 | 19 | -6 | 13 | IFA | 2022-03-22 | 2022-04-19 | 2022-04-30 | 28 | 11 | 39 | IFA | 2022-05-24 | 0 | 0 | -44705 | 0 | -44705 | Modify | 2021-07-27 | 0 |  | D05 | IFA | T-0925 | 2022-05-10 | 1401/02/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 |  |  |  | L-9966 | 2021-08-15 | 1400/05/24 | CM | [6 empty] | 1400/2294/159308 | 2021-08-10 | 1400/05/19 | 2021-08-08 | 1400/05/17 | CM | [10 empty] | D01 | IFA | T-0160 | 2021-10-17 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01969 | 2021-11-10 | 1400/08/19 | CM-C3 | PEDCO-CRS-BK-00-HD-000-PR-DB-0001_D00 | [5 empty] | 1400-2294-261463 | 2021-11-04 | 1400/08/13 | 2021-11-10 | 1400/08/19 | CM | NISOC-CRS-BK-00-HD-000-PR-DB-0001_D00 | [9 empty] | D02 | IFA | T-0285 | 2021-11-30 | 1400/09/09 |  |  |  | BK-SUR-ENG-PCS-00-02363 | 2021-12-19 | 1400/09/28 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001-D01 | [5 empty] | 1400-2294-342083 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001-D01 | [9 empty] | D03 | IFA | T-0503 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-PCS-00-03096 | 2022-02-19 | 1400/11/30 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D02 | [5 empty] | 1400-2294-416040 | 2022-02-26 | 1400/12/07 | 2022-02-20 | 1400/12/01 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D02 | [9 empty] | D04 | IFA | T-0700 | 2022-03-08 | 1400/12/17 |  |  |  | BK-SUR-ENG-PCS-01-03783 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D03 | [5 empty] | 1401-2294-33692 | 2022-04-19 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D03 | [9 empty] | D05 | IFA | T-0925 | 2022-05-10 | 1401/02/20 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D04 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-DB-0001_D04
1 | 2 | 0 | 2 | 0 | 2 | 0 | 1.2.2.2 | Philosophy
1 | 2 | 0 | 2 | 0 | 2 | 1 | 1.2.2.2.1 | Drainage Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0001 | BK-GNRAL-PEDCO-000-PR-PH-0001 | [51 empty] | Deleted | 2021-07-27 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 | 0 | 0 | 0 | L-9804 | 2021-08-10 | 1400/05/19 | CM | 0 | BK-SUR-ENG-PCS-00-01352 | 2021-08-22 | 1400/05/31 | CM-C3 | 0 | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 2021-08-08 | 1400/05/17 | CM | 0 | 1400-2294-186540 | 2021-09-06 | 1400/06/15 | 0 | 0 | CM | 0 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 |  |  |  | L-9804 | 2021-08-10 | 1400/05/19 | CM |  | BK-SUR-ENG-PCS-00-01352 | 2021-08-22 | 1400/05/31 | CM-C3 |  | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 2021-08-08 | 1400/05/17 | CM |  | 1400-2294-186540 | 2021-09-06 | 1400/06/15 |  |  | CM
1 | 2 | 0 | 2 | 0 | 2 | 2 | 1.2.2.2.2 | Control Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0002 | BK-GNRAL-PEDCO-000-PR-PH-0002 | [51 empty] | Deleted | 2021-07-27 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 | 0 | 0 | 0 | L-9804 | 2021-08-10 | 1400/05/19 | CM | 0 | BK-SUR-ENG-PCS-00-01353 | 2021-08-22 | 1400/05/31 | C4-RJ | 0 | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 2021-08-08 | 1400/05/17 | CM | 0 | 1400/2294/186540 | 2021-09-06 | 1400/06/15 | 0 | 0 | CM | 0 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 |  |  |  | L-9804 | 2021-08-10 | 1400/05/19 | CM |  | BK-SUR-ENG-PCS-00-01353 | 2021-08-22 | 1400/05/31 | C4-RJ |  | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 2021-08-08 | 1400/05/17 | CM |  | 1400/2294/186540 | 2021-09-06 | 1400/06/15 |  |  | CM
1 | 2 | 0 | 2 | 0 | 2 | 3 | 1.2.2.2.3 | Flare,Blow Down And Relief Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0003 | BK-GNRAL-PEDCO-000-PR-PH-0003 | [51 empty] | Deleted | 2021-07-27 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 | 0 | 0 | 0 | L-9804 | 2021-08-10 | 1400/05/19 | CM | 0 | BK-SUR-ENG-PCS-00-01356 | 2021-08-22 | 1400/05/31 | CM-C3 | 0 | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 2021-08-08 | 1400/05/17 | CM | 0 | 1400/2294/186540 | 2021-09-06 | 1400/06/15 | 0 | 0 | CM | 0 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 |  |  |  | L-9804 | 2021-08-10 | 1400/05/19 | CM |  | BK-SUR-ENG-PCS-00-01356 | 2021-08-22 | 1400/05/31 | CM-C3 |  | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 2021-08-08 | 1400/05/17 | CM |  | 1400/2294/186540 | 2021-09-06 | 1400/06/15 |  |  | CM
1 | 2 | 0 | 2 | 0 | 2 | 4 | 1.2.2.2.4 | Isolation Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0004 | BK-GNRAL-PEDCO-000-PR-PH-0004 | [51 empty] | Deleted | 2021-07-27 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 | 0 | 0 | 0 | L-9804 | 2021-08-10 | 1400/05/19 | CM | 0 | BK-SUR-ENG-PCS-00-01358 | 2021-08-22 | 1400/05/31 | CM-C2 | 0 | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 2021-08-08 | 1400/05/17 | CM | 0 | 1400/2294/186540 | 2021-09-06 | 1400/06/15 | 0 | 0 | CM | 0 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 |  |  |  | L-9804 | 2021-08-10 | 1400/05/19 | CM |  | BK-SUR-ENG-PCS-00-01358 | 2021-08-22 | 1400/05/31 | CM-C2 |  | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 2021-08-08 | 1400/05/17 | CM |  | 1400/2294/186540 | 2021-09-06 | 1400/06/15 |  |  | CM
1 | 2 | 0 | 2 | 0 | 2 | 5 | 1.2.2.2.5 | ESD Philosophy | BK-GNRAL-PEDCO-000-PR-PH-0005 | BK-GNRAL-PEDCO-000-PR-PH-0005 | [51 empty] | Deleted | 2021-07-27 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 | 0 | 0 | 0 | L-9804 | 2021-08-10 | 1400/05/19 | CM | 0 | BK-SUR-ENG-PCS-00-01362 | 2021-08-22 | 1400/05/31 | CM-C2 | 0 | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 2021-08-08 | 1400/05/17 | CM | 0 | 1400/2294/186540 | 2021-09-06 | 1400/06/15 | 0 | 0 | CM | 0 | 0 |  | D00 | IFC | T-0014 | 2021-07-27 | 1400/05/05 |  |  |  | L-9804 | 2021-08-10 | 1400/05/19 | CM |  | BK-SUR-ENG-PCS-00-01362 | 2021-08-22 | 1400/05/31 | CM-C2 |  | 1400-2294-150565 | 2021-08-03 | 1400/05/12 | 2021-08-08 | 1400/05/17 | CM |  | 1400/2294/186540 | 2021-09-06 | 1400/06/15 |  |  | CM
1 | 2 | 0 | 2 | 0 | 3 | 0 | 1.2.2.3 | Drawing/Diagram
1 | 2 | 0 | 2 | 0 | 3 | 1 | 1.2.2.3.1 | Symbol & Legend For PFD and P&ID | BK-GNRAL-PEDCO-000-PR-PI-0001 | BK-GNRAL-PEDCO-000-PR-PI-0001 | [51 empty] | Deleted | 2021-08-04 | 0 |  | D00 | IFC | T-0030 | 2021-08-04 | 1400/05/13 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-01391 | 2021-08-24 | 1400/06/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-179417 | 2021-08-30 | 1400/06/08 | 2021-09-07 | 1400/06/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0030 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-PCS-00-01391 | 2021-08-24 | 1400/06/02 | CM-C3 | [6 empty] | 1400-2294-179417 | 2021-08-30 | 1400/06/08 | 2021-09-07 | 1400/06/16 | CM
1 | 2 | 0 | 3 | 0 | 0 | 0 | 1.2.3 | Mechanical
1 | 2 | 0 | 3 | 0 | 1 | 0 | 1.2.3.1 | Basis/Criteria
1 | 2 | 0 | 3 | 0 | 1 | 1 | 1.2.3.1.1 | Mechanical Design Criteria | BK-GNRAL-PEDCO-000-ME-DC-0001 | BK-GNRAL-PEDCO-000-ME-DC-0001 | BK | GNRAL | PEDCO | 000 | ME | DC | 0001 | F0Z-707120 | AFD | IFC | 44419 | 0 | 0 | -44419 | 0 | -44419 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 0 |  | D00 | IFC | T-0015 | 2021-07-28 | 1400/05/06 | 0 | 0 | 0 | BK-SUR-ENG-FXE-00-01277 | 2021-08-08 | 1400/05/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0015 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-FXE-00-01277 | 2021-08-08 | 1400/05/17 | CM-C3
1 | 2 | 0 | 3 | 0 | 2 | 0 | 1.2.3.2 | Specification
1 | 2 | 0 | 3 | 0 | 2 | 1 | 1.2.3.2.1 | Specification For Pressure Vessels | BK-GNRAL-PEDCO-000-ME-SP-0001 | BK-GNRAL-PEDCO-000-ME-SP-0001 | BK | GNRAL | PEDCO | 000 | ME | SP | 0001 | F0Z-707121 | AFD | IFC | 2021-08-11 | 0 | 0 | -44419 | 0 | -44419 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 0 |  | D00 | IFC | T-0015 | 2021-07-28 | 1400/05/06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0015 | 2021-07-28 | 1400/05/06
1 | 2 | 0 | 3 | 0 | 2 | 2 | 1.2.3.2.2 | Specification For Atmospheric Above Ground Welded Steel Tanks | BK-GNRAL-PEDCO-000-ME-SP-0002 | BK-GNRAL-PEDCO-000-ME-SP-0002 | BK | GNRAL | PEDCO | 000 | ME | SP | 0002 | F0Z-707122 | AFD | IFC | 2021-08-11 | 0 | 0 | -44419 | 0 | -44419 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 0 |  | D00 | IFC | T-0015 | 2021-07-28 | 1400/05/06 | 0 | 0 | 0 | BK-SUR-ENG-FXE-00-01277 | 2021-08-08 | 1400/05/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0015 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-FXE-00-01277 | 2021-08-08 | 1400/05/17 | CM-C3
1 | 2 | 0 | 3 | 0 | 3 | 0 | 1.2.3.3 | Drawing/Diagram
1 | 2 | 0 | 3 | 0 | 3 | 1 | 1.2.3.3.1 | Standard Detail Drawing For Pressure Vessels and Heat Exchangers | BK-GNRAL-PEDCO-000-ME-DW-0001 | BK-GNRAL-PEDCO-000-ME-DW-0001 | BK | GNRAL | PEDCO | 000 | ME | DW | 0001 | F2C-707123 | IFI | IFI | 2021-08-11 | 0 | 0 | -44419 | 0 | -44419 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 2021-07-28 |  | D00 | IFI | T-0015 | 2021-07-28 | 1400/05/06 | 0 | 0 | 0 | BK-SUR-ENG-FXE-00-01277 | 2021-08-08 | 1400/05/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0015 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-FXE-00-01277 | 2021-08-08 | 1400/05/17 | CM-C3
1 | 2 | 0 | 3 | 0 | 3 | 2 | 1.2.3.3.2 | Standard Detail Drawing For Storage Tanks | BK-GNRAL-PEDCO-000-ME-DW-0002 | BK-GNRAL-PEDCO-000-ME-DW-0002 | BK | GNRAL | PEDCO | 000 | ME | DW | 0002 | F2D-707124 | IFI | IFI | 2021-08-11 | 0 | 0 | -44419 | 0 | -44419 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 2021-07-28 |  | D00 | IFI | T-0015 | 2021-07-28 | 1400/05/06 | 0 | 0 | 0 | BK-SUR-ENG-FXE-00-01277 | 2021-08-08 | 1400/05/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0015 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-FXE-00-01277 | 2021-08-08 | 1400/05/17 | AP
1 | 2 | 0 | 4 | 0 | 0 | 0 | 1.2.4 | HVAC/Plumbing
1 | 2 | 0 | 4 | 0 | 1 | 0 | 1.2.4.1 | Basis/Criteria
1 | 2 | 0 | 4 | 0 | 1 | 1 | 1.2.4.1.1 | HVAC & Plumbing Design Criteria | BK-GNRAL-PEDCO-000-HV-DC-0001 | BK-GNRAL-PEDCO-000-HV-DC-0001 | BK | GNRAL | PEDCO | 000 | HV | DC | 0001 | F0Z-707125 | AFD | IFC | 44415 | 44433 | 0 | 18 | -44433 | -44415 | IFA | 44465 | 44452 | 44454 | -13 | 2 | -11 | AFD | 44628 | 44630 | 44633 | 2 | 3 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-02-22 |  | D02 | AFD | T-0624 | 2022-02-22 | 1400/12/03 | 0 | 0 | 0 | BK-SUR-ENG-HVC-00-03493 | 2022-03-13 | 1400/12/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-DC-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443215 | 2022-03-10 | 1400/12/19 | 2022-03-13 | 1400/12/22 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0005 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/173327 | 2021-08-25 | 1400/06/03 |  |  | AP | [10 empty] | D01 | IFA | T-0085 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-HVC-00-01522 | 2021-09-18 | 1400/06/27 | CM-C2 | [6 empty] | 1400-2294-197387 | 2021-09-13 | 1400/06/22 | 2021-09-15 | 1400/06/24 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-HV-DC-0001_D00 | [9 empty] | D02 | AFD | T-0624 | 2022-02-22 | 1400/12/03 |  |  |  | BK-SUR-ENG-HVC-00-03493 | 2022-03-13 | 1400/12/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-DC-0001_D01 | [5 empty] | 1400-2294-443215 | 2022-03-10 | 1400/12/19 | 2022-03-13 | 1400/12/22 | RJ
1 | 2 | 0 | 4 | 0 | 2 | 0 | 1.2.4.2 | Specification
1 | 2 | 0 | 4 | 0 | 2 | 1 | 1.2.4.2.1 | Specification For HVAC Equipment | BK-GNRAL-PEDCO-000-HV-SP-0001 | BK-GNRAL-PEDCO-000-HV-SP-0001 | BK | GNRAL | PEDCO | 000 | HV | SP | 0001 | F0Z-707126 | AFD | IFC | 2021-08-07 | 2021-08-25 | 0 | 18 | -44433 | -44415 | AFD | 2021-09-26 | 2021-09-13 | 2021-09-15 | -13 | 2 | -11 | AFD | 2021-10-24 | 2021-10-17 | 2021-10-19 | -7 | 2 | -5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2021-10-10 |  | D02 | AFD | T-0144 | 2021-10-10 | 1400/07/18 | 0 | 0 | 0 | BK-SUR-ENG-HVC-00-01791 | 2021-10-19 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-SP-0001-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-237984 | 2021-10-17 | 1400/07/25 | 2021-10-19 | 1400/07/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0005 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/173327 | 2021-08-25 | 1400/06/03 |  |  | AP | [10 empty] | D01 | AFD | T-0086 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-HVC-00-01519 | 2021-09-15 | 1400/06/24 | CM-C2 | [6 empty] | 1400-2294-197389 | 2021-09-13 | 1400/06/22 | 2021-09-15 | 1400/06/24 | AP | [10 empty] | D02 | AFD | T-0144 | 2021-10-10 | 1400/07/18 |  |  |  | BK-SUR-ENG-HVC-00-01791 | 2021-10-19 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-SP-0001-D01 | [5 empty] | 1400-2294-237984 | 2021-10-17 | 1400/07/25 | 2021-10-19 | 1400/07/27 | AP
1 | 2 | 0 | 4 | 0 | 2 | 2 | 1.2.4.2.2 | Specification For Duct Work & Pipe Work | BK-GNRAL-PEDCO-000-HV-SP-0002 | BK-GNRAL-PEDCO-000-HV-SP-0002 | BK | GNRAL | PEDCO | 000 | HV | SP | 0002 | F0Z-707127 | AFD | IFC | 2021-08-07 | 2021-08-25 | 0 | 18 | -44433 | -44415 | AFD | 2021-09-26 | 2021-09-13 | 2021-09-15 | -13 | 2 | -11 | AFD | 2021-10-24 | 2021-10-17 | 2021-10-19 | -7 | 2 | -5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2021-10-10 |  | D02 | AFD | T-0144 | 2021-10-10 | 1400/07/18 | 0 | 0 | 0 | BK-SUR-ENG-HVC-00-01791 | 2021-10-19 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-SP-0002-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-237984 | 2021-10-17 | 1400/07/25 | 2021-10-19 | 1400/07/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0005 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/173327 | 2021-08-25 | 1400/06/03 |  |  | AP | [10 empty] | D01 | AFD | T-0086 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-HVC-00-01519 | 2021-09-15 | 1400/06/24 | CM-C2 | [6 empty] | 1400-2294-197389 | 2021-09-13 | 1400/06/22 | 2021-09-15 | 1400/06/24 | AP | [10 empty] | D02 | AFD | T-0144 | 2021-10-10 | 1400/07/18 |  |  |  | BK-SUR-ENG-HVC-00-01791 | 2021-10-19 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-SP-0002-D01 | [5 empty] | 1400-2294-237984 | 2021-10-17 | 1400/07/25 | 2021-10-19 | 1400/07/27 | AP
1 | 2 | 0 | 4 | 0 | 3 | 0 | 1.2.4.3 | Drawing/Diagram
1 | 2 | 0 | 4 | 0 | 3 | 1 | 1.2.4.3.1 | Standard Drawing For HVAC & Plumbing | BK-GNRAL-PEDCO-000-HV-DW-0001 | BK-GNRAL-PEDCO-000-HV-DW-0001 | BK | GNRAL | PEDCO | 000 | HV | DW | 0001 | F4B-707128 | IFI | IFC | 2021-08-07 | 2021-08-25 | 0 | 18 | -44433 | -44415 | IFI | 2021-09-26 | 2021-09-13 | 2021-09-15 | -13 | 2 | -11 | IFI | 2021-10-24 | 2021-10-17 | 2021-10-19 | -7 | 2 | -5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2021-10-10 |  | D02 | IFI | T-0145 | 2021-10-10 | 1400/07/18 | 0 | 0 | 0 | BK-SUR-ENG-HVC-00-01791 | 2021-10-19 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-DW-0001-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-238019 | 2021-10-17 | 1400/07/25 | 2021-10-19 | 1400/07/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0005 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/173327 | 2021-08-25 | 1400/06/03 |  |  | AP | [10 empty] | D01 | IFI | T-0086 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-HVC-00-01519 | 2021-09-15 | 1400/06/24 | CM-C2 | [6 empty] | 1400-2294-197389 | 2021-09-13 | 1400/06/22 | 2021-09-15 | 1400/06/24 | AP | [10 empty] | D02 | IFI | T-0145 | 2021-10-10 | 1400/07/18 |  |  |  | BK-SUR-ENG-HVC-00-01791 | 2021-10-19 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-HV-DW-0001-D01 | [5 empty] | 1400-2294-238019 | 2021-10-17 | 1400/07/25 | 2021-10-19 | 1400/07/27 | AP
1 | 2 | 0 | 4 | 0 | 3 | 2 | 1.2.4.3.2 | Symbol & Legend For HVAC & Plumbing | BK-GNRAL-PEDCO-000-HV-DW-0002 | BK-GNRAL-PEDCO-000-HV-DW-0002 | BK | GNRAL | PEDCO | 000 | HV | DW | 0002 | F4B-707129 | AFC | IFC | 2021-09-05 | 0 | 0 | -44444 | 0 | -44444 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 0 |  | D00 | IFC | T-0055 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0055 | 2021-08-22 | 1400/05/31
1 | 2 | 0 | 5 | 0 | 0 | 0 | 1.2.5 | Piping
1 | 2 | 0 | 5 | 0 | 1 | 0 | 1.2.5.1 | Basis/Criteria
1 | 2 | 0 | 5 | 0 | 1 | 1 | 1.2.5.1.1 | Piping Design Criteria | BK-GNRAL-PEDCO-000-PI-DC-0001 | BK-GNRAL-PEDCO-000-PI-DC-0001 | BK | GNRAL | PEDCO | 000 | PI | DC | 0001 | F0Z-707130 | AFD | IFC | 44415 | 44438 | 44444 | 23 | 6 | 29 | IFA | 44495 | 44493 | 44522 | -2 | 29 | 27 | IFA | 44563 | 44559 | 44563 | -4 | 4 | 0 | AFD | 44591 | 44584 | 44586 | -7 | 2 | -5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-01-16 |  | D03 | AFD | T-0466 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-377387 | 2022-01-23 | 1400/11/03 | 2022-01-25 | 1400/11/05 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0006 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PIP-00-01266 | 2021-08-07 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/179375 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM | [10 empty] | D01 | IFA | T-0153 | 2021-10-12 | 1400/07/12 |  |  |  | BK-SUR-ENG-PIP-00-01776 | 2021-10-18 | 1400/07/26 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-DC-0001 | [5 empty] | 1400-2294-245975 | 2021-10-24 | 1400/08/02 | 2021-11-22 | 1400/09/01 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-DC-0001 | [9 empty] | D02 | IFA | T-0365 | 2021-12-19 | 1400/09/28 |  |  |  | BK-SUR-ENG-PIP-00-02490 | 2021-06-01 | 1400/10/11 | AP | [6 empty] | 1400-2294-341974 | 2021-12-29 | 1400/10/08 | 2022-01-02 | 1400/10/12 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-DC-0001_D01 | [9 empty] | D03 | AFD | T-0466 | 2022-01-16 | 1400/10/26 | [13 empty] | 1400-2294-377387 | 2022-01-23 | 1400/11/03 | 2022-01-25 | 1400/11/05 | AP
1 | 2 | 0 | 5 | 0 | 2 | 0 | 1.2.5.2 | Specification
1 | 2 | 0 | 5 | 0 | 2 | 1 | 1.2.5.2.1 | Specification For Color Coding and Marking | BK-GNRAL-PEDCO-000-PI-SP-0001 | BK-GNRAL-PEDCO-000-PI-SP-0001 | BK | GNRAL | PEDCO | 000 | PI | SP | 0001 | F0Z-707131 | AFD | IFC | 2021-08-23 | 0 | 0 | -44431 | 0 | -44431 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C2
1 | 2 | 0 | 5 | 0 | 2 | 2 | 1.2.5.2.2 | Specification For Transportation, Handling, Storage of pipes | BK-GNRAL-PEDCO-000-PI-SP-0002 | BK-GNRAL-PEDCO-000-PI-SP-0002 | BK | GNRAL | PEDCO | 000 | PI | SP | 0002 | F0Z-707132 | AFD | IFC | 2021-12-26 | 2021-12-20 | 2021-12-26 | -6 | 6 | 0 | IFA | 2022-03-20 | 2022-01-17 | 2022-04-19 | -62 | 92 | 30 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-12 | 0 |  | D01 | IFA | T-0677 | 2022-03-06 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03538 | 2022-03-14 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27248 | 2022-01-17 | 1401/01/28 | 2022-04-19 | 1401/01/30 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0330 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PIP-00-02422 | 2021-12-26 | 1400/10/05 | CM-C3 | [6 empty] | 1400-2294-327385 | 2021-12-20 | 1400/09/29 | 2021-12-26 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0677 | 2022-03-06 | 1400/12/14 |  |  |  | BK-SUR-ENG-PIP-00-03538 | 2022-03-14 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0002_D00 | [5 empty] | 1401-2294-27248 | 2022-01-17 | 1401/01/28 | 2022-04-19 | 1401/01/30 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0002_D00
1 | 2 | 0 | 5 | 0 | 2 | 3 | 1.2.5.2.3 | Specification For the Design of Piping in Mechanical Packages | BK-GNRAL-PEDCO-000-PI-SP-0003 | BK-GNRAL-PEDCO-000-PI-SP-0003 | BK | GNRAL | PEDCO | 000 | PI | SP | 0003 | F0Z-707133 | AFD | IFC | 2021-08-23 | 0 | 0 | -44431 | 0 | -44431 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3
1 | 2 | 0 | 5 | 0 | 2 | 4 | 1.2.5.2.4 | Specification For Metallic Pipes | BK-GNRAL-PEDCO-000-PI-SP-0004 | BK-GNRAL-PEDCO-000-PI-SP-0004 | BK | GNRAL | PEDCO | 000 | PI | SP | 0004 | F0Z-707134 | AFD | IFC | 2021-08-07 | 2021-08-30 | 2021-09-05 | 23 | 6 | 29 | IFA | 2021-10-13 | 2021-10-13 | 2021-10-18 | 0 | 5 | 5 | IFA | 2021-11-21 | 2021-11-24 | 2021-11-27 | 3 | 3 | 6 | IFA | 2021-12-21 | 2021-12-22 | 2021-12-26 | 1 | 4 | 5 | IFA | 2022-01-18 | 2022-01-16 | 2022-01-16 | -2 | 0 | -2 | IFA | 2022-03-09 | 2022-03-13 | 2022-04-03 | 4 | 21 | 25 | Modify | 2021-07-24 | 0 |  | D05 | IFA | T-0637 | 2022-02-23 | 1400/12/04 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03402 | 2022-03-08 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-447219 | 2022-03-13 | 1400/12/22 | 2022-04-03 | 1401/01/14 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0004_D04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0006 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/179375 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM | [10 empty] | D01 | IFA | T-0124 | 2021-09-29 | 1400/07/07 |  |  |  | BK-SUR-ENG-PIP-00-01734 | 2021-10-13 | 1400/07/21 | CM-C2 | [6 empty] | 1400-2294-236255 | 2021-10-13 | 1400/07/21 | 2021-10-18 | 1400/07/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0004_D00 | [9 empty] | D02 | IFA | T-0214 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-PIP-00-01985 | 2021-11-14 | 1400/08/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0004-D01 | [5 empty] | 1400-2294-290052 | 2021-11-24 | 1400/09/03 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0004-D01 | [9 empty] | D03 | IFA | T-0310 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02442 | 2021-12-26 | 1400/10/05 | AP | [6 empty] | 1400-2294-331639 | 2021-12-22 | 1400/10/01 | 2021-12-26 | 1400/10/05 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0004-D02 | [9 empty] | D04 | IFA | T-0424 | 2022-01-04 | 1400/10/14 |  |  |  | BK-SUR-ENG-PIP-00-02583 | 2022-01-05 | 1400/10/15 | AP | [6 empty] | 1400-2294-365876 | 2022-01-16 | 1400/10/26 | 2022-01-16 | 1400/10/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0004-D03 | [9 empty] | D05 | IFA | T-0637 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-PIP-00-03402 | 2022-03-08 | 1400/12/17 | AP | [6 empty] | 1400-2294-447219 | 2022-03-13 | 1400/12/22 | 2022-04-03 | 1401/01/14 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0004_D04
1 | 2 | 0 | 5 | 0 | 2 | 5 | 1.2.5.2.5 | Specification For Fittings, Flanges, Gaskets and Bolts | BK-GNRAL-PEDCO-000-PI-SP-0005 | BK-GNRAL-PEDCO-000-PI-SP-0005 | BK | GNRAL | PEDCO | 000 | PI | SP | 0005 | F0Z-707135 | AFD | IFC | 2021-08-07 | 2021-08-30 | 2021-09-05 | 23 | 6 | 29 | IFA | 2021-10-13 | 2021-10-13 | 2021-10-18 | 0 | 5 | 5 | AFD | 2021-11-21 | 2021-11-09 | 2021-11-14 | -12 | 5 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2021-11-07 |  | D02 | AFD | T-0216 | 2021-11-07 | 1400/08/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01983 | 2021-11-13 | 1400/08/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0005-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-269292 | 2021-11-09 | 1400/08/18 | 2021-11-14 | 1400/08/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0006 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PIP-00-01266 | 2021-08-07 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/179375 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM | [10 empty] | D01 | IFA | T-0124 | 2021-09-29 | 1400/07/07 |  |  |  | BK-SUR-ENG-PIP-00-01734 | 2021-10-13 | 1400/07/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0005_D00 | [5 empty] | 1400-2294-236255 | 2021-10-13 | 1400/07/21 | 2021-10-18 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0005_D00 | [9 empty] | D02 | AFD | T-0216 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-PIP-00-01983 | 2021-11-13 | 1400/08/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0005-D01 | [5 empty] | 1400-2294-269292 | 2021-11-09 | 1400/08/18 | 2021-11-14 | 1400/08/23 | AP
1 | 2 | 0 | 5 | 0 | 2 | 6 | 1.2.5.2.6 | Specification For Painting | BK-GNRAL-PEDCO-000-PI-SP-0006 | BK-GNRAL-PEDCO-000-PI-SP-0006 | BK | GNRAL | PEDCO | 000 | PI | SP | 0006 | F0Z-707136 | AFD | IFC | 2021-08-07 | 2021-08-30 | 2021-09-05 | 23 | 6 | 29 | IFA | 2021-10-13 | 2021-10-13 | 2021-10-18 | 0 | 5 | 5 | IFA | 2021-11-21 | 2021-11-24 | 2021-11-27 | 3 | 3 | 6 | IFA | 2021-12-21 | 2021-12-22 | 2021-12-26 | 1 | 4 | 5 | AFD | 2022-01-18 | 2022-01-16 | 2022-01-16 | -2 | 0 | -2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-01-04 |  | D04 | AFD | T-0424 | 2022-01-04 | 1400/10/14 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02583 | 2022-01-05 | 1400/10/15 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-365876 | 2022-01-16 | 1400/10/26 | 2022-01-16 | 1400/10/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0006 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PIP-00-01266 | 2021-08-07 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/179375 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM | [10 empty] | D01 | IFA | T-0124 | 2021-09-29 | 1400/07/07 |  |  |  | BK-SUR-ENG-PIP-00-01734 | 2021-10-13 | 1400/07/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0006-D00 | [5 empty] | 1400-2294-236255 | 2021-10-13 | 1400/07/21 | 2021-10-18 | 1400/07/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0006_D00 | [9 empty] | D02 | IFA | T-0214 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-PIP-00-01985 | 2021-11-14 | 1400/08/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0006-D01 | [5 empty] | 1400-2294-290052 | 2021-11-24 | 1400/09/03 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0006-D01 | [9 empty] | D03 | IFA | T-0310 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02442 | 2021-12-26 | 1400/10/05 | AP | [6 empty] | 1400-2294-331639 | 2021-12-22 | 1400/10/01 | 2021-12-26 | 1400/10/05 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0006-D02 | [9 empty] | D04 | AFD | T-0424 | 2022-01-04 | 1400/10/14 |  |  |  | BK-SUR-ENG-PIP-00-02583 | 2022-01-05 | 1400/10/15 | AP | [6 empty] | 1400-2294-365876 | 2022-01-16 | 1400/10/26 | 2022-01-16 | 1400/10/26 | AP
1 | 2 | 0 | 5 | 0 | 2 | 7 | 1.2.5.2.7 | Specification For Lining (Internal Protection of Equipment by Painting) | BK-GNRAL-PEDCO-000-PI-SP-0007 | BK-GNRAL-PEDCO-000-PI-SP-0007 | BK | GNRAL | PEDCO | 000 | PI | SP | 0007 | F0Z-707137 | AFD | IFC | 2021-08-23 | 0 | 0 | -44431 | 0 | -44431 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3
1 | 2 | 0 | 5 | 0 | 2 | 8 | 1.2.5.2.8 | Specification For Material Requirements in Sour service | BK-GNRAL-PEDCO-000-PI-SP-0008 | BK-GNRAL-PEDCO-000-PI-SP-0008 | BK | GNRAL | PEDCO | 000 | PI | SP | 0008 | F0Z-707138 | AFD | IFC | 2021-08-23 | 0 | 0 | -44431 | 0 | -44431 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3
1 | 2 | 0 | 5 | 0 | 2 | 9 | 1.2.5.2.9 | Specification For Manual Valves | BK-GNRAL-PEDCO-000-PI-SP-0009 | BK-GNRAL-PEDCO-000-PI-SP-0009 | BK | GNRAL | PEDCO | 000 | PI | SP | 0009 | F0Z-707139 | AFD | IFC | 2021-08-23 | 0 | 0 | -44431 | 0 | -44431 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3
1 | 2 | 0 | 5 | 0 | 2 | 10 | 1.2.5.2.10 | Specification For Plant Piping Systems Pressure Testing | BK-GNRAL-PEDCO-000-PI-SP-0010 | BK-GNRAL-PEDCO-000-PI-SP-0010 | BK | GNRAL | PEDCO | 000 | PI | SP | 0010 | F0Z-707140 | AFD | IFC | 2021-08-23 | 0 | 0 | -44431 | 0 | -44431 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3
1 | 2 | 0 | 5 | 0 | 2 | 11 | 1.2.5.2.11 | Specification For Welding of Plant Piping System | BK-GNRAL-PEDCO-000-PI-SP-0011 | BK-GNRAL-PEDCO-000-PI-SP-0011 | BK | GNRAL | PEDCO | 000 | PI | SP | 0011 | F0Z-707141 | AFD | IFC | 2021-08-23 | 0 | 0 | -44431 | 0 | -44431 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C2
1 | 2 | 0 | 5 | 0 | 2 | 12 | 1.2.5.2.12 | Specification For Flexibility Analysis | BK-GNRAL-PEDCO-000-PI-SP-0012 | BK-GNRAL-PEDCO-000-PI-SP-0012 | BK | GNRAL | PEDCO | 000 | PI | SP | 0012 | F0Z-707142 | AFD | IFC | 2021-08-23 | 0 | 0 | -44431 | 0 | -44431 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3
1 | 2 | 0 | 5 | 0 | 2 | 13 | 1.2.5.2.13 | Specification For Coating Of Underground Piping | BK-GNRAL-PEDCO-000-PI-SP-0013 | BK-GNRAL-PEDCO-000-PI-SP-0013 | BK | GNRAL | PEDCO | 000 | PI | SP | 0013 | F0Z-707143 | AFD | IFC | 2021-08-07 | 2021-08-30 | 2021-09-05 | 23 | 6 | 29 | IFA | 2021-10-13 | 2021-10-13 | 2021-10-18 | 0 | 5 | 5 | IFA | 2021-11-21 | 2021-11-24 | 2021-11-27 | 3 | 3 | 6 | IFA | 2021-12-21 | 2021-12-22 | 2021-12-26 | 1 | 4 | 5 | IFA | 2022-01-18 | 2022-01-16 | 2022-01-16 | -2 | 0 | -2 | AFD | 2022-03-09 | 2022-03-06 | 2022-03-08 | -3 | 2 | -1 | Modify | 2021-07-24 | 2022-02-23 |  | D05 | AFD | T-0638 | 2022-02-23 | 1400/12/04 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03396 | 2022-03-08 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-436238 | 2022-03-06 | 1400/12/15 | 2022-03-08 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0006 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PIP-00-01266 | 2021-08-07 | 1400/05/16 | CM-C2 | [6 empty] | 1400/2294/179375 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM | [10 empty] | D01 | IFA | T-0124 | 2021-09-29 | 1400/07/07 |  |  |  | BK-SUR-ENG-PIP-00-01734 | 2021-10-13 | 1400/07/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0013_D00 | [5 empty] | 1400-2294-236255 | 2021-10-13 | 1400/07/21 | 2021-10-18 | 1400/07/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0013_D00 | [9 empty] | D02 | IFA | T-0214 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-PIP-00-01985 | 2021-11-14 | 1400/08/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0013-D01 | [5 empty] | 1400-2294-290052 | 2021-11-24 | 1400/09/03 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0013-D01 | [9 empty] | D03 | IFA | T-0310 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02442 | 2021-12-26 | 1400/10/05 | AP | [6 empty] | 1400-2294-331639 | 2021-12-22 | 1400/10/01 | 2021-12-26 | 1400/10/05 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0013-D02 | [9 empty] | D04 | IFA | T-0424 | 2022-01-04 | 1400/10/14 |  |  |  | BK-SUR-ENG-PIP-00-02583 | 2022-01-05 | 1400/10/15 | AP | [6 empty] | 1400-2294-365876 | 2022-01-16 | 1400/10/26 | 2022-01-16 | 1400/10/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0013-D03 | [9 empty] | D05 | AFD | T-0638 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-PIP-00-03396 | 2022-03-08 | 1400/12/17 | AP | [6 empty] | 1400-2294-436238 | 2022-03-06 | 1400/12/15 | 2022-03-08 | 1400/12/17 | AP
1 | 2 | 0 | 5 | 0 | 2 | 14 | 1.2.5.2.14 | Specification For Pipe Support | BK-GNRAL-PEDCO-000-PI-SP-0014 | BK-GNRAL-PEDCO-000-PI-SP-0014 | BK | GNRAL | PEDCO | 000 | PI | SP | 0014 | F0Z-707144 | AFD | IFC | 2021-08-23 | 0 | 0 | -44431 | 0 | -44431 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3
1 | 2 | 0 | 5 | 0 | 2 | 15 | 1.2.5.2.15 | Specification For Piping Construction, Fabrication & Erection | BK-GNRAL-PEDCO-000-PI-SP-0015 | BK-GNRAL-PEDCO-000-PI-SP-0015 | BK | GNRAL | PEDCO | 000 | PI | SP | 0015 | F0Z-707145 | AFD | IFC | 2021-08-23 | 0 | 0 | -44431 | 0 | -44431 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C2
1 | 2 | 0 | 5 | 0 | 2 | 16 | 1.2.5.2.16 | Specification For Piping Design & Plant Layout | BK-GNRAL-PEDCO-000-PI-SP-0016 | BK-GNRAL-PEDCO-000-PI-SP-0016 | BK | GNRAL | PEDCO | 000 | PI | SP | 0016 | F0Z-707146 | AFD | IFC | 2021-08-23 | 0 | 0 | -44431 | 0 | -44431 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0039 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | 1400/06/14 | CM-C3
1 | 2 | 0 | 5 | 0 | 2 | 17 | 1.2.5.2.17 | Specification For Cleaning and Flushing | BK-GNRAL-PEDCO-000-PI-SP-0017 | BK-GNRAL-PEDCO-000-PI-SP-0017 | BK | GNRAL | PEDCO | 000 | PI | SP | 0017 | F0Z-707147 | AFD | IFC | 2021-09-07 | 2021-09-12 | 2021-09-14 | 5 | 2 | 7 | IFA | 2021-10-18 | 2021-12-04 | 2021-11-08 | 47 | -26 | 21 | AFD | 2021-12-29 | 0 | 0 | -44559 | 0 | -44559 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-24 | 2021-12-15 |  | D02 | AFD | T-0350 | 2021-12-15 | 1400/09/24 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02374 | 2021-12-19 | 1400/09/28 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0017-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0065 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PIP-00-01517 | 2021-09-14 | 1400/06/23 | CM-C3 | [6 empty] | 1400-2294-194218 | 2021-09-12 | 1400-06-21 | 2021-09-14 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0137 | 2021-10-04 | 1400/07/12 |  |  |  | BK-SUR-ENG-PIP-00-01729 | 2021-10-13 | 1400/07/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0017-D00 | [5 empty] | 1400-2294-261499 | 2021-12-04 | 1400/08/13 | 2021-11-08 | 1400/08/17 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0017-D00 | [9 empty] | D02 | AFD | T-0350 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-PIP-00-02374 | 2021-12-19 | 1400/09/28 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0017-D01
1 | 2 | 0 | 5 | 0 | 2 | 18 | 1.2.5.2.18 | Specification For HDPE Pipes | BK-GNRAL-PEDCO-000-PI-SP-0018 | BK-GNRAL-PEDCO-000-PI-SP-0018 | BK | GNRAL | PEDCO | 000 | PI | SP | 0018 | F0Z-707148 | AFD | IFC | 2021-09-07 | 2021-09-12 | 2021-09-14 | 5 | 2 | 7 | AFD | 2021-11-02 | 2021-10-23 | 2021-10-25 | -10 | 2 | -8 | AFD | 2021-12-26 | 2021-12-20 | 2021-12-25 | -6 | 5 | -1 | AFD | 2022-02-05 | 2022-01-23 | 2022-01-30 | -13 | 7 | -6 | AFD | 2022-03-19 | 0 | 0 | -44639 | 0 | -44639 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-24 | 2022-03-05 |  | D04 | AFD | T-0674 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0018_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0065 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PIP-00-01517 | 2021-09-14 | 1400/06/23 | CM-C3 | [6 empty] | 1400-2294-194218 | 2021-09-12 | 1400-06-21 | 2021-09-14 | 1400/06/23 | AP | [10 empty] | D01 | AFD | T-0173 | 2021-10-19 | 1400/07/27 |  |  |  | BK-SUR-ENG-PIP-00-01790 | 2021-10-19 | 1400/07/27 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0018-D00 | [5 empty] | 1400-2294-243783 | 2021-10-23 | 1400/08/01 | 2021-10-25 | 1400/08/03 | AP | [10 empty] | D02 | AFD | T-0328 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PIP-00-02382 | 2021-12-20 | 1400/09/29 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0018-D01 | [5 empty] | 1400-2294-327374 | 2021-12-20 | 1400/09/29 | 2021-12-25 | 1400/10/04 | AP | [10 empty] | D03 | AFD | T-0483 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-PIP-00-02756 | 2022-01-21 | 1400/11/01 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0018-D02 | [5 empty] | 1400-2294-377397 | 2022-01-23 | 1400/11/03 | 2022-01-30 | 1400/11/10 | RJ | [10 empty] | D04 | AFD | T-0674 | 2022-03-05 | 1400/12/14 | [19 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0018_D03
1 | 2 | 0 | 5 | 0 | 2 | 19 | 1.2.5.2.19 | Specification For Insulation | BK-GNRAL-PEDCO-000-PI-SP-0019 | BK-GNRAL-PEDCO-000-PI-SP-0019 | BK | GNRAL | PEDCO | 000 | PI | SP | 0019 | F0Z-707149 | AFD | IFC | 2021-09-07 | 2021-09-12 | 2021-09-14 | 5 | 2 | 7 | IFA | 2021-10-13 | 2021-10-13 | 2021-10-18 | 0 | 5 | 5 | AFD | 2021-11-21 | 2021-11-09 | 2021-11-14 | -12 | 5 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-24 | 2021-11-07 |  | D02 | AFD | T-0216 | 2021-11-07 | 1400/08/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-01983 | 2021-11-13 | 1400/08/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0019-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-269292 | 2021-11-09 | 1400/08/18 | 2021-11-14 | 1400/08/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0065 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PIP-00-01517 | 2021-09-14 | 1400/06/23 | CM-C3 | [6 empty] | 1400-2294-194218 | 2021-09-12 | 1400-06-21 | 2021-09-14 | 1400/06/23 | AP | [10 empty] | D01 | IFA | T-0124 | 2021-09-29 | 1400/07/07 |  |  |  | BK-SUR-ENG-PIP-00-01734 | 2021-10-13 | 1400/07/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0019_D00 | [5 empty] | 1400-2294-236255 | 2021-10-13 | 1400/07/21 | 2021-10-18 | 1400/07/26 | AP | [10 empty] | D02 | AFD | T-0216 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-PIP-00-01983 | 2021-11-13 | 1400/08/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0019-D01 | [5 empty] | 1400-2294-269292 | 2021-11-09 | 1400/08/18 | 2021-11-14 | 1400/08/23 | AP
1 | 2 | 0 | 5 | 0 | 3 | 0 | 1.2.5.3 | Procedure/Plan
1 | 2 | 0 | 5 | 0 | 3 | 1 | 1.2.5.3.1 | 3D-Model (PDMS) Review Procedure | BK-GNRAL-PEDCO-000-PI-PR-0001 | BK-GNRAL-PEDCO-000-PI-PR-0001 | BK | GNRAL | PEDCO | 000 | PI | PR | 0001 | F0Z-707150 | AFC | IFC | 2021-08-07 | 2021-08-30 | 2021-09-05 | 23 | 6 | 29 | IFA | 2021-12-11 | 2021-12-05 | 2021-12-07 | -6 | 2 | -4 | AFC | 2022-01-30 | 2022-01-23 | 2022-01-25 | -7 | 2 | -5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-01-16 |  | D02 | AFC | T-0466 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-377387 | 2022-01-23 | 1400/11/03 | 2022-01-25 | 1400/11/05 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0006 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PIP-00-01266 | 2021-08-07 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/179375 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM | [10 empty] | D01 | IFA | T-0273 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-PIP-00-02385 | 2021-12-21 | 1400/09/30 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-PR-0001-D00 | [5 empty] | 1400-2294-303942 | 2021-12-05 | 1400/09/14 | 2021-12-07 | 1400/09/16 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PI-PR-0001_D00 | [9 empty] | D02 | AFC | T-0466 | 2022-01-16 | 1400/10/26 | [13 empty] | 1400-2294-377387 | 2022-01-23 | 1400/11/03 | 2022-01-25 | 1400/11/05 | AP
1 | 2 | 0 | 5 | 0 | 3 | 2 | 1.2.5.3.2 | Piping Hydrostatic Test Diagram - Sub Surface | BK-GNRAL-PEDCO-000-PI-PR-0002 | BK-GNRAL-PEDCO-000-PI-PR-0002 | BK | GNRAL | PEDCO | 000 | PI | PR | 0002 | 0 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 6 | 0 | 0 | 0 | 1.2.6 | Pipeline
1 | 2 | 0 | 6 | 0 | 1 | 0 | 1.2.6.1 | Basis/Criteria
1 | 2 | 0 | 6 | 0 | 1 | 1 | 1.2.6.1.1 | Pipeline Design Criteria | BK-GNRAL-PEDCO-000-PL-DC-0001 | BK-GNRAL-PEDCO-000-PL-DC-0001 | BK | GNRAL | PEDCO | 000 | PL | DC | 0001 | F0Z-707151 | AFD | IFC | 44450 | 44497 | 44551 | 47 | 54 | 101 | IFA | 44591 | 44590 | 44591 | -1 | 1 | 0 | AFD | 44608 | 44618 | 44620 | 10 | 2 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-28 | 2022-02-02 |  | D02 | AFD | T-0537 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-426685 | 2022-02-26 | 1400/12/07 | 2022-02-28 | 1400/12/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0068 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-PPL-00-02396 | 2021-12-21 | 1400/09/30 | CM-C2 | [6 empty] | 1400-2294-215883 | 2021-10-28 | 1400/07/06 | 2021-12-21 | 1400/09/30 | CM | [10 empty] | D01 | IFA | T-0467 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-PPL-00-02747 | 2022-01-19 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DC-0001_D00 | [5 empty] | 1400-2294-386710 | 2022-01-29 | 1400/11/09 | 2022-01-30 | 1400/11/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DC-0001_D00 | [9 empty] | D02 | AFD | T-0537 | 2022-02-02 | 1400/11/13 | [13 empty] | 1400-2294-426685 | 2022-02-26 | 1400/12/07 | 2022-02-28 | 1400/12/09 | AP
1 | 2 | 0 | 6 | 0 | 2 | 0 | 1.2.6.2 | Specification
1 | 2 | 0 | 6 | 0 | 2 | 1 | 1.2.6.2.1 | Specification For Line Pipes | BK-GNRAL-PEDCO-000-PL-SP-0002 | BK-GNRAL-PEDCO-000-PL-SP-0002 | BK | GNRAL | PEDCO | 000 | PL | SP | 0002 | F0Z-707152 | AFD | IFC | 2021-08-07 | 2021-08-08 | 2021-08-10 | 1 | 2 | 3 | IFA | 2021-10-04 | 2021-09-25 | 2021-09-29 | -9 | 4 | -5 | IFA | 2021-11-02 | 2021-11-09 | 2021-11-14 | 7 | 5 | 12 | AFD | 2021-12-21 | 2021-12-14 | 2021-12-18 | -7 | 4 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2021-12-07 |  | D03 | AFD | T-0312 | 2021-12-07 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02343 | 2021-12-18 | 1400/09/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-318810 | 2021-12-14 | 1400/09/23 | 2021-12-18 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PPL-00-01311 | 2021-08-10 | 1400/05/19 | CM-C2 | [6 empty] | 1400/2294/157439 | 2021-08-08 | 1400/05/17 | 2021-08-10 | 1400/05/19 | CM | [10 empty] | D01 | IFA | T-0108 | 2021-09-20 | 1400/06/29 |  |  |  | BK-SUR-ENG-PPL-00-01581 | 2021-09-22 | 1400/06/31 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0002_D00 | [5 empty] | 1400-2294-210823 | 2021-09-25 | 1400/07/03 | 2021-09-29 | 1400/07/07 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0002_D00 | [9 empty] | D02 | IFA | T-0174 | 2021-10-19 | 1400/07/27 |  |  |  | BK-SUR-ENG-PPL-00-01877 | 2021-10-31 | 1400/08/09 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0002-D01 | [5 empty] | 1400-2294-269298 | 2021-11-09 | 1400/08/18 | 2021-11-14 | 1400/08/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0002-D01 | [9 empty] | D03 | AFD | T-0312 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02343 | 2021-12-18 | 1400/09/18 | AP | [6 empty] | 1400-2294-318810 | 2021-12-14 | 1400/09/23 | 2021-12-18 | 1400/09/27 | AP
1 | 2 | 0 | 6 | 0 | 2 | 2 | 1.2.6.2.2 | Specification For Pipeline Cold Bending | BK-GNRAL-PEDCO-000-PL-SP-0003 | BK-GNRAL-PEDCO-000-PL-SP-0003 | BK | GNRAL | PEDCO | 000 | PL | SP | 0003 | F0Z-707153 | AFD | IFC | 2021-09-11 | 2021-10-28 | 2021-12-21 | 47 | 54 | 101 | IFA | 2022-02-01 | 2022-02-04 | 2022-02-08 | 3 | 4 | 7 | IFA | 2022-03-09 | 2022-03-14 | 2022-04-01 | 5 | 18 | 23 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-28 | 0 |  | D02 | IFA | T-0639 | 2022-02-23 | 1400/12/04 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-03403 | 2022-03-08 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448473 | 2022-03-14 | 1400/12/23 | 2022-04-01 | 1401/01/14 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0068 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-PPL-00-02396 | 2021-12-21 | 1400/09/30 | [7 empty] | 1400-2294-215883 | 2021-10-28 | 1400/07/06 | 2021-12-21 | 1400/09/30 | CM | [10 empty] | D01 | IFA | T-0474 | 2022-01-18 | 1400/10/28 |  |  |  | BK-SUR-ENG-PPL-00-02753 | 2022-01-19 | 1400/10/29 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0003_D00 | [5 empty] | 1400-2294-395120 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0003_D00 | [9 empty] | D02 | IFA | T-0639 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-PPL-00-03403 | 2022-03-08 | 1400/12/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0003_D01 | [5 empty] | 1400-2294-448473 | 2022-03-14 | 1400/12/23 | 2022-04-01 | 1401/01/14 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0003_D01
1 | 2 | 0 | 6 | 0 | 2 | 3 | 1.2.6.2.3 | Specification For Barred Tee | BK-GNRAL-PEDCO-000-PL-SP-0004 | BK-GNRAL-PEDCO-000-PL-SP-0004 | BK | GNRAL | PEDCO | 000 | PL | SP | 0004 | F0Z-707154 | AFD | IFC | 2021-09-11 | 2021-10-28 | 2021-12-21 | 47 | 54 | 101 | IFA | 2022-01-18 | 2022-01-08 | 2022-01-11 | -10 | 3 | -7 | IFA | 2022-02-05 | 2022-02-16 | 2022-02-21 | 11 | 5 | 16 | AFD | 2022-04-09 | 2022-04-05 | 2022-04-16 | -4 | 11 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-28 | 2022-03-26 |  | D03 | AFD | T-0743 | 2022-03-26 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-03741 | 2022-04-06 | 1401/01/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-9899 | 2022-04-05 | 1401/01/16 | 2022-04-16 | 1401/01/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0068 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-PPL-00-02396 | 2021-12-21 | 1400/09/30 | [7 empty] | 1400-2294-215883 | 2021-10-28 | 1400/07/06 | 2021-12-21 | 1400/09/30 | CM | [10 empty] | D01 | IFA | T-0426 | 2022-01-04 | 1400/10/14 |  |  |  | BK-SUR-ENG-PPL-00-02637 | 2022-01-11 | 1400/10/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0004_D00 | [5 empty] | 1400-2294-354640 | 2022-01-08 | 1400/10/18 | 2022-01-11 | 1400/10/21 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0004_D00 | [9 empty] | D02 | IFA | T-0490 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-PPL-00-02779 | 2022-01-22 | 1400/10/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0004_D01 | [5 empty] | 1400-2294-412890 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0004_D01 | [9 empty] | D03 | AFD | T-0743 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-PPL-01-03741 | 2022-04-06 | 1401/01/17 | AP | [6 empty] | 1401-2294-9899 | 2022-04-05 | 1401/01/16 | 2022-04-16 | 1401/01/27 | AP
1 | 2 | 0 | 6 | 0 | 2 | 4 | 1.2.6.2.4 | Specification For Fittings, Flanges, Gaskets and Bolts | BK-GNRAL-PEDCO-000-PL-SP-0005 | BK-GNRAL-PEDCO-000-PL-SP-0005 | BK | GNRAL | PEDCO | 000 | PL | SP | 0005 | F0Z-707155 | AFD | IFC | 2021-08-07 | 2021-08-08 | 2021-08-10 | 1 | 2 | 3 | IFA | 2021-09-27 | 2021-09-23 | 2021-09-26 | -4 | 3 | -1 | IFA | 2021-11-02 | 2021-11-09 | 2021-11-14 | 7 | 5 | 12 | AFD | 2021-12-21 | 2021-12-14 | 2021-12-18 | -7 | 4 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2021-12-07 |  | D03 | AFD | T-0312 | 2021-12-07 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02343 | 2021-12-18 | 1400/09/18 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-318810 | 2021-12-14 | 1400/09/23 | 2021-12-18 | 1400/09/27 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0005-D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PPL-00-01274 | 2021-08-07 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/157439 | 2021-08-08 | 1400/05/17 | 2021-08-10 | 1400/05/19 | CM | [10 empty] | D01 | IFA | T-0091 | 2021-09-13 | 1400/06/22 |  |  |  | BK-SUR-ENG-PPL-00-01585 | 2021-09-25 | 1400/07/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0005_D00 | [5 empty] | 1400-2294-210024 | 2021-09-23 | 1400/07/01 | 2021-09-26 | 1400/07/04 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0005_D00 | [9 empty] | D02 | IFA | T-0174 | 2021-10-19 | 1400/07/27 |  |  |  | BK-SUR-ENG-PPL-00-01877 | 2021-10-31 | 1400/08/09 | AP | [6 empty] | 1400-2294-269298 | 2021-11-09 | 1400/08/18 | 2021-11-14 | 1400/08/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0005-D01 | [9 empty] | D03 | AFD | T-0312 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02343 | 2021-12-18 | 1400/09/18 | CM-C2 | [6 empty] | 1400-2294-318810 | 2021-12-14 | 1400/09/23 | 2021-12-18 | 1400/09/27 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0005-D02
1 | 2 | 0 | 6 | 0 | 2 | 5 | 1.2.6.2.5 | Specification For Pipeline Valves | BK-GNRAL-PEDCO-000-PL-SP-0006 | BK-GNRAL-PEDCO-000-PL-SP-0006 | BK | GNRAL | PEDCO | 000 | PL | SP | 0006 | F0Z-707156 | AFD | IFC | 2021-09-11 | 2021-10-28 | 2021-12-21 | 47 | 54 | 101 | IFA | 2022-02-01 | 2022-02-04 | 2022-02-08 | 3 | 4 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-28 | 0 |  | D01 | IFA | T-0474 | 2022-01-18 | 1400/10/28 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02753 | 2022-01-19 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-395120 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0068 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-PPL-00-02396 | 2021-12-21 | 1400/09/30 | [7 empty] | 1400-2294-215883 | 2021-10-28 | 1400/07/06 | 2021-12-21 | 1400/09/30 | CM | [10 empty] | D01 | IFA | T-0474 | 2022-01-18 | 1400/10/28 |  |  |  | BK-SUR-ENG-PPL-00-02753 | 2022-01-19 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0006_D00 | [5 empty] | 1400-2294-395120 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0006_D00
1 | 2 | 0 | 6 | 0 | 2 | 6 | 1.2.6.2.6 | Specification For Pipeline Coating | BK-GNRAL-PEDCO-000-PL-SP-0007 | BK-GNRAL-PEDCO-000-PL-SP-0007 | BK | GNRAL | PEDCO | 000 | PL | SP | 0007 | F0Z-707157 | AFD | IFC | 2021-08-07 | 2021-08-08 | 2021-08-10 | 1 | 2 | 3 | IFA | 2021-09-27 | 2021-09-23 | 2021-09-26 | -4 | 3 | -1 | IFA | 2021-11-02 | 2021-11-09 | 2021-11-14 | 7 | 5 | 12 | AFD | 2021-12-21 | 2021-12-14 | 2021-12-18 | -7 | 4 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2021-12-07 |  | D03 | AFD | T-0312 | 2021-12-07 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02343 | 2021-12-18 | 1400/09/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-318810 | 2021-12-14 | 1400/09/23 | 2021-12-18 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PPL-00-01274 | 2021-08-07 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/157439 | 2021-08-08 | 1400/05/17 | 2021-08-10 | 1400/05/19 | CM | [10 empty] | D01 | IFA | T-0091 | 2021-09-13 | 1400/06/22 |  |  |  | BK-SUR-ENG-PPL-00-01602 | 2021-09-26 | 1400/07/04 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0007_D00 | [5 empty] | 1400-2294-210024 | 2021-09-23 | 1400/07/01 | 2021-09-26 | 1400/07/04 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0007_D00 | [9 empty] | D02 | IFA | T-0174 | 2021-10-19 | 1400/07/27 |  |  |  | BK-SUR-ENG-PPL-00-01877 | 2021-10-31 | 1400/08/09 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0007-D01 | [5 empty] | 1400-2294-269298 | 2021-11-09 | 1400/08/18 | 2021-11-14 | 1400/08/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0007-D01 | [9 empty] | D03 | AFD | T-0312 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02343 | 2021-12-18 | 1400/09/18 | AP | [6 empty] | 1400-2294-318810 | 2021-12-14 | 1400/09/23 | 2021-12-18 | 1400/09/27 | AP
1 | 2 | 0 | 6 | 0 | 2 | 7 | 1.2.6.2.7 | Specification For Pipeline Flushing, Cleaning And Hydrostatic Testing | BK-GNRAL-PEDCO-000-PL-SP-0008 | BK-GNRAL-PEDCO-000-PL-SP-0008 | BK | GNRAL | PEDCO | 000 | PL | SP | 0008 | F0Z-707158 | AFD | IFC | 2021-08-07 | 2021-08-08 | 2021-08-10 | 1 | 2 | 3 | IFA | 2021-10-04 | 2021-09-25 | 2021-09-29 | -9 | 4 | -5 | IFA | 2021-11-02 | 2021-11-09 | 2021-11-14 | 7 | 5 | 12 | AFD | 2021-12-21 | 2021-12-14 | 2021-12-18 | -7 | 4 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2021-12-07 |  | D03 | AFD | T-0312 | 2021-12-07 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02343 | 2021-12-18 | 1400/09/18 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0008-D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-318810 | 2021-12-14 | 1400/09/23 | 2021-12-18 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PPL-00-01274 | 2021-08-07 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/157439 | 2021-08-08 | 1400/05/17 | 2021-08-10 | 1400/05/19 | CM | [10 empty] | D01 | IFA | T-0108 | 2021-09-20 | 1400/06/29 |  |  |  | BK-SUR-ENG-PPL-00-01581 | 2021-09-22 | 1400/06/31 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0008_D00 | [5 empty] | 1400-2294-210823 | 2021-09-25 | 1400/07/03 | 2021-09-29 | 1400/07/07 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0008_D00 | [9 empty] | D02 | IFA | T-0174 | 2021-10-19 | 1400/07/27 |  |  |  | BK-SUR-ENG-PPL-00-01877 | 2021-10-31 | 1400/08/09 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0008-D01 | [5 empty] | 1400-2294-269298 | 2021-11-09 | 1400/08/18 | 2021-11-14 | 1400/08/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0008-D01 | [9 empty] | D03 | AFD | T-0312 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02343 | 2021-12-18 | 1400/09/18 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0008-D02 | [5 empty] | 1400-2294-318810 | 2021-12-14 | 1400/09/23 | 2021-12-18 | 1400/09/27 | AP
1 | 2 | 0 | 6 | 0 | 2 | 8 | 1.2.6.2.8 | Specification For Welding of Transportation Pipeline | BK-GNRAL-PEDCO-000-PL-SP-0009 | BK-GNRAL-PEDCO-000-PL-SP-0009 | BK | GNRAL | PEDCO | 000 | PL | SP | 0009 | F0Z-707159 | AFD | IFC | 2021-12-26 | 2021-12-30 | 2022-01-02 | 4 | 3 | 7 | IFA | 2022-02-01 | 2022-02-04 | 2022-02-08 | 3 | 4 | 7 | IFA | 2022-03-12 | 2022-03-03 | 2022-03-08 | -9 | 5 | -4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-12 | 0 |  | D02 | IFA | T-0644 | 2022-02-26 | 1400/12/07 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-03397 | 2022-03-08 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-432767 | 2022-03-03 | 1400/12/12 | 2022-03-08 | 1400/12/17 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0009_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0332 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PPL-00-02484 | 2021-12-29 | 1400/10/08 | CM-C2 | [6 empty] | 1400-2294-342111 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0474 | 2022-01-18 | 1400/10/28 |  |  |  | BK-SUR-ENG-PPL-00-02753 | 2022-01-19 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0009_D00 | [5 empty] | 1400-2294-395120 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0009_D00 | [9 empty] | D02 | IFA | T-0644 | 2022-02-26 | 1400/12/07 |  |  |  | BK-SUR-ENG-PPL-00-03397 | 2022-03-08 | 1400/12/17 | AP | [6 empty] | 1400-2294-432767 | 2022-03-03 | 1400/12/12 | 2022-03-08 | 1400/12/17 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0009_D01
1 | 2 | 0 | 6 | 0 | 2 | 9 | 1.2.6.2.9 | Specification For Pipeline Stress Analysis | BK-GNRAL-PEDCO-000-PL-SP-0010 | BK-GNRAL-PEDCO-000-PL-SP-0010 | BK | GNRAL | PEDCO | 000 | PL | SP | 0010 | F0Z-707160 | AFD | IFC | 2021-08-07 | 2021-08-08 | 2021-08-10 | 1 | 2 | 3 | IFA | 2021-11-03 | 2021-11-04 | 2021-11-08 | 1 | 4 | 5 | IFA | 2021-11-29 | 2021-11-23 | 2021-11-27 | -6 | 4 | -2 | IFA | 2021-12-21 | 2022-12-14 | 2022-04-19 | 358 | -239 | 119 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 0 |  | D03 | IFA | T-0313 | 2021-12-07 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02271 | 2021-12-12 | 1400/09/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-317186 | 2022-12-14 | 1401/09/23 | 2022-04-19 | 1401/01/30 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PPL-00-01274 | 2021-08-07 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/157439 | 2021-08-08 | 1400/05/17 | 2021-08-10 | 1400/05/19 | CM | [10 empty] | D01 | IFA | T-0179 | 2021-10-20 | 1400/07/28 |  |  |  | BK-SUR-ENG-PPL-00-01842 | 2021-10-26 | 1400/08/04 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010_D00 | [5 empty] | 1400-2294-261476 | 2021-11-04 | 1400/08/13 | 2021-11-08 | 1400/08/17 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010-D00 | [9 empty] | D02 | IFA | T-0246 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PPL-00-02079 | 2021-11-22 | 1400/09/01 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010_D02 | [5 empty] | 1400-2294-288567 | 2021-11-23 | 1400/09/02 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010_D02 | [9 empty] | D03 | IFA | T-0313 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-PPL-00-02271 | 2021-12-12 | 1400/09/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010_D02 | [5 empty] | 1400-2294-317186 | 2022-12-14 | 1401/09/23 | 2022-04-19 | 1401/01/30 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0010_D02
1 | 2 | 0 | 6 | 0 | 2 | 10 | 1.2.6.2.10 | Specification For Pipeline Insulation Joint | BK-GNRAL-PEDCO-000-PL-SP-0011 | BK-GNRAL-PEDCO-000-PL-SP-0011 | BK | GNRAL | PEDCO | 000 | PL | SP | 0011 | F0Z-707161 | AFD | IFC | 2021-08-07 | 2021-08-08 | 2021-08-10 | 1 | 2 | 3 | IFA | 2021-09-27 | 2021-09-23 | 2021-09-26 | -4 | 3 | -1 | IFA | 2021-11-02 | 2021-11-09 | 2021-11-14 | 7 | 5 | 12 | AFD | 2021-12-21 | 2021-12-14 | 2021-12-18 | -7 | 4 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2021-12-07 |  | D03 | AFD | T-0312 | 2021-12-07 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02343 | 2021-12-18 | 1400/09/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-318810 | 2021-12-14 | 1400/09/23 | 2021-12-18 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PPL-00-01274 | 2021-08-07 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/157439 | 2021-08-08 | 1400/05/17 | 2021-08-10 | 1400/05/19 | CM | [10 empty] | D01 | IFA | T-0091 | 2021-09-13 | 1400/06/22 |  |  |  | BK-SUR-ENG-PPL-00-01585 | 2021-09-25 | 1400/07/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0011_D00 | [5 empty] | 1400-2294-210024 | 2021-09-23 | 1400/07/01 | 2021-09-26 | 1400/07/04 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0011_D00 | [9 empty] | D02 | IFA | T-0174 | 2021-10-19 | 1400/07/27 |  |  |  | BK-SUR-ENG-PPL-00-01877 | 2021-10-31 | 1400/08/09 | AP | [6 empty] | 1400-2294-269298 | 2021-11-09 | 1400/08/18 | 2021-11-14 | 1400/08/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0011-D01 | [9 empty] | D03 | AFD | T-0312 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-PIP-00-02343 | 2021-12-18 | 1400/09/18 | AP | [6 empty] | 1400-2294-318810 | 2021-12-14 | 1400/09/23 | 2021-12-18 | 1400/09/27 | AP
1 | 2 | 0 | 6 | 0 | 2 | 11 | 1.2.6.2.11 | Specification For Pipeline Construction | BK-GNRAL-PEDCO-000-PL-SP-0012 | BK-GNRAL-PEDCO-000-PL-SP-0012 | BK | GNRAL | PEDCO | 000 | PL | SP | 0012 | F0Z-707162 | AFD | IFC | 2022-02-08 | 2022-02-16 | 2022-02-16 | 8 | 0 | 8 | IFA | 2022-03-20 | 2022-03-10 | 2022-03-12 | -10 | 2 | -8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-25 | 0 |  | D01 | IFA | T-0683 | 2022-03-06 | 1400/12/15 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-03488 | 2022-03-12 | 1400/12/21 | AP | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0012_D00 | 1400-2294-443197 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0012_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0507 | 2022-01-25 | 1400/11/05 |  |  |  | BK-SUR-ENG-PPL-00-02938 | 2022-02-05 | 1400/11/16 | CM-C2 | [6 empty] | 1400-2294-395163 | 2022-02-15 | 1400/11/15 | 2022-02-08 | 1400/11/19 | CM |  | 1400-2294-412883 | 2022-02-16 | 1400/11/27 | 2022-02-16 | 1400/11/27 | CM |  |  |  | D01 | IFA | T-0683 | 2022-03-06 | 1400/12/15 |  |  |  | BK-SUR-ENG-PPL-00-03488 | 2022-03-12 | 1400/12/21 | AP | [5 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0012_D00 | 1400-2294-443197 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0012_D00
1 | 2 | 0 | 6 | 0 | 2 | 12 | 1.2.6.2.12 | Specification For Pipeline Cleaning and Flushing | BK-GNRAL-PEDCO-000-PL-SP-0013 | BK-GNRAL-PEDCO-000-PL-SP-0013 | BK | GNRAL | PEDCO | 000 | PL | SP | 0013 | F0Z-707163 | AFD | IFC | 2021-08-07 | 2021-08-08 | 2021-08-10 | 1 | 2 | 3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-01274 | 2021-08-07 | 1400/05/16 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-157439 | 2021-08-08 | 1400/05/17 | 2021-08-10 | 1400/05/19 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0007 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-PPL-00-01274 | 2021-08-07 | 1400/05/16 | CM-C3 | [6 empty] | 1400-2294-157439 | 2021-08-08 | 1400/05/17 | 2021-08-10 | 1400/05/19 | CM
1 | 2 | 0 | 6 | 0 | 2 | 13 | 1.2.6.2.13 | Specification For Anchor Flanges | BK-GNRAL-PEDCO-000-PL-SP-0014 | BK-GNRAL-PEDCO-000-PL-SP-0014 | BK | GNRAL | PEDCO | 000 | PL | SP | 0014 | F0Z-707164 | AFD | IFC | 2021-09-11 | 2021-10-28 | 2021-12-21 | 47 | 54 | 101 | IFA | 2022-02-01 | 2022-02-04 | 2022-02-08 | 3 | 4 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-28 | 0 |  | D01 | IFA | T-0474 | 2022-01-18 | 1400/10/28 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02753 | 2022-01-19 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0014-D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-395120 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0014-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0068 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-PPL-00-02396 | 2021-12-21 | 1400/09/30 | [7 empty] | 1400-2294-215883 | 2021-10-28 | 1400/07/06 | 2021-12-21 | 1400/09/30 | CM | [10 empty] | D01 | IFA | T-0474 | 2022-01-18 | 1400/10/28 |  |  |  | BK-SUR-ENG-PPL-00-02753 | 2022-01-19 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0014-D00 | [5 empty] | 1400-2294-395120 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0014-D00
1 | 2 | 0 | 6 | 0 | 2 | 14 | 1.2.6.2.14 | Specification For Pigs | BK-GNRAL-PEDCO-000-PL-SP-0015 | BK-GNRAL-PEDCO-000-PL-SP-0015 | BK | GNRAL | PEDCO | 000 | PL | SP | 0015 | F0Z-707165 | AFD | IFC | 2021-09-11 | 2021-10-28 | 2021-12-21 | 47 | 54 | 101 | IFA | 2022-02-01 | 2022-02-04 | 2022-02-08 | 3 | 4 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-28 | 0 |  | D01 | IFA | T-0474 | 2022-01-18 | 1400/10/28 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02753 | 2022-01-19 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0015_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-395120 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0015_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0068 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-PPL-00-02396 | 2021-12-21 | 1400/09/30 | [7 empty] | 1400-2294-215883 | 2021-10-28 | 1400/07/06 | 2021-12-21 | 1400/09/30 | CM | [10 empty] | D01 | IFA | T-0474 | 2022-01-18 | 1400/10/28 |  |  |  | BK-SUR-ENG-PPL-00-02753 | 2022-01-19 | 1400/10/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0015_D00 | [5 empty] | 1400-2294-395120 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0015_D00
1 | 2 | 0 | 6 | 0 | 2 | 15 | 1.2.6.2.15 | Specification For LBV | BK-GNRAL-PEDCO-000-PL-SP-0016 | BK-GNRAL-PEDCO-000-PL-SP-0016 | [7 empty] | - | [43 empty] | Moved to IN | 2021-10-06 | 0 |  | D00 | IFC | T-0139 | 2021-10-06 | 1400/07/14 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-01800 | 2021-10-20 | 1400/07/28 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0016_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-245969 | 2021-10-24 | 1400/08/02 | 2021-11-22 | 1400/09/01 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0016_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0139 | 2021-10-06 | 1400/07/14 |  |  |  | BK-SUR-ENG-PPL-00-01800 | 2021-10-20 | 1400/07/28 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-SP-0016_D00 | [5 empty] | 1400-2294-245969 | 2021-10-24 | 1400/08/02 | 2021-11-22 | 1400/09/01 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-SP-0016_D00
1 | 2 | 0 | 6 | 0 | 3 | 0 | 1.2.6.3 | Drawing/Diagram
1 | 2 | 0 | 6 | 0 | 3 | 1 | 1.2.6.3.1 | Pipeline Standard Drawing For Line Marker Post and Cathodic Protection System | BK-GNRAL-PEDCO-000-PL-DW-0001 | BK-GNRAL-PEDCO-000-PL-DW-0001 | BK | GNRAL | PEDCO | 000 | PL | DW | 0001 | F4L-707166 | AFC | IFC | 2021-10-02 | 2021-10-02 | 2021-10-10 | 0 | 8 | 8 | IFA | 2021-12-21 | 2021-12-14 | 2021-12-18 | -7 | 4 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-18 | 0 |  | D01 | IFA | T-0303 | 2021-12-07 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02291 | 2021-12-14 | 1400/09/23 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0001-D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-318687 | 2021-12-14 | 1400/09/23 | 2021-12-18 | 1400/09/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0101 | 2021-09-18 | 1400/06/27 |  |  |  | BK-SUR-ENG-PPL-00-01618 | 2021-09-28 | 1400/07/06 | CM-C3 | [6 empty] | 1400-2294-222587 | 2021-10-02 | 1400/07/12 | 2021-10-10 | 1400/07/18 | CM | [10 empty] | D01 | IFA | T-0303 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-PPL-00-02291 | 2021-12-14 | 1400/09/23 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0001-D00 | [5 empty] | 1400-2294-318687 | 2021-12-14 | 1400/09/23 | 2021-12-18 | 1400/09/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0001-D00
1 | 2 | 0 | 6 | 0 | 3 | 2 | 1.2.6.3.2 | Standard Drawing For Above Ground Pipeline Construction R.O.W | BK-GNRAL-PEDCO-000-PL-DW-0002 | BK-GNRAL-PEDCO-000-PL-DW-0002 | BK | GNRAL | PEDCO | 000 | PL | DW | 0002 | F4L-707167 | AFC | IFC | 2021-12-11 | 2021-12-08 | 2021-12-12 | -3 | 4 | 1 | IFA | 2022-02-16 | 2022-02-26 | 2022-02-28 | 10 | 2 | 12 | AFC | 2022-04-11 | 0 | 0 | -44662 | 0 | -44662 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-27 | 2022-03-28 |  | D02 | AFC | T-0760 | 2022-03-28 | 1401/01/08 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-03878 | 2022-04-12 | 1401/01/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0272 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-PPL-00-02258 | 2021-12-11 | 1400/09/20 | CM-C3 | [6 empty] | 1400-3394-310752 | 2021-12-08 | 1400/09/17 | 2021-12-12 | 1400/09/21 | CM | [10 empty] | D01 | IFA | T-0546 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-PPL-00-03086 | 2022-02-16 | 1400/11/27 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0002_D00 | [5 empty] | 1400-2294-426611 | 2022-02-26 | 1400/12/07 | 2022-02-28 | 1400/12/09 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0002_D00 | [9 empty] | D02 | AFC | T-0760 | 2022-03-28 | 1401/01/08 |  |  |  | BK-SUR-ENG-PPL-01-03878 | 2022-04-12 | 1401/01/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0002_D01
1 | 2 | 0 | 6 | 0 | 3 | 3 | 1.2.6.3.3 | Standard Drawing For Under Ground Pipeline Construction R.O.W | BK-GNRAL-PEDCO-000-PL-DW-0003 | BK-GNRAL-PEDCO-000-PL-DW-0003 | BK | GNRAL | PEDCO | 000 | PL | DW | 0003 | F4L-707168 | AFC | IFC | 2021-12-18 | 2021-12-12 | 2021-12-15 | -6 | 3 | -3 | AFC | 2022-02-16 | 2022-02-26 | 2022-02-28 | 10 | 2 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-04 | 2022-02-02 |  | D01 | AFC | T-0537 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02951 | 2022-02-06 | 1400/11/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0003-D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-426685 | 2022-02-26 | 1400/12/07 | 2022-02-28 | 1400/12/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0289 | 2021-12-04 | 1400/09/13 |  |  |  | BK-SUR-ENG-PPL-00-02228 | 2021-12-07 | 1400/09/16 | CM-C3 | [6 empty] | 1400-2294-315076 | 2021-12-12 | 1400/09/21 | 2021-12-15 | 1400/09/24 | AP | [10 empty] | D01 | AFC | T-0537 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-PPL-00-02951 | 2022-02-06 | 1400/11/17 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0003-D00 | [5 empty] | 1400-2294-426685 | 2022-02-26 | 1400/12/07 | 2022-02-28 | 1400/12/09 | AP
1 | 2 | 0 | 6 | 0 | 3 | 4 | 1.2.6.3.4 | Pipeline Standard Drawing For Anchor Support | BK-GNRAL-PEDCO-000-PL-DW-0004 | BK-GNRAL-PEDCO-000-PL-DW-0004 | BK | GNRAL | PEDCO | 000 | PL | DW | 0004 | F2L-707169 | AFC | IFC | 2022-01-05 | 2021-12-30 | 2022-01-02 | -6 | 3 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-22 | 0 |  | D00 | IFC | T-0375 | 2021-12-22 | 1400/10/01 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02228 | 2022-01-02 | 1400/10/12 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-342150 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0375 | 2021-12-22 | 1400/10/01 |  |  |  | BK-SUR-ENG-PPL-00-02228 | 2022-01-02 | 1400/10/12 | CM-C3 | [6 empty] | 1400-2294-342150 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM
1 | 2 | 0 | 6 | 0 | 3 | 5 | 1.2.6.3.5 | Standard Drawing For A/G Pipeline Road Crossing | BK-GNRAL-PEDCO-000-PL-DW-0005 | BK-GNRAL-PEDCO-000-PL-DW-0005 | BK | GNRAL | PEDCO | 000 | PL | DW | 0005 | F5L-707170 | AFC | IFC | 2021-12-19 | 2021-12-12 | 2021-12-14 | -7 | 2 | -5 | IFA | 2022-04-13 | 2020-04-28 | 2022-04-02 | -715 | 704 | -11 | AFC | 2022-05-30 | 0 | 0 | -44711 | 0 | -44711 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-05 | 2022-05-16 |  | D02 | AFC | T-0959 | 2022-05-16 | 1401/02/26 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-04336 | 2022-05-21 | 1401/02/31 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0005_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0293 | 2021-12-05 | 1400/09/14 |  |  |  | BK-SUR-ENG-PPL-00-02268 | 2021-12-12 | 1400/09/21 | CM-C3 | [6 empty] | 1400-2294-315114 | 2021-12-12 | 1400/09/21 | 2021-12-14 | 1400/09/23 | CM | [10 empty] | D01 | IFA | T-0764 | 2022-03-30 | 1401/01/10 |  |  |  | BK-SUR-ENG-PPL-01-03906 | 2022-04-16 | 1400/01/27 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0005_D00 | [5 empty] | 1401-2294-43099 | 2020-04-28 | 1401/02/08 | 2022-04-02 | 1401/02/12 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0005_D00 | [9 empty] | D02 | AFC | T-0959 | 2022-05-16 | 1401/02/26 |  |  |  | BK-SUR-ENG-PPL-01-04336 | 2022-05-21 | 1401/02/31 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0005_D02
1 | 2 | 0 | 6 | 0 | 3 | 6 | 1.2.6.3.6 | Standard Drawing For Existing Pipeline Crossing | BK-GNRAL-PEDCO-000-PL-DW-0006 | BK-GNRAL-PEDCO-000-PL-DW-0006 | BK | GNRAL | PEDCO | 000 | PL | DW | 0006 | F2L-707171 | AFC | IFC | 2022-01-01 | 2021-12-22 | 2021-12-26 | -10 | 4 | -6 | IFA | 2022-04-12 | 2022-04-13 | 2022-04-16 | 1 | 3 | 4 | IFA | 2022-06-07 | 0 | 0 | -44719 | 0 | -44719 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-18 | 0 |  | D02 | IFA | T-0999 | 2022-05-24 | 1401/03/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0356 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-PPL-00-02431 | 2021-12-26 | 1400/10/05 | CM-C3 | [6 empty] | 1400-2294-331426 | 2021-12-22 | 1400/10/01 | 2021-12-26 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0762 | 2022-03-29 | 1401/01/09 |  |  |  | BK-SUR-ENG-PPL-01-03905 | 2022-04-13 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0006_D00 | [5 empty] | 1401-2294-22793 | 2022-04-13 | 1401/01/24 | 2022-04-16 | 1401/01/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0006_D00 | [9 empty] | D02 | IFA | T-0999 | 2022-05-24 | 1401/03/03 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0006_D01 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0006_D01
1 | 2 | 0 | 6 | 0 | 3 | 7 | 1.2.6.3.7 | Pipeline Standard Drawing For Irish Crossing | BK-GNRAL-PEDCO-000-PL-DW-0007 | BK-GNRAL-PEDCO-000-PL-DW-0007 | BK | GNRAL | PEDCO | 000 | PL | DW | 0007 | F5L-707172 | AFC | IFC | 2021-12-18 | 2021-12-12 | 2021-12-15 | -6 | 3 | -3 | AFC | 2022-06-01 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-04 | 2022-05-18 |  | D01 | AFC | T-0972 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-04327 | 2022-05-21 | 1401/02/31 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0289 | 2021-12-04 | 1400/09/13 |  |  |  | BK-SUR-ENG-PPL-00-02228 | 2021-12-07 | 1400/09/16 | C4-RJ | [6 empty] | 1400-2294-315076 | 2021-12-12 | 1400/09/21 | 2021-12-15 | 1400/09/24 | AP | [10 empty] | D01 | AFC | T-0972 | 2022-05-18 | 1401/02/28 |  |  |  | BK-SUR-ENG-PPL-01-04327 | 2022-05-21 | 1401/02/31 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0007_D00
1 | 2 | 0 | 6 | 0 | 3 | 8 | 1.2.6.3.8 | Pipeline Standard Drawing For Water - Way Crossing | BK-GNRAL-PEDCO-000-PL-DW-0008 | BK-GNRAL-PEDCO-000-PL-DW-0008 | BK | GNRAL | PEDCO | 000 | PL | DW | 0008 | F5L-707173 | AFC | IFC | 2021-12-06 | 2021-12-06 | 2022-04-19 | 0 | 134 | 134 | AFC | 2022-05-29 | 0 | 0 | -44710 | 0 | -44710 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-22 | 2022-05-15 |  | D01 | AFC | T-0951 | 2022-05-15 | 1401/02/25 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-04434 | 2022-05-24 | 1401/03/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0264 | 2021-11-22 | 1400/09/01 |  |  |  | BK-SUR-ENG-PPL-00-02094 | 2021-11-24 | 1400/09/03 | CM-C2 |  | BK-SUR-ENG-PPL-00-02261 | 2021-12-12 | 1400/09/21 | CM-C3 |  | 1400-2294-305732 | 2021-12-06 | 1400/09/15 | 2022-04-19 | 1401/01/30 | AP | [10 empty] | D01 | AFC | T-0951 | 2022-05-15 | 1401/02/25 |  |  |  | BK-SUR-ENG-PPL-01-04434 | 2022-05-24 | 1401/03/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0008_D00
1 | 2 | 0 | 6 | 0 | 3 | 9 | 1.2.6.3.9 | Pipeline Standard Drawing For Pig Signaller Concrete Pit | BK-GNRAL-PEDCO-000-PL-DW-0009 | BK-GNRAL-PEDCO-000-PL-DW-0009 | BK | GNRAL | PEDCO | 000 | PL | DW | 0009 | F2L-707174 | AFC | IFC | 2021-12-11 | 2021-12-08 | 2021-12-12 | -3 | 4 | 1 | IFA | 2022-04-17 | 2022-04-09 | 2022-04-12 | -8 | 3 | -5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | AFC | 2022-06-04 | 0 | 0 | -44716 | 0 | -44716 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-27 | 2022-05-21 |  | D03 | AFC | T-0977 | 2022-05-21 | 1401/02/31 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-04438 | 2022-05-28 | 1401/03/07 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0009_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0272 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-PPL-00-02258 | 2021-12-11 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-310752 | 2021-12-08 | 1400/09/17 | 2021-12-12 | 1400/09/21 | CM | [10 empty] | D01 | IFA | T-0770 | 2022-04-03 | 1401/01/14 |  |  |  | BK-SUR-ENG-PPL-01-03937 | 2022-04-16 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0009_D01 | [5 empty] | 1401-2294-14511 | 2022-04-09 | 1401/01/20 | 2022-04-12 | 1401/01/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0009_D01 | [43 empty] | D03 | AFC | T-0977 | 2022-05-21 | 1401/02/31 |  |  |  | BK-SUR-ENG-PPL-01-04438 | 2022-05-28 | 1401/03/07 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0009_D01
1 | 2 | 0 | 6 | 0 | 3 | 10 | 1.2.6.3.10 | Pipeline Standard Drawing For H-Pipe Support | BK-GNRAL-PEDCO-000-PL-DW-0010 | BK-GNRAL-PEDCO-000-PL-DW-0010 | BK | GNRAL | PEDCO | 000 | PL | DW | 0010 | F5L-707175 | AFC | IFC | 2021-12-11 | 2021-12-08 | 2021-12-12 | -3 | 4 | 1 | AFC | 2022-02-14 | 2022-02-05 | 2022-02-08 | -9 | 3 | -6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-27 | 2022-01-31 |  | D01 | AFC | T-0524 | 2022-01-31 | 1400/11/11 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02891 | 2022-01-31 | 1400/11/11 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0010_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-397300 | 2022-02-05 | 1400/11/16 | 2022-02-08 | 1400/11/19 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0272 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-PPL-00-02258 | 2021-12-11 | 1400/09/20 | CM-C2 | [6 empty] | 1400-3394-310752 | 2021-12-08 | 1400/09/17 | 2021-12-12 | 1400/09/21 | CM | [10 empty] | D01 | AFC | T-0524 | 2022-01-31 | 1400/11/11 |  |  |  | BK-SUR-ENG-PPL-00-02891 | 2022-01-31 | 1400/11/11 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0010_D00 | [5 empty] | 1400-2294-397300 | 2022-02-05 | 1400/11/16 | 2022-02-08 | 1400/11/19 | AP
1 | 2 | 0 | 6 | 0 | 3 | 11 | 1.2.6.3.11 | Pipeline Standard Drawing For Vent Valve Pre-cast Concrete Box | BK-GNRAL-PEDCO-000-PL-DW-0011 | BK-GNRAL-PEDCO-000-PL-DW-0011 | BK | GNRAL | PEDCO | 000 | PL | DW | 0011 | F2L-707176 | AFC | IFC | 2021-12-11 | 2021-12-08 | 2021-12-12 | -3 | 4 | 1 | IFA | 2022-05-01 | 2022-04-28 | 2022-05-02 | -3 | 4 | 1 | AFC | 2022-06-08 | 0 | 0 | -44720 | 0 | -44720 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-27 | 2022-05-25 |  | D02 | AFC | T-1005 | 2022-05-25 | 1401/03/04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0011_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0272 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-PPL-00-02258 | 2021-12-11 | 1400/09/20 | CM-C3 | [6 empty] | 1400-3394-310752 | 2021-12-08 | 1400/09/17 | 2021-12-12 | 1400/09/21 | CM | [10 empty] | D01 | IFA | T-0830 | 2022-04-17 | 1401/01/28 |  |  |  | BK-SUR-ENG-PPL-01-04070 | 2022-04-26 | 1401/02/06 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0011_D00 | [5 empty] | 1401-2294-73173 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0011_D00 | [9 empty] | D02 | AFC | T-1005 | 2022-05-25 | 1401/03/04 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0011_D01
1 | 2 | 0 | 6 | 0 | 3 | 12 | 1.2.6.3.12 | Pipeline Standard Drawing For Cover Slabs And Set-On-Weight | BK-GNRAL-PEDCO-000-PL-DW-0013 | BK-GNRAL-PEDCO-000-PL-DW-0013 | BK | GNRAL | PEDCO | 000 | PL | DW | 0013 | F5L-707177 | AFC | IFC | 2022-01-04 | 2021-12-29 | 2022-01-01 | -6 | 3 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-21 | 0 |  | D00 | IFC | T-0373 | 2021-12-21 | 1400/09/30 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02492 | 2022-01-01 | 1400/10/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-341839 | 2021-12-29 | 1400/10/08 | 2022-01-01 | 1400/10/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0373 | 2021-12-21 | 1400/09/30 |  |  |  | BK-SUR-ENG-PPL-00-02492 | 2022-01-01 | 1400/10/11 | CM-C3 | [6 empty] | 1400-2294-341839 | 2021-12-29 | 1400/10/08 | 2022-01-01 | 1400/10/11 | CM
1 | 2 | 0 | 6 | 0 | 3 | 13 | 1.2.6.3.13 | Pipeline Standard Drawing For River Crossing | BK-GNRAL-PEDCO-000-PL-DW-0014 | BK-GNRAL-PEDCO-000-PL-DW-0014 | BK | GNRAL | PEDCO | 000 | PL | DW | 0014 | F5L-707178 | AFC | IFC | 2021-12-29 | 2021-12-22 | 2021-12-26 | -7 | 4 | -3 | IFA | 2022-05-14 | 2022-05-12 | 2022-05-18 | -2 | 6 | 4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-15 | 0 |  | D01 | IFA | T-0875 | 2022-04-30 | 1401/02/10 | T-0875 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PPL-01-04302 | 2022-05-18 | 1401/02/28 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0014_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59524 | 2022-05-12 | 1401/02/22 | 2022-05-18 | 1401/02/28 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0014_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0347 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-PPL-00-02435 | 2021-12-26 | 1400/10/26 | CM-C3 | [6 empty] | 1400-2294-331441 | 2021-12-22 | 1400/10/01 | 2021-12-26 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0875 | 2022-04-30 | 1401/02/10 | T-0875 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PPL-01-04302 | 2022-05-18 | 1401/02/28 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0014_D00 | [5 empty] | 1401-2294-59524 | 2022-05-12 | 1401/02/22 | 2022-05-18 | 1401/02/28 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-PL-DW-0014_D00
1 | 2 | 0 | 6 | 0 | 4 | 0 | 1.2.6.4 | Procedure/Plan
1 | 2 | 0 | 7 | 0 | 0 | 0 | 1.2.7 | Control & Instrumentation
1 | 2 | 0 | 7 | 0 | 1 | 0 | 1.2.7.1 | Specification
1 | 2 | 0 | 7 | 0 | 1 | 1 | 1.2.7.1.1 | Specification For Instrumentation | BK-GNRAL-PEDCO-000-IN-SP-0001 | BK-GNRAL-PEDCO-000-IN-SP-0001 | BK | GNRAL | PEDCO | 000 | IN | SP | 0001 | F9J-707179 | AFD | IFC | 2021-08-09 | 2021-08-29 | 2021-09-12 | 20 | 14 | 34 | IFA | 2021-10-02 | 2021-10-07 | 2021-10-13 | 5 | 6 | 11 | IFA | 2021-11-28 | 2021-11-21 | 2021-12-01 | -7 | 10 | 3 | AFD | 2022-02-16 | 0 | 0 | -44608 | 0 | -44608 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-26 | 2022-02-02 |  | D03 | AFD | T-0534 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02952 | 2022-02-06 | 1400/11/17 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0011 | 2021-07-26 | 1400/05/04 |  |  |  | BK-SUR-ENG-INS-00-01354 | 2021-08-15 | 1400/05/24 | CM-C3 | [6 empty] | 1400/2294/177758 | 2021-08-29 | 1400/06/07 | 2021-09-12 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0095 | 2021-09-18 | 1400/06/27 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D00 | [5 empty] | 1400-2290-225563 | 2021-10-07 | 1400/07/15 | 2021-10-13 | 1400/07/21 | CM | NISOC-CRS- BK-GNRAL-PEDCO-000-IN-SP-0001_D00 | [9 empty] | D02 | IFA | T-0234 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02169 | 2021-12-01 | 1400/09/10 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D01 | [5 empty] | 1400-2294-283469 | 2021-11-21 | 1400/08/30 | 2021-12-01 | 1400/09/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D01 | [9 empty] | D03 | AFD | T-0534 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-02952 | 2022-02-06 | 1400/11/17 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D02 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0001_D02
1 | 2 | 0 | 7 | 0 | 1 | 2 | 1.2.7.1.2 | Specification For Control System | BK-GNRAL-PEDCO-000-IN-SP-0002 | BK-GNRAL-PEDCO-000-IN-SP-0002 | BK | GNRAL | PEDCO | 000 | IN | SP | 0002 | F9J-707180 | AFD | IFC | 2021-08-11 | 2021-09-22 | 2021-09-12 | 42 | -10 | 32 | IFA | 2021-10-13 | 2021-10-17 | 2021-10-20 | 4 | 3 | 7 | IFA | 2021-12-12 | 2021-12-14 | 2021-12-15 | 2 | 1 | 3 | IFA | 2022-02-06 | 2022-03-08 | 2022-03-11 | 30 | 3 | 33 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 0 |  | D03 | IFA | T-0495 | 2022-01-23 | 1400/11/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-441071 | 2022-03-08 | 1400/12/17 | 2022-03-11 | 1400/12/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0016 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-INS-00-01336 | 2021-08-22 | 1400/05/31 | CM-C3 | [6 empty] | 1400-2294-208200 | 2021-09-22 | 1400/06/31 | 2021-09-12 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0125 | 2021-09-29 | 1400/07/07 |  |  |  | BK-SUR-ENG-INS-00-01744 | 2021-10-16 | 1400/07/24 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002_D00 | [5 empty] | 1400-2294-238033 | 2021-10-17 | 1400/07/25 | 2021-10-20 | 1400/07/28 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002_D00 | [9 empty] | D02 | IFA | T-0281 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-INS-00-02277 | 2021-12-13 | 1400/09/22 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002_D01 | [5 empty] | 1400-2294-317175 | 2021-12-14 | 1400/09/23 | 2021-12-15 | 1400/09/24 | CM | NICOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002_D01 | [9 empty] | D03 | IFA | T-0495 | 2022-01-23 | 1400/11/03 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002_D02 | [5 empty] | 1400-2294-441071 | 2022-03-08 | 1400/12/17 | 2022-03-11 | 1400/12/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0002_D02
1 | 2 | 0 | 7 | 0 | 1 | 3 | 1.2.7.1.3 | Specification For ESD System | BK-GNRAL-PEDCO-000-IN-SP-0003 | BK-GNRAL-PEDCO-000-IN-SP-0003 | BK | GNRAL | PEDCO | 000 | IN | SP | 0003 | F9J-707181 | AFD | IFC | 2021-08-11 | 2021-08-29 | 2021-09-12 | 18 | 14 | 32 | IFA | 2021-10-04 | 2021-10-07 | 2021-10-13 | 3 | 6 | 9 | IFA | 2022-01-15 | 2022-01-26 | 2022-01-29 | 11 | 3 | 14 | IFA | 2022-05-11 | 2022-05-18 | 2022-05-23 | 7 | 5 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 0 |  | D03 | IFA | T-0868 | 2022-04-27 | 1401/02/07 | T-0868 | 2022-04-27 | 1401/02/07 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0003_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-66361 | 2022-05-18 | 1401/02/28 | 2022-05-23 | 1401/03/03 | CM | NISCO-CRS-BK-GNRAL-NISCO-000-IN-SP-0003_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0016 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-INS-00-01336 | 2021-08-22 | 1400/05/31 | CM-C3 | [6 empty] | 1400/2294/177758 | 2021-08-29 | 1400/06/07 | 2021-09-12 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0104 | 2021-09-20 | 1400/06/29 |  |  |  | BK-SUR-ENG-INS-00-01675 | 2021-10-04 | 1400/07/12 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0003_D00 | [5 empty] | 1400-2290-225567 | 2021-10-07 | 1400/07/15 | 2021-10-13 | 1400/07/21 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0003_D00 | [9 empty] | D02 | IFA | T-0414 | 2022-01-01 | 1400/10/11 |  |  |  | BK-SUR-ENG-INS-00-02675 | 2022-01-15 | 1400/10/25 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0003_D01 | [5 empty] | 1400-2294-382426 | 2022-01-26 | 1400/11/06 | 2022-01-29 | 1400/11/09 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0003-D01 | [9 empty] | D03 | IFA | T-0868 | 2022-04-27 | 1401/02/07 | T-0868 | 2022-04-27 | 1401/02/07 |  |  |  |  | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0003_D02 | [5 empty] | 1401-2294-66361 | 2022-05-18 | 1401/02/28 | 2022-05-23 | 1401/03/03 | CM | NISCO-CRS-BK-GNRAL-NISCO-000-IN-SP-0003_D02
1 | 2 | 0 | 7 | 0 | 1 | 4 | 1.2.7.1.4 | Specification For Instrument and Control of Package Unit System (PU) | BK-GNRAL-PEDCO-000-IN-SP-0004 | BK-GNRAL-PEDCO-000-IN-SP-0004 | BK | GNRAL | PEDCO | 000 | IN | SP | 0004 | F9J-707182 | AFD | IFC | 2021-08-18 | 2021-12-17 | 2022-04-19 | 121 | 123 | 244 | IFA | 2022-06-12 | 0 | 0 | -44724 | 0 | -44724 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-04 | 0 |  | D01 | IFA | T-1017 | 2022-05-29 | 1401/03/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0029 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-INS-00-01341 | 2021-08-15 | 1400/5/24 | CM-C3 | [6 empty] | 1400-2294-320793 | 2021-12-17 | 1400/09/26 | 2022-04-19 | 1401/01/30 | CM | [10 empty] | D01 | IFA | T-1017 | 2022-05-29 | 1401/03/08 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0004_D00 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0004_D00
1 | 2 | 0 | 7 | 0 | 1 | 5 | 1.2.7.1.5 | Specification For Control Valves | BK-GNRAL-PEDCO-000-IN-SP-0005 | BK-GNRAL-PEDCO-000-IN-SP-0005 | BK | GNRAL | PEDCO | 000 | IN | SP | 0005 | F9J-707183 | AFD | IFC | 2021-08-07 | 2021-08-29 | 2021-09-12 | 22 | 14 | 36 | IFA | 2021-10-16 | 2021-10-17 | 2022-03-14 | 1 | 148 | 149 | IFA | 2022-05-11 | 2022-05-17 | 2022-05-23 | 6 | 6 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 0 |  | D02 | IFA | T-0871 | 2022-04-27 | 1401/02/07 | T-0871 | 2022-04-27 | 1401/02/07 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0005_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65621 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0002 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-INS-00-01299 | 2021-08-09 | 1400/05/18 | CM | [6 empty] | 1400/2294/177758 | 2021-08-29 | 1400/06/07 | 2021-09-12 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0126 | 2021-10-02 | 1400/07/10 |  |  |  | BK-SUR-ENG-INS-00-01768 | 2021-10-21 | 1400/07/28 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0005_D00 | [5 empty] | 1400-2294-238042 | 2021-10-17 | 1400/07/25 | 2022-03-14 | 1400/12/23 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0005_D00 | [9 empty] | D02 | IFA | T-0871 | 2022-04-27 | 1401/02/07 | T-0871 | 2022-04-27 | 1401/02/07 |  |  |  |  | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0005_D01 | [5 empty] | 1401-2294-65621 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0005_D01
1 | 2 | 0 | 7 | 0 | 1 | 6 | 1.2.7.1.6 | Specification For On-off /Shut Down Valves(ESDV/MOV) | BK-GNRAL-PEDCO-000-IN-SP-0006 | BK-GNRAL-PEDCO-000-IN-SP-0006 | BK | GNRAL | PEDCO | 000 | IN | SP | 0006 | F9J-707184 | AFD | IFC | 2021-08-07 | 2021-08-29 | 2021-09-12 | 22 | 14 | 36 | IFA | 2021-10-17 | 2021-10-18 | 2021-10-20 | 1 | 2 | 3 | IFA | 2022-02-06 | 2022-03-08 | 2022-03-11 | 30 | 3 | 33 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 0 |  | D02 | IFA | T-0495 | 2022-01-23 | 1400/11/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0006_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-441071 | 2022-03-08 | 1400/12/17 | 2022-03-11 | 1400/12/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0002 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-INS-00-01299 | 2021-08-09 | 1400/05/18 | CM-C3 | [6 empty] | 1400/2294/177758 | 2021-08-29 | 1400/06/07 | 2021-09-12 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0130 | 2021-10-03 | 1400/07/11 |  |  |  | BK-SUR-ENG-INS-00-01773 | 2021-10-18 | 1400/07/26 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0006_D00 | [5 empty] | 1400-2294-239930 | 2021-10-18 | 1400/07/26 | 2021-10-20 | 1400/07/28 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0006_D00 | [9 empty] | D02 | IFA | T-0495 | 2022-01-23 | 1400/11/03 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0006_D01 | [5 empty] | 1400-2294-441071 | 2022-03-08 | 1400/12/17 | 2022-03-11 | 1400/12/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0006_D01
1 | 2 | 0 | 7 | 0 | 1 | 7 | 1.2.7.1.7 | Specification For Pressure Safety Valves(PSV) | BK-GNRAL-PEDCO-000-IN-SP-0007 | BK-GNRAL-PEDCO-000-IN-SP-0007 | BK | GNRAL | PEDCO | 000 | IN | SP | 0007 | F9J-707185 | AFD | IFC | 2021-08-07 | 2021-08-29 | 2021-09-12 | 22 | 14 | 36 | IFA | 2021-10-20 | 2021-10-19 | 2021-10-26 | -1 | 7 | 6 | IFA | 2022-01-30 | 2022-01-31 | 2022-02-01 | 1 | 1 | 2 | AFD | 2022-03-12 | 2022-03-14 | 2022-03-25 | 2 | 11 | 13 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-02-26 |  | D03 | AFD | T-0647 | 2022-02-26 | 1400/12/07 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03457 | 2022-03-12 | 1400/12/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0007_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-449046 | 2022-03-14 | 1400/12/23 | 2022-03-25 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0002 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-INS-00-01299 | 2021-08-09 | 1400/05/18 | CM-C3 | [6 empty] | 1400/2294/177758 | 2021-08-29 | 1400/06/07 | 2021-09-12 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0140 | 2021-10-06 | 1400/07/14 |  |  |  | BK-SUR-ENG-INS-00-01834 | 2021-10-25 | 1400/08/03 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0007_D00 | [5 empty] | 1400-2294-241761 | 2021-10-19 | 1400/07/27 | 2021-10-26 | 1400/08/04 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0007_D00 | [9 empty] | D02 | IFA | T-0469 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02863 | 2022-01-30 | 1400/11/10 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0007_D01 | [5 empty] | 1400-2294-390759 | 2022-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0007_D01 | [9 empty] | D03 | AFD | T-0647 | 2022-02-26 | 1400/12/07 |  |  |  | BK-SUR-ENG-INS-00-03457 | 2022-03-12 | 1400/12/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0007_D02 | [5 empty] | 1400-2294-449046 | 2022-03-14 | 1400/12/23 | 2022-03-25 | 1401/01/08 | AP
1 | 2 | 0 | 7 | 0 | 1 | 8 | 1.2.7.1.8 | Specification For Fire & Gas Sensor and Devices | BK-GNRAL-PEDCO-000-IN-SP-0009 | BK-GNRAL-PEDCO-000-IN-SP-0009 | BK | GNRAL | PEDCO | 000 | IN | SP | 0009 | F9J-707186 | AFD | IFC | 2021-08-09 | 2021-09-22 | 2021-09-12 | 44 | -10 | 34 | IFA | 2021-10-10 | 2021-10-17 | 2021-10-20 | 7 | 3 | 10 | IFA | 2022-01-15 | 2022-01-26 | 2022-01-29 | 11 | 3 | 14 | IFA | 2022-03-20 | 2022-03-14 | 2022-03-25 | -6 | 11 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-26 | 0 |  | D03 | IFA | T-0682 | 2022-03-06 | 1400/12/15 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03655 | 2022-03-16 | 1400/12/25 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-449020 | 2022-03-14 | 1400/12/23 | 2022-03-25 | 1401/01/08 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0009_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0011 | 2021-07-26 | 1400/05/04 |  |  |  | BK-SUR-ENG-INS-00-01354 | 2021-08-22 | 1400/05/31 | CM-C3 | [6 empty] | 1400/2294/177758 | 2021-08-29 | 1400/06/07 | 2021-09-12 | 1400/06/21 | CM |  | 1400-2294-208200 | 2021-09-22 | 1400/06/31 |  |  | CM |  |  |  | D01 | IFA | T-0123 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-INS-00-01683 | 2021-10-09 | 1400/07/17 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0009-D00 | [5 empty] | 1400-2294-238037 | 2021-10-17 | 1400/07/25 | 2021-10-20 | 1400/07/28 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0009-D00 | [9 empty] | D02 | IFA | T-0414 | 2022-01-01 | 1400/10/11 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0009-D01 | [5 empty] | 1400-2294-382426 | 2022-01-26 | 1400/11/06 | 2022-01-29 | 1400/11/09 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0009-D01 | [9 empty] | D03 | IFA | T-0682 | 2022-03-06 | 1400/12/15 |  |  |  | BK-SUR-ENG-INS-00-03655 | 2022-03-16 | 1400/12/25 | CM-C3 | [6 empty] | 1400-2294-449020 | 2022-03-14 | 1400/12/23 | 2022-03-25 | 1401/01/08 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0009_D02
1 | 2 | 0 | 7 | 0 | 1 | 9 | 1.2.7.1.9 | Specification For Instrument/F&G Cables | BK-GNRAL-PEDCO-000-IN-SP-0010 | BK-GNRAL-PEDCO-000-IN-SP-0010 | BK | GNRAL | PEDCO | 000 | IN | SP | 0010 | F9J-707187 | AFD | IFC | 2021-08-18 | 2021-12-17 | 2022-04-19 | 121 | 123 | 244 | IFA | 2022-06-14 | 0 | 0 | -44726 | 0 | -44726 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-04 | 0 |  | D01 | IFA | T-1029 | 2022-05-31 | 1401/03/10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0010_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0010_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0029 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-INS-00-01341 | 2021-08-15 | 1400/5/24 | CM-C3 | [6 empty] | 1400-2294-320793 | 2021-12-17 | 1400/09/26 | 2022-04-19 | 1401/01/30 | CM | [10 empty] | D01 | IFA | T-1029 | 2022-05-31 | 1401/03/10 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0010_D00 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0010_D00
1 | 2 | 0 | 7 | 0 | 1 | 10 | 1.2.7.1.10 | Specification For Control Panels and System Cabinets | BK-GNRAL-PEDCO-000-IN-SP-0011 | BK-GNRAL-PEDCO-000-IN-SP-0011 | BK | GNRAL | PEDCO | 000 | IN | SP | 0011 | F9J-707188 | AFD | IFC | 2021-08-07 | 2021-08-29 | 2021-09-12 | 22 | 14 | 36 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 0 |  | D00 | IFC | T-0002 | 2021-07-24 | 1400/05/02 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-01299 | 2021-08-09 | 1400/05/18 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-177758 | 2021-08-29 | 1400/06/07 | 2021-09-12 | 1400/06/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0002 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-INS-00-01299 | 2021-08-09 | 1400/05/18 | CM-C3 | [6 empty] | 1400-2294-177758 | 2021-08-29 | 1400/06/07 | 2021-09-12 | 1400/06/21 | CM
1 | 2 | 0 | 7 | 0 | 1 | 11 | 1.2.7.1.11 | Specification For Fire & Gas System | BK-GNRAL-PEDCO-000-IN-SP-0012 | BK-GNRAL-PEDCO-000-IN-SP-0012 | BK | GNRAL | PEDCO | 000 | IN | SP | 0012 | F9J-707189 | AFD | IFC | 2021-08-11 | 2021-08-29 | 2021-09-12 | 18 | 14 | 32 | IFA | 2021-10-05 | 2021-10-11 | 2021-10-18 | 6 | 7 | 13 | IFA | 2022-01-24 | 2022-01-29 | 2022-01-30 | 5 | 1 | 6 | AFD | 2022-03-20 | 2022-03-15 | 2022-03-25 | -5 | 10 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 2022-03-06 |  | D03 | AFD | T-0686 | 2022-03-06 | 1400/14/15 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03653 | 2022-03-16 | 1400/12/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0012_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-449047 | 2022-03-15 | 1400/12/23 | 2022-03-25 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0016 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-INS-00-01336 | 2021-08-22 | 1400/05/31 | CM-C3 | [6 empty] | 1400/2294/177758 | 2021-08-29 | 1400/06/07 | 2021-09-12 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0113 | 2021-09-21 | 1400/06/30 |  |  |  | BK-SUR-ENG-INS-00-01676 | 2021-10-04 | 1400/07/12 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0012_D00 | [5 empty] | 1400-2290-230716 | 2021-10-11 | 1400/07/19 | 2021-10-18 | 1400/07/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0012_D00 | [9 empty] | D02 | IFA | T-0444 | 2022-01-10 | 1400/10/20 |  |  |  | BK-SUR-ENG-INS-00-02815 | 2022-01-25 | 1400/11/05 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0012_D01 | [5 empty] | 1400-2294-385430 | 2022-01-29 | 1400/11/09 | 2022-01-30 | 1400/11/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0012_D01 | [9 empty] | D03 | AFD | T-0686 | 2022-03-06 | 1400/14/15 |  |  |  | BK-SUR-ENG-INS-00-03653 | 2022-03-16 | 1400/12/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0012_D02 | [5 empty] | 1400-2294-449047 | 2022-03-15 | 1400/12/23 | 2022-03-25 | 1401/01/08 | AP
1 | 2 | 0 | 7 | 0 | 1 | 12 | 1.2.7.1.12 | Specification For LBV | BK-GNRAL-PEDCO-000-IN-SP-0013 | BK-GNRAL-PEDCO-000-IN-SP-0013 | BK | GNRAL | PEDCO | 000 | IN | SP | 0013 | F9J-707191 | AFD | IFC | 2021-08-24 | 2021-08-29 | 2021-09-12 | 5 | 14 | 19 | IFA | 2022-02-05 | 2022-03-10 | 2022-03-14 | 33 | 4 | 37 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-10 | 0 |  | D01 | IFA | T-0485 | 2022-01-22 | 1400/11/02 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02926 | 2022-02-02 | 1400/11/13 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0013_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443274 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0013_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0041 | 2021-08-10 | 1400/05/19 |  |  |  | BK-SUR-ENG-PPL-00-01500 | 2021-09-12 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-177780 | 2021-08-29 | 1400/06/07 | 2021-09-12 | 1400/06/21 | CM | [10 empty] | D01 | IFA | T-0485 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-INS-00-02926 | 2022-02-02 | 1400/11/13 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0013_D00 | [5 empty] | 1400-2294-443274 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0013_D00
1 | 2 | 0 | 7 | 0 | 1 | 13 | 1.2.7.1.13 | Specification For CCTV | BK-GNRAL-PEDCO-000-IN-SP-0014 | BK-GNRAL-PEDCO-000-IN-SP-0014 | BK | GNRAL | PEDCO | 000 | IN | SP | 0014 | F9J-707190 | AFD | IFC | 2021-10-09 | 2021-10-11 | 2021-10-18 | 2 | 7 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-25 | 0 |  | D00 | IFC | T-0114 | 2021-09-25 | 1400/07/03 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-01711 | 2021-10-19 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0014_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2290-230714 | 2021-10-11 | 1400/07/19 | 2021-10-18 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0014_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0114 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-INS-00-01711 | 2021-10-19 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0014_D00 | [5 empty] | 1400-2290-230714 | 2021-10-11 | 1400/07/19 | 2021-10-18 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0014_D00
1 | 2 | 0 | 7 | 0 | 2 | 0 | 1.2.7.2 | Drawing/Diagram
1 | 2 | 0 | 7 | 0 | 2 | 1 | 1.2.7.2.1 | CCTV Typical Installation Details & Notes | BK-GNRAL-PEDCO-000-IN-DW-0001 | BK-GNRAL-PEDCO-000-IN-DW-0001 | BK | GNRAL | PEDCO | 000 | IN | DW | 0001 | F2J-707192 | IFI | IFI | 44478 | 44480 | 44487 | 2 | 7 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-25 | 2021-09-25 |  | D00 | IFI | T-0114 | 2021-09-25 | 1400/07/03 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-01711 | 2021-10-19 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2290-230714 | 2021-10-11 | 1400/07/19 | 2021-10-18 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0114 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-INS-00-01711 | 2021-10-19 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-DW-0001_D00 | [5 empty] | 1400-2290-230714 | 2021-10-11 | 1400/07/19 | 2021-10-18 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-DW-0001_D00
1 | 2 | 0 | 8 | 0 | 0 | 0 | 1.2.8 | Safety & Fire Fighting
1 | 2 | 0 | 8 | 0 | 1 | 0 | 1.2.8.1 | Specification
1 | 2 | 0 | 8 | 0 | 1 | 1 | 1.2.8.1.1 | Specification For Fire Fighting Equipment | BK-GNRAL-PEDCO-000-SA-SP-0001 | BK-GNRAL-PEDCO-000-SA-SP-0001 | BK | GNRAL | PEDCO | 000 | SA | SP | 0001 | F0Z-707193 | AFD | IFC | 2021-09-12 | 2021-09-13 | 2021-09-18 | 1 | 5 | 6 | IFA | 2021-11-08 | 2021-11-22 | 2021-11-27 | 14 | 5 | 19 | IFA | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | AFD | 2022-01-12 | 2021-12-30 | 2022-01-02 | -13 | 3 | -10 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-29 | 2021-12-29 |  | D03 | AFD | T-0399 | 2021-12-29 | 1400/10/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-342159 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0070 | 2021-08-29 | 1400/06/07 | [13 empty] | 1400-2294-197171 | 2021-09-13 | 1400/06/22 | 2021-09-18 | 1400/06/27 | CM | [10 empty] | D01 | IFA | T-0184 | 2021-10-25 | 1400/08/03 | [13 empty] | 1400-2294-286876 | 2021-11-22 | 1400/09/01 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS- BK-GNRAL-PEDCO- 000-SA-SP-0001-D00 | [9 empty] | D02 | IFA | T-0314 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327298 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP | NISOC-CRS- BK-GNRAL-PEDCO- 000-SA-SP-0001-D01 | [9 empty] | D03 | AFD | T-0399 | 2021-12-29 | 1400/10/08 | [13 empty] | 1400-2294-342159 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | AP
1 | 2 | 0 | 8 | 0 | 1 | 2 | 1.2.8.1.2 | Specification For Hazardous Area Classification | BK-GNRAL-PEDCO-000-SA-SP-0002 | BK-GNRAL-PEDCO-000-SA-SP-0002 | BK | GNRAL | PEDCO | 000 | SA | SP | 0002 | F0Z-707194 | AFD | IFC | 2021-08-07 | 2021-08-22 | 2021-09-08 | 15 | 17 | 32 | IFA | 2021-09-21 | 2021-09-29 | 2021-10-11 | 8 | 12 | 20 | IFA | 2021-11-10 | 2021-11-21 | 2021-11-06 | 11 | -15 | -4 | AFD | 2022-01-23 | 2022-01-11 | 2022-01-30 | -12 | 19 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-01-09 |  | D03 | AFD | T-0440 | 2022-01-09 | 1400/10/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-360413 | 2022-01-11 | 1400/10/21 | 2022-01-30 | 1400/11/10 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0004 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/168847 | 2021-08-22 | 1400/05/31 | 2021-09-08 | 1400/06/17 | CM | [10 empty] | D01 | IFA | T-0081 | 2021-09-07 | 1400/06/16 | [13 empty] | 1400-2294-217844 | 2021-09-29 | 1400/07/07 | 2021-10-11 | 1400/07/19 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0002_D00 | [9 empty] | D02 | IFA | T-0188 | 2021-10-27 | 1400/08/05 | [13 empty] | 1400-2294-285007 | 2021-11-21 | 1400/08/30 | 2021-11-06 | 1400/08/15 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0002_D01 | [9 empty] | D03 | AFD | T-0440 | 2022-01-09 | 1400/10/19 | [13 empty] | 1400-2294-360413 | 2022-01-11 | 1400/10/21 | 2022-01-30 | 1400/11/10 | AP
1 | 2 | 0 | 8 | 0 | 1 | 3 | 1.2.8.1.3 | Specification For Fire Water System | BK-GNRAL-PEDCO-000-SA-SP-0003 | BK-GNRAL-PEDCO-000-SA-SP-0003 | BK | GNRAL | PEDCO | 000 | SA | SP | 0003 | F0Z-707195 | AFD | IFC | 2021-08-07 | 2021-08-22 | 2021-09-08 | 15 | 17 | 32 | IFA | 2021-09-21 | 2021-09-29 | 2021-10-11 | 8 | 12 | 20 | IFA | 2021-11-15 | 2021-11-29 | 2021-12-06 | 14 | 7 | 21 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 0 |  | D02 | IFA | T-0199 | 2021-11-01 | 1400/08/10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2290-295054 | 2021-11-29 | 1400/09/08 | 2021-12-06 | 1400/09/15 | CM | NISO-CCRS-BK-GNRAL-PEDCO-000-SA-SP-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0004 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/168847 | 2021-08-22 | 1400/05/31 | 2021-09-08 | 1400/06/17 | CM | [10 empty] | D01 | IFA | T-0081 | 2021-09-07 | 1400/06/16 | [13 empty] | 1400-2294-217844 | 2021-09-29 | 1400/07/07 | 2021-10-11 | 1400/07/19 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0003_D00 | [9 empty] | D02 | IFA | T-0199 | 2021-11-01 | 1400/08/10 | [13 empty] | 1400-2290-295054 | 2021-11-29 | 1400/09/08 | 2021-12-06 | 1400/09/15 | CM | NISO-CCRS-BK-GNRAL-PEDCO-000-SA-SP-0003_D01
1 | 2 | 0 | 8 | 0 | 1 | 4 | 1.2.8.1.4 | Specification For Environmental Job | BK-GNRAL-PEDCO-000-SA-SP-0004 | BK-GNRAL-PEDCO-000-SA-SP-0004 | BK | GNRAL | PEDCO | 000 | SA | SP | 0004 | F0Z-707196 | AFD | IFC | 2021-08-25 | 0 | 0 | -44433 | 0 | -44433 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-11 | 0 |  | D00 | IFC | T-0047 | 2021-08-11 | 1400/05/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0047 | 2021-08-11 | 1400/05/20
1 | 2 | 0 | 8 | 0 | 1 | 5 | 1.2.8.1.5 | Specification For Total Flooding System | BK-GNRAL-PEDCO-000-SA-SP-0005 | BK-GNRAL-PEDCO-000-SA-SP-0005 | BK | GNRAL | PEDCO | 000 | SA | SP | 0005 | F0Z-707197 | AFD | IFC | 2021-08-07 | 2021-08-22 | 2021-09-08 | 15 | 17 | 32 | IFA | 2021-11-15 | 2021-11-29 | 2021-12-06 | 14 | 7 | 21 | AFD | 2022-03-12 | 2022-03-09 | 2022-03-12 | -3 | 3 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-02-26 |  | D02 | AFD | T-0646 | 2022-02-26 | 1400/12/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443038 | 2022-03-09 | 1400/12/18 | 2022-03-12 | 1400/12/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0004 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/168847 | 2021-08-22 | 1400/05/31 | 2021-09-08 | 1400/06/17 | CM | [10 empty] | D01 | IFA | T-0199 | 2021-11-01 | 1400/08/10 | [13 empty] | 1400-2290-295054 | 2021-11-29 | 1400/09/08 | 2021-12-06 | 1400/09/15 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0005_D00 | [9 empty] | D02 | AFD | T-0646 | 2022-02-26 | 1400/12/07 | [13 empty] | 1400-2294-443038 | 2022-03-09 | 1400/12/18 | 2022-03-12 | 1400/12/21 | AP
1 | 2 | 0 | 8 | 0 | 1 | 6 | 1.2.8.1.6 | Specification For Safety Equipment | BK-GNRAL-PEDCO-000-SA-SP-0006 | BK-GNRAL-PEDCO-000-SA-SP-0006 | BK | GNRAL | PEDCO | 000 | SA | SP | 0006 | F0Z-707198 | AFD | IFC | 2021-09-12 | 2021-09-13 | 2021-09-18 | 1 | 5 | 6 | IFA | 2021-11-08 | 2021-11-22 | 2021-11-27 | 14 | 5 | 19 | AFD | 2021-12-20 | 2021-12-09 | 2021-12-14 | -11 | 5 | -6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-29 | 2021-12-06 |  | D02 | AFD | T-0297 | 2021-12-06 | 1400/09/15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-310955 | 2021-12-09 | 1400/09/18 | 2021-12-14 | 1400/09/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0070 | 2021-08-29 | 1400/06/07 | [13 empty] | 1400-2294-197171 | 2021-09-13 | 1400/06/22 | 2021-09-18 | 1400/06/27 | CM | [10 empty] | D01 | IFA | T-0184 | 2021-10-25 | 1400/08/03 | [13 empty] | 1400-2294-286876 | 2021-11-22 | 1400/09/01 | 2021-11-27 | 1400/09/06 | AP | NISOC-CRS- BK-GNRAL-PEDCO- 000-SA-SP-0006-D00 | [9 empty] | D02 | AFD | T-0297 | 2021-12-06 | 1400/09/15 | [13 empty] | 1400-2294-310955 | 2021-12-09 | 1400/09/18 | 2021-12-14 | 1400/09/23 | AP
1 | 2 | 0 | 8 | 0 | 1 | 7 | 1.2.8.1.7 | Specification For passive Fire protection | BK-GNRAL-PEDCO-000-SA-SP-0007 | BK-GNRAL-PEDCO-000-SA-SP-0007 | BK | GNRAL | PEDCO | 000 | SA | SP | 0007 | F0Z-707199 | AFD | IFC | 2021-08-07 | 2021-08-22 | 2021-09-08 | 15 | 17 | 32 | AFD | 2021-09-21 | 2021-09-30 | 2021-09-18 | 9 | -12 | -3 | AFD | 2022-03-19 | 2022-03-30 | 2022-04-03 | 11 | 4 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-03-05 |  | D02 | AFD | T-0667 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-6037 | 2022-03-30 | 1401/01/10 | 2022-04-03 | 1401/01/14 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0007_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0004 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/168847 | 2021-08-22 | 1400/05/31 | 2021-09-08 | 1400/06/17 | AP | [10 empty] | D01 | AFD | T-0079 | 2021-09-07 | 1400/06/16 | [13 empty] | 1400-2294-195927 | 2021-09-13 | 1400/06/22 | 2021-09-18 | 1400/06/27 | CM | BK-HD-PEDCO-L-0100 | 1400-2294-217946 | 2021-09-30 | 1400/07/08 |  |  | CM |  |  |  | D02 | AFD | T-0667 | 2022-03-05 | 1400/12/14 | [13 empty] | 1401-2294-6037 | 2022-03-30 | 1401/01/10 | 2022-04-03 | 1401/01/14 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0007_D01
1 | 2 | 0 | 8 | 0 | 1 | 8 | 1.2.8.1.8 | Specification For Safety Signs | BK-GNRAL-PEDCO-000-SA-SP-0008 | BK-GNRAL-PEDCO-000-SA-SP-0008 | BK | GNRAL | PEDCO | 000 | SA | SP | 0008 | F0Z-707200 | AFD | IFC | 2021-08-07 | 2021-08-22 | 2021-09-08 | 15 | 17 | 32 | IFA | 2021-09-21 | 2021-09-29 | 2021-10-11 | 8 | 12 | 20 | IFA | 2021-11-10 | 2021-11-01 | 2021-11-06 | -9 | 5 | -4 | AFD | 2022-01-23 | 2022-01-11 | 2022-01-30 | -12 | 19 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-01-09 |  | D03 | AFD | T-0440 | 2022-01-09 | 1400/10/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-360413 | 2022-01-11 | 1400/10/21 | 2022-01-30 | 1400/11/10 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0004 | 2021-07-24 | 1400/05/02 | [13 empty] | 1400/2294/168847 | 2021-08-22 | 1400/05/31 | 2021-09-08 | 1400/06/17 | CM | [10 empty] | D01 | IFA | T-0081 | 2021-09-07 | 1400/06/16 | [13 empty] | 1400-2294-217844 | 2021-09-29 | 1400/07/07 | 2021-10-11 | 1400/07/19 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0008_D00 | [9 empty] | D02 | IFA | T-0191 | 2021-10-27 | 1400/08/05 | [13 empty] | 1400-2294-256924 | 2021-11-01 | 1400/08/10 | 2021-11-06 | 1400/08/15 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-SA-SP-0008_D01 | [9 empty] | D03 | AFD | T-0440 | 2022-01-09 | 1400/10/19 | [13 empty] | 1400-2294-360413 | 2022-01-11 | 1400/10/21 | 2022-01-30 | 1400/11/10 | AP
1 | 2 | 0 | 8 | 0 | 2 | 0 | 1.2.8.2 | Drawing/Diagram
1 | 2 | 0 | 8 | 0 | 2 | 1 | 1.2.8.2.1 | Typical Installation Detail for Safety & Fire Fighting Equipment | BK-GNRAL-PEDCO-000-SA-DW-0002 | BK-GNRAL-PEDCO-000-SA-DW-0002 | BK | GNRAL | PEDCO | 000 | SA | DW | 0002 | F2L-707201 | IFI | IFI | 2022-01-12 | 2022-01-20 | 2022-01-22 | 8 | 2 | 10 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-29 | 2021-12-29 |  | D00 | IFI | T-0405 | 2021-12-29 | 1400/10/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-372872 | 2022-01-20 | 1400/10/30 | 2022-01-22 | 1400/11/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0405 | 2021-12-29 | 1400/10/08 | [13 empty] | 1400-2294-372872 | 2022-01-20 | 1400/10/30 | 2022-01-22 | 1400/11/02 | AP
1 | 2 | 0 | 8 | 0 | 2 | 2 | 1.2.8.2.2 | Symbol & Legend For Safety & Firefighting Systems | BK-GNRAL-PEDCO-000-SA-DW-0003 | BK-GNRAL-PEDCO-000-SA-DW-0003 | BK | GNRAL | PEDCO | 000 | SA | DW | 0003 | F2L-707202 | AFC | IFC | 2021-09-12 | 2021-09-13 | 2021-09-18 | 1 | 5 | 6 | IFA | 2021-11-08 | 2021-11-22 | 2021-11-27 | 14 | 5 | 19 | AFC | 2021-12-22 | 2021-12-13 | 2021-12-15 | -9 | 2 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-29 | 2021-12-08 |  | D02 | AFC | T-0315 | 2021-12-08 | 1400/09/18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-316975 | 2021-12-13 | 1400/09/22 | 2021-12-15 | 1400/09/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0070 | 2021-08-29 | 1400/06/07 | [13 empty] | 1400-2294-197171 | 2021-09-13 | 1400/06/22 | 2021-09-18 | 1400/06/27 | CM | [10 empty] | D01 | IFA | T-0184 | 2021-10-25 | 1400/08/03 | [13 empty] | 1400-2294-286876 | 2021-11-22 | 1400/09/01 | 2021-11-27 | 1400/09/06 | AP | NISOC-CRS- BK-GNRAL-PEDCO-000-SA-DW-0003 D00 | [9 empty] | D02 | AFC | T-0315 | 2021-12-08 | 1400/09/18 | [13 empty] | 1400-2294-316975 | 2021-12-13 | 1400/09/22 | 2021-12-15 | 1400/09/24 | AP
1 | 2 | 0 | 8 | 0 | 3 | 0 | 1.2.8.3 | Data Sheets
1 | 2 | 0 | 8 | 0 | 3 | 1 | 1.2.8.3.1 | Material Safety Data Sheets | BK-GNRAL-PEDCO-000-SA-DT-0001 | BK-GNRAL-PEDCO-000-SA-DT-0001 | BK | GNRAL | PEDCO | 000 | SA | DT | 0001 | F0Z-707203 | AFC | IFC | 44474 | 44590 | 44592 | 116 | 2 | 118 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-21 | 0 |  | D00 | IFC | T-0111 | 2021-09-21 | 1400/06/30 | 0 | 0 | 0 | BK-SUR-HSE-HSE-00-01662 | 2021-10-03 | 1400/07/11 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-386703 | 2022-01-29 | 1400/11/09 | 2022-01-31 | 1400/11/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0111 | 2021-09-21 | 1400/06/30 |  |  |  | BK-SUR-HSE-HSE-00-01662 | 2021-10-03 | 1400/07/11 | CM-C2 | [6 empty] | 1400-2294-386703 | 2022-01-29 | 1400/11/09 | 2022-01-31 | 1400/11/11 | CM
1 | 2 | 0 | 9 | 0 | 0 | 0 | 1.2.9 | Electrical
1 | 2 | 0 | 9 | 0 | 1 | 0 | 1.2.9.1 | Basis/Criteria
1 | 2 | 0 | 9 | 0 | 1 | 1 | 1.2.9.1.1 | Electrical System Design Criteria | BK-GNRAL-PEDCO-000-EL-DC-0001 | BK-GNRAL-PEDCO-000-EL-DC-0001 | BK | GNRAL | PEDCO | 000 | EL | DC | 0001 | F0Z-707204 | AFD | IFC | 44425 | 44441 | 44443 | 16 | 2 | 18 | IFA | 44460 | 44461 | 44465 | 1 | 4 | 5 | AFD | 44627 | 44625 | 44621 | -2 | -4 | -6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-03 | 2022-02-21 |  | D02 | AFD | T-0619 | 2022-02-21 | 1400/12/02 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03251 | 2022-02-27 | 1400/12/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430788 | 2022-03-05 | 1400/12/05 | 2022-03-01 | 1400/12/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DC-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0026 | 2021-08-03 | 1400/05/12 |  |  |  | BK-SUR-ENG-ELE-00-01318 | 2021-08-14 | 1400/05/23 | CM-C3 | [6 empty] | 1400/2294/182812 | 2021-09-02 | 1400/06/11 | 2021-09-04 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0083 | 2021-09-07 | 1400/06/16 |  |  |  | BK-SUR-ENG-ELE-00-01545 | 2021-09-18 | 1400/06/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DC-0001_D00 | [5 empty] | 1400-2294-209506 | 2021-09-22 | 1400/06/31 | 2021-09-26 | 1400/07/04 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DC-0001_D00 | [9 empty] | D02 | AFD | T-0619 | 2022-02-21 | 1400/12/02 |  |  |  | BK-SUR-ENG-ELE-00-03251 | 2022-02-27 | 1400/12/08 | AP | [6 empty] | 1400-2294-430788 | 2022-03-05 | 1400/12/05 | 2022-03-01 | 1400/12/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DC-0001_D01
1 | 2 | 0 | 9 | 0 | 2 | 0 | 1.2.9.2 | Specification
1 | 2 | 0 | 9 | 0 | 2 | 1 | 1.2.9.2.1 | Specification For LV Switchgear & Motor Control Centers | BK-GNRAL-PEDCO-000-EL-SP-0001 | BK-GNRAL-PEDCO-000-EL-SP-0001 | BK | GNRAL | PEDCO | 000 | EL | SP | 0001 | F0Z-707205 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-10-31 | 2022-01-02 | 2021-11-07 | 63 | -56 | 7 | AFD | 2022-02-27 | 2022-03-05 | 2022-03-01 | 6 | -4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-02-13 |  | D03 | AFD | T-0586 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03175 | 2022-02-22 | 1400/12/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430789 | 2022-03-05 | 1400/12/14 | 2022-03-01 | 1400/12/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 2021-08-04 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 2021-08-23 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 2021-09-06 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 2021-10-01 | 1400/07/09 | 2021-10-10 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0001_D00 | [9 empty] | D02 | IFA | T-0163 | 2021-10-17 | 1400/07/25 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 2021-10-31 | 1400/08/09 | AP | [6 empty] | 1400-2294-261165 | 2022-01-02 | 1400/08/12 | 2021-11-07 | 1400/08/16 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0001-D01 | [9 empty] | D03 | AFD | T-0586 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03175 | 2022-02-22 | 1400/12/02 | AP | [6 empty] | 1400-2294-430789 | 2022-03-05 | 1400/12/14 | 2022-03-01 | 1400/12/10 | CM
1 | 2 | 0 | 9 | 0 | 2 | 2 | 1.2.9.2.2 | Specification For MV Switchgear | BK-GNRAL-PEDCO-000-EL-SP-0002 | BK-GNRAL-PEDCO-000-EL-SP-0002 | BK | GNRAL | PEDCO | 000 | EL | SP | 0002 | F0Z-707206 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-10-31 | 2022-01-02 | 2021-11-07 | 63 | -56 | 7 | AFD | 2022-02-27 | 2022-03-05 | 2022-03-01 | 6 | -4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-02-13 |  | D03 | AFD | T-0586 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03175 | 2022-02-22 | 1400/12/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430789 | 2022-03-05 | 1400/12/14 | 2022-03-01 | 1400/12/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 2021-08-04 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 2021-08-23 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 2021-09-06 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 2021-10-01 | 1400/07/09 | 2021-10-10 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0002_D00 | [9 empty] | D02 | IFA | T-0163 | 2021-10-17 | 1400/07/25 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 2021-10-31 | 1400/08/09 | AP | [6 empty] | 1400-2294-261165 | 2022-01-02 | 1400/08/12 | 2021-11-07 | 1400/08/16 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0002_D01 | [9 empty] | D03 | AFD | T-0586 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03175 | 2022-02-22 | 1400/12/02 | AP | [6 empty] | 1400-2294-430789 | 2022-03-05 | 1400/12/14 | 2022-03-01 | 1400/12/10 | CM
1 | 2 | 0 | 9 | 0 | 2 | 3 | 1.2.9.2.3 | Specification For UPS System | BK-GNRAL-PEDCO-000-EL-SP-0003 | BK-GNRAL-PEDCO-000-EL-SP-0003 | BK | GNRAL | PEDCO | 000 | EL | SP | 0003 | F0Z-707207 | AFD | IFC | 2021-08-18 | 2021-09-02 | 2021-09-04 | 15 | 2 | 17 | IFA | 2021-09-21 | 2021-09-22 | 2021-09-26 | 1 | 4 | 5 | IFA | 2021-12-29 | 2022-01-06 | 2022-01-08 | 8 | 2 | 10 | AFD | 2022-02-27 | 2022-03-01 | 2022-03-08 | 2 | 7 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-04 | 2022-02-13 |  | D03 | AFD | T-0594 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03178 | 2022-02-22 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430798 | 2022-03-01 | 1400/12/10 | 2022-03-08 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0028 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-ELE-00-01337 | 2021-08-15 | 1400/05/24 | CM-C2 | [6 empty] | 1400/2294/182811 | 2021-09-02 | 1400/06/13 | 2021-09-04 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0083 | 2021-09-07 | 1400/06/16 |  |  |  | BK-SUR-ENG-ELE-00-01545 | 2021-09-18 | 1400/06/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-SP-0003_D00 | [5 empty] | 1400-2294-209506 | 2021-09-22 | 1400/06/31 | 2021-09-26 | 1400/07/04 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0003_D00 | [9 empty] | D02 | IFA | T-0348 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-ELE-00-02411 | 2021-12-25 | 1400/10/04 | AP | [6 empty] | 1400-2294-352441 | 2022-01-06 | 1400/10/16 | 2022-01-08 | 1400/10/18 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0003_D01 | [9 empty] | D03 | AFD | T-0594 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03178 | 2022-02-22 | 1400/12/03 | AP | [6 empty] | 1400-2294-430798 | 2022-03-01 | 1400/12/10 | 2022-03-08 | 1400/12/17 | CM
1 | 2 | 0 | 9 | 0 | 2 | 4 | 1.2.9.2.4 | Specification For Transformers | BK-GNRAL-PEDCO-000-EL-SP-0004 | BK-GNRAL-PEDCO-000-EL-SP-0004 | BK | GNRAL | PEDCO | 000 | EL | SP | 0004 | F0Z-707208 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-11-01 | 2022-01-02 | 2021-11-07 | 62 | -56 | 6 | AFD | 2022-03-22 | 2022-03-14 | 2022-03-26 | -8 | 12 | 4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-03-08 |  | D03 | AFD | T-0696 | 2022-03-08 | 1400/12/17 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03532 | 2022-03-13 | 1400/12/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448998 | 2022-03-14 | 1400/12/23 | 2022-03-26 | 1401/01/06 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 2021-08-04 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 2021-08-23 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 2021-09-06 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 2021-10-01 | 1400/07/09 | 2021-10-10 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0004_D00 | [9 empty] | D02 | IFA | T-0166 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 2021-10-31 | 1400/08/09 | AP | [6 empty] | 1400-2294-261157 | 2022-01-02 | 1400/10/12 | 2021-11-07 | 1400/08/16 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0004_D01 | [9 empty] | D03 | AFD | T-0696 | 2022-03-08 | 1400/12/17 |  |  |  | BK-SUR-ENG-ELE-00-03532 | 2022-03-13 | 1400/12/22 | AP | [6 empty] | 1400-2294-448998 | 2022-03-14 | 1400/12/23 | 2022-03-26 | 1401/01/06 | AP
1 | 2 | 0 | 9 | 0 | 2 | 5 | 1.2.9.2.5 | Specification For DC Charger | BK-GNRAL-PEDCO-000-EL-SP-0005 | BK-GNRAL-PEDCO-000-EL-SP-0005 | BK | GNRAL | PEDCO | 000 | EL | SP | 0005 | F0Z-707209 | AFD | IFC | 2021-08-18 | 2021-09-02 | 2021-09-04 | 15 | 2 | 17 | IFA | 2021-09-21 | 2021-09-22 | 2021-09-26 | 1 | 4 | 5 | IFA | 2021-11-03 | 2021-11-09 | 2021-11-14 | 6 | 5 | 11 | AFD | 2021-12-21 | 2022-01-03 | 2022-01-05 | 13 | 2 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-04 | 2021-12-07 |  | D03 | AFD | T-0307 | 2021-12-07 | 1400/09/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-348119 | 2022-01-03 | 1400/10/13 | 2022-01-05 | 1400/10/15 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0028 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-ELE-00-01337 | 2021-08-15 | 1400/05/24 | CM-C2 | [6 empty] | 1400/2294/182811 | 2021-09-02 | 1400/06/13 | 2021-09-04 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0083 | 2021-09-07 | 1400/06/16 |  |  |  | BK-SUR-ENG-ELE-00-01545 | 2021-09-18 | 1400/06/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-SP-0005_D00 | [5 empty] | 1400-2294-209506 | 2021-09-22 | 1400/06/31 | 2021-09-26 | 1400/07/04 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0005_D00 | [9 empty] | D02 | IFA | T-0177 | 2021-10-20 | 1400/07/28 |  |  |  | FW BK-SUR-ENG-ELE-00-01862 | 2021-10-31 | 1400/08/09 | AP | [6 empty] | 1400-2294-268781 | 2021-11-09 | 1400/08/18 | 2021-11-14 | 1400/08/23 | AP | NISOC-CRS-BK-GNRAL-PEDEC-000-EL-SP-0005-D01 | [9 empty] | D03 | AFD | T-0307 | 2021-12-07 | 1400/09/16 | [13 empty] | 1400-2294-348119 | 2022-01-03 | 1400/10/13 | 2022-01-05 | 1400/10/15 | AP
1 | 2 | 0 | 9 | 0 | 2 | 6 | 1.2.9.2.6 | Specification For Earthing & Lightning System | BK-GNRAL-PEDCO-000-EL-SP-0006 | BK-GNRAL-PEDCO-000-EL-SP-0006 | BK | GNRAL | PEDCO | 000 | EL | SP | 0006 | F0Z-707210 | AFD | IFC | 2021-08-11 | 2021-08-22 | 2021-09-01 | 11 | 10 | 21 | IFA | 2021-09-18 | 2021-09-14 | 2021-09-18 | -4 | 4 | 0 | IFA | 2021-10-09 | 2021-10-13 | 2021-10-18 | 4 | 5 | 9 | AFD | 2021-11-16 | 2021-11-16 | 2021-11-21 | 0 | 5 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 2021-11-02 |  | D03 | AFD | T-0206 | 2021-11-02 | 1400/08/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-01957 | 2021-11-09 | 1400/08/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-279102 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0020 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-ELE-00-01304 | 2021-08-10 | 1400/05/19 | AP | [6 empty] | 1400/2294/168846 | 2021-08-22 | 1400/05/31 | 2021-09-01 | 1400/06/10 | CM | [10 empty] | D01 | IFA | T-0075 | 2021-09-04 | 1400/06/13 |  |  |  | BK-SSR-ENG-ELE-00-01507 | 2021-09-13 | 1400/06/22 | AP | [6 empty] | 1400-2294-198779 | 2021-09-14 | 1400/06/23 | 2021-09-18 | 1400/06/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0006_D00 | [9 empty] | D02 | IFA | T-0116 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-ELE-00-01666 | 2021-10-03 | 1400/07/11 | AP | [6 empty] | 1400-2294-232456 | 2021-10-13 | 1400/07/21 | 2021-10-18 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0006_D01 | [9 empty] | D03 | AFD | T-0206 | 2021-11-02 | 1400/08/11 |  |  |  | BK-SUR-ENG-ELE-00-01957 | 2021-11-09 | 1400/08/18 | AP | [6 empty] | 1400-2294-279102 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | AP
1 | 2 | 0 | 9 | 0 | 2 | 7 | 1.2.9.2.7 | Specification For Lighting & Small Power System | BK-GNRAL-PEDCO-000-EL-SP-0007 | BK-GNRAL-PEDCO-000-EL-SP-0007 | BK | GNRAL | PEDCO | 000 | EL | SP | 0007 | F0Z-707211 | AFD | IFC | 2021-08-11 | 2021-08-22 | 2021-09-01 | 11 | 10 | 21 | IFA | 2021-09-18 | 2021-09-14 | 2021-09-18 | -4 | 4 | 0 | IFA | 2021-10-09 | 2021-10-13 | 2021-10-18 | 4 | 5 | 9 | AFD | 2021-11-16 | 2021-11-16 | 2021-11-21 | 0 | 5 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 2021-11-02 |  | D03 | AFD | T-0206 | 2021-11-02 | 1400/08/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-01957 | 2021-11-09 | 1400/08/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-279102 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0020 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-ELE-00-01304 | 2021-08-10 | 1400/05/19 | AP | [6 empty] | 1400/2294/168846 | 2021-08-22 | 1400/05/31 | 2021-09-01 | 1400/06/10 | CM | [10 empty] | D01 | IFA | T-0075 | 2021-09-04 | 1400/06/13 |  |  |  | BK-SSR-ENG-ELE-00-01507 | 2021-09-13 | 1400/06/22 | AP | [6 empty] | 1400-2294-198779 | 2021-09-14 | 1400/06/23 | 2021-09-18 | 1400/06/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0007_D00 | [9 empty] | D02 | IFA | T-0116 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-ELE-00-01666 | 2021-10-03 | 1400/07/11 | AP | [6 empty] | 1400-2294-232456 | 2021-10-13 | 1400/07/21 | 2021-10-18 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0007_D01 | [9 empty] | D03 | AFD | T-0206 | 2021-11-02 | 1400/08/11 |  |  |  | BK-SUR-ENG-ELE-00-01957 | 2021-11-09 | 1400/08/18 | AP | [6 empty] | 1400-2294-279102 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | AP
1 | 2 | 0 | 9 | 0 | 2 | 8 | 1.2.9.2.8 | Specification For Bulk Materials | BK-GNRAL-PEDCO-000-EL-SP-0008 | BK-GNRAL-PEDCO-000-EL-SP-0008 | BK | GNRAL | PEDCO | 000 | EL | SP | 0008 | F0Z-707212 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-11-01 | 2022-01-02 | 2021-11-07 | 62 | -56 | 6 | AFD | 2022-02-27 | 2022-03-05 | 2022-03-01 | 6 | -4 | 2 | AFD | 2022-03-21 | 2022-03-14 | 2022-03-26 | -7 | 12 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-03-07 |  | D04 | AFD | T-0693 | 2022-03-07 | 1400/12/16 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03530 | 2022-03-13 | 1400/12/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448996 | 2022-03-14 | 1400/12/23 | 2022-03-26 | 1401/01/06 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0008_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 2021-08-04 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 2021-08-23 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 2021-09-06 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 2021-10-01 | 1400/07/09 | 2021-10-10 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0008_D00 | [9 empty] | D02 | IFA | T-0166 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 2021-10-31 | 1400/08/09 | AP | [6 empty] | 1400-2294-261157 | 2022-01-02 | 1400/10/12 | 2021-11-07 | 1400/08/16 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0008_D01 | [9 empty] | D03 | AFD | T-0586 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03175 | 2022-02-22 | 1400/12/02 | AP | [6 empty] | 1400-2294-430789 | 2022-03-05 | 1400/12/14 | 2022-03-01 | 1400/12/10 | CM | [10 empty] | D04 | AFD | T-0693 | 2022-03-07 | 1400/12/16 |  |  |  | BK-SUR-ENG-ELE-00-03530 | 2022-03-13 | 1400/12/22 | AP | [6 empty] | 1400-2294-448996 | 2022-03-14 | 1400/12/23 | 2022-03-26 | 1401/01/06 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0008_D03
1 | 2 | 0 | 9 | 0 | 2 | 9 | 1.2.9.2.9 | Specification For Diesel Generator | BK-GNRAL-PEDCO-000-EL-SP-0009 | BK-GNRAL-PEDCO-000-EL-SP-0009 | BK | GNRAL | PEDCO | 000 | EL | SP | 0009 | F0Z-707213 | AFD | IFC | 2021-08-11 | 2021-08-22 | 2021-09-01 | 11 | 10 | 21 | IFA | 2021-09-18 | 2021-09-14 | 2021-09-18 | -4 | 4 | 0 | IFA | 2021-10-09 | 2021-10-13 | 2021-10-18 | 4 | 5 | 9 | AFD | 2021-11-16 | 2021-11-16 | 2021-11-21 | 0 | 5 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 2021-11-02 |  | D03 | AFD | T-0206 | 2021-11-02 | 1400/08/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-01957 | 2021-11-09 | 1400/08/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-279102 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0020 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-ELE-00-01304 | 2021-08-10 | 1400/05/19 | AP | [6 empty] | 1400/2294/168846 | 2021-08-22 | 1400/05/31 | 2021-09-01 | 1400/06/10 | CM | [10 empty] | D01 | IFA | T-0075 | 2021-09-04 | 1400/06/13 |  |  |  | BK-SSR-ENG-ELE-00-01507 | 2021-09-13 | 1400/06/22 | AP | [6 empty] | 1400-2294-198779 | 2021-09-14 | 1400/06/23 | 2021-09-18 | 1400/06/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0009_D00 | [9 empty] | D02 | IFA | T-0116 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-ELE-00-01666 | 2021-10-03 | 1400/07/11 | AP | [6 empty] | 1400-2294-232456 | 2021-10-13 | 1400/07/21 | 2021-10-18 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0009_D01 | [9 empty] | D03 | AFD | T-0206 | 2021-11-02 | 1400/08/11 |  |  |  | BK-SUR-ENG-ELE-00-01957 | 2021-11-09 | 1400/08/18 | AP | [6 empty] | 1400-2294-279102 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | AP
1 | 2 | 0 | 9 | 0 | 2 | 10 | 1.2.9.2.10 | Specification For LV Induction Motors | BK-GNRAL-PEDCO-000-EL-SP-0010 | BK-GNRAL-PEDCO-000-EL-SP-0010 | BK | GNRAL | PEDCO | 000 | EL | SP | 0010 | F0Z-707214 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFC | 2021-11-01 | 2022-01-02 | 2021-11-07 | 62 | -56 | 6 | AFD | 2022-02-27 | 2022-03-05 | 2022-03-01 | 6 | -4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-02-13 |  | D03 | AFD | T-0586 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03175 | 2022-02-22 | 1400/12/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430789 | 2022-03-05 | 1400/12/14 | 2022-03-01 | 1400/12/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 2021-08-04 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 2021-08-23 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 2021-09-06 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 2021-10-01 | 1400/07/09 | 2021-10-10 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0010_D00 | [9 empty] | D02 | IFC | T-0170 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 2021-10-31 | 1400/08/09 | AP | [6 empty] | 1400-2294-261334 | 2022-01-02 | 1400/10/12 | 2021-11-07 | 1400/08/16 | AP | NISOC-CRS- BK-GNRAL-PEDCO-000-EL-SP-0010_D01 | [9 empty] | D03 | AFD | T-0586 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03175 | 2022-02-22 | 1400/12/02 | AP | [6 empty] | 1400-2294-430789 | 2022-03-05 | 1400/12/14 | 2022-03-01 | 1400/12/10 | CM
1 | 2 | 0 | 9 | 0 | 2 | 11 | 1.2.9.2.11 | Specification For Electrical Requirements of Packaged Units | BK-GNRAL-PEDCO-000-EL-SP-0011 | BK-GNRAL-PEDCO-000-EL-SP-0011 | BK | GNRAL | PEDCO | 000 | EL | SP | 0011 | F0Z-707215 | AFD | IFC | 2021-08-11 | 2021-08-22 | 2021-09-01 | 11 | 10 | 21 | IFA | 2021-09-18 | 2021-09-14 | 2021-09-18 | -4 | 4 | 0 | IFA | 2021-10-09 | 2021-10-13 | 2021-10-18 | 4 | 5 | 9 | AFD | 2021-11-16 | 2021-11-16 | 2021-11-21 | 0 | 5 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 2021-11-02 |  | D03 | AFD | T-0206 | 2021-11-02 | 1400/08/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-01957 | 2021-11-09 | 1400/08/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-279102 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0020 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-ELE-00-01304 | 2021-08-10 | 1400/05/19 | AP | [6 empty] | 1400/2294/168846 | 2021-08-22 | 1400/05/31 | 2021-09-01 | 1400/06/10 | CM | [10 empty] | D01 | IFA | T-0075 | 2021-09-04 | 1400/06/13 |  |  |  | BK-SSR-ENG-ELE-00-01507 | 2021-09-13 | 1400/06/22 | AP | [6 empty] | 1400-2294-198779 | 2021-09-14 | 1400/06/23 | 2021-09-18 | 1400/06/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0011_D00 | [9 empty] | D02 | IFA | T-0116 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-ELE-00-01666 | 2021-10-03 | 1400/07/11 | AP | [6 empty] | 1400-2294-232456 | 2021-10-13 | 1400/07/21 | 2021-10-18 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0011_D01 | [9 empty] | D03 | AFD | T-0206 | 2021-11-02 | 1400/08/11 |  |  |  | BK-SUR-ENG-ELE-00-01957 | 2021-11-09 | 1400/08/18 | AP | [6 empty] | 1400-2294-279102 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | AP
1 | 2 | 0 | 9 | 0 | 2 | 12 | 1.2.9.2.12 | Specification For Capacitor Bank | BK-GNRAL-PEDCO-000-EL-SP-0012 | BK-GNRAL-PEDCO-000-EL-SP-0012 | BK | GNRAL | PEDCO | 000 | EL | SP | 0012 | F0Z-707216 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-11-01 | 2021-11-07 | 2021-11-07 | 6 | 0 | 6 | AFD | 2022-02-27 | 2022-03-01 | 2022-03-08 | 2 | 7 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-02-13 |  | D03 | AFD | T-0594 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03178 | 2022-02-22 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430798 | 2022-03-01 | 1400/12/10 | 2022-03-08 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 2021-08-04 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 2021-08-23 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 2021-09-06 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 2021-10-01 | 1400/07/09 | 2021-10-10 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0012_D00 | [9 empty] | D02 | IFA | T-0171 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 2021-10-31 | 1400/08/09 | AP | [6 empty] | 1400-2294-263867 | 2021-11-07 | 1400/08/16 | 2021-11-07 | 1400/08/16 | AP | NISOC-CRS- BK-GNRAL-PEDCO-000-EL-SP-0012_D01 | [9 empty] | D03 | AFD | T-0594 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03178 | 2022-02-22 | 1400/12/03 | AP | [6 empty] | 1400-2294-430798 | 2022-03-01 | 1400/12/10 | 2022-03-08 | 1400/12/17 | CM
1 | 2 | 0 | 9 | 0 | 2 | 13 | 1.2.9.2.13 | Specification For Distribution & Lighting Panels | BK-GNRAL-PEDCO-000-EL-SP-0013 | BK-GNRAL-PEDCO-000-EL-SP-0013 | BK | GNRAL | PEDCO | 000 | EL | SP | 0013 | F0Z-707217 | AFD | IFC | 2021-08-11 | 2021-08-22 | 2021-09-01 | 11 | 10 | 21 | IFA | 2021-09-18 | 2021-09-14 | 2021-09-18 | -4 | 4 | 0 | IFA | 2021-10-09 | 2021-10-13 | 2021-10-18 | 4 | 5 | 9 | AFD | 2021-11-16 | 2021-11-16 | 2021-11-21 | 0 | 5 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 2021-11-02 |  | D03 | AFD | T-0206 | 2021-11-02 | 1400/08/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-01957 | 2021-11-09 | 1400/08/18 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-279102 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0020 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-ELE-00-01304 | 2021-08-10 | 1400/05/19 | AP | [6 empty] | 1400/2294/168846 | 2021-08-22 | 1400/05/31 | 2021-09-01 | 1400/06/10 | CM | [10 empty] | D01 | IFA | T-0075 | 2021-09-04 | 1400/06/13 |  |  |  | BK-SSR-ENG-ELE-00-01507 | 2021-09-13 | 1400/06/22 | AP | [6 empty] | 1400-2294-198779 | 2021-09-14 | 1400/06/23 | 2021-09-18 | 1400/06/27 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0013_D00 | [9 empty] | D02 | IFA | T-0116 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-ELE-00-01666 | 2021-10-03 | 1400/07/11 | AP | [6 empty] | 1400-2294-232456 | 2021-10-13 | 1400/07/21 | 2021-10-18 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0013_D01 | [9 empty] | D03 | AFD | T-0206 | 2021-11-02 | 1400/08/11 |  |  |  | BK-SUR-ENG-ELE-00-01957 | 2021-11-09 | 1400/08/18 | AP | [6 empty] | 1400-2294-279102 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | AP
1 | 2 | 0 | 9 | 0 | 2 | 14 | 1.2.9.2.14 | Specification For Power & Control Cables | BK-GNRAL-PEDCO-000-EL-SP-0014 | BK-GNRAL-PEDCO-000-EL-SP-0014 | BK | GNRAL | PEDCO | 000 | EL | SP | 0014 | F0Z-707218 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-11-01 | 2021-11-07 | 2021-11-07 | 6 | 0 | 6 | AFD | 2022-02-27 | 2022-03-01 | 2022-03-08 | 2 | 7 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-02-13 |  | D03 | AFD | T-0594 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03178 | 2022-02-22 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430798 | 2022-03-01 | 1400/12/10 | 2022-03-08 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 2021-08-04 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 2021-08-23 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 2021-09-06 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 2021-10-01 | 1400/07/09 | 2021-10-10 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0014_D00 | [9 empty] | D02 | IFA | T-0171 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 2021-10-31 | 1400/08/09 | AP | [6 empty] | 1400-2294-263867 | 2021-11-07 | 1400/08/16 | 2021-11-07 | 1400/08/16 | AP | NISOC-CRS- BK-GNRAL-PEDCO-000-EL-SP-0014_D01 | [9 empty] | D03 | AFD | T-0594 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03178 | 2022-02-22 | 1400/12/03 | AP | [6 empty] | 1400-2294-430798 | 2022-03-01 | 1400/12/10 | 2022-03-08 | 1400/12/17 | CM
1 | 2 | 0 | 9 | 0 | 2 | 15 | 1.2.9.2.15 | Specification For Cathodic Protection System | BK-GNRAL-PEDCO-000-EL-SP-0016 | BK-GNRAL-PEDCO-000-EL-SP-0016 | BK | GNRAL | PEDCO | 000 | EL | SP | 0016 | F0Z-707219 | AFD | IFC | 2021-08-14 | 2021-09-02 | 2021-09-04 | 19 | 2 | 21 | IFA | 2021-09-28 | 2021-09-28 | 2021-10-02 | 0 | 4 | 4 | IFA | 2021-10-25 | 2021-10-30 | 2021-11-01 | 5 | 2 | 7 | AFD | 2021-12-21 | 2022-01-03 | 2022-01-05 | 13 | 2 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-31 | 2021-12-07 |  | D03 | AFD | T-0307 | 2021-12-07 | 1400/09/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-348119 | 2022-01-03 | 1400/10/13 | 2022-01-05 | 1400/10/15 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0024 | 2021-07-31 | 1400/05/09 |  |  |  | BK-SUR-ENG-ELE-00-01306 | 2021-08-10 | 1400/05/19 | CM-C2 |  | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-SP-0016_D01 | 2021-09-25 | 1400/07/03 | CM-C2 |  | 1400/2294/182822 | 2021-09-02 | 1400/06/11 | 2021-09-04 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0092 | 2021-09-14 | 1400/06/23 |  |  |  | BK-SUR-ENG-ELE-00-01592 | 2021-09-25 | 1400/07/03 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-SP-0016_D00 | [5 empty] | 1400-2294-215960 | 2021-09-28 | 1400/07/06 | 2021-10-02 | 1400/07/10 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0016_D00 | [9 empty] | D02 | IFA | T-0146 | 2021-10-11 | 1400/07/19 |  |  |  | BK-SUR-ENG-ELE-00-01783 | 2021-10-19 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-SP-0016-D01 | [5 empty] | 1400-2294-253895 | 2021-10-30 | 1400/08/08 | 2021-11-01 | 1400/08/10 | AP | NISOC-CRS-CRS-BK-GNRAL-PEDCO-000-EL-SP-0016-D01 | [9 empty] | D03 | AFD | T-0307 | 2021-12-07 | 1400/09/16 | [13 empty] | 1400-2294-348119 | 2022-01-03 | 1400/10/13 | 2022-01-05 | 1400/10/15 | AP
1 | 2 | 0 | 9 | 0 | 2 | 16 | 1.2.9.2.16 | Specification For MV Induction Motors | BK-GNRAL-PEDCO-000-EL-SP-0017 | BK-GNRAL-PEDCO-000-EL-SP-0017 | BK | GNRAL | PEDCO | 000 | EL | SP | 0017 | F0Z-707220 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-12-29 | 2022-01-06 | 2022-01-08 | 8 | 2 | 10 | AFD | 2022-02-27 | 2022-03-01 | 2022-03-08 | 2 | 7 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-02-13 |  | D03 | AFD | T-0594 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03178 | 2022-02-22 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430798 | 2022-03-01 | 1400/12/10 | 2022-03-08 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 2021-08-04 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 2021-08-23 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 2021-09-06 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 2021-10-01 | 1400/07/09 | 2021-10-10 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0017_D00 | [9 empty] | D02 | IFA | T-0348 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-ELE-00-02411 | 2021-12-25 | 1400/10/04 | AP | [6 empty] | 1400-2294-352441 | 2022-01-06 | 1400/10/16 | 2022-01-08 | 1400/10/18 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0017_D01 | [9 empty] | D03 | AFD | T-0594 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03178 | 2022-02-22 | 1400/12/03 | AP | [6 empty] | 1400-2294-430798 | 2022-03-01 | 1400/12/10 | 2022-03-08 | 1400/12/17 | CM
1 | 2 | 0 | 9 | 0 | 2 | 17 | 1.2.9.2.17 | Specification For NGR | BK-GNRAL-PEDCO-000-EL-SP-0018 | BK-GNRAL-PEDCO-000-EL-SP-0018 | BK | GNRAL | PEDCO | 000 | EL | SP | 0018 | F0Z-707221 | AFD | IFC | 2021-08-07 | 2021-08-16 | 2021-08-23 | 9 | 7 | 16 | IFA | 2021-09-11 | 2021-10-01 | 2021-10-10 | 20 | 9 | 29 | IFA | 2021-11-01 | 2021-11-07 | 2021-11-07 | 6 | 0 | 6 | AFD | 2022-02-27 | 2022-03-01 | 2022-03-08 | 2 | 7 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-24 | 2022-02-13 |  | D03 | AFD | T-0594 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03178 | 2022-02-22 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430798 | 2022-03-01 | 1400/12/10 | 2022-03-08 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0003 | 2021-07-24 | 1400/05/02 |  |  |  | BK-SUR-ENG-ELE-00-01258 | 2021-08-04 | 1400/05/13 | AP | [6 empty] | 1400-2294-166482 | 2021-08-16 | 1400/05/25 | 2021-08-23 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0069 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-ELE-00-01466 | 2021-09-06 | 1400/06/15 | AP | [6 empty] | 1400-2294-218020 | 2021-10-01 | 1400/07/09 | 2021-10-10 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0018_D00 | [9 empty] | D02 | IFA | T-0171 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-ELE-00-01862 | 2021-10-31 | 1400/08/09 | AP | [6 empty] | 1400-2294-263867 | 2021-11-07 | 1400/08/16 | 2021-11-07 | 1400/08/16 | AP | NISOC-CRS- BK-GNRAL-PEDCO-000-EL-SP-0018_D01 | [9 empty] | D03 | AFD | T-0594 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03178 | 2022-02-22 | 1400/12/03 | AP | [6 empty] | 1400-2294-430798 | 2022-03-01 | 1400/12/10 | 2022-03-08 | 1400/12/17 | CM
1 | 2 | 0 | 9 | 0 | 2 | 18 | 1.2.9.2.18 | Specification For Overhead Transmission Lines | BK-GNRAL-PEDCO-000-EL-SP-0019 | BK-GNRAL-PEDCO-000-EL-SP-0019 | BK | GNRAL | PEDCO | 000 | EL | SP | 0019 | F0Z-707222 | AFD | IFC | 2021-08-11 | 2021-08-22 | 2021-09-01 | 11 | 10 | 21 | IFA | 2021-10-04 | 2021-09-30 | 2021-10-10 | -4 | 10 | 6 | IFA | 2021-10-26 | 2022-01-01 | 2021-11-07 | 67 | -55 | 12 | AFD | 2022-02-27 | 2022-03-05 | 2022-03-01 | 6 | -4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 2022-02-13 |  | D03 | AFD | T-0586 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03175 | 2022-02-22 | 1400/12/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430789 | 2022-03-05 | 1400/12/14 | 2022-03-01 | 1400/12/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0020 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-ELE-00-01304 | 2021-08-10 | 1400/05/19 | C4-RJ | [6 empty] | 1400/2294/168846 | 2021-08-22 | 1400/05/31 | 2021-09-01 | 1400/06/10 | CM | [10 empty] | D01 | IFA | T-0109 | 2021-09-20 | 1400/06/29 |  |  |  | BK-SSR-ENG-ELE-00-01652 | 2021-10-02 | 1400/07/10 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-SP-0019-D00 | [5 empty] | 1400-2294-217976 | 2021-09-30 | 1400/07/08 | 2021-10-10 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0019-D00 | [9 empty] | D02 | IFA | T-0154 | 2021-10-12 | 1400/07/20 |  |  |  | BK-SUR-ENG-ELE-00-01783 | 2021-10-19 | 1400/07/27 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-SP-0019-D01 | [5 empty] | 1400-2294-259366 | 2022-01-01 | 1400/08/11 | 2021-11-07 | 1400/08/16 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-SP-0019-D01 | [9 empty] | D03 | AFD | T-0586 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03175 | 2022-02-22 | 1400/12/02 | AP | [6 empty] | 1400-2294-430789 | 2022-03-05 | 1400/12/14 | 2022-03-01 | 1400/12/10 | CM
1 | 2 | 0 | 9 | 0 | 3 | 0 | 1.2.9.3 | Drawing/Diagram
1 | 2 | 0 | 9 | 0 | 3 | 1 | 1.2.9.3.1 | Electrical Legend and Symbols | BK-GNRAL-PEDCO-000-EL-DW-0001 | BK-GNRAL-PEDCO-000-EL-DW-0001 | BK | GNRAL | PEDCO | 000 | EL | DW | 0001 | F2P-707223 | AFC | IFC | 2021-08-23 | 2021-08-31 | 2021-09-04 | 8 | 4 | 12 | IFA | 2021-09-19 | 2021-09-19 | 2021-09-20 | 0 | 1 | 1 | AFC | 2021-12-22 | 2021-12-17 | 2021-12-18 | -5 | 1 | -4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 2021-12-08 |  | D02 | AFC | T-0318 | 2021-12-08 | 1400/09/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-320829 | 2021-12-17 | 1400/09/26 | 2021-12-18 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0038 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-ELE-00-01386 | 2021-08-23 | 1400/06/01 | CM-C2 | [6 empty] | 1400/2294/180348 | 2021-08-31 | 1400/06/09 | 2021-09-04 | 1400/06/13 | AP | [10 empty] | D01 | IFA | T-0077 | 2021-09-05 | 1400/06/14 |  |  |  | BK-SUR-ENG-ELE-00-01508 | 2021-09-13 | 1400/06/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0001_D00 | [5 empty] | 1400-2294-204414 | 2021-09-19 | 1400/06/28 | 2021-09-20 | 1400/06/29 | AP | [10 empty] | D02 | AFC | T-0318 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-320829 | 2021-12-17 | 1400/09/26 | 2021-12-18 | 1400/09/27 | AP
1 | 2 | 0 | 9 | 0 | 3 | 2 | 1.2.9.3.2 | Typical Installation Details & Notes For Earthing and Lightning Protection System | BK-GNRAL-PEDCO-000-EL-DW-0002 | BK-GNRAL-PEDCO-000-EL-DW-0002 | BK | GNRAL | PEDCO | 000 | EL | DW | 0002 | F2P-707224 | IFI | IFI | 2021-09-08 | 2021-09-13 | 2021-09-18 | 5 | 5 | 10 | IFI | 2021-10-16 | 2021-10-14 | 2021-10-18 | -2 | 4 | 2 | IFI | 2021-11-13 | 2021-11-14 | 2021-11-21 | 1 | 7 | 8 | IFI | 2021-12-12 | 2021-12-09 | 2021-12-11 | -3 | 2 | -1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-25 | 2021-11-28 |  | D03 | IFI | T-0280 | 2021-11-28 | 1400/09/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-310950 | 2021-12-09 | 1400/09/18 | 2021-12-11 | 1400/09/20 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DW-0002-D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0066 | 2021-08-25 | 1400/06/03 |  |  |  | BK-SUR-ENG-ELE-00-01447 | 2021-09-01 | 1400/06/10 | CM-C2 | [6 empty] | 1400-2294-197234 | 2021-09-13 | 1400/06/22 | 2021-09-18 | 1400/06/27 | CM | [10 empty] | D01 | IFI | T-0129 | 2021-10-02 | 1400/07/10 |  |  |  | BK-SUR-ENG-ELE-00-01713 | 2021-10-12 | 1400/07/20 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0002-D00 | [5 empty] | 1400-2294-234294 | 2021-10-14 | 1400/07/22 | 2021-10-18 | 1400/07/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DW-0002-D00 | [9 empty] | D02 | IFI | T-0192 | 2021-10-30 | 1400/08/08 | [13 empty] | 1400-2294-275278 | 2021-11-14 | 1400/08/23 | 2021-11-21 | 1400/08/30 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DW-0004-D01 | [9 empty] | D03 | IFI | T-0280 | 2021-11-28 | 1400/09/07 | [13 empty] | 1400-2294-310950 | 2021-12-09 | 1400/09/18 | 2021-12-11 | 1400/09/20 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DW-0002-D03
1 | 2 | 0 | 9 | 0 | 3 | 3 | 1.2.9.3.3 | Typical Installation Details & Notes For Lighting System | BK-GNRAL-PEDCO-000-EL-DW-0003 | BK-GNRAL-PEDCO-000-EL-DW-0003 | BK | GNRAL | PEDCO | 000 | EL | DW | 0003 | F2P-707225 | IFI | IFI | 2021-09-08 | 2021-09-13 | 2021-09-18 | 5 | 5 | 10 | IFI | 2021-11-08 | 2021-11-07 | 2021-11-07 | -1 | 0 | -1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-25 | 2021-10-25 |  | D01 | IFI | T-0182 | 2021-10-25 | 1400/08/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0003-D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-263872 | 2021-11-07 | 1400/08/16 | 2021-11-07 | 1400/08/16 | AP | NISOC- CRS-BK-GNRAL-PEDCO-000-EL-DW-0003-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0066 | 2021-08-25 | 1400/06/03 |  |  |  | BK-SUR-ENG-ELE-00-01447 | 2021-09-01 | 1400/06/10 | CM-C2 | [6 empty] | 1400-2294-197234 | 2021-09-13 | 1400/06/22 | 2021-09-18 | 1400/06/27 | CM | [10 empty] | D01 | IFI | T-0182 | 2021-10-25 | 1400/08/03 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0003-D00 | [5 empty] | 1400-2294-263872 | 2021-11-07 | 1400/08/16 | 2021-11-07 | 1400/08/16 | AP | NISOC- CRS-BK-GNRAL-PEDCO-000-EL-DW-0003-D00
1 | 2 | 0 | 9 | 0 | 3 | 4 | 1.2.9.3.4 | Typical Installation Details & Notes For Power System | BK-GNRAL-PEDCO-000-EL-DW-0004 | BK-GNRAL-PEDCO-000-EL-DW-0004 | BK | GNRAL | PEDCO | 000 | EL | DW | 0004 | F2P-707226 | IFI | IFI | 2021-09-08 | 2021-09-13 | 2021-09-18 | 5 | 5 | 10 | IFI | 2021-11-09 | 2021-11-09 | 2021-11-14 | 0 | 5 | 5 | IFI | 2021-12-12 | 2021-12-09 | 2021-12-11 | -3 | 2 | -1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-25 | 2021-11-28 |  | D02 | IFI | T-0280 | 2021-11-28 | 1400/09/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0004-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-310950 | 2021-12-09 | 1400/09/18 | 2021-12-11 | 1400/09/20 | AP | NISCO_CRS-BK-GNRAL-PEDCO-000-EL-DW-0004-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0066 | 2021-08-25 | 1400/06/03 |  |  |  | BK-SUR-ENG-ELE-00-01447 | 2021-09-01 | 1400/06/10 | CM-C2 | [6 empty] | 1400-2294-197234 | 2021-09-13 | 1400/06/22 | 2021-09-18 | 1400/06/27 | CM | [10 empty] | D01 | IFI | T-0187 | 2021-10-26 | 1400/08/04 |  |  |  | BK-SUR-ENG-ELE-00-01899 | 2021-11-14 | 1400/08/23 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0004-D00 | [5 empty] | 1400-2294-269297 | 2021-11-09 | 1400/08/18 | 2021-11-14 | 1400/08/23 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DW-0004-D00 | [9 empty] | D02 | IFI | T-0280 | 2021-11-28 | 1400/09/07 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0004-D01 | [5 empty] | 1400-2294-310950 | 2021-12-09 | 1400/09/18 | 2021-12-11 | 1400/09/20 | AP | NISCO_CRS-BK-GNRAL-PEDCO-000-EL-DW-0004-D01
1 | 2 | 0 | 9 | 0 | 3 | 5 | 1.2.9.3.5 | Installation Details & Notes For Cathodic Protection Systems | BK-GNRAL-PEDCO-000-EL-DW-0005 | BK-GNRAL-PEDCO-000-EL-DW-0005 | BK | GNRAL | PEDCO | 000 | EL | DW | 0005 | F2P-707227 | AFC | IFC | 2021-09-08 | 2021-09-13 | 2021-09-18 | 5 | 5 | 10 | IFA | 2021-10-09 | 2021-10-13 | 2021-10-18 | 4 | 5 | 9 | AFC | 2022-02-27 | 0 | 0 | -44619 | 0 | -44619 | 0 | 14 | 2022-03-05 | 2022-03-01 | 2022-02-19 | -4 | 2022-02-15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-25 | 2022-02-13 |  | D02 | AFC | T-0586 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03175 | 2022-02-22 | 1400/12/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0066 | 2021-08-25 | 1400/06/03 |  |  |  | BK-SUR-ENG-ELE-00-01447 | 2021-09-01 | 1400/06/10 | CM-C2 | [6 empty] | 1400-2294-197234 | 2021-09-13 | 1400/06/22 | 2021-09-18 | 1400/06/27 | CM | [10 empty] | D01 | IFA | T-0116 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-ELE-00-01666 | 2021-10-03 | 1400/07/11 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-EL-DW-0005_D00 | [5 empty] | 1400-2294-232456 | 2021-10-13 | 1400/07/21 | 2021-10-18 | 1400/07/26 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-EL-DW-0005_D00 | [9 empty] | D02 | AFC | T-0586 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03175 | 2022-02-22 | 1400/12/02 | AP | [30 empty] | BK-SUR-ENG-ELE-00-03175 | 2022-02-22 | 1400/12/02 | AP | [6 empty] | 1400-2294-430789 | 2022-03-05 | 1400/12/14 | 2022-03-01 | 1400/12/10 | AP
1 | 2 | 0 | 10 | 0 | 0 | 0 | 1.2.10 | Intercom. & Telecomm.
1 | 2 | 0 | 10 | 0 | 1 | 0 | 1.2.10.1 | Basis/Criteria
1 | 2 | 0 | 10 | 0 | 1 | 1 | 1.2.10.1.1 | Telecom. Design Criteria | BK-GNRAL-PEDCO-000-TE-DC-0001 | BK-GNRAL-PEDCO-000-TE-DC-0001 | BK | GNRAL | PEDCO | 000 | TE | DC | 0001 | F0Z-707228 | AFD | IFC | 44419 | 44451 | 44453 | 32 | 2 | 34 | IFA | 44478 | 44478 | 44481 | 0 | 3 | 3 | IFA | 44513 | 44519 | 44528 | 6 | 9 | 15 | AFD | 44551 | 44547 | 44548 | -4 | 1 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 2021-12-07 |  | D03 | AFD | T-0305 | 2021-12-07 | 1400/09/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-320827 | 2021-12-17 | 1400/09/26 | 2021-12-18 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0019 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-TEL-00-01305 | 2021-08-10 | 1400/05/19 | CM-C3 | [6 empty] | 1400/2294/194238 | 2021-09-12 | 1400/06/21 | 2021-09-14 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0117 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-INS-00-01711 | 2021-10-11 | 1400/07/19 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-DC-0001_D00 | [5 empty] | 1400-2290-227453 | 2021-10-09 | 1400/07/17 | 2021-10-12 | 1400/07/20 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-DC-0001_D00 | [9 empty] | D02 | IFA | T-0193 | 2021-10-30 | 1400/08/08 | [13 empty] | 1400-2294-281433 | 2021-11-19 | 1400/08/27 | 2021-11-28 | 1400/09/07 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-DC-0001_D01 | [9 empty] | D03 | AFD | T-0305 | 2021-12-07 | 1400/09/16 | [13 empty] | 1400-2294-320827 | 2021-12-17 | 1400/09/26 | 2021-12-18 | 1400/09/27 | AP
1 | 2 | 0 | 10 | 0 | 2 | 0 | 1.2.10.2 | Specification
1 | 2 | 0 | 10 | 0 | 2 | 1 | 1.2.10.2.1 | Specification For CCTV | BK-GNRAL-PEDCO-000-TE-SP-0001 | BK-GNRAL-PEDCO-000-TE-SP-0001 | [7 empty] | - | [43 empty] | Moved to IN | 2021-08-10 | 0 |  | D00 | IFC | T-0042 | 2021-08-10 | 1400/05/19 | 0 | 0 | 0 | BK-SUR-ENG-TEL-00-01364 | 2021-08-22 | 1400/05/31 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-191906 | 2021-09-09 | 1400/06/18 | 2021-09-14 | 1400/06/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0042 | 2021-08-10 | 1400/05/19 |  |  |  | BK-SUR-ENG-TEL-00-01364 | 2021-08-22 | 1400/05/31 | AP | [6 empty] | 1400-2294-191906 | 2021-09-09 | 1400/06/18 | 2021-09-14 | 1400/06/23 | CM
1 | 2 | 0 | 10 | 0 | 2 | 2 | 1.2.10.2.2 | Specification For PABX | BK-GNRAL-PEDCO-000-TE-SP-0002 | BK-GNRAL-PEDCO-000-TE-SP-0002 | BK | GNRAL | PEDCO | 000 | TE | SP | 0002 | F0Z-707229 | AFD | IFC | 2021-08-18 | 2021-09-12 | 2021-09-14 | 25 | 2 | 27 | IFA | 2021-10-09 | 2021-10-09 | 2021-10-12 | 0 | 3 | 3 | AFD | 2021-12-21 | 2021-12-17 | 2021-12-18 | -4 | 1 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-04 | 2021-12-07 |  | D02 | AFD | T-0305 | 2021-12-07 | 1400/09/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-320827 | 2021-12-17 | 1400/09/26 | 2021-12-18 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0027 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-TEL-00-01301 | 2021-08-10 | 1400/05/19 | CM-C2 | [6 empty] | 1400/2294/194252 | 2021-09-12 | 1400/06/21 | 2021-09-14 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0117 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-INS-00-01711 | 2021-10-11 | 1400/07/19 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-SP-0002_D00 | [5 empty] | 1400-2290-227453 | 2021-10-09 | 1400/07/17 | 2021-10-12 | 1400/07/20 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0002_D00 | [9 empty] | D02 | AFD | T-0305 | 2021-12-07 | 1400/09/16 | [13 empty] | 1400-2294-320827 | 2021-12-17 | 1400/09/26 | 2021-12-18 | 1400/09/27 | AP
1 | 2 | 0 | 10 | 0 | 2 | 3 | 1.2.10.2.3 | Specification For PAGA | BK-GNRAL-PEDCO-000-TE-SP-0003 | BK-GNRAL-PEDCO-000-TE-SP-0003 | BK | GNRAL | PEDCO | 000 | TE | SP | 0003 | F0Z-707230 | AFD | IFC | 2021-08-18 | 2021-09-12 | 2021-09-14 | 25 | 2 | 27 | IFA | 2021-10-05 | 2021-10-06 | 2021-10-10 | 1 | 4 | 5 | IFA | 2021-11-15 | 2021-12-28 | 2021-12-05 | 43 | -23 | 20 | IFA | 2022-01-30 | 2022-01-26 | 2022-01-31 | -4 | 5 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-04 | 0 |  | D03 | IFA | T-0468 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-SP-0003_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-383927 | 2022-01-26 | 1400/11/06 | 2022-01-31 | 1400/11/11 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0003_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0027 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-TEL-00-01301 | 2021-08-10 | 1400/05/19 | CM-C2 | [6 empty] | 1400/2294/194252 | 2021-09-12 | 1400/06/21 | 2021-09-14 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0112 | 2021-09-21 | 1400/06/30 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-SP-0003_D00 | [5 empty] | 1400-2290-223856 | 2021-10-06 | 1400/07/14 | 2021-10-10 | 1400/07/18 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0003_D00 | [9 empty] | D02 | IFA | T-0200 | 2021-11-01 | 1400/08/10 |  |  |  | BK-SUR-ENG-TEL-00-02390 | 2021-12-21 | 1400/09/30 | CM-C2 | [6 empty] | 1400-2290-294875 | 2021-12-28 | 1400/09/07 | 2021-12-05 | 1400/09/14 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0003_D01 | [9 empty] | D03 | IFA | T-0468 | 2022-01-16 | 1400/10/26 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-SP-0003_D02 | [5 empty] | 1400-2294-383927 | 2022-01-26 | 1400/11/06 | 2022-01-31 | 1400/11/11 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0003_D02
1 | 2 | 0 | 10 | 0 | 2 | 4 | 1.2.10.2.4 | Specification For Radio | BK-GNRAL-PEDCO-000-TE-SP-0004 | BK-GNRAL-PEDCO-000-TE-SP-0004 | BK | GNRAL | PEDCO | 000 | TE | SP | 0004 | F0Z-707231 | AFD | IFC | 2021-08-18 | 2021-09-14 | 2021-09-19 | 27 | 5 | 32 | IFA | 2021-10-16 | 2021-10-10 | 2021-12-29 | -6 | 80 | 74 | AFD | 2022-03-08 | 2022-03-06 | 2022-03-01 | -2 | -5 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-04 | 2022-02-22 |  | D02 | AFD | T-0626 | 2022-02-22 | 1400/12/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430786 | 2022-03-06 | 1400/12/15 | 2022-03-01 | 1400/12/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0031 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-TEL-00-01302 | 2021-08-10 | 1400/05/19 | CM-C2 | [6 empty] | 1400-2294-198551 | 2021-09-14 | 1400/06/23 | 2021-09-19 | 1400/06/28 | CM | [10 empty] | D01 | IFA | T-0128 | 2021-10-02 | 1400/07/10 |  |  |  | BK-SUR-ENG-TEL-00-02388 | 2021-12-21 | 1400/09/30 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-SP-0004_D00 | [5 empty] | 1400-2290-227505 | 2021-10-10 | 1400/07/18 | 2021-12-29 | 1400/10/08 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0004_D00 | [9 empty] | D02 | AFD | T-0626 | 2022-02-22 | 1400/12/03 | [13 empty] | 1400-2294-430786 | 2022-03-06 | 1400/12/15 | 2022-03-01 | 1400/12/10 | CM
1 | 2 | 0 | 10 | 0 | 2 | 5 | 1.2.10.2.5 | Specification For Telecommunication Tower | BK-GNRAL-PEDCO-000-TE-SP-0005 | BK-GNRAL-PEDCO-000-TE-SP-0005 | BK | GNRAL | PEDCO | 000 | TE | SP | 0005 | F0Z-707232 | AFD | IFC | 2021-08-18 | 2021-09-14 | 2021-09-19 | 27 | 5 | 32 | IFA | 2021-10-24 | 2021-11-13 | 2021-11-15 | 20 | 2 | 22 | IFA | 2022-03-09 | 2022-03-06 | 2022-03-01 | -3 | -5 | -8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-04 | 0 |  | D02 | IFA | T-0635 | 2022-02-23 | 1400/12/04 | 0 | 0 | 0 | BK-SUR-ENG-TEL-00-03219 | 2022-02-26 | 1400/12/07 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430784 | 2022-03-06 | 1400/11/15 | 2022-03-01 | 1400/11/10 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0031 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-TEL-00-01302 | 2021-08-10 | 1400/05/19 | CM-C2 | [6 empty] | 1400-2294-198551 | 2021-09-14 | 1400/06/23 | 2021-09-19 | 1400/06/28 | CM | [10 empty] | D01 | IFA | T-0142 | 2021-10-10 | 1400/07/18 |  |  |  | BK-SUR-ENG-TEL-00-02389 | 2021-12-21 | 1400/09/30 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-SP-0005-D00 | [5 empty] | 1400-2294-273260 | 2021-11-13 | 1400/08/22 | 2021-11-15 | 1400/08/24 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0005-D00 | [9 empty] | D02 | IFA | T-0635 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-TEL-00-03219 | 2022-02-26 | 1400/12/07 | AP | [6 empty] | 1400-2294-430784 | 2022-03-06 | 1400/11/15 | 2022-03-01 | 1400/11/10 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0005_D01
1 | 2 | 0 | 10 | 0 | 2 | 6 | 1.2.10.2.6 | Specification For Telecom. Cable | BK-GNRAL-PEDCO-000-TE-SP-0006 | BK-GNRAL-PEDCO-000-TE-SP-0006 | BK | GNRAL | PEDCO | 000 | TE | SP | 0006 | F0Z-707233 | AFD | IFC | 2021-08-23 | 2021-09-12 | 2021-09-14 | 20 | 2 | 22 | IFA | 2021-10-04 | 2021-10-06 | 2021-10-10 | 2 | 4 | 6 | IFA | 2021-11-13 | 2021-11-19 | 2021-11-28 | 6 | 9 | 15 | AFD | 2021-12-22 | 2021-12-17 | 2021-12-18 | -5 | 1 | -4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 2021-12-08 |  | D03 | AFD | T-0323 | 2021-12-08 | 1400/09/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-320823 | 2021-12-17 | 1400/09/26 | 2021-12-18 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0037 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-TEL-00-01363 | 2021-08-22 | 1400/05/31 | CM-C2 | [6 empty] | 1400/2294/194247 | 2021-09-12 | 1400/06/21 | 2021-09-14 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0107 | 2021-09-20 | 1400/06/29 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-SP-0006_D00 |  |  |  |  | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0006_D00 | 1400-2290-223858 | 2021-10-06 | 1400/07/14 | 2021-10-10 | 1400/07/18 | CM | [10 empty] | D02 | IFA | T-0193 | 2021-10-30 | 1400/08/08 | [13 empty] | 1400-2294-281433 | 2021-11-19 | 1400/08/27 | 2021-11-28 | 1400/09/07 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-TE-SP-0006_D01 | [9 empty] | D03 | AFD | T-0323 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-320823 | 2021-12-17 | 1400/09/26 | 2021-12-18 | 1400/09/27 | AP
1 | 2 | 0 | 10 | 0 | 3 | 0 | 1.2.10.3 | Drawing/Diagram
1 | 2 | 0 | 10 | 0 | 3 | 1 | 1.2.10.3.1 | Telecom Systems Legend and Symbols | BK-GNRAL-PEDCO-000-TE-DW-0001 | BK-GNRAL-PEDCO-000-TE-DW-0001 | BK | GNRAL | PEDCO | 000 | TE | DW | 0001 | F2T-707234 | AFC | IFC | 2021-08-15 | 2021-09-12 | 2022-04-19 | 28 | 219 | 247 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-01 | 0 |  | D00 | IFC | T-0025 | 2021-08-01 | 1400/05/10 | 0 | 0 | 0 | BK-SUR-ENG-TEL-00-01300 | 2021-08-10 | 1400/05/19 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-194346 | 2021-09-12 | 1400/06/21 | 2022-04-19 | 1401/01/30 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0025 | 2021-08-01 | 1400/05/10 |  |  |  | BK-SUR-ENG-TEL-00-01300 | 2021-08-10 | 1400/05/19 | AP | [6 empty] | 1400-2294-194346 | 2021-09-12 | 1400/06/21 | 2022-04-19 | 1401/01/30 | CM
1 | 2 | 0 | 10 | 0 | 3 | 2 | 1.2.10.3.2 | Telecom Typical Installation Details & Notes | BK-GNRAL-PEDCO-000-TE-DW-0002 | BK-GNRAL-PEDCO-000-TE-DW-0002 | BK | GNRAL | PEDCO | 000 | TE | DW | 0002 | F2T-707235 | IFI | IFI | 2021-08-15 | 2021-09-12 | 2022-04-19 | 28 | 219 | 247 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-01 | 2021-08-01 |  | D00 | IFI | T-0025 | 2021-08-01 | 1400/05/10 | 0 | 0 | 0 | BK-SUR-ENG-TEL-00-01300 | 2021-08-10 | 1400/05/19 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-194346 | 2021-09-12 | 1400/06/21 | 2022-04-19 | 1401/01/30 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0025 | 2021-08-01 | 1400/05/10 |  |  |  | BK-SUR-ENG-TEL-00-01300 | 2021-08-10 | 1400/05/19 | CM-C2 | [6 empty] | 1400-2294-194346 | 2021-09-12 | 1400/06/21 | 2022-04-19 | 1401/01/30 | CM
1 | 2 | 0 | 10 | 0 | 3 | 3 | 1.2.10.3.3 | CCTV Typical Installation Details & Notes | BK-GNRAL-PEDCO-000-TE-DW-0003 | BK-GNRAL-PEDCO-000-TE-DW-0003 | [7 empty] | - | [43 empty] | Moved to IN | 0 | 0 |  | D00 | IFI | T-0052 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-TEL-00-01360 | 2021-08-22 | 1400/05/31 | AP | 0 | BK-SUR-ENG-TEL-00-01488 | 2021-09-11 | 1400/06/20 | AP | 0 | 1400-2294-170637 | 2021-08-23 | 1400/06/01 | 2021-09-11 | 1400/06/20 | RJ | 0 | 1400-2294-191906 | 2021-09-09 | 1400/06/18 | 0 | 0 | CM | 0 | 0 |  | D00 | IFI | T-0052 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-TEL-00-01360 | 2021-08-22 | 1400/05/31 | AP |  | BK-SUR-ENG-TEL-00-01488 | 2021-09-11 | 1400/06/20 | AP |  | 1400-2294-170637 | 2021-08-23 | 1400/06/01 | 2021-09-11 | 1400/06/20 | RJ |  | 1400-2294-191906 | 2021-09-09 | 1400/06/18 |  |  | CM
1 | 2 | 0 | 11 | 0 | 0 | 0 | 1.2.11 | Architecture
1 | 2 | 0 | 11 | 0 | 1 | 0 | 1.2.11.1 | Basis/Criteria
1 | 2 | 0 | 11 | 0 | 1 | 1 | 1.2.11.1.1 | Architectural Design Criteria | BK-GNRAL-PEDCO-000-AR-DC-0001 | BK-GNRAL-PEDCO-000-AR-DC-0001 | BK | GNRAL | PEDCO | 000 | AR | DC | 0001 | F0Z-707236 | AFD | IFC | 44614 | 44605 | 44605 | -9 | 0 | -9 | IFA | 44724 | 0 | 0 | -44724 | 0 | -44724 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-08 | 0 |  | D01 | IFA | T-1020 | 2022-05-29 | 1401/03/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-AR-DC-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-AR-DC-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0566 | 2022-02-08 | 1400/11/19 |  |  |  | BK-SUR-ENG-ARC-00-03120 | 2022-02-19 | 1400/11/30 | CM-C2 | [6 empty] | 1400-2294-407460 | 2022-02-13 | 1400/11/24 | 2022-02-13 | 1400/11/24 | CM | [10 empty] | D01 | IFA | T-1020 | 2022-05-29 | 1401/03/08 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-AR-DC-0001_D00 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-AR-DC-0001_D00
1 | 2 | 0 | 11 | 0 | 2 | 0 | 1.2.11.2 | Specification
1 | 2 | 0 | 11 | 0 | 2 | 1 | 1.2.11.2.1 | Buildings General Specification | BK-GNRAL-PEDCO-000-AR-SP-0001 | BK-GNRAL-PEDCO-000-AR-SP-0001 | BK | GNRAL | PEDCO | 000 | AR | SP | 0001 | F0Z-707237 | AFD | IFC | 44671 | 44662 | 44663 | -9 | 1 | -8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-06 | 0 |  | D00 | IFC | T-0781 | 2022-04-06 | 1401/01/17 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-03874 | 2022-04-13 | 1401/01/24 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-16799 | 2022-04-11 | 1401/01/21 | 2022-04-12 | 1401/01/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0781 | 2022-04-06 | 1401/01/17 |  |  |  | BK-SUR-ENG-ARC-01-03874 | 2022-04-13 | 1401/01/24 | CM-C2 | [6 empty] | 1401-2294-16799 | 2022-04-11 | 1401/01/21 | 2022-04-12 | 1401/01/23 | CM
1 | 2 | 0 | 11 | 0 | 3 | 0 | 1.2.11.3 | Drawing/Diagram
1 | 2 | 0 | 11 | 0 | 3 | 1 | 1.2.11.3.1 | Standard Drawing for Architectural Details | BK-GNRAL-PEDCO-000-AR-DW-0001 | BK-GNRAL-PEDCO-000-AR-DW-0001 | BK | GNRAL | PEDCO | 000 | AR | DW | 0001 | F4B-707238 | AFC | IFC | 44562 | 44553 | 44562 | -9 | 9 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-18 | 0 |  | D00 | IFC | T-0360 | 2021-12-18 | 1400/09/27 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-02489 | 2022-01-01 | 1400/10/01 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-331872 | 2021-12-23 | 1400/10/02 | 2022-01-01 | 1400/10/11 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0360 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-ARC-00-02489 | 2022-01-01 | 1400/10/01 | CM-C2 | [6 empty] | 1400-2294-331872 | 2021-12-23 | 1400/10/02 | 2022-01-01 | 1400/10/11 | AP
1 | 2 | 0 | 12 | 0 | 0 | 0 | 1.2.12 | Civil
1 | 2 | 0 | 12 | 0 | 1 | 0 | 1.2.12.1 | Basis/Criteria
1 | 2 | 0 | 12 | 0 | 1 | 1 | 1.2.12.1.1 | Civil Design Criteria | BK-GNRAL-PEDCO-000-CV-DC-0001 | BK-GNRAL-PEDCO-000-CV-DC-0001 | BK | GNRAL | PEDCO | 000 | CV | DC | 0001 | F0Z-707239 | AFD | IFC | 2022-02-27 | 2022-02-16 | 2022-02-16 | -11 | 0 | -11 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D00 | IFC | T-0589 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-4130901 | 2022-02-16 | 1400/11/27 | 2022-02-16 | 1400/11/27 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0589 | 2022-02-13 | 1400/11/24 | [13 empty] | 1400-2294-4130901 | 2022-02-16 | 1400/11/27 | 2022-02-16 | 1400/11/27 | RJ
1 | 2 | 0 | 12 | 0 | 1 | 2 | 1.2.12.1.2 | Design Criteria for Sewerage & Drainage | BK-GNRAL-PEDCO-000-CV-DC-0002 | BK-GNRAL-PEDCO-000-CV-DC-0002 | BK | GNRAL | PEDCO | 000 | CV | DC | 0002 | F0Z-707240 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 12 | 0 | 2 | 0 | 1.2.12.2 | Specification
1 | 2 | 0 | 12 | 0 | 2 | 1 | 1.2.12.2.1 | Specification For Civil Works | BK-GNRAL-PEDCO-000-CV-SP-0001 | BK-GNRAL-PEDCO-000-CV-SP-0001 | BK | GNRAL | PEDCO | 000 | CV | SP | 0001 | F0Z-707241 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 12 | 0 | 2 | 2 | 1.2.12.2.2 | Specification For Road & Paving | BK-GNRAL-PEDCO-000-CV-SP-0002 | BK-GNRAL-PEDCO-000-CV-SP-0002 | BK | GNRAL | PEDCO | 000 | CV | SP | 0002 | F0Z-707242 | AFD | IFC | 2021-08-23 | 2021-08-22 | 2021-09-04 | -1 | 13 | 12 | IFA | 2022-03-19 | 2022-03-12 | 2022-03-14 | -7 | 2 | -5 | IFA | 2022-04-17 | 2022-04-07 | 2022-04-10 | -10 | 3 | -7 | AFD | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 2022-05-22 |  | D03 | AFD | T-0981 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0040 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-CIV-00-01343 | 2021-08-17 | 1400/05/26 | CM-C3 | [6 empty] | 1400-2294-167232 | 2021-08-22 | 1400/05/31 | 2021-09-04 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0671 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-CIV-00-03480 | 2022-03-13 | 1400/12/22 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0002_D01 | [5 empty] | 1400-2294-445103 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0002_D01 | [9 empty] | D02 | IFA | T-0769 | 2022-04-03 | 1401/01/14 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0002_D01 | [5 empty] | 1401-2294-13815 | 2022-04-07 | 1401/01/18 | 2022-04-10 | 1401/01/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0002_D01 | [9 empty] | D03 | AFD | T-0981 | 2022-05-22 | 1401/03/01
1 | 2 | 0 | 12 | 0 | 2 | 3 | 1.2.12.2.3 | Specification For Fence & Gate | BK-GNRAL-PEDCO-000-CV-SP-0003 | BK-GNRAL-PEDCO-000-CV-SP-0003 | BK | GNRAL | PEDCO | 000 | CV | SP | 0003 | F0Z-707243 | AFD | IFC | 2021-10-02 | 2021-09-20 | 2021-09-25 | -12 | 5 | -7 | IFA | 2021-11-02 | 2021-10-25 | 2021-11-22 | -8 | 28 | 20 | AFD | 2022-01-09 | 2021-12-29 | 2022-01-02 | -11 | 4 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-18 | 2021-12-26 |  | D02 | AFD | T-0382 | 2021-12-26 | 1400/10/05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-341743 | 2021-12-29 | 1400/10/08 | 2022-01-02 | 1400/10/12 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0098 | 2021-09-18 | 1400/06/27 |  |  |  | BK-SUR-ENG-CIV-00-01597 | 2021-09-25 | 1400/07/03 | CM-C2 | [6 empty] | 1400-2294-209491 | 2021-09-20 | 1400/06/31 | 2021-09-25 | 1400/07/03 | CM | [10 empty] | D01 | IFA | T-0172 | 2021-10-19 | 1400/07/27 |  |  |  | BK-SUR-ENG-CIV-00-01875 | 2021-10-31 | 1400/08/08 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0003-D00 | [5 empty] | 1400-2294-247798 | 2021-10-25 | 1400/08/03 | 2021-11-22 | 1400/09/01 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0003-D00 | [9 empty] | D02 | AFD | T-0382 | 2021-12-26 | 1400/10/05 | [13 empty] | 1400-2294-341743 | 2021-12-29 | 1400/10/08 | 2022-01-02 | 1400/10/12 | AP
1 | 2 | 0 | 12 | 0 | 2 | 4 | 1.2.12.2.4 | Specification For Earth Work | BK-GNRAL-PEDCO-000-CV-SP-0004 | BK-GNRAL-PEDCO-000-CV-SP-0004 | BK | GNRAL | PEDCO | 000 | CV | SP | 0004 | F0Z-707244 | AFD | IFC | 2021-08-23 | 2021-08-22 | 2021-09-04 | -1 | 13 | 12 | IFA | 2022-03-19 | 2022-03-12 | 2022-03-14 | -7 | 2 | -5 | IFA | 2022-04-26 | 2022-04-16 | 2022-04-18 | -10 | 2 | -8 | AFD | 2022-05-09 | 2022-04-30 | 2022-05-02 | -9 | 2 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 2022-04-25 |  | D03 | AFD | T-0860 | 2022-04-25 | 1401/02/06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-45391 | 2022-04-30 | 1401/02/`10 | 2022-05-02 | 1401/02/`12 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0040 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-CIV-00-01343 | 2021-08-17 | 1400/05/26 | CM-C3 | [6 empty] | 1400-2294-167232 | 2021-08-22 | 1400/05/31 | 2021-09-04 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0671 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-CIV-00-03480 | 2022-03-13 | 1400/12/22 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0004_D01 | [5 empty] | 1400-2294-445103 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0005_D01 | [9 empty] | D02 | IFA | T-0810 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-CIV-01-03977 | 2022-04-18 | 1401/01/29 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0004_D01 | [5 empty] | 1401-2294-23983 | 2022-04-16 | 1401/01/27 | 2022-04-18 | 1401/01/29 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0004_D01 | [9 empty] | D03 | AFD | T-0860 | 2022-04-25 | 1401/02/06 | [13 empty] | 1401-2294-45391 | 2022-04-30 | 1401/02/`10 | 2022-05-02 | 1401/02/`12 | AP
1 | 2 | 0 | 12 | 0 | 2 | 5 | 1.2.12.2.5 | Specification For Sewerage & Drainage | BK-GNRAL-PEDCO-000-CV-SP-0005 | BK-GNRAL-PEDCO-000-CV-SP-0005 | BK | GNRAL | PEDCO | 000 | CV | SP | 0005 | F0Z-707245 | AFD | IFC | 2021-08-23 | 2021-08-22 | 2021-09-04 | -1 | 13 | 12 | IFA | 2022-03-12 | 2022-03-02 | 2022-03-05 | -10 | 3 | -7 | AFD | 2022-03-26 | 2022-03-15 | 2022-03-25 | -11 | 10 | -1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-09 | 2022-03-12 |  | D02 | AFD | T-0717 | 2022-03-12 | 1400/12/21 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03512 | 2022-03-13 | 1400/12/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-449833 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0040 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-CIV-00-01343 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400-2294-167232 | 2021-08-22 | 1400/05/31 | 2021-09-04 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0643 | 2022-02-26 | 1400/12/07 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0005_D00 | [5 empty] | 1400-2294-431005 | 2022-03-02 | 1400/12/11 | 2022-03-05 | 1400/12/15 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0005_D00 | [9 empty] | D02 | AFD | T-0717 | 2022-03-12 | 1400/12/21 |  |  |  | BK-SUR-ENG-CIV-00-03512 | 2022-03-13 | 1400/12/22 | AP | [6 empty] | 1400-2294-449833 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | AP
1 | 2 | 0 | 12 | 0 | 2 | 6 | 1.2.12.2.6 | Specification For Geological & Geotechnical Survey | BK-GNRAL-PEDCO-000-CV-SP-0006 | BK-GNRAL-PEDCO-000-CV-SP-0006 | BK | GNRAL | PEDCO | 000 | CV | SP | 0006 | F0Z-707246 | AFD | IFC | 2022-04-09 | 2022-04-01 | 2022-04-06 | -8 | 5 | -3 | IFA | 2022-05-22 | 0 | 0 | -44703 | 0 | -44703 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-26 | 0 |  | D01 | IFA | T-0910 | 2022-05-08 | 1401/02/18 | T-0910 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-CIV-01-04381 | 2022-05-23 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0735 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-CIV-01-03740 | 2022-04-05 | 1401/01/16 | CM-C2 | [6 empty] | 1401-2294-7284 | 2022-04-01 | 1401/01/14 | 2022-04-06 | 1401/01/17 | CM | [10 empty] | D01 | IFA | T-0910 | 2022-05-08 | 1401/02/18 | T-0910 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-CIV-01-04381 | 2022-05-23 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-SP-0006_D00 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-SP-0006_D00
1 | 2 | 0 | 12 | 0 | 3 | 0 | 1.2.12.3 | Drawing/Diagram
1 | 2 | 0 | 12 | 0 | 3 | 1 | 1.2.12.3.1 | Standard Drawing For Civil Works | BK-GNRAL-PEDCO-000-CV-DW-0001 | BK-GNRAL-PEDCO-000-CV-DW-0001 | BK | GNRAL | PEDCO | 000 | CV | DW | 0001 | F4S-707247 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 12 | 0 | 3 | 2 | 1.2.12.3.2 | Standard Drawing For Slope Protection Details | BK-GNRAL-PEDCO-000-CV-DW-0002 | BK-GNRAL-PEDCO-000-CV-DW-0002 | BK | GNRAL | PEDCO | 000 | CV | DW | 0002 | F4S-707248 | IFI | IFI | 2021-09-05 | 2021-08-25 | 2021-09-04 | -11 | 10 | -1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2021-08-22 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | 1400/06/13 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 2021-09-04 | 1400/06/13 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | 1400/06/13 | CM-C3 | [6 empty] | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 2021-09-04 | 1400/06/13 | CM
1 | 2 | 0 | 12 | 0 | 3 | 3 | 1.2.12.3.3 | Standard Drawing For Roads | BK-GNRAL-PEDCO-000-CV-DW-0003 | BK-GNRAL-PEDCO-000-CV-DW-0003 | BK | GNRAL | PEDCO | 000 | CV | DW | 0003 | F4S-707249 | AFC | IFI | 2021-09-05 | 2021-08-25 | 2021-09-04 | -11 | 10 | -1 | IFA | 2022-01-23 | 2022-01-11 | 2022-01-15 | -12 | 4 | -8 | IFA | 2022-04-27 | 2022-04-19 | 2022-04-26 | -8 | 7 | -1 | AFC | 2022-06-04 | 0 | 0 | -44716 | 0 | -44716 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2022-05-21 |  | D03 | AFC | T-0976 | 2022-05-21 | 1401/02/31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0003_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | 1400/06/13 | CM-C3 | [6 empty] | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 2021-09-04 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0441 | 2022-01-09 | 1400/10/19 |  |  |  | BK-SUR-ENG-CIV-00-02684 | 2022-01-15 | 1400/10/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0003-D00 | [5 empty] | 1400-2294-360424 | 2022-01-11 | 1400/10/21 | 2022-01-15 | 1400/10/25 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0003-D00 | [9 empty] | D02 | IFA | T-0814 | 2022-04-13 | 1401/01/24 |  |  |  | BK-SUR-ENG-CIV-01-04064 | 2022-04-26 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0003_D01 | [5 empty] | 1401-2294-31389 | 2022-04-19 | 1401/01/30 | 2022-04-26 | 1401/02/06 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0003_D01 | [9 empty] | D03 | AFC | T-0976 | 2022-05-21 | 1401/02/31 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0003_D02
1 | 2 | 0 | 12 | 0 | 3 | 4 | 1.2.12.3.4 | Standard Drawing For Electrical Cable Trench | BK-GNRAL-PEDCO-000-CV-DW-0004 | BK-GNRAL-PEDCO-000-CV-DW-0004 | BK | GNRAL | PEDCO | 000 | CV | DW | 0004 | F4S-707250 | IFI | IFI | 2021-09-05 | 2021-08-25 | 2021-09-04 | -11 | 10 | -1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2021-08-22 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | 1400/06/13 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 2021-09-04 | 1400/06/13 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | 1400/06/13 | CM-C3 | [6 empty] | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 2021-09-04 | 1400/06/13 | CM
1 | 2 | 0 | 12 | 0 | 3 | 5 | 1.2.12.3.5 | Standard Drawing For Manholes | BK-GNRAL-PEDCO-000-CV-DW-0005 | BK-GNRAL-PEDCO-000-CV-DW-0005 | BK | GNRAL | PEDCO | 000 | CV | DW | 0005 | F4S-707251 | AFC | IFI | 2021-09-05 | 2021-08-25 | 2021-09-04 | -11 | 10 | -1 | IFA | 2022-01-25 | 2021-01-15 | 2022-01-16 | -375 | 366 | -9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 0 |  | D01 | IFA | T-0448 | 2022-01-11 | 1400/10/20 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-02699 | 2022-01-16 | 1400/10/26 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0005-D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-364648 | 2021-01-15 | 1400/10/25 | 2022-01-16 | 1400/10/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0005-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | 1400/06/13 | CM-C3 | [6 empty] | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 2021-09-04 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0448 | 2022-01-11 | 1400/10/20 |  |  |  | BK-SUR-ENG-CIV-00-02699 | 2022-01-16 | 1400/10/26 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0005-D00 | [5 empty] | 1400-2294-364648 | 2021-01-15 | 1400/10/25 | 2022-01-16 | 1400/10/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0005-D00
1 | 2 | 0 | 12 | 0 | 3 | 6 | 1.2.12.3.6 | Standard Drawing For Catch Basins | BK-GNRAL-PEDCO-000-CV-DW-0006 | BK-GNRAL-PEDCO-000-CV-DW-0006 | BK | GNRAL | PEDCO | 000 | CV | DW | 0006 | F4S-707252 | AFC | IFI | 2021-09-05 | 2021-08-25 | 2021-09-04 | -11 | 10 | -1 | IFA | 2022-01-25 | 2021-01-15 | 2022-01-16 | -375 | 366 | -9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 0 |  | D01 | IFA | T-0448 | 2022-01-11 | 1400/10/20 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-02699 | 2022-01-16 | 1400/10/26 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0006-D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-364648 | 2021-01-15 | 1400/10/25 | 2022-01-16 | 1400/10/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0006-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | 1400/06/13 | CM-C3 | [6 empty] | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 2021-09-04 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0448 | 2022-01-11 | 1400/10/20 |  |  |  | BK-SUR-ENG-CIV-00-02699 | 2022-01-16 | 1400/10/26 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0006-D00 | [5 empty] | 1400-2294-364648 | 2021-01-15 | 1400/10/25 | 2022-01-16 | 1400/10/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0006-D00
1 | 2 | 0 | 12 | 0 | 3 | 7 | 1.2.12.3.7 | Standard Drawing For Sewerage & Drainage Details | BK-GNRAL-PEDCO-000-CV-DW-0007 | BK-GNRAL-PEDCO-000-CV-DW-0007 | BK | GNRAL | PEDCO | 000 | CV | DW | 0007 | F4S-707253 | AFC | IFC | 2022-02-16 | 2022-02-08 | 2022-02-13 | -8 | 5 | -3 | IFA | 2022-05-29 | 2022-05-21 | 2022-05-29 | -8 | 8 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 0 |  | D01 | IFA | T-0948 | 2022-05-15 | 1401/02/25 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-04469 | 2022-05-29 | 1401/03/08 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0007_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-69915 | 2022-05-21 | 1401/02/31 | 2022-05-29 | 1401/03/08 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0547 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-CIV-00-02953 | 2022-02-06 | 1400/11/17 | CM-C2 | [6 empty] | 1400-2294-402785 | 2022-02-08 | 1400/11/19 | 2022-02-13 | 1400/11/24 | CM | [10 empty] | D01 | IFA | T-0948 | 2022-05-15 | 1401/02/25 |  |  |  | BK-SUR-ENG-CIV-01-04469 | 2022-05-29 | 1401/03/08 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0007_D00 | [5 empty] | 1401-2294-69915 | 2022-05-21 | 1401/02/31 | 2022-05-29 | 1401/03/08 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0007_D00
1 | 2 | 0 | 12 | 0 | 3 | 8 | 1.2.12.3.8 | Standard Drawing For Civil Underground Crossings | BK-GNRAL-PEDCO-000-CV-DW-0008 | BK-GNRAL-PEDCO-000-CV-DW-0008 | BK | GNRAL | PEDCO | 000 | CV | DW | 0008 | F4S-707254 | AFC | IFC | 2022-02-21 | 2022-02-13 | 2022-02-13 | -8 | 0 | -8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-07 | 0 |  | D00 | IFC | T-0560 | 2022-02-07 | 1400/11/18 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03076 | 2022-02-16 | 1400/11/27 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-407467 | 2022-02-13 | 1400/11/24 | 2022-02-13 | 1400/11/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0560 | 2022-02-07 | 1400/11/18 |  |  |  | BK-SUR-ENG-CIV-00-03076 | 2022-02-16 | 1400/11/27 | CM-C2 | [6 empty] | 1400-2294-407467 | 2022-02-13 | 1400/11/24 | 2022-02-13 | 1400/11/24 | CM
1 | 2 | 0 | 12 | 0 | 3 | 9 | 1.2.12.3.9 | Standard Drawing For Fence & Gate Details | BK-GNRAL-PEDCO-000-CV-DW-0009 | BK-GNRAL-PEDCO-000-CV-DW-0009 | BK | GNRAL | PEDCO | 000 | CV | DW | 0009 | F4S-707255 | AFC | IFC | 2021-10-02 | 2021-09-22 | 2021-09-25 | -10 | 3 | -7 | IFA | 2021-11-02 | 2021-10-25 | 2021-11-22 | -8 | 28 | 20 | IFA | 2022-02-06 | 2022-01-26 | 2022-01-29 | -11 | 3 | -8 | AFC | 2022-03-14 | 2022-03-19 | 2022-03-27 | 5 | 8 | 13 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-18 | 2022-02-28 |  | D03 | AFC | T-0655 | 2022-02-28 | 1400/12/09 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-03560 | 2022-03-14 | 1400/12/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0009_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-454970 | 2022-03-19 | 1400/12/28 | 2022-03-27 | 1401/01/07 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0099 | 2021-09-18 | 1400/06/27 |  |  |  | BK-SUR-ENG-CIV-00-01599 | 2021-09-25 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-209547 | 2021-09-22 | 1400/06/31 | 2021-09-25 | 1400/07/03 | CM | [10 empty] | D01 | IFA | T-0172 | 2021-10-19 | 1400/07/27 |  |  |  | BK-SUR-ENG-CIV-00-01875 | 2021-10-31 | 1400/08/08 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0009-D00 | [5 empty] | 1400-2294-247798 | 2021-10-25 | 1400/08/03 | 2021-11-22 | 1400/09/01 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0009-D00 | [9 empty] | D02 | IFA | T-0492 | 2022-01-23 | 1400/11/03 |  |  |  | BK-SUR-ENG-CIV-00-02844 | 2022-01-29 | 1400/11/09 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0009_D01 | [5 empty] | 1400-2294-383930 | 2022-01-26 | 1400/11/06 | 2022-01-29 | 1400/11/09 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0009_D01 | [9 empty] | D03 | AFC | T-0655 | 2022-02-28 | 1400/12/09 |  |  |  | BK-SUR-ENG-ARC-00-03560 | 2022-03-14 | 1400/12/23 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0009_D02 | [5 empty] | 1400-2294-454970 | 2022-03-19 | 1400/12/28 | 2022-03-27 | 1401/01/07 | AP
1 | 2 | 0 | 12 | 0 | 3 | 10 | 1.2.12.3.10 | Standard Drawing For Concrete Continues Weight | BK-GNRAL-PEDCO-000-CV-DW-0010 | BK-GNRAL-PEDCO-000-CV-DW-0010 | BK | GNRAL | PEDCO | 000 | CV | DW | 0010 | F4S-707256 | IFI | IFI | 2021-08-22 | 2021-08-14 | 0 | -8 | -44422 | -44430 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2021-08-08 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01345 | 2021-08-19 | 1400/05/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-164383 | 2021-08-14 | 1400/05/23 | 0 | 0 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-CIV-00-01345 | 2021-08-19 | 1400/05/28 | CM-C3 | [6 empty] | 1400-2294-164383 | 2021-08-14 | 1400/05/23 |  |  | RJ
1 | 2 | 0 | 12 | 0 | 3 | 11 | 1.2.12.3.11 | Standard Drawing For Major Floodway Crossing | BK-GNRAL-PEDCO-000-CV-DW-0012 | BK-GNRAL-PEDCO-000-CV-DW-0012 | BK | GNRAL | PEDCO | 000 | CV | DW | 0012 | F4S-707257 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 12 | 0 | 3 | 12 | 1.2.12.3.12 | Standard Drawing For Culvert & Details | BK-GNRAL-PEDCO-000-CV-DW-0014 | BK-GNRAL-PEDCO-000-CV-DW-0014 | BK | GNRAL | PEDCO | 000 | CV | DW | 0014 | F4S-707261 | AFC | IFC | 2021-10-09 | 2021-10-02 | 2021-10-09 | -7 | 7 | 0 | IFA | 2021-11-20 | 2021-11-08 | 0 | -12 | -44508 | -44520 | AFC | 2021-11-29 | 2021-11-18 | 2021-11-21 | -11 | 3 | -8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-25 | 2021-11-15 |  | D02 | AFC | T-0244 | 2021-11-15 | 1400/08/24 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-02054 | 2021-11-21 | 1400/08/30 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0014-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-281432 | 2021-11-18 | 1400/08/27 | 2021-11-21 | 1400/08/30 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0014-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0119 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-CIV-00-01677 | 2021-10-04 | 1400/07/12 | CM-C2 | [6 empty] | 1400-2294-219939 | 2021-10-02 | 1400/07/10 | 2021-10-09 | 1400/07/17 | CM | [10 empty] | D01 | IFA | T-0204 | 2021-11-06 | 1400/08/015 |  |  |  | BK-SUR-ENG-CIV-00-01920 | 2021-11-06 | 1400/08/15 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0014-D00 | [5 empty] | 1400-2294-267473 | 2021-11-08 | 1400/08/17 |  |  | AP | NISOCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0014-D00 | [9 empty] | D02 | AFC | T-0244 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-CIV-00-02054 | 2021-11-21 | 1400/08/30 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0014-D01 | [5 empty] | 1400-2294-281432 | 2021-11-18 | 1400/08/27 | 2021-11-21 | 1400/08/30 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0014-D01
1 | 2 | 0 | 12 | 0 | 3 | 13 | 1.2.12.3.13 | Standard Drawing For Valve Box | BK-GNRAL-PEDCO-000-CV-DW-0016 | BK-GNRAL-PEDCO-000-CV-DW-0016 | BK | GNRAL | PEDCO | 000 | CV | DW | 0016 | F4S-707258 | IFI | IFI | 2022-01-26 | 2022-01-17 | 2022-01-19 | -9 | 2 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-12 | 2022-01-12 |  | D00 | IFI | T-0455 | 2022-01-12 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-02714 | 2022-01-17 | 1400/10/26 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-368537 | 2022-01-17 | 1400/10/27 | 2022-01-19 | 1400/10/29 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0455 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-CIV-00-02714 | 2022-01-17 | 1400/10/26 | CM-C2 | [6 empty] | 1400-2294-368537 | 2022-01-17 | 1400/10/27 | 2022-01-19 | 1400/10/29 | CM
1 | 2 | 0 | 12 | 0 | 3 | 14 | 1.2.12.3.14 | Standard Drawing For Fire Hydrant PAD | BK-GNRAL-PEDCO-000-CV-DW-0018 | BK-GNRAL-PEDCO-000-CV-DW-0018 | BK | GNRAL | PEDCO | 000 | CV | DW | 0018 | F4S-707259 | AFC | IFC | 2022-03-27 | 2022-03-16 | 2022-03-25 | -11 | 9 | -2 | IFA | 2022-05-14 | 2022-05-08 | 2022-05-11 | -6 | 3 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-13 | 0 |  | D01 | IFA | T-0874 | 2022-04-30 | 1401/02/10 | T-0874 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-CIV-01-04277 | 2022-05-15 | 1401/02/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0018-D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52735 | 2022-05-08 | 1401/02/18 | 2022-05-11 | 1401/02/21 | RJ | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0018_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0725 | 2022-03-13 | 1400/12/22 |  |  |  | BK-SUR-ENG-CIV-00-03623 | 2022-03-16 | 1400/12/25 | CM-C2 | [6 empty] | 1400-2294-452344 | 2022-03-16 | 1400/12/25 | 2022-03-25 | 1401/01/08 | CM | [10 empty] | D01 | IFA | T-0874 | 2022-04-30 | 1401/02/10 | T-0874 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-CIV-01-04277 | 2022-05-15 | 1401/02/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0018-D00 | [5 empty] | 1401-2294-52735 | 2022-05-08 | 1401/02/18 | 2022-05-11 | 1401/02/21 | RJ | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0018_D00
1 | 2 | 0 | 12 | 0 | 3 | 15 | 1.2.12.3.15 | Standard Drawing For Cable Pull Pit | BK-GNRAL-PEDCO-000-CV-DW-0020 | BK-GNRAL-PEDCO-000-CV-DW-0020 | BK | GNRAL | PEDCO | 000 | CV | DW | 0020 | F4S-707260 | AFC | IFC | 2022-04-25 | 2022-04-13 | 2022-04-17 | -12 | 4 | -8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-11 | 0 |  | D00 | IFC | T-0803 | 2022-04-11 | 1401/01/22 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-03944 | 2022-04-17 | 1401/01/28 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-22847 | 2022-04-13 | 1401/01/24 | 2022-04-17 | 1401/01/28 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0803 | 2022-04-11 | 1401/01/22 |  |  |  | BK-SUR-ENG-CIV-01-03944 | 2022-04-17 | 1401/01/28 | CM-C2 | [6 empty] | 1401-2294-22847 | 2022-04-13 | 1401/01/24 | 2022-04-17 | 1401/01/28 | AP
1 | 2 | 0 | 12 | 0 | 3 | 16 | 1.2.12.3.16 | Standard Drawing For Pavings | BK-GNRAL-PEDCO-000-CV-DW-0035 | BK-GNRAL-PEDCO-000-CV-DW-0035 | BK | GNRAL | PEDCO | 000 | CV | DW | 0035 | F4S-707262 | AFC | IFC | 2022-01-22 | 2022-01-11 | 2022-01-15 | -11 | 4 | -7 | IFA | 2022-05-03 | 0 | 0 | -44684 | 0 | -44684 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-08 | 0 |  | D01 | IFA | T-0845 | 2022-04-19 | 1401/01/30 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-04051 | 2022-04-25 | 1401/02/05 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0035_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0035_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0439 | 2022-01-08 | 1400/10/18 |  |  |  | BK-SUR-ENG-CIV-00-02716 | 2022-01-17 | 1400/10/27 | CM-C3 | [6 empty] | 1400-2294-359208 | 2022-01-11 | 1400/10/21 | 2022-01-15 | 1400/10/25 | CM | [10 empty] | D01 | IFA | T-0845 | 2022-04-19 | 1401/01/30 |  |  |  | BK-SUR-ENG-CIV-01-04051 | 2022-04-25 | 1401/02/05 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0035_D00 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0035_D00
1 | 2 | 0 | 12 | 0 | 3 | 17 | 1.2.12.3.17 | Standard Drawing For Earth Pit | BK-GNRAL-PEDCO-000-CV-DW-0037 | BK-GNRAL-PEDCO-000-CV-DW-0037 | BK | GNRAL | PEDCO | 000 | CV | DW | 0037 | F4S-707263 | AFC | IFC | 2022-02-27 | 2022-02-19 | 2022-02-20 | -8 | 1 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-13 | 0 |  | D00 | IFC | T-0592 | 2022-02-13 | 1400/11/23 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03115 | 2022-02-19 | 1400/11/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-413792 | 2022-02-19 | 1400/11/30 | 2022-02-20 | 1400/12/01 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0592 | 2022-02-13 | 1400/11/23 |  |  |  | BK-SUR-ENG-CIV-00-03115 | 2022-02-19 | 1400/11/30 | CM-C2 | [6 empty] | 1400-2294-413792 | 2022-02-19 | 1400/11/30 | 2022-02-20 | 1400/12/01 | CM
1 | 2 | 0 | 12 | 0 | 3 | 18 | 1.2.12.3.18 | Standard Detail For Pipe Bedding | BK-GNRAL-PEDCO-000-CV-DW-0039 | BK-GNRAL-PEDCO-000-CV-DW-0039 | BK | GNRAL | PEDCO | 000 | CV | DW | 0039 | F4S-707264 | IFI | IFI | 2021-09-05 | 2021-08-25 | 2021-09-04 | -11 | 10 | -1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2021-08-22 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | 1400/06/13 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 2021-09-04 | 1400/06/13 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0059 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | 1400/06/13 | CM-C3 | [6 empty] | 1400-2294-173204 | 2021-08-25 | 1400/06/03 | 2021-09-04 | 1400/06/13 | CM
1 | 2 | 0 | 12 | 0 | 3 | 19 | 1.2.12.3.19 | Standard Details of Miscellaneous Items | BK-GNRAL-PEDCO-000-CV-DW-0040 | BK-GNRAL-PEDCO-000-CV-DW-0040 | BK | GNRAL | PEDCO | 000 | CV | DW | 0040 | F4S-707265 | AFC | IFC | 2022-03-20 | 2022-03-10 | 2022-03-12 | -10 | 2 | -8 | AFC | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-06 | 2022-05-22 |  | D01 | AFC | T-0981 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0040_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0679 | 2022-03-06 | 1400/12/15 |  |  |  | BK-SUR-ENG-CIV-00-03448 | 2022-03-12 | 1400/12/21 | CM-C2 | [6 empty] | 1400-2294-443244 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | AP | [10 empty] | D01 | AFC | T-0981 | 2022-05-22 | 1401/03/01 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0040_D00
1 | 2 | 0 | 12 | 0 | 3 | 20 | 1.2.12.3.20 | Typical Drawing For A/G Pipeline Road Crossing | BK-GNRAL-PEDCO-000-CV-DW-0025 | BK-GNRAL-PEDCO-000-CV-DW-0025 | [7 empty] | - | [43 empty] | Deleted | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01345 | 2021-08-19 | 1400/05/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-164383 | 2021-08-14 | 1400/05/23 | 0 | 0 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-CIV-00-01345 | 2021-08-19 | 1400/05/28 | CM-C3 | [6 empty] | 1400-2294-164383 | 2021-08-14 | 1400/05/23 |  |  | RJ
1 | 2 | 0 | 12 | 0 | 3 | 21 | 1.2.12.3.21 | Pipeline Typical Drawing For Irish Crossing | BK-GNRAL-PEDCO-000-CV-DW-0027 | BK-GNRAL-PEDCO-000-CV-DW-0027 | [7 empty] | - | [43 empty] | Deleted | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01345 | 2021-08-19 | 1400/05/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-164383 | 2021-08-14 | 1400/05/23 | 0 | 0 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-CIV-00-01345 | 2021-08-19 | 1400/05/28 | CM-C3 | [6 empty] | 1400-2294-164383 | 2021-08-14 | 1400/05/23 |  |  | RJ
1 | 2 | 0 | 12 | 0 | 3 | 22 | 1.2.12.3.22 | Pipeline Typical Drawing For Water - Way Crossing | BK-GNRAL-PEDCO-000-CV-DW-0028 | BK-GNRAL-PEDCO-000-CV-DW-0028 | [7 empty] | - | [43 empty] | Deleted | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01345 | 2021-08-19 | 1400/05/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-164383 | 2021-08-14 | 1400/05/23 | 0 | 0 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-CIV-00-01345 | 2021-08-19 | 1400/05/28 | CM-C3 | [6 empty] | 1400-2294-164383 | 2021-08-14 | 1400/05/23 |  |  | RJ
1 | 2 | 0 | 12 | 0 | 3 | 23 | 1.2.12.3.23 | Pipeline Typical Drawing For Pig Signaller Concrete Pit | BK-GNRAL-PEDCO-000-CV-DW-0029 | BK-GNRAL-PEDCO-000-CV-DW-0029 | [7 empty] | - | [43 empty] | Deleted | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01345 | 2021-08-19 | 1400/05/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-164383 | 2021-08-14 | 1400/05/23 | 0 | 0 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-CIV-00-01345 | 2021-08-19 | 1400/05/28 | CM-C3 | [6 empty] | 1400-2294-164383 | 2021-08-14 | 1400/05/23 |  |  | RJ
1 | 2 | 0 | 12 | 0 | 3 | 24 | 1.2.12.3.24 | Pipeline Typical Drawing For H-Pipe Support | BK-GNRAL-PEDCO-000-CV-DW-0030 | BK-GNRAL-PEDCO-000-CV-DW-0030 | [7 empty] | - | [43 empty] | Deleted | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01345 | 2021-08-19 | 1400/05/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-164383 | 2021-08-14 | 1400/05/23 | 0 | 0 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-CIV-00-01345 | 2021-08-19 | 1400/05/28 | CM-C3 | [6 empty] | 1400-2294-164383 | 2021-08-14 | 1400/05/23 |  |  | RJ
1 | 2 | 0 | 12 | 0 | 3 | 25 | 1.2.12.3.25 | Pipeline Typical Drawing For Vent Valve Pre-cast Concrete Box | BK-GNRAL-PEDCO-000-CV-DW-0031 | BK-GNRAL-PEDCO-000-CV-DW-0031 | [7 empty] | - | [43 empty] | Deleted | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01345 | 2021-08-19 | 1400/05/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-164383 | 2021-08-14 | 1400/05/23 | 0 | 0 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0035 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-CIV-00-01345 | 2021-08-19 | 1400/05/28 | CM-C3 | [6 empty] | 1400-2294-164383 | 2021-08-14 | 1400/05/23 |  |  | RJ
1 | 2 | 0 | 12 | 0 | 3 | 26 | 1.2.12.3.26 | Standard Detail curbed Stone Bounded Area | BK-GNRAL-PEDCO-000-CV-DW-0038 | BK-GNRAL-PEDCO-000-CV-DW-0038 | [7 empty] | - | [43 empty] | Deleted | 0 | 0 |  | D00 | IFI | T-0061 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-01408 | 2021-08-25 | 1400/06/03 | C4-RJ |  | 0 | 0 | 0 | 0 | 0 | 1400-2294-170684 | 2021-08-24 | 1400/06/02 | 2021-09-04 | 1400/06/13 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0061 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-CIV-00-01408 | 2021-08-25 | 1400/06/03 | C4-RJ | RE: BK-SUR-ENG-CIV-00-01408 | [5 empty] | 1400-2294-170684 | 2021-08-24 | 1400/06/02 | 2021-09-04 | 1400/06/13 | RJ
1 | 2 | 0 | 13 | 0 | 0 | 0 | 1.2.13 | Structure
1 | 2 | 0 | 13 | 0 | 1 | 0 | 1.2.13.1 | Basis/Criteria
1 | 2 | 0 | 13 | 0 | 1 | 1 | 1.2.13.1.1 | Design Criteria For Concrete Works | BK-GNRAL-PEDCO-000-ST-DC-0001 | BK-GNRAL-PEDCO-000-ST-DC-0001 | BK | GNRAL | PEDCO | 000 | ST | DC | 0001 | F0Z-707266 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 13 | 0 | 2 | 0 | 1.2.13.2 | Specification
1 | 2 | 0 | 13 | 0 | 2 | 1 | 1.2.13.2.1 | Specification For Concrete Work | BK-GNRAL-PEDCO-000-ST-SP-0001 | BK-GNRAL-PEDCO-000-ST-SP-0001 | BK | GNRAL | PEDCO | 000 | ST | SP | 0001 | F0Z-707267 | AFD | IFC | 2021-08-28 | 2021-08-22 | 2021-09-04 | -6 | 13 | 7 | IFA | 2021-11-17 | 2021-11-09 | 2021-11-14 | -8 | 5 | -3 | IFA | 2022-05-11 | 2022-05-08 | 2022-05-11 | -3 | 3 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-14 | 0 |  | D02 | IFA | T-0870 | 2022-04-27 | 1401/02/07 | T-0870 | 2022-04-27 | 1401/02/07 | BK-SUR-ENG-STR-01-04139 | 2022-05-07 | 1401/02/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52736 | 2022-05-08 | 1401/02/18 | 2022-05-11 | 1401/02/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0044 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-CIV-00-01346 | 2021-08-20 | 1400/05/29 | C4-RJ | [6 empty] | 1400/2294/167414 | 2021-08-22 | 1400/05/31 | 2021-09-04 | 1400/06/13 | CM | [8 empty] | Binak Codes and standards proposal |  | D01 | IFA | T-0209 | 2021-11-03 | 1400/08/12 |  |  |  | BK-SUR-ENG-STR-00-01965 | 2021-11-10 | 1400/08/19 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0001-D00 | [5 empty] | 1400-2294-269294 | 2021-11-09 | 1400/08/18 | 2021-11-14 | 1400/08/23 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0001-D00 | [9 empty] | D02 | IFA | T-0870 | 2022-04-27 | 1401/02/07 | T-0870 | 2022-04-27 | 1401/02/07 | BK-SUR-ENG-STR-01-04139 | 2022-05-07 | 1401/02/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0001_D01 | [5 empty] | 1401-2294-52736 | 2022-05-08 | 1401/02/18 | 2022-05-11 | 1401/02/21 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0001_D01
1 | 2 | 0 | 13 | 0 | 2 | 2 | 1.2.13.2.2 | Specification For Storage Tank Foundation | BK-GNRAL-PEDCO-000-ST-SP-0002 | BK-GNRAL-PEDCO-000-ST-SP-0002 | BK | GNRAL | PEDCO | 000 | ST | SP | 0002 | F0Z-707268 | AFD | IFC | 2021-12-07 | 2021-12-05 | 2021-12-06 | -2 | 1 | -1 | IFA | 2022-02-21 | 2022-02-19 | 2022-02-12 | -2 | -7 | -9 | AFD | 2022-03-23 | 2022-03-16 | 2022-03-25 | -7 | 9 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-23 | 2022-03-09 |  | D02 | AFD | T-0711 | 2022-03-09 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-03590 | 2022-03-15 | 1400/12/24 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-452371 | 2022-03-16 | 1400/12/25 | 2022-03-25 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0268 | 2021-11-23 | 1400/09/02 |  |  |  | BK-SUR-ENG-STR-00-02214 | 2021-12-06 | 1400/09/15 | CM-C3 | [6 empty] | 1400-2294-304921 | 2021-12-05 | 1400/09/14 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0557 | 2022-02-07 | 1400/11/18 |  |  |  | BK-SUR-ENG-STR-00-03111 | 2022-02-19 | 1400/11/30 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0002_D00 | [5 empty] | 1400-2294-406574 | 2022-02-19 | 1400/11/30 | 2022-02-12 | 1400/11/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0002_D00 | [9 empty] | D02 | AFD | T-0711 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-STR-00-03590 | 2022-03-15 | 1400/12/24 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0002_D01 | [5 empty] | 1400-2294-452371 | 2022-03-16 | 1400/12/25 | 2022-03-25 | 1401/01/08 | AP
1 | 2 | 0 | 13 | 0 | 2 | 3 | 1.2.13.2.3 | Specification for Fabrication of Steel Structures | BK-GNRAL-PEDCO-000-ST-SP-0003 | BK-GNRAL-PEDCO-000-ST-SP-0003 | BK | GNRAL | PEDCO | 000 | ST | SP | 0003 | F0Z-707269 | AFD | IFC | 2022-02-07 | 2022-01-27 | 2022-01-30 | -11 | 3 | -8 | IFA | 2022-02-27 | 2022-02-09 | 2022-02-09 | -18 | 0 | -18 | AFD | 2022-03-14 | 2022-03-12 | 2022-03-14 | -2 | 2 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-24 | 2022-02-28 |  | D02 | AFD | T-0656 | 2022-02-28 | 1400/12/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445229 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0500 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-STR-00-02867 | 2022-01-30 | 1400/11/10 | CM-C2 | [6 empty] | 1400-2294-384196 | 2022-01-27 | 1400/11/07 | 2022-01-30 | 1400/11/10 | CM | [10 empty] | D01 | IFA | T-0593 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-STR-00-03206 | 2022-02-23 | 1400/12/04 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0003_D00 | [5 empty] | 1400-2294-413120 | 2022-02-09 | 1400/11/20 | 2022-02-09 | 1400/11/20 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0003_D00 | [9 empty] | D02 | AFD | T-0656 | 2022-02-28 | 1400/12/09 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0003_D01 | [5 empty] | 1400-2294-445229 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | AP
1 | 2 | 0 | 13 | 0 | 2 | 4 | 1.2.13.2.4 | Specification For Grouting | BK-GNRAL-PEDCO-000-ST-SP-0004 | BK-GNRAL-PEDCO-000-ST-SP-0004 | BK | GNRAL | PEDCO | 000 | ST | SP | 0004 | F0Z-707270 | AFD | IFC | 2021-08-28 | 2021-08-22 | 2021-09-04 | -6 | 13 | 7 | IFA | 2022-01-08 | 2021-12-27 | 2022-01-02 | -12 | 6 | -6 | AFD | 2022-02-01 | 2022-01-26 | 2022-01-29 | -6 | 3 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-14 | 2022-01-18 |  | D02 | AFD | T-0475 | 2022-01-18 | 1400/10/28 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-02762 | 2022-01-22 | 1400/11/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0004_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-383290 | 2022-01-26 | 1400/11/06 | 2022-01-29 | 1400/11/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0050 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-CIV-00-01373 | 2021-08-22 | 1400/05/31 | CM-C2 | [6 empty] | 1400/2294/168853 | 2021-08-22 | 1400/05/31 | 2021-09-04 | 1400/06/13 | CM | [10 empty] | D01 | IFA | T-0376 | 2021-12-25 | 1400/10/04 |  |  |  | BK-SUR-ENG-STR-00-02516 | 2022-01-02 | 1400/10/12 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0004_D00 | [5 empty] | 1400-2294-336451 | 2021-12-27 | 1400/10/06 | 2022-01-02 | 1400/10/12 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0004_D00 | [9 empty] | D02 | AFD | T-0475 | 2022-01-18 | 1400/10/28 |  |  |  | BK-SUR-ENG-STR-00-02762 | 2022-01-22 | 1400/11/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0004_D01 | [5 empty] | 1400-2294-383290 | 2022-01-26 | 1400/11/06 | 2022-01-29 | 1400/11/09 | AP
1 | 2 | 0 | 13 | 0 | 2 | 5 | 1.2.13.2.5 | Specification for Erection of Steel Structures | BK-GNRAL-PEDCO-000-ST-SP-0005 | BK-GNRAL-PEDCO-000-ST-SP-0005 | BK | GNRAL | PEDCO | 000 | ST | SP | 0005 | F0Z-707271 | AFD | IFC | 2022-02-07 | 2022-01-27 | 2022-02-06 | -11 | 10 | -1 | IFA | 2022-02-28 | 2022-02-16 | 2022-02-16 | -12 | 0 | -12 | AFD | 2022-03-14 | 2022-03-13 | 2022-03-26 | -1 | 13 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-24 | 2022-02-28 |  | D02 | AFD | T-0657 | 2022-02-28 | 1400/12/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0005_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-446504 | 2022-03-13 | 1400/12/22 | 2022-03-26 | 1401/01/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0504 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-STR-00-02947 | 2022-02-06 | 1400/11/17 | CM-C2 | [6 empty] | 1400-2294-384198 | 2022-01-27 | 1400/11/07 | 2022-02-06 | 1400/11/17 | CM | [10 empty] | D01 | IFA | T-0595 | 2022-02-14 | 1400/11/25 |  |  |  | BK-SUR-ENG-STR-00-03207 | 2022-02-23 | 1400/12/04 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0005_D00 | [5 empty] | 1400-2294-413132 | 2022-02-16 | 1400/11/27 | 2022-02-16 | 1400/11/27 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0005_D00 | [9 empty] | D02 | AFD | T-0657 | 2022-02-28 | 1400/12/09 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0005_D01 | [5 empty] | 1400-2294-446504 | 2022-03-13 | 1400/12/22 | 2022-03-26 | 1401/01/09 | AP
1 | 2 | 0 | 13 | 0 | 2 | 6 | 1.2.13.2.6 | Specification for Fireproofing | BK-GNRAL-PEDCO-000-ST-SP-0006 | BK-GNRAL-PEDCO-000-ST-SP-0006 | BK | GNRAL | PEDCO | 000 | ST | SP | 0006 | F0Z-707272 | AFD | IFC | 2021-10-02 | 2021-09-22 | 2021-09-25 | -10 | 3 | -7 | IFA | 2021-10-25 | 2021-10-16 | 2021-10-18 | -9 | 2 | -7 | IFA | 2021-12-29 | 2021-12-20 | 2021-12-22 | -9 | 2 | -7 | AFD | 2022-01-09 | 2021-12-29 | 2022-01-02 | -11 | 4 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-18 | 2021-12-26 |  | D03 | AFD | T-0383 | 2021-12-26 | 1400/10/05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-341664 | 2021-12-29 | 1400/10/08 | 2022-01-02 | 1400/10/12 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0096 | 2021-09-18 | 1400/06/27 |  |  |  | BK-SUR-ENG-STR-00-01590 | 2021-09-25 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-209486 | 2021-09-22 | 1400/06/31 | 2021-09-25 | 1400/07/03 | CM | [10 empty] | D01 | IFA | T-0152 | 2021-10-11 | 1400/07/15 |  |  |  | BK-SUR-ENG-STR-00-01767 | 2021-10-18 | 1400/07/26 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0006_D00 | [5 empty] | 1400-2294-236248 | 2021-10-16 | 1400/07/24 | 2021-10-18 | 1400/07/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0006_D00 | [9 empty] | D02 | IFA | T-0353 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-STR-00-02407 | 2021-12-22 | 1400/10/01 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-SP-0006_D01 | [5 empty] | 1400-2294-327398 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-SP-0006_D01 | [9 empty] | D03 | AFD | T-0383 | 2021-12-26 | 1400/10/05 | [13 empty] | 1400-2294-341664 | 2021-12-29 | 1400/10/08 | 2022-01-02 | 1400/10/12 | AP
1 | 2 | 0 | 13 | 0 | 2 | 7 | 1.2.13.2.7 | Specification for Design of Blast Resistant Buildings | BK-GNRAL-PEDCO-000-ST-SP-0007 | BK-GNRAL-PEDCO-000-ST-SP-0007 | BK | GNRAL | PEDCO | 000 | ST | SP | 0007 | F0Z-707273 | AFD | IFC | 2021-12-26 | 2021-12-16 | 2021-12-18 | -10 | 2 | -8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-12 | 0 |  | D00 | IFC | T-0327 | 2021-12-12 | 1400/09/21 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-02288 | 2021-12-15 | 1400/09/24 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-320801 | 2021-12-16 | 1400/09/26 | 2021-12-18 | 1400/09/27 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0327 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-STR-00-02288 | 2021-12-15 | 1400/09/24 | C4-RJ | [6 empty] | 1400-2294-320801 | 2021-12-16 | 1400/09/26 | 2021-12-18 | 1400/09/27 | CM
1 | 2 | 0 | 13 | 0 | 2 | 8 | 1.2.13.2.8 | Specification For Steel Structural Works | BK-GNRAL-PEDCO-000-ST-SP-0008 | BK-GNRAL-PEDCO-000-ST-SP-0008 | BK | GNRAL | PEDCO | 000 | ST | SP | 0008 | F0Z-707274 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 13 | 0 | 3 | 0 | 1.2.13.3 | Drawing/Diagram
1 | 2 | 0 | 13 | 0 | 3 | 1 | 1.2.13.3.1 | Standard Drawing For Fire Proofing | BK-GNRAL-PEDCO-000-ST-DW-0001 | BK-GNRAL-PEDCO-000-ST-DW-0001 | BK | GNRAL | PEDCO | 000 | ST | DW | 0001 | F4M-707275 | AFC | IFI | 2021-08-22 | 2021-08-15 | 2021-08-23 | -7 | 8 | 1 | IFA | 2021-10-02 | 2021-09-23 | 2021-09-28 | -9 | 5 | -4 | IFA | 2021-10-25 | 2021-10-16 | 2021-10-18 | -9 | 2 | -7 | IFA | 2022-01-08 | 2021-12-27 | 2022-01-08 | -12 | 12 | 0 | AFC | 2022-02-01 | 2022-01-20 | 2022-01-22 | -12 | 2 | -10 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-08 | 2022-01-18 |  | D04 | AFC | T-0478 | 2022-01-18 | 1400/10/28 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-02763 | 2022-01-22 | 1400/11/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-372847 | 2022-01-20 | 1400/10/30 | 2022-01-22 | 1400/11/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0033 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-STR-00-01317 | 2021-08-14 | 1400/05/23 | CM-C3 | [6 empty] | 1400/2294/166216 | 2021-08-15 | 1400/05/24 | 2021-08-23 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0100 | 2021-09-18 | 1400/06/27 |  |  |  | BK-SUR-ENG-STR-00-01606 | 2021-09-26 | 1400/07/04 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0001-D00 | [5 empty] | 1400-2294-210029 | 2021-09-23 | 1400/07/01 | 2021-09-28 | 1400/07/06 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0001-D00 | [9 empty] | D02 | IFA | T-0148 | 2021-10-11 | 1400/07/19 |  |  |  | BK-SUR-ENG-STR-00-01764 | 2021-10-18 | 1400/07/26 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0001-D01 | [5 empty] | 1400-2294-236278 | 2021-10-16 | 1400/07/24 | 2021-10-18 | 1400/07/26 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0001-D01 | [9 empty] | D03 | IFA | T-0378 | 2021-12-25 | 1400/10/04 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0001_D02 | [5 empty] | 1400-2294-338026 | 2021-12-27 | 1400/10/06 | 2022-01-08 | 1400/10/18 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0001_D02 | 1400-2294-338026 | 2021-12-27 | 1400/10/06 | 2022-01-02 | 1400/10/12 | AP |  |  |  | D04 | AFC | T-0478 | 2022-01-18 | 1400/10/28 |  |  |  | BK-SUR-ENG-STR-00-02763 | 2022-01-22 | 1400/11/02 | AP | [6 empty] | 1400-2294-372847 | 2022-01-20 | 1400/10/30 | 2022-01-22 | 1400/11/03 | AP
1 | 2 | 0 | 13 | 0 | 3 | 2 | 1.2.13.3.2 | Standard Drawing For Anchor Bolts | BK-GNRAL-PEDCO-000-ST-DW-0002 | BK-GNRAL-PEDCO-000-ST-DW-0002 | BK | GNRAL | PEDCO | 000 | ST | DW | 0002 | F4Q-707276 | AFC | IFC | 2021-12-29 | 2021-12-22 | 2021-12-26 | -7 | 4 | -3 | IFA | 2022-02-16 | 2021-02-07 | 2022-02-09 | -374 | 367 | -7 | AFC | 2022-02-26 | 2022-03-12 | 2022-03-14 | 14 | 2 | 16 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-15 | 2022-02-12 |  | D02 | AFC | T-0579 | 2022-02-12 | 1400/11/23 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-03190 | 2022-02-22 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445199 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0352 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-STR-00-02366 | 2021-12-19 | 1400/09/28 | C4-RJ | [6 empty] | 1400-2294-331499 | 2021-12-22 | 1400/10/01 | 2021-12-26 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0545 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-STR-00-03009 | 2022-02-09 | 1400/11/20 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0002_D00 | [5 empty] | 1400-2294-400988 | 2021-02-07 | 1400/11/18 | 2022-02-09 | 1400/11/20 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0002_D00 | [9 empty] | D02 | AFC | T-0579 | 2022-02-12 | 1400/11/23 |  |  |  | BK-SUR-ENG-STR-00-03190 | 2022-02-22 | 1400/12/03 | AP | [6 empty] | 1400-2294-445199 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | AP
1 | 2 | 0 | 13 | 0 | 3 | 3 | 1.2.13.3.3 | Standard Drawing For Steel Stairs | BK-GNRAL-PEDCO-000-ST-DW-0003 | BK-GNRAL-PEDCO-000-ST-DW-0003 | BK | GNRAL | PEDCO | 000 | ST | DW | 0003 | F4M-707277 | AFC | IFC | 2022-01-01 | 2021-12-22 | 2021-12-27 | -10 | 5 | -5 | IFA | 2022-02-16 | 2021-02-07 | 2022-02-09 | -374 | 367 | -7 | AFC | 2022-02-27 | 2022-03-14 | 2022-03-26 | 15 | 12 | 27 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-18 | 2022-02-13 |  | D02 | AFC | T-0583 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-03192 | 2022-02-22 | 1400/12/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448458 | 2022-03-14 | 1400/12/23 | 2022-03-26 | 1401/01/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0355 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-STR-00-02409 | 2021-12-22 | 1400/10/01 | C4-RJ | [6 empty] | 1400-2294-331510 | 2021-12-22 | 1400/10/01 | 2021-12-27 | 1400/10/06 | CM | [10 empty] | D01 | IFA | T-0545 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-STR-00-03009 | 2022-02-09 | 1400/11/20 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0003_D00 | [5 empty] | 1400-2294-400988 | 2021-02-07 | 1400/11/18 | 2022-02-09 | 1400/11/20 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0003_D00 | [9 empty] | D02 | AFC | T-0583 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-STR-00-03192 | 2022-02-22 | 1400/12/03 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0003_D01 | [5 empty] | 1400-2294-448458 | 2022-03-14 | 1400/12/23 | 2022-03-26 | 1401/01/09 | AP
1 | 2 | 0 | 13 | 0 | 3 | 4 | 1.2.13.3.4 | Standard Drawing For Operating Platform | BK-GNRAL-PEDCO-000-ST-DW-0005 | BK-GNRAL-PEDCO-000-ST-DW-0005 | BK | GNRAL | PEDCO | 000 | ST | DW | 0005 | F4M-707278 | AFC | IFC | 2022-01-10 | 2021-12-30 | 2022-01-02 | -11 | 3 | -8 | IFA | 2022-02-09 | 2022-01-31 | 2022-02-02 | -9 | 2 | -7 | IFA | 2022-03-09 | 2022-03-07 | 2022-02-28 | -2 | -7 | -9 | AFC | 2022-03-26 | 2022-03-16 | 2022-03-25 | -10 | 9 | -1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-27 | 2022-03-12 |  | D03 | AFC | T-0719 | 2022-03-12 | 1400/12/21 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-03509 | 2022-03-12 | 1400/12/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0005_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-452397 | 2022-03-16 | 1400/12/25 | 2022-03-25 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0387 | 2021-12-27 | 1400/10/06 |  |  |  | BK-SUR-ENG-STR-00-02603 | 2022-01-08 | 1400/10/18 | CM-C2 | [6 empty] | 1400-2294-342106 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0514 | 2022-01-26 | 1400/11/06 |  |  |  | BK-SUR-ENG-STR-00-02917 | 2022-02-02 | 1400/11/13 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0005_D00 | [5 empty] | 1400-2294-390694 | 2022-01-31 | 1400/11/11 | 2022-02-02 | 1400/11/13 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0005_D00 | [9 empty] | D02 | IFA | T-0630 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-STR-00-03384 | 2022-03-07 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0005_D01 | [5 empty] | 1400-2294-430111 | 2022-03-07 | 1400/12/17 | 2022-02-28 | 1400/12/09 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0005_D01 | [9 empty] | D03 | AFC | T-0719 | 2022-03-12 | 1400/12/21 |  |  |  | BK-SUR-ENG-STR-00-03509 | 2022-03-12 | 1400/12/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0005_D02 | [5 empty] | 1400-2294-452397 | 2022-03-16 | 1400/12/25 | 2022-03-25 | 1401/01/08 | AP
1 | 2 | 0 | 13 | 0 | 3 | 5 | 1.2.13.3.5 | Standard Drawing For Handrail | BK-GNRAL-PEDCO-000-ST-DW-0006 | BK-GNRAL-PEDCO-000-ST-DW-0006 | BK | GNRAL | PEDCO | 000 | ST | DW | 0006 | F4M-707279 | AFC | IFC | 2022-01-01 | 2021-12-22 | 2021-12-26 | -10 | 4 | -6 | IFA | 2022-02-07 | 2022-01-27 | 2022-01-30 | -11 | 3 | -8 | AFC | 2022-02-23 | 2022-03-12 | 2022-03-14 | 17 | 2 | 19 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-18 | 2022-02-09 |  | D02 | AFC | T-0569 | 2022-02-09 | 1400/11/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0006_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445210 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0354 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-STR-00-02408 | 2021-12-22 | 1400/10/01 | CM-C2 | [6 empty] | 1400-2294-331513 | 2021-12-22 | 1400/10/01 | 2021-12-26 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0501 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-STR-00-02870 | 2022-01-30 | 1400/11/10 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0006_D00 | [5 empty] | 1400-2294-384202 | 2022-01-27 | 1400/11/07 | 2022-01-30 | 1400/11/10 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0006_D00 | [9 empty] | D02 | AFC | T-0569 | 2022-02-09 | 1400/11/20 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0006_D01 | [5 empty] | 1400-2294-445210 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | AP
1 | 2 | 0 | 13 | 0 | 3 | 6 | 1.2.13.3.6 | Standard Drawing For Insert Plates in Concrete | BK-GNRAL-PEDCO-000-ST-DW-0007 | BK-GNRAL-PEDCO-000-ST-DW-0007 | BK | GNRAL | PEDCO | 000 | ST | DW | 0007 | F4M-707280 | AFC | IFI | 2021-08-22 | 2021-08-15 | 2021-08-23 | -7 | 8 | 1 | IFA | 2022-01-12 | 2022-01-02 | 2022-01-12 | -10 | 10 | 0 | AFC | 2022-02-07 | 0 | 0 | -44599 | 0 | -44599 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-08 | 2022-01-24 |  | D02 | AFC | T-0502 | 2022-01-24 | 1400/11/04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0007_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0033 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-STR-00-01317 | 2021-08-14 | 1400/05/23 | CM-C3 | [6 empty] | 1400/2294/166216 | 2021-08-15 | 1400/05/24 | 2021-08-23 | 1400/06/01 | CM | [10 empty] | D01 | IFA | T-0407 | 2021-12-29 | 1400/10/08 |  |  |  | MB-SUR-ENG-STR-00-02655 | 2022-01-11 | 1400/10/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0007_D00 | [5 empty] | 1400-2294-346161 | 2022-01-02 | 1400/10/12 | 2022-01-12 | 1400/10/22 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0007_D00 | [9 empty] | D02 | AFC | T-0502 | 2022-01-24 | 1400/11/04 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0007_D01
1 | 2 | 0 | 13 | 0 | 3 | 7 | 1.2.13.3.7 | Standard Details For Ladder & Safety Cage | BK-GNRAL-PEDCO-000-ST-DW-0009 | BK-GNRAL-PEDCO-000-ST-DW-0009 | BK | GNRAL | PEDCO | 000 | ST | DW | 0009 | F4M-707281 | AFC | IFC | 2021-12-29 | 2021-12-22 | 2021-12-26 | -7 | 4 | -3 | IFA | 2022-02-13 | 2022-02-03 | 2022-02-02 | -10 | -1 | -11 | AFC | 2022-03-02 | 2022-03-14 | 2022-03-25 | 12 | 11 | 23 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-15 | 2022-02-16 |  | D02 | AFC | T-0596 | 2022-02-16 | 1400/11/27 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-03442 | 2022-03-09 | 1400/12/18 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0009_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448461 | 2022-03-14 | 1400/12/23 | 2022-03-25 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0352 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-STR-00-02366 | 2021-12-19 | 1400/09/28 | C4-RJ | [6 empty] | 1400-2294-331499 | 2021-12-22 | 1400/10/01 | 2021-12-26 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0523 | 2022-01-30 | 1400/11/10 |  |  |  | BK-SUR-ENG-STR-00-02955 | 2022-02-06 | 1400/11/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0009_D00 | [5 empty] | 1400-2294-395079 | 2022-02-03 | 1400/11/14 | 2022-02-02 | 1400/11/24 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0009_D00 | [9 empty] | D02 | AFC | T-0596 | 2022-02-16 | 1400/11/27 |  |  |  | BK-SUR-ENG-STR-00-03442 | 2022-03-09 | 1400/12/18 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0009_D01 | [5 empty] | 1400-2294-448461 | 2022-03-14 | 1400/12/23 | 2022-03-25 | 1401/01/08 | AP
1 | 2 | 0 | 13 | 0 | 3 | 8 | 1.2.13.3.8 | Standard Drawing For Lighting pole foundation Plan & Details | BK-GNRAL-PEDCO-000-ST-DW-0010 | BK-GNRAL-PEDCO-000-ST-DW-0010 | BK | GNRAL | PEDCO | 000 | ST | DW | 0010 | F4Q-707282 | AFC | IFC | 2022-02-12 | 2022-02-02 | 2022-02-13 | -10 | 11 | 1 | IFA | 2022-04-12 | 2022-04-06 | 2022-04-09 | -6 | 3 | -3 | IFA | 2022-05-22 | 2022-05-16 | 2022-05-23 | -6 | 7 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-29 | 0 |  | D02 | IFA | T-0911 | 2022-05-08 | 1401/02/18 | T-0911 | 2022-05-08 | 1401/02/18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-63887 | 2022-05-16 | 1401/02/26 | 2022-05-23 | 1401/03/03 | RJ | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0010_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0519 | 2022-01-29 | 1400/11/09 |  |  |  | BK-SUR-ENG-STR-00-02944 | 2022-02-06 | 1400/11/17 | CM-C2 | [6 empty] | 1400-2294-393696 | 2022-02-02 | 1400/11/13 | 2022-02-13 | 1400/11/24 | CM | [10 empty] | D01 | IFA | T-0763 | 2022-03-29 | 1401/01/09 |  |  |  | BK-SUR-ENG-STR-01-03775 | 2022-04-09 | 1401/01/20 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0010_D00 | [5 empty] | 1401-2294-13795 | 2022-04-06 | 1401/01/17 | 2022-04-09 | 1401/01/25 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0010_D00 | [9 empty] | D02 | IFA | T-0911 | 2022-05-08 | 1401/02/18 | T-0911 | 2022-05-08 | 1401/02/18 | [10 empty] | 1401-2294-63887 | 2022-05-16 | 1401/02/26 | 2022-05-23 | 1401/03/03 | RJ | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0010_D01
1 | 2 | 0 | 13 | 0 | 3 | 9 | 1.2.13.3.9 | General Notes - Steel Structures | BK-GNRAL-PEDCO-000-ST-DW-0011 | BK-GNRAL-PEDCO-000-ST-DW-0011 | BK | GNRAL | PEDCO | 000 | ST | DW | 0011 | F4M-707283 | AFC | IFC | 2022-02-08 | 2022-01-27 | 2022-01-30 | -12 | 3 | -9 | IFA | 2022-02-22 | 2022-02-19 | 2022-02-12 | -3 | -7 | -10 | AFC | 2022-03-26 | 2022-03-16 | 2022-03-25 | -10 | 9 | -1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-25 | 2022-03-12 |  | D02 | AFC | T-0719 | 2022-03-12 | 1400/12/21 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-03509 | 2022-03-12 | 1400/12/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0011_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-452397 | 2022-03-16 | 1400/12/25 | 2022-03-25 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0506 | 2022-01-25 | 1400/11/05 |  |  |  | BK-SUR-ENG-STR-00-02871 | 2022-01-30 | 1400/11/10 | CM-C2 | [6 empty] | 1400-2294-384203 | 2022-01-27 | 1400/11/07 | 2022-01-30 | 1400/11/10 | CM | [10 empty] | D01 | IFA | T-0565 | 2022-02-08 | 1400/11/19 |  |  |  | BK-SUR-ENG-STR-00-03041 | 2022-02-13 | 1400/11/24 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0011_D00 | [5 empty] | 1400-2294-406885 | 2022-02-19 | 1400/11/30 | 2022-02-12 | 1400/11/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0011_D00 | [9 empty] | D02 | AFC | T-0719 | 2022-03-12 | 1400/12/21 |  |  |  | BK-SUR-ENG-STR-00-03509 | 2022-03-12 | 1400/12/22 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0011_D01 | [5 empty] | 1400-2294-452397 | 2022-03-16 | 1400/12/25 | 2022-03-25 | 1401/01/08 | AP
1 | 2 | 0 | 13 | 0 | 3 | 10 | 1.2.13.3.10 | General Notes - Reinforced Concrete Structures | BK-GNRAL-PEDCO-000-ST-DW-0012 | BK-GNRAL-PEDCO-000-ST-DW-0012 | BK | GNRAL | PEDCO | 000 | ST | DW | 0012 | F4M-707284 | AFC | IFC | 2022-01-03 | 2021-12-23 | 2021-12-26 | -11 | 3 | -8 | IFA | 2022-02-14 | 2022-02-03 | 2022-02-13 | -11 | 10 | -1 | AFC | 2022-03-02 | 2022-03-14 | 2022-03-25 | 12 | 11 | 23 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-20 | 2022-02-16 |  | D02 | AFC | T-0596 | 2022-02-16 | 1400/11/27 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-03442 | 2022-03-09 | 1400/12/18 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0012_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448461 | 2022-03-14 | 1400/12/23 | 2022-03-25 | 1401/01/08 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0372 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-STR-00-02428 | 2021-12-26 | 1400/10/05 | CM-C3 | [6 empty] | 1400-2294-331871 | 2021-12-23 | 1400/10/02 | 2021-12-26 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0530 | 2022-01-31 | 1400/11/11 |  |  |  | BK-SUR-ENG-STR-00-02956 | 2022-02-06 | 1400/11/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0012_D00 | [5 empty] | 1400-2294-395082 | 2022-02-03 | 1400/11/14 | 2022-02-13 | 1400/11/24 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0012_D00 | [9 empty] | D02 | AFC | T-0596 | 2022-02-16 | 1400/11/27 |  |  |  | BK-SUR-ENG-STR-00-03442 | 2022-03-09 | 1400/12/18 | AP | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0012_D01 | [5 empty] | 1400-2294-448461 | 2022-03-14 | 1400/12/23 | 2022-03-25 | 1401/01/08 | AP
1 | 2 | 0 | 13 | 0 | 3 | 11 | 1.2.13.3.11 | Standard Drawing For Structural Built-up Sections | BK-GNRAL-PEDCO-000-ST-DW-0014 | BK-GNRAL-PEDCO-000-ST-DW-0014 | BK | GNRAL | PEDCO | 000 | ST | DW | 0014 | F4M-707285 | AFC | IFC | 2021-12-18 | 2021-12-09 | 2021-12-12 | -9 | 3 | -6 | IFA | 2022-02-14 | 2022-02-07 | 2022-02-19 | -7 | 12 | 5 | IFA | 2022-05-11 | 2022-05-08 | 2022-05-08 | -3 | 0 | -3 | AFC | 2022-06-06 | 0 | 0 | -44718 | 0 | -44718 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-04 | 2022-05-23 |  | D03 | AFC | T-0994 | 2022-05-23 | 1401/03/02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0014_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0288 | 2021-12-04 | 1400/09/13 |  |  |  | BK-SUR-ENG-STR-00-02269 | 2021-12-12 | 1400/09/21 | CM-C2 | [6 empty] | 1400-2294-310899 | 2021-12-09 | 1400/09/18 | 2021-12-12 | 1400/09/21 | CM | [10 empty] | D01 | IFA | T-0525 | 2022-01-31 | 1400/11/11 |  |  |  | BK-SUR-ENG-STR-00-02950 | 2022-02-06 | 1400/11/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0014_D00 | [5 empty] | 1400-2294-400912 | 2022-02-07 | 1400/11/18 | 2022-02-19 | 1400/11/30 | RJ | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0014_D00 | [9 empty] | D02 | IFA | T-0870 | 2022-04-27 | 1401/02/07 | T-0870 | 2022-04-27 | 1401/02/07 | BK-SUR-ENG-STR-01-04139 | 2022-05-07 | 1401/02/17 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0014_D01 | [5 empty] | 1401-2294-52736 | 2022-05-08 | 1401/02/18 | 2022-05-08 | 1401/02/18 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0014_D01 | [9 empty] | D03 | AFC | T-0994 | 2022-05-23 | 1401/03/02 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0014_D02
1 | 2 | 0 | 13 | 0 | 3 | 12 | 1.2.13.3.12 | Standard Drawing For Steel Flooring, Grating and Chequered Plate | BK-GNRAL-PEDCO-000-ST-DW-0015 | BK-GNRAL-PEDCO-000-ST-DW-0015 | BK | GNRAL | PEDCO | 000 | ST | DW | 0015 | F4M-707286 | AFC | IFC | 2022-01-19 | 2022-01-10 | 2022-01-15 | -9 | 5 | -4 | AFC | 2022-02-26 | 2022-03-12 | 2022-03-14 | 14 | 2 | 16 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-05 | 2022-02-12 |  | D01 | AFC | T-0574 | 2022-02-12 | 1400/11/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0015-D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445213 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0430 | 2022-01-05 | 1400/10/15 |  |  |  | BK-SUR-ENG-STR-00-02683 | 2022-01-15 | 1400/10/15 | CM-C2 | [6 empty] | 1400-2294-358439 | 2022-01-10 | 1400/10/20 | 2022-01-15 | 1400/10/25 | AP | [10 empty] | D01 | AFC | T-0574 | 2022-02-12 | 1400/11/23 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0015-D00 | [5 empty] | 1400-2294-445213 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | AP
1 | 2 | 0 | 13 | 0 | 3 | 13 | 1.2.13.3.13 | Concrete Reinforcement Shape Code | BK-GNRAL-PEDCO-000-ST-DW-0016 | BK-GNRAL-PEDCO-000-ST-DW-0016 | BK | GNRAL | PEDCO | 000 | ST | DW | 0016 | F4M-707287 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 13 | 0 | 3 | 14 | 1.2.13.3.14 | Standard Drawing For Septic Tank | BK-GNRAL-PEDCO-000-ST-DW-0017 | BK-GNRAL-PEDCO-000-ST-DW-0017 | BK | GNRAL | PEDCO | 000 | ST | DW | 0017 | F4M-707288 | AFC | IFC | 2022-02-05 | 2022-01-27 | 2022-01-29 | -9 | 2 | -7 | IFA | 2022-03-08 | 2022-02-26 | 2022-03-08 | -10 | 10 | 0 | IFA | 2022-06-08 | 0 | 0 | -44720 | 0 | -44720 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-22 | 0 |  | D02 | IFA | T-1006 | 2022-05-25 | 1401/03/04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0489 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-STR-00-02822 | 2022-01-26 | 1400/11/09 | CM-C2 | [6 empty] | 1400-2294-384171 | 2022-01-27 | 1400/11/07 | 2022-01-29 | 1400/11/09 | CM | [10 empty] | D01 | IFA | T-0625 | 2022-02-22 | 1400/12/03 |  |  |  | MB-SUR-ENG-STR-00-03355 | 2022-05-24 | 1401/03/03 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D00 | [5 empty] | 1400-2294-425598 | 2022-02-26 | 1400/12/07 | 2022-03-08 | 1400/12/17 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D00 | [9 empty] | D02 | IFA | T-1006 | 2022-05-25 | 1401/03/04 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D01 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-ST-DW-0017_D01
1 | 2 | 0 | 14 | 0 | 0 | 0 | 1.2.14 | Risk & Environmental Assessment
1 | 2 | 0 | 14 | 1 | 0 | 0 | 1.2.14.1 | Environmental Assessment
1 | 2 | 0 | 14 | 1 | 1 | 0 | 1.2.14.1.1 | Procedure/Plan
1 | 2 | 0 | 14 | 1 | 1 | 1 | 1.2.14.1.1.1 | EPC Waste Management Plan | BK-GNRAL-HD-000-SA-HP-0001 | BK-GNRAL-HD-000-SA-HP-0001 | BK | GNRAL | HD | 000 | SA | HP | 0001 | F0Z-707050 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 14 | 2 | 0 | 0 | 1.2.14.2 | Risk Assessment
1 | 2 | 0 | 14 | 2 | 1 | 0 | 1.2.14.2.1 | Procedure/Plan
1 | 2 | 0 | 14 | 2 | 1 | 1 | 1.2.14.2.1.1 | HAZOP Study Procedure | BK-GNRAL-PEDCO-000-GE-PR-0001 | BK-GNRAL-PEDCO-000-GE-PR-0001 | BK | GNRAL | PEDCO | 000 | GE | PR | 0001 | F0Z-707289 | AFC | IFC | 2021-11-08 | 2021-12-22 | 2021-11-27 | 44 | -25 | 19 | IFA | 2021-12-20 | 2021-12-17 | 2021-12-18 | -3 | 1 | -2 | AFC | 2022-03-16 | 2022-03-12 | 2022-03-15 | -4 | 3 | -1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-25 | 2022-03-02 |  | D02 | AFC | T-0664 | 2022-03-02 | 1400/12/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445251 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0183 | 2021-10-25 | 1400/08/03 | [13 empty] | 1400-2294-285014 | 2021-11-21 | 1400/08/30 | 2021-11-27 | 1400/09/06 | CM |  | 1400-2294-330830 | 2021-12-22 | 1400/10/01 |  |  | AP |  |  |  | D01 | IFA | T-0296 | 2021-12-06 | 1400/09/15 | [13 empty] | 1400-2294-320830 | 2021-12-17 | 1400/09/26 | 2021-12-18 | 1400/09/27 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-GE-PR-0001_D00 | [9 empty] | D02 | AFC | T-0664 | 2022-03-02 | 1400/12/11 | [13 empty] | 1400-2294-445251 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | AP
1 | 2 | 0 | 14 | 2 | 1 | 2 | 1.2.14.2.1.2 | HAZID Study Procedure | BK-GNRAL-PEDCO-000-GE-PR-0002 | BK-GNRAL-PEDCO-000-GE-PR-0002 | BK | GNRAL | PEDCO | 000 | GE | PR | 0002 | F0Z-707290 | AFC | IFC | 2021-09-19 | 2021-09-22 | 2021-09-25 | 3 | 3 | 6 | IFA | 2021-10-17 | 2021-10-19 | 2021-10-26 | 2 | 7 | 9 | AFC | 2021-11-10 | 2021-11-01 | 2021-11-06 | -9 | 5 | -4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-05 | 2021-10-27 |  | D02 | AFC | T-0189 | 2021-10-27 | 1400/08/05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-257495 | 2021-11-01 | 1400/08/10 | 2021-11-06 | 1400/08/15 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0078 | 2021-09-05 | 1400/06/14 | [13 empty] | 1400-2294-208400 | 2021-09-22 | 1400/06/31 | 2021-09-25 | 1400/07/03 | CM | [10 empty] | D01 | IFA | T-0132 | 2021-10-03 | 1400/07/11 | [13 empty] | 1400-2294-241736 | 2021-10-19 | 1400/07/27 | 2021-10-26 | 1400/08/04 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-GE-PR-0002_D01 | [9 empty] | D02 | AFC | T-0189 | 2021-10-27 | 1400/08/05 | [13 empty] | 1400-2294-257495 | 2021-11-01 | 1400/08/10 | 2021-11-06 | 1400/08/15 | AP
1 | 2 | 0 | 14 | 2 | 1 | 3 | 1.2.14.2.1.3 | SIL Study Procedure | BK-GNRAL-PEDCO-000-GE-PR-0003 | BK-GNRAL-PEDCO-000-GE-PR-0003 | BK | GNRAL | PEDCO | 000 | GE | PR | 0003 | F0Z-707291 | AFC | IFC | 2021-11-08 | 2021-12-22 | 2021-11-27 | 44 | -25 | 19 | AFC | 2022-03-21 | 2022-03-12 | 2022-03-15 | -9 | 3 | -6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-25 | 2022-03-07 |  | D01 | AFC | T-0688 | 2022-03-07 | 1400/12/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445304 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0183 | 2021-10-25 | 1400/08/03 | [13 empty] | 1400-2294-285014 | 2021-11-21 | 1400/08/30 | 2021-11-27 | 1400/09/06 | CM |  | 1400-2294-330830 | 2021-12-22 | 1400/10/01 |  |  | AP |  |  |  | D01 | AFC | T-0688 | 2022-03-07 | 1400/12/16 | [13 empty] | 1400-2294-445304 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | AP
1 | 2 | 0 | 14 | 2 | 1 | 4 | 1.2.14.2.1.4 | Crisis Management Plan | BK-GNRAL-HD-000-GE-PR-0004 | BK-GNRAL-HD-000-GE-PR-0004 | BK | GNRAL | HD | 000 | GE | PR | 0004 | F0Z-707051 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 14 | 2 | 1 | 5 | 1.2.14.2.1.5 | EPC FMEA report | BK-GNRAL-HD-000-GE-PR-0005 | BK-GNRAL-HD-000-GE-PR-0005 | BK | GNRAL | HD | 000 | GE | PR | 0005 | F0Z-707052 | AFC | IFC | 2022-01-11 | 0 | 0 | -44572 | 0 | -44572 | AFC | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-28 | 2022-05-22 |  | G01 | AFC | T-0982 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0393 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-HSE-HSE-00-02476 | 2021-12-28 | 1400/10/06 | AP | [22 empty] | G01 | AFC | T-0982 | 2022-05-22 | 1401/03/01
1 | 2 | 0 | 14 | 2 | 1 | 6 | 1.2.14.2.1.6 | PSSR Procedure | BK-GNRAL-HD-000-GE-PR-0006 | BK-GNRAL-HD-000-GE-PR-0006 | BK | GNRAL | HD | 000 | GE | PR | 0006 | F0Z-707053 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 14 | 2 | 1 | 7 | 1.2.14.2.1.7 | Pigging Safety Requirement | BK-GNRAL-PEDCO-000-GE-PR-0007 | BK-GNRAL-PEDCO-000-GE-PR-0007 | BK | GNRAL | PEDCO | 000 | GE | PR | 0007 | F0Z-707054 | AFC | IFC | 2022-04-23 | 2022-05-10 | 2022-05-16 | 17 | 6 | 23 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-09 | 0 |  | D00 | IFC | T-0787 | 2022-04-09 | 1401/01/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-56285 | 2022-05-10 | 1401/02/20 | 2022-05-16 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0787 | 2022-04-09 | 1401/01/20 | [13 empty] | 1401-2294-56285 | 2022-05-10 | 1401/02/20 | 2022-05-16 | 1401/02/26 | CM
1 | 2 | 0 | 15 | 0 | 0 | 0 | 1.2.15 | QC/QA
1 | 2 | 0 | 15 | 1 | 0 | 0 | 1.2.15.1 | QC Management
1 | 2 | 0 | 15 | 1 | 0 | 1 | 1.2.15.1.1 | Project Quality Plan | BK-GNRAL-PEDCO-000-QC-PR-0001 | BK-GNRAL-PEDCO-000-QC-PR-0001 | BK | GNRAL | PEDCO | 000 | QC | PR | 0001 | F0Z-707299 | AFD | IFC | 2021-12-22 | 2022-03-30 | 2022-04-13 | 98 | 14 | 112 | IFA | 2022-05-28 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-08 | 0 |  | D01 | IFA | T-0446 | 2022-05-14 | 1401/02/24 | 0 | 0 | 0 | BK-SUR-ENG-QAC-00-02667 | 2022-01-15 | 1400/10/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0322 | 2021-12-08 | 1400/09/17 |  |  |  | BK-SUR-ENG-QAC-00-02295 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1401-2294-6237 | 2022-03-30 | 1401/01/10 | 2022-04-13 | 1401/01/24 | AP | [10 empty] | D01 | IFA | T-0446 | 2022-05-14 | 1401/02/24 |  |  |  | BK-SUR-ENG-QAC-00-02667 | 2022-01-15 | 1400/10/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0001_D00 | [33 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0001_D01
1 | 2 | 0 | 15 | 1 | 0 | 2 | 1.2.15.1.2 | Project Audit Procedure | BK-GNRAL-PEDCO-000-QC-PR-0003 | BK-GNRAL-PEDCO-000-QC-PR-0003 | BK | GNRAL | PEDCO | 000 | QC | PR | 0003 | F0Z-707292 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 1 | 0 | 3 | 1.2.15.1.3 | Non Conformance Control Procedure | BK-GNRAL-PEDCO-000-QC-PR-0042 | BK-GNRAL-PEDCO-000-QC-PR-0042 | BK | GNRAL | PEDCO | 000 | QC | PR | 0042 | F0Z-707294 | AFC | IFC | 2022-04-24 | 2022-05-16 | 2022-05-23 | 22 | 7 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-10 | 0 |  | D00 | IFC | T-0793 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-03981 | 2022-04-29 | 1401/01/29 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65519 | 2022-05-16 | 1401/02/26 | 2022-05-23 | 1401/03/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0793 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-QAC-01-03981 | 2022-04-29 | 1401/01/29 | CM-C3 | [6 empty] | 1401-2294-65519 | 2022-05-16 | 1401/02/26 | 2022-05-23 | 1401/03/03 | AP
1 | 2 | 0 | 15 | 1 | 0 | 4 | 1.2.15.1.4 | Corrective Action Procedure | BK-GNRAL-PEDCO-000-QC-PR-0043 | BK-GNRAL-PEDCO-000-QC-PR-0043 | BK | GNRAL | PEDCO | 000 | QC | PR | 0043 | F0Z-707295 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 1 | 0 | 5 | 1.2.15.1.5 | Material Reciving, Storage, Handling Procedure | BK-GNRAL-PEDCO-000-QC-PR-0044 | BK-GNRAL-PEDCO-000-QC-PR-0044 | BK | GNRAL | PEDCO | 000 | QC | PR | 0044 | F0Z-707296 | AFC | IFC | 2022-03-06 | 2022-05-12 | 2022-05-21 | 67 | 9 | 76 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-20 | 0 |  | D00 | IFC | T-0610 | 2022-02-20 | 1400/12/01 | 0 | 0 | 0 | BK-SUR-ENG-QAC-00-03238 | 2022-02-27 | 1400/12/08 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59522 | 2022-05-12 | 1401/02/22 | 2022-05-21 | 1401/02/31 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0610 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-QAC-00-03238 | 2022-02-27 | 1400/12/08 | CM-C2 | [6 empty] | 1401-2294-59522 | 2022-05-12 | 1401/02/22 | 2022-05-21 | 1401/02/31 | AP
1 | 2 | 0 | 15 | 1 | 0 | 6 | 1.2.15.1.6 | Packing, Marking, Transportation Procedure | BK-GNRAL-PEDCO-000-QC-PR-0045 | BK-GNRAL-PEDCO-000-QC-PR-0045 | BK | GNRAL | PEDCO | 000 | QC | PR | 0045 | F0Z-707297 | AFC | IFC | 2022-05-08 | 2022-05-12 | 2022-05-21 | 4 | 9 | 13 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-24 | 0 |  | D00 | IFC | T-0855 | 2022-04-24 | 1401/02/04 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-04118 | 2022-05-01 | 1401/02/11 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59527 | 2022-05-12 | 1401/02/22 | 2022-05-21 | 1401/02/31 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0855 | 2022-04-24 | 1401/02/04 |  |  |  | BK-SUR-ENG-QAC-01-04118 | 2022-05-01 | 1401/02/11 | AP | [6 empty] | 1401-2294-59527 | 2022-05-12 | 1401/02/22 | 2022-05-21 | 1401/02/31 | AP
1 | 2 | 0 | 15 | 1 | 0 | 7 | 1.2.15.1.7 | Criticality Assessment Procedure | BK-GNRAL-PEDCO-000-PM-PR-0013 | BK-GNRAL-PEDCO-000-PM-PR-0013 | BK | GNRAL | PEDCO | 000 | PM | PR | 0013 | F0Z-707298 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 1 | 0 | 8 | 1.2.15.1.8 | Specification For Final Data Book (FDB) Requirements | BK-GNRAL-PEDCO-000-QC-PR-0022 | BK-GNRAL-PEDCO-000-QC-PR-0022 | BK | GNRAL | PEDCO | 000 | QC | PR | 0022 | F0Z-707293 | AFC | IFC | 2022-04-17 | 2022-04-19 | 2022-04-24 | 2 | 5 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-03 | 0 |  | D00 | IFC | T-0771 | 2022-04-03 | 1401/01/14 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-03936 | 2022-04-16 | 1401/01/27 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31420 | 2022-04-19 | 1401/01/30 | 2022-04-24 | 1401/02/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0771 | 2022-04-03 | 1401/01/14 |  |  |  | BK-SUR-ENG-QAC-01-03936 | 2022-04-16 | 1401/01/27 | CM-C3 | [6 empty] | 1401-2294-31420 | 2022-04-19 | 1401/01/30 | 2022-04-24 | 1401/02/04 | CM
1 | 2 | 0 | 15 | 1 | 0 | 9 | 1.2.15.1.9 | Technical Query Procedure | BK-GNRAL-PEDCO-000-QC-PR-0014 | BK-GNRAL-PEDCO-000-QC-PR-0014 | BK | GNRAL | PEDCO | 000 | QC | PR | 0014 | F0Z-707300 | AFC | IFC | 2022-04-17 | 2022-04-19 | 2022-04-24 | 2 | 5 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-03 | 0 |  | D00 | IFC | T-0771 | 2022-04-03 | 1401/01/14 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-03936 | 2022-04-16 | 1401/01/27 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31420 | 2022-04-19 | 1401/01/30 | 2022-04-24 | 1401/02/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0771 | 2022-04-03 | 1401/01/14 |  |  |  | BK-SUR-ENG-QAC-01-03936 | 2022-04-16 | 1401/01/27 | CM-C3 | [6 empty] | 1401-2294-31420 | 2022-04-19 | 1401/01/30 | 2022-04-24 | 1401/02/04 | CM
1 | 2 | 0 | 15 | 2 | 0 | 0 | 1.2.15.2 | QC General Document
1 | 2 | 0 | 15 | 2 | 0 | 1 | 1.2.15.2.1 | Quality Control Plan (QCP) | BK-GNRAL-PEDCO-000-QC-PR-0002 | BK-GNRAL-PEDCO-000-QC-PR-0002 | BK | GNRAL | PEDCO | 000 | QC | PR | 0002 | F0Z-707301 | AFC | IFC | 2021-12-12 | 2022-02-16 | 2022-02-16 | 66 | 0 | 66 | IFC | 2022-02-05 | 0 | 0 | -44597 | 0 | -44597 | IFC | 2022-03-27 | 0 | 0 | -44647 | 0 | -44647 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-28 | 0 |  | D01 | IFC | T-0724 | 2022-03-13 | 1400/12/22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0282 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-QAC-00-02163 | 2021-12-01 | 1400/09/10 | C4-RJ | [6 empty] | 1400-2294-412900 | 2022-02-16 | 1400/11/27 | 2022-02-16 | 1400/11/27 | AP | [10 empty] | D00 | IFC | T-0487 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-QAC-00-02925 | 2022-02-02 | 1400/11/13 | C4-RJ | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0002_D00 | [21 empty] | D01 | IFC | T-0724 | 2022-03-13 | 1400/12/22 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0002_D00
1 | 2 | 0 | 15 | 2 | 0 | 2 | 1.2.15.2.2 | Specification for Welding Procedure | BK-GNRAL-PEDCO-000-QC-PR-0015 | BK-GNRAL-PEDCO-000-QC-PR-0015 | BK | GNRAL | PEDCO | 000 | QC | PR | 0015 | F0Z-707302 | AFC | IFC | 2022-04-30 | 0 | 0 | -44681 | 0 | -44681 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-16 | 0 |  | D00 | IFC | T-0819 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-03943 | 2022-04-17 | 1401/01/28 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0819 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-QAC-01-03943 | 2022-04-17 | 1401/01/28 | C4-RJ
1 | 2 | 0 | 15 | 2 | 0 | 3 | 1.2.15.2.3 | Heat Treatment Procedure (Pre Heating , PWHT) | BK-GNRAL-PEDCO-000-QC-PR-0016 | BK-GNRAL-PEDCO-000-QC-PR-0016 | BK | GNRAL | PEDCO | 000 | QC | PR | 0016 | F0Z-707303 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 2 | 0 | 4 | 1.2.15.2.4 | Welder Performance Qualification Test (WQT) Procedure | BK-GNRAL-PEDCO-000-QC-PR-0017 | BK-GNRAL-PEDCO-000-QC-PR-0017 | BK | GNRAL | PEDCO | 000 | QC | PR | 0017 | F0Z-707304 | AFC | IFC | 2022-04-18 | 2022-05-08 | 2022-05-18 | 20 | 10 | 30 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-04 | 0 |  | D00 | IFC | T-0772 | 2022-04-04 | 1400/01/15 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-03946 | 2022-04-17 | 1401/01/28 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52746 | 2022-05-08 | 1401/02/18 | 2022-05-18 | 1401/02/28 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0772 | 2022-04-04 | 1400/01/15 |  |  |  | BK-SUR-ENG-QAC-01-03946 | 2022-04-17 | 1401/01/28 | CM-C2 | [6 empty] | 1401-2294-52746 | 2022-05-08 | 1401/02/18 | 2022-05-18 | 1401/02/28 | CM
1 | 2 | 0 | 15 | 2 | 0 | 5 | 1.2.15.2.5 | NDT Procedure | BK-GNRAL-PEDCO-000-QC-PR-0018 | BK-GNRAL-PEDCO-000-QC-PR-0018 | BK | GNRAL | PEDCO | 000 | QC | PR | 0018 | F0Z-707305 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 2 | 0 | 6 | 1.2.15.2.6 | Surface Preparation and Coating/Painting Procedure | BK-GNRAL-PEDCO-000-QC-PR-0019 | BK-GNRAL-PEDCO-000-QC-PR-0019 | BK | GNRAL | PEDCO | 000 | QC | PR | 0019 | F0Z-707306 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 2 | 0 | 7 | 1.2.15.2.7 | Control of Inspection Measuring and Test Equipment Procedure | BK-GNRAL-PEDCO-000-QC-PR-0021 | BK-GNRAL-PEDCO-000-QC-PR-0021 | BK | GNRAL | PEDCO | 000 | QC | PR | 0021 | F0Z-707307 | AFC | IFC | 2022-04-24 | 2022-05-16 | 2022-05-23 | 22 | 7 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-10 | 0 |  | D00 | IFC | T-0793 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-03981 | 2022-04-29 | 1401/01/29 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65519 | 2022-05-16 | 1401/02/26 | 2022-05-23 | 1401/03/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0793 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-QAC-01-03981 | 2022-04-29 | 1401/01/29 | CM-C3 | [6 empty] | 1401-2294-65519 | 2022-05-16 | 1401/02/26 | 2022-05-23 | 1401/03/03 | AP
1 | 2 | 0 | 15 | 2 | 0 | 8 | 1.2.15.2.8 | Field Joint Coating Procedure For Pipeline | BK-GNRAL-PEDCO-000-QC-PR-0035 | BK-GNRAL-PEDCO-000-QC-PR-0035 | BK | GNRAL | PEDCO | 000 | QC | PR | 0035 | F0Z-707315 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 0 | 0 | 1.2.15.3 | QC Discipline Document
1 | 2 | 0 | 15 | 3 | 1 | 0 | 1.2.15.3.1 | Piping
1 | 2 | 0 | 15 | 3 | 1 | 1 | 1.2.15.3.1.1 | ITP For Piping Works | BK-GNRAL-PEDCO-000-QC-PR-0004 | BK-GNRAL-PEDCO-000-QC-PR-0004 | BK | GNRAL | PEDCO | 000 | QC | PR | 0004 | F0Z-707308 | AFC | IFC | 2022-04-24 | 2022-05-16 | 2022-05-23 | 22 | 7 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-10 | 0 |  | D00 | IFC | T-0793 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-03981 | 2022-04-29 | 1401/01/29 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65519 | 2022-05-16 | 1401/02/26 | 2022-05-23 | 1401/03/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0793 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-QAC-01-03981 | 2022-04-29 | 1401/01/29 | CM-C3 | [6 empty] | 1401-2294-65519 | 2022-05-16 | 1401/02/26 | 2022-05-23 | 1401/03/03 | AP
1 | 2 | 0 | 15 | 3 | 1 | 2 | 1.2.15.3.1.2 | PIPING PWPS (Preliminary Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0023 | BK-GNRAL-PEDCO-000-QC-PR-0023 | BK | GNRAL | PEDCO | 000 | QC | PR | 0023 | F0Z-707309 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 1 | 3 | 1.2.15.3.1.3 | PIPING WPS (Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0024 | BK-GNRAL-PEDCO-000-QC-PR-0024 | BK | GNRAL | PEDCO | 000 | QC | PR | 0024 | F0Z-707310 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 1 | 4 | 1.2.15.3.1.4 | PIPING PQR (Procedure Qualification Record) | BK-GNRAL-PEDCO-000-QC-PR-0025 | BK-GNRAL-PEDCO-000-QC-PR-0025 | BK | GNRAL | PEDCO | 000 | QC | PR | 0025 | F0Z-707311 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 1 | 5 | 1.2.15.3.1.5 | PIPING PWPS (Preliminary Welding Procedure Specification) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0026 | BK-GNRAL-PEDCO-000-QC-PR-0026 | BK | GNRAL | PEDCO | 000 | QC | PR | 0026 | F0Z-707312 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 1 | 6 | 1.2.15.3.1.6 | PIPING WPS (Preliminary Welding Procedure Specification) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0027 | BK-GNRAL-PEDCO-000-QC-PR-0027 | BK | GNRAL | PEDCO | 000 | QC | PR | 0027 | F0Z-707313 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 1 | 7 | 1.2.15.3.1.7 | PIPING PQR (Procedure Qualification Record) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0028 | BK-GNRAL-PEDCO-000-QC-PR-0028 | BK | GNRAL | PEDCO | 000 | QC | PR | 0028 | F0Z-707314 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 2 | 0 | 1.2.15.3.2 | Telecomm.
1 | 2 | 0 | 15 | 3 | 2 | 1 | 1.2.15.3.2.1 | ITP For Telecommunication Installation | BK-GNRAL-PEDCO-000-QC-PR-0012 | BK-GNRAL-PEDCO-000-QC-PR-0012 | BK | GNRAL | PEDCO | 000 | QC | PR | 0012 | F0Z-707317 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 3 | 0 | 1.2.15.3.3 | Safety
1 | 2 | 0 | 15 | 3 | 3 | 1 | 1.2.15.3.3.1 | ITP For Safety Installation | BK-GNRAL-PEDCO-000-QC-PR-0013 | BK-GNRAL-PEDCO-000-QC-PR-0013 | BK | GNRAL | PEDCO | 000 | QC | PR | 0013 | F0Z-707318 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 4 | 0 | 1.2.15.3.4 | Architectural
1 | 2 | 0 | 15 | 3 | 4 | 1 | 1.2.15.3.4.1 | ITP For Architectural Works | BK-GNRAL-PEDCO-000-QC-PR-0008 | BK-GNRAL-PEDCO-000-QC-PR-0008 | BK | GNRAL | PEDCO | 000 | QC | PR | 0008 | F0Z-707319 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 5 | 0 | 1.2.15.3.5 | Mechanical
1 | 2 | 0 | 15 | 3 | 5 | 1 | 1.2.15.3.5.1 | ITP For Mechanical Installation | BK-GNRAL-PEDCO-000-QC-PR-0009 | BK-GNRAL-PEDCO-000-QC-PR-0009 | BK | GNRAL | PEDCO | 000 | QC | PR | 0009 | F0Z-707320 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 6 | 0 | 1.2.15.3.6 | Structure
1 | 2 | 0 | 15 | 3 | 6 | 1 | 1.2.15.3.6.1 | ITP For Steel Structural Works | BK-GNRAL-PEDCO-000-QC-PR-0007 | BK-GNRAL-PEDCO-000-QC-PR-0007 | BK | GNRAL | PEDCO | 000 | QC | PR | 0007 | F0Z-707321 | AFC | IFC | 2022-06-04 | 0 | 0 | -44716 | 0 | -44716 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-21 | 0 |  | D00 | IFC | T-0980 | 2022-05-21 | 1401/02/31 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-04484 | 2022-05-29 | 1401/03/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0980 | 2022-05-21 | 1401/02/31 |  |  |  | BK-SUR-ENG-QAC-01-04484 | 2022-05-29 | 1401/03/09 | CM-C3
1 | 2 | 0 | 15 | 3 | 6 | 2 | 1.2.15.3.6.2 | Steel Structure WPS (Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0036 | BK-GNRAL-PEDCO-000-QC-PR-0036 | BK | GNRAL | PEDCO | 000 | QC | PR | 0036 | F0Z-707322 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 6 | 3 | 1.2.15.3.6.3 | Steel Structure PQR (Procedure Qualification Record) | BK-GNRAL-PEDCO-000-QC-PR-0037 | BK-GNRAL-PEDCO-000-QC-PR-0037 | BK | GNRAL | PEDCO | 000 | QC | PR | 0037 | F0Z-707323 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 6 | 4 | 1.2.15.3.6.4 | Steel Structure WPS (Welding Procedure Specification) For Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0038 | BK-GNRAL-PEDCO-000-QC-PR-0038 | BK | GNRAL | PEDCO | 000 | QC | PR | 0038 | F0Z-707324 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 6 | 5 | 1.2.15.3.6.5 | Steel Structure PQR (Procedure Qualification Record) For Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0039 | BK-GNRAL-PEDCO-000-QC-PR-0039 | BK | GNRAL | PEDCO | 000 | QC | PR | 0039 | F0Z-707325 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 6 | 6 | 1.2.15.3.6.6 | Weld Map For Steel Structures | BK-GNRAL-PEDCO-000-QC-PR-0040 | BK-GNRAL-PEDCO-000-QC-PR-0040 | BK | GNRAL | PEDCO | 000 | QC | PR | 0040 | F0Z-707326 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 6 | 7 | 1.2.15.3.6.7 | NDT Plan For steel Structures | BK-GNRAL-PEDCO-000-QC-PR-0041 | BK-GNRAL-PEDCO-000-QC-PR-0041 | BK | GNRAL | PEDCO | 000 | QC | PR | 0041 | F0Z-707327 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 7 | 0 | 1.2.15.3.7 | Instrumentation
1 | 2 | 0 | 15 | 3 | 7 | 1 | 1.2.15.3.7.1 | ITP For I&C Installation | BK-GNRAL-PEDCO-000-QC-PR-0011 | BK-GNRAL-PEDCO-000-QC-PR-0011 | BK | GNRAL | PEDCO | 000 | QC | PR | 0011 | F0Z-707328 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 8 | 0 | 1.2.15.3.8 | Pipeline
1 | 2 | 0 | 15 | 3 | 8 | 1 | 1.2.15.3.8.1 | ITP For Pipeline | BK-GNRAL-PEDCO-000-QC-PR-0005 | BK-GNRAL-PEDCO-000-QC-PR-0005 | BK | GNRAL | PEDCO | 000 | QC | PR | 0005 | F0Z-707329 | AFC | IFC | 2022-01-30 | 2022-03-23 | 2022-03-25 | 52 | 2 | 54 | IFA | 2022-05-04 | 0 | 0 | -44685 | 0 | -44685 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-16 | 0 |  | D01 | IFA | T-0853 | 2022-04-20 | 1401/01/31 | 0 | 0 | 0 | BK-SUR-ENG-QAC-01-04120 | 2022-05-01 | 1401/02/11 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GNRAL-PEDCO-000-QC-PR-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0462 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-QAC-00-02928 | 2022-02-05 | 1400/11/16 | CM-C2 | [6 empty] | 1400-2294-397208 | 2022-02-05 | 1400/11/16 | 2022-02-05 | 1400/11/16 | CM |  | 1401-2294-1325 | 2022-03-23 | 1401/01/06 | 2022-03-25 | 1401/01/08 | CM |  |  |  | D01 | IFA | T-0853 | 2022-04-20 | 1401/01/31 |  |  |  | BK-SUR-ENG-QAC-01-04120 | 2022-05-01 | 1401/02/11 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0005_D00 | [11 empty] | NISOC-CRS-BK-GNRAL-PEDCO-000-QC-PR-0005_D00
1 | 2 | 0 | 15 | 3 | 8 | 2 | 1.2.15.3.8.2 | PIPELINE PWPS (Preliminary Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0029 | BK-GNRAL-PEDCO-000-QC-PR-0029 | BK | GNRAL | PEDCO | 000 | QC | PR | 0029 | F0Z-707330 | AFC | IFC | 2022-03-09 | 2022-03-23 | 2022-03-25 | 14 | 2 | 16 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-23 | 0 |  | D00 | IFC | T-0629 | 2022-02-23 | 1400/12/04 | 0 | 0 | 0 | BK-SUR-ENG-QAC-00-03286 | 2022-03-02 | 1400/12/11 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-1320 | 2022-03-23 | 1401/01/06 | 2022-03-25 | 1401/01/08 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0629 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-QAC-00-03286 | 2022-03-02 | 1400/12/11 | C4-RJ | [6 empty] | 1401-2294-1320 | 2022-03-23 | 1401/01/06 | 2022-03-25 | 1401/01/08 | CM
1 | 2 | 0 | 15 | 3 | 8 | 3 | 1.2.15.3.8.3 | PIPELINE WPS (Welding Procedure Specification) | BK-GNRAL-PEDCO-000-QC-PR-0030 | BK-GNRAL-PEDCO-000-QC-PR-0030 | BK | GNRAL | PEDCO | 000 | QC | PR | 0030 | F0Z-707331 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 8 | 4 | 1.2.15.3.8.4 | PIPELINE PQR (Procedure Qualification Record) | BK-GNRAL-PEDCO-000-QC-PR-0031 | BK-GNRAL-PEDCO-000-QC-PR-0031 | BK | GNRAL | PEDCO | 000 | QC | PR | 0031 | F0Z-707332 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 8 | 5 | 1.2.15.3.8.5 | PIPELINE PWPS (Preliminary Welding Procedure Specification) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0032 | BK-GNRAL-PEDCO-000-QC-PR-0032 | BK | GNRAL | PEDCO | 000 | QC | PR | 0032 | F0Z-707333 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 8 | 6 | 1.2.15.3.8.6 | PIPELINE WPS (Preliminary Welding Procedure Specification) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0033 | BK-GNRAL-PEDCO-000-QC-PR-0033 | BK | GNRAL | PEDCO | 000 | QC | PR | 0033 | F0Z-707334 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 8 | 7 | 1.2.15.3.8.7 | PIPELINE PQR (Procedure Qualification Record) for Repair Welding | BK-GNRAL-PEDCO-000-QC-PR-0034 | BK-GNRAL-PEDCO-000-QC-PR-0034 | BK | GNRAL | PEDCO | 000 | QC | PR | 0034 | F0Z-707335 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
1 | 2 | 0 | 15 | 3 | 9 | 0 | 1.2.15.3.9 | Civil
1 | 2 | 0 | 15 | 3 | 9 | 1 | 1.2.15.3.9.1 | ITP For Civil Works | BK-GNRAL-PEDCO-000-QC-PR-0006 | BK-GNRAL-PEDCO-000-QC-PR-0006 | BK | GNRAL | PEDCO | 000 | PM | CG | 0001 | F0Z-707336 | AFD | IFC | 44473 | 44462 | 44465 | -11 | 3 | -8 | AFD | 44536 | 44528 | 44545 | -8 | 17 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-20 | 2021-11-22 |  | D01 | AFD | T-0267 | 2021-11-22 | 1400/09/01 | 0 | 0 | 0 | BK-SUR-ENG-QAC-00-02266 | 2021-12-12 | 1400/09/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDEC-000-QC-PR-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2290-294991 | 2021-11-28 | 1400/09/07 | 2021-12-15 | 1400/09/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0103 | 2021-09-20 | 1400/06/29 |  |  |  | BK-SUR-ENG-QAC-00-01584 | 2021-09-22 | 1400/06/31 | CM-C2 | [6 empty] | 1400-2294-210031 | 2021-09-23 | 1400/07/01 | 2021-09-26 | 1400/07/04 | AP | [10 empty] | D01 | AFD | T-0267 | 2021-11-22 | 1400/09/01 |  |  |  | BK-SUR-ENG-QAC-00-02266 | 2021-12-12 | 1400/09/21 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDEC-000-QC-PR-0006_D00 | [5 empty] | 1400-2290-294991 | 2021-11-28 | 1400/09/07 | 2021-12-15 | 1400/09/24 | AP
1 | 2 | 0 | 15 | 3 | 10 | 0 | 1.2.15.3.10 | Electrical
1 | 2 | 0 | 15 | 3 | 10 | 1 | 1.2.15.3.10.1 | ITP For Electrical Installation | BK-GNRAL-PEDCO-000-QC-PR-0010 | BK-GNRAL-PEDCO-000-QC-PR-0010 | BK | GNRAL | PEDCO | 000 | QC | PR | 0010 | F0Z-707337 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | SUB-Surface DEVELOPMENT
2 | 1 | 0 | 0 | 0 | 0 | 0 | 2.1 | Sub-Surface Common Docs
2 | 1 | 0 | 1 | 0 | 0 | 0 | 2.1.1 | Basic Design Endorsement
2 | 1 | 0 | 1 | 0 | 0 | 1 | 2.1.1.1 | Endorsement Report For Basic Design & Scope of Work | BK-SSGRL-PEDCO-110-GE-RT-0001 | BK-SSGRL-PEDCO-110-GE-RT-0001 | [7 empty] | - | [43 empty] | Deleted | 2021-07-31 | 0 |  | B00 | IFC | T-0023 | 2021-07-31 | 1400/05/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-176098 | 2021-08-28 | 1400/06/06 | 2021-09-07 | 1400/06/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | B00-Reject |  | B00 | IFC | T-0023 | 2021-07-31 | 1400/05/09 | [13 empty] | 1400-2294-176098 | 2021-08-28 | 1400/06/06 | 2021-09-07 | 1400/06/16 | CM | [8 empty] | B00-Reject
2 | 1 | 0 | 2 | 0 | 0 | 0 | 2.1.2 | Value Engineering
2 | 1 | 0 | 2 | 0 | 0 | 1 | 2.1.2.1 | Value Engineering Study Report | BK-SSGRL-PEDCO-110-GE-RT-0002 | BK-SSGRL-PEDCO-110-GE-RT-0002 | BK | SSGRL | PEDCO | 110 | GE | RT | 0002 | F0Z-707338 | AFD | IFC | 2022-02-15 | 2022-03-10 | 2022-03-15 | 23 | 5 | 28 | IFA | 2022-04-24 | 2022-05-21 | 2022-05-23 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-01 | 0 |  | D01 | IFA | T-0785 | 2022-04-10 | 1400/01/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-SSGRL-PEDCO-110-GE-RT-0002-D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-68426 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-GE-RT-0002-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0531 | 2022-02-01 | 1400/11/12 |  |  |  | BK-SUR-ENG-PCS-00-03282 | 2022-03-02 | 1400/12/11 | CM-C2 | [6 empty] | 1400-2294-443284 | 2022-03-10 | 1400/12/19 | 2022-03-15 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0785 | 2022-04-10 | 1400/01/21 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-GE-RT-0002-D00 | [5 empty] | 1401-2294-68426 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-GE-RT-0002-D00
2 | 1 | 0 | 2 | 0 | 0 | 2 | 2.1.2.2 | HAZID Report For WHF & Flow lines | BK-SSGRL-PEDCO-110-GE-RT-0003 | BK-SSGRL-PEDCO-110-GE-RT-0003 | BK | SSGRL | PEDCO | 110 | GE | RT | 0003 | F0Z-707339 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 2 | 0 | 0 | 3 | 2.1.2.3 | HAZOP Report For Binak B/C Manifold Extension | BK-SSGRL-PEDCO-110-GE-RT-0004 | BK-SSGRL-PEDCO-110-GE-RT-0004 | BK | SSGRL | PEDCO | 110 | GE | RT | 0004 | F0Z-707340 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 2 | 0 | 0 | 4 | 2.1.2.4 | SIL Report For Binak B/C Manifold Extension | BK-SSGRL-PEDCO-110-GE-RT-0005 | BK-SSGRL-PEDCO-110-GE-RT-0005 | BK | SSGRL | PEDCO | 110 | GE | RT | 0005 | F0Z-707341 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 3 | 0 | 0 | 0 | 2.1.3 | Process
2 | 1 | 0 | 3 | 0 | 1 | 0 | 2.1.3.1 | Philosophy
2 | 1 | 0 | 3 | 0 | 1 | 1 | 2.1.3.1.1 | Drainage Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0001 | BK-SSGRL-PEDCO-110-PR-PH-0001 | BK | SSGRL | PEDCO | 110 | PR | PH | 0001 | F0Z-707342 | AFD | IFC | 2022-04-09 | 2022-05-07 | 2022-05-09 | 28 | 2 | 30 | AFD | 2022-05-24 | 0 | 0 | -44705 | 0 | -44705 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-26 | 2022-05-10 |  | D01 | AFD | T-0927 | 2022-05-10 | 1401/02/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PH-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0746 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-PCS-01-03956 | 2022-04-17 | 1401/01/28 | CM-C2 | [6 empty] | 1401-2294-49820 | 2022-05-07 | 1401/02/17 | 2022-05-09 | 1401/02/19 | AP | [10 empty] | D01 | AFD | T-0927 | 2022-05-10 | 1401/02/20 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PH-0001_D00
2 | 1 | 0 | 3 | 0 | 1 | 2 | 2.1.3.1.2 | Control Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0002 | BK-SSGRL-PEDCO-110-PR-PH-0002 | BK | SSGRL | PEDCO | 110 | PR | PH | 0002 | F0Z-707343 | AFD | IFC | 2022-05-23 | 0 | 0 | -44704 | 0 | -44704 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-09 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19
2 | 1 | 0 | 3 | 0 | 1 | 3 | 2.1.3.1.3 | Flare,Blow Down And Relief Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0003 | BK-SSGRL-PEDCO-110-PR-PH-0003 | BK | SSGRL | PEDCO | 110 | PR | PH | 0003 | F0Z-707344 | AFD | IFC | 2022-04-09 | 2022-05-07 | 2022-05-09 | 28 | 2 | 30 | AFD | 2022-05-24 | 0 | 0 | -44705 | 0 | -44705 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-26 | 2022-05-10 |  | D01 | AFD | T-0927 | 2022-05-10 | 1401/02/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PH-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0746 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-PCS-01-03956 | 2022-04-17 | 1401/01/28 | CM-C2 | [6 empty] | 1401-2294-49820 | 2022-05-07 | 1401/02/17 | 2022-05-09 | 1401/02/19 | AP | [10 empty] | D01 | AFD | T-0927 | 2022-05-10 | 1401/02/20 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PH-0003_D00
2 | 1 | 0 | 3 | 0 | 1 | 4 | 2.1.3.1.4 | Isolation Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0004 | BK-SSGRL-PEDCO-110-PR-PH-0004 | BK | SSGRL | PEDCO | 110 | PR | PH | 0004 | F0Z-707345 | AFD | IFC | 2021-12-05 | 0 | 0 | -44535 | 0 | -44535 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-21 | 0 |  | D00 | IFC | T-0262 | 2021-11-21 | 1400/08/30 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02227 | 2021-12-07 | 1400/09/16 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0262 | 2021-11-21 | 1400/08/30 |  |  |  | BK-SUR-ENG-PCS-00-02227 | 2021-12-07 | 1400/09/16 | CM-C3
2 | 1 | 0 | 3 | 0 | 1 | 5 | 2.1.3.1.5 | ESD Philosophy | BK-SSGRL-PEDCO-110-PR-PH-0005 | BK-SSGRL-PEDCO-110-PR-PH-0005 | BK | SSGRL | PEDCO | 110 | PR | PH | 0005 | F0Z-707346 | AFD | IFC | 2022-05-23 | 0 | 0 | -44704 | 0 | -44704 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-09 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19
2 | 1 | 0 | 3 | 0 | 2 | 0 | 2.1.3.2 | Drawing/Diagram
2 | 1 | 0 | 3 | 0 | 2 | 1 | 2.1.3.2.1 | Symbol & Legend For PFD and P&ID | BK-SSGRL-PEDCO-110-PR-PI-0001 | BK-SSGRL-PEDCO-110-PR-PI-0001 | BK | SSGRL | PEDCO | 110 | PR | PI | 0001 | F2A-707349 | AFC | IFC | 44513 | 44509 | 44516 | -4 | 7 | 3 | IFA | 44634 | 44679 | 44682 | 45 | 3 | 48 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-30 | 0 |  | D01 | IFA | T-0653 | 2022-02-28 | 1400/12/09 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PR-PI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0194 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-PCS-00-02022 | 2021-11-17 | 1400/08/26 | CM-C3 | [6 empty] | 1400-2294-269245 | 2021-11-09 | 1400/08/18 | 2021-11-16 | 1400/08/25 | CM | [10 empty] | D01 | IFA | T-0653 | 2022-02-28 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PR-PI-0001_D00
2 | 1 | 0 | 3 | 0 | 3 | 0 | 2.1.3.3 | List
2 | 1 | 0 | 3 | 0 | 3 | 1 | 2.1.3.3.1 | Consumption List | BK-SSGRL-PEDCO-110-PR-LI-0001 | BK-SSGRL-PEDCO-110-PR-LI-0001 | BK | SSGRL | PEDCO | 110 | PR | LI | 0001 | F0Z-707350 | AFC | IFC | 44629 | 44632 | 44634 | 3 | 2 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-23 | 0 |  | D00 | IFC | T-0628 | 2022-02-23 | 1400/12/04 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03421 | 2022-03-09 | 1400/12/18 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445285 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0628 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-PCS-00-03421 | 2022-03-09 | 1400/12/18 | CM-C2 | [6 empty] | 1400-2294-445285 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/24 | CM
2 | 1 | 0 | 4 | 0 | 0 | 0 | 2.1.4 | Mechanical
2 | 1 | 0 | 4 | 0 | 1 | 0 | 2.1.4.1 | Data Sheets
2 | 1 | 0 | 4 | 0 | 1 | 1 | 2.1.4.1.1 | Data Sheets For FUEL Oil Storage Drum of Well Pads | BK-SSGRL-PEDCO-110-ME-DT-0001 | BK-SSGRL-PEDCO-110-ME-DT-0001 | BK | SSGRL | PEDCO | 110 | ME | DT | 0001 | F0Z-707351 | AFC | IFC | 2022-01-30 | 2022-02-03 | 2022-02-13 | 4 | 10 | 14 | IFA | 2022-04-23 | 2022-04-29 | 2022-05-01 | 6 | 2 | 8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-16 | 0 |  | D01 | IFA | T-0790 | 2022-04-09 | 1401/01/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43245 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-ME-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0464 | 2022-01-16 | 1400/10/26 | [13 empty] | 1400-2294-395075 | 2022-02-03 | 1400/11/14 | 2022-02-13 | 1400/11/24 | CM | [10 empty] | D01 | IFA | T-0790 | 2022-04-09 | 1401/01/20 | [13 empty] | 1401-2294-43245 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-ME-DT-0001_D00
2 | 1 | 0 | 4 | 0 | 1 | 2 | 2.1.4.1.2 | Data Sheets For Potable Water Tank of Well Pads | BK-SSGRL-PEDCO-110-ME-DT-0002 | BK-SSGRL-PEDCO-110-ME-DT-0002 | BK | SSGRL | PEDCO | 110 | ME | DT | 0002 | F0Z-707352 | AFC | IFC | 2022-02-23 | 2022-03-01 | 2022-03-05 | 6 | 4 | 10 | IFA | 2022-05-04 | 2022-05-09 | 2022-05-22 | 5 | 13 | 18 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-09 | 0 |  | D01 | IFA | T-0851 | 2022-04-20 | 1401/01/31 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-04152 | 2022-05-07 | 1401/02/17 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-ME-DT-0002-D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54998 | 2022-05-09 | 1401/02/19 | 2022-05-22 | 1401/03/01 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-ME-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0568 | 2022-02-09 | 1400/11/20 |  |  |  | BK-SUR-ENG-MEC-00-03304 | 2022-03-02 | 1400/12/11 | CM-C3 | [6 empty] | 1400-2294-430775 | 2022-03-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | CM | [10 empty] | D01 | IFA | T-0851 | 2022-04-20 | 1401/01/31 |  |  |  | BK-SUR-ENG-MEC-01-04152 | 2022-05-07 | 1401/02/17 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-ME-DT-0002-D00 | [5 empty] | 1401-2294-54998 | 2022-05-09 | 1401/02/19 | 2022-05-22 | 1401/03/01 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-ME-DT-0002_D00
2 | 1 | 0 | 5 | 0 | 0 | 0 | 2.1.5 | Piping
2 | 1 | 0 | 5 | 0 | 1 | 0 | 2.1.5.1 | Specification
2 | 1 | 0 | 5 | 0 | 1 | 1 | 2.1.5.1.1 | Piping Material Specification | BK-SSGRL-PEDCO-110-PI-SP-0001 | BK-SSGRL-PEDCO-110-PI-SP-0001 | BK | SSGRL | PEDCO | 110 | PI | SP | 0001 | F0Z-707353 | AFD | IFC | 44542 | 44552 | 44556 | 10 | 4 | 14 | IFA | 44664 | 0 | 0 | -44664 | 0 | -44664 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-28 | 0 |  | D01 | IFA | T-0766 | 2022-03-30 | 1401/01/10 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-03917 | 2022-04-16 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-SP-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-SP-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0278 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PIP-00-02246 | 2021-12-11 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-331524 | 2021-12-22 | 1400/10/01 | 2021-12-26 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0766 | 2022-03-30 | 1401/01/10 |  |  |  | BK-SUR-ENG-PIP-01-03917 | 2022-04-16 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-SP-0001_D00 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-SP-0001_D00
2 | 1 | 0 | 5 | 0 | 2 | 0 | 2.1.5.2 | Data Sheets
2 | 1 | 0 | 5 | 0 | 2 | 1 | 2.1.5.2.1 | Data Sheets For Stone Trap | BK-SSGRL-PEDCO-110-PI-DT-0001 | BK-SSGRL-PEDCO-110-PI-DT-0001 | BK | SSGRL | PEDCO | 110 | PI | DT | 0001 | F0Z-707354 | AFC | IFC | 44571 | 44564 | 44569 | -7 | 5 | -2 | IFA | 44670 | 44680 | 44695 | 10 | 15 | 25 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-27 | 0 |  | D01 | IFA | T-0777 | 2022-04-05 | 1401/01/16 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-03984 | 2022-04-18 | 1401/01/29 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-43242 | 2022-04-29 | 1401/02/09 | 2022-05-14 | 1401/02/24 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0388 | 2021-12-27 | 1400/10/06 |  |  |  | BK-SUR-ENG-PIP-00-02554 | 2022-01-03 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-348122 | 2022-01-03 | 1400/10/13 | 2022-01-08 | 1400/10/18 | CM | [10 empty] | D01 | IFA | T-0777 | 2022-04-05 | 1401/01/16 |  |  |  | BK-SUR-ENG-PIP-01-03984 | 2022-04-18 | 1401/01/29 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-DT-0001_D00 | [5 empty] | 1400-2294-43242 | 2022-04-29 | 1401/02/09 | 2022-05-14 | 1401/02/24 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-DT-0001_D00
2 | 1 | 0 | 5 | 0 | 3 | 0 | 2.1.5.3 | Drawing/Diagram
2 | 1 | 0 | 5 | 0 | 3 | 1 | 2.1.5.3.1 | Standard Pipe Support Drawings | BK-SSGRL-PEDCO-110-PI-DW-0001 | BK-SSGRL-PEDCO-110-PI-DW-0001 | BK | SSGRL | PEDCO | 110 | PI | DW | 0001 | F1L-707355 | IFI | IFI | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 2022-02-19 |  | D00 | IFI | T-0605 | 2022-02-19 | 1400/11/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443258 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0605 | 2022-02-19 | 1400/11/30 | [13 empty] | 1400-2294-443258 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM
2 | 1 | 0 | 5 | 0 | 3 | 2 | 2.1.5.3.2 | Piping Assembly Drawing | BK-SSGRL-PEDCO-110-PI-DW-0002 | BK-SSGRL-PEDCO-110-PI-DW-0002 | BK | SSGRL | PEDCO | 110 | PI | DW | 0002 | F1L-707356 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 5 | 0 | 3 | 3 | 2.1.5.3.3 | Piping Hydrostatic Test Diagram - Sub Surface | BK-SSGRL-PEDCO-110-PI-DW-0003 | BK-SSGRL-PEDCO-110-PI-DW-0003 | BK | SSGRL | PEDCO | 110 | PI | DW | 0003 | F2L-707357 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 5 | 0 | 4 | 0 | 2.1.5.4 | Calculation
2 | 1 | 0 | 5 | 0 | 4 | 1 | 2.1.5.4.1 | Piping Wall Thickness Calculation | BK-SSGRL-PEDCO-110-PI-CN-0001 | BK-SSGRL-PEDCO-110-PI-CN-0001 | BK | SSGRL | PEDCO | 110 | PI | CN | 0001 | F0Z-707358 | AFD | IFC | 44542 | 44552 | 44556 | 10 | 4 | 14 | IFA | 44664 | 0 | 0 | -44664 | 0 | -44664 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-28 | 0 |  | D01 | IFA | T-0766 | 2022-03-30 | 1401/01/10 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-03917 | 2022-04-16 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0278 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PIP-00-02246 | 2021-12-11 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-331524 | 2021-12-22 | 1400/10/01 | 2021-12-26 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0766 | 2022-03-30 | 1401/01/10 |  |  |  | BK-SUR-ENG-PIP-01-03917 | 2022-04-16 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-CN-0001_D00 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-CN-0001_D00
2 | 1 | 0 | 5 | 0 | 5 | 0 | 2.1.5.5 | Report
2 | 1 | 0 | 5 | 0 | 5 | 1 | 2.1.5.5.1 | Piping Corrosion Study & Material Selection Report | BK-SSGRL-PEDCO-110-PI-RT-0001 | BK-SSGRL-PEDCO-110-PI-RT-0001 | BK | SSGRL | PEDCO | 110 | PI | RT | 0001 | F0Z-707359 | AFD | IFC | 44542 | 44552 | 44556 | 10 | 4 | 14 | IFA | 44664 | 0 | 0 | -44664 | 0 | -44664 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-28 | 0 |  | D01 | IFA | T-0766 | 2022-03-30 | 1401/01/10 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-03917 | 2022-04-16 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0278 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PIP-00-02322 | 2021-12-18 | 1400/09/27 | CM-C2 | [6 empty] | 1400-2294-331524 | 2021-12-22 | 1400/10/01 | 2021-12-26 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0766 | 2022-03-30 | 1401/01/10 |  |  |  | BK-SUR-ENG-PIP-01-03917 | 2022-04-16 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PI-RT-0001_D00 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-PI-RT-0001_D00
2 | 1 | 0 | 6 | 0 | 0 | 0 | 2.1.6 | Pipeline & Flow line
2 | 1 | 0 | 6 | 0 | 1 | 0 | 2.1.6.1
2 | 1 | 0 | 6 | 0 | 1 | 1 | 2.1.6.1.1 | Pipeline Material Specification | BK-SSGRL-PEDCO-110-PL-SP-0001 | BK-SSGRL-PEDCO-110-PL-SP-0001 | BK | SSGRL | PEDCO | 110 | PL | SP | 0001 | F0Z-707360 | AFD | IFC | 44510 | 44516 | 44521 | 6 | 5 | 11 | IFA | 44548 | 0 | 0 | -44548 | 0 | -44548 | IFA | 44719 | 0 | 0 | -44719 | 0 | -44719 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-27 | 0 |  | D02 | IFA | T-0997 | 2022-05-24 | 1401/03/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0190 | 2021-10-27 | 1400/08/05 |  |  |  | BK-SUR-ENG-PPL-00-01931 | 2021-11-07 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-279110 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | CM | [10 empty] | D01 | IFA | T-0291 | 2021-12-04 | 1400/09/13 |  |  |  | BK-SUR-ENG-PPL-00-02462 | 2021-12-27 | 1400/10/06 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D00 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D00 | [9 empty] | D02 | IFA | T-0997 | 2022-05-24 | 1401/03/03 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D01 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D01
2 | 1 | 0 | 6 | 0 | 2 | 0 | 2.1.6.2 | Drawing/Diagram
2 | 1 | 0 | 6 | 0 | 2 | 1 | 2.1.6.2.1 | Pipeline Standard Support Drawings | BK-SSGRL-PEDCO-110-PL-DW-0001 | BK-SSGRL-PEDCO-110-PL-DW-0001 | BK | SSGRL | PEDCO | 110 | PL | DW | 0001 | F2L-707361 | IFI | IFI | 2021-08-10 | 2021-08-04 | 0 | -6 | -44412 | -44418 | IFI | 2021-11-29 | 2021-11-24 | 2021-11-27 | -5 | 3 | -2 | IFI | 2022-01-19 | 2022-01-12 | 2022-01-15 | -7 | 3 | -4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-27 | 2022-01-05 |  | D02 | IFI | T-0432 | 2022-01-05 | 1400/10/15 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02648 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-DW-0001-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-362222 | 2022-01-12 | 1400/10/22 | 2022-01-15 | 1400/10/25 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-DW-0001-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0013 | 2021-07-27 | 1400/05/05 |  |  |  | BK-SUR-ENG-PPL-00-01270 | 2021-08-07 | 1400/05/16 | CM-C3 | [6 empty] | 1400/2294/153763 | 2021-08-04 | 1400/05/13 |  |  | CM | [10 empty] | D01 | IFI | T-0247 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PPL-00-02073 | 2021-11-22 | 1400/09/01 | CM-C2 | PEDCO-CRS-D00-BK-SSGRL-PEDCO-110-PL-DW-0001-D00 | [5 empty] | 1400-2294-290695 | 2021-11-24 | 1400/09/03 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-D00-BK-SSGRL-PEDCO-110-PL-DW-0001-D00 | [9 empty] | D02 | IFI | T-0432 | 2022-01-05 | 1400/10/15 |  |  |  | BK-SUR-ENG-PPL-00-02648 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-DW-0001-D01 | [5 empty] | 1400-2294-362222 | 2022-01-12 | 1400/10/22 | 2022-01-15 | 1400/10/25 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-DW-0001-D01
2 | 1 | 0 | 6 | 0 | 2 | 2 | 2.1.6.2.2 | Pipeline Hydrostatic Test Diagram - Sub Surface | BK-SSGRL-PEDCO-110-PL-DG-0001 | BK-SSGRL-PEDCO-110-PL-DG-0001 | BK | SSGRL | PEDCO | 110 | PL | DG | 0001 | F2L-707362 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 6 | 0 | 3 | 0 | 2.1.6.3 | Calculation
2 | 1 | 0 | 6 | 0 | 3 | 1 | 2.1.6.3.1 | Pipeline Wall Thickness Calculation | BK-SSGRL-PEDCO-110-PL-CN-0001 | BK-SSGRL-PEDCO-110-PL-CN-0001 | BK | SSGRL | PEDCO | 110 | PL | CN | 0001 | F0Z-707363 | AFD | IFC | 44510 | 44516 | 44521 | 6 | 5 | 11 | IFA | 44548 | 0 | 0 | -44548 | 0 | -44548 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-27 | 0 |  | D01 | IFA | T-0291 | 2021-12-04 | 1400/09/13 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02462 | 2021-12-27 | 1400/10/06 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0190 | 2021-10-27 | 1400/08/05 |  |  |  | BK-SUR-ENG-PPL-00-01931 | 2021-11-07 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-279110 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | CM | [10 empty] | D01 | IFA | T-0291 | 2021-12-04 | 1400/09/13 |  |  |  | BK-SUR-ENG-PPL-00-02462 | 2021-12-27 | 1400/10/06 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D00 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D00
2 | 1 | 0 | 6 | 0 | 4 | 0 | 2.1.6.4 | Report
2 | 1 | 0 | 6 | 0 | 4 | 1 | 2.1.6.4.1 | Pipeline Corrosion Study & Material Selection Report | BK-SSGRL-PEDCO-110-PL-RT-0001 | BK-SSGRL-PEDCO-110-PL-RT-0001 | BK | SSGRL | PEDCO | 110 | PL | RT | 0001 | F0Z-707364 | AFD | IFC | 44510 | 44516 | 44521 | 6 | 5 | 11 | IFA | 44548 | 0 | 0 | -44548 | 0 | -44548 | IFA | 44634 | 44636 | 44652 | 2 | 16 | 18 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-27 | 0 |  | D02 | IFA | T-0658 | 2022-02-28 | 1400/12/09 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-03447 | 2022-03-12 | 1400/12/21 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-453303 | 2022-03-16 | 1400/12/25 | 2022-04-01 | 1401/01/14 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0190 | 2021-10-27 | 1400/08/05 |  |  |  | BK-SUR-ENG-PPL-00-02059 | 2021-11-21 | 1400/08/30 | CM-C3 | [6 empty] | 1400-2294-279110 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | CM | [10 empty] | D01 | IFA | T-0291 | 2021-12-04 | 1400/09/13 |  |  |  | BK-SUR-ENG-PPL-00-02462 | 2021-12-27 | 1400/10/06 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001-D00 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001-D00 | [9 empty] | D02 | IFA | T-0658 | 2022-02-28 | 1400/12/09 |  |  |  | BK-SUR-ENG-PPL-00-03447 | 2022-03-12 | 1400/12/21 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D01 | [5 empty] | 1400-2294-453303 | 2022-03-16 | 1400/12/25 | 2022-04-01 | 1401/01/14 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D01
2 | 1 | 0 | 7 | 0 | 0 | 0 | 2.1.7 | Control & Instrumentation
2 | 1 | 0 | 7 | 0 | 1 | 0 | 2.1.7.1 | Basis/Criteria
2 | 1 | 0 | 7 | 0 | 1 | 1 | 2.1.7.1.1 | Instrument & Control System Design Criteria | BK-SSGRL-PEDCO-110-IN-DC-0002 | BK-SSGRL-PEDCO-110-IN-DC-0002 | BK | SSGRL | PEDCO | 110 | IN | DC | 0002 | F0Z-707366 | AFD | IFC | 2022-01-17 | 2022-02-16 | 2022-02-21 | 30 | 5 | 35 | IFA | 2022-05-31 | 0 | 0 | -44712 | 0 | -44712 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-03 | 0 |  | D01 | IFA | T-0968 | 2022-05-17 | 1401/02/27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DC-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DC-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0420 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-INS-00-02625 | 2022-01-10 | 1400/10/20 | CM-C3 | [6 empty] | 1400-2294-412682 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0968 | 2022-05-17 | 1401/02/27 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DC-0002_D00 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DC-0002_D00
2 | 1 | 0 | 7 | 0 | 1 | 2 | 2.1.7.1.2 | Fire & Gas Detection Design Criteria | BK-SSGRL-PEDCO-110-IN-DC-0001 | BK-SSGRL-PEDCO-110-IN-DC-0001 | BK | SSGRL | PEDCO | 110 | IN | DC | 0001 | F0Z-707365 | AFD | IFC | 2021-08-28 | 2021-09-15 | 2021-09-14 | 18 | -1 | 17 | IFA | 2021-11-03 | 2021-10-29 | 2021-11-03 | -5 | 5 | 0 | AFD | 2022-01-15 | 2022-01-26 | 2022-01-29 | 11 | 3 | 14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-14 | 2022-01-01 |  | D02 | AFD | T-0414 | 2022-01-01 | 1400/10/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DC-0001-D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-382426 | 2022-01-26 | 1400/11/06 | 2022-01-29 | 1400/11/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0045 | 2021-08-14 | 1400/05/23 | [13 empty] | 1400-2294-193915 | 2021-09-15 | 1400/06/20 | 2021-09-14 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0178 | 2021-10-20 | 1400/07/28 |  |  |  | BK-SUR-ENG-INS-00-01906 | 2021-11-03 | 1400/08/12 | CM-C3 | [6 empty] | 1400-2294-251691 | 2021-10-29 | 1400/08/07 | 2021-11-03 | 1400/08/12 | AP | NISOC-CRS-BK-GNRAL-PEDCO-000-IN-DS-0001-D00 | [9 empty] | D02 | AFD | T-0414 | 2022-01-01 | 1400/10/11 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DC-0001-D01 | [5 empty] | 1400-2294-382426 | 2022-01-26 | 1400/11/06 | 2022-01-29 | 1400/11/09 | AP
2 | 1 | 0 | 7 | 0 | 1 | 3 | 2.1.7.1.3 | Instrument & Control System Basis of Design | BK-SSGRL-PEDCO-110-IN-DB-0001 | BK-SSGRL-PEDCO-110-IN-DB-0001 | [7 empty] | - | [43 empty] | Deleted | 2021-08-22 | 0 |  | D00 | IFC | T-0054 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-200192 | 2021-09-15 | 1400/06/24 | 2021-09-20 | 1400/06/29 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0054 | 2021-08-22 | 1400/05/31 | [13 empty] | 1400-2294-200192 | 2021-09-15 | 1400/06/24 | 2021-09-20 | 1400/06/29 | CM
2 | 1 | 0 | 7 | 0 | 2 | 0 | 2.1.7.2 | Specification
2 | 1 | 0 | 7 | 0 | 2 | 1 | 2.1.7.2.1 | Specification For WHCP/HPU | BK-SSGRL-PEDCO-110-IN-SP-0001 | BK-SSGRL-PEDCO-110-IN-SP-0001 | BK | SSGRL | PEDCO | 110 | IN | SP | 0001 | F9J-707367 | AFD | IFC | 44430 | 44457 | 44453 | 27 | -4 | 23 | IFA | 44493 | 44560 | 44563 | 67 | 3 | 70 | IFA | 44585 | 44590 | 44591 | 5 | 1 | 6 | AFD | 44661 | 44668 | 44676 | 7 | 8 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-08 | 2022-03-27 |  | D03 | AFD | T-0748 | 2022-03-27 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03940 | 2022-04-16 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-SP-0001_D02 | 0 | 0 | 0 | 0 | 0 | 14014-2294-25743 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0034 | 2021-08-08 | 1400/05/17 |  |  |  | BK-SUR-ENG-INS-00-01375 | 2021-08-22 | 1400/06/31 | CM-C3 | [6 empty] | 1400-2294-193985 | 2021-09-18 | 1400/06/20 | 2021-09-14 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0143 | 2021-10-10 | 1400/07/18 |  |  |  | BK-SUR-ENG-INS-00-01846 | 2021-10-26 | 1400/08/04 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-SP-0001_D00 | [5 empty] | 1400-2294-320796 | 2021-12-17 | 1400/09/26 | 2022-01-02 | 1400/10/12 | RJ | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-SP-0001_D00 | 1400-2294-342129 | 2021-12-30 | 1400/10/09 |  |  | CM |  |  |  | D02 | IFA | T-0444 | 2022-01-10 | 1400/10/20 |  |  |  | BK-SUR-ENG-INS-00-02815 | 2022-01-25 | 1400/11/05 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-SP-0001_D01 | [5 empty] | 1400-2294-385430 | 2022-01-29 | 1400/11/09 | 2022-01-30 | 1400/11/10 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-SP-0001_D01 | [9 empty] | D03 | AFD | T-0748 | 2022-03-27 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03940 | 2022-04-16 | 1401/01/27 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-SP-0001_D02 | [5 empty] | 14014-2294-25743 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | AP
2 | 1 | 0 | 7 | 0 | 3 | 0 | 2.1.7.3 | Data Sheets
2 | 1 | 0 | 7 | 0 | 3 | 1 | 2.1.7.3.1 | Data Sheets For WHCP/HPU - Wellheads | BK-SSGRL-PEDCO-110-IN-DT-0001 | BK-SSGRL-PEDCO-110-IN-DT-0001 | BK | SSGRL | PEDCO | 110 | IN | DT | 0001 | F9Z-707368 | AFC | IFC | 2021-09-05 | 2021-09-15 | 2021-09-20 | 10 | 5 | 15 | IFA | 2021-11-23 | 2021-11-21 | 2021-11-27 | -2 | 6 | 4 | IFA | 2022-01-04 | 2022-01-06 | 2022-01-08 | 2 | 2 | 4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 0 |  | D02 | IFA | T-0374 | 2021-12-21 | 1400/09/30 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02519 | 2022-01-02 | 1400/10/11 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-352435 | 2022-01-06 | 1400/10/16 | 2022-01-08 | 1400/10/18 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0054 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-INS-00-01426 | 2021-08-29 | 1400/06/07 | CM-C3 | [6 empty] | 1400-2294-200192 | 2021-09-15 | 1400/06/24 | 2021-09-20 | 1400/06/29 | CM | [10 empty] | D01 | IFA | T-0218 | 2021-11-09 | 1400/08/18 |  |  |  | BK-SUR-ENG-INS-00-02067 | 2021-11-21 | 1400/08/30 | C4-RJ | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D00 | [5 empty] | 1400-2294-283482 | 2021-11-21 | 1400/08/30 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D00 | [9 empty] | D02 | IFA | T-0374 | 2021-12-21 | 1400/09/30 |  |  |  | BK-SUR-ENG-INS-00-02519 | 2022-01-02 | 1400/10/11 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D01 | [5 empty] | 1400-2294-352435 | 2022-01-06 | 1400/10/16 | 2022-01-08 | 1400/10/18 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D01
2 | 1 | 0 | 7 | 0 | 3 | 2 | 2.1.7.3.2 | Data Sheets For Pressure Gauge - Wellheads | BK-SSGRL-PEDCO-110-IN-DT-0002 | BK-SSGRL-PEDCO-110-IN-DT-0002 | BK | SSGRL | PEDCO | 110 | IN | DT | 0002 | F9Z-707369 | AFC | IFC | 2021-12-21 | 2021-12-30 | 2022-01-02 | 9 | 3 | 12 | IFA | 2022-03-16 | 2022-03-15 | 2022-03-25 | -1 | 10 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-07 | 0 |  | D01 | IFA | T-0660 | 2022-03-02 | 1400/12/11 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03646 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-449418 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0308 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-INS-00-02404 | 2021-12-22 | 1400/10/01 | CM-C3 | [6 empty] | 1400-2294-342119 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0660 | 2022-03-02 | 1400/12/11 |  |  |  | BK-SUR-ENG-INS-00-03646 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0002_D00 | [5 empty] | 1400-2294-449418 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0002_D00
2 | 1 | 0 | 7 | 0 | 3 | 3 | 2.1.7.3.3 | Data Sheets For Temperature Gauge - Wellheads | BK-SSGRL-PEDCO-110-IN-DT-0003 | BK-SSGRL-PEDCO-110-IN-DT-0003 | BK | SSGRL | PEDCO | 110 | IN | DT | 0003 | F9Z-707370 | AFC | IFC | 2021-12-21 | 2021-12-30 | 2022-01-02 | 9 | 3 | 12 | IFA | 2022-03-16 | 2022-03-15 | 2022-03-25 | -1 | 10 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-07 | 0 |  | D01 | IFA | T-0660 | 2022-03-02 | 1400/12/11 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03646 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-449418 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0308 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-INS-00-02404 | 2021-12-22 | 1400/10/01 | CM-C3 | [6 empty] | 1400-2294-342119 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0660 | 2022-03-02 | 1400/12/11 |  |  |  | BK-SUR-ENG-INS-00-03646 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0003_D00 | [5 empty] | 1400-2294-449418 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0003_D00
2 | 1 | 0 | 7 | 0 | 4 | 0 | 2.1.7.4 | Drawing/Diagram
2 | 1 | 0 | 7 | 0 | 4 | 1 | 2.1.7.4.1 | Instrument Hook-up Diagram - Wellheads | BK-SSGRL-PEDCO-110-IN-DG-0001 | BK-SSGRL-PEDCO-110-IN-DG-0001 | BK | SSGRL | PEDCO | 110 | IN | DG | 0001 | F2J-707371 | AFC | IFC | 2021-11-28 | 2021-11-21 | 2021-11-29 | -7 | 8 | 1 | IFA | 2022-01-02 | 2022-03-09 | 2022-03-13 | 66 | 4 | 70 | IFA | 2022-05-23 | 0 | 0 | -44704 | 0 | -44704 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-14 | 0 |  | D02 | IFA | T-0922 | 2022-05-09 | 1401/02/19 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04475 | 2022-05-29 | 1401/03/08 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0235 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02137 | 2021-11-29 | 1400/09/08 | C4-RJ | [6 empty] | 1400-2294-283471 | 2021-11-21 | 1400/08/30 | 2021-11-29 | 1400/09/08 | CM | [10 empty] | D01 | IFA | T-0364 | 2021-12-19 | 1400/09/28 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0001_D00 | [5 empty] | 1400-2294-347498 | 2021-01-03 | 1400/10/13 | 2022-01-04 | 1400/10/14 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DG-0001_D00 | 1400-2294-442076 | 2022-03-09 | 1400/12/18 | 2022-03-13 | 1400/12/22 | AP |  |  |  | D02 | IFA | T-0922 | 2022-05-09 | 1401/02/19 |  |  |  | BK-SUR-ENG-INS-01-04475 | 2022-05-29 | 1401/03/08 | CM-C2 | [12 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DG-0001_D01
2 | 1 | 0 | 7 | 0 | 4 | 2 | 2.1.7.4.2 | WHCP HYDRAULIC\PNEUMATIC DIAGRAMS-WELLHEADS | BK-SSGRL-PEDCO-110-IN-DG-0002 | BK-SSGRL-PEDCO-110-IN-DG-0002 | BK | SSGRL | PEDCO | 110 | IN | DG | 0002 | F2J-707372 | AFC | IFC | 2021-09-05 | 2021-09-15 | 2021-09-20 | 10 | 5 | 15 | IFA | 2021-11-24 | 2021-11-21 | 2021-11-27 | -3 | 6 | 3 | AFC | 2022-01-03 | 2022-01-06 | 2022-01-08 | 3 | 2 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2021-12-20 |  | D02 | AFC | T-0369 | 2021-12-20 | 1400/09/29 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02502 | 2022-01-01 | 1400/10/11 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-352438 | 2022-01-06 | 1400/10/16 | 2022-01-08 | 1400/10/18 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0054 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-INS-00-01426 | 2021-08-29 | 1400/06/07 | CM-C3 | [6 empty] | 1400-2294-200192 | 2021-09-15 | 1400/06/24 | 2021-09-20 | 1400/06/29 | CM | [10 empty] | D01 | IFA | T-0230 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-INS-00-02064 | 2021-11-21 | 1400/08/30 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0002_D00 | [5 empty] | 1400-2294-283484 | 2021-11-21 | 1400/08/30 | 2021-11-27 | 1400/09/06 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DG-0002-D00 | [9 empty] | D02 | AFC | T-0369 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-INS-00-02502 | 2022-01-01 | 1400/10/11 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0002_D01 | [5 empty] | 1400-2294-352438 | 2022-01-06 | 1400/10/16 | 2022-01-08 | 1400/10/18 | CM
2 | 1 | 0 | 7 | 0 | 5 | 0 | 2.1.7.5 | List
2 | 1 | 0 | 7 | 0 | 5 | 1 | 2.1.7.5.1 | Instrument Index For New Wells & Manifold Extension | BK-SSGRL-PEDCO-110-IN-LI-0001 | BK-SSGRL-PEDCO-110-IN-LI-0001 | BK | SSGRL | PEDCO | 110 | IN | LI | 0001 | F0Z-707373 | AFC | IFI | 44524 | 44521 | 44527 | -3 | 6 | 3 | IFA | 44636 | 0 | 0 | -44636 | 0 | -44636 | 0 | 14 | 44632 | 44632 | 44618 | 0 | 44618 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D01 | IFA | T-0666 | 2022-03-02 | 1400/12/11 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03648 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0229 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-INS-00-02062 | 2021-11-21 | 1400/08/30 | CM | [6 empty] | 1400-2294-283479 | 2021-11-21 | 1400/08/30 | 2021-11-27 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0666 | 2022-03-02 | 1400/12/11 |  |  |  | BK-SUR-ENG-INS-00-03648 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-LI-0001_D00 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-IN-LI-0001_D00 | [27 empty] | 1400-2294-445246 | 2022-03-12 | 1400/12/21 | 2022-03-12 | 1400/12/21 | AP
2 | 1 | 0 | 8 | 0 | 0 | 0 | 2.1.8 | Safety
2 | 1 | 0 | 8 | 0 | 1 | 0 | 2.1.8.1 | Basis/Criteria
2 | 1 | 0 | 8 | 0 | 1 | 1 | 2.1.8.1.1 | Active Fire Protection and Safety Concept | BK-SSGRL-PEDCO-110-SA-DC-0001 | BK-SSGRL-PEDCO-110-SA-DC-0001 | BK | SSGRL | PEDCO | 110 | SA | DC | 0001 | F0Z-707374 | AFD | IFC | 44451 | 44452 | 44457 | 1 | 5 | 6 | IFA | 44508 | 44522 | 44527 | 14 | 5 | 19 | AFD | 44550 | 44539 | 44544 | -11 | 5 | -6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-29 | 2021-12-06 |  | D02 | AFD | T-0297 | 2021-12-06 | 1400/09/15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-310955 | 2021-12-09 | 1400/09/18 | 2021-12-14 | 1400/09/23 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0070 | 2021-08-29 | 1400/06/07 | [13 empty] | 1400-2294-197171 | 2021-09-13 | 1400/06/22 | 2021-09-18 | 1400/06/27 | CM | [10 empty] | D01 | IFA | T-0184 | 2021-10-25 | 1400/08/03 | [13 empty] | 1400-2294-286876 | 2021-11-22 | 1400/09/01 | 2021-11-27 | 1400/09/06 | AP | NISOC-CRS- BK-SSGRL-PEDCO- 110-SA-DC-0001-D00 | [9 empty] | D02 | AFD | T-0297 | 2021-12-06 | 1400/09/15 | [13 empty] | 1400-2294-310955 | 2021-12-09 | 1400/09/18 | 2021-12-14 | 1400/09/23 | AP
2 | 1 | 0 | 8 | 0 | 2 | 0 | 2.1.8.2 | Data Sheets
2 | 1 | 0 | 8 | 0 | 2 | 1 | 2.1.8.2.1 | Data Sheets For Fire Fighting Equipment | BK-SSGRL-PEDCO-110-SA-DT-0001 | BK-SSGRL-PEDCO-110-SA-DT-0001 | BK | SSGRL | PEDCO | 110 | SA | DT | 0001 | F0Z-707375 | AFC | IFC | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | AFC | 2022-01-23 | 2022-01-11 | 2022-01-30 | -12 | 19 | 7 | AFC | 2022-04-20 | 2022-04-19 | 2022-04-30 | -1 | 11 | 10 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-08 | 2022-04-06 |  | D02 | AFC | T-0782 | 2022-04-06 | 1401/01/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31231 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0320 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327319 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP | [10 empty] | D01 | AFC | T-0440 | 2022-01-09 | 1400/10/19 | [13 empty] | 1400-2294-360413 | 2022-01-11 | 1400/10/21 | 2022-01-30 | 1400/11/10 | CM | [10 empty] | D02 | AFC | T-0782 | 2022-04-06 | 1401/01/17 | [13 empty] | 1401-2294-31231 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | AP
2 | 1 | 0 | 8 | 0 | 2 | 2 | 2.1.8.2.2 | Data Sheets For Safety Equipment | BK-SSGRL-PEDCO-110-SA-DT-0002 | BK-SSGRL-PEDCO-110-SA-DT-0002 | BK | SSGRL | PEDCO | 110 | SA | DT | 0002 | F0Z-707376 | AFC | IFC | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | AFC | 2022-01-23 | 2022-01-11 | 2022-01-30 | -12 | 19 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-08 | 2022-01-09 |  | D01 | AFC | T-0440 | 2022-01-09 | 1400/10/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-360413 | 2022-01-11 | 1400/10/21 | 2022-01-30 | 1400/11/10 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0320 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327319 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP | [10 empty] | D01 | AFC | T-0440 | 2022-01-09 | 1400/10/19 | [13 empty] | 1400-2294-360413 | 2022-01-11 | 1400/10/21 | 2022-01-30 | 1400/11/10 | AP
2 | 1 | 0 | 8 | 0 | 2 | 3 | 2.1.8.2.3 | Data Sheets For Safety Sign | BK-SSGRL-PEDCO-110-SA-DT-0003 | BK-SSGRL-PEDCO-110-SA-DT-0003 | BK | SSGRL | PEDCO | 110 | SA | DT | 0003 | F0Z-707377 | AFC | IFC | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | AFC | 2022-01-23 | 2022-01-11 | 2022-01-30 | -12 | 19 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-08 | 2022-01-09 |  | D01 | AFC | T-0440 | 2022-01-09 | 1400/10/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-360413 | 2022-01-11 | 1400/10/21 | 2022-01-30 | 1400/11/10 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0320 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327319 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP | [10 empty] | D01 | AFC | T-0440 | 2022-01-09 | 1400/10/19 | [13 empty] | 1400-2294-360413 | 2022-01-11 | 1400/10/21 | 2022-01-30 | 1400/11/10 | AP
2 | 1 | 0 | 9 | 0 | 0 | 0 | 2.1.9 | Electrical
2 | 1 | 0 | 9 | 0 | 1 | 0 | 2.1.9.1 | Calculation
2 | 1 | 0 | 9 | 0 | 1 | 1 | 2.1.9.1.1 | Calculation Note For Lighting System of Well Pads Switchgear Building | BK-SSGRL-PEDCO-110-EL-CN-0002 | BK-SSGRL-PEDCO-110-EL-CN-0002 | BK | SSGRL | PEDCO | 110 | EL | CN | 0002 | F0Z-707378 | AFD | IFC | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-11 | 0 |  | D00 | IFC | T-0930 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04347 | 2022-05-22 | 1401/03/01 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0930 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-ELE-01-04347 | 2022-05-22 | 1401/03/01 | CM-C2
2 | 1 | 0 | 9 | 0 | 1 | 2 | 2.1.9.1.2 | Calculation Note For Lighting System of Well Pads Security Building | BK-SSGRL-PEDCO-110-EL-CN-0003 | BK-SSGRL-PEDCO-110-EL-CN-0003 | BK | SSGRL | PEDCO | 110 | EL | CN | 0003 | F0Z-707379 | AFD | IFC | 2022-05-14 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-30 | 0 |  | D00 | IFC | T-0879 | 2022-04-30 | 1401/02/10 | T-0879 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-ELE-01-04215 | 2022-05-10 | 1401/02/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0879 | 2022-04-30 | 1401/02/10 | T-0879 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-ELE-01-04215 | 2022-05-10 | 1401/02/20 | CM-C3
2 | 1 | 0 | 9 | 0 | 1 | 3 | 2.1.9.1.3 | Calculation Note For Lighting System of Well Pads Area | BK-SSGRL-PEDCO-110-EL-CN-0004 | BK-SSGRL-PEDCO-110-EL-CN-0004 | BK | SSGRL | PEDCO | 110 | EL | CN | 0004 | F0Z-707380 | AFD | IFC | 2022-05-28 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-14 | 0 |  | D00 | IFC | T-0939 | 2022-05-14 | 1401/02/24 | T-0939 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-ELE-01-04389 | 2022-05-23 | 1401/03/02 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0939 | 2022-05-14 | 1401/02/24 | T-0939 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-ELE-01-04389 | 2022-05-23 | 1401/03/02 | CM-C2
2 | 1 | 0 | 9 | 0 | 1 | 4 | 2.1.9.1.4 | Calculation Note For Cable Sizing of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0005 | BK-SSGRL-PEDCO-110-EL-CN-0005 | BK | SSGRL | PEDCO | 110 | EL | CN | 0005 | F0Z-707381 | AFD | IFC | 2021-11-16 | 2021-11-30 | 2021-11-24 | 14 | -6 | 8 | IFA | 2021-12-22 | 2022-01-06 | 2022-01-08 | 15 | 2 | 17 | IFA | 2022-04-23 | 2022-04-19 | 2022-04-25 | -4 | 6 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-02 | 0 |  | D02 | IFA | T-0788 | 2022-04-09 | 1401/01/20 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-03999 | 2022-04-20 | 1400/01/31 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0005_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31358 | 2022-04-19 | 1401/01/30 | 2022-04-25 | 1401/02/05 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0207 | 2021-11-02 | 1400/08/11 |  |  |  | BK-SUR-ENG-ELE-00-01957 | 2021-11-09 | 1400/08/18 | C4-RJ | [6 empty] | 1400-2294-286864 | 2021-11-30 | 1400/09/01 | 2021-11-24 | 1400/09/03 | CM | [10 empty] | D01 | IFA | T-0317 | 2021-12-08 | 1400/09/17 |  |  |  | BK-SUR-ENG-ELE-00-02323 | 2021-12-18 | 1400/09/27 | C4-RJ | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0005-D00 | [5 empty] | 1400-2294-352392 | 2022-01-06 | 1400/10/16 | 2022-01-08 | 1400/10/18 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0005-D00 | [9 empty] | D02 | IFA | T-0788 | 2022-04-09 | 1401/01/20 |  |  |  | BK-SUR-ENG-ELE-01-03999 | 2022-04-20 | 1400/01/31 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0005_D01 | [5 empty] | 1401-2294-31358 | 2022-04-19 | 1401/01/30 | 2022-04-25 | 1401/02/05 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0005_D01
2 | 1 | 0 | 9 | 0 | 1 | 5 | 2.1.9.1.5 | Calculation Note For UPS System of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0006 | BK-SSGRL-PEDCO-110-EL-CN-0006 | BK | SSGRL | PEDCO | 110 | EL | CN | 0006 | F0Z-707382 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 9 | 0 | 1 | 6 | 2.1.9.1.6 | Calculation Note For Earthing & Lightning System of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0007 | BK-SSGRL-PEDCO-110-EL-CN-0007 | BK | SSGRL | PEDCO | 110 | EL | CN | 0007 | F0Z-707383 | AFD | IFC | 2022-05-15 | 0 | 0 | -44696 | 0 | -44696 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-01 | 0 |  | D00 | IFC | T-0890 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04252 | 2022-05-24 | 1401/02/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0890 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ELE-01-04252 | 2022-05-24 | 1401/02/24 | CM-C3
2 | 1 | 0 | 9 | 0 | 1 | 7 | 2.1.9.1.7 | Calculation Note For Diesel Generator Sizing of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0008 | BK-SSGRL-PEDCO-110-EL-CN-0008 | BK | SSGRL | PEDCO | 110 | EL | CN | 0008 | F0Z-707384 | AFD | IFC | 2022-02-09 | 2022-02-12 | 2022-02-21 | 3 | 9 | 12 | IFA | 2022-05-03 | 2022-05-18 | 2022-05-22 | 15 | 4 | 19 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-26 | 0 |  | D01 | IFA | T-0844 | 2022-04-19 | 1401/01/30 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04079 | 2022-04-30 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0008_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-66366 | 2022-05-18 | 1401/02/28 | 2022-05-22 | 1401/03/01 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0515 | 2022-01-26 | 1400/11/06 |  |  |  | BK-SUR-ENG-ELE-00-03005 | 2022-02-09 | 1400/11/20 | CM-C3 | [6 empty] | 1400-2294-407130 | 2022-02-12 | 1400/11/23 | 2022-02-21 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0844 | 2022-04-19 | 1401/01/30 |  |  |  | BK-SUR-ENG-ELE-01-04079 | 2022-04-30 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0008_D00 | [5 empty] | 1401-2294-66366 | 2022-05-18 | 1401/02/28 | 2022-05-22 | 1401/03/01 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0008_D00
2 | 1 | 0 | 9 | 0 | 1 | 8 | 2.1.9.1.8 | Calculation Note For DC Charger of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0009 | BK-SSGRL-PEDCO-110-EL-CN-0009 | BK | SSGRL | PEDCO | 110 | EL | CN | 0009 | F0Z-707385 | AFD | IFC | 2022-02-09 | 2022-02-12 | 2022-02-21 | 3 | 9 | 12 | IFA | 2022-03-23 | 2022-03-19 | 2022-03-27 | -4 | 8 | 4 | IFA | 2022-05-04 | 2022-05-09 | 2022-05-16 | 5 | 7 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-26 | 0 |  | D02 | IFA | T-0850 | 2022-04-20 | 1401/01/14 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04092 | 2022-04-30 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0009_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54908 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0009_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0511 | 2022-01-26 | 1400/11/06 |  |  |  | BK-SUR-ENG-ELE-00-02998 | 2022-02-08 | 1400/11/19 | CM-C2 | [6 empty] | 1400-2294-407153 | 2022-02-12 | 1400/11/23 | 2022-02-21 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0712 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-ELE-00-03642 | 2022-03-16 | 1400/12/25 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0009_D00 | [5 empty] | 1400-2294-455098 | 2022-03-19 | 1400/12/28 | 2022-03-27 | 1401/01/07 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0009_D00 | [9 empty] | D02 | IFA | T-0850 | 2022-04-20 | 1401/01/14 |  |  |  | BK-SUR-ENG-ELE-01-04092 | 2022-04-30 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0009_D01 | [5 empty] | 1401-2294-54908 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0009_D01
2 | 1 | 0 | 9 | 0 | 1 | 9 | 2.1.9.1.9 | Calculation Note For LV Capacitor Bank of Well Pads | BK-SSGRL-PEDCO-110-EL-CN-0010 | BK-SSGRL-PEDCO-110-EL-CN-0010 | BK | SSGRL | PEDCO | 110 | EL | CN | 0010 | F0Z-707386 | AFD | IFC | 2022-02-12 | 2022-02-20 | 2022-03-07 | 8 | 15 | 23 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-29 | 0 |  | D00 | IFC | T-0517 | 2022-01-29 | 1400/11/09 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03024 | 2022-02-12 | 1400/11/23 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-415826 | 2022-02-20 | 1400/12/01 | 2022-03-07 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0517 | 2022-01-29 | 1400/11/09 |  |  |  | BK-SUR-ENG-ELE-00-03024 | 2022-02-12 | 1400/11/23 | CM-C2 | [6 empty] | 1400-2294-415826 | 2022-02-20 | 1400/12/01 | 2022-03-07 | 1400/12/17 | CM
2 | 1 | 0 | 9 | 0 | 1 | 10 | 2.1.9.1.10 | Calculation Note For 11 KV Over Head Line Sag and Tension | BK-SSGRL-PEDCO-110-EL-CN-0011 | BK-SSGRL-PEDCO-110-EL-CN-0011 | BK | SSGRL | PEDCO | 110 | EL | CN | 0011 | F0Z-707387 | AFD | IFC | 2021-10-27 | 2022-01-01 | 2021-11-07 | 66 | -55 | 11 | IFA | 2022-03-21 | 2022-03-14 | 2022-03-26 | -7 | 12 | 5 | IFA | 2022-06-13 | 0 | 0 | -44725 | 0 | -44725 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-13 | 0 |  | D02 | IFA | T-1023 | 2022-05-30 | 1401/03/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0011_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0011_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0155 | 2021-10-13 | 1400/07/21 |  |  |  | BK-SUR-ENG-ELE-00-01828 | 2021-10-25 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-259348 | 2022-01-01 | 1400/08/11 | 2021-11-07 | 1400/08/16 | CM | [10 empty] | D01 | IFA | T-0687 | 2022-03-07 | 1400/12/16 |  |  |  | BK-SUR-ENG-ELE-00-03586 | 2022-03-15 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0011_D00 | [5 empty] | 1400-2294-449000 | 2022-03-14 | 1400/12/23 | 2022-03-26 | 1401/01/06 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0011_D00 | [9 empty] | D02 | IFA | T-1023 | 2022-05-30 | 1401/03/09 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0011_D01 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0011_D01
2 | 1 | 0 | 9 | 0 | 1 | 11 | 2.1.9.1.11 | Calculation Note For 33 KV Over Head Line Sag and Tension | BK-SSGRL-PEDCO-110-EL-CN-0012 | BK-SSGRL-PEDCO-110-EL-CN-0012 | BK | SSGRL | PEDCO | 110 | EL | CN | 0012 | F0Z-707388 | AFD | IFC | 2021-10-25 | 2022-01-01 | 2021-11-07 | 68 | -55 | 13 | IFA | 2022-03-21 | 2022-03-14 | 2022-03-26 | -7 | 12 | 5 | IFA | 2022-06-13 | 0 | 0 | -44725 | 0 | -44725 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-11 | 0 |  | D02 | IFA | T-1023 | 2022-05-30 | 1401/03/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0012_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0012_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0147 | 2021-10-11 | 1400/07/19 |  |  |  | BK-SUR-ENG-ELE-00-01828 | 2021-10-25 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-259367 | 2022-01-01 | 1400/08/11 | 2021-11-07 | 1400/08/16 | CM | [10 empty] | D01 | IFA | T-0687 | 2022-03-07 | 1400/12/16 |  |  |  | BK-SUR-ENG-ELE-00-03586 | 2022-03-15 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0012_D00 | [5 empty] | 1400-2294-449000 | 2022-03-14 | 1400/12/23 | 2022-03-26 | 1401/01/06 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0012_D00 | [9 empty] | D02 | IFA | T-1023 | 2022-05-30 | 1401/03/09 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0012_D01 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0012_D01
2 | 1 | 0 | 9 | 0 | 2 | 0 | 2.1.9.2 | Data Sheets
2 | 1 | 0 | 9 | 0 | 2 | 1 | 2.1.9.2.1 | Data Sheets For UPS of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0002 | BK-SSGRL-PEDCO-110-EL-DT-0002 | BK | SSGRL | PEDCO | 110 | EL | DT | 0002 | F0Z-707389 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 9 | 0 | 2 | 2 | 2.1.9.2.2 | Data Sheets For DC Charger of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0003 | BK-SSGRL-PEDCO-110-EL-DT-0003 | BK | SSGRL | PEDCO | 110 | EL | DT | 0003 | F0Z-707390 | AFC | IFC | 2022-02-12 | 2022-02-20 | 2022-03-07 | 8 | 15 | 23 | IFA | 2022-03-23 | 2022-03-19 | 2022-03-27 | -4 | 8 | 4 | IFA | 2022-05-04 | 2022-05-09 | 2022-05-16 | 5 | 7 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-29 | 0 |  | D02 | IFA | T-0850 | 2022-04-20 | 1401/01/14 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04092 | 2022-04-30 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54908 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0517 | 2022-01-29 | 1400/11/09 |  |  |  | BK-SUR-ENG-ELE-00-03024 | 2022-02-12 | 1400/11/23 | CM-C3 | [6 empty] | 1400-2294-415826 | 2022-02-20 | 1400/12/01 | 2022-03-07 | 1400/12/17 | CM | [10 empty] | D01 | IFA | T-0712 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-ELE-00-03642 | 2022-03-16 | 1400/12/25 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0003_D00 | [5 empty] | 1400-2294-455098 | 2022-03-19 | 1400/12/28 | 2022-03-27 | 1401/01/07 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0003_D00 | [9 empty] | D02 | IFA | T-0850 | 2022-04-20 | 1401/01/14 |  |  |  | BK-SUR-ENG-ELE-01-04092 | 2022-04-30 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0003_D01 | [5 empty] | 1401-2294-54908 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0003_D01
2 | 1 | 0 | 9 | 0 | 2 | 3 | 2.1.9.2.3 | Data Sheets For Diesel Generator of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0004 | BK-SSGRL-PEDCO-110-EL-DT-0004 | BK | SSGRL | PEDCO | 110 | EL | DT | 0004 | F0Z-707391 | AFC | IFC | 2021-10-04 | 2021-09-27 | 2021-10-02 | -7 | 5 | -2 | IFA | 2022-05-03 | 2022-05-18 | 2022-05-22 | 15 | 4 | 19 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-20 | 0 |  | D01 | IFA | T-0844 | 2022-04-19 | 1401/01/30 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04079 | 2022-04-30 | 1401/02/10 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-66366 | 2022-05-18 | 1401/02/28 | 2022-05-22 | 1401/03/01 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0105 | 2021-09-20 | 1400/06/29 |  |  |  | BK-SUR-ENG-ELE-00-01651 | 2021-10-02 | 1400/07/10 | CM-C2 | [6 empty] | 1400-2294-213965 | 2021-09-27 | 1400/07/05 | 2021-10-02 | 1400/07/10 | CM | [10 empty] | D01 | IFA | T-0844 | 2022-04-19 | 1401/01/30 |  |  |  | BK-SUR-ENG-ELE-01-04079 | 2022-04-30 | 1401/02/10 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0004_D00 | [5 empty] | 1401-2294-66366 | 2022-05-18 | 1401/02/28 | 2022-05-22 | 1401/03/01 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0004_D00
2 | 1 | 0 | 9 | 0 | 2 | 4 | 2.1.9.2.4 | Data Sheets For Local Control Stations (LCS) of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0005 | BK-SSGRL-PEDCO-110-EL-DT-0005 | [7 empty] | - | [43 empty] | Deleted | 2021-08-30 | 0 |  | D00 | IFC | T-0072 | 2021-08-30 | 1400/06/08 | 0 | 0 | 0 | BK-SSR-ENG-ELE-00-01506 | 2021-09-13 | 1400/06/22 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-198862 | 2021-09-14 | 1400/06/23 | 2021-09-18 | 1400/06/27 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0072 | 2021-08-30 | 1400/06/08 |  |  |  | BK-SSR-ENG-ELE-00-01506 | 2021-09-13 | 1400/06/22 | C4-RJ | [6 empty] | 1400-2294-198862 | 2021-09-14 | 1400/06/23 | 2021-09-18 | 1400/06/27 | CM
2 | 1 | 0 | 9 | 0 | 2 | 5 | 2.1.9.2.5 | Data Sheets For LV Capacitor Bank of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0006 | BK-SSGRL-PEDCO-110-EL-DT-0006 | BK | SSGRL | PEDCO | 110 | EL | DT | 0006 | F0Z-707392 | AFC | IFC | 2021-09-26 | 2021-09-28 | 2021-10-02 | 2 | 4 | 6 | IFA | 2022-03-13 | 2022-03-13 | 2022-03-26 | 0 | 13 | 13 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-12 | 0 |  | D01 | IFA | T-0651 | 2022-02-27 | 1400/12/08 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03377 | 2022-03-07 | 1400/12/17 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-447229 | 2022-03-13 | 1400/12/22 | 2022-03-26 | 1401/01/06 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0087 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-ELE-00-01560 | 2021-09-25 | 1400/07/03 | C4-RJ | [6 empty] | 1400-2294-213958 | 2021-09-28 | 1400/07/05 | 2021-10-02 | 1400/07/10 | CM | [10 empty] | D01 | IFA | T-0651 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-ELE-00-03377 | 2022-03-07 | 1400/12/17 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0006_D00 | [5 empty] | 1400-2294-447229 | 2022-03-13 | 1400/12/22 | 2022-03-26 | 1401/01/06 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0006_D00
2 | 1 | 0 | 9 | 0 | 2 | 6 | 2.1.9.2.6 | Data Sheets For LV Switchgear of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0008 | BK-SSGRL-PEDCO-110-EL-DT-0008 | BK | SSGRL | PEDCO | 110 | EL | DT | 0008 | F0Z-707393 | AFC | IFC | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | IFA | 2022-06-07 | 0 | 0 | -44719 | 0 | -44719 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 0 |  | D01 | IFA | T-0998 | 2022-05-24 | 1401/03/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0601 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-ELE-00-03320 | 2022-03-05 | 1400/12/14 | CM-C2 | [6 empty] | 1400-2294-443157 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0998 | 2022-05-24 | 1401/03/03 | [7 empty] | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0008_D00 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0008_D00
2 | 1 | 0 | 9 | 0 | 2 | 7 | 2.1.9.2.7 | Data Sheets For Power & Control Cables of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0009 | BK-SSGRL-PEDCO-110-EL-DT-0009 | BK | SSGRL | PEDCO | 110 | EL | DT | 0009 | F0Z-707394 | AFC | IFC | 2021-09-27 | 2021-09-19 | 2021-09-25 | -8 | 6 | -2 | IFA | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | IFA | 2022-04-10 | 2022-04-13 | 2022-04-16 | 3 | 3 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-13 | 0 |  | D02 | IFA | T-0751 | 2022-03-27 | 1401/01/07 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-03699 | 2022-03-30 | 1401/01/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0009_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-22895 | 2022-04-13 | 1401/01/24 | 2022-04-16 | 1401/01/27 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0009_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0090 | 2021-09-13 | 1400/06/22 |  |  |  | BK-SUR-ENG-ELE-00-01559 | 2021-09-25 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-204476 | 2021-09-19 | 1400/06/28 | 2021-09-25 | 1400/07/03 | CM | [10 empty] | D01 | IFA | T-0606 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-ELE-00-03321 | 2022-03-05 | 1400/12/14 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0009_D00 | [5 empty] | 1400-2294-443207 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0009_D00 | [9 empty] | D02 | IFA | T-0751 | 2022-03-27 | 1401/01/07 |  |  |  | BK-SUR-ENG-ELE-01-03699 | 2022-03-30 | 1401/01/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0009_D01 | [5 empty] | 1401-2294-22895 | 2022-04-13 | 1401/01/24 | 2022-04-16 | 1401/01/27 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0009_D01
2 | 1 | 0 | 9 | 0 | 2 | 8 | 2.1.9.2.8 | Data Sheets For Power Transformers of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0010 | BK-SSGRL-PEDCO-110-EL-DT-0010 | BK | SSGRL | PEDCO | 110 | EL | DT | 0010 | F0Z-707395 | AFC | IFC | 2021-09-29 | 2021-09-28 | 2021-10-02 | -1 | 4 | 3 | IFA | 2022-02-22 | 2022-02-24 | 2022-02-28 | 2 | 4 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-15 | 0 |  | D01 | IFA | T-0563 | 2022-02-08 | 1400/11/19 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03126 | 2022-02-20 | 1400/12/01 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0010_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-424217 | 2022-02-24 | 1400/12/05 | 2022-02-28 | 1400/12/09 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0010_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0094 | 2021-09-15 | 1400/06/24 |  |  |  | BK-SSR-ENG-ELE-00-01608 | 2021-09-26 | 1400/07/04 | CM-C2 | [6 empty] | 1400-2294-213964 | 2021-09-28 | 1400/07/05 | 2021-10-02 | 1400/07/10 | CM | [10 empty] | D01 | IFA | T-0563 | 2022-02-08 | 1400/11/19 |  |  |  | BK-SUR-ENG-ELE-00-03126 | 2022-02-20 | 1400/12/01 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0010_D00 | [5 empty] | 1400-2294-424217 | 2022-02-24 | 1400/12/05 | 2022-02-28 | 1400/12/09 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0010_D00
2 | 1 | 0 | 9 | 0 | 2 | 9 | 2.1.9.2.9 | Data Sheets For Distribution & Lighting Panels of Well Pads | BK-SSGRL-PEDCO-110-EL-DT-0011 | BK-SSGRL-PEDCO-110-EL-DT-0011 | BK | SSGRL | PEDCO | 110 | EL | DT | 0011 | F0Z-707396 | AFC | IFC | 2021-09-26 | 2021-09-28 | 2021-10-02 | 2 | 4 | 6 | IFA | 2022-05-31 | 0 | 0 | -44712 | 0 | -44712 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-12 | 0 |  | D01 | IFA | T-0966 | 2022-05-17 | 1401/02/27 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04478 | 2022-05-29 | 1401/03/08 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0011_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0011_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0087 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-ELE-00-01560 | 2021-09-25 | 1400/07/03 | C4-RJ | [6 empty] | 1400-2294-213958 | 2021-09-28 | 1400/07/05 | 2021-10-02 | 1400/07/10 | CM | [10 empty] | D01 | IFA | T-0966 | 2022-05-17 | 1401/02/27 |  |  |  | BK-SUR-ENG-ELE-01-04478 | 2022-05-29 | 1401/03/08 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0011_D00 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0011_D00
2 | 1 | 0 | 9 | 0 | 2 | 10 | 2.1.9.2.10 | Data Sheets For 11 KV Over Head Line Equipment | BK-SSGRL-PEDCO-110-EL-DT-0012 | BK-SSGRL-PEDCO-110-EL-DT-0012 | BK | SSGRL | PEDCO | 110 | EL | DT | 0012 | F0Z-707397 | AFC | IFC | 2021-11-24 | 2021-11-27 | 2021-11-28 | 3 | 1 | 4 | IFA | 2022-01-09 | 2022-01-12 | 2022-01-15 | 3 | 3 | 6 | IFA | 2022-02-09 | 2022-02-08 | 2022-02-13 | -1 | 5 | 4 | IFA | 2022-03-07 | 2022-02-28 | 2022-03-05 | -7 | 5 | -2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D03 | IFA | T-0615 | 2022-02-21 | 1400/12/02 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03305 | 2022-03-02 | 1400/12/11 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0012_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430270 | 2022-02-28 | 1400/12/09 | 2022-03-05 | 1400/12/14 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0012_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0226 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-ELE-00-02011 | 2021-11-15 | 1400/08/24 | CM-C2 | [6 empty] | 1400-2294-293077 | 2021-11-27 | 1400/09/06 | 2021-11-28 | 1400/09/07 | CM | [10 empty] | D01 | IFA | T-0380 | 2021-12-26 | 1400/10/05 |  |  |  | BK-SUR-ENG-ELE-00-02561 | 2022-01-04 | 1400/10/14 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0012_D00 | [5 empty] | 1400-2294-362424 | 2022-01-12 | 1400/10/22 | 2022-01-15 | 1400/10/25 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0012_D00 | [9 empty] | D02 | IFA | T-0510 | 2022-01-26 | 1400/11/06 |  |  |  | BK-SUR-ENG-ELE-00-02999 | 2022-02-08 | 1400/11/19 | CM-C3 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0012_D01 | [5 empty] | 1400-2294-402924 | 2022-02-08 | 1400/11/19 | 2022-02-13 | 1400/11/13 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0012_D01 | [9 empty] | D03 | IFA | T-0615 | 2022-02-21 | 1400/12/02 |  |  |  | BK-SUR-ENG-ELE-00-03305 | 2022-03-02 | 1400/12/11 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0012_D02 | [5 empty] | 1400-2294-430270 | 2022-02-28 | 1400/12/09 | 2022-03-05 | 1400/12/14 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0012_D02
2 | 1 | 0 | 9 | 0 | 2 | 11 | 2.1.9.2.11 | Data Sheets For 33 KV Over Head Line Equipment | BK-SSGRL-PEDCO-110-EL-DT-0013 | BK-SSGRL-PEDCO-110-EL-DT-0013 | BK | SSGRL | PEDCO | 110 | EL | DT | 0013 | F0Z-707398 | AFC | IFC | 2021-11-24 | 2021-11-27 | 2021-11-28 | 3 | 1 | 4 | IFA | 2022-01-09 | 2022-01-12 | 2022-01-15 | 3 | 3 | 6 | IFA | 2022-02-09 | 2022-02-08 | 2022-02-13 | -1 | 5 | 4 | IFA | 2022-03-07 | 2022-02-28 | 2022-03-05 | -7 | 5 | -2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D03 | IFA | T-0615 | 2022-02-21 | 1400/12/02 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03305 | 2022-03-02 | 1400/12/11 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430270 | 2022-02-28 | 1400/12/09 | 2022-03-05 | 1400/12/14 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0013_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0226 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-ELE-00-02011 | 2021-11-15 | 1400/08/24 | CM-C2 | [6 empty] | 1400-2294-293077 | 2021-11-27 | 1400/09/06 | 2021-11-28 | 1400/09/07 | CM | [10 empty] | D01 | IFA | T-0380 | 2021-12-26 | 1400/10/05 |  |  |  | BK-SUR-ENG-ELE-00-02561 | 2022-01-04 | 1400/10/14 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0013_D00 | [5 empty] | 1400-2294-362424 | 2022-01-12 | 1400/10/22 | 2022-01-15 | 1400/10/25 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0013_D00 | [9 empty] | D02 | IFA | T-0510 | 2022-01-26 | 1400/11/06 |  |  |  | BK-SUR-ENG-ELE-00-03000 | 2022-02-08 | 1400/11/19 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DT-0013_D01 | [5 empty] | 1400-2294-402924 | 2022-02-08 | 1400/11/19 | 2022-02-13 | 1400/11/13 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0013_D01 | [9 empty] | D03 | IFA | T-0615 | 2022-02-21 | 1400/12/02 |  |  |  | BK-SUR-ENG-ELE-00-03305 | 2022-03-02 | 1400/12/11 | AP | [6 empty] | 1400-2294-430270 | 2022-02-28 | 1400/12/09 | 2022-03-05 | 1400/12/14 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0013_D02
2 | 1 | 0 | 9 | 0 | 3 | 0 | 2.1.9.3 | Drawing/Diagram
2 | 1 | 0 | 9 | 0 | 3 | 1 | 2.1.9.3.1 | Typical Installation Details For Over Head Line Equipment | BK-SSGRL-PEDCO-110-EL-DW-0001 | BK-SSGRL-PEDCO-110-EL-DW-0001 | BK | SSGRL | PEDCO | 110 | EL | DW | 0001 | F2P-707399 | IFI | IFI | 2021-09-05 | 2021-09-06 | 2021-09-11 | 1 | 5 | 6 | IFI | 2021-10-09 | 2021-10-13 | 2021-10-18 | 4 | 5 | 9 | IFI | 2021-11-21 | 2021-11-16 | 2021-11-21 | -5 | 5 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2021-11-07 |  | D02 | IFI | T-0212 | 2021-11-07 | 1400/08/16 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-01957 | 2021-12-07 | 1400/09/16 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-279099 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DW-0001-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0051 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-ELE-00-01439 | 2021-08-30 | 1400/06/08 | CM-C2 | [6 empty] | 1400/2294/188317 | 2021-09-06 | 1400/06/15 | 2021-09-11 | 1400/06/20 | CM | [10 empty] | D01 | IFI | T-0115 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SSR-ENG-ELE-00-01665 | 2021-10-03 | 1400/07/11 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DW-0001_D00 | [5 empty] | 1400-2294-234035 | 2021-10-13 | 1400/07/21 | 2021-10-18 | 1400/07/26 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DW-0001_D00 | [9 empty] | D02 | IFI | T-0212 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-ELE-00-01957 | 2021-12-07 | 1400/09/16 | AP | [6 empty] | 1400-2294-279099 | 2021-11-16 | 1400/08/25 | 2021-11-21 | 1400/08/30 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DW-0001-D01
2 | 1 | 0 | 9 | 0 | 3 | 2 | 2.1.9.3.2 | Installation Detail & Notes for Connection OHL to Gantries for Wells | BK-SSGRL-PEDCO-110-EL-DW-0002 | BK-SSGRL-PEDCO-110-EL-DW-0002 | BK | SSGRL | PEDCO | 110 | EL | DW | 0002 | F2P-707400 | AFC | IFC | 2022-03-20 | 2022-03-15 | 2022-03-24 | -5 | 9 | 4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-06 | 0 |  | D00 | IFC | T-0684 | 2022-03-06 | 1400/12/15 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03585 | 2022-03-15 | 1400/12/24 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-451069 | 2022-03-15 | 1400/12/24 | 2022-03-24 | 1401/01/07 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0684 | 2022-03-06 | 1400/12/15 |  |  |  | BK-SUR-ENG-ELE-00-03585 | 2022-03-15 | 1400/12/24 | CM-C2 | [6 empty] | 1400-2294-451069 | 2022-03-15 | 1400/12/24 | 2022-03-24 | 1401/01/07 | CM
2 | 1 | 0 | 9 | 0 | 3 | 3 | 2.1.9.3.3 | Electrical Typical Schematic Diagrams For LV Panels of Well Pads | BK-SSGRL-PEDCO-110-EL-DG-0001 | BK-SSGRL-PEDCO-110-EL-DG-0001 | BK | SSGRL | PEDCO | 110 | EL | DG | 0001 | F2P-707401 | IFI | IFI | 2021-09-13 | 2021-09-14 | 2021-09-18 | 1 | 4 | 5 | IFI | 2022-05-02 | 2022-05-08 | 2022-05-11 | 6 | 3 | 9 | IFI | 2022-06-04 | 0 | 0 | -44716 | 0 | -44716 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-30 | 2022-05-21 |  | D02 | IFI | T-0979 | 2022-05-21 | 1401/02/31 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04487 | 2022-05-29 | 1401/03/09 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0072 | 2021-08-30 | 1400/06/08 |  |  |  | BK-SSR-ENG-ELE-00-01506 | 2021-09-13 | 1400/06/22 | C4-RJ | [6 empty] | 1400-2294-198862 | 2021-09-14 | 1400/06/23 | 2021-09-18 | 1400/06/27 | CM | [10 empty] | D01 | IFI | T-0835 | 2022-04-18 | 1400/01/29 |  |  |  | BK-SUR-ENG-ELE-01-04072 | 2022-04-26 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D00 | [5 empty] | 1401-2294-52754 | 2022-05-08 | 1401/02/18 | 2022-05-11 | 1401/02/21 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D00 | [9 empty] | D02 | IFI | T-0979 | 2022-05-21 | 1401/02/31 |  |  |  | BK-SUR-ENG-ELE-01-04487 | 2022-05-29 | 1401/03/09 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D01 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001_D01
2 | 1 | 0 | 9 | 0 | 3 | 4 | 2.1.9.3.4 | Control Logic Diagram For LV Incomers of Well Pads | BK-SSGRL-PEDCO-110-EL-LD-0001 | BK-SSGRL-PEDCO-110-EL-LD-0001 | BK | SSGRL | PEDCO | 110 | EL | LD | 0001 | F2P-707402 | AFC | IFC | 2021-09-13 | 2021-09-14 | 2021-09-18 | 1 | 4 | 5 | IFA | 2022-03-09 | 2022-03-10 | 2022-03-12 | 1 | 2 | 3 | IFA | 2022-06-04 | 0 | 0 | -44716 | 0 | -44716 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-30 | 0 |  | D02 | IFA | T-0975 | 2022-05-21 | 1401/02/31 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04489 | 2022-05-29 | 1401/03/09 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-LD-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-LD-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0072 | 2021-08-30 | 1400/06/08 |  |  |  | BK-SSR-ENG-ELE-00-01506 | 2021-09-13 | 1400/06/22 | C4-RJ | [6 empty] | 1400-2294-198862 | 2021-09-14 | 1400/06/23 | 2021-09-18 | 1400/06/27 | CM | [10 empty] | D01 | IFA | T-0632 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-ELE-00-03376 | 2022-03-07 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-LD-0001_D00 | [5 empty] | 1400-2294-443146 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-LD-0001_D00 | [9 empty] | D02 | IFA | T-0975 | 2022-05-21 | 1401/02/31 |  |  |  | BK-SUR-ENG-ELE-01-04489 | 2022-05-29 | 1401/03/09 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-LD-0001_D01 | [11 empty] | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-LD-0001_D01
2 | 1 | 0 | 9 | 0 | 3 | 5 | 2.1.9.3.5 | Earthing Layout For Electrical Tower (Gantry) of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0001 | BK-SSGRL-PEDCO-110-EL-PY-0001 | BK | SSGRL | PEDCO | 110 | EL | PY | 0001 | F2P-707403 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 9 | 0 | 3 | 6 | 2.1.9.3.6 | Cable Route Layout For Electrical Tower (Gantry) of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0002 | BK-SSGRL-PEDCO-110-EL-PY-0002 | BK | SSGRL | PEDCO | 110 | EL | PY | 0002 | F2P-707404 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 9 | 0 | 3 | 7 | 2.1.9.3.7 | Overall Single Line Diagram of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0001 | BK-SSGRL-PEDCO-110-EL-SL-0001 | BK | SSGRL | PEDCO | 110 | EL | SL | 0001 | F2P-707405 | AFC | IFC | 2022-03-16 | 2022-04-09 | 2022-04-13 | 24 | 4 | 28 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-02 | 0 |  | D00 | IFC | T-0662 | 2022-03-02 | 1400/12/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03469 | 2022-03-12 | 1400/12/21 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-16106 | 2022-04-09 | 1401/01/20 | 2022-04-13 | 1401/01/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0662 | 2022-03-02 | 1400/12/11 |  |  |  | BK-SUR-ENG-ELE-00-03469 | 2022-03-12 | 1400/12/21 | CM-C2 | [6 empty] | 1401-2294-16106 | 2022-04-09 | 1401/01/20 | 2022-04-13 | 1401/01/24 | CM
2 | 1 | 0 | 9 | 0 | 3 | 8 | 2.1.9.3.8 | Single Line Diagram For LV Switchgear of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0002 | BK-SSGRL-PEDCO-110-EL-SL-0002 | BK | SSGRL | PEDCO | 110 | EL | SL | 0002 | F2P-707406 | AFC | IFC | 2022-02-22 | 2022-03-10 | 2022-03-12 | 16 | 2 | 18 | IFA | 2022-05-03 | 2022-05-18 | 2022-05-22 | 15 | 4 | 19 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-08 | 0 |  | D01 | IFA | T-0844 | 2022-04-19 | 1401/01/30 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04079 | 2022-04-30 | 1401/02/10 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0002 _D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-66366 | 2022-05-18 | 1401/02/28 | 2022-05-22 | 1401/03/01 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0002 _D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0564 | 2022-02-08 | 1400/11/19 |  |  |  | BK-SUR-ENG-ELE-00-03159 | 2022-02-21 | 1400/12/02 | CM-C3 | [6 empty] | 1400-2294-443103 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0844 | 2022-04-19 | 1401/01/30 |  |  |  | BK-SUR-ENG-ELE-01-04079 | 2022-04-30 | 1401/02/10 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0002 _D00 | [5 empty] | 1401-2294-66366 | 2022-05-18 | 1401/02/28 | 2022-05-22 | 1401/03/01 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0002 _D00
2 | 1 | 0 | 9 | 0 | 3 | 9 | 2.1.9.3.9 | Single Line Diagram For LV Power Distribution Panel of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0003 | BK-SSGRL-PEDCO-110-EL-SL-0003 | BK | SSGRL | PEDCO | 110 | EL | SL | 0003 | F2P-707407 | AFC | IFC | 2022-05-28 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-14 | 0 |  | D00 | IFC | T-0947 | 2022-05-14 | 1401/02/24 | T-0947 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-ELE-01-04393 | 2022-05-23 | 1401/03/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0947 | 2022-05-14 | 1401/02/24 | T-0947 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-ELE-01-04393 | 2022-05-23 | 1401/03/02 | CM-C3
2 | 1 | 0 | 9 | 0 | 3 | 10 | 2.1.9.3.10 | Single Line Diagram For DC Charger of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0004 | BK-SSGRL-PEDCO-110-EL-SL-0004 | BK | SSGRL | PEDCO | 110 | EL | SL | 0004 | F2P-707408 | AFC | IFC | 2022-02-20 | 2022-02-24 | 2022-02-28 | 4 | 4 | 8 | IFA | 2022-03-23 | 2022-03-19 | 2022-03-27 | -4 | 8 | 4 | IFA | 2022-05-04 | 2022-05-09 | 2022-05-16 | 5 | 7 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-06 | 0 |  | D02 | IFA | T-0850 | 2022-04-20 | 1401/01/14 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04092 | 2022-04-30 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0004_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54908 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0554 | 2022-02-06 | 1400/11/17 |  |  |  | BK-SUR-ENG-ELE-00-03087 | 2022-02-19 | 1400/11/30 | CM-C2 | [6 empty] | 1400-2294-424218 | 2022-02-24 | 1400/12/05 | 2022-02-28 | 1400/12/09 | CM | [10 empty] | D01 | IFA | T-0712 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-ELE-00-03642 | 2022-03-16 | 1400/12/25 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0004_D00 | [5 empty] | 1400-2294-455098 | 2022-03-19 | 1400/12/28 | 2022-03-27 | 1401/01/07 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0004_D00 | [9 empty] | D02 | IFA | T-0850 | 2022-04-20 | 1401/01/14 |  |  |  | BK-SUR-ENG-ELE-01-04092 | 2022-04-30 | 1401/02/10 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-SL-0004_D01 | [5 empty] | 1401-2294-54908 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-SL-0004_D01
2 | 1 | 0 | 9 | 0 | 3 | 11 | 2.1.9.3.11 | Single Line Diagram For Capacitor Banks of Well Pads | BK-SSGRL-PEDCO-110-EL-SL-0005 | BK-SSGRL-PEDCO-110-EL-SL-0005 | BK | SSGRL | PEDCO | 110 | EL | SL | 0005 | F2P-707409 | AFC | IFC | 2022-02-16 | 2022-03-09 | 2022-03-12 | 21 | 3 | 24 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 0 |  | D00 | IFC | T-0541 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03060 | 2022-02-14 | 1400/11/25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-442066 | 2022-03-09 | 1400/12/18 | 2022-03-12 | 1400/12/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0541 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-ELE-00-03060 | 2022-02-14 | 1400/11/25 | [7 empty] | 1400-2294-442066 | 2022-03-09 | 1400/12/18 | 2022-03-12 | 1400/12/21 | CM
2 | 1 | 0 | 9 | 0 | 3 | 12 | 2.1.9.3.12 | Interconnection Wiring Diagram of Well Pads | BK-SSGRL-PEDCO-110-EL-DG-0002 | BK-SSGRL-PEDCO-110-EL-DG-0002 | BK | SSGRL | PEDCO | 110 | EL | DG | 0002 | F2P-707410 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 9 | 0 | 3 | 13 | 2.1.9.3.13 | Area Lighting & Small Power Layout of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0003 | BK-SSGRL-PEDCO-110-EL-PY-0003 | BK | SSGRL | PEDCO | 110 | EL | PY | 0003 | F2P-707411 | AFC | IFC | 2022-05-28 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-14 | 0 |  | D00 | IFC | T-0947 | 2022-05-14 | 1401/02/24 | T-0947 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-ELE-01-04393 | 2022-05-23 | 1401/03/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0947 | 2022-05-14 | 1401/02/24 | T-0947 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-ELE-01-04393 | 2022-05-23 | 1401/03/02 | CM-C3
2 | 1 | 0 | 9 | 0 | 3 | 14 | 2.1.9.3.14 | Lighting & Small Power Layout For Switchgear Building of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0004 | BK-SSGRL-PEDCO-110-EL-PY-0004 | BK | SSGRL | PEDCO | 110 | EL | PY | 0004 | F2P-707412 | AFC | IFC | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-11 | 0 |  | D00 | IFC | T-0930 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04347 | 2022-05-22 | 1401/03/01 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0930 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-ELE-01-04347 | 2022-05-22 | 1401/03/01 | CM-C2
2 | 1 | 0 | 9 | 0 | 3 | 15 | 2.1.9.3.15 | Lighting & Small Power Layout For Security Building of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0005 | BK-SSGRL-PEDCO-110-EL-PY-0005 | BK | SSGRL | PEDCO | 110 | EL | PY | 0005 | F2P-707413 | AFC | IFC | 2022-05-21 | 0 | 0 | -44702 | 0 | -44702 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-07 | 0 |  | D00 | IFC | T-0903 | 2022-05-07 | 1401/02/17 | T-0903 | 2022-05-07 | 1401/02/17 | BK-SUR-ENG-ELE-01-04301 | 2022-05-08 | 1401/02/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0903 | 2022-05-07 | 1401/02/17 | T-0903 | 2022-05-07 | 1401/02/17 | BK-SUR-ENG-ELE-01-04301 | 2022-05-08 | 1401/02/28 | CM-C3
2 | 1 | 0 | 9 | 0 | 3 | 16 | 2.1.9.3.16 | Area Electrical Cable Route & Section Layout of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0006 | BK-SSGRL-PEDCO-110-EL-PY-0006 | BK | SSGRL | PEDCO | 110 | EL | PY | 0006 | F2P-707414 | AFC | IFC | 2022-06-11 | 0 | 0 | -44723 | 0 | -44723 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-28 | 0 |  | D00 | IFC | T-1008 | 2022-05-28 | 1401/03/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1008 | 2022-05-28 | 1401/03/07
2 | 1 | 0 | 9 | 0 | 3 | 17 | 2.1.9.3.17 | Electrical Cable Route & Section Layout For Switchgear Building of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0007 | BK-SSGRL-PEDCO-110-EL-PY-0007 | BK | SSGRL | PEDCO | 110 | EL | PY | 0007 | F2P-707415 | AFC | IFC | 2022-06-08 | 0 | 0 | -44720 | 0 | -44720 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-25 | 0 |  | D00 | IFC | T-1001 | 2022-05-25 | 1401/03/04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1001 | 2022-05-25 | 1401/03/04
2 | 1 | 0 | 9 | 0 | 3 | 18 | 2.1.9.3.18 | Electrical Equipment Arrangement Layout For Switchgear Building of Well Pads | BK-SSGRL-PEDCO-110-EL-PY-0008 | BK-SSGRL-PEDCO-110-EL-PY-0008 | BK | SSGRL | PEDCO | 110 | EL | PY | 0008 | F2P-707416 | AFC | IFC | 2022-06-06 | 0 | 0 | -44718 | 0 | -44718 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-23 | 0 |  | D00 | IFC | T-0992 | 2022-05-23 | 1401/03/02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0992 | 2022-05-23 | 1401/03/02
2 | 1 | 0 | 9 | 0 | 3 | 20 | 2.1.9.3.20 | Earthing & Lightning Layout for well pads | BK-SSGRL-PEDCO-110-EL-PY-0010 | BK-SSGRL-PEDCO-110-EL-PY-0010 | BK | SSGRL | PEDCO | 110 | EL | PY | 0010 | F2P-707417 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 9 | 0 | 4 | 0 | 2.1.9.4 | List
2 | 1 | 0 | 9 | 0 | 4 | 1 | 2.1.9.4.1 | Electrical Load List of Well Pads | BK-SSGRL-PEDCO-110-EL-LI-0001 | BK-SSGRL-PEDCO-110-EL-LI-0001 | BK | SSGRL | PEDCO | 110 | EL | LI | 0001 | F0Z-707418 | AFC | IFC | 2022-02-08 | 2022-02-12 | 2022-02-21 | 4 | 9 | 13 | IFA | 2022-03-23 | 2022-03-19 | 2022-03-27 | -4 | 8 | 4 | IFA | 2022-05-08 | 2022-05-09 | 2022-05-16 | 1 | 7 | 8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-25 | 0 |  | D02 | IFA | T-0856 | 2022-04-24 | 1401/02/04 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04161 | 2022-05-08 | 1401/02/18 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54909 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0505 | 2022-01-25 | 1400/11/05 |  |  |  | BK-SUR-ENG-ELE-00-02909 | 2022-02-01 | 1400/11/13 | CM-C2 | [6 empty] | 1400-2294-407156 | 2022-02-12 | 1400/11/23 | 2022-02-21 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0712 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-ELE-00-03642 | 2022-03-16 | 1400/12/25 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-LI-0001_D00 | [5 empty] | 1400-2294-455098 | 2022-03-19 | 1400/12/28 | 2022-03-27 | 1401/01/07 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-LI-0001_D00 | [9 empty] | D02 | IFA | T-0856 | 2022-04-24 | 1401/02/04 |  |  |  | BK-SUR-ENG-ELE-01-04161 | 2022-05-08 | 1401/02/18 | AP | PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-LI-0001_D01 | [5 empty] | 1401-2294-54909 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-EL-LI-0001_D01
2 | 1 | 0 | 9 | 0 | 4 | 2 | 2.1.9.4.2 | Electrical Power & Control Cable List of Well Pads | BK-SSGRL-PEDCO-110-EL-LI-0002 | BK-SSGRL-PEDCO-110-EL-LI-0002 | BK | SSGRL | PEDCO | 110 | EL | LI | 0002 | F0Z-707419 | AFC | IFC | 2022-06-08 | 0 | 0 | -44720 | 0 | -44720 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-25 | 0 |  | D00 | IFC | T-1001 | 2022-05-25 | 1401/03/04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1001 | 2022-05-25 | 1401/03/04
2 | 1 | 0 | 9 | 0 | 4 | 3 | 2.1.9.4.3 | Cable Drum Schedule and Cutting List of Well Pads | BK-SSGRL-PEDCO-110-EL-LI-0003 | BK-SSGRL-PEDCO-110-EL-LI-0003 | BK | SSGRL | PEDCO | 110 | EL | LI | 0003 | F0Z-707420 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 9 | 0 | 5 | 0 | 2.1.9.5 | Report
2 | 1 | 0 | 9 | 0 | 5 | 1 | 2.1.9.5.1 | Electrical Network (Load Flow, Motor Starting & Short Circuit) Study Report of Well Pads | BK-SSGRL-PEDCO-110-EL-RT-0002 | BK-SSGRL-PEDCO-110-EL-RT-0002 | BK | SSGRL | PEDCO | 110 | EL | RT | 0002 | F0Z-707421 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 9 | 0 | 5 | 2 | 2.1.9.5.2 | Relay Coordination & Setting Study Report of Well Pads | BK-SSGRL-PEDCO-110-EL-RT-0003 | BK-SSGRL-PEDCO-110-EL-RT-0003 | BK | SSGRL | PEDCO | 110 | EL | RT | 0003 | F0Z-707422 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 1 | 0 | 9 | 0 | 5 | 3 | 2.1.9.5.3 | 11KV Over Head Line Study Report | BK-SSGRL-PEDCO-110-EL-RT-0004 | BK-SSGRL-PEDCO-110-EL-RT-0004 | BK | SSGRL | PEDCO | 110 | EL | RT | 0004 | F0Z-707423 | AFD | IFC | 2022-04-12 | 2022-05-01 | 2022-05-02 | 19 | 1 | 20 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-29 | 0 |  | D00 | IFC | T-0761 | 2022-03-29 | 1401/01/09 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-03742 | 2022-04-06 | 1401/01/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-47897 | 2022-05-01 | 1401/02/11 | 2022-05-02 | 1401/02/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0761 | 2022-03-29 | 1401/01/09 |  |  |  | BK-SUR-ENG-ELE-01-03742 | 2022-04-06 | 1401/01/17 | CM-C3 | [6 empty] | 1401-2294-47897 | 2022-05-01 | 1401/02/11 | 2022-05-02 | 1401/02/12 | CM
2 | 1 | 0 | 9 | 0 | 5 | 4 | 2.1.9.5.4 | 33KV Over Head Line Study Report | BK-SSGRL-PEDCO-110-EL-RT-0005 | BK-SSGRL-PEDCO-110-EL-RT-0005 | BK | SSGRL | PEDCO | 110 | EL | RT | 0005 | F0Z-707424 | AFD | IFC | 2022-04-12 | 2022-05-01 | 2022-05-02 | 19 | 1 | 20 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-29 | 0 |  | D00 | IFC | T-0761 | 2022-03-29 | 1401/01/09 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-03742 | 2022-04-06 | 1401/01/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-47897 | 2022-05-01 | 1401/02/11 | 2022-05-02 | 1401/02/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0761 | 2022-03-29 | 1401/01/09 |  |  |  | BK-SUR-ENG-ELE-01-03742 | 2022-04-06 | 1401/01/17 | CM-C3 | [6 empty] | 1401-2294-47897 | 2022-05-01 | 1401/02/11 | 2022-05-02 | 1401/02/12 | CM
2 | 1 | 0 | 10 | 0 | 0 | 0 | 2.1.10 | Civil
2 | 1 | 0 | 10 | 0 | 1 | 0 | 2.1.10.1 | Drawing/Diagram
2 | 1 | 0 | 10 | 0 | 1 | 1 | 2.1.10.1.1 | BINAK Oil Field Project Overall Well Location/Facilities Layout | BK-SSGRL-PEDCO-110-CV-PY-0001 | BK-SSGRL-PEDCO-110-CV-PY-0001 | BK | SSGRL | PEDCO | 110 | CV | PY | 0001 | F4A-707425 | AFC | IFC | 44671 | 44663 | 44668 | -8 | 5 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-06 | 0 |  | D00 | IFC | T-0783 | 2022-04-06 | 1401/01/17 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-03799 | 2022-04-09 | 1401/01/20 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-19624 | 2022-04-12 | 1401/01/23 | 2022-04-17 | 1401/01/28 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0783 | 2022-04-06 | 1401/01/17 |  |  |  | BK-SUR-ENG-CIV-01-03799 | 2022-04-09 | 1401/01/20 | CM-C2 | [6 empty] | 1401-2294-19624 | 2022-04-12 | 1401/01/23 | 2022-04-17 | 1401/01/28 | CM
2 | 1 | 0 | 10 | 0 | 2 | 0 | 2.1.10.2 | Calculation
2 | 1 | 0 | 10 | 0 | 2 | 1 | 2.1.10.2.1 | Calculation Note For Flood Control | BK-SSGRL-PEDCO-110-CV-CN-0001 | BK-SSGRL-PEDCO-110-CV-CN-0001 | BK | SSGRL | PEDCO | 110 | CV | CN | 0001 | F0Z-707426 | AFC | IFC | 44549 | 44539 | 44541 | -10 | 2 | -8 | IFA | 44590 | 44580 | 44587 | -10 | 7 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-05 | 0 |  | D01 | IFA | T-0460 | 2022-01-15 | 1400/10/25 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-02816 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-372879 | 2022-01-19 | 1400/10/30 | 2022-01-26 | 1400/11/06 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0294 | 2021-12-05 | 1400/09/14 |  |  |  | BK-SUR-ENG-CIV-00-02204 | 2021-12-05 | 1400/09/14 | CM-C2 | [6 empty] | 1400-2294-310923 | 2021-12-09 | 1400/09/18 | 2021-12-11 | 1400/09/20 | CM | [10 empty] | D01 | IFA | T-0460 | 2022-01-15 | 1400/10/25 |  |  |  | BK-SUR-ENG-CIV-00-02816 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001_D00 | [5 empty] | 1400-2294-372879 | 2022-01-19 | 1400/10/30 | 2022-01-26 | 1400/11/06 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001_D00
2 | 1 | 0 | 11 | 0 | 0 | 0 | 2.1.11 | Structure
2 | 1 | 0 | 11 | 0 | 1 | 0 | 2.1.11.1 | Drawing/Diagram
2 | 1 | 0 | 11 | 0 | 1 | 1 | 2.1.11.1.1 | Typical Drawing For Rig Foundation Plan & Details | BK-SSGRL-PEDCO-110-ST-DW-0003 | BK-SSGRL-PEDCO-110-ST-DW-0003 | [7 empty] | - | [43 empty] | Deleted | 0
2 | 1 | 0 | 12 | 0 | 0 | 0 | 2.1.12 | Geotechnical/Geoelectric
2 | 1 | 0 | 12 | 1 | 0 | 0 | 2.1.12.1 | Geotechnical/Geoelectrical
2 | 1 | 0 | 12 | 1 | 1 | 0 | 2.1.12.1.1 | Procedure/Plan
2 | 1 | 0 | 12 | 1 | 1 | 1 | 2.1.12.1.1.1 | Geotechnical Investigation Plan for Well Pads | BK-SSGRL-PEDCO-110-GT-PR-0001 | BK-SSGRL-PEDCO-110-GT-PR-0001 | BK | SSGRL | PEDCO | 110 | GT | PR | 0001 | F0Z-707427 | AFC | IFC | 44433 | 44423 | 44431 | -10 | 8 | -2 | IFA | 44460 | 44452 | 0 | -8 | -44452 | -44460 | IFA | 44485 | 44476 | 44480 | -9 | 4 | -5 | AFC | 44508 | 44498 | 44502 | -10 | 4 | -6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-11 | 2021-10-25 |  | D03 | AFC | T-0181 | 2021-10-25 | 1400/08/03 | 0 | 0 | 0 | BK-SUR-ENG-GEN-00-01893 | 2021-11-02 | 1400/08/11 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-251689 | 2021-10-29 | 1400/08/07 | 2021-11-02 | 1400/08/11 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0043 | 2021-08-11 | 1400/05/20 |  |  |  | BK-SUR-ENG-CIV-00-01344 | 2021-08-17 | 1400/05/26 | CM-C3 | [6 empty] | 1400/2294/166479 | 2021-08-15 | 1400/05/24 | 2021-08-23 | 1400/06/01 | CM | [8 empty] | L-7572 |  | D01 | IFA | T-0082 | 2021-09-07 | 1400/06/16 |  |  |  | BK-SUR-ENG-GEN-00-01491 | 2021-09-11 | 1400/06/20 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D00 | [5 empty] | 1400-2294-197155 | 2021-09-13 | 1400/06/22 |  |  | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D00 | [9 empty] | D02 | IFA | T-0127 | 2021-10-02 | 1400/07/10 |  |  |  | BK-SUR-ENG-GEN-00-01679 | 2021-10-06 | 1400/07/14 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D01 | [5 empty] | 1400-2290-225564 | 2021-10-07 | 1400/07/15 | 2021-10-11 | 1400/07/19 | CM | NISOC-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D01 | [9 empty] | D03 | AFC | T-0181 | 2021-10-25 | 1400/08/03 |  |  |  | BK-SUR-ENG-GEN-00-01893 | 2021-11-02 | 1400/08/11 | CM-C2 | PEDCO-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D02 | [5 empty] | 1400-2294-251689 | 2021-10-29 | 1400/08/07 | 2021-11-02 | 1400/08/11 | AP | NISOC-CRS-BK-SSGRL-PEDCO-110-GT-PR-0001_D02
2 | 2 | 0 | 0 | 0 | 0 | 0 | 2.2 | Package 01-New Well # W018S
2 | 2 | 1 | 0 | 0 | 0 | 0 | 2.2.1 | Detail Design Engineering
2 | 2 | 1 | 1 | 0 | 0 | 0 | 2.2.1.1 | Process
2 | 2 | 1 | 1 | 1 | 0 | 0 | 2.2.1.1.1 | Drawing/Diagram
2 | 2 | 1 | 1 | 1 | 0 | 1 | 2.2.1.1.1 | Process Flow Diagram - W018S | BK-W018S-PEDCO-110-PR-PF-0001 | BK-W018S-PEDCO-110-PR-PF-0001 | BK | W018S | PEDCO | 110 | PR | PF | 0001 | F2A-707428 | AFC | IFC | 2021-08-18 | 2021-08-30 | 2021-09-07 | 12 | 8 | 20 | IFC | 2021-11-16 | 0 | 0 | -44516 | 0 | -44516 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-02 | 0 |  | D01 | IFC | T-0205 | 2021-11-02 | 1400/08/11 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02020 | 2021-11-16 | 1400/08/25 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-PF-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-PR-PF-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0030 | 2021-08-04 | 1400/05/13 |  |  |  | BK-SUR-ENG-PCS-00-01391 | 2021-08-24 | 1400/06/02 | CM-C3 | [6 empty] | 1400/2294/179417 | 2021-08-30 | 1400/06/08 | 2021-09-07 | 1400/06/16 | RJ | [10 empty] | D01 | IFC | T-0205 | 2021-11-02 | 1400/08/11 |  |  |  | BK-SUR-ENG-PCS-00-02020 | 2021-11-16 | 1400/08/25 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-PF-0001_D00 | [11 empty] | NISOC-CRS-BK-W018S-PEDCO-110-PR-PF-0001_D00
2 | 2 | 1 | 1 | 1 | 0 | 2 | 2.2.1.1.1 | P&ID - W018S | BK-W018S-PEDCO-110-PR-PI-0001 | BK-W018S-PEDCO-110-PR-PI-0001 | BK | W018S | PEDCO | 110 | PR | PI | 0001 | F2A-707429 | AFC | IFC | 2021-08-23 | 2021-08-30 | 2021-09-06 | 7 | 7 | 14 | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-01 | 0 |  | D03 | IFA | T-0653 | 2022-02-28 | 1400/12/09 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0036 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PCS-00-01410 | 2021-08-25 | 1400/06/03 | CM-C3 | [6 empty] | 1400/2294/179419 | 2021-08-30 | 1400/06/08 | 2021-09-06 | 1400/06/15 | RJ | [10 empty] | D01 | IFC | T-0201 | 2021-11-01 | 1400/08/10 |  |  |  | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-279084 | 2021-11-16 | 1400/08/25 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0345 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-PCS-00-02540 | 2022-01-03 | 1400/10/13 | CM-C3 | PEDCO-BK-W018S-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-342085 | 2021-12-30 | 1400/10/09 | 2022-01-03 | 1400/10/13 | RJ | NISOC-BK-W018S-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0653 | 2022-02-28 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PR-PI-0001_D02
2 | 2 | 1 | 1 | 2 | 0 | 0 | 2.2.1.1.2 | List
2 | 2 | 1 | 1 | 2 | 0 | 1 | 2.2.1.1.2 | Line List - W018S | BK-W018S-PEDCO-110-PR-LI-0001 | BK-W018S-PEDCO-110-PR-LI-0001 | BK | W018S | PEDCO | 110 | PR | LI | 0001 | F0Z-707430 | AFC | IFC | 44431 | 44438 | 44445 | 7 | 7 | 14 | IFC | 44522 | 44527 | 44529 | 5 | 2 | 7 | IFA | 44573 | 0 | 0 | -44573 | 0 | -44573 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-08 | 0 |  | D02 | IFA | T-0403 | 2021-12-29 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0036 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PCS-00-01410 | 2021-08-25 | 1400/06/03 | CM-C3 | [6 empty] | 1400/2294/179419 | 2021-08-30 | 1400/06/08 | 2021-09-06 | 1400/06/15 | RJ | [10 empty] | D01 | IFC | T-0217 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PCS-00-02051 | 2021-11-20 | 1400/08/29 | CM-C2 | PEDCO-CRS-D01-BK-W018S-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1400-2290-293083 | 2021-11-27 | 1400/09/06 | 2021-11-29 | 1400/09/08 | CM | NISOC-CRS-D01-BK-W018S-PEDCO-110-PR-LI-0001_D00 | [9 empty] | D02 | IFA | T-0403 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-LI-0001_D01 | [11 empty] | NISOC-CRS-BK-W018S-PEDCO-110-PR-LI-0001_D01
2 | 2 | 1 | 1 | 3 | 0 | 0 | 2.2.1.1.3 | Report
2 | 2 | 1 | 1 | 3 | 0 | 1 | 2.2.1.1.3 | Flow line Hydraulic Calculation Report | BK-W018S-PEDCO-110-PR-RT-0001 | BK-W018S-PEDCO-110-PR-RT-0001 | BK | W018S | PEDCO | 110 | PR | RT | 0001 | F0Z-707431 | AFC | IFC | 44513 | 44514 | 44517 | 1 | 3 | 4 | IFA | 44576 | 44228 | 44597 | -348 | 369 | 21 | IFA | 44628 | 44630 | 44633 | 2 | 3 | 5 | IFA | 44695 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-30 | 0 |  | D03 | IFA | T-0878 | 2022-04-30 | 1401/02/10 | T-0878 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 2022-05-28 | 1402/03/07 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-PR-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0197 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-PCS-00-01993 | 2021-11-14 | 1400/08/23 | CM-C3 | [6 empty] | 1400-2294-275250 | 2021-11-14 | 1400/08/23 | 2021-11-17 | 1400/08/26 | CM | [10 empty] | D01 | IFA | T-0413 | 2022-01-01 | 1400/10/11 |  |  |  | BK-SUR-ENG-PCS-00-02735 | 2022-01-19 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-RT-0001_D00 | [5 empty] | 1400-2294-392131 | 2021-02-01 | 1400/11/12 | 2022-02-05 | 1400/11/16 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-0627 | 2022-02-22 | 1400/12/03 |  |  |  | BK-SUR-ENG-PCS-00-03387 | 2022-03-07 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-RT-0001_D01 | [5 empty] | 1400-2294-443285 | 2022-03-10 | 1400/12/19 | 2022-03-13 | 1400/12/22 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D01 | [9 empty] | D03 | IFA | T-0878 | 2022-04-30 | 1401/02/10 | T-0878 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 2022-05-28 | 1402/03/07 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PR-RT-0001_D02 | [11 empty] | NISOC-CRS-BK-W018S-PEDCO-110-PR-RT-0001_D02
2 | 2 | 1 | 1 | 4 | 0 | 0 | 2.2.1.1.4 | Data Sheet
2 | 2 | 1 | 1 | 4 | 0 | 1 | 2.2.1.1 | Process Data Sheets For Instrument Devices - W018S | BK-W018S-PEDCO-110-PR-DT-0001 | BK-W018S-PEDCO-110-PR-DT-0001 | BK | W018S | PEDCO | 110 | PR | DT | 0001 | F0Z-707432 | AFC | IFC | 44677 | 44689 | 44695 | 12 | 6 | 18 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-12 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04093 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 2022-05-14 | 1401/02/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-PCS-01-04093 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 2022-05-14 | 1401/02/24 | CM
2 | 2 | 1 | 2 | 0 | 0 | 0 | 2.2.1.2 | Piping
2 | 2 | 1 | 2 | 1 | 0 | 0 | 2.2.1.2.1 | Drawing/Diagram
2 | 2 | 1 | 2 | 1 | 0 | 1 | 2.2.1.2.1 | Plot Plan Drawing - W018S | BK-W018S-PEDCO-110-PI-PY-0001 | BK-W018S-PEDCO-110-PI-PY-0001 | BK | W018S | PEDCO | 110 | PI | PY | 0001 | F5A-707433 | AFC | IFC | 2021-09-05 | 2021-09-26 | 2021-09-29 | 21 | 3 | 24 | IFA | 2021-11-29 | 2021-12-08 | 2021-12-12 | 9 | 4 | 13 | IFA | 2022-02-14 | 2022-02-26 | 2022-03-05 | 12 | 7 | 19 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 0 |  | D02 | IFA | T-0526 | 2022-01-31 | 1400/11/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-424550 | 2022-02-26 | 1400/12/07 | 2022-03-05 | 1400/12/17 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0057 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PIP-00-01440 | 2021-08-31 | 1400/06/09 | CM-C3 | [6 empty] | 1400-2294-213932 | 2021-09-26 | 1400/07/04 | 2021-09-29 | 1400/07/07 | CM | [10 empty] | D01 | IFA | T-0240 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PIP-00-02069 | 2021-11-21 | 1400/08/30 | CM-C3 | PEDCO-BK-W018S-PEDCO-110-PI-PY-0001-D00 | [5 empty] | 1400-2294-310810 | 2021-12-08 | 1400/09/17 | 2021-12-12 | 1400/09/21 | CM | NISOC-BK-W018S-PEDCO-110-PI-PY-0001-D00 | [9 empty] | D02 | IFA | T-0526 | 2022-01-31 | 1400/11/11 | [7 empty] | PEDCO-CRS-BK-W018S-PEDCO-110-PI-PY-0001_D01 | [5 empty] | 1400-2294-424550 | 2022-02-26 | 1400/12/07 | 2022-03-05 | 1400/12/17 | AP | NISOC-CRS-BK-W018S-PEDCO-110-PI-PY-0001_D01
2 | 2 | 1 | 2 | 1 | 0 | 2 | 2.2.1.2.1 | Piping Plan - W018S | BK-W018S-PEDCO-110-PI-DW-0001 | BK-W018S-PEDCO-110-PI-DW-0001 | BK | W018S | PEDCO | 110 | PI | DW | 0001 | F4L-707434 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 1 | 2 | 1 | 0 | 3 | 2.2.1.2.1 | Isometric Drawings - W018S | BK-W018S-PEDCO-110-PI-DW-0002 | BK-W018S-PEDCO-110-PI-DW-0002 | BK | W018S | PEDCO | 110 | PI | DW | 0002 | F2L-707435 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 1 | 2 | 1 | 0 | 4 | 2.2.1.2.1 | Material Flow Diagram - W018S | BK-W018S-PEDCO-110-PI-DG-0001 | BK-W018S-PEDCO-110-PI-DG-0001 | BK | W018S | PEDCO | 110 | PI | DG | 0001 | F2A-707436 | AFC | IFC | 2021-11-22 | 2021-11-24 | 2021-11-27 | 2 | 3 | 5 | IFA | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-08 | 0 |  | D01 | IFA | T-0932 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04376 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-PI-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0219 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PIP-00-02060 | 2021-11-21 | 1400/08/30 | CM-C3 | [6 empty] | 1400-2294-289400 | 2021-11-24 | 1400/09/03 | 2021-11-27 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0932 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04376 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-DG-0001_D00 | [11 empty] | NISOC-CRS-BK-W018S-PEDCO-110-PI-DG-0001_D00
2 | 2 | 1 | 2 | 2 | 0 | 0 | 2.2.1.2.2 | List
2 | 2 | 1 | 2 | 2 | 0 | 1 | 2.2.1.2.2 | Piping Support List - W018S | BK-W018S-PEDCO-110-PI-LI-0001 | BK-W018S-PEDCO-110-PI-LI-0001 | BK | W018S | PEDCO | 110 | PI | LI | 0001 | F0Z-707437 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 1 | 2 | 2 | 0 | 2 | 2.2.1.2.2 | Critical Line List - W018S | BK-W018S-PEDCO-110-PI-LI-0002 | BK-W018S-PEDCO-110-PI-LI-0002 | BK | W018S | PEDCO | 110 | PI | LI | 0002 | F0Z-707438 | AFC | IFC | 2022-05-11 | 0 | 0 | -44692 | 0 | -44692 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-27 | 0 |  | D00 | IFC | T-0872 | 2022-04-27 | 1401/02/07 | T-0872 | 2022-04-27 | 1401/02/07 | BK-SUR-ENG-PIP-01-04121 | 2022-05-02 | 1401/02/12 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0872 | 2022-04-27 | 1401/02/07 | T-0872 | 2022-04-27 | 1401/02/07 | BK-SUR-ENG-PIP-01-04121 | 2022-05-02 | 1401/02/12 | C4-RJ
2 | 2 | 1 | 2 | 3 | 0 | 0 | 2.2.1.2.3 | Report
2 | 2 | 1 | 2 | 3 | 0 | 1 | 2.2.1.2.3 | PDMS Model Review Report (60%) - W018S | BK-W018S-PEDCO-110-PI-RT-0001 | BK-W018S-PEDCO-110-PI-RT-0001 | BK | W018S | PEDCO | 110 | PI | RT | 0001 | F0Z-707439 | AFC | IFC | 2022-04-18 | 2022-04-07 | 2022-04-11 | -11 | 4 | -7 | IFA | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-04 | 0 |  | D01 | IFA | T-0932 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04376 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-PI-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0774 | 2022-04-04 | 1401/01/15 |  |  |  | BK-SUR-ENG-PIP-01-03849 | 2022-04-11 | 1401/01/22 | CM-C2 | [6 empty] | 1401-2294-13831 | 2022-04-07 | 1401/01/18 | 2022-04-11 | 1401/01/22 | CM | [10 empty] | D01 | IFA | T-0932 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04376 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-RT-0001_D00 | [11 empty] | NISOC-CRS-BK-W018S-PEDCO-110-PI-RT-0001_D00
2 | 2 | 1 | 2 | 3 | 0 | 2 | 2.2.1.2.3 | PDMS Model Review Report (90%) - W018S | BK-W018S-PEDCO-110-PI-RT-0002 | BK-W018S-PEDCO-110-PI-RT-0002 | BK | W018S | PEDCO | 110 | PI | RT | 0002 | F0Z-707440 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 1 | 2 | 4 | 0 | 0 | 2.2.1.2.4 | MTO
2 | 2 | 1 | 2 | 4 | 0 | 1 | 2.2.1.2 | MTO For Pipes - W018S | BK-W018S-PEDCO-110-PI-MT-0001 | BK-W018S-PEDCO-110-PI-MT-0001 | BK | W018S | PEDCO | 110 | PI | MT | 0001 | F8Z-707441 | IFI | IFI | 2021-12-18 | 2021-12-13 | 2021-12-15 | -5 | 2 | -3 | IFI | 2022-05-01 | 2022-04-28 | 2022-05-02 | -3 | 4 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-04 | 2022-04-17 |  | D01 | IFI | T-0829 | 2022-04-17 | 1401/01/28 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04062 | 2022-04-26 | 1401/02/07 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42948 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0290 | 2021-12-04 | 1400/09/13 |  |  |  | BK-SUR-ENG-PIP-00-02319 | 2021-12-15 | 1400/09/24 | CM-C2 | [6 empty] | 1400-2294-316961 | 2021-12-13 | 1400/09/22 | 2021-12-15 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-0829 | 2022-04-17 | 1401/01/28 |  |  |  | BK-SUR-ENG-PIP-01-04062 | 2022-04-26 | 1401/02/07 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0001_D00 | [5 empty] | 1401-2294-42948 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0001_D00
2 | 2 | 1 | 2 | 4 | 0 | 2 | 2.2.1.2 | MTO For Fittings - W018S | BK-W018S-PEDCO-110-PI-MT-0002 | BK-W018S-PEDCO-110-PI-MT-0002 | BK | W018S | PEDCO | 110 | PI | MT | 0002 | F8Z-707442 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-20 | 2022-04-16 |  | D01 | IFI | T-0823 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04060 | 2022-04-26 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-429743 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0367 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02477 | 2021-12-29 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337967 | 2021-12-27 | 1400/10/06 | 2021-12-29 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0823 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04060 | 2022-04-26 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0002_D00 | [5 empty] | 1401-2294-429743 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0002_D00
2 | 2 | 1 | 2 | 4 | 0 | 3 | 2.2.1.2 | MTO For Flanges - W018S | BK-W018S-PEDCO-110-PI-MT-0003 | BK-W018S-PEDCO-110-PI-MT-0003 | BK | W018S | PEDCO | 110 | PI | MT | 0003 | F8Z-707443 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-20 | 2022-04-16 |  | D01 | IFI | T-0823 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04060 | 2022-04-26 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-429743 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0367 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02477 | 2021-12-29 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337967 | 2021-12-27 | 1400/10/06 | 2021-12-29 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0823 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04060 | 2022-04-26 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0003_D00 | [5 empty] | 1401-2294-429743 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0003_D00
2 | 2 | 1 | 2 | 4 | 0 | 4 | 2.2.1.2 | MTO For Manual Valves - W018S | BK-W018S-PEDCO-110-PI-MT-0004 | BK-W018S-PEDCO-110-PI-MT-0004 | BK | W018S | PEDCO | 110 | PI | MT | 0004 | F8Z-707444 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-20 | 2022-04-16 |  | D01 | IFI | T-0823 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04060 | 2022-04-26 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-429743 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0367 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02477 | 2021-12-29 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337967 | 2021-12-27 | 1400/10/06 | 2021-12-29 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0823 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04060 | 2022-04-26 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0004_D00 | [5 empty] | 1401-2294-429743 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0004_D00
2 | 2 | 1 | 2 | 4 | 0 | 5 | 2.2.1.2 | MTO For Gaskets - W018S | BK-W018S-PEDCO-110-PI-MT-0005 | BK-W018S-PEDCO-110-PI-MT-0005 | BK | W018S | PEDCO | 110 | PI | MT | 0005 | F8Z-707445 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-20 | 2022-04-16 |  | D01 | IFI | T-0823 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04060 | 2022-04-26 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-429743 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0367 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02477 | 2021-12-29 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337967 | 2021-12-27 | 1400/10/06 | 2021-12-29 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0823 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04060 | 2022-04-26 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0005_D00 | [5 empty] | 1401-2294-429743 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0005_D00
2 | 2 | 1 | 2 | 4 | 0 | 6 | 2.2.1.2 | MTO For Bolt & Nuts - W018S | BK-W018S-PEDCO-110-PI-MT-0006 | BK-W018S-PEDCO-110-PI-MT-0006 | BK | W018S | PEDCO | 110 | PI | MT | 0006 | F8Z-707446 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-20 | 2022-04-16 |  | D01 | IFI | T-0823 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04060 | 2022-04-26 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-429743 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0367 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02477 | 2021-12-29 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337967 | 2021-12-27 | 1400/10/06 | 2021-12-29 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0823 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04060 | 2022-04-26 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-PI-MT-0006_D00 | [5 empty] | 1401-2294-429743 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-PI-MT-0006_D00
2 | 2 | 1 | 3 | 0 | 0 | 0 | 2.2.1.3 | Pipeline & Flow line
2 | 2 | 1 | 3 | 1 | 0 | 0 | 2.2.1.3.1 | Drawing/Diagram
2 | 2 | 1 | 3 | 1 | 0 | 1 | 2.2.1.3.1 | Flow line Transversal Drawings - W018S | BK-W018S-PEDCO-110-PL-DW-0002 | BK-W018S-PEDCO-110-PL-DW-0002 | BK | W018S | PEDCO | 110 | PL | DW | 0002 | F4A-707447 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 1 | 3 | 2 | 0 | 0 | 2.2.1.3.2 | List
2 | 2 | 1 | 3 | 2 | 0 | 1 | 2.2.1.3.2 | Road Crossing Location List | BK-W018S-PEDCO-110-PL-LI-0001 | BK-W018S-PEDCO-110-PL-LI-0001 | BK | W018S | PEDCO | 110 | PL | LI | 0001 | F0Z-707448 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 1 | 3 | 3 | 0 | 0 | 2.2.1.3.3 | MTO
2 | 2 | 1 | 3 | 3 | 0 | 1 | 2.2.1.3 | MTO For Line Pipes (Flow lines) - W018S | BK-W018S-PEDCO-110-PL-MT-0001 | BK-W018S-PEDCO-110-PL-MT-0001 | BK | W018S | PEDCO | 110 | PL | MT | 0001 | F8Z-707449 | IFI | IFI | 44444 | 44438 | 44444 | -6 | 6 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2021-08-22 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | 1400/05/31 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | 1400/05/31 | CM-C2 | [6 empty] | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM
2 | 2 | 1 | 4 | 0 | 0 | 0 | 2.2.1.4 | Control & Instrumentation
2 | 2 | 1 | 4 | 1 | 0 | 0 | 2.2.1.4.1 | Drawing/Diagram
2 | 2 | 1 | 4 | 1 | 0 | 1 | 2.2.1.4.1 | Instrument Location Layout Drawing - W018S | BK-W018S-PEDCO-110-IN-PY-0001 | BK-W018S-PEDCO-110-IN-PY-0001 | BK | W018S | PEDCO | 110 | IN | PY | 0001 | F2J-707450 | AFC | IFC | 44629 | 44636 | 44647 | 7 | 11 | 18 | IFA | 44689 | 44702 | 44704 | 13 | 2 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-23 | 0 |  | D01 | IFA | T-0858 | 2022-04-24 | 1401/02/04 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04171 | 2022-05-08 | 1401/02/18 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-68583 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0633 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-INS-00-03437 | 2022-03-09 | 1400/12/18 | CM-C3 | [6 empty] | 1400-2294-453220 | 2022-03-16 | 1400/12/25 | 2022-03-27 | 1401/01/07 | CM | [10 empty] | D01 | IFA | T-0858 | 2022-04-24 | 1401/02/04 |  |  |  | BK-SUR-ENG-INS-01-04171 | 2022-05-08 | 1401/02/18 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-PY-0001_D00 | [5 empty] | 1401-2294-68583 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-PY-0001_D00
2 | 2 | 1 | 4 | 2 | 0 | 0 | 2.2.1.4.2 | MTO
2 | 2 | 1 | 4 | 2 | 0 | 1 | 2.2.1.4 | MTO For Instrument Tube and Fitting - W018S | BK-W018S-PEDCO-110-IN-MT-0001 | BK-W018S-PEDCO-110-IN-MT-0001 | BK | W018S | PEDCO | 110 | IN | MT | 0001 | F8Z-707451 | IFI | IFI | 2021-11-28 | 2021-11-21 | 2021-11-29 | -7 | 8 | 1 | IFI | 2022-01-01 | 2022-01-03 | 2022-01-05 | 2 | 2 | 4 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-14 | 2022-01-12 |  | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W018N-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0237 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02141 | 2021-11-28 | 1400/09/08 | C4-RJ | [6 empty] | 1400-2294-283475 | 2021-11-21 | 1400/08/30 | 2021-11-29 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0359 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-INS-00-02494 | 2022-01-01 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-MT-0001_D00 | [5 empty] | 1400-2294-347953 | 2022-01-03 | 1400/10/13 | 2022-01-05 | 1400/10/15 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-MT-0001_D00 | [9 empty] | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W018N-PEDCO-110-IN-MT-0001_D01 | [5 empty] | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-IN-MT-0001_D01
2 | 2 | 1 | 4 | 2 | 0 | 2 | 2.2.1.4 | MTO For Instrument Cable Tray - W018S | BK-W018S-PEDCO-110-IN-MT-0002 | BK-W018S-PEDCO-110-IN-MT-0002 | BK | W018S | PEDCO | 110 | IN | MT | 0002 | F8Z-707452 | IFI | IFI | 2021-11-28 | 2021-11-21 | 2021-11-29 | -7 | 8 | 1 | IFI | 2022-01-01 | 2022-01-03 | 2022-01-05 | 2 | 2 | 4 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-14 | 2022-01-12 |  | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W018N-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0237 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02141 | 2021-11-28 | 1400/09/08 | C4-RJ | [6 empty] | 1400-2294-283475 | 2021-11-21 | 1400/08/30 | 2021-11-29 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0359 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-INS-00-02494 | 2022-01-01 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-MT-0002_D00 | [5 empty] | 1400-2294-347953 | 2022-01-03 | 1400/10/13 | 2022-01-05 | 1400/10/15 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-MT-0002_D00 | [9 empty] | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W018N-PEDCO-110-IN-MT-0002_D01 | [5 empty] | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W018S-PEDCO-110-IN-MT-0002_D01
2 | 2 | 1 | 5 | 0 | 0 | 0 | 2.2.1.5 | Safety
2 | 2 | 1 | 5 | 1 | 0 | 0 | 2.2.1.5.1 | Drawing/Diagram
2 | 2 | 1 | 5 | 1 | 0 | 1 | 2.2.1.5.1 | Hazardous Area Classification Layout - W018S | BK-W018S-PEDCO-110-SA-PY-0001 | BK-W018S-PEDCO-110-SA-PY-0001 | BK | W018S | PEDCO | 110 | SA | PY | 0001 | F2L-707453 | AFC | IFC | 2021-11-29 | 2021-12-06 | 2022-04-19 | 7 | 134 | 141 | AFC | 2022-05-15 | 2022-05-09 | 2022-05-21 | -6 | 12 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 2022-05-01 |  | D01 | AFC | T-0887 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54966 | 2022-05-09 | 1401/02/19 | 2022-05-21 | 1401/02/31 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0248 | 2021-11-15 | 1400/08/24 | [13 empty] | 1400-2294-305726 | 2021-12-06 | 1400/09/15 | 2022-04-19 | 1401/01/30 | AP | [10 empty] | D01 | AFC | T-0887 | 2022-05-01 | 1401/02/11 | [13 empty] | 1401-2294-54966 | 2022-05-09 | 1401/02/19 | 2022-05-21 | 1401/02/31 | AP
2 | 2 | 1 | 5 | 1 | 0 | 2 | 2.2.1.5.1 | Safety & Fire Fighting Equipment Location Layout - W018S | BK-W018S-PEDCO-110-SA-PY-0002 | BK-W018S-PEDCO-110-SA-PY-0002 | BK | W018S | PEDCO | 110 | SA | PY | 0002 | F2L-707454 | AFC | IFC | 2021-09-21 | 2021-09-21 | 2021-09-25 | 0 | 4 | 4 | IFA | 2021-10-17 | 2021-10-19 | 2021-10-23 | 2 | 4 | 6 | AFC | 2022-05-03 | 2022-04-30 | 2022-05-07 | -3 | 7 | 4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-07 | 2022-04-19 |  | D02 | AFC | T-0843 | 2022-04-19 | 1401/01/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-45395 | 2022-04-30 | 1401/02/10 | 2022-05-07 | 1401/02/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0080 | 2021-09-07 | 1400/06/16 | [13 empty] | 1400-2294-207960 | 2021-09-21 | 1400/06/31 | 2021-09-25 | 1400/07/03 | CM | [10 empty] | D01 | IFA | T-0131 | 2021-10-03 | 1400/07/10 | [13 empty] | 1400-2294-240499 | 2021-10-19 | 1400/07/27 | 2021-10-23 | 1400/08/01 | AP | NISOC-CRS-BK-W018S-PEDCO-110-SA-PY-0002_D00 | 1400-2294-241737 | 2021-10-19 | 1400/07/27 |  |  | AP |  |  |  | D02 | AFC | T-0843 | 2022-04-19 | 1401/01/30 | [13 empty] | 1401-2294-45395 | 2022-04-30 | 1401/02/10 | 2022-05-07 | 1401/02/17 | AP
2 | 2 | 1 | 5 | 1 | 0 | 3 | 2.2.1.5.1 | Escape Route & Safety Sign Layout - W018S | BK-W018S-PEDCO-110-SA-PY-0003 | BK-W018S-PEDCO-110-SA-PY-0003 | BK | W018S | PEDCO | 110 | SA | PY | 0003 | F2L-707455 | AFC | IFC | 2021-11-29 | 2021-12-06 | 2022-04-19 | 7 | 134 | 141 | AFC | 2022-05-30 | 2022-05-21 | 2022-05-23 | -9 | 2 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 2022-05-16 |  | D01 | AFC | T-0956 | 2022-05-16 | 1401/02/26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70735 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0248 | 2021-11-15 | 1400/08/24 | [13 empty] | 1400-2294-305726 | 2021-12-06 | 1400/09/15 | 2022-04-19 | 1401/01/30 | AP | [10 empty] | D01 | AFC | T-0956 | 2022-05-16 | 1401/02/26 | [13 empty] | 1401-2294-70735 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | AP
2 | 2 | 1 | 5 | 2 | 0 | 0 | 2.2.1.5.2 | List
2 | 2 | 1 | 5 | 2 | 0 | 1 | 2.2.1.5.2 | Hazard Source List - W018S | BK-W018S-PEDCO-110-SA-LI-0001 | BK-W018S-PEDCO-110-SA-LI-0001 | BK | W018S | PEDCO | 110 | SA | LI | 0001 | F0Z-707456 | AFC | IFC | 44523 | 44530 | 44536 | 7 | 6 | 13 | IFA | 44608 | 44628 | 44626 | 20 | -2 | 18 | IFA | 44677 | 0 | 0 | -44677 | 0 | -44677 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-09 | 0 |  | D02 | IFA | T-0806 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-SA-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0220 | 2021-11-09 | 1400/08/18 | [13 empty] | 1400-2290-298651 | 2021-11-30 | 1400/09/09 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0544 | 2022-02-02 | 1400/11/13 | [13 empty] | 1400-2294-435413 | 2022-03-08 | 1400/12/15 | 2022-03-06 | 1400/12/15 | CM | NISOC-CRS-BK-W018S-PEDCO-110-SA-LI-0001_D00 | [9 empty] | D02 | IFA | T-0806 | 2022-04-12 | 1401/01/23 | [19 empty] | NISOC-CRS-BK-W018S-PEDCO-110-SA-LI-0001_D01
2 | 2 | 1 | 5 | 3 | 0 | 0 | 2.2.1.5.3 | MTO
2 | 2 | 1 | 5 | 3 | 0 | 1 | 2.2.1.5 | MTO For Fire Fighting & Safety Equipment - W018S | BK-W018S-PEDCO-110-SA-MT-0001 | BK-W018S-PEDCO-110-SA-MT-0001 | BK | W018S | PEDCO | 110 | SA | MT | 0001 | F8Z-707457 | IFI | IFI | 2021-11-29 | 2021-12-06 | 2022-02-22 | 7 | 78 | 85 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 2021-11-15 |  | D00 | IFI | T-0245 | 2021-11-15 | 1400/08/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-305188 | 2021-12-06 | 1400/09/15 | 2022-02-22 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0245 | 2021-11-15 | 1400/08/24 | [13 empty] | 1400-2294-305188 | 2021-12-06 | 1400/09/15 | 2022-02-22 | 1400/12/03 | AP
2 | 2 | 1 | 5 | 3 | 0 | 2 | 2.2.1.5 | MTO For Safety Sign - W018S | BK-W018S-PEDCO-110-SA-MT-0002 | BK-W018S-PEDCO-110-SA-MT-0002 | BK | W018S | PEDCO | 110 | SA | MT | 0002 | F8Z-707458 | IFI | IFI | 2021-11-29 | 2021-12-06 | 2022-02-22 | 7 | 78 | 85 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 2021-11-15 |  | D00 | IFI | T-0245 | 2021-11-15 | 1400/08/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-305188 | 2021-12-06 | 1400/09/15 | 2022-02-22 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0245 | 2021-11-15 | 1400/08/24 | [13 empty] | 1400-2294-305188 | 2021-12-06 | 1400/09/15 | 2022-02-22 | 1400/12/03 | AP
2 | 2 | 1 | 6 | 0 | 0 | 0 | 2.2.1.6 | Architecture
2 | 2 | 1 | 6 | 1 | 0 | 0 | 2.2.1.6.1 | Drawing/Diagram
2 | 2 | 1 | 6 | 1 | 0 | 1 | 2.2.1.6 | Architectural Drawing For WHCP/HPU Shelter of Well Pads - W018 | BK-W018S-PEDCO-110-AR-DW-0001 | BK-W018S-PEDCO-110-AR-DW-0001 | BK | W018S | PEDCO | 110 | AR | DW | 0001 | F4A-707459 | AFC | IFC | 44627 | 44619 | 44628 | -8 | 9 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-21 | 0 |  | D00 | IFC | T-0617 | 2022-02-21 | 1400/12/02 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-03203 | 2022-02-23 | 1400/12/04 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-427462 | 2022-02-27 | 1400/12/08 | 2022-03-08 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0617 | 2022-02-21 | 1400/12/02 |  |  |  | BK-SUR-ENG-ARC-00-03203 | 2022-02-23 | 1400/12/04 | CM-C2 | [6 empty] | 1400-2294-427462 | 2022-02-27 | 1400/12/08 | 2022-03-08 | 1400/12/17 | AP
2 | 2 | 1 | 7 | 0 | 0 | 0 | 2.2.1.7 | Civil
2 | 2 | 1 | 7 | 1 | 0 | 0 | 2.2.1.7.1 | Drawing/Diagram
2 | 2 | 1 | 7 | 1 | 0 | 1 | 2.2.1.7.1 | General Civil Layout - W018S | BK-W018S-PEDCO-110-CV-PY-0001 | BK-W018S-PEDCO-110-CV-PY-0001 | BK | W018S | PEDCO | 110 | CV | PY | 0001 | F4A-707460 | AFC | IFC | 2021-08-11 | 2021-08-03 | 2021-08-07 | -8 | 4 | -4 | IFA | 2021-09-11 | 2021-08-29 | 2021-09-04 | -13 | 6 | -7 | IFA | 2021-09-27 | 2021-09-18 | 2021-09-18 | -9 | 0 | -9 | IFA | 2021-11-06 | 2021-10-29 | 2021-11-02 | -8 | 4 | -4 | AFC | 2021-12-04 | 2021-11-23 | 2021-11-27 | -11 | 4 | -7 | AFC | 2022-01-10 | 2021-12-30 | 2022-01-02 | -11 | 3 | -8 | Modify | 2021-07-28 | 2021-12-27 |  | D05 | AFC | T-0384 | 2021-12-27 | 1400/10/06 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-02525 | 2022-01-02 | 1400/10/12 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D04 | 0 | 0 | 0 | 0 | 0 | 1400-2294-342104 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0018 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-CIV-00-01260 | 2021-08-04 | 1400/05/13 | CM-C3 |  | نقشه شماتيك Waste management موقعيت W018 | 2021-08-11 | 1400/05/20 | CM |  | 1400/2294/152141 | 2021-08-03 | 1400/05/12 | 2021-08-07 | 1400/05/16 | CM | [10 empty] | D01 | IFA | T-0067 | 2021-08-28 | 1400/06/06 |  |  |  | BK-SUR-ENG-CIV-00-01432 | 2021-08-30 | 1400/06/08 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D00 | [5 empty] | 1400-2294-177757 | 2021-08-29 | 1400/06/07 | 2021-09-04 | 1400/06/13 | CM | NISOC-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D00 | [9 empty] | D02 | IFA | T-0089 | 2021-09-13 | 1400/06/22 |  |  |  | BK-SUR-ENG-CIV-00-01544 | 2021-09-18 | 1400/06/27 | C4-RJ | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D01 | [5 empty] | 1400-2294-200540 | 2021-09-18 | 1400/06/27 | 2021-09-18 | 1400/06/27 | CM | NISOC-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D01 | [9 empty] | D03 | IFA | T-0180 | 2021-10-23 | 1400/08/01 |  |  |  | BK-SUR-ENG-CIV-00-01871 | 2021-10-31 | 1400/08/09 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D02 | [5 empty] | 1400-2294-251688 | 2021-10-29 | 1400/08/07 | 2021-11-02 | 1400/08/11 | AP | NISOC-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D02 | [9 empty] | D04 | AFC | T-0257 | 2021-11-20 | 1400/08/29 |  |  |  | BK-SUR-ENG-CIV-00-02056 | 2021-11-21 | 1400/08/30 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D03 | [5 empty] | 1400-2294-287963 | 2021-11-23 | 1400/09/02 | 2021-11-27 | 1400/09/06 | AP | NISOC-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D03 | [9 empty] | D05 | AFC | T-0384 | 2021-12-27 | 1400/10/06 |  |  |  | BK-SUR-ENG-CIV-00-02525 | 2022-01-02 | 1400/10/12 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0001_D04 | [5 empty] | 1400-2294-342104 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | AP
2 | 2 | 1 | 7 | 1 | 0 | 2 | 2.2.1.7.1 | Civil and Structural drawings - W018S | BK-W018S-PEDCO-110-CV-PY-0002 | BK-W018S-PEDCO-110-CV-PY-0002 | BK | W018S | PEDCO | 110 | CV | PY | 0002 | F4S-707461 | AFC | IFC | 2021-08-11 | 2021-08-03 | 2021-08-07 | -8 | 4 | -4 | IFA | 2022-01-18 | 2022-01-08 | 2022-01-11 | -10 | 3 | -7 | AFC | 2022-03-19 | 0 | 0 | -44639 | 0 | -44639 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 2022-03-05 |  | D02 | AFC | T-0673 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-CV-PY-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0021 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-CIV-00-01261 | 2021-08-04 | 1400/05/13 | CM-C3 | [6 empty] | 1400/2294/152142 | 2021-08-03 | 1400/05/12 | 2021-08-07 | 1400/05/16 | CM | [10 empty] | D01 | IFA | T-0425 | 2022-01-04 | 1400/10/14 |  |  |  | BK-SUR-ENG-CIV-00-02642 | 2022-01-11 | 1400/10/21 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0002-D01 | [5 empty] | 1400-2294-354625 | 2022-01-08 | 1400/10/18 | 2022-01-11 | 1400/10/21 | AP | NISOC-CRS-BK-W018S-PEDCO-110-CV-PY-0002-D01 | [9 empty] | D02 | AFC | T-0673 | 2022-03-05 | 1400/12/14 | [7 empty] | PEDCO-CRS-BK-W018S-PEDCO-110-CV-PY-0002_D01 | [11 empty] | NISOC-CRS-BK-W018S-PEDCO-110-CV-PY-0002_D01
2 | 2 | 1 | 7 | 1 | 0 | 3 | 2.2.1.7.1 | Rough Grading Plans -W018S | BK-W018S-PEDCO-110-CV-DW-0001 | BK-W018S-PEDCO-110-CV-DW-0001 | BK | W018S | PEDCO | 110 | CV | DW | 0001 | F4S-707462 | AFC | IFC | 2021-08-11 | 2021-08-03 | 2021-08-07 | -8 | 4 | -4 | IFC | 2021-11-13 | 2021-11-02 | 2021-11-06 | -11 | 4 | -7 | IFA | 2022-01-29 | 2022-01-20 | 2022-01-22 | -9 | 2 | -7 | IFA | 2022-03-12 | 2022-03-02 | 2022-03-05 | -10 | 3 | -7 | AFC | 2022-03-27 | 2022-03-16 | 2022-03-27 | -11 | 11 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-30 | 2022-03-13 |  | D03 | AFC | T-0727 | 2022-03-13 | 1400/12/22 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03505 | 2022-03-13 | 1400/12/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-453185 | 2022-03-16 | 1400/12/25 | 2022-03-27 | 1401/01/07 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0017 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-CIV-00-01259 | 2021-08-04 | 1400/05/13 | CM | [6 empty] | 1400/2294/152130 | 2021-08-03 | 1400/05/12 | 2021-08-07 | 1400/05/16 | RJ | [10 empty] | D00 | IFC | T-0195 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-CIV-00-01905 | 2021-11-03 | 1400/08/12 | CM-C2 | [6 empty] | 1400-2294-259112 | 2021-11-02 | 1400/08/11 | 2021-11-06 | 1400/08/15 | CM | [10 empty] | D01 | IFA | T-0461 | 2022-01-15 | 1400/10/25 |  |  |  | BK-SUR-ENG-CIV-00-02702 | 2022-01-16 | 1400/10/26 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-CV-DW-0001_D00 | [5 empty] | 1400-2294-372851 | 2022-01-20 | 1400/10/30 | 2022-01-22 | 1400/11/02 | CM | NISOC-CRS-BK-W018S-PEDCO-110-CV-DW-0001_D00 | [9 empty] | D02 | IFA | T-0643 | 2022-02-26 | 1400/12/07 | [7 empty] | PEDCO-CRS-BK-W018S-PEDCO-110-CV-DW-0001_D01 | [5 empty] | 1400-2294-431005 | 2022-03-02 | 1400/12/11 | 2022-03-05 | 1400/12/15 | AP | NISOC-CRS-BK-W018S-PEDCO-110-CV-DW-0001_D01 | [9 empty] | D03 | AFC | T-0727 | 2022-03-13 | 1400/12/22 |  |  |  | BK-SUR-ENG-CIV-00-03505 | 2022-03-13 | 1400/12/22 | AP | [6 empty] | 1400-2294-453185 | 2022-03-16 | 1400/12/25 | 2022-03-27 | 1401/01/07 | AP
2 | 2 | 1 | 7 | 2 | 0 | 0 | 2.2.1.7.2 | Calculation
2 | 2 | 1 | 7 | 2 | 0 | 1 | 2.2.1.7.2 | Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W018S | BK-W018S-PEDCO-110-CV-CN-0001 | BK-W018S-PEDCO-110-CV-CN-0001 | BK | W018S | PEDCO | 110 | CV | CN | 0001 | F0Z-707463 | AFC | IFC | 44625 | 44619 | 44614 | -6 | -5 | -11 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 0 |  | D00 | IFC | T-0600 | 2022-02-19 | 1400/11/30 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03411 | 2022-03-08 | 1400/12/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-421741 | 2022-02-27 | 1400/12/08 | 2022-02-22 | 1400/12/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0600 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-CIV-00-03411 | 2022-03-08 | 1400/12/17 | CM-C3 | [6 empty] | 1400-2294-421741 | 2022-02-27 | 1400/12/08 | 2022-02-22 | 1400/12/03 | AP
2 | 2 | 1 | 7 | 3 | 0 | 0 | 2.2.1.7.3 | MTO
2 | 2 | 1 | 7 | 3 | 0 | 1 | 2.2.1.7 | MTO For Civil Works - W018S | BK-W018S-PEDCO-110-CV-MT-0001 | BK-W018S-PEDCO-110-CV-MT-0001 | BK | W018S | PEDCO | 110 | CV | MT | 0001 | F8Z-707464 | IFI | IFI | 44710 | 44702 | 44704 | -8 | 2 | -6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-15 | 2022-05-15 |  | D00 | IFI | T-0955 | 2022-05-15 | 1401/02/25 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-04413 | 2022-05-23 | 1401/03/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-69670 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0955 | 2022-05-15 | 1401/02/25 |  |  |  | BK-SUR-ENG-CIV-01-04413 | 2022-05-23 | 1401/03/02 | AP | [6 empty] | 1401-2294-69670 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | AP
2 | 2 | 1 | 8 | 0 | 0 | 0 | 2.2.1.8 | Structure
2 | 2 | 1 | 8 | 1 | 0 | 0 | 2.2.1.8.1 | Drawing/Diagram
2 | 2 | 1 | 8 | 1 | 0 | 1 | 2.2.1.8.1 | Structure Drawing For WHCP/HPU Shelter - W018S | BK-W018S-PEDCO-110-ST-DW-0001 | BK-W018S-PEDCO-110-ST-DW-0001 | BK | W018S | PEDCO | 110 | ST | DW | 0001 | F4M-707465 | AFC | IFC | 2022-04-10 | 2022-04-03 | 2022-04-09 | -7 | 6 | -1 | IFA | 2022-05-15 | 2022-05-08 | 2022-05-11 | -7 | 3 | -4 | AFC | #VALUE! | 0 | 0 | #VALUE! | 0 | #VALUE! | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-27 | T-0961 |  | D02 | AFC | T-0961 | T-0961 | 1401/02/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W018S-PEDCO-110-ST-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0755 | 2022-03-27 | 1401/01/07 |  |  |  | BK-SUR-ENG-STR-01-03764 | 2022-04-09 | 1401/01/20 | CM | [6 empty] | 1401-2294-7521 | 2022-04-03 | 1401/01/14 | 2022-04-09 | 1401/01/20 | CM | [10 empty] | D01 | IFA | T-0893 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-STR-01-04140 | 2022-05-07 | 1401/02/17 | CM-C2 | PEDCO-CRS-BK-W018S-PEDCO-110-ST-DW-0001_D00 | [5 empty] | 1401-2294-52742 | 2022-05-08 | 1401/02/18 | 2022-05-11 | 1401/02/21 | AP | NISOC-CRS-BK-W018S-PEDCO-110-ST-DW-0001_D00 | [9 empty] | D02 | AFC | T-0961 | T-0961 | 1401/02/2 | [7 empty] | PEDCO-CRS-BK-W018S-PEDCO-110-ST-DW-0001_D01
2 | 2 | 1 | 8 | 1 | 0 | 2 | 2.2.1.8.1 | Platform Structure Drawing - W018S | BK-W018S-PEDCO-110-ST-DW-0002 | BK-W018S-PEDCO-110-ST-DW-0002 | BK | W018S | PEDCO | 110 | ST | DW | 0002 | F4M-707466 | AFC | IFC | 2022-02-16 | 2022-02-08 | 2022-02-13 | -8 | 5 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | IFC | 2022-05-01 | 2022-05-08 | 2022-05-11 | 7 | 3 | 10 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D02 | IFC | T-0832 | 2022-04-17 | 1401/01/28 | 0 | 0 | 0 | BK-SUR-ENG-STR-01-04053 | 2022-04-26 | 1401/02/06 | CM-C3 | PEDCO-CRS-BK-W18S-PEDCO-000-ST-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52739 | 2022-05-08 | 1401/02/18 | 2022-05-11 | 1401/02/21 | RJ | NISOC-CRS-BK-W18S-PEDCO-000-ST-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0535 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-STR-00-03007 | 2022-02-09 | 1400/11/20 | C4-RJ | [6 empty] | 1400-2294-402774 | 2022-02-08 | 1400/11/19 | 2022-02-13 | 1400/11/24 | RJ | [44 empty] | D02 | IFC | T-0832 | 2022-04-17 | 1401/01/28 |  |  |  | BK-SUR-ENG-STR-01-04053 | 2022-04-26 | 1401/02/06 | CM-C3 | PEDCO-CRS-BK-W18S-PEDCO-000-ST-DW-0002_D00 | [5 empty] | 1401-2294-52739 | 2022-05-08 | 1401/02/18 | 2022-05-11 | 1401/02/21 | RJ | NISOC-CRS-BK-W18S-PEDCO-000-ST-DW-0002_D00
[8 empty] | CALCULATION NOTE WHCP/ HPU SHELTER | BK-W018S-PEDCO-110-ST-CN-0003 | BK-W018S-PEDCO-110-ST-CN-0003 | BK | W018S | PEDCO | 110 | ST | CN | 3 | F4M-707467 | AFC | IFC | 2022-05-15 | 2022-05-08 | 2022-05-11 | -7 | 3 | -4 | AFC | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-01 | 2022-05-22 |  | D01 | AFC | T-0961 | 2022-05-22 | 1401/02/02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0894 | 2022-05-01 | 1401/02/11 | [13 empty] | 1401-2294-52752 | 2022-05-08 | 1401/02/18 | 2022-05-11 | 1401/02/21 | AP | [10 empty] | D01 | AFC | T-0961 | 2022-05-22 | 1401/02/02
2 | 2 | 1 | 8 | 2 | 0 | 0 | 2.2.1.8.2 | MTO
2 | 2 | 1 | 8 | 2 | 0 | 1 | 2.2.1.8 | MTO For Structural Works - W018S | BK-W018S-PEDCO-110-ST-MT-0001 | BK-W018S-PEDCO-110-ST-MT-0001 | BK | W018S | PEDCO | 110 | ST | MT | 0001 | F8Z-707467 | IFI | IFI | 44697 | 44690 | 44702 | -7 | 12 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-02 | 2022-05-02 |  | D00 | IFI | T-0896 | 2022-05-02 | 1401/02/12 | 0 | 0 | 0 | BK-SUR-ENG-STR-01-04427 | 2022-05-24 | 1401/03/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54881 | 2022-05-09 | 1401/02/19 | 2022-05-21 | 1401/02/31 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0896 | 2022-05-02 | 1401/02/12 |  |  |  | BK-SUR-ENG-STR-01-04427 | 2022-05-24 | 1401/03/03 | AP | [6 empty] | 1401-2294-54881 | 2022-05-09 | 1401/02/19 | 2022-05-21 | 1401/02/31 | CM
2 | 2 | 1 | 9 | 0 | 0 | 0 | 2.2.1.9 | Geotechnic/Geoelectric
2 | 2 | 1 | 9 | 1 | 0 | 0 | 2.2.1.9.1 | Geotechnic
2 | 2 | 1 | 9 | 1 | 1 | 0 | 2.2.9.1.1 | Report
2 | 2 | 1 | 9 | 1 | 1 | 1 | 2.2.1.9.1.1.1 | Geotechnical Investigation Report - W018S | BK-W018S-PEDCO-110-GT-RT-0001 | BK-W018S-PEDCO-110-GT-RT-0001 | BK | W018S | PEDCO | 110 | GT | RT | 0001 | F0Z-707468 | AFC | IFC | 44632 | 44625 | 44628 | -7 | 3 | -4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-26 | 0 |  | D00 | IFC | T-0641 | 2022-02-26 | 1400/12/07 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03408 | 2022-03-08 | 1400/12/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-435012 | 2022-03-05 | 1400/12/14 | 2022-03-08 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0641 | 2022-02-26 | 1400/12/07 |  |  |  | BK-SUR-ENG-CIV-00-03408 | 2022-03-08 | 1400/12/17 | CM-C3 | [6 empty] | 1400-2294-435012 | 2022-03-05 | 1400/12/14 | 2022-03-08 | 1400/12/17 | CM
2 | 2 | 1 | 9 | 2 | 0 | 0 | 2.2.1.9.2 | Drawing/Diagram
2 | 2 | 1 | 9 | 2 | 0 | 1 | 2.2.1.9 | Flow line Plan & Profile Drawings - W018S | BK-W018S-PEDCO-110-SU-DW-0001 | BK-W018S-PEDCO-110-SU-DW-0001 | BK | W018S | PEDCO | 110 | SU | DW | 0001 | F4A-707469 | AFC | IFC | 44632 | 0 | 0 | -44632 | 0 | -44632 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-26 | 0 |  | D00 | IFC | T-0636 | 2022-02-26 | 1400/12/04 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-03419 | 2022-03-08 | 1400/12/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0636 | 2022-02-26 | 1400/12/04 |  |  |  | BK-SUR-ENG-PPL-00-03419 | 2022-03-08 | 1400/12/17 | CM-C3
2 | 2 | 2 | 0 | 0 | 0 | 0 | 2.2.2 | Procurement Engineering
2 | 2 | 2 | 1 | 0 | 0 | 0 | 2.2.2.1 | Piping
2 | 2 | 2 | 1 | 1 | 0 | 0 | 2.2.2.1.1 | Pipes
2 | 2 | 2 | 1 | 1 | 1 | 0 | 2.2.1.1.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 1 | 1 | 1 | 1 | 2.2.2.1.1.1.1 | PMR For Pipes - W018S | BK-W018S-PEDCO-110-PI-MR-0001 | BK-W018S-PEDCO-110-PI-MR-0001 | BK | W018S | PEDCO | 110 | PI | MR | 0001 | F0Z-707470 | IFI | IFI | 44550 | 44545 | 44545 | -5 | 0 | -5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-06 | 2021-12-06 |  | D00 | IFI | T-0298 | 2021-12-06 | 1400/09/15 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02320 | 2021-12-15 | 1400/09/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-315076 | 2021-12-12 | 1400/09/21 | 2021-12-15 | 1400/09/24 | AP | 0 | 1400-2294-316959 | 2021-12-15 | 1400/09/22 | 0 | 0 | CM | 0 | 0 |  | D00 | IFI | T-0298 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PIP-00-02320 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-315076 | 2021-12-12 | 1400/09/21 | 2021-12-15 | 1400/09/24 | AP |  | 1400-2294-316959 | 2021-12-15 | 1400/09/22 |  |  | CM
2 | 2 | 2 | 1 | 1 | 2 | 0 | 2.2.1.1.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 1 | 2 | 1 | 2.2.2.1.1.2.1 | TBE For Pipes - W018S | BK-W018S-PEDCO-110-PI-TB-0001 | BK-W018S-PEDCO-110-PI-TB-0001 | BK | W018S | PEDCO | 110 | PI | TB | 0001 | F0Z-707471 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 2 | 1 | 2 | 0 | 0 | 2.2.2.1.2 | Fittings
2 | 2 | 2 | 1 | 2 | 1 | 0 | 2.2.1.2.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 1 | 2 | 1 | 1 | 2.2.2.1.2.1.1 | PMR For Fittings - W018S | BK-W018S-PEDCO-110-PI-MR-0002 | BK-W018S-PEDCO-110-PI-MR-0002 | BK | W018S | PEDCO | 110 | PI | MR | 0002 | F0Z-707472 | IFI | IFI | 44681 | 44679 | 44683 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-04-16 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04077 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04077 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ
2 | 2 | 2 | 1 | 2 | 2 | 0 | 2.2.1.2.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 2 | 2 | 1 | 2.2.2.1.2.2.1 | TBE For Fitting - W018S | BK-W018S-PEDCO-110-PI-TB-0002 | BK-W018S-PEDCO-110-PI-TB-0002 | BK | W018S | PEDCO | 110 | PI | TB | 0002 | F0Z-707473 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 2 | 1 | 3 | 0 | 0 | 2.2.2.1.3 | Flanges
2 | 2 | 2 | 1 | 3 | 1 | 0 | 2.2.1.3.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 1 | 3 | 1 | 1 | 2.2.2.1.3.1.1 | PMR For Flanges - W018S | BK-W018S-PEDCO-110-PI-MR-0003 | BK-W018S-PEDCO-110-PI-MR-0003 | BK | W018S | PEDCO | 110 | PI | MR | 0003 | F0Z-707474 | IFI | IFI | 44681 | 44679 | 44683 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-04-16 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04077 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04077 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ
2 | 2 | 2 | 1 | 3 | 2 | 0 | 2.2.1.3.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 3 | 2 | 1 | 2.2.2.1.3.2.1 | TBE For Flanges - W018S | BK-W018S-PEDCO-110-PI-TB-0003 | BK-W018S-PEDCO-110-PI-TB-0003 | BK | W018S | PEDCO | 110 | PI | TB | 0003 | F0Z-707475 | IFI | IFI | 44619 | 44652 | 44625 | 33 | -27 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-13 | 2022-02-13 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03334 | 2022-03-05 | 1400/12/14 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-PIP-00-03334 | 2022-03-05 | 1400/12/14 | C4-RJ | [6 empty] | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | CM
2 | 2 | 2 | 1 | 4 | 0 | 0 | 2.2.2.1.4 | Manual Valves
2 | 2 | 2 | 1 | 4 | 1 | 0 | 2.2.1.4.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 1 | 4 | 1 | 1 | 2.2.2.1.4.1.1 | PMR For Manual Valves - W018S | BK-W018S-PEDCO-110-PI-MR-0004 | BK-W018S-PEDCO-110-PI-MR-0004 | BK | W018S | PEDCO | 110 | PI | MR | 0004 | F0Z-707476 | IFI | IFI | 44681 | 44679 | 44683 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-04-16 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04077 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04077 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ
2 | 2 | 2 | 1 | 4 | 2 | 0 | 2.2.1.4.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 4 | 2 | 1 | 2.2.2.1.4.2.1 | TBE For Manual Valves - W018S | BK-W018S-PEDCO-110-PI-TB-0004 | BK-W018S-PEDCO-110-PI-TB-0004 | BK | W018S | PEDCO | 110 | PI | TB | 0004 | F0Z-707477 | IFI | IFI | 44619 | 44652 | 44625 | 33 | -27 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-13 | 2022-02-13 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03334 | 2022-03-05 | 1400/12/14 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-PIP-00-03334 | 2022-03-05 | 1400/12/14 | C4-RJ | [6 empty] | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | CM
2 | 2 | 2 | 1 | 5 | 0 | 0 | 2.2.2.1.5 | Gaskets
2 | 2 | 2 | 1 | 5 | 1 | 0 | 2.2.1.5.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 1 | 5 | 1 | 1 | 2.2.2.1.5.1.1 | PMR For Gaskets - W018S | BK-W018S-PEDCO-110-PI-MR-0005 | BK-W018S-PEDCO-110-PI-MR-0005 | BK | W018S | PEDCO | 110 | PI | MR | 0005 | F0Z-707478 | IFI | IFI | 44681 | 44679 | 44683 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-04-16 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04077 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04077 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ
2 | 2 | 2 | 1 | 5 | 2 | 0 | 2.2.1.5.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 5 | 2 | 1 | 2.2.2.1.5.2.1 | TBE For Gaskets - W018S | BK-W018S-PEDCO-110-PI-TB-0005 | BK-W018S-PEDCO-110-PI-TB-0005 | BK | W018S | PEDCO | 110 | PI | TB | 0005 | F0Z-707479 | IFI | IFI | 44619 | 44652 | 44625 | 33 | -27 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-13 | 2022-02-13 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03334 | 2022-03-05 | 1400/12/14 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-PIP-00-03334 | 2022-03-05 | 1400/12/14 | C4-RJ | [6 empty] | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | CM
2 | 2 | 2 | 1 | 6 | 0 | 0 | 2.2.2.1.6 | Bolt & Nuts
2 | 2 | 2 | 1 | 6 | 1 | 0 | 2.2.1.6.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 1 | 6 | 1 | 1 | 2.2.2.1.6.1.1 | PMR For Bolt/Nuts - W018S | BK-W018S-PEDCO-110-PI-MR-0006 | BK-W018S-PEDCO-110-PI-MR-0006 | BK | W018S | PEDCO | 110 | PI | MR | 0006 | F0Z-707480 | IFI | IFI | 44681 | 44679 | 44683 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-04-16 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04077 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0822 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04077 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42944 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ
2 | 2 | 2 | 1 | 6 | 2 | 0 | 2.2.1.6.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 6 | 2 | 1 | 2.2.2.1.6.2.1 | TBE For Bolt/Nuts - W018S | BK-W018S-PEDCO-110-PI-TB-0006 | BK-W018S-PEDCO-110-PI-TB-0006 | BK | W018S | PEDCO | 110 | PI | TB | 0006 | F0Z-707481 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 2 | 1 | 7 | 0 | 0 | 2.2.2.1.7 | Sampling Connection
2 | 2 | 2 | 1 | 7 | 1 | 0 | 2.2.1.7.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 1 | 7 | 1 | 1 | 2.2.2.1.7.1.1 | PMR For Sampling Connection Set - W018S | BK-W018S-PEDCO-110-PI-MR-0007 | BK-W018S-PEDCO-110-PI-MR-0007 | BK | W018S | PEDCO | 110 | PI | MR | 0007 | F0Z-707482 | IFI | IFI | 44626 | 44629 | 44627 | 3 | -2 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-02-20 |  | D00 | IFI | T-0613 | 2022-02-20 | 1400/12/01 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03420 | 2022-03-08 | 1400/12/17 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-438859 | 2022-03-09 | 1400/12/18 | 2022-03-07 | 1400/12/16 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0613 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-PIP-00-03420 | 2022-03-08 | 1400/12/17 | CM-C2 | [6 empty] | 1400-2294-438859 | 2022-03-09 | 1400/12/18 | 2022-03-07 | 1400/12/16 | RJ
2 | 2 | 2 | 1 | 7 | 2 | 0 | 2.2.1.7.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 7 | 2 | 1 | 2.2.2.1.7.2.1 | TBE For Sampling Connection | BK-W018S-PEDCO-110-PI-TB-0007 | BK-W018S-PEDCO-110-PI-TB-0007 | BK | W018S | PEDCO | 110 | PI | TB | 0007 | F0Z-707483 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 2 | 1 | 8 | 0 | 0 | 2.2.2.1.8 | Stone Trap
2 | 2 | 2 | 1 | 8 | 1 | 0 | 2.2.1.8.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 1 | 8 | 1 | 1 | 2.2.2.1.8.1.1 | PMR For Stone Trap - W018S | BK-W018S-PEDCO-110-PI-MR-0008 | BK-W018S-PEDCO-110-PI-MR-0008 | BK | W018S | PEDCO | 110 | PI | MR | 0008 | F0Z-707484 | IFI | IFI | 44692 | 44681 | 44695 | -11 | 14 | 3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-27 | 2022-04-27 |  | D00 | IFI | T-0869 | 2022-04-27 | 1401/02/07 | T-0869 | 2022-04-27 | 1401/02/07 | BK-SUR-ENG-PIP-01-04122 | 2022-05-02 | 1401/02/12 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-45413 | 2022-04-30 | 1401/02/10 | 2022-05-14 | 1401/02/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0869 | 2022-04-27 | 1401/02/07 | T-0869 | 2022-04-27 | 1401/02/07 | BK-SUR-ENG-PIP-01-04122 | 2022-05-02 | 1401/02/12 | CM-C2 | [6 empty] | 1401-2294-45413 | 2022-04-30 | 1401/02/10 | 2022-05-14 | 1401/02/24 | CM
2 | 2 | 2 | 1 | 8 | 2 | 0 | 2.2.1.8.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 8 | 2 | 1 | 2.2.2.1.8.2.1 | TBE For Stone Trap - W018S | BK-W018S-PEDCO-110-PI-TB-0008 | BK-W018S-PEDCO-110-PI-TB-0008 | BK | W018S | PEDCO | 110 | PI | TB | 0008 | F0Z-707485 | IFI | IFI | 44719 | 0 | 0 | -44719 | 0 | -44719 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-24 | 2022-05-24 |  | D00 | IFI | T-0996 | 2022-05-24 | 1401/03/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0996 | 2022-05-24 | 1401/03/03
2 | 2 | 2 | 1 | 9 | 0 | 0 | 2.2.2.1.9 | Pipe Support
2 | 2 | 2 | 1 | 9 | 1 | 0 | 2.2.1.9.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 1 | 9 | 1 | 1 | 2.2.2.1.9.1.1 | PMR For Pipe Support - W018S | BK-W018S-PEDCO-110-PI-MR-0010 | BK-W018S-PEDCO-110-PI-MR-0010 | BK | W018S | PEDCO | 110 | PI | MR | 0010 | F0Z-707486 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 2 | 1 | 9 | 2 | 0 | 2.2.1.9.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 1 | 9 | 2 | 1 | 2.2.2.1.9.2.1 | TBE For Pipe Support - W018S | BK-W018S-PEDCO-110-PI-TB-0010 | BK-W018S-PEDCO-110-PI-TB-0010 | BK | W018S | PEDCO | 110 | PI | TB | 0010 | F0Z-707487 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 2 | 2 | 0 | 0 | 0 | 2.2.2.2 | Pipeline
2 | 2 | 2 | 2 | 1 | 0 | 0 | 2.2.2.2.1 | Line Pipe
2 | 2 | 2 | 2 | 1 | 1 | 0 | 2.2.2.1.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 2 | 1 | 1 | 1 | 2.2.2.2.1.1.1 | PMR For Line Pipes - W018S | BK-W018S-PEDCO-110-PL-MR-0001 | BK-W018S-PEDCO-110-PL-MR-0001 | BK | W018S | PEDCO | 110 | PL | MR | 0001 | F0Z-707488 | IFI | IFI | 44550 | 44543 | 44545 | -7 | 2 | -5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-06 | 2021-12-06 |  | D00 | IFI | T-0299 | 2021-12-06 | 1400/09/15 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02321 | 2021-12-15 | 1400/09/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-316957 | 2021-12-13 | 1400/09/22 | 2021-12-15 | 1400/09/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0299 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PPL-00-02321 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-316957 | 2021-12-13 | 1400/09/22 | 2021-12-15 | 1400/09/24 | CM
2 | 2 | 2 | 2 | 1 | 2 | 0 | 2.2.2.1.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 2 | 1 | 2 | 1 | 2.2.2.2.1.2.1 | TBE For Line Pipes - W018S | BK-W018S-PEDCO-110-PL-TB-0001 | BK-W018S-PEDCO-110-PL-TB-0001 | BK | W018S | PEDCO | 110 | PL | TB | 0001 | F0Z-707489 | IFI | IFI | 44625 | 44630 | 44634 | 5 | 4 | 9 | IFI | 44709 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 2022-05-14 |  | D01 | IFI | T-0944 | 2022-05-14 | 1401/02/24 | T-0944 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0604 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PPL-00-03409 | 2022-03-08 | 1400/12/17 | C4-RJ | [6 empty] | 1400-2294-443269 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/23 | CM | [10 empty] | D01 | IFI | T-0944 | 2022-05-14 | 1401/02/24 | T-0944 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PL-TB-0001-D00 | [11 empty] | NISOC-CRS-BK-W018S-PEDCO-110-PL-TB-0001-D00
2 | 2 | 2 | 2 | 2 | 0 | 0 | 2.2.2.2.2 | Line Support
2 | 2 | 2 | 2 | 2 | 1 | 0 | 2.2.2.2.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 2 | 2 | 1 | 1 | 2.2.2.2.2.1.1 | PMR For Flow Line Support - W018S | BK-W018S-PEDCO-110-PL-MR-0002 | BK-W018S-PEDCO-110-PL-MR-0002 | BK | W018S | PEDCO | 110 | PL | MR | 0002 | F0Z-707490 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 2 | 2 | 2 | 2 | 0 | 2.2.2.2.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 2 | 2 | 2 | 1 | 2.2.2.2.2.2.1 | TBE For Flow Line Support - W018S | BK-W018S-PEDCO-110-PL-TB-0002 | BK-W018S-PEDCO-110-PL-TB-0002 | BK | W018S | PEDCO | 110 | PL | TB | 0002 | F0Z-707491 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 2 | 3 | 0 | 0 | 0 | 2.2.2.3 | Control & Instrumentation
2 | 2 | 2 | 3 | 1 | 0 | 0 | 2.2.2.3.1 | WHCP/HPU
2 | 2 | 2 | 3 | 1 | 1 | 0 | 2.2.3.1.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 3 | 1 | 1 | 1 | 2.2.2.3.1.1.1 | PMR For WHCP/HPU - W018S | BK-W018S-PEDCO-110-IN-MR-0001 | BK-W018S-PEDCO-110-IN-MR-0001 | BK | W018S | PEDCO | 110 | IN | MR | 0001 | F0Z-707492 | IFI | IFI | 44529 | 44547 | 44537 | 18 | -10 | 8 | IFI | 44591 | 44592 | 44593 | 1 | 1 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 2022-01-16 |  | D01 | IFI | T-0470 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02865 | 2022-01-30 | 1400/11/10 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-390765 | 2022-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0243 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-INS-00-02170 | 2021-12-01 | 1400/09/10 | C4-RJ |  | BK-SUR-ENG-INS-00-02224 | 2021-12-07 | 1400/09/16 | CM-C3 |  | 1400-2294-320808 | 2021-12-17 | 1400/09/26 | 2021-12-07 | 1400/09/16 | CM | [10 empty] | D01 | IFI | T-0470 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02865 | 2022-01-30 | 1400/11/10 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-MR-0001_D00 | [5 empty] | 1400-2294-390765 | 2022-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-MR-0001_D00
2 | 2 | 2 | 3 | 1 | 2 | 0 | 2.2.3.1.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 3 | 1 | 2 | 1 | 2.2.2.3.1.2.1 | TBE/TBA For WHCP/HPU - W018S | BK-W018S-PEDCO-110-IN-TB-0001 | BK-W018S-PEDCO-110-IN-TB-0001 | BK | W018S | PEDCO | 110 | IN | TB | 0001 | F0Z-707493 | IFI | IFI | 44544 | 44544 | 44545 | 0 | 1 | 1 | IFI | 44625 | 44655 | 44660 | 30 | 5 | 35 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-30 | 2022-02-19 |  | D01 | IFI | T-0602 | 2022-02-19 | 1400/11/30 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03345 | 2022-03-05 | 1400/12/15 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-TB-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-9652 | 2022-04-04 | 1401/01/15 | 2022-04-09 | 1401/01/20 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-TB-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0284 | 2021-11-30 | 1400/09/09 |  |  |  | BK-SUR-ENG-INS-00-02296 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-318638 | 2021-12-14 | 1400/09/23 | 2021-12-15 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-0602 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-INS-00-03345 | 2022-03-05 | 1400/12/15 | CM-C3 | PEDCO-CRS-BK-W018S-PEDCO-110-IN-TB-0001_D00 | [5 empty] | 1401-2294-9652 | 2022-04-04 | 1401/01/15 | 2022-04-09 | 1401/01/20 | CM | NISOC-CRS-BK-W018S-PEDCO-110-IN-TB-0001_D00
2 | 2 | 2 | 3 | 2 | 0 | 0 | 2.2.2.3.2 | Field Instrumentations
2 | 2 | 2 | 3 | 2 | 1 | 0 | 2.2.3.2.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 3 | 2 | 1 | 1 | 2.2.2.3.2.1.1 | PMR For Field Instrumentations - W018S | BK-W018S-PEDCO-110-IN-MR-0002 | BK-W018S-PEDCO-110-IN-MR-0002 | BK | W018S | PEDCO | 110 | IN | MR | 0002 | F0Z-707494 | IFI | IFI | 44557 | 44582 | 44221 | 25 | -361 | -336 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 2021-12-13 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | 1400/10/06 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-330276 | 2022-01-21 | 1400/11/01 | 2021-01-25 | 1400/11/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | 1400/10/06 | CM-C3 | [6 empty] | 1400-2294-330276 | 2022-01-21 | 1400/11/01 | 2021-01-25 | 1400/11/05 | CM
2 | 2 | 2 | 3 | 2 | 2 | 0 | 2.2.3.2.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 3 | 2 | 2 | 1 | 2.2.2.3.2.2.1 | TBE/TBA For Field Instrumentations - W018S | BK-W018S-PEDCO-110-IN-TB-0002 | BK-W018S-PEDCO-110-IN-TB-0002 | BK | W018S | PEDCO | 110 | IN | TB | 0002 | F0Z-707495 | IFI | IFI | 44723 | 0 | 0 | -44723 | 0 | -44723 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-28 | 2022-05-28 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07
2 | 2 | 2 | 3 | 3 | 0 | 0 | 2.2.2.3.3 | Instrument Bulk Items
2 | 2 | 2 | 3 | 3 | 1 | 0 | 2.2.3.3.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 3 | 3 | 1 | 1 | 2.2.2.3.3.1.1 | PMR For Instrument Bulk Items - W018S | BK-W018S-PEDCO-110-IN-MR-0003 | BK-W018S-PEDCO-110-IN-MR-0003 | BK | W018S | PEDCO | 110 | IN | MR | 0003 | F0Z-707496 | IFI | IFI | 44593 | 44626 | 44628 | 33 | 2 | 35 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-18 | 2022-01-18 |  | D00 | IFI | T-0472 | 2022-01-18 | 1400/10/28 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02832 | 2022-01-26 | 1400/11/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-436921 | 2022-03-06 | 1400/12/15 | 2022-03-08 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0472 | 2022-01-18 | 1400/10/28 |  |  |  | BK-SUR-ENG-INS-00-02832 | 2022-01-26 | 1400/11/09 | CM-C2 | [6 empty] | 1400-2294-436921 | 2022-03-06 | 1400/12/15 | 2022-03-08 | 1400/12/17 | CM
2 | 2 | 2 | 3 | 3 | 2 | 0 | 2.2.3.3.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 3 | 3 | 2 | 1 | 2.2.2.3.3.2.1 | TBE/TBA For Instrument Bulk Items - W018S | BK-W018S-PEDCO-110-IN-TB-0003 | BK-W018S-PEDCO-110-IN-TB-0003 | BK | W018S | PEDCO | 110 | IN | TB | 0003 | F0Z-707497 | IFI | IFI | 44608 | 0 | 0 | -44608 | 0 | -44608 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 2022-02-02 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03068 | 2022-02-14 | 1400/11/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03068 | 2022-02-14 | 1400/11/25 | CM-C2
2 | 2 | 2 | 4 | 0 | 0 | 0 | 2.2.2.4 | Safety & Fire Fighting
2 | 2 | 2 | 4 | 1 | 0 | 0 | 2.2.2.4.1 | Fire Fighting and Safety Equipment
2 | 2 | 2 | 4 | 1 | 1 | 0 | 2.2.4.1.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 4 | 1 | 1 | 1 | 2.2.2.4.1.1.1 | PMR For Fire Fighting and Safety Equipment - W018S | BK-W018S-PEDCO-110-SA-MR-0001 | BK-W018S-PEDCO-110-SA-MR-0001 | BK | W018S | PEDCO | 110 | SA | MR | 0001 | F0Z-707498 | IFI | IFI | 44552 | 44550 | 44552 | -2 | 2 | 0 | IFI | 44706 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-08 | 2022-05-11 |  | D01 | IFI | T-0933 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W018S-PEDCO-110-SA-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | CM | [10 empty] | D01 | IFI | T-0933 | 2022-05-11 | 1401/02/21 | [19 empty] | NISOC-CRS-BK-W018S-PEDCO-110-SA-MR-0001_D00
2 | 2 | 2 | 4 | 1 | 2 | 0 | 2.2.4.1.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 4 | 1 | 2 | 1 | 2.2.2.4.1.2.1 | TBE For Fire Fighting and Safety Equipment - W018S | BK-W018S-PEDCO-110-SA-TB-0001 | BK-W018S-PEDCO-110-SA-TB-0001 | BK | W018S | PEDCO | 110 | SA | TB | 0001 | F0Z-707499 | IFI | IFI | 44646 | 0 | 0 | -44646 | 0 | -44646 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-12 | 2022-03-12 |  | D00 | IFI | T-0721 | 2022-03-12 | 1400/12/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0721 | 2022-03-12 | 1400/12/21
2 | 2 | 2 | 4 | 2 | 0 | 0 | 2.2.2.4.2 | Safety Sign
2 | 2 | 2 | 4 | 2 | 1 | 0 | 2.2.4.2.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 4 | 2 | 1 | 1 | 2.2.2.4.2.1.1 | PMR For Fire Safety Sign - W018S | BK-W018S-PEDCO-110-SA-MR-0002 | BK-W018S-PEDCO-110-SA-MR-0002 | BK | W018S | PEDCO | 110 | SA | MR | 0002 | F0Z-707500 | IFI | IFI | 44552 | 44550 | 44552 | -2 | 2 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-08 | 2021-12-08 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP
2 | 2 | 2 | 4 | 2 | 2 | 0 | 2.2.4.2.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 4 | 2 | 2 | 1 | 2.2.2.4.2.2.1 | TBE For Fire Safety Sign - W018S | BK-W018S-PEDCO-110-SA-TB-0002 | BK-W018S-PEDCO-110-SA-TB-0002 | BK | W018S | PEDCO | 110 | SA | TB | 0002 | F0Z-707501 | IFI | IFI | 44646 | 0 | 0 | -44646 | 0 | -44646 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-12 | 2022-03-12 |  | D00 | IFI | T-0721 | 2022-03-12 | 1400/12/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0721 | 2022-03-12 | 1400/12/21
2 | 2 | 2 | 5 | 0 | 0 | 0 | 2.2.2.5 | Structure
2 | 2 | 2 | 5 | 1 | 0 | 0 | 2.2.2.5.1 | Steel Structure Items
2 | 2 | 2 | 5 | 1 | 1 | 0 | 2.2.5.1.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 5 | 1 | 1 | 1 | 2.2.2.5.1.1.1 | PMR For Steel Structure Items - W018S | BK-W018S-PEDCO-110-ST-MR-0001 | BK-W018S-PEDCO-110-ST-MR-0001 | BK | W018S | PEDCO | 110 | ST | MR | 0001 | F0Z-707502 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 2 | 5 | 1 | 2 | 0 | 2.2.5.1.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 5 | 1 | 2 | 1 | 2.2.2.5.1.2.1 | TBE For Steel Structure Items - W018S | BK-W018S-PEDCO-110-ST-TB-0001 | BK-W018S-PEDCO-110-ST-TB-0001 | BK | W018S | PEDCO | 110 | ST | TB | 0001 | F0Z-707503 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 2 | 5 | 2 | 0 | 0 | 2.2.2.5.2 | Anchor Bolts
2 | 2 | 2 | 5 | 2 | 1 | 0 | 2.2.5.2.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 5 | 2 | 1 | 1 | 2.2.2.5.2.1.1 | PMR For Anchor Bolts - W018S | BK-W018S-PEDCO-110-ST-MR-0002 | BK-W018S-PEDCO-110-ST-MR-0002 | BK | W018S | PEDCO | 110 | ST | MR | 0002 | F0Z-707504 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 2 | 5 | 2 | 2 | 0 | 2.2.5.2.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 5 | 2 | 2 | 1 | 2.2.2.5.2.2.1 | TBE For Anchor Bolts - W018S | BK-W018S-PEDCO-110-ST-TB-0002 | BK-W018S-PEDCO-110-ST-TB-0002 | BK | W018S | PEDCO | 110 | ST | TB | 0002 | F0Z-707505 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 2 | 6 | 0 | 0 | 0 | 2.2.2.6 | Civil
2 | 2 | 2 | 6 | 1 | 0 | 0 | 2.2.2.6.1 | Geomembrane
2 | 2 | 2 | 6 | 1 | 1 | 0 | 2.2.6.1.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 6 | 1 | 1 | 1 | 2.2.2.6.1.1.1 | PMR For Geomembrane - W018S | BK-W018S-PEDCO-110-CV-MR-0001 | BK-W018S-PEDCO-110-CV-MR-0001 | BK | W018S | PEDCO | 110 | CV | MR | 0001 | F0Z-707506 | IFI | IFI | 44668 | 44658 | 44661 | -10 | 3 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-03 | 2022-04-03 |  | D00 | IFI | T-0768 | 2022-04-03 | 1401/01/14 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-03846 | 2022-04-11 | 1401/01/22 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-13822 | 2022-04-07 | 1401/01/18 | 2022-04-10 | 1401/01/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0768 | 2022-04-03 | 1401/01/14 |  |  |  | BK-SUR-ENG-CIV-01-03846 | 2022-04-11 | 1401/01/22 | CM-C2 | [6 empty] | 1401-2294-13822 | 2022-04-07 | 1401/01/18 | 2022-04-10 | 1401/01/21 | CM
2 | 2 | 2 | 6 | 1 | 2 | 0 | 2.2.6.1.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 6 | 1 | 2 | 1 | 2.2.2.6.1.2.1 | TBE For Geomembrane - W018S | BK-W018S-PEDCO-110-CV-TB-0001 | BK-W018S-PEDCO-110-CV-TB-0001 | BK | W018S | PEDCO | 110 | CV | TB | 0001 | F0Z-707507 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 2 | 6 | 2 | 0 | 0 | 2.2.2.6.2 | Geotextile
2 | 2 | 2 | 6 | 2 | 1 | 0 | 2.2.6.2.1 | Purchase Material Requisition (PMR)
2 | 2 | 2 | 6 | 2 | 1 | 1 | 2.2.2.6.2.1.1 | PMR For Geotextile - W018S | BK-W018S-PEDCO-110-CV-MR-0002 | BK-W018S-PEDCO-110-CV-MR-0002 | BK | W018S | PEDCO | 110 | CV | MR | 0002 | F0Z-707508 | IFI | IFI | 44668 | 44658 | 44661 | -10 | 3 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-03 | 2022-04-03 |  | D00 | IFI | T-0768 | 2022-04-03 | 1401/01/14 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-03846 | 2022-04-11 | 1401/01/22 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-13822 | 2022-04-07 | 1401/01/18 | 2022-04-10 | 1401/01/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0768 | 2022-04-03 | 1401/01/14 |  |  |  | BK-SUR-ENG-CIV-01-03846 | 2022-04-11 | 1401/01/22 | CM-C2 | [6 empty] | 1401-2294-13822 | 2022-04-07 | 1401/01/18 | 2022-04-10 | 1401/01/21 | CM
2 | 2 | 2 | 6 | 2 | 2 | 0 | 2.2.6.2.2 | Technical Bid Evaluation (TBE)
2 | 2 | 2 | 6 | 2 | 2 | 1 | 2.2.2.6.2.2.1 | TBE For Geotextile - W018S | BK-W018S-PEDCO-110-CV-TB-0002 | BK-W018S-PEDCO-110-CV-TB-0002 | BK | W018S | PEDCO | 110 | CV | TB | 0002 | F0Z-707509 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 3 | 0 | 0 | 0 | 0 | 2.2.3 | Commissioning Engineering
2 | 2 | 3 | 0 | 0 | 1 | 0 | 2.2.3.1 | Procedure/Plan
2 | 2 | 3 | 0 | 0 | 1 | 1 | 2.2.3.1.1 | Pre-Commissioning, Commissioning & Startup Procedure - W018S | BK-W018S-PEDCO-110-CO-PR-0001 | BK-W018S-PEDCO-110-CO-PR-0001 | BK | W018S | PEDCO | 110 | CO | PR | 0001 | F0Z-707510 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 4 | 0 | 0 | 0 | 0 | 2.2.4 | Field Engineering
2 | 2 | 4 | 0 | 0 | 1 | 0 | 2.2.4.1 | Query
2 | 2 | 4 | 0 | 0 | 1 | 1 | 2.2.4.1.1 | Technical/Site Queries | BK-W018S-PEDCO-110-GE-TQ-0001 | BK-W018S-PEDCO-110-GE-TQ-0001 | BK | W018S | PEDCO | 110 | GE | TQ | 0001 | F7Z-707511 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 4 | 0 | 0 | 2 | 0 | 2.2.4.2 | Dossier
2 | 2 | 4 | 0 | 0 | 2 | 1 | 2.2.4.2.1 | As-Built Document Booklets - W018S | BK-W018S-PEDCO-110-GE-DO-0001 | BK-W018S-PEDCO-110-GE-DO-0001 | BK | W018S | PEDCO | 110 | GE | DO | 0001 | F0Z-707512 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 5 | 0 | 0 | 0 | 0 | 2.2.5 | Engineering Final Documentation
2 | 2 | 5 | 0 | 0 | 1 | 0 | 2.2.5.1 | Manual
2 | 2 | 5 | 0 | 0 | 1 | 1 | 2.2.5.1.1 | Operating Manual - W018S | BK-W018S-PEDCO-110-GE-ML-0001 | BK-W018S-PEDCO-110-GE-ML-0001 | BK | W018S | PEDCO | 110 | GE | ML | 0001 | F7Z-707513 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 5 | 0 | 0 | 2 | 0 | 2.2.5.2 | Dossier
2 | 2 | 5 | 0 | 0 | 2 | 1 | 2.2.5.2.1 | As-Built Document Booklets - W018S | BK-W018S-PEDCO-110-GE-DO-0001 | BK-W018S-PEDCO-110-GE-DO-0001 | [7 empty] | F0Z-707512 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 2 | 5 | 0 | 0 | 2 | 2 | 2.2.5.2.2 | Final Engineering Dossier - W018S | BK-W018S-PEDCO-110-GE-DO-0002 | BK-W018S-PEDCO-110-GE-DO-0002 | BK | W018S | PEDCO | 110 | GE | DO | 0002 | F0Z-707514 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 0 | 0 | 0 | 0 | 0 | 2.3 | Package 02-New Well # W028 (Bangestan)
2 | 3 | 1 | 0 | 0 | 0 | 0 | 2.3.1 | Detail Design
2 | 3 | 1 | 1 | 0 | 0 | 0 | 2.3.1.1 | Process
2 | 3 | 1 | 1 | 1 | 0 | 0 | 2.3.1.1.1 | Drawing/Diagram
2 | 3 | 1 | 1 | 1 | 0 | 1 | 2.3.1.1.1 | Process Flow Diagram - W028 | BK-W028-PEDCO-110-PR-PF-0001 | BK-W028-PEDCO-110-PR-PF-0001 | BK | W028 | PEDCO | 110 | PR | PF | 0001 | F2A-707515 | AFC | IFC | 2021-08-28 | 2021-08-30 | 2021-09-06 | 2 | 7 | 9 | IFC | 2021-11-16 | 0 | 0 | -44516 | 0 | -44516 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-02 | 0 |  | D01 | IFC | T-0205 | 2021-11-02 | 1400/08/11 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02020 | 2021-11-16 | 1400/08/25 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PR-PF-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-PR-PF-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0046 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-PCS-00-01394 | 2021-08-24 | 1400/06/02 | CM-C3 | [6 empty] | 1400/2294/179413 | 2021-08-30 | 1400/06/08 | 2021-09-06 | 1400/06/15 | RJ | [10 empty] | D01 | IFC | T-0205 | 2021-11-02 | 1400/08/11 |  |  |  | BK-SUR-ENG-PCS-00-02020 | 2021-11-16 | 1400/08/25 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PR-PF-0001_D00 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-PR-PF-0001_D00
2 | 3 | 1 | 1 | 1 | 0 | 2 | 2.3.1.1.1 | P&ID - W028 | BK-W028-PEDCO-110-PR-PI-0001 | BK-W028-PEDCO-110-PR-PI-0001 | BK | W028 | PEDCO | 110 | PR | PI | 0001 | F2A-707516 | AFC | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-01 | 0 |  | D03 | IFA | T-0653 | 2022-02-28 | 1400/12/09 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 2021-09-08 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0201 | 2021-11-01 | 1400/08/10 |  |  |  | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-279084 | 2021-11-16 | 1400/08/25 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0345 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-PCS-00-02540 | 2022-01-03 | 1400/10/13 | CM-C3 | PEDCO-BK-W028-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-342085 | 2021-12-30 | 1400/10/09 | 2022-01-03 | 1400/10/13 | RJ | NISOC-BK-W028-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0653 | 2022-02-28 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-PI-0001_D02
2 | 3 | 1 | 1 | 2 | 0 | 0 | 2.3.1.1.2 | List
2 | 3 | 1 | 1 | 2 | 0 | 1 | 2.3.1.1.2 | Line List - W028 | BK-W028-PEDCO-110-PR-LI-0001 | BK-W028-PEDCO-110-PR-LI-0001 | BK | W028 | PEDCO | 110 | PR | LI | 0001 | F0Z-707517 | AFC | IFC | 44444 | 44439 | 44447 | -5 | 8 | 3 | IFC | 44522 | 44527 | 44529 | 5 | 2 | 7 | IFA | 44573 | 0 | 0 | -44573 | 0 | -44573 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-08 | 0 |  | D02 | IFA | T-0403 | 2021-12-29 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 2021-09-08 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0217 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PCS-00-02051 | 2021-11-20 | 1400/08/29 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1400-2290-293083 | 2021-11-27 | 1400/09/06 | 2021-11-29 | 1400/09/08 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-LI-0001_D00 | [9 empty] | D02 | IFA | T-0403 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PR-LI-0001_D01 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-PR-LI-0001_D01
2 | 3 | 1 | 1 | 3 | 0 | 0 | 2.3.1.1.3 | Report | [134 empty] | 2021-11-20 | 1400/08/29
2 | 3 | 1 | 1 | 3 | 0 | 1 | 2.3.1.1.3 | Flow line Hydraulic Calculation Report | BK-W028-PEDCO-110-PR-RT-0001 | BK-W028-PEDCO-110-PR-RT-0001 | BK | W028 | PEDCO | 110 | PR | RT | 0001 | F0Z-707518 | AFC | IFC | 44513 | 44514 | 44517 | 1 | 3 | 4 | IFA | 44576 | 44228 | 44597 | -348 | 369 | 21 | IFA | 44628 | 44630 | 44633 | 2 | 3 | 5 | IFA | 44695 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-30 | 0 |  | D03 | IFA | T-0878 | 2022-04-30 | 1401/02/10 | T-0878 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 2022-05-28 | 1402/03/07 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PR-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-PR-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0197 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-PCS-00-01993 | 2021-11-14 | 1400/08/23 | CM-C3 | [6 empty] | 1400-2294-275250 | 2021-11-14 | 1400/08/23 | 2021-11-17 | 1400/08/26 | CM | [10 empty] | D01 | IFA | T-0413 | 2022-01-01 | 1400/10/11 |  |  |  | BK-SUR-ENG-PCS-00-02735 | 2022-01-19 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PR-RT-0001_D00 | [5 empty] | 1400-2294-392131 | 2021-02-01 | 1400/11/12 | 2022-02-05 | 1400/11/16 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-0627 | 2022-02-22 | 1400/12/03 |  |  |  | BK-SUR-ENG-PCS-00-03387 | 2022-03-07 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PR-RT-0001_D01 | [5 empty] | 1400-2294-443285 | 2022-03-10 | 1400/12/19 | 2022-03-13 | 1400/12/22 | CM | NISOC-CRS-BK-W028-PEDCO-110-PR-RT-0001_D01 | [9 empty] | D03 | IFA | T-0878 | 2022-04-30 | 1401/02/10 | T-0878 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 2022-05-28 | 1402/03/07 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PR-RT-0001_D02 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-PR-RT-0001_D02
2 | 3 | 1 | 1 | 4 | 0 | 0 | 2.3.1.1.4 | Data Sheet
2 | 3 | 1 | 1 | 4 | 0 | 1 | 2.3.1.1 | Process Data Sheets For Instrument Devices - W028 | BK-W028-PEDCO-110-PR-DT-0001 | BK-W028-PEDCO-110-PR-DT-0001 | BK | W028 | PEDCO | 110 | PR | DT | 0001 | F0Z-707519 | AFC | IFC | 44677 | 44689 | 44695 | 12 | 6 | 18 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-12 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04093 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 2022-05-14 | 1401/02/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-PCS-01-04093 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 2022-05-14 | 1401/02/24 | CM
2 | 3 | 1 | 2 | 0 | 0 | 0 | 2.3.1.2 | Piping
2 | 3 | 1 | 2 | 1 | 0 | 0 | 2.3.1.2.1 | Drawing/Diagram
2 | 3 | 1 | 2 | 1 | 0 | 1 | 2.3.1.2.1 | Plot Plan Drawing - W028 | BK-W028-PEDCO-110-PI-DW-0001 | BK-W028-PEDCO-110-PI-DW-0001 | BK | W028 | PEDCO | 110 | PI | DW | 0001 | F5A-707520 | AFC | IFC | 2022-02-16 | 2022-04-16 | 2022-04-25 | 59 | 9 | 68 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 0 |  | D00 | IFC | T-0533 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03123 | 2022-02-19 | 1400/11/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-25043 | 2022-04-16 | 1401/01/27 | 2022-04-25 | 1401/02/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0533 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-PIP-00-03123 | 2022-02-19 | 1400/11/30 | CM-C2 | [6 empty] | 1401-2294-25043 | 2022-04-16 | 1401/01/27 | 2022-04-25 | 1401/02/05 | CM
2 | 3 | 1 | 2 | 1 | 0 | 2 | 2.3.1.2.1 | Piping Plan - W028 | BK-W028-PEDCO-110-PI-DW-0002 | BK-W028-PEDCO-110-PI-DW-0002 | BK | W028 | PEDCO | 110 | PI | DW | 0002 | F4L-707521 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 1 | 2 | 1 | 0 | 3 | 2.3.1.2.1 | Isometric Drawings - W028 | BK-W028-PEDCO-110-PI-DW-0003 | BK-W028-PEDCO-110-PI-DW-0003 | BK | W028 | PEDCO | 110 | PI | DW | 0003 | F2L-707522 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 1 | 2 | 1 | 0 | 4 | 2.3.1.2.1 | Material Flow Diagram - W028 | BK-W028-PEDCO-110-PI-DG-0001 | BK-W028-PEDCO-110-PI-DG-0001 | BK | W028 | PEDCO | 110 | PI | DG | 0001 | F2A-707523 | AFC | IFC | 2021-11-22 | 2021-11-24 | 2021-11-27 | 2 | 3 | 5 | IFA | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-08 | 0 |  | D01 | IFA | T-0932 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04376 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PI-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-PI-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0219 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PIP-00-02060 | 2021-11-21 | 1400/08/30 | CM-C3 | [6 empty] | 1400-2294-289400 | 2021-11-24 | 1400/09/03 | 2021-11-27 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0932 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04376 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PI-DG-0001_D00 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-PI-DG-0001_D00
2 | 3 | 1 | 2 | 2 | 0 | 0 | 2.3.1.2.2 | List
2 | 3 | 1 | 2 | 2 | 0 | 1 | 2.3.1.2.2 | Piping Support List - W028 | BK-W028-PEDCO-110-PI-LI-0001 | BK-W028-PEDCO-110-PI-LI-0001 | BK | W028 | PEDCO | 110 | PI | LI | 0001 | F0Z-707524 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 1 | 2 | 2 | 0 | 2 | 2.3.1.2.2 | Critical Line List - W028 | BK-W028-PEDCO-110-PI-LI-0002 | BK-W028-PEDCO-110-PI-LI-0002 | BK | W028 | PEDCO | 110 | PI | LI | 0002 | F0Z-707525 | AFC | IFC | 2022-05-16 | 0 | 0 | -44697 | 0 | -44697 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-02 | 0 |  | D00 | IFC | T-0899 | 2022-05-02 | 1401/02/12 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04153 | 2022-03-07 | 1401/02/17 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0899 | 2022-05-02 | 1401/02/12 |  |  |  | BK-SUR-ENG-PIP-01-04153 | 2022-03-07 | 1401/02/17 | C4-RJ
2 | 3 | 1 | 2 | 3 | 0 | 0 | 2.3.1.2.3 | Report
2 | 3 | 1 | 2 | 3 | 0 | 1 | 2.3.1.2.3 | PDMS Model Review Report (60%) - W028 | BK-W028-PEDCO-110-PI-RT-0001 | BK-W028-PEDCO-110-PI-RT-0001 | BK | W028 | PEDCO | 110 | PI | RT | 0001 | F0Z-707526 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 1 | 2 | 3 | 0 | 2 | 2.3.1.2.3 | PDMS Model Review Report (90%) - W028 | BK-W028-PEDCO-110-PI-RT-0002 | BK-W028-PEDCO-110-PI-RT-0002 | BK | W028 | PEDCO | 110 | PI | RT | 0002 | F0Z-707527 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 1 | 2 | 4 | 0 | 0 | 2.3.1.2.4 | MTO
2 | 3 | 1 | 2 | 4 | 0 | 1 | 2.3.1.2 | MTO For Pipes - W028 | BK-W028-PEDCO-110-PI-MT-0001 | BK-W028-PEDCO-110-PI-MT-0001 | BK | W028 | PEDCO | 110 | PI | MT | 0001 | F8Z-707528 | IFI | IFI | 2021-12-18 | 2021-12-13 | 2021-12-15 | -5 | 2 | -3 | IFI | 2022-05-01 | 2022-04-28 | 2022-05-02 | -3 | 4 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-04 | 2022-04-17 |  | D01 | IFI | T-0829 | 2022-04-17 | 1401/01/28 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04062 | 2022-04-26 | 1401/02/07 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PI-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42948 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W028-PEDCO-110-PI-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0290 | 2021-12-04 | 1400/09/13 |  |  |  | BK-SUR-ENG-PIP-00-02319 | 2021-12-15 | 1400/09/24 | CM-C2 | [6 empty] | 1400-2294-316961 | 2021-12-13 | 1400/09/22 | 2021-12-15 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-0829 | 2022-04-17 | 1401/01/28 |  |  |  | BK-SUR-ENG-PIP-01-04062 | 2022-04-26 | 1401/02/07 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-PI-MT-0001_D00 | [5 empty] | 1401-2294-42948 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W028-PEDCO-110-PI-MT-0001_D00
2 | 3 | 1 | 2 | 4 | 0 | 2 | 2.3.1.2 | MTO For Fittings - W028 | BK-W028-PEDCO-110-PI-MT-0002 | BK-W028-PEDCO-110-PI-MT-0002 | BK | W028 | PEDCO | 110 | PI | MT | 0002 | F8Z-707529 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-20 | 2022-04-16 |  | D01 | IFI | T-0824 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04061 | 2022-04-06 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42964 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0368 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02478 | 2021-12-29 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337964 | 2021-12-27 | 1400/10/06 | 2021-12-29 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0824 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04061 | 2022-04-06 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0002_D00 | [5 empty] | 1401-2294-42964 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0002_D00
2 | 3 | 1 | 2 | 4 | 0 | 3 | 2.3.1.2 | MTO For Flanges - W028 | BK-W028-PEDCO-110-PI-MT-0003 | BK-W028-PEDCO-110-PI-MT-0003 | BK | W028 | PEDCO | 110 | PI | MT | 0003 | F8Z-707530 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-20 | 2022-04-16 |  | D01 | IFI | T-0824 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04061 | 2022-04-06 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42964 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0368 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02478 | 2021-12-29 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337964 | 2021-12-27 | 1400/10/06 | 2021-12-29 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0824 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04061 | 2022-04-06 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0003_D00 | [5 empty] | 1401-2294-42964 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0003_D00
2 | 3 | 1 | 2 | 4 | 0 | 4 | 2.3.1.2 | MTO For Manual Valves - W028 | BK-W028-PEDCO-110-PI-MT-0004 | BK-W028-PEDCO-110-PI-MT-0004 | BK | W028 | PEDCO | 110 | PI | MT | 0004 | F8Z-707531 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-20 | 2022-04-16 |  | D01 | IFI | T-0824 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04061 | 2022-04-06 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42964 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0368 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02478 | 2021-12-29 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337964 | 2021-12-27 | 1400/10/06 | 2021-12-29 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0824 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04061 | 2022-04-06 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0004_D00 | [5 empty] | 1401-2294-42964 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0004_D00
2 | 3 | 1 | 2 | 4 | 0 | 5 | 2.3.1.2 | MTO For Gaskets - W028 | BK-W028-PEDCO-110-PI-MT-0005 | BK-W028-PEDCO-110-PI-MT-0005 | BK | W028 | PEDCO | 110 | PI | MT | 0005 | F8Z-707532 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-20 | 2022-04-16 |  | D01 | IFI | T-0824 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04061 | 2022-04-06 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42964 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0368 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02478 | 2021-12-29 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337964 | 2021-12-27 | 1400/10/06 | 2021-12-29 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0824 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04061 | 2022-04-06 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0005_D00 | [5 empty] | 1401-2294-42964 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0005_D00
2 | 3 | 1 | 2 | 4 | 0 | 6 | 2.3.1.2 | MTO For Bolt & Nuts - W028 | BK-W028-PEDCO-110-PI-MT-0006 | BK-W028-PEDCO-110-PI-MT-0006 | BK | W028 | PEDCO | 110 | PI | MT | 0006 | F8Z-707533 | IFI | IFI | 2022-01-03 | 2021-12-27 | 2021-12-29 | -7 | 2 | -5 | IFI | 2022-04-30 | 2022-04-28 | 2022-05-02 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-20 | 2022-04-16 |  | D01 | IFI | T-0824 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04061 | 2022-04-06 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42964 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0368 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-PIP-00-02478 | 2021-12-29 | 1400/10/08 | CM-C3 | [6 empty] | 1400-2294-337964 | 2021-12-27 | 1400/10/06 | 2021-12-29 | 1400/10/08 | CM | [10 empty] | D01 | IFI | T-0824 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04061 | 2022-04-06 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-W028S-PEDCO-110-PI-MT-0006_D00 | [5 empty] | 1401-2294-42964 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W028S-PEDCO-110-PI-MT-0006_D00
2 | 3 | 1 | 3 | 0 | 0 | 0 | 2.3.1.3 | Pipeline & Flow line
2 | 3 | 1 | 3 | 1 | 0 | 0 | 2.3.1.3.1 | Drawings
2 | 3 | 1 | 3 | 1 | 0 | 1 | 2.3.1.3.1 | Flow line Transversal Drawings - W028 | BK-W028-PEDCO-110-PL-DW-0002 | BK-W028-PEDCO-110-PL-DW-0002 | BK | W028 | PEDCO | 110 | PL | DW | 0002 | F4A-707534 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 1 | 3 | 2 | 0 | 0 | 2.3.1.3.2 | List
2 | 3 | 1 | 3 | 2 | 0 | 1 | 2.3.1.3.2 | Road Crossing Location List | BK-W028-PEDCO-110-PL-LI-0001 | BK-W028-PEDCO-110-PL-LI-0001 | BK | W028 | PEDCO | 110 | PL | LI | 0001 | F0Z-707535 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 1 | 3 | 3 | 0 | 0 | 2.3.1.3.3 | MTO
2 | 3 | 1 | 3 | 3 | 0 | 1 | 2.3.1.3 | MTO For Line Pipes (Flow lines) - W028 | BK-W028-PEDCO-110-PL-MT-0001 | BK-W028-PEDCO-110-PL-MT-0001 | BK | W028 | PEDCO | 110 | PL | MT | 0001 | F8Z-707536 | IFI | IFI | 44444 | 44438 | 44444 | -6 | 6 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2021-08-22 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | 1400/05/31 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | 1400/05/31 | CM-C2 | [6 empty] | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM
2 | 3 | 1 | 4 | 0 | 0 | 0 | 2.3.1.4 | Control & Instrumentation
2 | 3 | 1 | 4 | 1 | 0 | 0 | 2.3.1.4.1 | Drawing/Diagram
2 | 3 | 1 | 4 | 1 | 0 | 1 | 2.3.1.4.1 | Instrument Location Layout Drawing - W028 | BK-W028-PEDCO-110-IN-PY-0001 | BK-W028-PEDCO-110-IN-PY-0001 | BK | W028 | PEDCO | 110 | IN | PY | 0001 | F2J-707537 | AFC | IFC | 44711 | 0 | 0 | -44711 | 0 | -44711 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-16 | 0 |  | D00 | IFC | T-0958 | 2022-05-16 | 1401/02/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04488 | 2022-05-29 | 1401/03/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0958 | 2022-05-16 | 1401/02/26 |  |  |  | BK-SUR-ENG-INS-01-04488 | 2022-05-29 | 1401/03/09 | CM-C2
2 | 3 | 1 | 4 | 2 | 0 | 0 | 2.3.1.4.2 | MTO
2 | 3 | 1 | 4 | 2 | 0 | 1 | 2.3.1.4 | MTO For Instrument Tube and Fitting - W028 | BK-W028-PEDCO-110-IN-MT-0001 | BK-W028-PEDCO-110-IN-MT-0001 | BK | W028 | PEDCO | 110 | IN | MT | 0001 | F8Z-707538 | IFI | IFI | 2021-11-28 | 2021-11-21 | 2021-11-29 | -7 | 8 | 1 | IFI | 2022-01-01 | 2022-01-03 | 2022-01-05 | 2 | 2 | 4 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-14 | 2022-01-12 |  | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W028-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0238 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02142 | 2021-11-28 | 1400/09/08 | C4-RJ | [6 empty] | 1400-2294-283472 | 2021-11-21 | 1400/08/30 | 2021-11-29 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0359 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-INS-00-02494 | 2022-01-01 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MT-0001_D00 | [5 empty] | 1400-2294-347953 | 2022-01-03 | 1400/10/13 | 2022-01-05 | 1400/10/15 | CM | NISOC-CRS-BK-W028-PEDCO-110-IN-MT-0001_D00 | [9 empty] | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MT-0001_D01 | [5 empty] | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W028-PEDCO-110-IN-MT-0001_D01
2 | 3 | 1 | 4 | 2 | 0 | 2 | 2.3.1.4 | MTO For Instrument Cable Tray - W028 | BK-W028-PEDCO-110-IN-MT-0002 | BK-W028-PEDCO-110-IN-MT-0002 | BK | W028 | PEDCO | 110 | IN | MT | 0002 | F8Z-707539 | IFI | IFI | 2021-11-28 | 2021-11-21 | 2021-11-29 | -7 | 8 | 1 | IFI | 2022-01-01 | 2022-01-03 | 2022-01-05 | 2 | 2 | 4 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-14 | 2022-01-12 |  | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W028-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0238 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02142 | 2021-11-28 | 1400/09/08 | C4-RJ | [6 empty] | 1400-2294-283472 | 2021-11-21 | 1400/08/30 | 2021-11-29 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0359 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-INS-00-02494 | 2022-01-01 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MT-0002_D00 | [5 empty] | 1400-2294-347953 | 2022-01-03 | 1400/10/13 | 2022-01-05 | 1400/10/15 | CM | NISOC-CRS-BK-W028-PEDCO-110-IN-MT-0002_D00 | [9 empty] | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MT-0002_D01 | [5 empty] | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W028-PEDCO-110-IN-MT-0002_D01
2 | 3 | 1 | 5 | 0 | 0 | 0 | 2.3.1.5 | Safety
2 | 3 | 1 | 5 | 1 | 0 | 0 | 2.3.1.5.1 | Drawing/Diagram
2 | 3 | 1 | 5 | 1 | 0 | 1 | 2.3.1.5.1 | Hazardous Area Classification Layout - W028 | BK-W028-PEDCO-110-SA-PY-0001 | BK-W028-PEDCO-110-SA-PY-0001 | BK | W028 | PEDCO | 110 | SA | PY | 0001 | F2L-707540 | AFC | IFC | 2022-05-21 | 0 | 0 | -44702 | 0 | -44702 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-07 | 0 |  | D00 | IFC | T-0905 | 2022-05-07 | 1401/02/17 | T-0905 | 2022-05-07 | 1401/02/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0905 | 2022-05-07 | 1401/02/17 | T-0905 | 2022-05-07 | 1401/02/17
2 | 3 | 1 | 5 | 1 | 0 | 2 | 2.3.1.5.1 | Safety & Fire Fighting Equipment Location Layout - W028 | BK-W028-PEDCO-110-SA-PY-0002 | BK-W028-PEDCO-110-SA-PY-0002 | BK | W028 | PEDCO | 110 | SA | PY | 0002 | F2L-707541 | AFC | IFC | 2022-04-30 | 0 | 0 | -44681 | 0 | -44681 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-16 | 0 |  | D00 | IFC | T-0820 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0820 | 2022-04-16 | 1401/01/27
2 | 3 | 1 | 5 | 1 | 0 | 3 | 2.3.1.5.1 | Escape Route & Safety Sign Layout - W028 | BK-W028-PEDCO-110-SA-PY-0003 | BK-W028-PEDCO-110-SA-PY-0003 | BK | W028 | PEDCO | 110 | SA | PY | 0003 | F2L-707542 | AFC | IFC | 2022-05-01 | 0 | 0 | -44682 | 0 | -44682 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-17 | 0 |  | D00 | IFC | T-0826 | 2022-04-17 | 1401/01/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0826 | 2022-04-17 | 1401/01/28
2 | 3 | 1 | 5 | 2 | 0 | 0 | 2.3.1.5.2 | List
2 | 3 | 1 | 5 | 2 | 0 | 1 | 2.3.1.5.2 | Hazard Source List - W028 | BK-W028-PEDCO-110-SA-LI-0001 | BK-W028-PEDCO-110-SA-LI-0001 | BK | W028 | PEDCO | 110 | SA | LI | 0001 | F0Z-707543 | AFC | IFC | 44523 | 44530 | 44536 | 7 | 6 | 13 | IFA | 44611 | 44618 | 44613 | 7 | -5 | 2 | IFA | 44677 | 0 | 0 | -44677 | 0 | -44677 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-09 | 0 |  | D02 | IFA | T-0806 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-SA-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0220 | 2021-11-09 | 1400/08/18 | [13 empty] | 1400-2290-298651 | 2021-11-30 | 1400/09/09 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0551 | 2022-02-05 | 1400/11/16 | [13 empty] | 1400-2294-419389 | 2022-02-26 | 1400/12/02 | 2022-02-21 | 1400/12/02 | CM | NISOC-CRS-BK-W028-PEDCO-110-SA-LI-0001_D00 | [9 empty] | D02 | IFA | T-0806 | 2022-04-12 | 1401/01/23 | [19 empty] | NISOC-CRS-BK-W028-PEDCO-110-SA-LI-0001_D01
2 | 3 | 1 | 5 | 3 | 0 | 0 | 2.3.1.5.3 | MTO
2 | 3 | 1 | 5 | 3 | 0 | 1 | 2.3.1.5 | MTO For Fire Fighting & Safety Equipment - W028 | BK-W028-PEDCO-110-SA-MT-0001 | BK-W028-PEDCO-110-SA-MT-0001 | BK | W028 | PEDCO | 110 | SA | MT | 0001 | F8Z-707544 | IFI | IFI | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-08 | 2021-12-08 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP
2 | 3 | 1 | 5 | 3 | 0 | 2 | 2.3.1.5 | MTO For Safety Sign - W028 | BK-W028-PEDCO-110-SA-MT-0002 | BK-W028-PEDCO-110-SA-MT-0002 | BK | W028 | PEDCO | 110 | SA | MT | 0002 | F8Z-707545 | IFI | IFI | 2021-12-22 | 2021-12-20 | 2021-12-22 | -2 | 2 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-08 | 2021-12-08 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP
2 | 3 | 1 | 6 | 0 | 0 | 0 | 2.3.1.6 | Architecture
2 | 3 | 1 | 6 | 1 | 0 | 0 | 2.3.1.6.1 | Drawing/Diagram
2 | 3 | 1 | 6 | 1 | 0 | 1 | 2.3.1.6 | Architectural Drawing For WHCP/HPU Shelter of Well Pads - W028 | BK-W028-PEDCO-110-AR-DW-0001 | BK-W028-PEDCO-110-AR-DW-0001 | BK | W028 | PEDCO | 110 | AR | DW | 0001 | F4B-707546 | AFC | IFC | 44632 | 44625 | 44628 | -7 | 3 | -4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-26 | 0 |  | D00 | IFC | T-0640 | 2022-02-26 | 1400/12/07 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-03400 | 2022-03-08 | 1400/12/17 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-435028 | 2022-03-05 | 1400/12/14 | 2022-03-08 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0640 | 2022-02-26 | 1400/12/07 |  |  |  | BK-SUR-ENG-ARC-00-03400 | 2022-03-08 | 1400/12/17 | CM-C2 | [6 empty] | 1400-2294-435028 | 2022-03-05 | 1400/12/14 | 2022-03-08 | 1400/12/17 | AP
2 | 3 | 1 | 7 | 0 | 0 | 0 | 2.3.1.7 | Civil
2 | 3 | 1 | 7 | 1 | 0 | 0 | 2.3.1.7.1 | Drawing/Diagram
2 | 3 | 1 | 7 | 1 | 0 | 1 | 2.3.1.7.1 | General Civil Layout -W028 | BK-W028-PEDCO-110-CV-PY-0001 | BK-W028-PEDCO-110-CV-PY-0001 | BK | W028 | PEDCO | 110 | CV | PY | 0001 | F4A-707547 | AFC | IFC | 2021-11-02 | 2021-10-25 | 2021-11-22 | -8 | 28 | 20 | IFA | 2022-03-26 | 2022-03-15 | 2022-03-25 | -11 | 10 | -1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-19 | 0 |  | D01 | IFA | T-0718 | 2022-03-12 | 1400/12/21 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03529 | 2022-03-13 | 1400/12/22 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-449851 | 2022-03-15 | 1400/12/25 | 2022-03-25 | 1401/01/08 | RJ | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0175 | 2021-10-19 | 1400/07/27 |  |  |  | BK-SUR-ENG-CIV-00-01825 | 2021-10-23 | 1400/08/01 | CM-C2 | [6 empty] | 1400-2294-247863 | 2021-10-25 | 1400/08/03 | 2021-11-22 | 1400/09/01 | CM | [10 empty] | D01 | IFA | T-0718 | 2022-03-12 | 1400/12/21 |  |  |  | BK-SUR-ENG-CIV-00-03529 | 2022-03-13 | 1400/12/22 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0001_D00 | [5 empty] | 1400-2294-449851 | 2022-03-15 | 1400/12/25 | 2022-03-25 | 1401/01/08 | RJ | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0001_D00
2 | 3 | 1 | 7 | 1 | 0 | 2 | 2.3.1.7.1 | Civil and Structural drawings -W028 | BK-W028-PEDCO-110-CV-PY-0002 | BK-W028-PEDCO-110-CV-PY-0002 | BK | W028 | PEDCO | 110 | CV | PY | 0002 | F4S-707548 | AFC | IFC | 2021-11-02 | 0 | 0 | -44502 | 0 | -44502 | IFA | 2021-12-04 | 2021-11-29 | 2021-12-01 | -5 | 2 | -3 | IFA | 2022-03-28 | 2022-03-30 | 2022-04-03 | 2 | 4 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-19 | 0 |  | D02 | IFA | T-0732 | 2022-03-14 | 1400/12/23 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-03695 | 2022-03-26 | 1401/01/09 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0002-D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-6027 | 2022-03-30 | 1401/01/10 | 2022-04-03 | 1401/01/14 | RJ | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0002-D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0175 | 2021-10-19 | 1400/07/27 |  |  |  | BK-SUR-ENG-CIV-00-01825 | 2021-10-23 | 1400/08/01 | CM-C2 | [22 empty] | D01 | IFA | T-0258 | 2021-11-20 | 1400/08/29 |  |  |  | BK-SUR-ENG-CIV-00-02096 | 2021-11-24 | 1400/09/03 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0002-D00 | [5 empty] | 1400-2290-296830 | 2021-11-29 | 1400/09/08 | 2021-12-01 | 1400/09/10 | CM | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0002-D01 | [9 empty] | D02 | IFA | T-0732 | 2022-03-14 | 1400/12/23 |  |  |  | BK-SUR-ENG-CIV-01-03695 | 2022-03-26 | 1401/01/09 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-CV-PY-0002-D02 | [5 empty] | 1401-2294-6027 | 2022-03-30 | 1401/01/10 | 2022-04-03 | 1401/01/14 | RJ | NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0002-D02
2 | 3 | 1 | 7 | 1 | 0 | 3 | 2.3.1.7.1 | Rough Grading Plans -W028 | BK-W028-PEDCO-110-CV-DW-0001 | BK-W028-PEDCO-110-CV-DW-0001 | BK | W028 | PEDCO | 110 | CV | DW | 0001 | F4S-707549 | AFC | IFC | 2021-10-25 | 2021-10-16 | 2021-10-18 | -9 | 2 | -7 | IFA | 2022-02-20 | 2022-02-19 | 2022-02-12 | -1 | -7 | -8 | IFA | 2022-03-28 | 2022-03-30 | 2022-04-03 | 2 | 4 | 6 | AFC | 2022-04-24 | 0 | 0 | -44675 | 0 | -44675 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-11 | 2022-04-10 |  | D03 | AFC | T-0796 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W028-PEDCO-110-CV-DW-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-CV-DW-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0149 | 2021-10-11 | 1400/07/19 |  |  |  | BK-SUR-ENG-CIV-00-01735 | 2021-10-13 | 1400/07/21 | CM-C2 | [6 empty] | 1400-2294-236267 | 2021-10-16 | 1400/07/24 | 2021-10-18 | 1400/07/26 | CM | [10 empty] | D01 | IFA | T-0556 | 2022-02-06 | 1400/11/17 |  |  |  | BK-SUR-ENG-CIV-00-02971 | 2022-02-07 | 1400/11/18 | CM-C2 | PEDCO-CRS-BK-W028-PEDCO-110-CV-DW-0001_D00 | [5 empty] | 1400-2294-406550 | 2022-02-19 | 1400/11/30 | 2022-02-12 | 1400/11/23 | RJ | NISOC-CRS-BK-W028-PEDCO-110-CV-DW-0001_D00 | [9 empty] | D02 | IFA | T-0732 | 2022-03-14 | 1400/12/23 |  |  |  | BK-SUR-ENG-CIV-01-03695 | 2022-03-26 | 1401/01/09 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-CV-DW-0001_D02 | [5 empty] | 1401-2294-6027 | 2022-03-30 | 1401/01/10 | 2022-04-03 | 1401/01/14 | AP | NISOC-CRS-BK-W028-PEDCO-110-CV-DW-0001_D02 | [9 empty] | D03 | AFC | T-0796 | 2022-04-10 | 1401/01/21 | [7 empty] | PEDCO-CRS-BK-W028-PEDCO-110-CV-DW-0001_D02 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-CV-DW-0001_D02
2 | 3 | 1 | 7 | 2 | 0 | 0 | 2.3.1.7.2 | Calculation
2 | 3 | 1 | 7 | 2 | 0 | 1 | 2.3.1.7.2 | Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W028 | BK-W028-PEDCO-110-CV-CN-0001 | BK-W028-PEDCO-110-CV-CN-0001 | BK | W028 | PEDCO | 110 | CV | CN | 0001 | F0Z-707550 | AFC | IFC | 44549 | 44542 | 44544 | -7 | 2 | -5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D00 | IFC | T-0292 | 2021-12-05 | 1400/09/14 | 0 | 0 | 0 | BK-SUR-ENG-STR-00-02212 | 2021-12-06 | 1400/09/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-315094 | 2021-12-12 | 1400/09/21 | 2021-12-14 | 1400/09/23 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0292 | 2021-12-05 | 1400/09/14 |  |  |  | BK-SUR-ENG-STR-00-02212 | 2021-12-06 | 1400/09/15 | CM-C3 | [6 empty] | 1400-2294-315094 | 2021-12-12 | 1400/09/21 | 2021-12-14 | 1400/09/23 | RJ
2 | 3 | 1 | 7 | 3 | 0 | 0 | 2.3.1.7.3 | MTO
2 | 3 | 1 | 7 | 3 | 0 | 1 | 2.3.1.7 | MTO For Civil Works - W028 | BK-W028-PEDCO-110-CV-MT-0001 | BK-W028-PEDCO-110-CV-MT-0001 | BK | W028 | PEDCO | 110 | CV | MT | 0001 | F8Z-707551 | IFI | IFI | 44704 | 44693 | 44697 | -11 | 4 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-09 | 2022-05-09 |  | D00 | IFI | T-0918 | 2022-05-09 | 1401/02/19 | T-0918 | 2022-05-09 | 1401/02/19 | BK-SUR-ENG-CIV-01-04328 | 2022-05-21 | 1401/02/31 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59526 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0918 | 2022-05-09 | 1401/02/19 | T-0918 | 2022-05-09 | 1401/02/19 | BK-SUR-ENG-CIV-01-04328 | 2022-05-21 | 1401/02/31 | CM-C2 | [6 empty] | 1401-2294-59526 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM
2 | 3 | 1 | 8 | 0 | 0 | 0 | 2.3.1.8 | Structure
2 | 3 | 1 | 8 | 1 | 0 | 0 | 2.3.1.8.1 | Drawing/Diagram
2 | 3 | 1 | 8 | 1 | 0 | 1 | 2.3.1.8.1 | Platform Structure Drawing - W028 | BK-W028-PEDCO-110-ST-DW-0002 | BK-W028-PEDCO-110-ST-DW-0002 | BK | W028 | PEDCO | 110 | ST | DW | 0002 | F4M-707552 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 1 | 8 | 2 | 0 | 0 | 2.3.1.8.2 | MTO
2 | 3 | 1 | 8 | 2 | 0 | 1 | 2.3.1.8 | MTO For Structural Works - W028 | BK-W028-PEDCO-110-ST-MT-0001 | BK-W028-PEDCO-110-ST-MT-0001 | BK | W028 | PEDCO | 110 | ST | MT | 0001 | F8Z-707553 | IFI | IFI | 44697 | 44690 | 44702 | -7 | 12 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-02 | 2022-05-02 |  | D00 | IFI | T-0896 | 2022-05-02 | 1401/02/12 | 0 | 0 | 0 | BK-SUR-ENG-STR-01-04427 | 2022-05-24 | 1401/03/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54881 | 2022-05-09 | 1401/02/19 | 2022-05-21 | 1401/02/31 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0896 | 2022-05-02 | 1401/02/12 |  |  |  | BK-SUR-ENG-STR-01-04427 | 2022-05-24 | 1401/03/03 | AP | [6 empty] | 1401-2294-54881 | 2022-05-09 | 1401/02/19 | 2022-05-21 | 1401/02/31 | CM
2 | 3 | 1 | 9 | 0 | 0 | 0 | 2.3.1.9 | Survey (Topography) & Geotechnic/Geoelectric
2 | 3 | 1 | 9 | 1 | 0 | 0 | 2.3.1.9.1 | Geotechnic
2 | 3 | 1 | 9 | 1 | 1 | 0 | 2.3.9.1.1 | Report
2 | 3 | 1 | 9 | 1 | 1 | 1 | 2.3.1.9.1.1.1 | Geotechnical Investigation Report - W028 | BK-W028-PEDCO-110-GT-RT-0001 | BK-W028-PEDCO-110-GT-RT-0001 | BK | W028 | PEDCO | 110 | GT | RT | 0001 | F0Z-707554 | AFC | IFC | 44712 | 0 | 0 | -44712 | 0 | -44712 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-17 | 0 |  | D00 | IFC | T-0963 | 2022-05-17 | 1401/02/27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0963 | 2022-05-17 | 1401/02/27
2 | 3 | 1 | 9 | 1 | 2 | 0 | 2.3.9.1.2 | Drawing/Diagram
2 | 3 | 1 | 9 | 1 | 2 | 1 | 2.3.1.9.1.2.1 | Flow line Plan & Profile Drawings - W028 | BK-W028-PEDCO-110-SU-DW-0001 | BK-W028-PEDCO-110-SU-DW-0001 | BK | W028 | PEDCO | 110 | SU | DW | 0001 | F4A-707555 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 0 | 0 | 0 | 0 | 2.3.2 | Procurement Engineering
2 | 3 | 2 | 1 | 0 | 0 | 0 | 2.3.2.1 | Piping
2 | 3 | 2 | 1 | 1 | 0 | 0 | 2.3.2.1.1 | Pipes
2 | 3 | 2 | 1 | 1 | 1 | 0 | 2.3.1.1.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 1 | 1 | 1 | 1 | 2.3.2.1.1.1.1 | PMR For Pipes - W028 | BK-W028-PEDCO-110-PI-MR-0001 | BK-W028-PEDCO-110-PI-MR-0001 | BK | W028 | PEDCO | 110 | PI | MR | 0001 | F0Z-707556 | IFI | IFI | 44550 | 44545 | 44545 | -5 | 0 | -5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-06 | 2021-12-06 |  | D00 | IFI | T-0298 | 2021-12-06 | 1400/09/15 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02320 | 2021-12-15 | 1400/09/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-315076 | 2021-12-12 | 1400/09/21 | 2021-12-15 | 1400/09/24 | AP | 0 | 1400-2294-316959 | 2021-12-15 | 1400/09/22 | 0 | 0 | CM | 0 | 0 |  | D00 | IFI | T-0298 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PIP-00-02320 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-315076 | 2021-12-12 | 1400/09/21 | 2021-12-15 | 1400/09/24 | AP |  | 1400-2294-316959 | 2021-12-15 | 1400/09/22 |  |  | CM
2 | 3 | 2 | 1 | 1 | 2 | 0 | 2.3.1.1.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 1 | 2 | 1 | 2.3.2.1.1.2.1 | TBE For Pipes - W028 | BK-W028-PEDCO-110-PI-TB-0001 | BK-W028-PEDCO-110-PI-TB-0001 | BK | W028 | PEDCO | 110 | PI | TB | 0001 | F0Z-707557 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 1 | 2 | 0 | 0 | 2.3.2.1.2 | Fittings
2 | 3 | 2 | 1 | 2 | 1 | 0 | 2.3.1.2.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 1 | 2 | 1 | 1 | 2.3.2.1.2.1.1 | PMR For Fittings - W028 | BK-W028-PEDCO-110-PI-MR-0002 | BK-W028-PEDCO-110-PI-MR-0002 | BK | W028 | PEDCO | 110 | PI | MR | 0002 | F0Z-707558 | IFI | IFI | 44681 | 44679 | 44683 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-04-16 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04084 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04084 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ
2 | 3 | 2 | 1 | 2 | 2 | 0 | 2.3.1.2.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 2 | 2 | 1 | 2.3.2.1.2.2.1 | TBE For Fitting - W028 | BK-W028-PEDCO-110-PI-TB-0002 | BK-W028-PEDCO-110-PI-TB-0002 | BK | W028 | PEDCO | 110 | PI | TB | 0002 | F0Z-707559 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 1 | 3 | 0 | 0 | 2.3.2.1.3 | Flanges
2 | 3 | 2 | 1 | 3 | 1 | 0 | 2.3.1.3.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 1 | 3 | 1 | 1 | 2.3.2.1.3.1.1 | PMR For Flanges - W028 | BK-W028-PEDCO-110-PI-MR-0003 | BK-W028-PEDCO-110-PI-MR-0003 | BK | W028 | PEDCO | 110 | PI | MR | 0003 | F0Z-707560 | IFI | IFI | 44681 | 44679 | 44683 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-04-16 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04084 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04084 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ
2 | 3 | 2 | 1 | 3 | 2 | 0 | 2.3.1.3.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 3 | 2 | 1 | 2.3.2.1.3.2.1 | TBE For Flanges - W028 | BK-W028-PEDCO-110-PI-TB-0003 | BK-W028-PEDCO-110-PI-TB-0003 | BK | W028 | PEDCO | 110 | PI | TB | 0003 | F0Z-707561 | IFI | IFI | 44619 | 44652 | 44625 | 33 | -27 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-13 | 2022-02-13 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03334 | 2022-03-05 | 1400/12/14 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-PIP-00-03334 | 2022-03-05 | 1400/12/14 | C4-RJ | [6 empty] | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | CM
2 | 3 | 2 | 1 | 4 | 0 | 0 | 2.3.2.1.4 | Manual Valves
2 | 3 | 2 | 1 | 4 | 1 | 0 | 2.3.1.4.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 1 | 4 | 1 | 1 | 2.3.2.1.4.1.1 | PMR For Manual Valves - W028 | BK-W028-PEDCO-110-PI-MR-0004 | BK-W028-PEDCO-110-PI-MR-0004 | BK | W028 | PEDCO | 110 | PI | MR | 0004 | F0Z-707562 | IFI | IFI | 44681 | 44679 | 44683 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-04-16 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04084 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04084 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ
2 | 3 | 2 | 1 | 4 | 2 | 0 | 2.3.1.4.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 4 | 2 | 1 | 2.3.2.1.4.2.1 | TBE For Manual Valves - W028 | BK-W028-PEDCO-110-PI-TB-0004 | BK-W028-PEDCO-110-PI-TB-0004 | BK | W028 | PEDCO | 110 | PI | TB | 0004 | F0Z-707563 | IFI | IFI | 44619 | 44652 | 44625 | 33 | -27 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-13 | 2022-02-13 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03334 | 2022-03-05 | 1400/12/14 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-PIP-00-03334 | 2022-03-05 | 1400/12/14 | C4-RJ | [6 empty] | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | CM
2 | 3 | 2 | 1 | 5 | 0 | 0 | 2.3.2.1.5 | Gaskets
2 | 3 | 2 | 1 | 5 | 1 | 0 | 2.3.1.5.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 1 | 5 | 1 | 1 | 2.3.2.1.5.1.1 | PMR For Gaskets - W028 | BK-W028-PEDCO-110-PI-MR-0005 | BK-W028-PEDCO-110-PI-MR-0005 | BK | W028 | PEDCO | 110 | PI | MR | 0005 | F0Z-707564 | IFI | IFI | 44681 | 44679 | 44683 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-04-16 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04084 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04084 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ
2 | 3 | 2 | 1 | 5 | 2 | 0 | 2.3.1.5.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 5 | 2 | 1 | 2.3.2.1.5.2.1 | TBE For Gaskets - W028 | BK-W028-PEDCO-110-PI-TB-0005 | BK-W028-PEDCO-110-PI-TB-0005 | BK | W028 | PEDCO | 110 | PI | TB | 0005 | F0Z-707565 | IFI | IFI | 44619 | 44652 | 44625 | 33 | -27 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-13 | 2022-02-13 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03334 | 2022-03-05 | 1400/12/14 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0580 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-PIP-00-03334 | 2022-03-05 | 1400/12/14 | C4-RJ | [6 empty] | 1400-2294-430726 | 2022-04-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | CM
2 | 3 | 2 | 1 | 6 | 0 | 0 | 2.3.2.1.6 | Bolt & Nuts
2 | 3 | 2 | 1 | 6 | 1 | 0 | 2.3.1.6.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 1 | 6 | 1 | 1 | 2.3.2.1.6.1.1 | PMR For Bolt/Nuts - W028 | BK-W028-PEDCO-110-PI-MR-0006 | BK-W028-PEDCO-110-PI-MR-0006 | BK | W028 | PEDCO | 110 | PI | MR | 0006 | F0Z-707566 | IFI | IFI | 44681 | 44679 | 44683 | -2 | 4 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-04-16 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04084 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0825 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PIP-01-04084 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-42939 | 2022-04-28 | 1401/02/08 | 2022-05-02 | 1401/02/12 | RJ
2 | 3 | 2 | 1 | 6 | 2 | 0 | 2.3.1.6.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 6 | 2 | 1 | 2.3.2.1.6.2.1 | TBE For Bolt/Nuts - W028 | BK-W028-PEDCO-110-PI-TB-0006 | BK-W028-PEDCO-110-PI-TB-0006 | BK | W028 | PEDCO | 110 | PI | TB | 0006 | F0Z-707567 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 1 | 7 | 0 | 0 | 2.3.2.1.7 | Sampling Connection
2 | 3 | 2 | 1 | 7 | 1 | 0 | 2.3.1.7.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 1 | 7 | 1 | 1 | 2.3.2.1.7.1.1 | PMR For Sampling Connection Set - W028 | BK-W028-PEDCO-110-PI-MR-0007 | BK-W028-PEDCO-110-PI-MR-0007 | BK | W028 | PEDCO | 110 | PI | MR | 0007 | F0Z-707568 | IFI | IFI | 44626 | 44629 | 44627 | 3 | -2 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-02-20 |  | D00 | IFI | T-0613 | 2022-02-20 | 1400/12/01 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03420 | 2022-03-08 | 1400/12/17 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-438859 | 2022-03-09 | 1400/12/18 | 2022-03-07 | 1400/12/16 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0613 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-PIP-00-03420 | 2022-03-08 | 1400/12/17 | CM-C2 | [6 empty] | 1400-2294-438859 | 2022-03-09 | 1400/12/18 | 2022-03-07 | 1400/12/16 | RJ
2 | 3 | 2 | 1 | 7 | 2 | 0 | 2.3.1.7.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 7 | 2 | 1 | 2.3.2.1.7.2.1 | TBE For Sampling Connection Set - W028 | BK-W028-PEDCO-110-PI-TB-0007 | BK-W028-PEDCO-110-PI-TB-0007 | BK | W028 | PEDCO | 110 | PI | TB | 0007 | F0Z-707569 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 1 | 8 | 0 | 0 | 2.3.2.1.8 | Stone Trap
2 | 3 | 2 | 1 | 8 | 1 | 0 | 2.3.1.8.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 1 | 8 | 1 | 1 | 2.3.2.1.8.1.1 | PMR For Stone Trap - W028 | BK-W028-PEDCO-110-PI-MR-0008 | BK-W028-PEDCO-110-PI-MR-0008 | BK | W028 | PEDCO | 110 | PI | MR | 0008 | F0Z-707570 | IFI | IFI | 44692 | 44681 | 44695 | -11 | 14 | 3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-27 | 2022-04-27 |  | D00 | IFI | T-0869 | 2022-04-27 | 1401/02/07 | T-0869 | 2022-04-27 | 1401/02/07 | BK-SUR-ENG-PIP-01-04122 | 2022-05-02 | 1401/02/12 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-45413 | 2022-04-30 | 1401/02/10 | 2022-05-14 | 1401/02/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0869 | 2022-04-27 | 1401/02/07 | T-0869 | 2022-04-27 | 1401/02/07 | BK-SUR-ENG-PIP-01-04122 | 2022-05-02 | 1401/02/12 | CM-C2 | [6 empty] | 1401-2294-45413 | 2022-04-30 | 1401/02/10 | 2022-05-14 | 1401/02/24 | CM
2 | 3 | 2 | 1 | 8 | 2 | 0 | 2.3.1.8.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 8 | 2 | 1 | 2.3.2.1.8.2.1 | TBE For Stone Trap - W028 | BK-W028-PEDCO-110-PI-TB-0008 | BK-W028-PEDCO-110-PI-TB-0008 | BK | W028 | PEDCO | 110 | PI | TB | 0008 | F0Z-707571 | IFI | IFI | 44719 | 0 | 0 | -44719 | 0 | -44719 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-24 | 2022-05-24 |  | D00 | IFI | T-0996 | 2022-05-24 | 1401/03/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0996 | 2022-05-24 | 1401/03/03
2 | 3 | 2 | 1 | 9 | 0 | 0 | 2.3.2.1.9 | Pipe Support
2 | 3 | 2 | 1 | 9 | 1 | 0 | 2.3.1.9.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 1 | 9 | 1 | 1 | 2.3.2.1.9.1.1 | PMR For Pipe Support - W028 | BK-W028-PEDCO-110-PI-MR-0009 | BK-W028-PEDCO-110-PI-MR-0009 | BK | W028 | PEDCO | 110 | PI | MR | 0009 | F0Z-707572 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 1 | 9 | 2 | 0 | 2.3.1.9.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 1 | 9 | 2 | 1 | 2.3.2.1.9.2.1 | TBE For Pipe Support - W028 | BK-W028-PEDCO-110-PI-TB-0009 | BK-W028-PEDCO-110-PI-TB-0009 | BK | W028 | PEDCO | 110 | PI | TB | 0009 | F0Z-707573 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 2 | 0 | 0 | 0 | 2.3.2.2 | Pipeline
2 | 3 | 2 | 2 | 1 | 0 | 0 | 2.3.2.2.1 | Line Pipe
2 | 3 | 2 | 2 | 1 | 1 | 0 | 2.3.2.1.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 2 | 1 | 1 | 1 | 2.3.2.2.1.1.1 | PMR For Line Pipes - W028 | BK-W028-PEDCO-110-PL-MR-0001 | BK-W028-PEDCO-110-PL-MR-0001 | BK | W028 | PEDCO | 110 | PL | MR | 0001 | F0Z-707574 | IFI | IFI | 44550 | 44543 | 44545 | -7 | 2 | -5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-06 | 2021-12-06 |  | D00 | IFI | T-0299 | 2021-12-06 | 1400/09/15 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02321 | 2021-12-15 | 1400/09/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-316957 | 2021-12-13 | 1400/09/22 | 2021-12-15 | 1400/09/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0299 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PPL-00-02321 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-316957 | 2021-12-13 | 1400/09/22 | 2021-12-15 | 1400/09/24 | CM
2 | 3 | 2 | 2 | 1 | 2 | 0 | 2.3.2.1.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 2 | 1 | 2 | 1 | 2.3.2.2.1.2.1 | TBE For Line Pipes - W028 | BK-W028-PEDCO-110-PL-TB-0001 | BK-W028-PEDCO-110-PL-TB-0001 | BK | W028 | PEDCO | 110 | PL | TB | 0001 | F0Z-707575 | IFI | IFI | 44625 | 44630 | 44634 | 5 | 4 | 9 | IFI | 44709 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 2022-05-14 |  | D01 | IFI | T-0944 | 2022-05-14 | 1401/02/24 | T-0944 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 2022-05-23 | 1401/03/02 | CM-C3 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0604 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PPL-00-03409 | 2022-03-08 | 1400/12/17 | C4-RJ | [6 empty] | 1400-2294-443269 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/23 | CM | [10 empty] | D01 | IFI | T-0944 | 2022-05-14 | 1401/02/24 | T-0944 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PL-TB-0001-D00 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-PL-TB-0001-D00
2 | 3 | 2 | 2 | 2 | 0 | 0 | 2.3.2.2.2 | Flow Line Support
2 | 3 | 2 | 2 | 2 | 1 | 0 | 2.3.2.2.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 2 | 2 | 1 | 1 | 2.3.2.2.2.1.1 | PMR For Flow Line Support - W028 | BK-W028-PEDCO-110-PL-MR-0002 | BK-W028-PEDCO-110-PL-MR-0002 | BK | W028 | PEDCO | 110 | PL | MR | 0002 | F0Z-707576 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 2 | 2 | 2 | 0 | 2.3.2.2.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 2 | 2 | 2 | 1 | 2.3.2.2.2.2.1 | TBE For Flow Line Support - W028 | BK-W028-PEDCO-110-PL-TB-0002 | BK-W028-PEDCO-110-PL-TB-0002 | BK | W028 | PEDCO | 110 | PL | TB | 0002 | F0Z-707577 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 3 | 0 | 0 | 0 | 2.3.2.3 | Control & Instrumentation
2 | 3 | 2 | 3 | 1 | 0 | 0 | 2.3.2.3.1 | WHCP/HPU
2 | 3 | 2 | 3 | 1 | 1 | 0 | 2.3.3.1.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 3 | 1 | 1 | 1 | 2.3.2.3.1.1.1 | PMR For WHCP/HPU - W028 | BK-W028-PEDCO-110-IN-MR-0001 | BK-W028-PEDCO-110-IN-MR-0001 | BK | W028 | PEDCO | 110 | IN | MR | 0001 | F0Z-707578 | IFI | IFI | 44529 | 44547 | 44537 | 18 | -10 | 8 | IFI | 44591 | 44592 | 44593 | 1 | 1 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 2022-01-16 |  | D01 | IFI | T-0470 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02865 | 2022-01-30 | 1400/11/10 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-390765 | 2022-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | NISOC-CRS-BK-W028-PEDCO-110-IN-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0243 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-INS-00-02170 | 2021-12-01 | 1400/09/10 | C4-RJ |  | BK-SUR-ENG-INS-00-02224 | 2021-12-07 | 1400/09/16 | CM-C3 |  | 1400-2294-320808 | 2021-12-17 | 1400/09/26 | 2021-12-07 | 1400/09/16 | CM | [10 empty] | D01 | IFI | T-0470 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02865 | 2022-01-30 | 1400/11/10 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-MR-0001_D00 | [5 empty] | 1400-2294-390765 | 2022-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | NISOC-CRS-BK-W028-PEDCO-110-IN-MR-0001_D00
2 | 3 | 2 | 3 | 1 | 2 | 0 | 2.3.3.1.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 3 | 1 | 2 | 1 | 2.3.2.3.1.2.1 | TBE/TBA For WHCP/HPU - W028 | BK-W028-PEDCO-110-IN-TB-0001 | BK-W028-PEDCO-110-IN-TB-0001 | BK | W028 | PEDCO | 110 | IN | TB | 0001 | F0Z-707579 | IFI | IFI | 44545 | 44544 | 44545 | -1 | 1 | 0 | IFI | 44625 | 44655 | 44660 | 30 | 5 | 35 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-01 | 2022-02-19 |  | D01 | IFI | T-0602 | 2022-02-19 | 1400/11/30 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03345 | 2022-03-05 | 1400/12/15 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-TB-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-9652 | 2022-04-04 | 1401/01/15 | 2022-04-09 | 1401/01/20 | CM | NISOC-CRS-BK-W028-PEDCO-110-IN-TB-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0286 | 2021-12-01 | 1400/09/10 |  |  |  | BK-SUR-ENG-INS-00-02297 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-317340 | 2021-12-14 | 1400/09/23 | 2021-12-15 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-0602 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-INS-00-03345 | 2022-03-05 | 1400/12/15 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-IN-TB-0001_D00 | [5 empty] | 1401-2294-9652 | 2022-04-04 | 1401/01/15 | 2022-04-09 | 1401/01/20 | CM | NISOC-CRS-BK-W028-PEDCO-110-IN-TB-0001_D00
2 | 3 | 2 | 3 | 2 | 0 | 0 | 2.3.2.3.2 | Field Instrumentations
2 | 3 | 2 | 3 | 2 | 1 | 0 | 2.3.3.2.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 3 | 2 | 1 | 1 | 2.3.2.3.2.1.1 | PMR For Field Instrumentations - W028 | BK-W028-PEDCO-110-IN-MR-0002 | BK-W028-PEDCO-110-IN-MR-0002 | BK | W028 | PEDCO | 110 | IN | MR | 0002 | F0Z-707580 | IFI | IFI | 44557 | 44582 | 44221 | 25 | -361 | -336 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 2021-12-13 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | 1400/10/06 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-330276 | 2022-01-21 | 1400/11/01 | 2021-01-25 | 1400/11/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | 1400/10/06 | CM-C3 | [6 empty] | 1400-2294-330276 | 2022-01-21 | 1400/11/01 | 2021-01-25 | 1400/11/05 | CM
2 | 3 | 2 | 3 | 2 | 2 | 0 | 2.3.3.2.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 3 | 2 | 2 | 1 | 2.3.2.3.2.2.1 | TBE/TBA For Field Instrumentations - W028 | BK-W028-PEDCO-110-IN-TB-0002 | BK-W028-PEDCO-110-IN-TB-0002 | BK | W028 | PEDCO | 110 | IN | TB | 0002 | F0Z-707581 | IFI | IFI | 44723 | 0 | 0 | -44723 | 0 | -44723 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-28 | 2022-05-28 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07
2 | 3 | 2 | 3 | 3 | 0 | 0 | 2.3.2.3.3 | Instrument Bulk Items
2 | 3 | 2 | 3 | 3 | 1 | 0 | 2.3.3.3.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 3 | 3 | 1 | 1 | 2.3.2.3.3.1.1 | PMR For Instrument Bulk Items - W028 | BK-W028-PEDCO-110-IN-MR-0003 | BK-W028-PEDCO-110-IN-MR-0003 | BK | W028 | PEDCO | 110 | IN | MR | 0003 | F0Z-707582 | IFI | IFI | 44591 | 44227 | 44593 | -364 | 366 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-16 | 2022-01-16 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C2 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM
2 | 3 | 2 | 3 | 3 | 2 | 0 | 2.3.3.3.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 3 | 3 | 2 | 1 | 2.3.2.3.3.2.1 | TBE/TBA For Instrument Bulk Items - W028 | BK-W028-PEDCO-110-IN-TB-0003 | BK-W028-PEDCO-110-IN-TB-0003 | BK | W028 | PEDCO | 110 | IN | TB | 0003 | F0Z-707583 | IFI | IFI | 44608 | 0 | 0 | -44608 | 0 | -44608 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 2022-02-02 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03068 | 2022-02-14 | 1400/11/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03068 | 2022-02-14 | 1400/11/25 | CM-C2
2 | 3 | 2 | 4 | 0 | 0 | 0 | 2.3.2.4 | Safety & Fire Fighting
2 | 3 | 2 | 4 | 1 | 0 | 0 | 2.3.2.4.1 | Fire Fighting and Safety Equipment
2 | 3 | 2 | 4 | 1 | 1 | 0 | 2.3.4.1.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 4 | 1 | 1 | 1 | 2.3.2.4.1.1.1 | PMR For Fire Fighting and Safety Equipment - W028 | BK-W028-PEDCO-110-SA-MR-0001 | BK-W028-PEDCO-110-SA-MR-0001 | BK | W028 | PEDCO | 110 | SA | MR | 0001 | F0Z-707584 | IFI | IFI | 44552 | 44550 | 44552 | -2 | 2 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-08 | 2021-12-08 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP
2 | 3 | 2 | 4 | 1 | 2 | 0 | 2.3.4.1.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 4 | 1 | 2 | 1 | 2.3.2.4.1.2.1 | TBE For Fire Fighting and Safety Equipment - W028 | BK-W028-PEDCO-110-SA-TB-0001 | BK-W028-PEDCO-110-SA-TB-0001 | BK | W028 | PEDCO | 110 | SA | TB | 0001 | F0Z-707585 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 4 | 2 | 0 | 0 | 2.3.2.4.2 | Safety Sign
2 | 3 | 2 | 4 | 2 | 1 | 0 | 2.3.4.2.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 4 | 2 | 1 | 1 | 2.3.2.4.2.1.1 | PMR For Fire Safety Sign - W028 | BK-W028-PEDCO-110-SA-MR-0002 | BK-W028-PEDCO-110-SA-MR-0002 | BK | W028 | PEDCO | 110 | SA | MR | 0002 | F0Z-707586 | IFI | IFI | 44552 | 44550 | 44552 | -2 | 2 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-08 | 2021-12-08 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0316 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-327316 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | AP
2 | 3 | 2 | 4 | 2 | 2 | 0 | 2.3.4.2.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 4 | 2 | 2 | 1 | 2.3.2.4.2.2.1 | TBE For Fire Safety Sign - W028 | BK-W028-PEDCO-110-SA-TB-0002 | BK-W028-PEDCO-110-SA-TB-0002 | BK | W028 | PEDCO | 110 | SA | TB | 0002 | F0Z-707587 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 5 | 0 | 0 | 0 | 2.3.2.5 | Structure
2 | 3 | 2 | 5 | 1 | 0 | 0 | 2.3.2.5.1 | Steel Structure Items
2 | 3 | 2 | 5 | 1 | 1 | 0 | 2.3.5.1.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 5 | 1 | 1 | 1 | 2.3.2.5.1.1.1 | PMR For Steel Structure Items - W028 | BK-W028-PEDCO-110-ST-MR-0001 | BK-W028-PEDCO-110-ST-MR-0001 | BK | W028 | PEDCO | 110 | ST | MR | 0001 | F0Z-707588 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 5 | 1 | 2 | 0 | 2.3.5.1.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 5 | 1 | 2 | 1 | 2.3.2.5.1.2.1 | TBE For Steel Structure Items - W028 | BK-W028-PEDCO-110-ST-TB-0001 | BK-W028-PEDCO-110-ST-TB-0001 | BK | W028 | PEDCO | 110 | ST | TB | 0001 | F0Z-707589 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 5 | 2 | 0 | 0 | 2.3.2.5.2 | Anchor Bolts
2 | 3 | 2 | 5 | 2 | 1 | 0 | 2.3.5.2.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 5 | 2 | 1 | 1 | 2.3.2.5.2.1.1 | PMR For Anchor Bolts - W028 | BK-W028-PEDCO-110-ST-MR-0002 | BK-W028-PEDCO-110-ST-MR-0002 | BK | W028 | PEDCO | 110 | ST | MR | 0002 | F0Z-707590 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 5 | 2 | 2 | 0 | 2.3.5.2.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 5 | 2 | 2 | 1 | 2.3.2.5.2.2.1 | TBE For Anchor Bolts - W028 | BK-W028-PEDCO-110-ST-TB-0002 | BK-W028-PEDCO-110-ST-TB-0002 | BK | W028 | PEDCO | 110 | ST | TB | 0002 | F0Z-707591 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 6 | 0 | 0 | 0 | 2.3.2.6 | Civil
2 | 3 | 2 | 6 | 1 | 0 | 0 | 2.3.2.6.1 | Geomembrane
2 | 3 | 2 | 6 | 1 | 1 | 0 | 2.3.6.1.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 6 | 1 | 1 | 1 | 2.3.2.6.1.1.1 | PMR For Geomembrane - W028 | BK-W028-PEDCO-110-CV-MR-0001 | BK-W028-PEDCO-110-CV-MR-0001 | BK | W028 | PEDCO | 110 | CV | MR | 0001 | F0Z-707592 | IFI | IFI | 44678 | 44667 | 44676 | -11 | 9 | -2 | IFI | 44717 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-13 | 2022-05-22 |  | D01 | IFI | T-0989 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-04468 | 2022-05-29 | 1401/03/08 | AP | PEDCO-CRS-BK-W028-PEDCO-110-CV-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-CV-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0813 | 2022-04-13 | 1401/01/24 |  |  |  | BK-SUR-ENG-CIV-01-04058 | 2022-04-25 | 1401/02/05 | CM-C2 | [6 empty] | 1401-2294-27299 | 2022-04-16 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM | [10 empty] | D01 | IFI | T-0989 | 2022-05-22 | 1401/03/01 |  |  |  | BK-SUR-ENG-CIV-01-04468 | 2022-05-29 | 1401/03/08 | AP | PEDCO-CRS-BK-W028-PEDCO-110-CV-MR-0001_D00 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-CV-MR-0001_D00
2 | 3 | 2 | 6 | 1 | 2 | 0 | 2.3.6.1.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 6 | 1 | 2 | 1 | 2.3.2.6.1.2.1 | TBE For Geomembrane - W028 | BK-W028-PEDCO-110-CV-TB-0001 | BK-W028-PEDCO-110-CV-TB-0001 | BK | W028 | PEDCO | 110 | CV | TB | 0001 | F0Z-707593 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 2 | 6 | 2 | 0 | 0 | 2.3.2.6.2 | Geotextile
2 | 3 | 2 | 6 | 2 | 1 | 0 | 2.3.6.2.1 | Purchase Material Requisition (PMR)
2 | 3 | 2 | 6 | 2 | 1 | 1 | 2.3.2.6.2.1.1 | PMR For Geotextile - W028 | BK-W028-PEDCO-110-CV-MR-0002 | BK-W028-PEDCO-110-CV-MR-0002 | BK | W028 | PEDCO | 110 | CV | MR | 0002 | F0Z-707594 | IFI | IFI | 44678 | 44667 | 44676 | -11 | 9 | -2 | IFI | 44717 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-13 | 2022-05-22 |  | D01 | IFI | T-0989 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-04468 | 2022-05-29 | 1401/03/08 | AP | PEDCO-CRS-BK-W028-PEDCO-110-CV-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W028-PEDCO-110-CV-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0813 | 2022-04-13 | 1401/01/24 |  |  |  | BK-SUR-ENG-CIV-01-04058 | 2022-04-25 | 1401/02/05 | CM-C2 | [6 empty] | 1401-2294-27299 | 2022-04-16 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM | [10 empty] | D01 | IFI | T-0989 | 2022-05-22 | 1401/03/01 |  |  |  | BK-SUR-ENG-CIV-01-04468 | 2022-05-29 | 1401/03/08 | AP | PEDCO-CRS-BK-W028-PEDCO-110-CV-MR-0002_D00 | [11 empty] | NISOC-CRS-BK-W028-PEDCO-110-CV-MR-0002_D00
2 | 3 | 2 | 6 | 2 | 2 | 0 | 2.3.6.2.2 | Technical Bid Evaluation (TBE)
2 | 3 | 2 | 6 | 2 | 2 | 1 | 2.3.2.6.2.2.1 | TBE For Geotextile - W028 | BK-W028-PEDCO-110-CV-TB-0002 | BK-W028-PEDCO-110-CV-TB-0002 | BK | W028 | PEDCO | 110 | CV | TB | 0002 | F0Z-707595 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 3 | 0 | 0 | 0 | 0 | 2.3.3 | Commissioning Engineering
2 | 3 | 3 | 0 | 0 | 1 | 0 | 2.3.3.1 | Procedure/Plan
2 | 3 | 3 | 0 | 0 | 1 | 1 | 2.3.3.1.1 | Pre-Commissioning, Commissioning & Startup Procedure - W028 | BK-W028-PEDCO-110-CO-PR-0001 | BK-W028-PEDCO-110-CO-PR-0001 | BK | W028 | PEDCO | 110 | CO | PR | 0001 | F0Z-707596 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 4 | 0 | 0 | 0 | 0 | 2.3.4 | Field Engineering
2 | 3 | 4 | 0 | 0 | 1 | 0 | 2.3.4.1 | Query
2 | 3 | 4 | 0 | 0 | 1 | 1 | 2.3.4.1.1 | Technical/Site Queries | BK-W028-PEDCO-110-GE-TQ-0001 | BK-W028-PEDCO-110-GE-TQ-0001 | BK | W028 | PEDCO | 110 | GE | TQ | 0001 | F7Z-707597 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 4 | 0 | 0 | 2 | 0 | 2.3.4.2 | Dossier
2 | 3 | 4 | 0 | 0 | 2 | 1 | 2.3.4.2.1 | As-Built Document Booklets - W028 | BK-W028-PEDCO-110-GE-DO-0001 | BK-W028-PEDCO-110-GE-DO-0001 | BK | W028 | PEDCO | 110 | GE | DO | 0001 | F0Z-707598 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 5 | 0 | 0 | 0 | 0 | 2.3.5 | Engineering Final Documentation
2 | 3 | 5 | 0 | 0 | 1 | 0 | 2.3.5.1 | Manual
2 | 3 | 5 | 0 | 0 | 1 | 1 | 2.3.5.1.1 | Operating Manual - W028 | BK-W028-PEDCO-110-GE-ML-0001 | BK-W028-PEDCO-110-GE-ML-0001 | BK | W028 | PEDCO | 110 | GE | ML | 0001 | F7Z-707599 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 5 | 0 | 0 | 2 | 0 | 2.3.5.2 | Dossier
2 | 3 | 5 | 0 | 0 | 2 | 1 | 2.3.5.2.1 | As-Built Document Booklets - W028 | BK-W028-PEDCO-110-GE-DO-0001 | BK-W028-PEDCO-110-GE-DO-0001 | [7 empty] | F0Z-707598 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 3 | 5 | 0 | 0 | 2 | 2 | 2.3.5.2.2 | Final Engineering Dossier - W028 | BK-W028-PEDCO-110-GE-DO-0002 | BK-W028-PEDCO-110-GE-DO-0002 | BK | W028 | PEDCO | 110 | GE | DO | 0002 | F0Z-707600 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 0 | 0 | 0 | 0 | 0 | 2.4 | Package 03-New Well # W046S (Bangestan)
2 | 4 | 1 | 0 | 0 | 0 | 0 | 2.4.1 | Detail Design
2 | 4 | 1 | 1 | 0 | 0 | 0 | 2.4.1.1 | Process
2 | 4 | 1 | 1 | 1 | 0 | 0 | 2.4.1.1.1 | Drawing/Diagram
2 | 4 | 1 | 1 | 1 | 0 | 1 | 2.4.1.1.1 | Process Flow Diagram - W0046S | BK-W046S-PEDCO-110-PR-PF-0001 | BK-W046S-PEDCO-110-PR-PF-0001 | BK | W046S | PEDCO | 110 | PR | PF | 0001 | F2A-707601 | AFC | IFC | 2021-09-07 | 2021-09-02 | 2021-09-07 | -5 | 5 | 0 | IFC | 2021-11-15 | 2021-11-28 | 2021-11-27 | 13 | -1 | 12 | IFA | 2022-01-12 | 2022-01-17 | 2022-01-19 | 5 | 2 | 7 | AFC | 2022-03-27 | 2022-04-29 | 2022-05-01 | 33 | 2 | 35 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-01 | 2022-03-13 |  | D03 | AFC | T-0729 | 2022-03-13 | 1400/12/22 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03886 | 2022-04-13 | 1401/01/23 | AP | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PF-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43234 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0063 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PCS-00-01417 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2290/182828 | 2021-09-02 | 1400/06/11 | 2021-09-07 | 1400/06/16 | RJ | [10 empty] | D01 | IFC | T-0203 | 2021-11-01 | 1400/08/10 | [7 empty] | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PF-0001_D00 | [5 empty] | 1400-2294-288935 | 2021-11-23 | 1400/09/02 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-PF-0001_D00 | 1400-2290-294909 | 2021-11-28 | 1400/09/07 |  |  | CM |  |  |  | D02 | IFA | T-0409 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02659 | 2022-01-12 | 1400/10/22 | CM-C3 | [6 empty] | 1400-2294-368486 | 2022-01-17 | 1400/10/27 | 2022-01-19 | 1400/10/19 | AP | NISOC-BK-W046S-PEDCO-110-PR-PF-0001_D01 | [9 empty] | D03 | AFC | T-0729 | 2022-03-13 | 1400/12/22 |  |  |  | BK-SUR-ENG-PCS-01-03886 | 2022-04-13 | 1401/01/23 | AP | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PF-0001_D02 | [5 empty] | 1401-2294-43234 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM
2 | 4 | 1 | 1 | 1 | 0 | 2 | 2.4.1.1.1 | P&ID - W0046S | BK-W046S-PEDCO-110-PR-PI-0001 | BK-W046S-PEDCO-110-PR-PI-0001 | BK | W046S | PEDCO | 110 | PR | PI | 0001 | F2A-707602 | AFC | IFC | 2021-09-07 | 2021-09-02 | 2021-09-07 | -5 | 5 | 0 | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-01 | 0 |  | D03 | IFA | T-0653 | 2022-02-28 | 1400/12/09 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0063 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PCS-00-01417 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2290/182828 | 2021-09-02 | 1400/06/11 | 2021-09-07 | 1400/06/16 | RJ | [10 empty] | D01 | IFC | T-0201 | 2021-11-01 | 1400/08/10 |  |  |  | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-279084 | 2021-11-16 | 1400/08/25 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0345 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-PCS-00-02540 | 2022-01-03 | 1400/10/13 | CM-C3 | PEDCO-BK-W046S-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-342085 | 2021-12-30 | 1400/10/09 | 2022-01-03 | 1400/10/13 | RJ | NISOC-BK-W046S-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0653 | 2022-02-28 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0001_D02
2 | 4 | 1 | 1 | 1 | 0 | 3 | 2.4.1.1.1 | P&ID for Diesel Oil Drum- W0046S | BK-W046S-PEDCO-110-PR-PI-0002 | BK-W046S-PEDCO-110-PR-PI-0002 | BK | W046S | PEDCO | 110 | PR | PI | 0002 | F2A-707603 | AFC | IFC | 2021-11-30 | 2021-12-01 | 2021-12-06 | 1 | 5 | 6 | IFA | 2022-01-17 | 2022-02-08 | 2022-02-12 | 22 | 4 | 26 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 0 | 0 | -44675 | 0 | -44675 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-16 | 0 |  | D03 | IFA | T-0794 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03985 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0242 | 2021-11-16 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02160 | 2021-11-30 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300481 | 2021-12-01 | 1400/09/10 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0423 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02778 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D00 | [5 empty] | 1400-2294-402841 | 2022-02-08 | 1400/11/19 | 2022-02-12 | 1400/11/23 | AP | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D00 | [9 empty] | D02 | IFA | T-0649 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03591 | 2022-03-14 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D01 | [5 empty] | 1400-2294-443282 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/24 | RJ | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D01 | [9 empty] | D03 | IFA | T-0794 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03985 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D02 | [11 empty] | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0002_D02
2 | 4 | 1 | 1 | 1 | 0 | 4 | 2.4.1.1.1 | P&ID for Potable Water Tank - W0046S | BK-W046S-PEDCO-110-PR-PI-0003 | BK-W046S-PEDCO-110-PR-PI-0003 | BK | W046S | PEDCO | 110 | PR | PI | 0003 | F2A-707604 | AFC | IFC | 2021-11-30 | 2021-12-01 | 2021-12-06 | 1 | 5 | 6 | IFA | 2022-01-17 | 2022-02-08 | 2022-02-12 | 22 | 4 | 26 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 0 | 0 | -44675 | 0 | -44675 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-16 | 0 |  | D03 | IFA | T-0794 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03985 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0242 | 2021-11-16 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02160 | 2021-11-30 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300481 | 2021-12-01 | 1400/09/10 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0423 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02778 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D00 | [5 empty] | 1400-2294-402841 | 2022-02-08 | 1400/11/19 | 2022-02-12 | 1400/11/23 | AP | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D00 | [9 empty] | D02 | IFA | T-0649 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03591 | 2022-03-14 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D01 | [5 empty] | 1400-2294-443282 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/24 | RJ | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D01 | [9 empty] | D03 | IFA | T-0794 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03985 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D02 | [11 empty] | NISOC-CRS-BK-W046S-PEDCO-110-PR-PI-0003_D02
2 | 4 | 1 | 1 | 2 | 0 | 0 | 2.4.1.1.2 | List
2 | 4 | 1 | 1 | 2 | 0 | 1 | 2.4.1.1.2 | Line List - W0046S | BK-W046S-PEDCO-110-PR-LI-0001 | BK-W046S-PEDCO-110-PR-LI-0001 | BK | W046S | PEDCO | 110 | PR | LI | 0001 | F0Z-707605 | AFC | IFC | 44446 | 44441 | 44446 | -5 | 5 | 0 | IFC | 44522 | 44527 | 44529 | 5 | 2 | 7 | IFA | 44573 | 0 | 0 | -44573 | 0 | -44573 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-08 | 0 |  | D02 | IFA | T-0403 | 2021-12-29 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-LI-0001 _D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0063 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PCS-00-01417 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2290/182828 | 2021-09-02 | 1400/06/11 | 2021-09-07 | 1400/06/16 | RJ | [10 empty] | D01 | IFC | T-0217 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PCS-00-02051 | 2021-11-20 | 1400/08/29 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1400-2290-293083 | 2021-11-27 | 1400/09/06 | 2021-11-29 | 1400/09/08 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-LI-0001_D00 | [9 empty] | D02 | IFA | T-0403 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-LI-0001 _D01 | [11 empty] | NISOC-CRS-BK-W046S-PEDCO-110-PR-LI-0001_D01
2 | 4 | 1 | 1 | 3 | 0 | 0 | 2.4.1.1.3 | Report | [145 empty] | 1400/09/06
2 | 4 | 1 | 1 | 3 | 0 | 1 | 2.4.1.1.3 | Flow line Hydraulic Calculation Report | BK-W046S-PEDCO-110-PR-RT-0001 | BK-W046S-PEDCO-110-PR-RT-0001 | BK | W046S | PEDCO | 110 | PR | RT | 0001 | F0Z-707606 | AFC | IFC | 44513 | 44514 | 44517 | 1 | 3 | 4 | IFA | 44576 | 44228 | 44597 | -348 | 369 | 21 | IFA | 44628 | 44630 | 44633 | 2 | 3 | 5 | IFA | 44695 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-30 | 0 |  | D03 | IFA | T-0878 | 2022-04-30 | 1401/02/10 | T-0878 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 2022-05-28 | 1402/03/07 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0197 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-PCS-00-01993 | 2021-11-14 | 1400/08/23 | CM-C3 | [6 empty] | 1400-2294-275250 | 2021-11-14 | 1400/08/23 | 2021-11-17 | 1400/08/26 | CM | [10 empty] | D01 | IFA | T-0413 | 2022-01-01 | 1400/10/11 |  |  |  | BK-SUR-ENG-PCS-00-02735 | 2022-01-19 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D00 | [5 empty] | 1400-2294-392131 | 2021-02-01 | 1400/11/12 | 2022-02-05 | 1400/11/16 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-0627 | 2022-02-22 | 1400/12/03 |  |  |  | BK-SUR-ENG-PCS-00-03387 | 2022-03-07 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D01 | [5 empty] | 1400-2294-443285 | 2022-03-10 | 1400/12/19 | 2022-03-13 | 1400/12/22 | CM | NISOC-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D01 | [9 empty] | D03 | IFA | T-0878 | 2022-04-30 | 1401/02/10 | T-0878 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 2022-05-28 | 1402/03/07 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D02 | [11 empty] | NISOC-CRS-BK-W046S-PEDCO-110-PR-RT-0001_D02
2 | 4 | 1 | 1 | 4 | 0 | 0 | 2.4.1.1.4 | Data Sheet
2 | 4 | 1 | 1 | 4 | 0 | 1 | 2.4.1.1 | Process Data Sheets For Instrument Devices - W046S | BK-W046S-PEDCO-110-PR-DT-0001 | BK-W046S-PEDCO-110-PR-DT-0001 | BK | W046S | PEDCO | 110 | PR | DT | 0001 | F0Z-707607 | AFC | IFC | 44677 | 44689 | 44695 | 12 | 6 | 18 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-12 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04093 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 2022-05-14 | 1401/02/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-PCS-01-04093 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 2022-05-14 | 1401/02/24 | CM
2 | 4 | 1 | 2 | 0 | 0 | 0 | 2.4.1.2 | HVAC/Plumbing
2 | 4 | 1 | 2 | 1 | 0 | 0 | 2.4.1.2.1 | Calculation
2 | 4 | 1 | 2 | 1 | 0 | 1 | 2.4.1.2.1 | HVAC Calculation Note For Switchgear Building - W046S | BK-W046S-PEDCO-110-HV-CN-0001 | BK-W046S-PEDCO-110-HV-CN-0001 | BK | W046S | PEDCO | 110 | HV | CN | 0001 | F0Z-707608 | AFD | IFC | 2022-03-28 | 2022-03-23 | 2022-03-26 | -5 | 3 | -2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-14 | 0 |  | D00 | IFC | T-0731 | 2022-03-14 | 1400/12/23 | 0 | 0 | 0 | BK-SUR-ENG-HVC-01-03861 | 2022-04-11 | 1401/01/22 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-1285 | 2022-03-23 | 1401/01/06 | 2022-03-26 | 1401/01/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0731 | 2022-03-14 | 1400/12/23 |  |  |  | BK-SUR-ENG-HVC-01-03861 | 2022-04-11 | 1401/01/22 | CM-C3 | [6 empty] | 1401-2294-1285 | 2022-03-23 | 1401/01/06 | 2022-03-26 | 1401/01/09 | CM
2 | 4 | 1 | 2 | 1 | 0 | 2 | 2.4.1.2.1 | HVAC Calculation Note For Security Building - W046S | BK-W046S-PEDCO-110-HV-CN-0002 | BK-W046S-PEDCO-110-HV-CN-0002 | BK | W046S | PEDCO | 110 | HV | CN | 0002 | F0Z-707609 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 2 | 2 | 0 | 0 | 2.4.1.2.2 | Data Sheets
2 | 4 | 1 | 2 | 2 | 0 | 1 | 2.4.1.2.2 | Data Sheets For Main HVAC Equipment - W046S | BK-W046S-PEDCO-110-HV-DT-0001 | BK-W046S-PEDCO-110-HV-DT-0001 | BK | W046S | PEDCO | 110 | HV | DT | 0001 | F0Z-707610 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 2 | 3 | 0 | 0 | 2.4.1.2.3 | Drawing/Diagram
2 | 4 | 1 | 2 | 3 | 0 | 1 | 2.4.1.2.3 | HVAC System Layout For Switchgear Building - W046S | BK-W046S-PEDCO-110-HV-PY-0001 | BK-W046S-PEDCO-110-HV-PY-0001 | BK | W046S | PEDCO | 110 | HV | PY | 0001 | F4B-707611 | AFC | IFC | 2022-05-03 | 2022-04-30 | 2022-05-01 | -3 | 1 | -2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-19 | 0 |  | D00 | IFC | T-0846 | 2022-04-19 | 1401/01/30 | 0 | 0 | 0 | BK-SUR-ENG-HVC-01-04149 | 2022-05-07 | 1401/02/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43977 | 2022-04-30 | 1401/02/10 | 2022-05-01 | 1401/02/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0846 | 2022-04-19 | 1401/01/30 |  |  |  | BK-SUR-ENG-HVC-01-04149 | 2022-05-07 | 1401/02/17 | CM-C3 | [6 empty] | 1401-2294-43977 | 2022-04-30 | 1401/02/10 | 2022-05-01 | 1401/02/11 | CM
2 | 4 | 1 | 2 | 3 | 0 | 2 | 2.4.1.2.3 | HVAC System Layout For Security Building - W046S | BK-W046S-PEDCO-110-HV-PY-0002 | BK-W046S-PEDCO-110-HV-PY-0002 | BK | W046S | PEDCO | 110 | HV | PY | 0002 | F4B-707612 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 2 | 3 | 0 | 3 | 2.4.1.2.3 | Plumbing & Sewage Piping Layout For Switchgear Building - W046S | BK-W046S-PEDCO-110-HV-PY-0003 | BK-W046S-PEDCO-110-HV-PY-0003 | BK | W046S | PEDCO | 110 | HV | PY | 0003 | F4B-707613 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 2 | 3 | 0 | 4 | 2.4.1.2.3 | Plumbing & Sewage Piping Layout For Security Building - W046S | BK-W046S-PEDCO-110-HV-PY-0004 | BK-W046S-PEDCO-110-HV-PY-0004 | BK | W046S | PEDCO | 110 | HV | PY | 0004 | F4B-707614 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 2 | 4 | 0 | 0 | 2.4.1.2.4 | MTO
2 | 4 | 1 | 2 | 4 | 0 | 1 | 2.4.1.2 | MTO For Building HVAC & Plumbing Systems - W046S | BK-W046S-PEDCO-110-HV-MT-0001 | BK-W046S-PEDCO-110-HV-MT-0001 | BK | W046S | PEDCO | 110 | HV | MT | 0001 | F8Z-707615 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 3 | 0 | 0 | 0 | 2.4.1.3 | Piping
2 | 4 | 1 | 3 | 1 | 0 | 0 | 2.4.1.3.1 | Drawing/Diagram
2 | 4 | 1 | 3 | 1 | 0 | 1 | 2.4.1.3.1 | Plot Plan Drawing - W046S | BK-W046S-PEDCO-110-PI-DW-0001 | BK-W046S-PEDCO-110-PI-DW-0001 | BK | W046S | PEDCO | 110 | PI | DW | 0001 | F5A-707616 | AFC | IFC | 2022-05-23 | 0 | 0 | -44704 | 0 | -44704 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-09 | 0 |  | D00 | IFC | T-0919 | 2022-05-09 | 1401/02/19 | T-0919 | 2022-05-09 | 1401/02/19 | BK-SUR-ENG-PIP-01-04388 | 2022-05-23 | 1401/03/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0919 | 2022-05-09 | 1401/02/19 | T-0919 | 2022-05-09 | 1401/02/19 | BK-SUR-ENG-PIP-01-04388 | 2022-05-23 | 1401/03/02 | CM-C3
2 | 4 | 1 | 3 | 1 | 0 | 2 | 2.4.1.3.1 | Piping Plan - W046S | BK-W046S-PEDCO-110-PI-DW-0002 | BK-W046S-PEDCO-110-PI-DW-0002 | BK | W046S | PEDCO | 110 | PI | DW | 0002 | F4L-707617 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 3 | 1 | 0 | 3 | 2.4.1.3.1 | Isometric Drawings - W046S | BK-W046S-PEDCO-110-PI-DW-0003 | BK-W046S-PEDCO-110-PI-DW-0003 | BK | W046S | PEDCO | 110 | PI | DW | 0003 | F2L-707618 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 3 | 1 | 0 | 4 | 2.4.1.3.1 | Material Flow Diagram - W046S | BK-W046S-PEDCO-110-PI-DG-0001 | BK-W046S-PEDCO-110-PI-DG-0001 | BK | W046S | PEDCO | 110 | PI | DG | 0001 | F2A-707619 | AFC | IFC | 2021-11-22 | 2021-11-24 | 2021-11-27 | 2 | 3 | 5 | IFA | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-08 | 0 |  | D01 | IFA | T-0932 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04376 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PI-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-PI-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0219 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PIP-00-02060 | 2021-11-21 | 1400/08/30 | CM-C3 | [6 empty] | 1400-2294-289400 | 2021-11-24 | 1400/09/03 | 2021-11-27 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0932 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04376 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PI-DG-0001_D00 | [11 empty] | NISOC-CRS-BK-W046S-PEDCO-110-PI-DG-0001_D00
2 | 4 | 1 | 3 | 2 | 0 | 0 | 2.4.1.3.2 | List
2 | 4 | 1 | 3 | 2 | 0 | 1 | 2.4.1.3.2 | Piping Support List - W046S | BK-W046S-PEDCO-110-PI-LI-0001 | BK-W046S-PEDCO-110-PI-LI-0001 | BK | W046S | PEDCO | 110 | PI | LI | 0001 | F0Z-707620 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 3 | 2 | 0 | 2 | 2.4.1.3.2 | Critical Line List - W046S | BK-W046S-PEDCO-110-PI-LI-0002 | BK-W046S-PEDCO-110-PI-LI-0002 | BK | W046S | PEDCO | 110 | PI | LI | 0002 | F0Z-707621 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 3 | 3 | 0 | 0 | 2.4.1.3.3 | Report
2 | 4 | 1 | 3 | 3 | 0 | 1 | 2.4.1.3.3 | PDMS Model Review Report (30%) - W046S | BK-W046S-PEDCO-110-PI-RT-0001 | BK-W046S-PEDCO-110-PI-RT-0001 | BK | W046S | PEDCO | 110 | PI | RT | 0001 | F0Z-707622 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 3 | 3 | 0 | 2 | 2.4.1.3.3 | PDMS Model Review Report (60%) - W046S | BK-W046S-PEDCO-110-PI-RT-0002 | BK-W046S-PEDCO-110-PI-RT-0002 | BK | W046S | PEDCO | 110 | PI | RT | 0002 | F0Z-707623 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 3 | 3 | 0 | 3 | 2.4.1.3.3 | PDMS Model Review Report (90%) - W046S | BK-W046S-PEDCO-110-PI-RT-0003 | BK-W046S-PEDCO-110-PI-RT-0003 | BK | W046S | PEDCO | 110 | PI | RT | 0003 | F0Z-707624 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 3 | 4 | 0 | 0 | 2.4.1.3.4 | MTO
2 | 4 | 1 | 3 | 4 | 0 | 1 | 2.4.1.3 | MTO For Pipes - W046S | BK-W046S-PEDCO-110-PI-MT-0001 | BK-W046S-PEDCO-110-PI-MT-0001 | BK | W046S | PEDCO | 110 | PI | MT | 0001 | F8Z-707625 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 3 | 4 | 0 | 2 | 2.4.1.3 | MTO For Fittings - W046S | BK-W046S-PEDCO-110-PI-MT-0002 | BK-W046S-PEDCO-110-PI-MT-0002 | BK | W046S | PEDCO | 110 | PI | MT | 0002 | F8Z-707626 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 3 | 4 | 0 | 3 | 2.4.1.3 | MTO For Flanges - W046S | BK-W046S-PEDCO-110-PI-MT-0003 | BK-W046S-PEDCO-110-PI-MT-0003 | BK | W046S | PEDCO | 110 | PI | MT | 0003 | F8Z-707627 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 3 | 4 | 0 | 4 | 2.4.1.3 | MTO For Manual Valves - W046S | BK-W046S-PEDCO-110-PI-MT-0004 | BK-W046S-PEDCO-110-PI-MT-0004 | BK | W046S | PEDCO | 110 | PI | MT | 0004 | F8Z-707628 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 3 | 4 | 0 | 5 | 2.4.1.3 | MTO For Gaskets - W046S | BK-W046S-PEDCO-110-PI-MT-0005 | BK-W046S-PEDCO-110-PI-MT-0005 | BK | W046S | PEDCO | 110 | PI | MT | 0005 | F8Z-707629 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 3 | 4 | 0 | 6 | 2.4.1.3 | MTO For Bolt & Nuts - W046S | BK-W046S-PEDCO-110-PI-MT-0006 | BK-W046S-PEDCO-110-PI-MT-0006 | BK | W046S | PEDCO | 110 | PI | MT | 0006 | F8Z-707630 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 4 | 0 | 0 | 0 | 2.4.1.4 | Pipeline & Flow line
2 | 4 | 1 | 4 | 1 | 0 | 0 | 2.4.1.4.1 | Drawing/Diagram
2 | 4 | 1 | 4 | 1 | 0 | 1 | 2.4.1.4.1 | Flow line Transversal Drawings - W046S | BK-W046S-PEDCO-110-PL-DW-0002 | BK-W046S-PEDCO-110-PL-DW-0002 | BK | W046S | PEDCO | 110 | PL | DW | 0002 | F4A-707631 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 4 | 2 | 0 | 0 | 2.4.1.4.2 | List
2 | 4 | 1 | 4 | 2 | 0 | 1 | 2.4.1.4.2 | Road Crossing Location List | BK-W046S-PEDCO-110-PL-LI-0001 | BK-W046S-PEDCO-110-PL-LI-0001 | BK | W046S | PEDCO | 110 | PL | LI | 0001 | F0Z-707632 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 4 | 3 | 0 | 0 | 2.4.1.4.3 | MTO
2 | 4 | 1 | 4 | 3 | 0 | 1 | 2.4.1.4 | MTO For Line Pipes (Flow lines) - W046S | BK-W046S-PEDCO-110-PL-MT-0001 | BK-W046S-PEDCO-110-PL-MT-0001 | BK | W046S | PEDCO | 110 | PL | MT | 0001 | F8Z-707633 | IFI | IFI | 44444 | 44438 | 44444 | -6 | 6 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2021-08-22 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | 1400/05/31 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | 1400/05/31 | CM-C2 | [6 empty] | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM
2 | 4 | 1 | 5 | 0 | 0 | 0 | 2.4.1.5 | Control & Instrumentation
2 | 4 | 1 | 5 | 1 | 0 | 0 | 2.4.1.5.1 | Drawing/Diagram
2 | 4 | 1 | 5 | 1 | 0 | 1 | 2.4.1.5.1 | Instrument Location Layout Drawing - W046S | BK-W046S-PEDCO-110-IN-PY-0001 | BK-W046S-PEDCO-110-IN-PY-0001 | BK | W046S | PEDCO | 110 | IN | PY | 0001 | F2J-707634 | AFC | IFC | 44711 | 0 | 0 | -44711 | 0 | -44711 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-16 | 0 |  | D00 | IFC | T-0958 | 2022-05-16 | 1401/02/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04488 | 2022-05-29 | 1401/03/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0958 | 2022-05-16 | 1401/02/26 |  |  |  | BK-SUR-ENG-INS-01-04488 | 2022-05-29 | 1401/03/09 | CM-C2
2 | 4 | 1 | 5 | 2 | 0 | 0 | 2.4.1.5.2 | MTO
2 | 4 | 1 | 5 | 2 | 0 | 1 | 2.4.1.5 | MTO For Instrument Tube and Fitting - W046S | BK-W046S-PEDCO-110-IN-MT-0001 | BK-W046S-PEDCO-110-IN-MT-0001 | BK | W046S | PEDCO | 110 | IN | MT | 0001 | F8Z-707635 | IFI | IFI | 44562 | 44199 | 44565 | -363 | 366 | 3 | IFI | 44604 | 44630 | 44634 | 26 | 4 | 30 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-18 | 2022-01-29 |  | D01 | IFI | T-0521 | 2022-01-29 | 1400/11/09 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03031 | 2022-02-12 | 1400/11/23 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443228 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/23 | AP | NISOC-CRS-BK-W046S-PEDCO-110-IN-MT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0358 | 2021-12-18 | 1400/09/27 | [13 empty] | 1400-2294-347081 | 2021-01-03 | 1400/10/13 | 2022-01-04 | 1400/10/14 | CM | [10 empty] | D01 | IFI | T-0521 | 2022-01-29 | 1400/11/09 |  |  |  | BK-SUR-ENG-INS-00-03031 | 2022-02-12 | 1400/11/23 | CM-C2 | [6 empty] | 1400-2294-443228 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/23 | AP | NISOC-CRS-BK-W046S-PEDCO-110-IN-MT-0001_D00
2 | 4 | 1 | 6 | 0 | 0 | 0 | 2.4.1.6 | Safety
2 | 4 | 1 | 6 | 1 | 0 | 0 | 2.4.1.6.1 | Drawing/Diagram
2 | 4 | 1 | 6 | 1 | 0 | 1 | 2.4.1.6.1 | Hazardous Area Classification Layout - W046S | BK-W046S-PEDCO-110-SA-PY-0001 | BK-W046S-PEDCO-110-SA-PY-0001 | BK | W046S | PEDCO | 110 | SA | PY | 0001 | F2L-707636 | AFC | IFC | 2022-06-08 | 0 | 0 | -44720 | 0 | -44720 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-25 | 0 |  | D00 | IFC | T-1003 | 2022-05-25 | 1401/03/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1003 | 2022-05-25 | 1401/03/03
2 | 4 | 1 | 6 | 1 | 0 | 2 | 2.4.1.6.1 | Safety & Fire Fighting Equipment Location Layout - W046S | BK-W046S-PEDCO-110-SA-PY-0002 | BK-W046S-PEDCO-110-SA-PY-0002 | BK | W046S | PEDCO | 110 | SA | PY | 0002 | F2L-707637 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 6 | 1 | 0 | 3 | 2.4.1.6.1 | Escape Route & Safety Sign Layout - W046S | BK-W046S-PEDCO-110-SA-PY-0003 | BK-W046S-PEDCO-110-SA-PY-0003 | BK | W046S | PEDCO | 110 | SA | PY | 0003 | F2L-707638 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 6 | 2 | 0 | 0 | 2.4.1.6.2 | List
2 | 4 | 1 | 6 | 2 | 0 | 1 | 2.4.1.6.2 | Hazard Source List - W046S | BK-W046S-PEDCO-110-SA-LI-0001 | BK-W046S-PEDCO-110-SA-LI-0001 | BK | W046S | PEDCO | 110 | SA | LI | 0001 | F0Z-707639 | AFC | IFC | 44523 | 44530 | 44536 | 7 | 6 | 13 | IFA | 44632 | 44656 | 44660 | 24 | 4 | 28 | IFA | 44681 | 0 | 0 | -44681 | 0 | -44681 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-09 | 0 |  | D02 | IFA | T-0821 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-SA-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0220 | 2021-11-09 | 1400/08/18 | [13 empty] | 1400-2290-298651 | 2021-11-30 | 1400/09/09 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0645 | 2022-02-26 | 1400/12/07 | [13 empty] | 1401-2294-13856 | 2022-04-05 | 1401/01/18 | 2022-04-09 | 1401/01/20 | CM | NISOC-CRS-BK-W046S-PEDCO-110-SA-LI-0001_D00 | [9 empty] | D02 | IFA | T-0821 | 2022-04-16 | 1401/01/27 | [19 empty] | NISOC-CRS-BK-W046S-PEDCO-110-SA-LI-0001_D01
2 | 4 | 1 | 6 | 3 | 0 | 0 | 2.4.1.6.3 | MTO
2 | 4 | 1 | 6 | 3 | 0 | 1 | 2.4.1.6 | MTO For Fire Fighting & Safety Equipment - W046S | BK-W046S-PEDCO-110-SA-MT-0001 | BK-W046S-PEDCO-110-SA-MT-0001 | BK | W046S | PEDCO | 110 | SA | MT | 0001 | F8Z-707640 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 6 | 3 | 0 | 2 | 2.4.1.6 | MTO For Safety Sign - W046S | BK-W046S-PEDCO-110-SA-MT-0002 | BK-W046S-PEDCO-110-SA-MT-0002 | BK | W046S | PEDCO | 110 | SA | MT | 0002 | F8Z-707641 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 7 | 0 | 0 | 0 | 2.4.1.7 | Electrical
2 | 4 | 1 | 7 | 1 | 0 | 0 | 2.4.1.7.1 | MTO
2 | 4 | 1 | 7 | 1 | 0 | 1 | 2.4.1.7 | MTO For Transmission Over Head Line - W046S | BK-W046S-PEDCO-110-EL-MT-0001 | BK-W046S-PEDCO-110-EL-MT-0001 | BK | W046S | PEDCO | 110 | EL | MT | 0001 | F8Z-707642 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 7 | 1 | 0 | 2 | 2.4.1.7 | MTO For Earthing & Lightning Systems - W046S | BK-W046S-PEDCO-110-EL-MT-0002 | BK-W046S-PEDCO-110-EL-MT-0002 | BK | W046S | PEDCO | 110 | EL | MT | 0002 | F8Z-707643 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 7 | 1 | 0 | 3 | 2.4.1.7 | MTO For Lighting & Small Powers - W046S | BK-W046S-PEDCO-110-EL-MT-0003 | BK-W046S-PEDCO-110-EL-MT-0003 | BK | W046S | PEDCO | 110 | EL | MT | 0003 | F8Z-707644 | IFI | IFI | 2022-06-01 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-18 | 2022-05-18 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04483 | 2022-05-29 | 1401/03/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 |  |  |  | BK-SUR-ENG-ELE-01-04483 | 2022-05-29 | 1401/03/09 | CM-C2
2 | 4 | 1 | 7 | 1 | 0 | 4 | 2.4.1.7 | MTO For Power & Control Cables - W046S | BK-W046S-PEDCO-110-EL-MT-0004 | BK-W046S-PEDCO-110-EL-MT-0004 | BK | W046S | PEDCO | 110 | EL | MT | 0004 | F8Z-707645 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 7 | 1 | 0 | 5 | 2.4.1.7 | MTO For Tray/Ladder and Accessories - W046S | BK-W046S-PEDCO-110-EL-MT-0005 | BK-W046S-PEDCO-110-EL-MT-0005 | BK | W046S | PEDCO | 110 | EL | MT | 0005 | F8Z-707646 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 7 | 1 | 0 | 6 | 2.4.1.7 | MTO For Electrical Bulk Items - W046S | BK-W046S-PEDCO-110-EL-MT-0006 | BK-W046S-PEDCO-110-EL-MT-0006 | BK | W046S | PEDCO | 110 | EL | MT | 0006 | F8Z-707647 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 8 | 0 | 0 | 0 | 2.4.1.8 | Architecture
2 | 4 | 1 | 8 | 1 | 0 | 0 | 2.4.1.8.1 | Drawing/Diagram
2 | 4 | 1 | 8 | 1 | 0 | 1 | 2.4.1.8.1 | Architectural Drawing For Diesel Generator Shelter of Well Pads - W046S | BK-W046S-PEDCO-110-AR-DW-0001 | BK-W046S-PEDCO-110-AR-DW-0001 | BK | W046S | PEDCO | 110 | AR | DW | 0001 | F4B-707648 | AFC | IFC | 2022-05-15 | 2022-05-09 | 2022-05-16 | -6 | 7 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-01 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04151 | 2022-05-07 | 1401/02/17 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04151 | 2022-05-07 | 1401/02/17 | CM-C2 | [6 empty] | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | CM
2 | 4 | 1 | 8 | 1 | 0 | 2 | 2.4.1.8.1 | Architectural Drawing For WHCP/HPU Shelter of Well Pads - W046S | BK-W046S-PEDCO-110-AR-DW-0002 | BK-W046S-PEDCO-110-AR-DW-0002 | BK | W046S | PEDCO | 110 | AR | DW | 0002 | F4B-707649 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 8 | 1 | 0 | 3 | 2.4.1.8.1 | Architectural Drawing For Switchgear Building of Well Pads - W046S | BK-W046S-PEDCO-110-AR-DW-0003 | BK-W046S-PEDCO-110-AR-DW-0003 | BK | W046S | PEDCO | 110 | AR | DW | 0003 | F4B-707650 | AFC | IFC | 2022-03-16 | 2022-03-10 | 2022-03-12 | -6 | 2 | -4 | IFC | 2022-06-01 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-18 | 0 |  | D01 | IFC | T-0974 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W046S-PEDCO-110-AR-DW-0003-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-AR-DW-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0661 | 2022-03-02 | 1400/12/11 |  |  |  | BK-SUR-ENG-ARC-00-03449 | 2022-03-12 | 1400/12/21 | CM-C2 | [6 empty] | 1400-2294-443270 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | RJ | [10 empty] | D01 | IFC | T-0974 | 2022-05-18 | 1401/02/28 | [7 empty] | PEDCO-CRS-BK-W046S-PEDCO-110-AR-DW-0003-D00 | [11 empty] | NISOC-CRS-BK-W046S-PEDCO-110-AR-DW-0003_D00
2 | 4 | 1 | 8 | 1 | 0 | 4 | 2.4.1.8.1 | Architectural Drawing For Security Building of Well Pads - W046S | BK-W046S-PEDCO-110-AR-DW-0004 | BK-W046S-PEDCO-110-AR-DW-0004 | BK | W046S | PEDCO | 110 | AR | DW | 0004 | F4B-707651 | AFC | IFC | 2022-05-15 | 2022-05-14 | 2022-05-16 | -1 | 2 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04190 | 2022-05-10 | 1401/02/20 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 2022-05-16 | 1401/02/26 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04190 | 2022-05-10 | 1401/02/20 | CM-C2 | [6 empty] | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 2022-05-16 | 1401/02/26 | RJ
2 | 4 | 1 | 8 | 2 | 0 | 0 | 2.4.1.8.2 | MTO
2 | 4 | 1 | 8 | 2 | 0 | 1 | 2.4.1.8 | MTO For Architectural Works - W0046S | BK-W046S-PEDCO-110-AR-MT-0001 | BK-W046S-PEDCO-110-AR-MT-0001 | BK | W046S | PEDCO | 110 | AR | MT | 0001 | F8Z-707652 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 9 | 0 | 0 | 0 | 2.4.1.9 | Civil
2 | 4 | 1 | 9 | 1 | 0 | 0 | 2.4.1.9.1 | Drawing/Diagram
2 | 4 | 1 | 9 | 1 | 0 | 1 | 2.4.1.9.1 | General Civil Layout -W046S | BK-W046S-PEDCO-110-CV-PY-0001 | BK-W046S-PEDCO-110-CV-PY-0001 | BK | W046S | PEDCO | 110 | CV | PY | 0001 | F4A-707653 | AFC | IFC | 2022-05-16 | 0 | 0 | -44697 | 0 | -44697 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-02 | 0 |  | D00 | IFC | T-0900 | 2022-05-02 | 1401/02/12 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-04158 | 2022-05-07 | 1401/02/17 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0900 | 2022-05-02 | 1401/02/12 |  |  |  | BK-SUR-ENG-CIV-01-04158 | 2022-05-07 | 1401/02/17 | CM-C2
2 | 4 | 1 | 9 | 1 | 0 | 2 | 2.4.1.9.1 | Civil and Structural drawings -W046S | BK-W046S-PEDCO-110-CV-PY-0002 | BK-W046S-PEDCO-110-CV-PY-0002 | BK | W046S | PEDCO | 110 | CV | PY | 0002 | F4S-707654 | AFC | IFC | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-22 | 0 |  | D00 | IFC | T-0988 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0988 | 2022-05-22 | 1401/03/01
2 | 4 | 1 | 9 | 1 | 0 | 3 | 2.4.1.9.1 | Rough Grading Plans -W046S | BK-W046S-PEDCO-110-CV-DW-0001 | BK-W046S-PEDCO-110-CV-DW-0001 | BK | W046S | PEDCO | 110 | CV | DW | 0001 | F4S-707655 | AFC | IFC | 2021-12-26 | 2021-12-16 | 2021-12-19 | -10 | 3 | -7 | IFA | 2022-02-07 | 2022-01-31 | 2022-02-02 | -7 | 2 | -5 | IFA | 2022-05-22 | 2022-05-11 | 2022-05-16 | -11 | 5 | -6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-12 | 0 |  | D02 | IFA | T-0910 | 2022-05-08 | 1401/02/18 | T-0910 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-CIV-01-04381 | 2022-05-23 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-CV-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59411 | 2022-05-11 | 1401/02/21 | 2022-05-16 | 1401/02/26 | AP | NISOC-CRS-BK-W046S-PEDCO-110-CV-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0331 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-CIV-00-02371 | 2021-12-19 | 1400/09/28 | CM-C3 | [6 empty] | 1400-2294-320697 | 2021-12-16 | 1400/09/25 | 2021-12-19 | 1400/09/28 | CM | [10 empty] | D01 | IFA | T-0496 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-CIV-00-02833 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-CV-DW-0001_D00 | [5 empty] | 1400-2294-389630 | 2022-01-31 | 1400/11/11 | 2022-02-02 | 1400/11/13 | CM | NISOC-CRS-BK-W046S-PEDCO-110-CV-DW-0001_D00 | [9 empty] | D02 | IFA | T-0910 | 2022-05-08 | 1401/02/18 | T-0910 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-CIV-01-04381 | 2022-05-23 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-W046S-PEDCO-110-CV-DW-0001_D01 | [5 empty] | 1401-2294-59411 | 2022-05-11 | 1401/02/21 | 2022-05-16 | 1401/02/26 | AP | NISOC-CRS-BK-W046S-PEDCO-110-CV-DW-0001_D01
2 | 4 | 1 | 9 | 2 | 0 | 0 | 2.4.1.9.2 | Calculation
2 | 4 | 1 | 9 | 2 | 0 | 1 | 2.4.1.9.2 | Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W046S | BK-W046S-PEDCO-110-CV-CN-0001 | BK-W046S-PEDCO-110-CV-CN-0001 | BK | W046S | PEDCO | 110 | CV | CN | 0001 | F0Z-707656 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 9 | 3 | 0 | 0 | 2.4.1.9.3 | MTO
2 | 4 | 1 | 9 | 3 | 0 | 1 | 2.4.1.9 | MTO For Civil Works - W046S | BK-W046S-PEDCO-110-CV-MT-0001 | BK-W046S-PEDCO-110-CV-MT-0001 | BK | W046S | PEDCO | 110 | CV | MT | 0001 | F8Z-707657 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 10 | 0 | 0 | 0 | 2.4.1.10 | Structure
2 | 4 | 1 | 10 | 1 | 0 | 0 | 2.4.1.10.1 | Drawing/Diagram
2 | 4 | 1 | 10 | 1 | 0 | 1 | 2.4.1.10.1 | Fuel Oil Storage Drum Detail Drawing For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0003 | BK-W046S-PEDCO-110-ST-DW-0003 | BK | W046S | PEDCO | 110 | ST | DW | 0003 | F4G-707658 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 10 | 1 | 0 | 2 | 2.4.1.10.1 | Foundation Drawing For Security Building For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0004 | BK-W046S-PEDCO-110-ST-DW-0004 | BK | W046S | PEDCO | 110 | ST | DW | 0004 | F4Q-707659 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 10 | 1 | 0 | 3 | 2.4.1.10.1 | Structural Drawing For Security Building For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0005 | BK-W046S-PEDCO-110-ST-DW-0005 | BK | W046S | PEDCO | 110 | ST | DW | 0005 | F4M-707660 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 10 | 1 | 0 | 4 | 2.4.1.10.1 | Foundation Drawing For Switchgear Building For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0006 | BK-W046S-PEDCO-110-ST-DW-0006 | BK | W046S | PEDCO | 110 | ST | DW | 0006 | F4Q-707661 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 10 | 1 | 0 | 5 | 2.4.1.10.1 | Structural Drawing For Switchgear Building For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0007 | BK-W046S-PEDCO-110-ST-DW-0007 | BK | W046S | PEDCO | 110 | ST | DW | 0007 | F4M-707662 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 10 | 1 | 0 | 6 | 2.4.1.10.1 | Foundation Drawing For Potable Water Tank For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0008 | BK-W046S-PEDCO-110-ST-DW-0008 | BK | W046S | PEDCO | 110 | ST | DW | 0008 | F4Q-707663 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 10 | 1 | 0 | 7 | 2.4.1.10.1 | Foundation Drawing For Diesel Generator Shelter For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0009 | BK-W046S-PEDCO-110-ST-DW-0009 | BK | W046S | PEDCO | 110 | ST | DW | 0009 | F4Q-707664 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 10 | 1 | 0 | 8 | 2.4.1.10.1 | Structural Drawing For Diesel Generator Shelter For Well Pads - W046S | BK-W046S-PEDCO-110-ST-DW-0010 | BK-W046S-PEDCO-110-ST-DW-0010 | BK | W046S | PEDCO | 110 | ST | DW | 0010 | F4M-707665 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 10 | 1 | 0 | 9 | 2.4.1.10.1 | Platform Structure Drawing - W046S | BK-W046S-PEDCO-110-ST-DW-0012 | BK-W046S-PEDCO-110-ST-DW-0012 | BK | W046S | PEDCO | 110 | ST | DW | 0012 | F4M-707666 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 10 | 1 | 0 | 10 | 2.4.1.10.1 | Foundation Drawing For Transmission Line Tower - W046S | BK-W046S-PEDCO-110-ST-DW-0013 | BK-W046S-PEDCO-110-ST-DW-0013 | BK | W046S | PEDCO | 110 | ST | DW | 0013 | F4Q-707667 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 10 | 2 | 0 | 0 | 2.4.1.10.2 | MTO
2 | 4 | 1 | 10 | 2 | 0 | 1 | 2.4.1.10 | MTO For Structural Works - W046S | BK-W046S-PEDCO-110-ST-MT-0001 | BK-W046S-PEDCO-110-ST-MT-0001 | BK | W046S | PEDCO | 110 | ST | MT | 0001 | F8Z-707668 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 11 | 0 | 0 | 0 | 2.4.1.11 | Survey (Topography) & Geotechnic/Geoelectric
2 | 4 | 1 | 11 | 1 | 0 | 0 | 2.4.1.11.1 | Geotechnic
2 | 4 | 1 | 11 | 1 | 1 | 0 | 2.4.11.1.1 | Report
2 | 4 | 1 | 11 | 1 | 1 | 1 | 2.4.1.11.1.1.1 | Geotechnical Investigation Report - W046S | BK-W046S-PEDCO-110-GT-RT-0001 | BK-W046S-PEDCO-110-GT-RT-0001 | BK | W046S | PEDCO | 110 | GT | RT | 0001 | F0Z-707669 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 11 | 1 | 2 | 0 | 2.4.11.1.2 | Drawing/Diagram
2 | 4 | 1 | 11 | 1 | 2 | 1 | 2.4.1.11.1.2.1 | Flow line Plan & Profile Drawings - W046S | BK-W046S-PEDCO-110-SU-DW-0001 | BK-W046S-PEDCO-110-SU-DW-0001 | BK | W046S | PEDCO | 110 | SU | DW | 0001 | F4A-707670 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 1 | 11 | 1 | 2 | 2 | 2.4.1.11.1.2.2 | Over Head Line Plan and Profile - W046S | BK-W046S-PEDCO-110-SU-DW-0002 | BK-W046S-PEDCO-110-SU-DW-0002 | BK | W046S | PEDCO | 110 | SU | DW | 0002 | F4A-707671 | AFC | IFC | 2022-04-09 | 2022-04-28 | 2022-05-01 | 19 | 3 | 22 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-26 | 0 |  | D00 | IFC | T-0745 | 2022-03-26 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-03676 | 2022-03-25 | 1401/01/08 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43154 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0745 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-CIV-01-03676 | 2022-03-25 | 1401/01/08 | CM-C2 | [6 empty] | 1401-2294-43154 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM
2 | 4 | 2 | 0 | 0 | 0 | 0 | 2.4.2 | Procurement Engineering
2 | 4 | 2 | 1 | 0 | 0 | 0 | 2.4.2.1 | Piping
2 | 4 | 2 | 1 | 1 | 0 | 0 | 2.4.2.1.1 | Pipes
2 | 4 | 2 | 1 | 1 | 1 | 0 | 2.4.1.1.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 1 | 1 | 1 | 1 | 2.4.2.1.1.1.1 | PMR For Pipes - W046S | BK-W046S-PEDCO-110-PI-MR-0001 | BK-W046S-PEDCO-110-PI-MR-0001 | BK | W046S | PEDCO | 110 | PI | MR | 0001 | F0Z-707672 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 1 | 2 | 0 | 2.4.1.1.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 1 | 2 | 1 | 2.4.2.1.1.2.1 | TBE For Pipes - W046S | BK-W046S-PEDCO-110-PI-TB-0001 | BK-W046S-PEDCO-110-PI-TB-0001 | BK | W046S | PEDCO | 110 | PI | TB | 0001 | F0Z-707673 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 2 | 0 | 0 | 2.4.2.1.2 | Fittings
2 | 4 | 2 | 1 | 2 | 1 | 0 | 2.4.1.2.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 1 | 2 | 1 | 1 | 2.4.2.1.2.1.1 | PMR For Fittings - W046S | BK-W046S-PEDCO-110-PI-MR-0002 | BK-W046S-PEDCO-110-PI-MR-0002 | BK | W046S | PEDCO | 110 | PI | MR | 0002 | F0Z-707674 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 2 | 2 | 0 | 2.4.1.2.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 2 | 2 | 1 | 2.4.2.1.2.2.1 | TBE For Fitting - W046S | BK-W046S-PEDCO-110-PI-TB-0002 | BK-W046S-PEDCO-110-PI-TB-0002 | BK | W046S | PEDCO | 110 | PI | TB | 0002 | F0Z-707675 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 3 | 0 | 0 | 2.4.2.1.3 | Flanges
2 | 4 | 2 | 1 | 3 | 1 | 0 | 2.4.1.3.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 1 | 3 | 1 | 1 | 2.4.2.1.3.1.1 | PMR For Flanges - W046S | BK-W046S-PEDCO-110-PI-MR-0003 | BK-W046S-PEDCO-110-PI-MR-0003 | BK | W046S | PEDCO | 110 | PI | MR | 0003 | F0Z-707676 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 3 | 2 | 0 | 2.4.1.3.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 3 | 2 | 1 | 2.4.2.1.3.2.1 | TBE For Flanges - W046S | BK-W046S-PEDCO-110-PI-TB-0003 | BK-W046S-PEDCO-110-PI-TB-0003 | BK | W046S | PEDCO | 110 | PI | TB | 0003 | F0Z-707677 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 4 | 0 | 0 | 2.4.2.1.4 | Manual Valves
2 | 4 | 2 | 1 | 4 | 1 | 0 | 2.4.1.4.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 1 | 4 | 1 | 1 | 2.4.2.1.4.1.1 | PMR For Manual Valves - W046S | BK-W046S-PEDCO-110-PI-MR-0004 | BK-W046S-PEDCO-110-PI-MR-0004 | BK | W046S | PEDCO | 110 | PI | MR | 0004 | F0Z-707678 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 4 | 2 | 0 | 2.4.1.4.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 4 | 2 | 1 | 2.4.2.1.4.2.1 | TBE For Manual Valves - W046S | BK-W046S-PEDCO-110-PI-TB-0004 | BK-W046S-PEDCO-110-PI-TB-0004 | BK | W046S | PEDCO | 110 | PI | TB | 0004 | F0Z-707679 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 5 | 0 | 0 | 2.4.2.1.5 | Gaskets
2 | 4 | 2 | 1 | 5 | 1 | 0 | 2.4.1.5.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 1 | 5 | 1 | 1 | 2.4.2.1.5.1.1 | PMR For Gaskets - W046S | BK-W046S-PEDCO-110-PI-MR-0005 | BK-W046S-PEDCO-110-PI-MR-0005 | BK | W046S | PEDCO | 110 | PI | MR | 0005 | F0Z-707680 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 5 | 2 | 0 | 2.4.1.5.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 5 | 2 | 1 | 2.4.2.1.5.2.1 | TBE For Gaskets - W046S | BK-W046S-PEDCO-110-PI-TB-0005 | BK-W046S-PEDCO-110-PI-TB-0005 | BK | W046S | PEDCO | 110 | PI | TB | 0005 | F0Z-707681 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 6 | 0 | 0 | 2.4.2.1.6 | Bolt & Nuts
2 | 4 | 2 | 1 | 6 | 1 | 0 | 2.4.1.6.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 1 | 6 | 1 | 1 | 2.4.2.1.6.1.1 | PMR For Bolt/Nuts - W046S | BK-W046S-PEDCO-110-PI-MR-0006 | BK-W046S-PEDCO-110-PI-MR-0006 | BK | W046S | PEDCO | 110 | PI | MR | 0006 | F0Z-707682 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 6 | 2 | 0 | 2.4.1.6.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 6 | 2 | 1 | 2.4.2.1.6.2.1 | TBE For Bolt/Nuts - W046S | BK-W046S-PEDCO-110-PI-TB-0006 | BK-W046S-PEDCO-110-PI-TB-0006 | BK | W046S | PEDCO | 110 | PI | TB | 0006 | F0Z-707683 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 7 | 0 | 0 | 2.4.2.1.7 | Sampling Connection
2 | 4 | 2 | 1 | 7 | 1 | 0 | 2.4.1.7.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 1 | 7 | 1 | 1 | 2.4.2.1.7.1.1 | PMR For Sampling Connection Set - W046S | BK-W046S-PEDCO-110-PI-MR-0007 | BK-W046S-PEDCO-110-PI-MR-0007 | BK | W046S | PEDCO | 110 | PI | MR | 0007 | F0Z-707684 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 7 | 2 | 0 | 2.4.1.7.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 7 | 2 | 1 | 2.4.2.1.7.2.1 | TBE For Sampling Connection - W046S | BK-W046S-PEDCO-110-PI-TB-0007 | BK-W046S-PEDCO-110-PI-TB-0007 | BK | W046S | PEDCO | 110 | PI | TB | 0007 | F0Z-707685 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 8 | 0 | 0 | 2.4.2.1.8 | Stone Trap
2 | 4 | 2 | 1 | 8 | 1 | 0 | 2.4.1.8.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 1 | 8 | 1 | 1 | 2.4.2.1.8.1.1 | PMR For Stone Trap - W046S | BK-W046S-PEDCO-110-PI-MR-0008 | BK-W046S-PEDCO-110-PI-MR-0008 | BK | W046S | PEDCO | 110 | PI | MR | 0008 | F0Z-707686 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 8 | 2 | 0 | 2.4.1.8.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 8 | 2 | 1 | 2.4.2.1.8.2.1 | TBE For Stone Trap - W046S | BK-W046S-PEDCO-110-PI-TB-0008 | BK-W046S-PEDCO-110-PI-TB-0008 | BK | W046S | PEDCO | 110 | PI | TB | 0008 | F0Z-707687 | IFI | IFI | 44720 | 0 | 0 | -44720 | 0 | -44720 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-25 | 2022-05-25 |  | D00 | IFI | T-1002 | 2022-05-25 | 1401/03/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1002 | 2022-05-25 | 1401/03/03
2 | 4 | 2 | 1 | 9 | 0 | 0 | 2.4.2.1.9 | Pipe Support
2 | 4 | 2 | 1 | 9 | 1 | 0 | 2.4.1.9.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 1 | 9 | 1 | 1 | 2.4.2.1.9.1.1 | PMR For Pipe Support - W046S | BK-W046S-PEDCO-110-PI-MR-0009 | BK-W046S-PEDCO-110-PI-MR-0009 | BK | W046S | PEDCO | 110 | PI | MR | 0009 | F0Z-707688 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 1 | 9 | 2 | 0 | 2.4.1.9.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 1 | 9 | 2 | 1 | 2.4.2.1.9.2.1 | TBE For Pipe Support - W046S | BK-W046S-PEDCO-110-PI-TB-0009 | BK-W046S-PEDCO-110-PI-TB-0009 | BK | W046S | PEDCO | 110 | PI | TB | 0009 | F0Z-707689 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 2 | 0 | 0 | 0 | 2.4.2.2 | HVAC
2 | 4 | 2 | 2 | 1 | 0 | 0 | 2.4.2.2.1 | Main HVAC Equipment
2 | 4 | 2 | 2 | 1 | 1 | 0 | 2.4.2.1.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 2 | 1 | 1 | 1 | 2.4.2.2.1.1.1 | PMR For Main HVAC Equipment - W046S | BK-W046S-PEDCO-110-HV-MR-0001 | BK-W046S-PEDCO-110-HV-MR-0001 | BK | W046S | PEDCO | 110 | HV | MR | 0001 | F0Z-707690 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 2 | 1 | 2 | 0 | 2.4.2.1.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 2 | 1 | 2 | 1 | 2.4.2.2.1.2.1 | TBE For Main HVAC Equipment - W046S | BK-W046S-PEDCO-110-HV-TB-0001 | BK-W046S-PEDCO-110-HV-TB-0001 | BK | W046S | PEDCO | 110 | HV | TB | 0001 | F0Z-707691 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 3 | 0 | 0 | 0 | 2.4.2.3 | Pipeline
2 | 4 | 2 | 3 | 1 | 0 | 0 | 2.4.2.3.1 | Line Pipe
2 | 4 | 2 | 3 | 1 | 1 | 0 | 2.4.3.1.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 3 | 1 | 1 | 1 | 2.4.2.3.1.1.1 | PMR For Line Pipes - W046S | BK-W046S-PEDCO-110-PL-MR-0001 | BK-W046S-PEDCO-110-PL-MR-0001 | BK | W046S | PEDCO | 110 | PL | MR | 0001 | F0Z-707692 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 3 | 1 | 2 | 0 | 2.4.3.1.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 3 | 1 | 2 | 1 | 2.4.2.3.1.2.1 | TBE For Line Pipes - W046S | BK-W046S-PEDCO-110-PL-TB-0001 | BK-W046S-PEDCO-110-PL-TB-0001 | BK | W046S | PEDCO | 110 | PL | TB | 0001 | F0Z-707693 | IFI | IFI | 44625 | 44630 | 44634 | 5 | 4 | 9 | IFI | 44709 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 2022-05-14 |  | D01 | IFI | T-0944 | 2022-05-14 | 1401/02/24 | T-0944 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W028-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W046S-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0604 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PPL-00-03409 | 2022-03-08 | 1400/12/17 | C4-RJ | [6 empty] | 1400-2294-443269 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/23 | CM | [10 empty] | D01 | IFI | T-0944 | 2022-05-14 | 1401/02/24 | T-0944 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PL-TB-0001-D00 | [11 empty] | NISOC-CRS-BK-W046S-PEDCO-110-PL-TB-0001-D00
2 | 4 | 2 | 3 | 2 | 0 | 0 | 2.4.2.3.2 | Line Support
2 | 4 | 2 | 3 | 2 | 1 | 0 | 2.4.3.2.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 3 | 2 | 1 | 1 | 2.4.2.3.2.1.1 | PMR For Flow Line Support - W046S | BK-W046S-PEDCO-110-PL-MR-0002 | BK-W046S-PEDCO-110-PL-MR-0002 | BK | W046S | PEDCO | 110 | PL | MR | 0002 | F0Z-707694 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 3 | 2 | 2 | 0 | 2.4.3.2.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 3 | 2 | 2 | 1 | 2.4.2.3.2.2.1 | TBE For Flow Line Support - W046S | BK-W046S-PEDCO-110-PL-TB-0002 | BK-W046S-PEDCO-110-PL-TB-0002 | BK | W046S | PEDCO | 110 | PL | TB | 0002 | F0Z-707695 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 4 | 0 | 0 | 0 | 2.4.2.4 | Control & Instrumentation
2 | 4 | 2 | 4 | 1 | 0 | 0 | 2.4.2.4.1 | Field Instrumentations
2 | 4 | 2 | 4 | 1 | 1 | 0 | 2.4.4.1.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 4 | 1 | 1 | 1 | 2.4.2.4.1.1.1 | PMR For Field Instrumentations - W046S | BK-W046S-PEDCO-110-IN-MR-0002 | BK-W046S-PEDCO-110-IN-MR-0002 | BK | W046S | PEDCO | 110 | IN | MR | 0002 | F0Z-707696 | IFI | IFI | 44557 | 44582 | 44221 | 25 | -361 | -336 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 2021-12-13 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | 1400/10/06 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-330276 | 2022-01-21 | 1400/11/01 | 2021-01-25 | 1400/11/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | 1400/10/06 | CM-C3 | [6 empty] | 1400-2294-330276 | 2022-01-21 | 1400/11/01 | 2021-01-25 | 1400/11/05 | CM
2 | 4 | 2 | 4 | 1 | 2 | 0 | 2.4.4.1.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 4 | 1 | 2 | 1 | 2.4.2.4.1.2.1 | TBE/TBA For Field Instrumentations - W046S | BK-W046S-PEDCO-110-IN-TB-0002 | BK-W046S-PEDCO-110-IN-TB-0002 | BK | W046S | PEDCO | 110 | IN | TB | 0002 | F0Z-707697 | IFI | IFI | 44723 | 0 | 0 | -44723 | 0 | -44723 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-28 | 2022-05-28 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07
2 | 4 | 2 | 4 | 2 | 0 | 0 | 2.4.2.4.2 | Instrument Bulk Items
2 | 4 | 2 | 4 | 2 | 1 | 0 | 2.4.4.2.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 4 | 2 | 1 | 1 | 2.4.2.4.2.1.1 | PMR For Instrument Bulk Items - W046S | BK-W046S-PEDCO-110-IN-MR-0003 | BK-W046S-PEDCO-110-IN-MR-0003 | BK | W046S | PEDCO | 110 | IN | MR | 0003 | F0Z-707698 | IFI | IFI | 44591 | 44227 | 44593 | -364 | 366 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-16 | 2022-01-16 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C2 | 0 | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C2 | 0 | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C2 |  | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C2 |  | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM
2 | 4 | 2 | 4 | 2 | 2 | 0 | 2.4.4.2.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 4 | 2 | 2 | 1 | 2.4.2.4.2.2.1 | TBE/TBA For Instrument Bulk Items - W046S | BK-W046S-PEDCO-110-IN-TB-0003 | BK-W046S-PEDCO-110-IN-TB-0003 | BK | W046S | PEDCO | 110 | IN | TB | 0003 | F0Z-707699 | IFI | IFI | 44608 | 44639 | 44634 | 31 | -5 | 26 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 2022-02-02 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03068 | 2022-02-14 | 1400/11/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443275 | 2022-03-19 | 1400/12/19 | 2022-03-14 | 1400/12/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03068 | 2022-02-14 | 1400/11/25 | CM-C2 | [6 empty] | 1400-2294-443275 | 2022-03-19 | 1400/12/19 | 2022-03-14 | 1400/12/23 | CM
2 | 4 | 2 | 5 | 0 | 0 | 0 | 2.4.2.5 | Safety & Fire Fighting
2 | 4 | 2 | 5 | 1 | 0 | 0 | 2.4.2.5.1 | Fire Fighting and Safety Equipment
2 | 4 | 2 | 5 | 1 | 1 | 0 | 2.4.5.1.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 5 | 1 | 1 | 1 | 2.4.2.5.1.1.1 | PMR For Fire Fighting and Safety Equipment - W046S | BK-W046S-PEDCO-110-SA-MR-0001 | BK-W046S-PEDCO-110-SA-MR-0001 | BK | W046S | PEDCO | 110 | SA | MR | 0001 | F0Z-707700 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 5 | 1 | 2 | 0 | 2.4.5.1.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 5 | 1 | 2 | 1 | 2.4.2.5.1.2.1 | TBE For Fire Fighting and Safety Equipment - W046S | BK-W046S-PEDCO-110-SA-TB-0001 | BK-W046S-PEDCO-110-SA-TB-0001 | BK | W046S | PEDCO | 110 | SA | TB | 0001 | F0Z-707701 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 5 | 2 | 0 | 0 | 2.4.2.5.2 | Safety Sign
2 | 4 | 2 | 5 | 2 | 1 | 0 | 2.4.5.2.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 5 | 2 | 1 | 1 | 2.4.2.5.2.1.1 | PMR For Fire Safety Sign - W046S | BK-W046S-PEDCO-110-SA-MR-0002 | BK-W046S-PEDCO-110-SA-MR-0002 | BK | W046S | PEDCO | 110 | SA | MR | 0002 | F0Z-707702 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 5 | 2 | 2 | 0 | 2.4.5.2.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 5 | 2 | 2 | 1 | 2.4.2.5.2.2.1 | TBE For Fire Safety Sign - W046S | BK-W046S-PEDCO-110-SA-TB-0002 | BK-W046S-PEDCO-110-SA-TB-0002 | BK | W046S | PEDCO | 110 | SA | TB | 0002 | F0Z-707703 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 0 | 0 | 0 | 2.4.2.6 | Electrical
2 | 4 | 2 | 6 | 1 | 0 | 0 | 2.4.2.6.1 | Transformers
2 | 4 | 2 | 6 | 1 | 1 | 0 | 2.4.6.1.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 1 | 1 | 1 | 2.4.2.6.1.1.1 | PMR For Transformers - W046S | BK-W046S-PEDCO-110-EL-MR-0001 | BK-W046S-PEDCO-110-EL-MR-0001 | BK | W046S | PEDCO | 110 | EL | MR | 0001 | F0Z-707704 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 1 | 2 | 0 | 2.4.6.1.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 1 | 2 | 1 | 2.4.2.6.1.2.1 | TBE For Transformers - W046S | BK-W046S-PEDCO-110-EL-TB-0001 | BK-W046S-PEDCO-110-EL-TB-0001 | BK | W046S | PEDCO | 110 | EL | TB | 0001 | F0Z-707705 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 2 | 0 | 0 | 2.4.2.6.2 | LV Switchgear & MCC
2 | 4 | 2 | 6 | 2 | 1 | 0 | 2.4.6.2.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 2 | 1 | 1 | 2.4.2.6.2.1.1 | PMR For LV Switchgear & MCC - W046S | BK-W046S-PEDCO-110-EL-MR-0002 | BK-W046S-PEDCO-110-EL-MR-0002 | BK | W046S | PEDCO | 110 | EL | MR | 0002 | F0Z-707706 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 2 | 2 | 0 | 2.4.6.2.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 2 | 2 | 1 | 2.4.2.6.2.2.1 | TBE For LV Switchgear & MCC - W046S | BK-W046S-PEDCO-110-EL-TB-0002 | BK-W046S-PEDCO-110-EL-TB-0002 | BK | W046S | PEDCO | 110 | EL | TB | 0002 | F0Z-707707 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 3 | 0 | 0 | 2.4.2.6.3 | Emergency Diesel Generator
2 | 4 | 2 | 6 | 3 | 1 | 0 | 2.4.6.3.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 3 | 1 | 1 | 2.4.2.6.3.1.1 | PMR For Emergency Diesel Generator - W046S | BK-W046S-PEDCO-110-EL-MR-0003 | BK-W046S-PEDCO-110-EL-MR-0003 | BK | W046S | PEDCO | 110 | EL | MR | 0003 | F0Z-707708 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 3 | 2 | 0 | 2.4.6.3.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 3 | 2 | 1 | 2.4.2.6.3.2.1 | TBE For Emergency Diesel Generator - W046S | BK-W046S-PEDCO-110-EL-TB-0003 | BK-W046S-PEDCO-110-EL-TB-0003 | BK | W046S | PEDCO | 110 | EL | TB | 0003 | F0Z-707709 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 4 | 0 | 0 | 2.4.2.6.4 | UPS System
2 | 4 | 2 | 6 | 4 | 1 | 0 | 2.4.6.4.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 4 | 1 | 1 | 2.4.2.6.4.1.1 | PMR For UPS System - W046S | BK-W046S-PEDCO-110-EL-MR-0004 | BK-W046S-PEDCO-110-EL-MR-0004 | BK | W046S | PEDCO | 110 | EL | MR | 0004 | F0Z-707710 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 4 | 2 | 0 | 2.4.6.4.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 4 | 2 | 1 | 2.4.2.6.4.2.1 | TBE For UPS System - W046S | BK-W046S-PEDCO-110-EL-TB-0004 | BK-W046S-PEDCO-110-EL-TB-0004 | BK | W046S | PEDCO | 110 | EL | TB | 0004 | F0Z-707711 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 5 | 0 | 0 | 2.4.2.6.5 | DC Charger
2 | 4 | 2 | 6 | 5 | 1 | 0 | 2.4.6.5.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 5 | 1 | 1 | 2.4.2.6.5.1.1 | PMR For DC Charger - W046S | BK-W046S-PEDCO-110-EL-MR-0005 | BK-W046S-PEDCO-110-EL-MR-0005 | BK | W046S | PEDCO | 110 | EL | MR | 0005 | F0Z-707712 | IFI | IFI | 44691 | 44710 | 44711 | 19 | 1 | 20 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-26 | 2022-04-26 |  | D00 | IFI | T-0864 | 2022-04-26 | 1401/02/06 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04211 | 2022-05-10 | 1401/02/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-78867 | 2022-05-29 | 1401/03/08 | 2022-05-30 | 1401/03/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0864 | 2022-04-26 | 1401/02/06 |  |  |  | BK-SUR-ENG-ELE-01-04211 | 2022-05-10 | 1401/02/20 | CM-C3 | [6 empty] | 1401-2294-78867 | 2022-05-29 | 1401/03/08 | 2022-05-30 | 1401/03/09 | CM
2 | 4 | 2 | 6 | 5 | 2 | 0 | 2.4.6.5.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 5 | 2 | 1 | 2.4.2.6.5.2.1 | TBE For DC Charger - W046S | BK-W046S-PEDCO-110-EL-TB-0005 | BK-W046S-PEDCO-110-EL-TB-0005 | BK | W046S | PEDCO | 110 | EL | TB | 0005 | F0Z-707713 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 6 | 0 | 0 | 2.4.2.6.6 | Capacitor Bank
2 | 4 | 2 | 6 | 6 | 1 | 0 | 2.4.6.6.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 6 | 1 | 1 | 2.4.2.6.6.1.1 | PMR For Capacitor Bank - W046S | BK-W046S-PEDCO-110-EL-MR-0006 | BK-W046S-PEDCO-110-EL-MR-0006 | BK | W046S | PEDCO | 110 | EL | MR | 0006 | F0Z-707714 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 6 | 2 | 0 | 2.4.6.6.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 6 | 2 | 1 | 2.4.2.6.6.2.1 | TBE For Capacitor Bank - W046S | BK-W046S-PEDCO-110-EL-TB-0006 | BK-W046S-PEDCO-110-EL-TB-0006 | BK | W046S | PEDCO | 110 | EL | TB | 0006 | F0Z-707715 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 7 | 0 | 0 | 2.4.2.6.7 | Lighting & Distribution Main Panels
2 | 4 | 2 | 6 | 7 | 1 | 0 | 2.4.6.7.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 7 | 1 | 1 | 2.4.2.6.7.1.1 | PMR For Lighting & Distribution Main Panels - W046S | BK-W046S-PEDCO-110-EL-MR-0007 | BK-W046S-PEDCO-110-EL-MR-0007 | BK | W046S | PEDCO | 110 | EL | MR | 0007 | F0Z-707716 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 7 | 2 | 0 | 2.4.6.7.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 7 | 2 | 1 | 2.4.2.6.7.2.1 | TBE For Lighting & Distribution Main Panels - W046S | BK-W046S-PEDCO-110-EL-TB-0007 | BK-W046S-PEDCO-110-EL-TB-0007 | BK | W046S | PEDCO | 110 | EL | TB | 0007 | F0Z-707717 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 8 | 0 | 0 | 2.4.2.6.8 | Earthing & Lightning System
2 | 4 | 2 | 6 | 8 | 1 | 0 | 2.4.6.8.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 8 | 1 | 1 | 2.4.2.6.8.1.1 | PMR For Earthing & Lightning System - W046S | BK-W046S-PEDCO-110-EL-MR-0008 | BK-W046S-PEDCO-110-EL-MR-0008 | BK | W046S | PEDCO | 110 | EL | MR | 0008 | F0Z-707718 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 8 | 2 | 0 | 2.4.6.8.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 8 | 2 | 1 | 2.4.2.6.8.2.1 | TBE For Earthing & Lightning System - W046S | BK-W046S-PEDCO-110-EL-TB-0008 | BK-W046S-PEDCO-110-EL-TB-0008 | BK | W046S | PEDCO | 110 | EL | TB | 0008 | F0Z-707719 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 9 | 0 | 0 | 2.4.2.6.9 | Lighting and Small Power Equipment
2 | 4 | 2 | 6 | 9 | 1 | 0 | 2.4.6.9.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 9 | 1 | 1 | 2.4.2.6.9.1.1 | PMR For Lighting and Small Power Equipment - W046S | BK-W046S-PEDCO-110-EL-MR-0009 | BK-W046S-PEDCO-110-EL-MR-0009 | BK | W046S | PEDCO | 110 | EL | MR | 0009 | F0Z-707720 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 9 | 2 | 0 | 2.4.6.9.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 9 | 2 | 1 | 2.4.2.6.9.2.1 | TBE For Lighting and Small Power Equipment - W046S | BK-W046S-PEDCO-110-EL-TB-0009 | BK-W046S-PEDCO-110-EL-TB-0009 | BK | W046S | PEDCO | 110 | EL | TB | 0009 | F0Z-707721 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 10 | 0 | 0 | 2.4.2.6.10 | Tray/Ladder and Accessories
2 | 4 | 2 | 6 | 10 | 1 | 0 | 2.4.6.10.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 10 | 1 | 1 | 2.4.2.6.10.1.1 | PMR For Tray/Ladder and Accessories - W046S | BK-W046S-PEDCO-110-EL-MR-0010 | BK-W046S-PEDCO-110-EL-MR-0010 | BK | W046S | PEDCO | 110 | EL | MR | 0010 | F0Z-707722 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 10 | 2 | 0 | 2.4.6.10.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 10 | 2 | 1 | 2.4.2.6.10.2.1 | TBE For Tray/Ladder and Accessories - W046S | BK-W046S-PEDCO-110-EL-TB-0010 | BK-W046S-PEDCO-110-EL-TB-0010 | BK | W046S | PEDCO | 110 | EL | TB | 0010 | F0Z-707723 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 11 | 0 | 0 | 2.4.2.6.11 | Power & Control Cables
2 | 4 | 2 | 6 | 11 | 1 | 0 | 2.4.6.11.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 11 | 1 | 1 | 2.4.2.6.11.1.1 | PMR For Power & Control Cables - W046S | BK-W046S-PEDCO-110-EL-MR-0011 | BK-W046S-PEDCO-110-EL-MR-0011 | BK | W046S | PEDCO | 110 | EL | MR | 0011 | F0Z-707724 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 11 | 2 | 0 | 2.4.6.11.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 11 | 2 | 1 | 2.4.2.6.11.2.1 | TBE For Power & Control Cables - W046S | BK-W046S-PEDCO-110-EL-TB-0011 | BK-W046S-PEDCO-110-EL-TB-0011 | BK | W046S | PEDCO | 110 | EL | TB | 0011 | F0Z-707725 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 12 | 0 | 0 | 2.4.2.6.12 | Electrical Bulk Items
2 | 4 | 2 | 6 | 12 | 1 | 0 | 2.4.6.12.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 12 | 1 | 1 | 2.4.2.6.12.1.1 | PMR For Electrical Bulk Items - W046S | BK-W046S-PEDCO-110-EL-MR-0012 | BK-W046S-PEDCO-110-EL-MR-0012 | BK | W046S | PEDCO | 110 | EL | MR | 0012 | F0Z-707726 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 12 | 2 | 0 | 2.4.6.12.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 12 | 2 | 1 | 2.4.2.6.12.2.1 | TBE For Electrical Bulk Items - W046S | BK-W046S-PEDCO-110-EL-TB-0012 | BK-W046S-PEDCO-110-EL-TB-0012 | BK | W046S | PEDCO | 110 | EL | TB | 0012 | F0Z-707727 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 13 | 0 | 0 | 2.4.2.6.13 | Transmission Over head Line
2 | 4 | 2 | 6 | 13 | 1 | 0 | 2.4.6.13.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 6 | 13 | 1 | 1 | 2.4.2.6.13.1.1 | PMR For Transmission Over head Line - W046S | BK-W046S-PEDCO-110-EL-MR-0013 | BK-W046S-PEDCO-110-EL-MR-0013 | BK | W046S | PEDCO | 110 | EL | MR | 0013 | F0Z-707728 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 6 | 13 | 2 | 0 | 2.4.6.13.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 6 | 13 | 2 | 1 | 2.4.2.6.13.2.1 | TBE For Transmission Over head Line - W046S | BK-W046S-PEDCO-110-EL-TB-0013 | BK-W046S-PEDCO-110-EL-TB-0013 | BK | W046S | PEDCO | 110 | EL | TB | 0013 | F0Z-707729 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 7 | 0 | 0 | 0 | 2.4.2.7 | Structure
2 | 4 | 2 | 7 | 1 | 0 | 0 | 2.4.2.7.1 | Steel Structure Items
2 | 4 | 2 | 7 | 1 | 1 | 0 | 2.4.7.1.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 7 | 1 | 1 | 1 | 2.4.2.7.1.1.1 | PMR For Steel Structure Items - W046S | BK-W046S-PEDCO-110-ST-MR-0001 | BK-W046S-PEDCO-110-ST-MR-0001 | BK | W046S | PEDCO | 110 | ST | MR | 0001 | F0Z-707730 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 7 | 1 | 2 | 0 | 2.4.7.1.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 7 | 1 | 2 | 1 | 2.4.2.7.1.2.1 | TBE For Steel Structure Items - W046S | BK-W046S-PEDCO-110-ST-TB-0001 | BK-W046S-PEDCO-110-ST-TB-0001 | BK | W046S | PEDCO | 110 | ST | TB | 0001 | F0Z-707731 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 7 | 2 | 0 | 0 | 2.4.2.7.2 | Anchor Bolts
2 | 4 | 2 | 7 | 2 | 1 | 0 | 2.4.7.2.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 7 | 2 | 1 | 1 | 2.4.2.7.2.1.1 | PMR For Anchor Bolts - W046S | BK-W046S-PEDCO-110-ST-MR-0002 | BK-W046S-PEDCO-110-ST-MR-0002 | BK | W046S | PEDCO | 110 | ST | MR | 0002 | F0Z-707732 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 7 | 2 | 2 | 0 | 2.4.7.2.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 7 | 2 | 2 | 1 | 2.4.2.7.2.2.1 | TBE For Anchor Bolts - W046S | BK-W046S-PEDCO-110-ST-TB-0002 | BK-W046S-PEDCO-110-ST-TB-0002 | BK | W046S | PEDCO | 110 | ST | TB | 0002 | F0Z-707733 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 7 | 3 | 0 | 0 | 2.4.2.7.3 | Blast Proof Doors
2 | 4 | 2 | 7 | 3 | 1 | 0 | 2.4.7.3.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 7 | 3 | 1 | 1 | 2.4.2.7.3.1.1 | PMR For Blast Proof Doors - W046S | BK-W046S-PEDCO-110-ST-MR-0003 | BK-W046S-PEDCO-110-ST-MR-0003 | BK | W046S | PEDCO | 110 | ST | MR | 0003 | F0Z-707734 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 7 | 3 | 2 | 0 | 2.4.7.3.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 7 | 3 | 2 | 1 | 2.4.2.7.3.2.1 | TBE For Blast Proof Doors - W046S | BK-W046S-PEDCO-110-ST-TB-0003 | BK-W046S-PEDCO-110-ST-TB-0003 | BK | W046S | PEDCO | 110 | ST | TB | 0003 | F0Z-707735 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 8 | 0 | 0 | 0 | 2.4.2.8 | Civil
2 | 4 | 2 | 8 | 1 | 0 | 0 | 2.4.2.8.1 | Geomembrane
2 | 4 | 2 | 8 | 1 | 1 | 0 | 2.4.8.1.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 8 | 1 | 1 | 1 | 2.4.2.8.1.1.1 | PMR For Geomembrane - W046S | BK-W046S-PEDCO-110-CV-MR-0001 | BK-W046S-PEDCO-110-CV-MR-0001 | BK | W046S | PEDCO | 110 | CV | MR | 0001 | F0Z-707736 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 8 | 1 | 2 | 0 | 2.4.8.1.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 8 | 1 | 2 | 1 | 2.4.2.8.1.2.1 | TBE For Geomembrane - W046S | BK-W046S-PEDCO-110-CV-TB-0001 | BK-W046S-PEDCO-110-CV-TB-0001 | BK | W046S | PEDCO | 110 | CV | TB | 0001 | F0Z-707737 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 8 | 2 | 0 | 0 | 2.4.2.8.2 | Geotextile
2 | 4 | 2 | 8 | 2 | 1 | 0 | 2.4.8.2.1 | Purchase Material Requisition (PMR)
2 | 4 | 2 | 8 | 2 | 1 | 1 | 2.4.2.8.2.1.1 | PMR For Geotextile - W046S | BK-W046S-PEDCO-110-CV-MR-0002 | BK-W046S-PEDCO-110-CV-MR-0002 | BK | W046S | PEDCO | 110 | CV | MR | 0002 | F0Z-707738 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 2 | 8 | 2 | 2 | 0 | 2.4.8.2.2 | Technical Bid Evaluation (TBE)
2 | 4 | 2 | 8 | 2 | 2 | 1 | 2.4.2.8.2.2.1 | TBE For Geotextile - W046S | BK-W046S-PEDCO-110-CV-TB-0002 | BK-W046S-PEDCO-110-CV-TB-0002 | BK | W046S | PEDCO | 110 | CV | TB | 0002 | F0Z-707739 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 3 | 0 | 0 | 0 | 0 | 2.4.3 | Commissioning Engineering
2 | 4 | 3 | 0 | 0 | 1 | 0 | 2.4.3.1 | Procedure/Plan
2 | 4 | 3 | 0 | 0 | 1 | 1 | 2.4.3.1.1 | Pre-Commissioning, Commissioning & Startup Procedure - W046S | BK-W046S-PEDCO-110-CO-PR-0001 | BK-W046S-PEDCO-110-CO-PR-0001 | BK | W046S | PEDCO | 110 | CO | PR | 0001 | F0Z-707740 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 4 | 0 | 0 | 0 | 0 | 2.4.4 | Field Engineering
2 | 4 | 4 | 0 | 0 | 1 | 0 | 2.4.4.1 | Query
2 | 4 | 4 | 0 | 0 | 1 | 1 | 2.4.4.1.1 | Technical/Site Queries | BK-W046S-PEDCO-110-GE-TQ-0001 | BK-W046S-PEDCO-110-GE-TQ-0001 | BK | W046S | PEDCO | 110 | GE | TQ | 0001 | F7Z-707741 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 4 | 0 | 0 | 2 | 0 | 2.4.4.2 | Dossier
2 | 4 | 4 | 0 | 0 | 2 | 1 | 2.4.4.2.1 | As-Built Document Booklets - W046S | BK-W046S-PEDCO-110-GE-DO-0001 | BK-W046S-PEDCO-110-GE-DO-0001 | BK | W046S | PEDCO | 110 | GE | DO | 0001 | F0Z-707742 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 5 | 0 | 0 | 0 | 0 | 2.4.5 | Engineering Final Documentation
2 | 4 | 5 | 0 | 0 | 1 | 0 | 2.4.5.1 | Manual
2 | 4 | 5 | 0 | 0 | 1 | 1 | 2.4.5.1.1 | Operating Manual - W046S | BK-W046S-PEDCO-110-GE-ML-0001 | BK-W046S-PEDCO-110-GE-ML-0001 | BK | W046S | PEDCO | 110 | GE | ML | 0001 | F7Z-707743 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 4 | 5 | 0 | 0 | 2 | 0 | 2.4.5.2 | Dossier
2 | 4 | 5 | 0 | 0 | 2 | 1 | 2.4.5.2.1 | As-Built Document Booklets - W046S | BK-W046S-PEDCO-110-GE-DO-0001 | BK-W046S-PEDCO-110-GE-DO-0001 | [7 empty] | F0Z-707742 | [43 empty] | Moved to Field | 0
2 | 4 | 5 | 0 | 0 | 2 | 2 | 2.4.5.2.2 | Final Engineering Dossier - W046S | BK-W046S-PEDCO-110-GE-DO-0002 | BK-W046S-PEDCO-110-GE-DO-0002 | BK | W046S | PEDCO | 110 | GE | DO | 0002 | F0Z-707744 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 0 | 0 | 0 | 0 | 0 | 2.5 | Package 04-New Well # W035 (Bangestan)
2 | 5 | 1 | 0 | 0 | 0 | 0 | 2.5.1 | Detail Design
2 | 5 | 1 | 1 | 0 | 0 | 0 | 2.5.1.1 | Process
2 | 5 | 1 | 1 | 1 | 0 | 0 | 2.5.1.1.1 | Drawing/Diagram
2 | 5 | 1 | 1 | 1 | 0 | 1 | 2.5.1.1.1 | Process Flow Diagram - W035 | BK-W035-PEDCO-110-PR-PF-0001 | BK-W035-PEDCO-110-PR-PF-0001 | BK | W035 | PEDCO | 110 | PR | PF | 0001 | F2A-707745 | AFC | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-11-16 | 0 | 0 | -44516 | 0 | -44516 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-02 | 0 |  | D01 | IFC | T-0205 | 2021-11-02 | 1400/08/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W035-PEDCO-110-PR-PF-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W035-PEDCO-110-PR-PF-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 2021-09-08 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0205 | 2021-11-02 | 1400/08/11 | [7 empty] | PEDCO-CRS-BK-W035-PEDCO-110-PR-PF-0001_D00 | [11 empty] | NISOC-CRS-BK-W035-PEDCO-110-PR-PF-0001_D00
2 | 5 | 1 | 1 | 1 | 0 | 2 | 2.5.1.1.1 | P&ID - W035 | BK-W035-PEDCO-110-PR-PI-0001 | BK-W035-PEDCO-110-PR-PI-0001 | BK | W035 | PEDCO | 110 | PR | PI | 0001 | F2A-707746 | AFC | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-01 | 0 |  | D03 | IFA | T-0653 | 2022-02-28 | 1400/12/09 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 2021-09-08 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0201 | 2021-11-01 | 1400/08/10 |  |  |  | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-279084 | 2021-11-16 | 1400/08/25 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0345 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-PCS-00-02540 | 2022-01-03 | 1400/10/13 | CM-C3 | PEDCO-BK-W035-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-342085 | 2021-12-30 | 1400/10/09 | 2022-01-03 | 1400/10/13 | RJ | NISOC-BK-W035-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0653 | 2022-02-28 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-PI-0001_D02
2 | 5 | 1 | 1 | 2 | 0 | 0 | 2.5.1.1.2 | List
2 | 5 | 1 | 1 | 2 | 0 | 1 | 2.5.1.1.2 | Line List - W035 | BK-W035-PEDCO-110-PR-LI-0001 | BK-W035-PEDCO-110-PR-LI-0001 | BK | W035 | PEDCO | 110 | PR | LI | 0001 | F0Z-707747 | AFC | IFC | 44444 | 44439 | 44447 | -5 | 8 | 3 | IFC | 44522 | 44527 | 44529 | 5 | 2 | 7 | IFA | 44573 | 0 | 0 | -44573 | 0 | -44573 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-08 | 0 |  | D02 | IFA | T-0403 | 2021-12-29 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PR-LI-0001 _D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W035-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 2021-09-08 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0217 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PCS-00-02051 | 2021-11-20 | 1400/08/29 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1400-2290-293083 | 2021-11-27 | 1400/09/06 | 2021-11-29 | 1400/09/08 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-LI-0001_D00 | [9 empty] | D02 | IFA | T-0403 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PR-LI-0001 _D01 | [11 empty] | NISOC-CRS-BK-W035-PEDCO-110-PR-LI-0001_D01
2 | 5 | 1 | 1 | 3 | 0 | 0 | 2.5.1.1.3 | Report | [145 empty] | 1400/09/06
2 | 5 | 1 | 1 | 3 | 0 | 1 | 2.5.1.1.3 | Flow line Hydraulic Calculation Report | BK-W035-PEDCO-110-PR-RT-0001 | BK-W035-PEDCO-110-PR-RT-0001 | BK | W035 | PEDCO | 110 | PR | RT | 0001 | F0Z-707748 | AFC | IFC | 44513 | 44514 | 44517 | 1 | 3 | 4 | IFA | 44576 | 44228 | 44597 | -348 | 369 | 21 | IFA | 44628 | 44630 | 44633 | 2 | 3 | 5 | IFA | 44695 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-30 | 0 |  | D03 | IFA | T-0878 | 2022-04-30 | 1401/02/10 | T-0878 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 2022-05-28 | 1402/03/07 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-PR-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W035-PEDCO-110-PR-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0197 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-PCS-00-01993 | 2021-11-14 | 1400/08/23 | CM-C3 | [6 empty] | 1400-2294-275250 | 2021-11-14 | 1400/08/23 | 2021-11-17 | 1400/08/26 | CM | [10 empty] | D01 | IFA | T-0413 | 2022-01-01 | 1400/10/11 |  |  |  | BK-SUR-ENG-PCS-00-02735 | 2022-01-19 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PR-RT-0001_D00 | [5 empty] | 1400-2294-392131 | 2021-02-01 | 1400/11/12 | 2022-02-05 | 1400/11/16 | CM | NISOC-CRS-BK-W035-PEDCO-110-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-0627 | 2022-02-22 | 1400/12/03 |  |  |  | BK-SUR-ENG-PCS-00-03387 | 2022-03-07 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-PR-RT-0001_D01 | [5 empty] | 1400-2294-443285 | 2022-03-10 | 1400/12/19 | 2022-03-13 | 1400/12/22 | CM | NISON-CRS-BK-W035-PEDCO-110-PR-RT-0001_D01 | [9 empty] | D03 | IFA | T-0878 | 2022-04-30 | 1401/02/10 | T-0878 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 2022-05-28 | 1402/03/07 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-PR-RT-0001_D02 | [11 empty] | NISOC-CRS-BK-W035-PEDCO-110-PR-RT-0001_D02
2 | 5 | 1 | 1 | 4 | 0 | 0 | 2.5.1.1.4 | Data Sheet
2 | 5 | 1 | 1 | 4 | 0 | 1 | 2.5.1.1 | Process Data Sheets For Instrument Devices - W035 | BK-W035-PEDCO-110-PR-DT-0001 | BK-W035-PEDCO-110-PR-DT-0001 | BK | W035 | PEDCO | 110 | PR | DT | 0001 | F0Z-707749 | AFC | IFC | 44677 | 44689 | 44695 | 12 | 6 | 18 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-12 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04093 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 2022-05-14 | 1401/02/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-PCS-01-04093 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 2022-05-14 | 1401/02/24 | CM
2 | 5 | 1 | 2 | 0 | 0 | 0 | 2.5.1.2 | Piping
2 | 5 | 1 | 2 | 1 | 0 | 0 | 2.5.1.2.1 | Drawing/Diagram
2 | 5 | 1 | 2 | 1 | 0 | 1 | 2.5.1.2.1 | Plot Plan Drawing - W035 | BK-W035-PEDCO-110-PI-DW-0001 | BK-W035-PEDCO-110-PI-DW-0001 | BK | W035 | PEDCO | 110 | PI | DW | 0001 | F5A-707750 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 2 | 1 | 0 | 2 | 2.5.1.2.1 | Piping Plan - W035 | BK-W035-PEDCO-110-PI-DW-0002 | BK-W035-PEDCO-110-PI-DW-0002 | BK | W035 | PEDCO | 110 | PI | DW | 0002 | F4L-707751 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 2 | 1 | 0 | 3 | 2.5.1.2.1 | Isometric Drawings - W035 | BK-W035-PEDCO-110-PI-DW-0003 | BK-W035-PEDCO-110-PI-DW-0003 | BK | W035 | PEDCO | 110 | PI | DW | 0003 | F2L-707752 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 2 | 1 | 0 | 4 | 2.5.1.2.1 | Material Flow Diagram - W035 | BK-W035-PEDCO-110-PI-DG-0001 | BK-W035-PEDCO-110-PI-DG-0001 | BK | W035 | PEDCO | 110 | PI | DG | 0001 | F2A-707753 | AFC | IFC | 2021-11-22 | 2021-11-24 | 2021-11-27 | 2 | 3 | 5 | IFA | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-08 | 0 |  | D01 | IFA | T-0932 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04376 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PI-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W035-PEDCO-110-PI-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0219 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PIP-00-02060 | 2021-11-21 | 1400/08/30 | CM-C3 | [6 empty] | 1400-2294-289400 | 2021-11-24 | 1400/09/03 | 2021-11-27 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0932 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04376 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PI-DG-0001_D00 | [11 empty] | NISOC-CRS-BK-W035-PEDCO-110-PI-DG-0001_D00
2 | 5 | 1 | 2 | 2 | 0 | 0 | 2.5.1.2.2 | List
2 | 5 | 1 | 2 | 2 | 0 | 1 | 2.5.1.2.2 | Piping Support List - W035 | BK-W035-PEDCO-110-PI-LI-0001 | BK-W035-PEDCO-110-PI-LI-0001 | BK | W035 | PEDCO | 110 | PI | LI | 0001 | F0Z-707754 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 2 | 2 | 0 | 2 | 2.5.1.2.2 | Critical Line List - W035 | BK-W035-PEDCO-110-PI-LI-0002 | BK-W035-PEDCO-110-PI-LI-0002 | BK | W035 | PEDCO | 110 | PI | LI | 0002 | F0Z-707755 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 2 | 3 | 0 | 0 | 2.5.1.2.3 | Report
2 | 5 | 1 | 2 | 3 | 0 | 1 | 2.5.1.2.3 | PDMS Model Review Report (60%) - W035 | BK-W035-PEDCO-110-PI-RT-0001 | BK-W035-PEDCO-110-PI-RT-0001 | BK | W035 | PEDCO | 110 | PI | RT | 0001 | F0Z-707756 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 2 | 3 | 0 | 2 | 2.5.1.2.3 | PDMS Model Review Report (90%) - W035 | BK-W035-PEDCO-110-PI-RT-0002 | BK-W035-PEDCO-110-PI-RT-0002 | BK | W035 | PEDCO | 110 | PI | RT | 0002 | F0Z-707757 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 2 | 4 | 0 | 0 | 2.5.1.2.4 | MTO
2 | 5 | 1 | 2 | 4 | 0 | 1 | 2.5.1.2 | MTO For Pipes - W035 | BK-W035-PEDCO-110-PI-MT-0001 | BK-W035-PEDCO-110-PI-MT-0001 | BK | W035 | PEDCO | 110 | PI | MT | 0001 | F8Z-707758 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 2 | 4 | 0 | 2 | 2.5.1.2 | MTO For Fittings - W035 | BK-W035-PEDCO-110-PI-MT-0002 | BK-W035-PEDCO-110-PI-MT-0002 | BK | W035 | PEDCO | 110 | PI | MT | 0002 | F8Z-707759 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 2 | 4 | 0 | 3 | 2.5.1.2 | MTO For Flanges - W035 | BK-W035-PEDCO-110-PI-MT-0003 | BK-W035-PEDCO-110-PI-MT-0003 | BK | W035 | PEDCO | 110 | PI | MT | 0003 | F8Z-707760 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 2 | 4 | 0 | 4 | 2.5.1.2 | MTO For Manual Valves - W035 | BK-W035-PEDCO-110-PI-MT-0004 | BK-W035-PEDCO-110-PI-MT-0004 | BK | W035 | PEDCO | 110 | PI | MT | 0004 | F8Z-707761 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 2 | 4 | 0 | 5 | 2.5.1.2 | MTO For Gaskets - W035 | BK-W035-PEDCO-110-PI-MT-0005 | BK-W035-PEDCO-110-PI-MT-0005 | BK | W035 | PEDCO | 110 | PI | MT | 0005 | F8Z-707762 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 2 | 4 | 0 | 6 | 2.5.1.2 | MTO For Bolt & Nuts - W035 | BK-W035-PEDCO-110-PI-MT-0006 | BK-W035-PEDCO-110-PI-MT-0006 | BK | W035 | PEDCO | 110 | PI | MT | 0006 | F8Z-707763 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 3 | 0 | 0 | 0 | 2.5.1.3 | Pipeline & Flow line
2 | 5 | 1 | 3 | 1 | 0 | 0 | 2.5.1.3.1 | Drawings
2 | 5 | 1 | 3 | 1 | 0 | 1 | 2.5.1.3.1 | Flow line Transversal Drawings - W035 | BK-W035-PEDCO-110-PL-DW-0002 | BK-W035-PEDCO-110-PL-DW-0002 | BK | W035 | PEDCO | 110 | PL | DW | 0002 | F4A-707764 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 3 | 2 | 0 | 0 | 2.5.1.3.2 | List
2 | 5 | 1 | 3 | 2 | 0 | 1 | 2.5.1.3.2 | Road Crossing Location List | BK-W035-PEDCO-110-PL-LI-0001 | BK-W035-PEDCO-110-PL-LI-0001 | BK | W035 | PEDCO | 110 | PL | LI | 0001 | F0Z-707765 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 3 | 3 | 0 | 0 | 2.5.1.3.3 | MTO
2 | 5 | 1 | 3 | 3 | 0 | 1 | 2.5.1.3 | MTO For Line Pipes (Flow lines) - W035 | BK-W035-PEDCO-110-PL-MT-0001 | BK-W035-PEDCO-110-PL-MT-0001 | BK | W035 | PEDCO | 110 | PL | MT | 0001 | F8Z-707766 | IFI | IFI | 44444 | 44438 | 44444 | -6 | 6 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2021-08-22 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | 1400/05/31 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | 1400/05/31 | CM-C2 | [6 empty] | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM
2 | 5 | 1 | 4 | 0 | 0 | 0 | 2.5.1.4 | Control & Instrumentation
2 | 5 | 1 | 4 | 1 | 0 | 0 | 2.5.1.4.1 | Drawing/Diagram
2 | 5 | 1 | 4 | 1 | 0 | 1 | 2.5.1.4.1 | Instrument Location Layout Drawing - W035 | BK-W035-PEDCO-110-IN-PY-0001 | BK-W035-PEDCO-110-IN-PY-0001 | BK | W035 | PEDCO | 110 | IN | PY | 0001 | F2J-707767 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 5 | 1 | 4 | 2 | 0 | 0 | 2.5.1.4.2 | MTO
2 | 5 | 1 | 4 | 2 | 0 | 1 | 2.5.1.4 | MTO For Instrument Tube and Fitting - W035 | BK-W035-PEDCO-110-IN-MT-0001 | BK-W035-PEDCO-110-IN-MT-0001 | BK | W035 | PEDCO | 110 | IN | MT | 0001 | F8Z-707768 | IFI | IFI | 2021-11-28 | 2021-10-21 | 2021-11-29 | -38 | 39 | 1 | IFI | 2022-01-02 | 2021-01-03 | 2022-01-04 | -364 | 366 | 2 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-14 | 2022-01-12 |  | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W035-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0239 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02143 | 2021-11-28 | 1400/09/08 | C4-RJ | [6 empty] | 1400-2294-283478 | 2021-10-21 | 1400/08/30 | 2021-11-29 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0363 | 2021-12-19 | 1400/09/28 |  |  |  | BK-SUR-ENG-INS-00-02500 | 2022-01-01 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MT-0001_D00 | [5 empty] | 1400-2294-347440 | 2021-01-03 | 1400/10/13 | 2022-01-04 | 1400/10/14 | CM | NISOC-CRS-BK-W035-PEDCO-110-IN-MT-0001_D00 | [9 empty] | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MT-0001_D01 | [5 empty] | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W035-PEDCO-110-IN-MT-0001_D01
2 | 5 | 1 | 4 | 2 | 0 | 2 | 2.5.1.4 | MTO For Instrument Cable Tray - W035 | BK-W035-PEDCO-110-IN-MT-0002 | BK-W035-PEDCO-110-IN-MT-0002 | BK | W035 | PEDCO | 110 | IN | MT | 0002 | F8Z-707769 | IFI | IFI | 2021-11-28 | 2021-10-21 | 2021-11-29 | -38 | 39 | 1 | IFI | 2022-01-02 | 2021-01-03 | 2022-01-04 | -364 | 366 | 2 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-14 | 2022-01-12 |  | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W035-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0239 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02143 | 2021-11-28 | 1400/09/08 | C4-RJ | [6 empty] | 1400-2294-283478 | 2021-10-21 | 1400/08/30 | 2021-11-29 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0363 | 2021-12-19 | 1400/09/28 |  |  |  | BK-SUR-ENG-INS-00-02500 | 2022-01-01 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MT-0002_D00 | [5 empty] | 1400-2294-347440 | 2021-01-03 | 1400/10/13 | 2022-01-04 | 1400/10/14 | CM | NISOC-CRS-BK-W035-PEDCO-110-IN-MT-0002_D00 | [9 empty] | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MT-0002_D01 | [5 empty] | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W035-PEDCO-110-IN-MT-0002_D01
2 | 5 | 1 | 5 | 0 | 0 | 0 | 2.5.1.5 | Safety
2 | 5 | 1 | 5 | 1 | 0 | 0 | 2.5.1.5.1 | Drawing/Diagram
2 | 5 | 1 | 5 | 1 | 0 | 1 | 2.5.1.5.1 | Hazardous Area Classification Layout - W035 | BK-W035-PEDCO-110-SA-PY-0001 | BK-W035-PEDCO-110-SA-PY-0001 | BK | W035 | PEDCO | 110 | SA | PY | 0001 | F2L-707770 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 1 | 5 | 1 | 0 | 2 | 2.5.1.5.1 | Safety & Fire Fighting Equipment Location Layout - W035 | BK-W035-PEDCO-110-SA-PY-0002 | BK-W035-PEDCO-110-SA-PY-0002 | BK | W035 | PEDCO | 110 | SA | PY | 0002 | F2L-707771 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 1 | 5 | 1 | 0 | 3 | 2.5.1.5.1 | Escape Route & Safety Sign Layout - W035 | BK-W035-PEDCO-110-SA-PY-0003 | BK-W035-PEDCO-110-SA-PY-0003 | BK | W035 | PEDCO | 110 | SA | PY | 0003 | F2L-707772 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 1 | 5 | 2 | 0 | 0 | 2.5.1.5.2 | List
2 | 5 | 1 | 5 | 2 | 0 | 1 | 2.5.1.5.2 | Hazard Source List - W035 | BK-W035-PEDCO-110-SA-LI-0001 | BK-W035-PEDCO-110-SA-LI-0001 | BK | W035 | PEDCO | 110 | SA | LI | 0001 | F0Z-707773 | AFC | IFC | 44523 | 44530 | 44536 | 7 | 6 | 13 | IFA | 44608 | 44628 | 44626 | 20 | -2 | 18 | IFA | 44677 | 0 | 0 | -44677 | 0 | -44677 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-09 | 0 |  | D02 | IFA | T-0806 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W035-PEDCO-110-SA-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0220 | 2021-11-09 | 1400/08/18 | [13 empty] | 1400-2290-298651 | 2021-11-30 | 1400/09/09 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0544 | 2022-02-02 | 1400/11/13 | [13 empty] | 1400-2294-435413 | 2022-03-08 | 1400/12/15 | 2022-03-06 | 1400/12/15 | CM | NISOC-CRS-BK-W035-PEDCO-110-SA-LI-0001_D00 | [9 empty] | D02 | IFA | T-0806 | 2022-04-12 | 1401/01/23 | [19 empty] | NISOC-CRS-BK-W035-PEDCO-110-SA-LI-0001_D01
2 | 5 | 1 | 5 | 3 | 0 | 0 | 2.5.1.5.3 | MTO
2 | 5 | 1 | 5 | 3 | 0 | 1 | 2.5.1.5 | MTO For Fire Fighting & Safety Equipment - W035 | BK-W035-PEDCO-110-SA-MT-0001 | BK-W035-PEDCO-110-SA-MT-0001 | BK | W035 | PEDCO | 110 | SA | MT | 0001 | F8Z-707774 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 1 | 5 | 3 | 0 | 2 | 2.5.1.5 | MTO For Safety Sign - W035 | BK-W035-PEDCO-110-SA-MT-0002 | BK-W035-PEDCO-110-SA-MT-0002 | BK | W035 | PEDCO | 110 | SA | MT | 0002 | F8Z-707775 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 1 | 6 | 0 | 0 | 0 | 2.5.1.6 | Architecture
2 | 5 | 1 | 6 | 1 | 0 | 0 | 2.5.1.6.1 | Drawing/Diagram
2 | 5 | 1 | 6 | 1 | 0 | 1 | 2.5.1.6 | Architectural Drawing For WHCP/HPU Shelter of Well Pads - W035 | BK-W035-PEDCO-110-AR-DW-0001 | BK-W035-PEDCO-110-AR-DW-0001 | BK | W035 | PEDCO | 110 | AR | DW | 0001 | F4B-707776 | AFC | IFC | 44632 | 44625 | 44628 | -7 | 3 | -4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-26 | 0 |  | D00 | IFC | T-0640 | 2022-02-26 | 1400/12/07 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-03400 | 2022-03-08 | 1400/12/18 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-435028 | 2022-03-05 | 1400/12/14 | 2022-03-08 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0640 | 2022-02-26 | 1400/12/07 |  |  |  | BK-SUR-ENG-ARC-00-03400 | 2022-03-08 | 1400/12/18 | CM-C2 | [6 empty] | 1400-2294-435028 | 2022-03-05 | 1400/12/14 | 2022-03-08 | 1400/12/17 | AP | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 1 | 7 | 0 | 0 | 0 | 2.5.1.7 | Civil
2 | 5 | 1 | 7 | 1 | 0 | 0 | 2.5.1.7.1 | Drawing/Diagram
2 | 5 | 1 | 7 | 1 | 0 | 1 | 2.5.1.7.1 | General Civil Layout -W035 | BK-W035-PEDCO-110-CV-PY-0001 | BK-W035-PEDCO-110-CV-PY-0001 | BK | W035 | PEDCO | 110 | CV | PY | 0001 | F4A-707777 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 1 | 7 | 1 | 0 | 2 | 2.5.1.7.1 | Civil and Structural drawings -W035 | BK-W035-PEDCO-110-CV-PY-0002 | BK-W035-PEDCO-110-CV-PY-0002 | BK | W035 | PEDCO | 110 | CV | PY | 0002 | F4S-707778 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 1 | 7 | 1 | 0 | 3 | 2.5.1.7.1 | Rough Grading Plans -W035 | BK-W035-PEDCO-110-CV-DW-0001 | BK-W035-PEDCO-110-CV-DW-0001 | BK | W035 | PEDCO | 110 | CV | DW | 0001 | F4S-707779 | AFC | IFC | 2021-12-29 | 2021-12-20 | 2021-12-22 | -9 | 2 | -7 | IFA | 2022-02-19 | 2022-02-19 | 2022-02-12 | 0 | -7 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-15 | 0 |  | D01 | IFA | T-0552 | 2022-02-05 | 1400/11/16 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-02945 | 2022-02-05 | 0 | 0 | PEDCO-CRS-BK-W035-PEDCO-110-CV-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-406451 | 2022-02-19 | 1400/11/30 | 2022-02-12 | 1400/11/23 | CM | NISOC-CRS-BK-W035-PEDCO-110-CV-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0351 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-CIV-00-02370 | 2021-12-19 | 1400/09/28 | CM-C3 |  | BK-SUR-ENG-CIV-00-02945 | 2022-02-05 | 1400/11/17 | CM |  | 1400-2294-327399 | 2021-12-20 | 1400/09/29 | 2021-12-22 | 1400/10/01 | CM | [10 empty] | D01 | IFA | T-0552 | 2022-02-05 | 1400/11/16 | [7 empty] | PEDCO-CRS-BK-W035-PEDCO-110-CV-DW-0001_D00 | [5 empty] | 1400-2294-406451 | 2022-02-19 | 1400/11/30 | 2022-02-12 | 1400/11/23 | CM | NISOC-CRS-BK-W035-PEDCO-110-CV-DW-0001_D00
2 | 5 | 1 | 7 | 2 | 0 | 0 | 2.5.1.7.2 | Calculation
2 | 5 | 1 | 7 | 2 | 0 | 1 | 2.5.1.7.2 | Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W035 | BK-W035-PEDCO-110-CV-CN-0001 | BK-W035-PEDCO-110-CV-CN-0001 | BK | W035 | PEDCO | 110 | CV | CN | 0001 | F0Z-707780 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 1 | 7 | 3 | 0 | 0 | 2.5.1.7.3 | MTO
2 | 5 | 1 | 7 | 3 | 0 | 1 | 2.5.1.7 | MTO For Civil Works - W035 | BK-W035-PEDCO-110-CV-MT-0001 | BK-W035-PEDCO-110-CV-MT-0001 | BK | W035 | PEDCO | 110 | CV | MT | 0001 | F8Z-707781 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 1 | 8 | 0 | 0 | 0 | 2.5.1.8 | Structure
2 | 5 | 1 | 8 | 1 | 0 | 0 | 2.5.1.8.1 | Drawing/Diagram
2 | 5 | 1 | 8 | 1 | 0 | 1 | 2.5.1.8.1 | Platform Structure Drawing - W035 | BK-W035-PEDCO-110-ST-DW-0002 | BK-W035-PEDCO-110-ST-DW-0002 | BK | W035 | PEDCO | 110 | ST | DW | 0002 | F4M-707782 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 1 | 8 | 2 | 0 | 0 | 2.5.1.8.2 | MTO
2 | 5 | 1 | 8 | 2 | 0 | 1 | 2.5.1.8 | MTO For Structural Works - W035 | BK-W035-PEDCO-110-ST-MT-0001 | BK-W035-PEDCO-110-ST-MT-0001 | BK | W035 | PEDCO | 110 | ST | MT | 0001 | F8Z-707783 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 1 | 9 | 0 | 0 | 0 | 2.5.1.9 | Survey (Topography) & Geotechnic/Geoelectric
2 | 5 | 1 | 9 | 1 | 0 | 0 | 2.5.1.9.1 | Geotechnic
2 | 5 | 1 | 9 | 1 | 1 | 0 | 2.5.9.1.1 | Report
2 | 5 | 1 | 9 | 1 | 1 | 1 | 2.5.1.9.1.1.1 | Geotechnical Investigation Report - W035 | BK-W035-PEDCO-110-GT-RT-0001 | BK-W035-PEDCO-110-GT-RT-0001 | BK | W035 | PEDCO | 110 | GT | RT | 0001 | F0Z-707784 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 1 | 9 | 1 | 2 | 0 | 2.5.9.1.2 | Drawing/Diagram
2 | 5 | 1 | 9 | 1 | 2 | 1 | 2.5.1.9.1.2.1 | Flow line Plan & Profile Drawings - W035 | BK-W035-PEDCO-110-SU-DW-0001 | BK-W035-PEDCO-110-SU-DW-0001 | BK | W035 | PEDCO | 110 | SU | DW | 0001 | F4A-707785 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 0 | 0 | 0 | 0 | 2.5.2 | Procurement Engineering
2 | 5 | 2 | 1 | 0 | 0 | 0 | 2.5.2.1 | Piping
2 | 5 | 2 | 1 | 1 | 0 | 0 | 2.5.2.1.1 | Pipes
2 | 5 | 2 | 1 | 1 | 1 | 0 | 2.5.1.1.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 1 | 1 | 1 | 1 | 2.5.2.1.1.1.1 | PMR For Pipes - W035 | BK-W035-PEDCO-110-PI-MR-0001 | BK-W035-PEDCO-110-PI-MR-0001 | BK | W035 | PEDCO | 110 | PI | MR | 0001 | F0Z-707786 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 1 | 2 | 0 | 2.5.1.1.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 1 | 2 | 1 | 2.5.2.1.1.2.1 | TBE For Pipes - W035 | BK-W035-PEDCO-110-PI-TB-0001 | BK-W035-PEDCO-110-PI-TB-0001 | BK | W035 | PEDCO | 110 | PI | TB | 0001 | F0Z-707787 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 2 | 0 | 0 | 2.5.2.1.2 | Fittings
2 | 5 | 2 | 1 | 2 | 1 | 0 | 2.5.1.2.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 1 | 2 | 1 | 1 | 2.5.2.1.2.1.1 | PMR For Fittings - W035 | BK-W035-PEDCO-110-PI-MR-0002 | BK-W035-PEDCO-110-PI-MR-0002 | BK | W035 | PEDCO | 110 | PI | MR | 0002 | F0Z-707788 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 2 | 2 | 0 | 2.5.1.2.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 2 | 2 | 1 | 2.5.2.1.2.2.1 | TBE For Fitting - W035 | BK-W035-PEDCO-110-PI-TB-0002 | BK-W035-PEDCO-110-PI-TB-0002 | BK | W035 | PEDCO | 110 | PI | TB | 0002 | F0Z-707789 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 3 | 0 | 0 | 2.5.2.1.3 | Flanges
2 | 5 | 2 | 1 | 3 | 1 | 0 | 2.5.1.3.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 1 | 3 | 1 | 1 | 2.5.2.1.3.1.1 | PMR For Flanges - W035 | BK-W035-PEDCO-110-PI-MR-0003 | BK-W035-PEDCO-110-PI-MR-0003 | BK | W035 | PEDCO | 110 | PI | MR | 0003 | F0Z-707790 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 3 | 2 | 0 | 2.5.1.3.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 3 | 2 | 1 | 2.5.2.1.3.2.1 | TBE For Flanges - W035 | BK-W035-PEDCO-110-PI-TB-0003 | BK-W035-PEDCO-110-PI-TB-0003 | BK | W035 | PEDCO | 110 | PI | TB | 0003 | F0Z-707791 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 4 | 0 | 0 | 2.5.2.1.4 | Manual Valves
2 | 5 | 2 | 1 | 4 | 1 | 0 | 2.5.1.4.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 1 | 4 | 1 | 1 | 2.5.2.1.4.1.1 | PMR For Manual Valves - W035 | BK-W035-PEDCO-110-PI-MR-0004 | BK-W035-PEDCO-110-PI-MR-0004 | BK | W035 | PEDCO | 110 | PI | MR | 0004 | F0Z-707792 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 4 | 2 | 0 | 2.5.1.4.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 4 | 2 | 1 | 2.5.2.1.4.2.1 | TBE For Manual Valves - W035 | BK-W035-PEDCO-110-PI-TB-0004 | BK-W035-PEDCO-110-PI-TB-0004 | BK | W035 | PEDCO | 110 | PI | TB | 0004 | F0Z-707793 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 5 | 0 | 0 | 2.5.2.1.5 | Gaskets
2 | 5 | 2 | 1 | 5 | 1 | 0 | 2.5.1.5.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 1 | 5 | 1 | 1 | 2.5.2.1.5.1.1 | PMR For Gaskets - W035 | BK-W035-PEDCO-110-PI-MR-0005 | BK-W035-PEDCO-110-PI-MR-0005 | BK | W035 | PEDCO | 110 | PI | MR | 0005 | F0Z-707794 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 5 | 2 | 0 | 2.5.1.5.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 5 | 2 | 1 | 2.5.2.1.5.2.1 | TBE For Gaskets - W035 | BK-W035-PEDCO-110-PI-TB-0005 | BK-W035-PEDCO-110-PI-TB-0005 | BK | W035 | PEDCO | 110 | PI | TB | 0005 | F0Z-707795 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 6 | 0 | 0 | 2.5.2.1.6 | Bolt & Nuts
2 | 5 | 2 | 1 | 6 | 1 | 0 | 2.5.1.6.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 1 | 6 | 1 | 1 | 2.5.2.1.6.1.1 | PMR For Bolt/Nuts - W035 | BK-W035-PEDCO-110-PI-MR-0006 | BK-W035-PEDCO-110-PI-MR-0006 | BK | W035 | PEDCO | 110 | PI | MR | 0006 | F0Z-707796 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 6 | 2 | 0 | 2.5.1.6.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 6 | 2 | 1 | 2.5.2.1.6.2.1 | TBE For Bolt/Nuts - W035 | BK-W035-PEDCO-110-PI-TB-0006 | BK-W035-PEDCO-110-PI-TB-0006 | BK | W035 | PEDCO | 110 | PI | TB | 0006 | F0Z-707797 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 7 | 0 | 0 | 2.5.2.1.7 | Sampling Connection
2 | 5 | 2 | 1 | 7 | 1 | 0 | 2.5.1.7.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 1 | 7 | 1 | 1 | 2.5.2.1.7.1.1 | PMR For Sampling Connection Set - W035 | BK-W035-PEDCO-110-PI-MR-0007 | BK-W035-PEDCO-110-PI-MR-0007 | BK | W035 | PEDCO | 110 | PI | MR | 0007 | F0Z-707798 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 7 | 2 | 0 | 2.5.1.7.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 7 | 2 | 1 | 2.5.2.1.7.2.1 | TBE For Sampling Connection Set - W035 | BK-W035-PEDCO-110-PI-TB-0007 | BK-W035-PEDCO-110-PI-TB-0007 | BK | W035 | PEDCO | 110 | PI | TB | 0007 | F0Z-707799 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 8 | 0 | 0 | 2.5.2.1.8 | Stone Trap
2 | 5 | 2 | 1 | 8 | 1 | 0 | 2.5.1.8.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 1 | 8 | 1 | 1 | 2.5.2.1.8.1.1 | PMR For Stone Trap - W035 | BK-W035-PEDCO-110-PI-MR-0008 | BK-W035-PEDCO-110-PI-MR-0008 | BK | W035 | PEDCO | 110 | PI | MR | 0008 | F0Z-707800 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 8 | 2 | 0 | 2.5.1.8.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 8 | 2 | 1 | 2.5.2.1.8.2.1 | TBE For Stone Trap - W035 | BK-W035-PEDCO-110-PI-TB-0008 | BK-W035-PEDCO-110-PI-TB-0008 | BK | W035 | PEDCO | 110 | PI | TB | 0008 | F0Z-707801 | IFI | IFI | 44720 | 0 | 0 | -44720 | 0 | -44720 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-25 | 2022-05-25 |  | D00 | IFI | T-1002 | 2022-05-25 | 1401/03/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1002 | 2022-05-25 | 1401/03/03 | [37 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 9 | 0 | 0 | 2.5.2.1.9 | Pipe Support
2 | 5 | 2 | 1 | 9 | 1 | 0 | 2.5.1.9.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 1 | 9 | 1 | 1 | 2.5.2.1.9.1.1 | PMR For Pipe Support - W035 | BK-W035-PEDCO-110-PI-MR-0009 | BK-W035-PEDCO-110-PI-MR-0009 | BK | W035 | PEDCO | 110 | PI | MR | 0009 | F0Z-707802 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 1 | 9 | 2 | 0 | 2.5.1.9.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 1 | 9 | 2 | 1 | 2.5.2.1.9.2.1 | TBE For Pipe Support - W035 | BK-W035-PEDCO-110-PI-TB-0009 | BK-W035-PEDCO-110-PI-TB-0009 | BK | W035 | PEDCO | 110 | PI | TB | 0009 | F0Z-707803 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 2 | 0 | 0 | 0 | 2.5.2.2 | Pipeline
2 | 5 | 2 | 2 | 1 | 0 | 0 | 2.5.2.2.1 | Line Pipe
2 | 5 | 2 | 2 | 1 | 1 | 0 | 2.5.2.1.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 2 | 1 | 1 | 1 | 2.5.2.2.1.1.1 | PMR For Line Pipes - W035 | BK-W035-PEDCO-110-PL-MR-0001 | BK-W035-PEDCO-110-PL-MR-0001 | BK | W035 | PEDCO | 110 | PL | MR | 0001 | F0Z-707804 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 2 | 1 | 2 | 0 | 2.5.2.1.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 2 | 1 | 2 | 1 | 2.5.2.2.1.2.1 | TBE For Line Pipes - W035 | BK-W035-PEDCO-110-PL-TB-0001 | BK-W035-PEDCO-110-PL-TB-0001 | BK | W035 | PEDCO | 110 | PL | TB | 0001 | F0Z-707805 | IFI | IFI | 44625 | 44630 | 44634 | 5 | 4 | 9 | IFI | 44709 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 2022-05-14 |  | D01 | IFI | T-0944 | 2022-05-14 | 1401/02/24 | T-0944 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W046S-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W035-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0604 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PPL-00-03409 | 2022-03-08 | 1400/12/17 | C4-RJ | [6 empty] | 1400-2294-443269 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/23 | CM | [10 empty] | D01 | IFI | T-0944 | 2022-05-14 | 1401/02/24 | T-0944 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PL-TB-0001-D00 | [11 empty] | NISOC-CRS-BK-W035-PEDCO-110-PL-TB-0001-D00
2 | 5 | 2 | 2 | 2 | 0 | 0 | 2.5.2.2.2 | Line Pipe
2 | 5 | 2 | 2 | 2 | 1 | 0 | 2.5.2.2.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 2 | 2 | 1 | 1 | 2.5.2.2.2.1.1 | PMR For Flow Line Support - W035 | BK-W035-PEDCO-110-PL-MR-0002 | BK-W035-PEDCO-110-PL-MR-0002 | BK | W035 | PEDCO | 110 | PL | MR | 0002 | F0Z-707806 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 2 | 2 | 2 | 0 | 2.5.2.2.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 2 | 2 | 2 | 1 | 2.5.2.2.2.2.1 | TBE For Flow Line Support - W035 | BK-W035-PEDCO-110-PL-TB-0002 | BK-W035-PEDCO-110-PL-TB-0002 | BK | W035 | PEDCO | 110 | PL | TB | 0002 | F0Z-707807 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 3 | 0 | 0 | 0 | 2.5.2.3 | Control & Instrumentation
2 | 5 | 2 | 3 | 1 | 0 | 0 | 2.5.2.3.1 | WHCP/HPU
2 | 5 | 2 | 3 | 1 | 1 | 0 | 2.5.3.1.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 3 | 1 | 1 | 1 | 2.5.2.3.1.1.1 | PMR For WHCP/HPU - W035 | BK-W035-PEDCO-110-IN-MR-0001 | BK-W035-PEDCO-110-IN-MR-0001 | BK | W035 | PEDCO | 110 | IN | MR | 0001 | F0Z-707808 | IFI | IFI | 44529 | 44547 | 44537 | 18 | -10 | 8 | IFI | 44591 | 44592 | 44593 | 1 | 1 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 2022-01-16 |  | D01 | IFI | T-0470 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02865 | 2022-01-30 | 1400/11/10 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-390765 | 2022-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | NISOC-CRS-BK-W035-PEDCO-110-IN-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0243 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-INS-00-02170 | 2021-12-01 | 1400/09/10 | C4-RJ |  | BK-SUR-ENG-INS-00-02224 | 2021-12-07 | 1400/09/16 | CM-C3 |  | 1400-2294-320808 | 2021-12-17 | 1400/09/26 | 2021-12-07 | 1400/09/16 | CM | [10 empty] | D01 | IFI | T-0470 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02865 | 2022-01-30 | 1400/11/10 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-MR-0001_D00 | [5 empty] | 1400-2294-390765 | 2022-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | NISOC-CRS-BK-W035-PEDCO-110-IN-MR-0001_D00
2 | 5 | 2 | 3 | 1 | 2 | 0 | 2.5.3.1.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 3 | 1 | 2 | 1 | 2.5.2.3.1.2.1 | TBE/TBA For WHCP/HPU - W035 | BK-W035-PEDCO-110-IN-TB-0001 | BK-W035-PEDCO-110-IN-TB-0001 | BK | W035 | PEDCO | 110 | IN | TB | 0001 | F0Z-707809 | IFI | IFI | 44545 | 44544 | 44545 | -1 | 1 | 0 | IFI | 44625 | 44655 | 44660 | 30 | 5 | 35 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-01 | 2022-02-19 |  | D01 | IFI | T-0602 | 2022-02-19 | 1400/11/30 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03345 | 2022-03-05 | 1400/12/15 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-TB-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-9652 | 2022-04-04 | 1401/01/15 | 2022-04-09 | 1401/01/20 | CM | NISOC-CRS-BK-W035-PEDCO-110-IN-TB-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0286 | 2021-12-01 | 1400/09/10 |  |  |  | BK-SUR-ENG-INS-00-02297 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-317340 | 2021-12-14 | 1400/09/23 | 2021-12-15 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-0602 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-INS-00-03345 | 2022-03-05 | 1400/12/15 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-IN-TB-0001_D00 | [5 empty] | 1401-2294-9652 | 2022-04-04 | 1401/01/15 | 2022-04-09 | 1401/01/20 | CM | NISOC-CRS-BK-W035-PEDCO-110-IN-TB-0001_D00
2 | 5 | 2 | 3 | 2 | 0 | 0 | 2.5.2.3.2 | Field Instrumentations
2 | 5 | 2 | 3 | 2 | 1 | 0 | 2.5.3.2.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 3 | 2 | 1 | 1 | 2.5.2.3.2.1.1 | PMR For Field Instrumentations - W035 | BK-W035-PEDCO-110-IN-MR-0002 | BK-W035-PEDCO-110-IN-MR-0002 | BK | W035 | PEDCO | 110 | IN | MR | 0002 | F0Z-707810 | IFI | IFI | 44557 | 44582 | 44221 | 25 | -361 | -336 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 2021-12-13 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | 1400/10/06 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-330276 | 2022-01-21 | 1400/11/01 | 2021-01-25 | 1400/11/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | 1400/10/06 | CM-C3 | [6 empty] | 1400-2294-330276 | 2022-01-21 | 1400/11/01 | 2021-01-25 | 1400/11/05 | CM | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 3 | 2 | 2 | 0 | 2.5.3.2.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 3 | 2 | 2 | 1 | 2.5.2.3.2.2.1 | TBE/TBA For Field Instrumentations - W035 | BK-W035-PEDCO-110-IN-TB-0002 | BK-W035-PEDCO-110-IN-TB-0002 | BK | W035 | PEDCO | 110 | IN | TB | 0002 | F0Z-707811 | IFI | IFI | 44723 | 0 | 0 | -44723 | 0 | -44723 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-28 | 2022-05-28 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07 | [37 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 3 | 3 | 0 | 0 | 2.5.2.3.3 | Instrument Bulk Items
2 | 5 | 2 | 3 | 3 | 1 | 0 | 2.5.3.3.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 3 | 3 | 1 | 1 | 2.5.2.3.3.1.1 | PMR For Instrument Bulk Items - W035 | BK-W035-PEDCO-110-IN-MR-0003 | BK-W035-PEDCO-110-IN-MR-0003 | BK | W035 | PEDCO | 110 | IN | MR | 0003 | F0Z-707812 | IFI | IFI | 44591 | 44227 | 44593 | -364 | 366 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-16 | 2022-01-16 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C2 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 3 | 3 | 2 | 0 | 2.5.3.3.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 3 | 3 | 2 | 1 | 2.5.2.3.3.2.1 | TBE/TBA For Instrument Bulk Items - W035 | BK-W035-PEDCO-110-IN-TB-0003 | BK-W035-PEDCO-110-IN-TB-0003 | BK | W035 | PEDCO | 110 | IN | TB | 0003 | F0Z-707813 | IFI | IFI | 44608 | 44639 | 44634 | 31 | -5 | 26 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 2022-02-02 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03068 | 2022-02-14 | 1400/11/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443275 | 2022-03-19 | 1400/12/19 | 2022-03-14 | 1400/12/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03068 | 2022-02-14 | 1400/11/25 | CM-C2 | [6 empty] | 1400-2294-443275 | 2022-03-19 | 1400/12/19 | 2022-03-14 | 1400/12/23 | CM
2 | 5 | 2 | 4 | 0 | 0 | 0 | 2.5.2.4 | Safety & Fire Fighting
2 | 5 | 2 | 4 | 1 | 0 | 0 | 2.5.2.4.1 | Fire Fighting and Safety Equipment
2 | 5 | 2 | 4 | 1 | 1 | 0 | 2.5.4.1.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 4 | 1 | 1 | 1 | 2.5.2.4.1.1.1 | PMR For Fire Fighting and Safety Equipment - W035 | BK-W035-PEDCO-110-SA-MR-0001 | BK-W035-PEDCO-110-SA-MR-0001 | BK | W035 | PEDCO | 110 | SA | MR | 0001 | F0Z-707814 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 4 | 1 | 2 | 0 | 2.5.4.1.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 4 | 1 | 2 | 1 | 2.5.2.4.1.2.1 | TBE For Fire Fighting and Safety Equipment - W035 | BK-W035-PEDCO-110-SA-TB-0001 | BK-W035-PEDCO-110-SA-TB-0001 | BK | W035 | PEDCO | 110 | SA | TB | 0001 | F0Z-707815 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 4 | 2 | 0 | 0 | 2.5.2.4.2 | Safety Sign
2 | 5 | 2 | 4 | 2 | 1 | 0 | 2.5.4.2.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 4 | 2 | 1 | 1 | 2.5.2.4.2.1.1 | PMR For Fire Safety Sign - W035 | BK-W035-PEDCO-110-SA-MR-0002 | BK-W035-PEDCO-110-SA-MR-0002 | BK | W035 | PEDCO | 110 | SA | MR | 0002 | F0Z-707816 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 4 | 2 | 2 | 0 | 2.5.4.2.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 4 | 2 | 2 | 1 | 2.5.2.4.2.2.1 | TBE For Fire Safety Sign - W035 | BK-W035-PEDCO-110-SA-TB-0002 | BK-W035-PEDCO-110-SA-TB-0002 | BK | W035 | PEDCO | 110 | SA | TB | 0002 | F0Z-707817 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 5 | 0 | 0 | 0 | 2.5.2.5 | Structure
2 | 5 | 2 | 5 | 1 | 0 | 0 | 2.5.2.5.1 | Steel Structure Items
2 | 5 | 2 | 5 | 1 | 1 | 0 | 2.5.5.1.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 5 | 1 | 1 | 1 | 2.5.2.5.1.1.1 | PMR For Steel Structure Items - W035 | BK-W035-PEDCO-110-ST-MR-0001 | BK-W035-PEDCO-110-ST-MR-0001 | BK | W035 | PEDCO | 110 | ST | MR | 0001 | F0Z-707818 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 5 | 1 | 2 | 0 | 2.5.5.1.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 5 | 1 | 2 | 1 | 2.5.2.5.1.2.1 | TBE For Steel Structure Items - W035 | BK-W035-PEDCO-110-ST-TB-0001 | BK-W035-PEDCO-110-ST-TB-0001 | BK | W035 | PEDCO | 110 | ST | TB | 0001 | F0Z-707819 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 5 | 2 | 0 | 0 | 2.5.2.5.2 | Anchor Bolts
2 | 5 | 2 | 5 | 2 | 1 | 0 | 2.5.5.2.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 5 | 2 | 1 | 1 | 2.5.2.5.2.1.1 | PMR For Anchor Bolts - W035 | BK-W035-PEDCO-110-ST-MR-0002 | BK-W035-PEDCO-110-ST-MR-0002 | BK | W035 | PEDCO | 110 | ST | MR | 0002 | F0Z-707820 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 5 | 2 | 2 | 0 | 2.5.5.2.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 5 | 2 | 2 | 1 | 2.5.2.5.2.2.1 | TBE For Anchor Bolts - W035 | BK-W035-PEDCO-110-ST-TB-0002 | BK-W035-PEDCO-110-ST-TB-0002 | BK | W035 | PEDCO | 110 | ST | TB | 0002 | F0Z-707821 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 6 | 0 | 0 | 0 | 2.5.2.6 | Civil
2 | 5 | 2 | 6 | 1 | 0 | 0 | 2.5.2.6.1 | Geomembrane
2 | 5 | 2 | 6 | 1 | 1 | 0 | 2.5.6.1.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 6 | 1 | 1 | 1 | 2.5.2.6.1.1.1 | PMR For Geomembrane - W035 | BK-W035-PEDCO-110-CV-MR-0001 | BK-W035-PEDCO-110-CV-MR-0001 | BK | W035 | PEDCO | 110 | CV | MR | 0001 | F0Z-707822 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 6 | 1 | 2 | 0 | 2.5.6.1.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 6 | 1 | 2 | 1 | 2.5.2.6.1.2.1 | TBE For Geomembrane - W035 | BK-W035-PEDCO-110-CV-TB-0001 | BK-W035-PEDCO-110-CV-TB-0001 | BK | W035 | PEDCO | 110 | CV | TB | 0001 | F0Z-707823 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 6 | 2 | 0 | 0 | 2.5.2.6.2 | Geotextile
2 | 5 | 2 | 6 | 2 | 1 | 0 | 2.5.6.2.1 | Purchase Material Requisition (PMR)
2 | 5 | 2 | 6 | 2 | 1 | 1 | 2.5.2.6.2.1.1 | PMR For Geotextile - W035 | BK-W035-PEDCO-110-CV-MR-0002 | BK-W035-PEDCO-110-CV-MR-0002 | BK | W035 | PEDCO | 110 | CV | MR | 0002 | F0Z-707824 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 2 | 6 | 2 | 2 | 0 | 2.5.6.2.2 | Technical Bid Evaluation (TBE)
2 | 5 | 2 | 6 | 2 | 2 | 1 | 2.5.2.6.2.2.1 | TBE For Geotextile - W035 | BK-W035-PEDCO-110-CV-TB-0002 | BK-W035-PEDCO-110-CV-TB-0002 | BK | W035 | PEDCO | 110 | CV | TB | 0002 | F0Z-707825 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 3 | 0 | 0 | 0 | 0 | 2.5.3 | Commissioning Engineering
2 | 5 | 3 | 0 | 0 | 1 | 0 | 2.5.3.1 | Procedure/Plan
2 | 5 | 3 | 0 | 0 | 1 | 1 | 2.5.3.1.1 | Pre-Commissioning, Commissioning & Startup Procedure - W035 | BK-W035-PEDCO-110-CO-PR-0001 | BK-W035-PEDCO-110-CO-PR-0001 | BK | W035 | PEDCO | 110 | CO | PR | 0001 | F0Z-707826 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 4 | 0 | 0 | 0 | 0 | 2.5.4 | Field Engineering
2 | 5 | 4 | 0 | 0 | 1 | 0 | 2.5.4.1 | Query
2 | 5 | 4 | 0 | 0 | 1 | 1 | 2.5.4.1.1 | Technical/Site Queries | BK-W035-PEDCO-110-GE-TQ-0001 | BK-W035-PEDCO-110-GE-TQ-0001 | BK | W035 | PEDCO | 110 | GE | TQ | 0001 | F7Z-707827 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 4 | 0 | 0 | 2 | 0 | 2.5.4.2 | Dossier
2 | 5 | 4 | 0 | 0 | 2 | 1 | 2.5.4.2.1 | As-Built Document Booklets - W035 | BK-W035-PEDCO-110-GE-DO-0001 | BK-W035-PEDCO-110-GE-DO-0001 | BK | W035 | PEDCO | 110 | GE | DO | 0001 | F0Z-707828 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 5 | 0 | 0 | 0 | 0 | 2.5.5 | Engineering Final Documentation
2 | 5 | 5 | 0 | 0 | 1 | 0 | 2.5.5.1 | Manual
2 | 5 | 5 | 0 | 0 | 1 | 1 | 2.5.5.1.1 | Operating Manual - W035 | BK-W035-PEDCO-110-GE-ML-0001 | BK-W035-PEDCO-110-GE-ML-0001 | BK | W035 | PEDCO | 110 | GE | ML | 0001 | F0Z-707829 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 5 | 0 | 0 | 2 | 0 | 2.5.5.2 | Dossier
2 | 5 | 5 | 0 | 0 | 2 | 1 | 2.5.5.2.1 | As-Built Document Booklets - W035 | BK-W035-PEDCO-110-GE-DO-0001 | BK-W035-PEDCO-110-GE-DO-0001 | [7 empty] | F0Z-707828 | [43 empty] | Moved to Field | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 5 | 5 | 0 | 0 | 2 | 2 | 2.5.5.2.2 | Final Engineering Dossier - W035 | BK-W035-PEDCO-110-GE-DO-0002 | BK-W035-PEDCO-110-GE-DO-0002 | BK | W035 | PEDCO | 110 | GE | DO | 0002 | F0Z-707830 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 0 | 0 | 0 | 0 | 0 | 2.6 | Package 05-New Well # W008N
2 | 6 | 1 | 0 | 0 | 0 | 0 | 2.6.1 | Detail Design
2 | 6 | 1 | 1 | 0 | 0 | 0 | 2.6.1.1 | Process
2 | 6 | 1 | 1 | 1 | 0 | 0 | 2.6.1.1.1 | Drawing/Diagram
2 | 6 | 1 | 1 | 1 | 0 | 1 | 2.6.1.1.1 | Process Flow Diagram - W008N | BK-W008N-PEDCO-110-PR-PF-0001 | BK-W008N-PEDCO-110-PR-PF-0001 | BK | W008N | PEDCO | 110 | PR | PF | 0001 | F2A-707831 | AFC | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-11-16 | 0 | 0 | -44516 | 0 | -44516 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-02 | 0 |  | D01 | IFC | T-0205 | 2021-11-02 | 1400/08/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-PF-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W008N-PEDCO-110-PR-PF-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 2021-09-08 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0205 | 2021-11-02 | 1400/08/11 | [7 empty] | PEDCO-CRS-BK-W008N-PEDCO-110-PR-PF-0001_D00 | [11 empty] | NISOC-CRS-BK-W008N-PEDCO-110-PR-PF-0001_D00
2 | 6 | 1 | 1 | 1 | 0 | 2 | 2.6.1.1.1 | P&ID - W008N | BK-W008N-PEDCO-110-PR-PI-0001 | BK-W008N-PEDCO-110-PR-PI-0001 | BK | W008N | PEDCO | 110 | PR | PI | 0001 | F2A-707832 | AFC | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-01 | 0 |  | D03 | IFA | T-0653 | 2022-02-28 | 1400/12/09 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 2021-09-08 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0201 | 2021-11-01 | 1400/08/10 |  |  |  | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-279084 | 2021-11-16 | 1400/08/25 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0345 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-PCS-00-02540 | 2022-01-03 | 1400/10/13 | CM-C3 | PEDCO-BK-W008N-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-342085 | 2021-12-30 | 1400/10/09 | 2022-01-03 | 1400/10/13 | RJ | NISOC-BK-W008N-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0653 | 2022-02-28 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-PI-0001_D02
2 | 6 | 1 | 1 | 2 | 0 | 0 | 2.6.1.1.2 | List
2 | 6 | 1 | 1 | 2 | 0 | 1 | 2.6.1.1.2 | Line List - W008N | BK-W008N-PEDCO-110-PR-LI-0001 | BK-W008N-PEDCO-110-PR-LI-0001 | BK | W008N | PEDCO | 110 | PR | LI | 0001 | F0Z-707833 | AFC | IFC | 44444 | 44439 | 44447 | -5 | 8 | 3 | IFC | 44522 | 44527 | 44529 | 5 | 2 | 7 | IFA | 44573 | 0 | 0 | -44573 | 0 | -44573 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-08 | 0 |  | D02 | IFA | T-0403 | 2021-12-29 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W008N-PEDCO-110-PR-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2294/181042 | 2021-08-31 | 1400/06/09 | 2021-09-08 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0217 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PCS-00-02051 | 2021-11-20 | 1400/08/29 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-LI-0001_D00 | [5 empty] | 1400-2290-293083 | 2021-11-27 | 1400/09/06 | 2021-11-29 | 1400/09/08 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-LI-0001_D00 | [9 empty] | D02 | IFA | T-0403 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-LI-0001_D01 | [11 empty] | NISOC-CRS-BK-W008N-PEDCO-110-PR-LI-0001_D01
2 | 6 | 1 | 1 | 3 | 0 | 0 | 2.6.1.1.3 | Report | [145 empty] | 1400/09/06
2 | 6 | 1 | 1 | 3 | 0 | 1 | 2.6.1.1.3 | Flow line Hydraulic Calculation Report | BK-W008N-PEDCO-110-PR-RT-0001 | BK-W008N-PEDCO-110-PR-RT-0001 | BK | W008N | PEDCO | 110 | PR | RT | 0001 | F0Z-707834 | AFC | IFC | 44513 | 44514 | 44517 | 1 | 3 | 4 | IFA | 44576 | 44228 | 44597 | -348 | 369 | 21 | IFA | 44628 | 44630 | 44633 | 2 | 3 | 5 | IFA | 44695 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-30 | 0 |  | D03 | IFA | T-0878 | 2022-04-30 | 1401/02/10 | T-0878 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 2022-05-28 | 1402/03/07 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0197 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-PCS-00-01993 | 2021-11-14 | 1400/08/23 | CM-C3 | [6 empty] | 1400-2294-275250 | 2021-11-14 | 1400/08/23 | 2021-11-17 | 1400/08/26 | CM | [10 empty] | D01 | IFA | T-0413 | 2022-01-01 | 1400/10/11 |  |  |  | BK-SUR-ENG-PCS-00-02735 | 2022-01-19 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D00 | [5 empty] | 1400-2294-392131 | 2021-02-01 | 1400/11/12 | 2022-02-05 | 1400/11/16 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-0627 | 2022-02-22 | 1400/12/03 |  |  |  | BK-SUR-ENG-PCS-00-03387 | 2022-03-07 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D01 | [5 empty] | 1400-2294-443285 | 2022-03-10 | 1400/12/19 | 2022-03-13 | 1400/12/22 | CM | NISOC-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D01 | [9 empty] | D03 | IFA | T-0878 | 2022-04-30 | 1401/02/10 | T-0878 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 2022-05-28 | 1402/03/07 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D02 | [11 empty] | NISOC-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D02
2 | 6 | 1 | 1 | 4 | 0 | 0 | 2.6.1.1.4 | Data Sheet
2 | 6 | 1 | 1 | 4 | 0 | 1 | 2.6.1.1 | Process Data Sheets For Instrument Devices - W008N | BK-W008N-PEDCO-110-PR-DT-0001 | BK-W008N-PEDCO-110-PR-DT-0001 | BK | W008N | PEDCO | 110 | PR | DT | 0001 | F0Z-707835 | AFC | IFC | 44677 | 44689 | 44695 | 12 | 6 | 18 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-12 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04093 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 2022-05-14 | 1401/02/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-PCS-01-04093 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 2022-05-14 | 1401/02/24 | CM | [19 empty] | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 2 | 0 | 0 | 0 | 2.6.1.2 | Piping
2 | 6 | 1 | 2 | 1 | 0 | 0 | 2.6.1.2.1 | Drawing/Diagram
2 | 6 | 1 | 2 | 1 | 0 | 1 | 2.6.1.2.1 | Plot Plan Drawing - W008N | BK-W008N-PEDCO-110-PI-DW-0001 | BK-W008N-PEDCO-110-PI-DW-0001 | BK | W008N | PEDCO | 110 | PI | DW | 0001 | F5A-707836 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 2 | 1 | 0 | 2 | 2.6.1.2.1 | Piping Plan - W008N | BK-W008N-PEDCO-110-PI-DW-0002 | BK-W008N-PEDCO-110-PI-DW-0002 | BK | W008N | PEDCO | 110 | PI | DW | 0002 | F4L-707837 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 2 | 1 | 0 | 3 | 2.6.1.2.1 | Isometric Drawings - W008N | BK-W008N-PEDCO-110-PI-DW-0003 | BK-W008N-PEDCO-110-PI-DW-0003 | BK | W008N | PEDCO | 110 | PI | DW | 0003 | F2L-707838 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 2 | 1 | 0 | 4 | 2.6.1.2.1 | Material Flow Diagram - W008N | BK-W008N-PEDCO-110-PI-DG-0001 | BK-W008N-PEDCO-110-PI-DG-0001 | BK | W008N | PEDCO | 110 | PI | DG | 0001 | F2A-707839 | AFC | IFC | 2021-11-22 | 2021-11-24 | 2021-11-27 | 2 | 3 | 5 | IFA | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-08 | 0 |  | D01 | IFA | T-0932 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04376 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PI-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W008N-PEDCO-110-PI-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0219 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PIP-00-02060 | 2021-11-21 | 1400/08/30 | CM-C3 | [6 empty] | 1400-2294-289400 | 2021-11-24 | 1400/09/03 | 2021-11-27 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0932 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04376 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PI-DG-0001_D00 | [11 empty] | NISOC-CRS-BK-W008N-PEDCO-110-PI-DG-0001_D00
2 | 6 | 1 | 2 | 2 | 0 | 0 | 2.6.1.2.2 | List
2 | 6 | 1 | 2 | 2 | 0 | 1 | 2.6.1.2.2 | Piping Support List - W008N | BK-W008N-PEDCO-110-PI-LI-0001 | BK-W008N-PEDCO-110-PI-LI-0001 | BK | W008N | PEDCO | 110 | PI | LI | 0001 | F0Z-707840 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 2 | 2 | 0 | 2 | 2.6.1.2.2 | Critical Line List - W008N | BK-W008N-PEDCO-110-PI-LI-0002 | BK-W008N-PEDCO-110-PI-LI-0002 | BK | W008N | PEDCO | 110 | PI | LI | 0002 | F0Z-707841 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 2 | 3 | 0 | 0 | 2.6.1.2.3 | Report
2 | 6 | 1 | 2 | 3 | 0 | 1 | 2.6.1.2.3 | PDMS Model Review Report (60%) - W008N | BK-W008N-PEDCO-110-PI-RT-0001 | BK-W008N-PEDCO-110-PI-RT-0001 | BK | W008N | PEDCO | 110 | PI | RT | 0001 | F0Z-707842 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 2 | 3 | 0 | 2 | 2.6.1.2.3 | PDMS Model Review Report (90%) - W008N | BK-W008N-PEDCO-110-PI-RT-0002 | BK-W008N-PEDCO-110-PI-RT-0002 | BK | W008N | PEDCO | 110 | PI | RT | 0002 | F0Z-707843 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 2 | 4 | 0 | 0 | 2.6.1.2.4 | MTO
2 | 6 | 1 | 2 | 4 | 0 | 1 | 2.6.1.2 | MTO For Pipes - W008N | BK-W008N-PEDCO-110-PI-MT-0001 | BK-W008N-PEDCO-110-PI-MT-0001 | BK | W008N | PEDCO | 110 | PI | MT | 0001 | F8Z-707844 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 2 | 4 | 0 | 2 | 2.6.1.2 | MTO For Fittings - W008N | BK-W008N-PEDCO-110-PI-MT-0002 | BK-W008N-PEDCO-110-PI-MT-0002 | BK | W008N | PEDCO | 110 | PI | MT | 0002 | F8Z-707845 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 2 | 4 | 0 | 3 | 2.6.1.2 | MTO For Flanges - W008N | BK-W008N-PEDCO-110-PI-MT-0003 | BK-W008N-PEDCO-110-PI-MT-0003 | BK | W008N | PEDCO | 110 | PI | MT | 0003 | F8Z-707846 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 2 | 4 | 0 | 4 | 2.6.1.2 | MTO For Manual Valves - W008N | BK-W008N-PEDCO-110-PI-MT-0004 | BK-W008N-PEDCO-110-PI-MT-0004 | BK | W008N | PEDCO | 110 | PI | MT | 0004 | F8Z-707847 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 2 | 4 | 0 | 5 | 2.6.1.2 | MTO For Gaskets - W008N | BK-W008N-PEDCO-110-PI-MT-0005 | BK-W008N-PEDCO-110-PI-MT-0005 | BK | W008N | PEDCO | 110 | PI | MT | 0005 | F8Z-707848 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 2 | 4 | 0 | 6 | 2.6.1.2 | MTO For Bolt & Nuts - W008N | BK-W008N-PEDCO-110-PI-MT-0006 | BK-W008N-PEDCO-110-PI-MT-0006 | BK | W008N | PEDCO | 110 | PI | MT | 0006 | F8Z-707849 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 3 | 0 | 0 | 0 | 2.6.1.3 | Pipeline & Flow line
2 | 6 | 1 | 3 | 1 | 0 | 0 | 2.6.1.3.1 | Drawings
2 | 6 | 1 | 3 | 1 | 0 | 1 | 2.6.1.3.1 | Flow line Transversal Drawings - W008N | BK-W008N-PEDCO-110-PL-DW-0002 | BK-W008N-PEDCO-110-PL-DW-0002 | BK | W008N | PEDCO | 110 | PL | DW | 0002 | F4A-707850 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 3 | 2 | 0 | 0 | 2.6.1.3.2 | List
2 | 6 | 1 | 3 | 2 | 0 | 1 | 2.6.1.3.2 | Road Crossing Location List | BK-W008N-PEDCO-110-PL-LI-0001 | BK-W008N-PEDCO-110-PL-LI-0001 | BK | W008N | PEDCO | 110 | PL | LI | 0001 | F0Z-707851 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 3 | 3 | 0 | 0 | 2.6.1.3.3 | MTO
2 | 6 | 1 | 3 | 3 | 0 | 1 | 2.6.1.3 | MTO For Line Pipes (Flow lines) - W008N | BK-W008N-PEDCO-110-PL-MT-0001 | BK-W008N-PEDCO-110-PL-MT-0001 | BK | W008N | PEDCO | 110 | PL | MT | 0001 | F8Z-707852 | IFI | IFI | 44444 | 44438 | 44444 | -6 | 6 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2021-08-22 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | 1400/05/31 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | 1400/05/31 | CM-C2 | [6 empty] | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 4 | 0 | 0 | 0 | 2.6.1.4 | Control & Instrumentation
2 | 6 | 1 | 4 | 1 | 0 | 0 | 2.6.1.4.1 | Drawing/Diagram
2 | 6 | 1 | 4 | 1 | 0 | 1 | 2.6.1.4.1 | Instrument Location Layout Drawing - W008N | BK-W008N-PEDCO-110-IN-PY-0001 | BK-W008N-PEDCO-110-IN-PY-0001 | BK | W008N | PEDCO | 110 | IN | PY | 0001 | F2J-707853 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 4 | 2 | 0 | 0 | 2.6.1.4.2 | MTO
2 | 6 | 1 | 4 | 2 | 0 | 1 | 2.6.1.4 | MTO For Instrument Tube and Fitting - W008N | BK-W008N-PEDCO-110-IN-MT-0001 | BK-W008N-PEDCO-110-IN-MT-0001 | BK | W008N | PEDCO | 110 | IN | MT | 0001 | F8Z-707854 | IFI | IFI | 2021-11-28 | 2021-11-21 | 2021-11-29 | -7 | 8 | 1 | IFI | 2022-01-01 | 2022-01-03 | 2022-01-05 | 2 | 2 | 4 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-14 | 2022-01-12 |  | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W008N-PEDCO-110-IN-MT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0236 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02140 | 2021-11-28 | 1400/09/08 | C4-RJ | [6 empty] | 1400-2294-283474 | 2021-11-21 | 1400/08/30 | 2021-11-29 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0359 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-INS-00-02494 | 2022-01-01 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MT-0001_D00 | [5 empty] | 1400-2294-347953 | 2022-01-03 | 1400/10/13 | 2022-01-05 | 1400/10/15 | CM | NISOC-CRS-BK-W008N-PEDCO-110-IN-MT-0001_D00 | [9 empty] | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MT-0001_D01 | [5 empty] | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W008N-PEDCO-110-IN-MT-0001_D01
2 | 6 | 1 | 4 | 2 | 0 | 2 | 2.6.1.4 | MTO For Instrument Cable Tray - W008N | BK-W008N-PEDCO-110-IN-MT-0002 | BK-W008N-PEDCO-110-IN-MT-0002 | BK | W008N | PEDCO | 110 | IN | MT | 0002 | F8Z-707855 | IFI | IFI | 2021-11-28 | 2021-11-21 | 2021-11-29 | -7 | 8 | 1 | IFI | 2022-01-01 | 2022-01-03 | 2022-01-05 | 2 | 2 | 4 | IFI | 2022-01-26 | 2022-02-02 | 2022-02-07 | 7 | 5 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-14 | 2022-01-12 |  | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W008N-PEDCO-110-IN-MT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0236 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-INS-00-02140 | 2021-11-28 | 1400/09/08 | C4-RJ | [6 empty] | 1400-2294-283474 | 2021-11-21 | 1400/08/30 | 2021-11-29 | 1400/09/08 | CM | [10 empty] | D01 | IFI | T-0359 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-INS-00-02494 | 2022-01-01 | 1400/10/11 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MT-0002_D00 | [5 empty] | 1400-2294-347953 | 2022-01-03 | 1400/10/13 | 2022-01-05 | 1400/10/15 | CM | NISOC-CRS-BK-W008N-PEDCO-110-IN-MT-0002_D00 | [9 empty] | D02 | IFI | T-0451 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-INS-00-02819 | 2022-01-26 | 1400/11/06 | CM-C2 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MT-0002_D01 | [5 empty] | 1400-2294-394002 | 2022-02-02 | 1400/11/13 | 2022-02-07 | 1400/11/18 | AP | NISOC-CRS-BK-W008N-PEDCO-110-IN-MT-0002_D01
2 | 6 | 1 | 5 | 0 | 0 | 0 | 2.6.1.5 | Safety
2 | 6 | 1 | 5 | 1 | 0 | 0 | 2.6.1.5.1 | Drawing/Diagram
2 | 6 | 1 | 5 | 1 | 0 | 1 | 2.6.1.5.1 | Hazardous Area Classification Layout - W008N | BK-W008N-PEDCO-110-SA-PY-0001 | BK-W008N-PEDCO-110-SA-PY-0001 | BK | W008N | PEDCO | 110 | SA | PY | 0001 | F2L-707856 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 5 | 1 | 0 | 2 | 2.6.1.5.1 | Safety & Fire Fighting Equipment Location Layout - W008N | BK-W008N-PEDCO-110-SA-PY-0002 | BK-W008N-PEDCO-110-SA-PY-0002 | BK | W008N | PEDCO | 110 | SA | PY | 0002 | F2L-707857 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 5 | 1 | 0 | 3 | 2.6.1.5.1 | Escape Route & Safety Sign Layout - W008N | BK-W008N-PEDCO-110-SA-PY-0003 | BK-W008N-PEDCO-110-SA-PY-0003 | BK | W008N | PEDCO | 110 | SA | PY | 0003 | F2L-707858 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 5 | 2 | 0 | 0 | 2.6.1.5.2 | List
2 | 6 | 1 | 5 | 2 | 0 | 1 | 2.6.1.5.2 | Hazard Source List - W008N | BK-W008N-PEDCO-110-SA-LI-0001 | BK-W008N-PEDCO-110-SA-LI-0001 | BK | W008N | PEDCO | 110 | SA | LI | 0001 | F0Z-707859 | AFC | IFC | 44523 | 44530 | 44536 | 7 | 6 | 13 | IFA | 44608 | 44628 | 44626 | 20 | -2 | 18 | IFA | 44677 | 0 | 0 | -44677 | 0 | -44677 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-09 | 0 |  | D02 | IFA | T-0806 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W008N-PEDCO-110-SA-LI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0220 | 2021-11-09 | 1400/08/18 | [13 empty] | 1400-2290-298651 | 2021-11-30 | 1400/09/09 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0544 | 2022-02-02 | 1400/11/13 | [13 empty] | 1400-2294-435413 | 2022-03-08 | 1400/12/15 | 2022-03-06 | 1400/12/15 | CM | NISOC-CRS-BK-W008N-PEDCO-110-SA-LI-0001_D00 | [9 empty] | D02 | IFA | T-0806 | 2022-04-12 | 1401/01/23 | [19 empty] | NISOC-CRS-BK-W008N-PEDCO-110-SA-LI-0001_D01
2 | 6 | 1 | 5 | 3 | 0 | 0 | 2.6.1.5.3 | MTO
2 | 6 | 1 | 5 | 3 | 0 | 1 | 2.6.1.5 | MTO For Fire Fighting & Safety Equipment - W008N | BK-W008N-PEDCO-110-SA-MT-0001 | BK-W008N-PEDCO-110-SA-MT-0001 | BK | W008N | PEDCO | 110 | SA | MT | 0001 | F8Z-707860 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 5 | 3 | 0 | 2 | 2.6.1.5 | MTO For Safety Sign - W008N | BK-W008N-PEDCO-110-SA-MT-0002 | BK-W008N-PEDCO-110-SA-MT-0002 | BK | W008N | PEDCO | 110 | SA | MT | 0002 | F8Z-707861 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 6 | 0 | 0 | 0 | 2.6.1.6 | Architecture
2 | 6 | 1 | 6 | 1 | 0 | 0 | 2.6.1.6.1 | Drawing/Diagram
2 | 6 | 1 | 6 | 1 | 0 | 1 | 2.6.1.6 | Architectural Drawing For WHCP/HPU Shelter of Well Pads - W008N | BK-W008N-PEDCO-110-AR-DW-0001 | BK-W008N-PEDCO-110-AR-DW-0001 | BK | W008N | PEDCO | 110 | AR | DW | 0001 | F4B-707862 | AFC | IFC | 44632 | 44625 | 44628 | -7 | 3 | -4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-26 | 0 |  | D00 | IFC | T-0640 | 2022-02-26 | 1400/12/07 | 0 | 0 | 0 | BK-SUR-ENG-ARC-00-03400 | 2022-03-08 | 1400/12/18 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-435028 | 2022-03-05 | 1400/12/14 | 2022-03-08 | 1400/12/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0640 | 2022-02-26 | 1400/12/07 |  |  |  | BK-SUR-ENG-ARC-00-03400 | 2022-03-08 | 1400/12/18 | CM-C2 | [6 empty] | 1400-2294-435028 | 2022-03-05 | 1400/12/14 | 2022-03-08 | 1400/12/17 | AP | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 7 | 0 | 0 | 0 | 2.6.1.7 | Civil
2 | 6 | 1 | 7 | 1 | 0 | 0 | 2.6.1.7.1 | Drawing/Diagram
2 | 6 | 1 | 7 | 1 | 0 | 1 | 2.6.1.7.1 | General Civil Layout -W008N | BK-W008N-PEDCO-110-CV-PY-0001 | BK-W008N-PEDCO-110-CV-PY-0001 | BK | W008N | PEDCO | 110 | CV | PY | 0001 | F4A-707863 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 7 | 1 | 0 | 2 | 2.6.1.7.1 | Civil and Structural drawings -W008N | BK-W008N-PEDCO-110-CV-PY-0002 | BK-W008N-PEDCO-110-CV-PY-0002 | BK | W008N | PEDCO | 110 | CV | PY | 0002 | F4S-707864 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 7 | 1 | 0 | 3 | 2.6.1.7.1 | Rough Grading Plans -W008N | BK-W008N-PEDCO-110-CV-DW-0001 | BK-W008N-PEDCO-110-CV-DW-0001 | BK | W008N | PEDCO | 110 | CV | DW | 0001 | F4S-707865 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 7 | 2 | 0 | 0 | 2.6.1.7.2 | Calculation
2 | 6 | 1 | 7 | 2 | 0 | 1 | 2.6.1.7.2 | Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W008N | BK-W008N-PEDCO-110-CV-CN-0001 | BK-W008N-PEDCO-110-CV-CN-0001 | BK | W008N | PEDCO | 110 | CV | CN | 0001 | F0Z-707866 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 7 | 3 | 0 | 0 | 2.6.1.7.3 | MTO
2 | 6 | 1 | 7 | 3 | 0 | 1 | 2.6.1.7 | MTO For Civil Works | BK-W008N-PEDCO-110-CV-MT-0001 | BK-W008N-PEDCO-110-CV-MT-0001 | BK | W008N | PEDCO | 110 | CV | MT | 0001 | F8Z-707867 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 8 | 0 | 0 | 0 | 2.6.1.8 | Structure
2 | 6 | 1 | 8 | 1 | 0 | 0 | 2.6.1.8.1 | Drawing/Diagram
2 | 6 | 1 | 8 | 1 | 0 | 1 | 2.6.1.8.1 | Platform Structure Drawing - W008N | BK-W008N-PEDCO-110-ST-DW-0002 | BK-W008N-PEDCO-110-ST-DW-0002 | BK | W008N | PEDCO | 110 | ST | DW | 0002 | F4M-707868 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 8 | 2 | 0 | 0 | 2.6.1.8.2 | MTO
2 | 6 | 1 | 8 | 2 | 0 | 1 | 2.6.1.8 | MTO For Structural Works - W008N | BK-W008N-PEDCO-110-ST-MT-0001 | BK-W008N-PEDCO-110-ST-MT-0001 | BK | W008N | PEDCO | 110 | ST | MT | 0001 | F8Z-707869 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 9 | 0 | 0 | 0 | 2.6.1.9 | Survey (Topography) & Geotechnic/Geoelectric
2 | 6 | 1 | 9 | 1 | 0 | 0 | 2.6.1.9.1 | Geotechnic
2 | 6 | 1 | 9 | 1 | 1 | 0 | 2.6.9.1.1 | Report
2 | 6 | 1 | 9 | 1 | 1 | 1 | 2.6.1.9.1.1.1 | Geotechnical Investigation Report - W008N | BK-W008N-PEDCO-110-GT-RT-0001 | BK-W008N-PEDCO-110-GT-RT-0001 | BK | W008N | PEDCO | 110 | GT | RT | 0001 | F0Z-707870 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 1 | 9 | 1 | 2 | 0 | 2.6.9.1.2 | Drawing/Diagram
2 | 6 | 1 | 9 | 1 | 2 | 1 | 2.6.1.9.1.2.1 | Flow line Plan & Profile Drawings - W008N | BK-W008N-PEDCO-110-SU-DW-0001 | BK-W008N-PEDCO-110-SU-DW-0001 | BK | W008N | PEDCO | 110 | SU | DW | 0001 | F4A-707871 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 0 | 0 | 0 | 0 | 2.6.2 | Procurement Engineering
2 | 6 | 2 | 1 | 0 | 0 | 0 | 2.6.2.1 | Piping
2 | 6 | 2 | 1 | 1 | 0 | 0 | 2.6.2.1.1 | Pipes
2 | 6 | 2 | 1 | 1 | 1 | 0 | 2.6.1.1.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 1 | 1 | 1 | 1 | 2.6.2.1.1.1.1 | PMR For Pipes - W008N | BK-W008N-PEDCO-110-PI-MR-0001 | BK-W008N-PEDCO-110-PI-MR-0001 | BK | W008N | PEDCO | 110 | PI | MR | 0001 | F0Z-707872 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 1 | 2 | 0 | 2.6.1.1.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 1 | 2 | 1 | 2.6.2.1.1.2.1 | TBE For Pipes - W008N | BK-W008N-PEDCO-110-PI-TB-0001 | BK-W008N-PEDCO-110-PI-TB-0001 | BK | W008N | PEDCO | 110 | PI | TB | 0001 | F0Z-707873 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 2 | 0 | 0 | 2.6.2.1.2 | Fittings
2 | 6 | 2 | 1 | 2 | 1 | 0 | 2.6.1.2.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 1 | 2 | 1 | 1 | 2.6.2.1.2.1.1 | PMR For Fittings - W008N | BK-W008N-PEDCO-110-PI-MR-0002 | BK-W008N-PEDCO-110-PI-MR-0002 | BK | W008N | PEDCO | 110 | PI | MR | 0002 | F0Z-707874 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 2 | 2 | 0 | 2.6.1.2.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 2 | 2 | 1 | 2.6.2.1.2.2.1 | TBE For Fitting - W008N | BK-W008N-PEDCO-110-PI-TB-0002 | BK-W008N-PEDCO-110-PI-TB-0002 | BK | W008N | PEDCO | 110 | PI | TB | 0002 | F0Z-707875 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 3 | 0 | 0 | 2.6.2.1.3 | Flanges
2 | 6 | 2 | 1 | 3 | 1 | 0 | 2.6.1.3.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 1 | 3 | 1 | 1 | 2.6.2.1.3.1.1 | PMR For Flanges - W008N | BK-W008N-PEDCO-110-PI-MR-0003 | BK-W008N-PEDCO-110-PI-MR-0003 | BK | W008N | PEDCO | 110 | PI | MR | 0003 | F0Z-707876 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 3 | 2 | 0 | 2.6.1.3.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 3 | 2 | 1 | 2.6.2.1.3.2.1 | TBE For Flanges - W008N | BK-W008N-PEDCO-110-PI-TB-0003 | BK-W008N-PEDCO-110-PI-TB-0003 | BK | W008N | PEDCO | 110 | PI | TB | 0003 | F0Z-707877 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 4 | 0 | 0 | 2.6.2.1.4 | Manual Valves
2 | 6 | 2 | 1 | 4 | 1 | 0 | 2.6.1.4.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 1 | 4 | 1 | 1 | 2.6.2.1.4.1.1 | PMR For Manual Valves - W008N | BK-W008N-PEDCO-110-PI-MR-0004 | BK-W008N-PEDCO-110-PI-MR-0004 | BK | W008N | PEDCO | 110 | PI | MR | 0004 | F0Z-707878 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 4 | 2 | 0 | 2.6.1.4.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 4 | 2 | 1 | 2.6.2.1.4.2.1 | TBE For Manual Valves - W008N | BK-W008N-PEDCO-110-PI-TB-0004 | BK-W008N-PEDCO-110-PI-TB-0004 | BK | W008N | PEDCO | 110 | PI | TB | 0004 | F0Z-707879 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 5 | 0 | 0 | 2.6.2.1.5 | Gaskets
2 | 6 | 2 | 1 | 5 | 1 | 0 | 2.6.1.5.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 1 | 5 | 1 | 1 | 2.6.2.1.5.1.1 | PMR For Gaskets - W008N | BK-W008N-PEDCO-110-PI-MR-0005 | BK-W008N-PEDCO-110-PI-MR-0005 | BK | W008N | PEDCO | 110 | PI | MR | 0005 | F0Z-707880 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 5 | 2 | 0 | 2.6.1.5.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 5 | 2 | 1 | 2.6.2.1.5.2.1 | TBE For Gaskets - W008N | BK-W008N-PEDCO-110-PI-TB-0005 | BK-W008N-PEDCO-110-PI-TB-0005 | BK | W008N | PEDCO | 110 | PI | TB | 0005 | F0Z-707881 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 6 | 0 | 0 | 2.6.2.1.6 | Bolt & Nuts
2 | 6 | 2 | 1 | 6 | 1 | 0 | 2.6.1.6.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 1 | 6 | 1 | 1 | 2.6.2.1.6.1.1 | PMR For Bolt/Nuts - W008N | BK-W008N-PEDCO-110-PI-MR-0006 | BK-W008N-PEDCO-110-PI-MR-0006 | BK | W008N | PEDCO | 110 | PI | MR | 0006 | F0Z-707882 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 6 | 2 | 0 | 2.6.1.6.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 6 | 2 | 1 | 2.6.2.1.6.2.1 | TBE For Bolt/Nuts - W008N | BK-W008N-PEDCO-110-PI-TB-0006 | BK-W008N-PEDCO-110-PI-TB-0006 | BK | W008N | PEDCO | 110 | PI | TB | 0006 | F0Z-707883 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 7 | 0 | 0 | 2.6.2.1.7 | Sampling Connection
2 | 6 | 2 | 1 | 7 | 1 | 0 | 2.6.1.7.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 1 | 7 | 1 | 1 | 2.6.2.1.7.1.1 | PMR For Sampling Connection Set - W008N | BK-W008N-PEDCO-110-PI-MR-0007 | BK-W008N-PEDCO-110-PI-MR-0007 | BK | W008N | PEDCO | 110 | PI | MR | 0007 | F0Z-707884 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 7 | 2 | 0 | 2.6.1.7.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 7 | 2 | 1 | 2.6.2.1.7.2.1 | TBE For Sampling Connection Set - W008N | BK-W008N-PEDCO-110-PI-TB-0007 | BK-W008N-PEDCO-110-PI-TB-0007 | BK | W008N | PEDCO | 110 | PI | TB | 0007 | F0Z-707885 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 8 | 0 | 0 | 2.6.2.1.8 | Stone Trap
2 | 6 | 2 | 1 | 8 | 1 | 0 | 2.6.1.8.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 1 | 8 | 1 | 1 | 2.6.2.1.8.1.1 | PMR For Stone Trap - W008N | BK-W008N-PEDCO-110-PI-MR-0008 | BK-W008N-PEDCO-110-PI-MR-0008 | BK | W008N | PEDCO | 110 | PI | MR | 0008 | F0Z-707886 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 8 | 2 | 0 | 2.6.1.8.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 8 | 2 | 1 | 2.6.2.1.8.2.1 | TBE For Stone Trap - W008N | BK-W008N-PEDCO-110-PI-TB-0008 | BK-W008N-PEDCO-110-PI-TB-0008 | BK | W008N | PEDCO | 110 | PI | TB | 0008 | F0Z-707887 | IFI | IFI | 44719 | 0 | 0 | -44719 | 0 | -44719 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-24 | 2022-05-24 |  | D00 | IFI | T-0996 | 2022-05-24 | 1401/03/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0996 | 2022-05-24 | 1401/03/03 | [37 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 9 | 0 | 0 | 2.6.2.1.9 | Pipe Support
2 | 6 | 2 | 1 | 9 | 1 | 0 | 2.6.1.9.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 1 | 9 | 1 | 1 | 2.6.2.1.9.1.1 | PMR For Pipe Support - W008N | BK-W008N-PEDCO-110-PI-MR-0009 | BK-W008N-PEDCO-110-PI-MR-0009 | BK | W008N | PEDCO | 110 | PI | MR | 0009 | F0Z-707888 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 1 | 9 | 2 | 0 | 2.6.1.9.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 1 | 9 | 2 | 1 | 2.6.2.1.9.2.1 | TBE For Pipe Support - W008N | BK-W008N-PEDCO-110-PI-TB-0009 | BK-W008N-PEDCO-110-PI-TB-0009 | BK | W008N | PEDCO | 110 | PI | TB | 0009 | F0Z-707889 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 2 | 0 | 0 | 0 | 2.6.2.2 | Pipeline
2 | 6 | 2 | 2 | 1 | 0 | 0 | 2.6.2.2.1 | Line Pipe
2 | 6 | 2 | 2 | 1 | 1 | 0 | 2.6.2.1.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 2 | 1 | 1 | 1 | 2.6.2.2.1.1.1 | PMR For Line Pipes - W008N | BK-W008N-PEDCO-110-PL-MR-0001 | BK-W008N-PEDCO-110-PL-MR-0001 | BK | W008N | PEDCO | 110 | PL | MR | 0001 | F0Z-707890 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 2 | 1 | 2 | 0 | 2.6.2.1.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 2 | 1 | 2 | 1 | 2.6.2.2.1.2.1 | TBE For Line Pipes - W008N | BK-W008N-PEDCO-110-PL-TB-0001 | BK-W008N-PEDCO-110-PL-TB-0001 | BK | W008N | PEDCO | 110 | PL | TB | 0001 | F0Z-707891 | IFI | IFI | 44625 | 44630 | 44634 | 5 | 4 | 9 | IFI | 44709 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 2022-05-14 |  | D01 | IFI | T-0944 | 2022-05-14 | 1401/02/24 | T-0944 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W035-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W008N-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0604 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PPL-00-03409 | 2022-03-08 | 1400/12/17 | C4-RJ | [6 empty] | 1400-2294-443269 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/23 | CM | [10 empty] | D01 | IFI | T-0944 | 2022-05-14 | 1401/02/24 | T-0944 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PL-TB-0001-D00 | [11 empty] | NISOC-CRS-BK-W008N-PEDCO-110-PL-TB-0001-D00
2 | 6 | 2 | 2 | 2 | 0 | 0 | 2.6.2.2.2 | Flow Line Support
2 | 6 | 2 | 2 | 2 | 1 | 0 | 2.6.2.2.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 2 | 2 | 1 | 1 | 2.6.2.2.2.1.1 | PMR For Flow Line Support - W008N | BK-W008N-PEDCO-110-PL-MR-0002 | BK-W008N-PEDCO-110-PL-MR-0002 | BK | W008N | PEDCO | 110 | PL | MR | 0002 | F0Z-707892 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 2 | 2 | 2 | 0 | 2.6.2.2.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 2 | 2 | 2 | 1 | 2.6.2.2.2.2.1 | TBE For Flow Line Support - W008N | BK-W008N-PEDCO-110-PL-TB-0002 | BK-W008N-PEDCO-110-PL-TB-0002 | BK | W008N | PEDCO | 110 | PL | TB | 0002 | F0Z-707893 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 3 | 0 | 0 | 0 | 2.6.2.3 | Control & Instrumentation
2 | 6 | 2 | 3 | 1 | 0 | 0 | 2.6.2.3.1 | WHCP/HPU
2 | 6 | 2 | 3 | 1 | 1 | 0 | 2.6.3.1.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 3 | 1 | 1 | 1 | 2.6.2.3.1.1.1 | PMR For WHCP/HPU - W008N | BK-W008N-PEDCO-110-IN-MR-0001 | BK-W008N-PEDCO-110-IN-MR-0001 | BK | W008N | PEDCO | 110 | IN | MR | 0001 | F0Z-707894 | IFI | IFI | 44529 | 44547 | 44537 | 18 | -10 | 8 | IFI | 44591 | 44592 | 44593 | 1 | 1 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 2022-01-16 |  | D01 | IFI | T-0470 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02865 | 2022-01-30 | 1400/11/10 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-390765 | 2022-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | NISOC-CRS-BK-W008N-PEDCO-110-IN-MR-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0243 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-INS-00-02170 | 2021-12-01 | 1400/09/10 | C4-RJ |  | BK-SUR-ENG-INS-00-02224 | 2021-12-07 | 1400/09/16 | CM-C3 |  | 1400-2294-320808 | 2021-12-17 | 1400/09/26 | 2021-12-07 | 1400/09/16 | CM | [10 empty] | D01 | IFI | T-0470 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02865 | 2022-01-30 | 1400/11/10 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-MR-0001_D00 | [5 empty] | 1400-2294-390765 | 2022-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | NISOC-CRS-BK-W008N-PEDCO-110-IN-MR-0001_D00
2 | 6 | 2 | 3 | 1 | 2 | 0 | 2.6.3.1.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 3 | 1 | 2 | 1 | 2.6.2.3.1.2.1 | TBE/TBA For WHCP/HPU - W008N | BK-W008N-PEDCO-110-IN-TB-0001 | BK-W008N-PEDCO-110-IN-TB-0001 | BK | W008N | PEDCO | 110 | IN | TB | 0001 | F0Z-707895 | IFI | IFI | 44545 | 44544 | 44545 | -1 | 1 | 0 | IFI | 44625 | 44655 | 44660 | 30 | 5 | 35 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-01 | 2022-02-19 |  | D01 | IFI | T-0602 | 2022-02-19 | 1400/11/30 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03345 | 2022-03-05 | 1400/12/15 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-TB-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-9652 | 2022-04-04 | 1401/01/15 | 2022-04-09 | 1401/01/20 | CM | NISOC-CRS-BK-W008N-PEDCO-110-IN-TB-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0286 | 2021-12-01 | 1400/09/10 |  |  |  | BK-SUR-ENG-INS-00-02297 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-317340 | 2021-12-14 | 1400/09/23 | 2021-12-15 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-0602 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-INS-00-03345 | 2022-03-05 | 1400/12/15 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-IN-TB-0001_D00 | [5 empty] | 1401-2294-9652 | 2022-04-04 | 1401/01/15 | 2022-04-09 | 1401/01/20 | CM | NISOC-CRS-BK-W008N-PEDCO-110-IN-TB-0001_D00
2 | 6 | 2 | 3 | 2 | 0 | 0 | 2.6.2.3.2 | Field Instrumentations
2 | 6 | 2 | 3 | 2 | 1 | 0 | 2.6.3.2.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 3 | 2 | 1 | 1 | 2.6.2.3.2.1.1 | PMR For Field Instrumentations - W008N | BK-W008N-PEDCO-110-IN-MR-0002 | BK-W008N-PEDCO-110-IN-MR-0002 | BK | W008N | PEDCO | 110 | IN | MR | 0002 | F0Z-707896 | IFI | IFI | 44557 | 44582 | 44221 | 25 | -361 | -336 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 2021-12-13 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | 1400/10/06 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-330276 | 2022-01-21 | 1400/11/01 | 2021-01-25 | 1400/11/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0334 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | 1400/10/06 | CM-C3 | [6 empty] | 1400-2294-330276 | 2022-01-21 | 1400/11/01 | 2021-01-25 | 1400/11/05 | CM | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 3 | 2 | 2 | 0 | 2.6.3.2.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 3 | 2 | 2 | 1 | 2.6.2.3.2.2.1 | TBE/TBA For Field Instrumentations - W008N | BK-W008N-PEDCO-110-IN-TB-0002 | BK-W008N-PEDCO-110-IN-TB-0002 | BK | W008N | PEDCO | 110 | IN | TB | 0002 | F0Z-707897 | IFI | IFI | 44723 | 0 | 0 | -44723 | 0 | -44723 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-28 | 2022-05-28 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1012 | 2022-05-28 | 1401/03/07 | [37 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 3 | 3 | 0 | 0 | 2.6.2.3.3 | Instrument Bulk Items
2 | 6 | 2 | 3 | 3 | 1 | 0 | 2.6.3.3.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 3 | 3 | 1 | 1 | 2.6.2.3.3.1.1 | PMR For Instrument Bulk Items - W008N | BK-W008N-PEDCO-110-IN-MR-0003 | BK-W008N-PEDCO-110-IN-MR-0003 | BK | W008N | PEDCO | 110 | IN | MR | 0003 | F0Z-707898 | IFI | IFI | 44591 | 44227 | 44593 | -364 | 366 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-16 | 2022-01-16 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C2 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 3 | 3 | 2 | 0 | 2.6.3.3.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 3 | 3 | 2 | 1 | 2.6.2.3.3.2.1 | TBE/TBA For Instrument Bulk Items-W008N | BK-W008N-PEDCO-110-IN-TB-0003 | BK-W008N-PEDCO-110-IN-TB-0003 | BK | W008N | PEDCO | 110 | IN | TB | 0003 | F0Z-707899 | IFI | IFI | 44608 | 44639 | 44634 | 31 | -5 | 26 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 2022-02-02 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03068 | 2022-02-14 | 1400/11/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443275 | 2022-03-19 | 1400/12/19 | 2022-03-14 | 1400/12/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0539 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03068 | 2022-02-14 | 1400/11/25 | CM-C2 | [6 empty] | 1400-2294-443275 | 2022-03-19 | 1400/12/19 | 2022-03-14 | 1400/12/23 | CM
2 | 6 | 2 | 4 | 0 | 0 | 0 | 2.6.2.4 | Safety & Fire Fighting
2 | 6 | 2 | 4 | 1 | 0 | 0 | 2.6.2.4.1 | Fire Fighting and Safety Equipment
2 | 6 | 2 | 4 | 1 | 1 | 0 | 2.6.4.1.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 4 | 1 | 1 | 1 | 2.6.2.4.1.1.1 | PMR For Fire Fighting and Safety Equipment - W008N | BK-W008N-PEDCO-110-SA-MR-0001 | BK-W008N-PEDCO-110-SA-MR-0001 | BK | W008N | PEDCO | 110 | SA | MR | 0001 | F0Z-707900 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 4 | 1 | 2 | 0 | 2.6.4.1.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 4 | 1 | 2 | 1 | 2.6.2.4.1.2.1 | TBE For Fire Fighting and Safety Equipment - W008N | BK-W008N-PEDCO-110-SA-TB-0001 | BK-W008N-PEDCO-110-SA-TB-0001 | BK | W008N | PEDCO | 110 | SA | TB | 0001 | F0Z-707901 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 4 | 2 | 0 | 0 | 2.6.2.4.2 | Safety Sign
2 | 6 | 2 | 4 | 2 | 1 | 0 | 2.6.4.2.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 4 | 2 | 1 | 1 | 2.6.2.4.2.1.1 | PMR For Fire Safety Sign - W008N | BK-W008N-PEDCO-110-SA-MR-0002 | BK-W008N-PEDCO-110-SA-MR-0002 | BK | W008N | PEDCO | 110 | SA | MR | 0002 | F0Z-707902 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 4 | 2 | 2 | 0 | 2.6.4.2.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 4 | 2 | 2 | 1 | 2.6.2.4.2.2.1 | TBE For Fire Safety Sign - W008N | BK-W008N-PEDCO-110-SA-TB-0002 | BK-W008N-PEDCO-110-SA-TB-0002 | BK | W008N | PEDCO | 110 | SA | TB | 0002 | F0Z-707903 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 5 | 0 | 0 | 0 | 2.6.2.5 | Structure
2 | 6 | 2 | 5 | 1 | 0 | 0 | 2.6.2.5.1 | Steel Structure Items
2 | 6 | 2 | 5 | 1 | 1 | 0 | 2.6.5.1.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 5 | 1 | 1 | 1 | 2.6.2.5.1.1.1 | PMR For Steel Structure Items - W008N | BK-W008N-PEDCO-110-ST-MR-0001 | BK-W008N-PEDCO-110-ST-MR-0001 | BK | W008N | PEDCO | 110 | ST | MR | 0001 | F0Z-707904 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 5 | 1 | 2 | 0 | 2.6.5.1.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 5 | 1 | 2 | 1 | 2.6.2.5.1.2.1 | TBE For Steel Structure Items - W008N | BK-W008N-PEDCO-110-ST-TB-0001 | BK-W008N-PEDCO-110-ST-TB-0001 | BK | W008N | PEDCO | 110 | ST | TB | 0001 | F0Z-707905 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 5 | 2 | 0 | 0 | 2.6.2.5.2 | Anchor Bolts
2 | 6 | 2 | 5 | 2 | 1 | 0 | 2.6.5.2.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 5 | 2 | 1 | 1 | 2.6.2.5.2.1.1 | PMR For Anchor Bolts - W008N | BK-W008N-PEDCO-110-ST-MR-0002 | BK-W008N-PEDCO-110-ST-MR-0002 | BK | W008N | PEDCO | 110 | ST | MR | 0002 | F0Z-707906 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 5 | 2 | 2 | 0 | 2.6.5.2.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 5 | 2 | 2 | 1 | 2.6.2.5.2.2.1 | TBE For Anchor Bolts - W008N | BK-W008N-PEDCO-110-ST-TB-0002 | BK-W008N-PEDCO-110-ST-TB-0002 | BK | W008N | PEDCO | 110 | ST | TB | 0002 | F0Z-707907 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 6 | 0 | 0 | 0 | 2.6.2.6 | Civil
2 | 6 | 2 | 6 | 1 | 0 | 0 | 2.6.2.6.1 | Geomembrane
2 | 6 | 2 | 6 | 1 | 1 | 0 | 2.6.6.1.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 6 | 1 | 1 | 1 | 2.6.2.6.1.1.1 | PMR For Geomembrane - W008N | BK-W008N-PEDCO-110-CV-MR-0001 | BK-W008N-PEDCO-110-CV-MR-0001 | BK | W008N | PEDCO | 110 | CV | MR | 0001 | F0Z-707908 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 6 | 1 | 2 | 0 | 2.6.6.1.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 6 | 1 | 2 | 1 | 2.6.2.6.1.2.1 | TBE For Geomembrane - W008N | BK-W008N-PEDCO-110-CV-TB-0001 | BK-W008N-PEDCO-110-CV-TB-0001 | BK | W008N | PEDCO | 110 | CV | TB | 0001 | F0Z-707909 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 7 | 0 | 0 | 0 | 2.6.2.7 | Geotextile
2 | 6 | 2 | 7 | 0 | 1 | 0 | 2.6.2.7.1 | Purchase Material Requisition (PMR)
2 | 6 | 2 | 7 | 0 | 1 | 1 | 2.6.2.7.1.1 | PMR For Geotextile - W008N | BK-W008N-PEDCO-110-CV-MR-0002 | BK-W008N-PEDCO-110-CV-MR-0002 | BK | W008N | PEDCO | 110 | CV | MR | 0002 | F0Z-707910 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 2 | 7 | 0 | 2 | 0 | 2.6.2.7.2 | Technical Bid Evaluation (TBE)
2 | 6 | 2 | 7 | 0 | 2 | 1 | 2.6.2.7.2.1 | TBE For Geotextile - W008N | BK-W008N-PEDCO-110-CV-TB-0002 | BK-W008N-PEDCO-110-CV-TB-0002 | BK | W008N | PEDCO | 110 | CV | TB | 0002 | F0Z-707911 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 3 | 0 | 0 | 0 | 0 | 2.6.3 | Commissioning Engineering
2 | 6 | 3 | 0 | 0 | 1 | 0 | 2.6.3.1 | Procedure/Plan
2 | 6 | 3 | 0 | 0 | 1 | 1 | 2.6.3.1.1 | Pre-Commissioning, Commissioning & Startup Procedure - W008N | BK-W008N-PEDCO-110-CO-PR-0001 | BK-W008N-PEDCO-110-CO-PR-0001 | BK | W008N | PEDCO | 110 | CO | PR | 0001 | F0Z-707912 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 4 | 0 | 0 | 0 | 0 | 2.6.4 | Field Engineering
2 | 6 | 4 | 0 | 0 | 1 | 0 | 2.6.4.1 | Query
2 | 6 | 4 | 0 | 0 | 1 | 1 | 2.6.4.1.1 | Technical/Site Queries | BK-W008N-PEDCO-110-GE-TQ-0001 | BK-W008N-PEDCO-110-GE-TQ-0001 | BK | W008N | PEDCO | 110 | GE | TQ | 0001 | F7Z-707913 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 4 | 0 | 0 | 2 | 0 | 2.6.4.2 | Dossier
2 | 6 | 4 | 0 | 0 | 2 | 1 | 2.6.4.2.1 | As-Built Document Booklets - W008N | BK-W008N-PEDCO-110-GE-DO-0001 | BK-W008N-PEDCO-110-GE-DO-0001 | BK | W008N | PEDCO | 110 | GE | DO | 0001 | F0Z-707914 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 5 | 0 | 0 | 0 | 0 | 2.6.5 | Engineering Final Documentation
2 | 6 | 5 | 0 | 1 | 0 | 0 | 2.6.5.1 | Manual
2 | 6 | 5 | 0 | 1 | 0 | 1 | 2.6.5.1.1 | Operating Manual - W008N | BK-W008N-PEDCO-110-GE-ML-0001 | BK-W008N-PEDCO-110-GE-ML-0001 | BK | W008N | PEDCO | 110 | GE | ML | 0001 | F0Z-707915 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 5 | 0 | 2 | 0 | 0 | 2.6.5.2 | Dossier
2 | 6 | 5 | 0 | 2 | 0 | 1 | 2.6 | As-Built Document Booklets - W008N | BK-W008N-PEDCO-110-GE-DO-0001 | BK-W008N-PEDCO-110-GE-DO-0001 | [7 empty] | F0Z-707914 | [43 empty] | Moved to Field | 0 | [78 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 6 | 5 | 0 | 2 | 0 | 2 | 2.6 | Final Engineering Dossier - W008N | BK-W008N-PEDCO-110-GE-DO-0002 | BK-W008N-PEDCO-110-GE-DO-0002 | BK | W008N | PEDCO | 110 | GE | DO | 0002 | F0Z-707916 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 7 | 0 | 0 | 0 | 0 | 0 | 2.7 | Package 06-New Well # W007S/Manifold Extension (Bangestan)
2 | 7 | 1 | 0 | 0 | 0 | 0 | 2.7.1 | Detail Design
2 | 7 | 1 | 1 | 0 | 0 | 0 | 2.7.1.1 | Process
2 | 7 | 1 | 1 | 1 | 0 | 0 | 2.7.1.1.1 | Description
2 | 7 | 1 | 1 | 1 | 0 | 1 | 2.7.1.1.1 | Process Description - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-DP-0001 | BK-W007S-PEDCO-110-PR-DP-0001 | BK | W007S | PEDCO | 110 | PR | DP | 0001 | F0Z-707917 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 7 | 1 | 1 | 2 | 0 | 0 | 2.7.1.1.2 | Calculation
2 | 7 | 1 | 1 | 2 | 0 | 1 | 2.7.1.1.2 | Calculation book for (CV,PSV,Pump & Line sizing) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-CN-0001 | BK-W007S-PEDCO-110-PR-CN-0001 | BK | W007S | PEDCO | 110 | PR | CN | 0001 | F0Z-707918 | AFD | IFC | 44629 | 44632 | 44634 | 3 | 2 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-23 | 0 |  | D00 | IFC | T-0628 | 2022-02-23 | 1400/12/04 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03421 | 2022-03-09 | 1400/12/18 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445285 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0628 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-PCS-00-03421 | 2022-03-09 | 1400/12/18 | CM-C3 | [6 empty] | 1400-2294-445285 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/24 | CM | [18 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 7 | 1 | 1 | 3 | 0 | 0 | 2.7.1.1.3 | Drawing/Diagram
2 | 7 | 1 | 1 | 3 | 0 | 1 | 2.7.1.1.3 | ESD Block Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-DG-0001 | BK-W007S-PEDCO-110-PR-DG-0001 | BK | W007S | PEDCO | 110 | PR | DG | 0001 | F2A-707919 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 7 | 1 | 1 | 3 | 0 | 2 | 2.7.1.1.3 | Process Flow Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-PF-0001 | BK-W007S-PEDCO-110-PR-PF-0001 | BK | W007S | PEDCO | 110 | PR | PF | 0001 | F2A-707920 | AFC | IFC | 2021-08-23 | 2021-08-30 | 2021-09-06 | 7 | 7 | 14 | IFC | 2021-11-15 | 2021-11-14 | 2021-11-17 | -1 | 3 | 2 | IFA | 2022-05-01 | 2022-05-12 | 2022-05-16 | 11 | 4 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-01 | 0 |  | D02 | IFA | T-0831 | 2022-04-17 | 1401/01/28 | 0 | 0 | 0 | BK-SUR-ENG-STR-01-04053 | 2022-04-26 | 1401/02/06 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D01 | BK-SUR-ENG-PCS-01-04104 | 2022-05-01 | 1401/02/11 | CM-C3 | 0 | 1401-2294-59523 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0036 | 2021-08-09 | 1400/05/18 |  |  |  | BK-SUR-ENG-PCS-00-01410 | 2021-08-25 | 1400/06/03 | CM-C3 | [6 empty] | 1400/2294/179419 | 2021-08-30 | 1400/06/08 | 2021-09-06 | 1400/06/15 | RJ | [10 empty] | D01 | IFC | T-0198 | 2021-11-01 | 1400/08/10 |  |  |  | BK-SUR-ENG-PCS-00-02015 | 2021-11-15 | 1400/08/24 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D00 | [5 empty] | 1400-2294-275268 | 2021-11-14 | 1400/08/23 | 2021-11-17 | 1400/08/26 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D00 | [9 empty] | D02 | IFA | T-0831 | 2022-04-17 | 1401/01/28 |  |  |  | BK-SUR-ENG-STR-01-04053 | 2022-04-26 | 1401/02/06 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D01 | BK-SUR-ENG-PCS-01-04104 | 2022-05-01 | 1401/02/11 | CM-C3 |  | 1401-2294-59523 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D01
2 | 7 | 1 | 1 | 3 | 0 | 3 | 2.7.1.1.3 | P&ID - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-PI-0001 | BK-W007S-PEDCO-110-PR-PI-0001 | BK | W007S | PEDCO | 110 | PR | PI | 0001 | F2A-707921 | AFC | IFC | 2021-11-09 | 2021-11-28 | 2021-11-14 | 19 | -14 | 5 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-26 | 0 |  | D01 | IFA | T-0653 | 2022-02-28 | 1400/12/09 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | 0 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0186 | 2021-10-26 | 1400/08/04 |  |  |  | BK-SUR-ENG-PCS-00-01976 | 2021-11-13 | 1400/08/22 | CM-C3 | [6 empty] | 1400-2294-271311 | 2021-11-11 | 1400/08/20 | 2021-11-14 | 1400/08/23 | CM |  | 1400-2290-294882 | 2021-11-28 | 1400/09/07 |  |  | CM |  |  |  | D01 | IFA | T-0653 | 2022-02-28 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 |  | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0001_D00
2 | 7 | 1 | 1 | 3 | 0 | 4 | 2.7.1.1.3 | Cause & Effect Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-DG-0002 | BK-W007S-PEDCO-110-PR-DG-0002 | BK | W007S | PEDCO | 110 | PR | DG | 0002 | F2A-707922 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 | [77 empty] | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29
2 | 7 | 1 | 1 | 3 | 0 | 5 | 2.7.1.1.3 | Process Flow Diagram - W007S | BK-W007S-PEDCO-110-PR-PF-0002 | BK-W007S-PEDCO-110-PR-PF-0002 | BK | W007S | PEDCO | 110 | PR | PF | 0002 | F2A-707923 | AFC | IFC | 2021-09-07 | 2021-09-02 | 2021-09-07 | -5 | 5 | 0 | IFC | 2021-11-16 | 0 | 0 | -44516 | 0 | -44516 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-02 | 0 |  | D01 | IFC | T-0205 | 2021-11-02 | 1400/08/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PF-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-PR-PF-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0063 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PCS-00-01417 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2290/182828 | 2021-09-02 | 1400/06/11 | 2021-09-07 | 1400/06/16 | RJ | [10 empty] | D01 | IFC | T-0205 | 2021-11-02 | 1400/08/11 | [7 empty] | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PF-0002_D00 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-PR-PF-0002_D00
2 | 7 | 1 | 1 | 3 | 0 | 6 | 2.7.1.1.3 | P&ID - W007S | BK-W007S-PEDCO-110-PR-PI-0002 | BK-W007S-PEDCO-110-PR-PI-0002 | BK | W007S | PEDCO | 110 | PR | PI | 0002 | F2A-707924 | AFC | IFC | 2021-09-07 | 2021-09-02 | 2021-09-07 | -5 | 5 | 0 | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-01 | 0 |  | D03 | IFA | T-0653 | 2022-02-28 | 1400/12/09 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0063 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PCS-00-01417 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2290/182828 | 2021-09-02 | 1400/06/11 | 2021-09-07 | 1400/06/16 | RJ | [10 empty] | D01 | IFC | T-0201 | 2021-11-01 | 1400/08/10 |  |  |  | BK-SUR-ENG-PCS-00-02050 | 2021-11-20 | 1400/08/29 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0002_D00 | [5 empty] | 1400-2294-279084 | 2021-11-16 | 1400/08/25 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0002_D00 | [9 empty] | D02 | IFA | T-0345 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-PCS-00-02540 | 2022-01-03 | 1400/10/13 | CM-C3 | PEDCO-BK-W007S-PEDCO-110-PR-PI-0002_D01 | [5 empty] | 1400-2294-342085 | 2021-12-30 | 1400/10/09 | 2022-01-03 | 1400/10/13 | RJ | NISOC-BK-W007S-PEDCO-110-PR-PI-0002_D01 | [9 empty] | D03 | IFA | T-0653 | 2022-02-28 | 1400/12/09 |  |  |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0002_D02 | [5 empty] | 1401-2294-43153 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0002_D02
2 | 7 | 1 | 1 | 3 | 0 | 7 | 2.7.1.1.3 | P&ID for Diesel Oil Drum- W007S | BK-W007S-PEDCO-110-PR-PI-0003 | BK-W007S-PEDCO-110-PR-PI-0003 | BK | W007S | PEDCO | 110 | PR | PI | 0003 | F2A-707925 | AFC | IFC | 2021-11-30 | 2021-12-01 | 2021-12-06 | 1 | 5 | 6 | IFA | 2022-01-17 | 2022-02-08 | 2022-02-12 | 22 | 4 | 26 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 0 | 0 | -44675 | 0 | -44675 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-16 | 0 |  | D03 | IFA | T-0794 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03985 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0242 | 2021-11-16 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02160 | 2021-11-30 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300481 | 2021-12-01 | 1400/09/10 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0423 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02778 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D00 | [5 empty] | 1400-2294-402841 | 2022-02-08 | 1400/11/19 | 2022-02-12 | 1400/11/23 | AP | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D00 | [9 empty] | D02 | IFA | T-0649 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03591 | 2022-03-14 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D01 | [5 empty] | 1400-2294-443282 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/24 | RJ | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D01 | [9 empty] | D03 | IFA | T-0794 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03985 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D02 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0003_D02
2 | 7 | 1 | 1 | 3 | 0 | 8 | 2.7.1.1.3 | P&ID for Potable Water Tank - W007S | BK-W007S-PEDCO-110-PR-PI-0004 | BK-W007S-PEDCO-110-PR-PI-0004 | BK | W007S | PEDCO | 110 | PR | PI | 0004 | F2A-707926 | AFC | IFC | 2021-11-30 | 2021-12-01 | 2021-12-06 | 1 | 5 | 6 | IFA | 2022-01-17 | 2022-02-08 | 2022-02-12 | 22 | 4 | 26 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 0 | 0 | -44675 | 0 | -44675 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-16 | 0 |  | D03 | IFA | T-0794 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03985 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0242 | 2021-11-16 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02160 | 2021-11-30 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300481 | 2021-12-01 | 1400/09/10 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0423 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02778 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D00 | [5 empty] | 1400-2294-402841 | 2022-02-08 | 1400/11/19 | 2022-02-12 | 1400/11/23 | AP | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D00 | [9 empty] | D02 | IFA | T-0649 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03591 | 2022-03-14 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D01 | [5 empty] | 1400-2294-443282 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/24 | RJ | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D01 | [9 empty] | D03 | IFA | T-0794 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03985 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D02 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0004_D02
2 | 7 | 1 | 1 | 4 | 0 | 0 | 2.7.1.1.4 | List | [134 empty] | 2021-11-20 | 1400/08/29
2 | 7 | 1 | 1 | 4 | 0 | 1 | 2.7.1.1.4 | Line List - W007S & Manifold Extension | BK-W007S-PEDCO-110-PR-LI-0001 | BK-W007S-PEDCO-110-PR-LI-0001 | BK | W007S | PEDCO | 110 | PR | LI | 0001 | F0Z-707927 | AFC | IFC | 2022-05-04 | 2022-05-21 | 2022-05-23 | 17 | 2 | 19 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-20 | 0 |  | D00 | IFC | T-0848 | 2022-04-20 | 1401/01/31 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | 1401/02/31 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70086 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0848 | 2022-04-20 | 1401/01/31 |  |  |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | 1401/02/31 | CM-C3 | [6 empty] | 1401-2294-70086 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | [19 empty] | 2021-11-20 | 1400/08/29
2 | 7 | 1 | 1 | 4 | 0 | 2 | 2.7.1.1.4 | Tie-In List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PR-LI-0002 | BK-W007S-PEDCO-110-PR-LI-0002 | BK | W007S | PEDCO | 110 | PR | LI | 0002 | F0Z-707928 | AFC | IFC | 2022-05-04 | 2022-05-21 | 2022-05-23 | 17 | 2 | 19 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-20 | 0 |  | D00 | IFC | T-0848 | 2022-04-20 | 1401/01/31 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | 1401/02/31 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70086 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0848 | 2022-04-20 | 1401/01/31 |  |  |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | 1401/02/31 | CM-C3 | [6 empty] | 1401-2294-70086 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | [19 empty] | 2021-11-20 | 1400/08/29
2 | 7 | 1 | 1 | 4 | 0 | 3 | 2.7.1.1.4 | Line List - W007S | BK-W007S-PEDCO-110-PR-LI-0003 | BK-W007S-PEDCO-110-PR-LI-0003 | BK | W007S | PEDCO | 110 | PR | LI | 0003 | F0Z-707929 | AFC | IFC | 2021-09-07 | 2021-09-02 | 2021-09-07 | -5 | 5 | 0 | IFC | 2021-11-22 | 2021-11-27 | 2021-11-29 | 5 | 2 | 7 | IFA | 2022-01-12 | 0 | 0 | -44573 | 0 | -44573 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-08 | 0 |  | D02 | IFA | T-0403 | 2021-12-29 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-LI-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-PR-LI-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0063 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-PCS-00-01417 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2290/182828 | 2021-09-02 | 1400/06/11 | 2021-09-07 | 1400/06/16 | RJ | [10 empty] | D01 | IFC | T-0217 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PCS-00-02051 | 2021-11-20 | 1400/08/29 | CM-C2 | PEDCO-CRS-D01-BK-W007S-PEDCO-110-PR-LI-0003_D00 | [5 empty] | 1400-2290-293083 | 2021-11-27 | 1400/09/06 | 2021-11-29 | 1400/09/08 | CM | NISOC-CRS-D01-BK-W007S-PEDCO-110-PR-LI-0003_D00 | [9 empty] | D02 | IFA | T-0403 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-LI-0003_D01 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-PR-LI-0003_D01
2 | 7 | 1 | 1 | 5 | 0 | 0 | 2.7.1.1.5 | Report | [145 empty] | 1400/09/06
2 | 7 | 1 | 1 | 5 | 0 | 1 | 2.7.1.1.5 | Flow line Hydraulic Calculation Report | BK-W007S-PEDCO-110-PR-RT-0001 | BK-W007S-PEDCO-110-PR-RT-0001 | BK | W007S | PEDCO | 110 | PR | RT | 0001 | F0Z-707930 | AFC | IFC | 44513 | 44514 | 44517 | 1 | 3 | 4 | IFA | 44576 | 44228 | 44597 | -348 | 369 | 21 | IFA | 44628 | 44630 | 44633 | 2 | 3 | 5 | IFA | 44695 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-30 | 0 |  | D03 | IFA | T-0878 | 2022-04-30 | 1401/02/10 | T-0878 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 2022-05-28 | 1402/03/07 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0197 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-PCS-00-01993 | 2021-11-14 | 1400/08/23 | CM-C3 | [6 empty] | 1400-2294-275250 | 2021-11-14 | 1400/08/23 | 2021-11-17 | 1400/08/26 | CM | [10 empty] | D01 | IFA | T-0413 | 2022-01-01 | 1400/10/11 |  |  |  | BK-SUR-ENG-PCS-00-02735 | 2022-01-19 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D00 | [5 empty] | 1400-2294-392131 | 2021-02-01 | 1400/11/12 | 2022-02-05 | 1400/11/16 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-0627 | 2022-02-22 | 1400/12/03 |  |  |  | BK-SUR-ENG-PCS-00-03387 | 2022-03-07 | 1400/12/17 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D01 | [5 empty] | 1400-2294-443285 | 2022-03-10 | 1400/12/19 | 2022-03-13 | 1400/12/22 | CM | NISOC-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D01 | [9 empty] | D03 | IFA | T-0878 | 2022-04-30 | 1401/02/10 | T-0878 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04444 | 2022-05-28 | 1402/03/07 | CM-C2 | PEDCO-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D02 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-PR-RT-0001_D02
2 | 7 | 1 | 1 | 6 | 0 | 0 | 2.7.1.1.6 | Data Sheet
2 | 7 | 1 | 1 | 6 | 0 | 1 | 2.7.1.1 | Process Data Sheets For Instrument Devices - W007S & Extension Manifold | BK-W007S-PEDCO-110-PR-DT-0001 | BK-W007S-PEDCO-110-PR-DT-0001 | BK | W007S | PEDCO | 110 | PR | DT | 0001 | F0Z-707931 | AFC | IFC | 44677 | 44689 | 44695 | 12 | 6 | 18 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-12 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04093 | 2022-04-30 | 1401/02/10 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 2022-05-14 | 1401/02/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0808 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-PCS-01-04093 | 2022-04-30 | 1401/02/10 | CM-C2 | [6 empty] | 1401-2294-52764 | 2022-05-08 | 1401/02/18 | 2022-05-14 | 1401/02/24 | CM
2 | 7 | 1 | 2 | 0 | 0 | 0 | 2.7.1.2 | Mechanical
2 | 7 | 1 | 2 | 1 | 0 | 0 | 2.7.1.2.1 | Specification
2 | 7 | 1 | 2 | 1 | 0 | 1 | 2.7.1.2.1 | Specification For Positive Displacement Rotary Pumps | BK-W007S-PEDCO-110-ME-SP-0001 | BK-W007S-PEDCO-110-ME-SP-0001 | BK | W007S | PEDCO | 110 | ME | SP | 0001 | F0Z-707932 | AFD | IFC | 44627 | 44657 | 44664 | 30 | 7 | 37 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-21 | 0 |  | D00 | IFC | T-0614 | 2022-02-21 | 1400/11/02 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03504 | 2022-03-13 | 1400/12/22 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-13623 | 2022-04-06 | 1401/01/17 | 2022-04-13 | 1401/01/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0614 | 2022-02-21 | 1400/11/02 |  |  |  | BK-SUR-ENG-MEC-00-03504 | 2022-03-13 | 1400/12/22 | CM-C3 | [6 empty] | 1401-2294-13623 | 2022-04-06 | 1401/01/17 | 2022-04-13 | 1401/01/24 | AP
2 | 7 | 1 | 2 | 2 | 0 | 0 | 2.7.1.2.2 | Data Sheets
2 | 7 | 1 | 2 | 2 | 1 | 0 | 2.7.2.2.1 | Rotary Equipment
2 | 7 | 1 | 2 | 2 | 1 | 1 | 2.7.1.2.2.1.1 | Data Sheets For Oil Sump Pump - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ME-DT-0001 | BK-W007S-PEDCO-110-ME-DT-0001 | BK | W007S | PEDCO | 110 | ME | DT | 0001 | F0Z-707933 | AFC | IFC | 44648 | 44648 | 44655 | 0 | 7 | 7 | IFA | 44675 | 44681 | 44688 | 6 | 7 | 13 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-14 | 0 |  | D01 | IFA | T-0799 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-03921 | 2022-04-16 | 1401/01/27 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-45436 | 2022-04-30 | 1401/02/10 | 2022-05-07 | 1401/02/17 | CM | NISOC-CRS-BK-W007S-PEDCO-110-ME-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0730 | 2022-03-14 | 1400/12/12 |  |  |  | BK-SUR-ENG-MEC-01-03941 | 2022-04-16 | 1401/01/27 | CM-C3 | [6 empty] | 1401-2294-4004 | 2022-03-28 | 1401/01/08 | 2022-04-04 | 1401/01/15 | CM | [10 empty] | D01 | IFA | T-0799 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-MEC-01-03921 | 2022-04-16 | 1401/01/27 | CM-C3 | [6 empty] | 1401-2294-45436 | 2022-04-30 | 1401/02/10 | 2022-05-07 | 1401/02/17 | CM | NISOC-CRS-BK-W007S-PEDCO-110-ME-DT-0001_D00
2 | 7 | 1 | 3 | 0 | 0 | 0 | 2.7.1.3 | HVAC/Plumbing
2 | 7 | 1 | 3 | 1 | 0 | 0 | 2.7.1.3.1 | Calculation
2 | 7 | 1 | 3 | 1 | 0 | 1 | 2.7.1.3.1 | HVAC Calculation Note For Switchgear Building - W007S | BK-W007S-PEDCO-110-HV-CN-0001 | BK-W007S-PEDCO-110-HV-CN-0001 | BK | W007S | PEDCO | 110 | HV | CN | 0001 | F0Z-707934 | AFD | IFC | 2022-04-18 | 2022-04-12 | 2022-04-18 | -6 | 6 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-04 | 0 |  | D00 | IFC | T-0773 | 2022-04-04 | 1401/01/15 | 0 | 0 | 0 | BK-SUR-ENG-HVC-01-03863 | 2022-04-11 | 1401/01/22 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-20740 | 2022-04-12 | 1401/01/23 | 2022-04-18 | 1401/01/29 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0773 | 2022-04-04 | 1401/01/15 |  |  |  | BK-SUR-ENG-HVC-01-03863 | 2022-04-11 | 1401/01/22 | CM-C3 | [6 empty] | 1401-2294-20740 | 2022-04-12 | 1401/01/23 | 2022-04-18 | 1401/01/29 | CM
2 | 7 | 1 | 3 | 1 | 0 | 2 | 2.7.1.3.1 | HVAC Calculation Note For Security Building - W007S | BK-W007S-PEDCO-110-HV-CN-0002 | BK-W007S-PEDCO-110-HV-CN-0002 | BK | W007S | PEDCO | 110 | HV | CN | 0002 | F0Z-707935 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 3 | 2 | 0 | 0 | 2.7.1.3.2 | Data Sheets
2 | 7 | 1 | 3 | 2 | 0 | 1 | 2.7.1.3.2 | Data Sheets For Main HVAC Equipment - W007S | BK-W007S-PEDCO-110-HV-DT-0001 | BK-W007S-PEDCO-110-HV-DT-0001 | BK | W007S | PEDCO | 110 | HV | DT | 0001 | F0Z-707936 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 3 | 3 | 0 | 0 | 2.7.1.3.3 | Drawing/Diagram
2 | 7 | 1 | 3 | 3 | 0 | 1 | 2.7.1.3.3 | HVAC System Layout For Switchgear Building - W007S | BK-W007S-PEDCO-110-HV-PY-0001 | BK-W007S-PEDCO-110-HV-PY-0001 | BK | W007S | PEDCO | 110 | HV | PY | 0001 | F4B-707937 | AFC | IFC | 2022-05-03 | 2022-04-30 | 2022-05-01 | -3 | 1 | -2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-19 | 0 |  | D00 | IFC | T-0846 | 2022-04-19 | 1401/01/30 | 0 | 0 | 0 | BK-SUR-ENG-HVC-01-04149 | 2022-05-07 | 1401/02/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43977 | 2022-04-30 | 1401/02/10 | 2022-05-01 | 1401/02/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0846 | 2022-04-19 | 1401/01/30 |  |  |  | BK-SUR-ENG-HVC-01-04149 | 2022-05-07 | 1401/02/17 | CM-C3 | [6 empty] | 1401-2294-43977 | 2022-04-30 | 1401/02/10 | 2022-05-01 | 1401/02/11 | CM
2 | 7 | 1 | 3 | 3 | 0 | 2 | 2.7.1.3.3 | HVAC System Layout For Security Building - W007S | BK-W007S-PEDCO-110-HV-PY-0002 | BK-W007S-PEDCO-110-HV-PY-0002 | BK | W007S | PEDCO | 110 | HV | PY | 0002 | F4B-707938 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 3 | 3 | 0 | 3 | 2.7.1.3.3 | Plumbing & Sewage Piping Layout For Switchgear Building - W007S | BK-W007S-PEDCO-110-HV-PY-0003 | BK-W007S-PEDCO-110-HV-PY-0003 | BK | W007S | PEDCO | 110 | HV | PY | 0003 | F4B-707939 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 3 | 3 | 0 | 4 | 2.7.1.3.3 | Plumbing & Sewage Piping Layout For Security Building - W007S | BK-W007S-PEDCO-110-HV-PY-0004 | BK-W007S-PEDCO-110-HV-PY-0004 | BK | W007S | PEDCO | 110 | HV | PY | 0004 | F4B-707940 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 3 | 4 | 0 | 0 | 2.7.1.3.4 | MTO
2 | 7 | 1 | 3 | 4 | 0 | 1 | 2.7.1.3 | MTO For Building HVAC & Plumbing Systems - W007S | BK-W007S-PEDCO-110-HV-MT-0001 | BK-W007S-PEDCO-110-HV-MT-0001 | BK | W007S | PEDCO | 110 | HV | MT | 0001 | F8Z-707941 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 0 | 0 | 0 | 2.7.1.4 | Piping
2 | 7 | 1 | 4 | 1 | 0 | 0 | 2.7.1.4.1 | Drawing/Diagram
2 | 7 | 1 | 4 | 1 | 0 | 1 | 2.7.1.4.1 | Plot Plan Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-PY-0001 | BK-W007S-PEDCO-110-PI-PY-0001 | BK | W007S | PEDCO | 110 | PI | PY | 0001 | F5A-707942 | AFC | IFC | 2022-01-29 | 2022-02-04 | 2022-02-08 | 6 | 4 | 10 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-15 | 0 |  | D00 | IFC | T-0458 | 2022-01-15 | 1400/10/25 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02800 | 2022-01-24 | 1400/11/04 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-395124 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0458 | 2022-01-15 | 1400/10/25 |  |  |  | BK-SUR-ENG-PIP-00-02800 | 2022-01-24 | 1400/11/04 | C4-RJ | [6 empty] | 1400-2294-395124 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | CM
2 | 7 | 1 | 4 | 1 | 0 | 2 | 2.7.1.4.1 | Piping Plan Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-DW-0001 | BK-W007S-PEDCO-110-PI-DW-0001 | BK | W007S | PEDCO | 110 | PI | DW | 0001 | F4L-707943 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 1 | 0 | 3 | 2.7.1.4.1 | Isometric Drawings - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-DW-0002 | BK-W007S-PEDCO-110-PI-DW-0002 | BK | W007S | PEDCO | 110 | PI | DW | 0002 | F2L-707944 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 1 | 0 | 4 | 2.7.1.4.1 | Plot Plan Drawing - W007S | BK-W007S-PEDCO-110-PI-PY-0002 | BK-W007S-PEDCO-110-PI-PY-0002 | BK | W007S | PEDCO | 110 | PI | PY | 0002 | F5A-707945 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 1 | 0 | 5 | 2.7.1.4.1 | Piping Plan - W007S | BK-W007S-PEDCO-110-PI-DW-0003 | BK-W007S-PEDCO-110-PI-DW-0003 | BK | W007S | PEDCO | 110 | PI | DW | 0003 | F4L-707946 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 1 | 0 | 6 | 2.7.1.4.1 | Isometric Drawings - W007S | BK-W007S-PEDCO-110-PI-DW-0004 | BK-W007S-PEDCO-110-PI-DW-0004 | BK | W007S | PEDCO | 110 | PI | DW | 0004 | F2L-707947 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 1 | 0 | 7 | 2.7.1.4.1 | Material Flow Diagram - W007S | BK-W007S-PEDCO-110-PI-DG-0001 | BK-W007S-PEDCO-110-PI-DG-0001 | BK | W007S | PEDCO | 110 | PI | DG | 0001 | F2A-707948 | AFC | IFC | 2021-11-22 | 2021-11-24 | 2021-11-27 | 2 | 3 | 5 | IFA | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-08 | 0 |  | D01 | IFA | T-0932 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04376 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PI-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-PI-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0219 | 2021-11-08 | 1400/08/17 |  |  |  | BK-SUR-ENG-PIP-00-02060 | 2021-11-21 | 1400/08/30 | CM-C3 | [6 empty] | 1400-2294-289400 | 2021-11-24 | 1400/09/03 | 2021-11-27 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0932 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04376 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PI-DG-0001_D00 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-PI-DG-0001_D00
2 | 7 | 1 | 4 | 1 | 0 | 8 | 2.7.1.4.1 | Material Flow Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-DG-0002 | BK-W007S-PEDCO-110-PI-DG-0002 | BK | W007S | PEDCO | 110 | PI | DG | 0002 | F2A-707949 | AFC | IFC | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-11 | 0 |  | D00 | IFC | T-0934 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04380 | 2022-05-23 | 1401-03/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0934 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04380 | 2022-05-23 | 1401-03/02 | CM-C3
2 | 7 | 1 | 4 | 2 | 0 | 0 | 2.7.1.4.2 | List
2 | 7 | 1 | 4 | 2 | 0 | 1 | 2.7.1.4.2 | Critical Line List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-LI-0001 | BK-W007S-PEDCO-110-PI-LI-0001 | BK | W007S | PEDCO | 110 | PI | LI | 0001 | F0Z-707950 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 2 | 0 | 2 | 2.7.1.4.2 | Piping Tie-In List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-LI-0002 | BK-W007S-PEDCO-110-PI-LI-0002 | BK | W007S | PEDCO | 110 | PI | LI | 0002 | F0Z-707951 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 2 | 0 | 3 | 2.7.1.4.2 | Piping Support List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-LI-0003 | BK-W007S-PEDCO-110-PI-LI-0003 | BK | W007S | PEDCO | 110 | PI | LI | 0003 | F0Z-707952 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 2 | 0 | 4 | 2.7.1.4.2 | Piping Support List - W007S | BK-W007S-PEDCO-110-PI-LI-0004 | BK-W007S-PEDCO-110-PI-LI-0004 | BK | W007S | PEDCO | 110 | PI | LI | 0004 | F0Z-707953 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 2 | 0 | 5 | 2.7.1.4.2 | Critical Line List - W007S | BK-W007S-PEDCO-110-PI-LI-0005 | BK-W007S-PEDCO-110-PI-LI-0005 | BK | W007S | PEDCO | 110 | PI | LI | 0005 | F0Z-707954 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 3 | 0 | 0 | 2.7.1.4.3 | Report
2 | 7 | 1 | 4 | 3 | 0 | 1 | 2.7.1.4.3 | PDMS Model Review Report (30%) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-RT-0001 | BK-W007S-PEDCO-110-PI-RT-0001 | BK | W007S | PEDCO | 110 | PI | RT | 0001 | F0Z-707955 | AFC | IFC | 2022-04-23 | 2022-04-12 | 2022-04-16 | -11 | 4 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-09 | 0 |  | D00 | IFC | T-0791 | 2022-04-09 | 1401/01/20 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-03935 | 2022-04-16 | 1401/01/27 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-20714 | 2022-04-12 | 1401/01/23 | 2022-04-16 | 1401/01/27 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0791 | 2022-04-09 | 1401/01/20 |  |  |  | BK-SUR-ENG-PIP-01-03935 | 2022-04-16 | 1401/01/27 | CM-C3 | [6 empty] | 1401-2294-20714 | 2022-04-12 | 1401/01/23 | 2022-04-16 | 1401/01/27 | CM
2 | 7 | 1 | 4 | 3 | 0 | 2 | 2.7.1.4.3 | PDMS Model Review Report (60%) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-RT-0002 | BK-W007S-PEDCO-110-PI-RT-0002 | BK | W007S | PEDCO | 110 | PI | RT | 0002 | F0Z-707956 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 3 | 0 | 3 | 2.7.1.4.3 | PDMS Model Review Report (90%) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-PI-RT-0003 | BK-W007S-PEDCO-110-PI-RT-0003 | BK | W007S | PEDCO | 110 | PI | RT | 0003 | F0Z-707957 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 3 | 0 | 4 | 2.7.1.4.3 | PDMS Model Review Report | BK-W007S-PEDCO-110-PI-RT-0004 | BK-W007S-PEDCO-110-PI-RT-0004 | BK | W007S | PEDCO | 110 | PI | RT | 0004 | F0Z-707958 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 3 | 0 | 5 | 2.7.1.4.3 | PDMS Model Review Report (60%) - W007S | BK-W007S-PEDCO-110-PI-RT-0005 | BK-W007S-PEDCO-110-PI-RT-0005 | BK | W007S | PEDCO | 110 | PI | RT | 0005 | F0Z-707959 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 3 | 0 | 6 | 2.7.1.4.3 | PDMS Model Review Report (90%) - W007S | BK-W007S-PEDCO-110-PI-RT-0006 | BK-W007S-PEDCO-110-PI-RT-0006 | BK | W007S | PEDCO | 110 | PI | RT | 0006 | F0Z-707960 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 3 | 0 | 7 | 2.7.1.4.3 | Stress Analysis Calculations Report For Manifold area | BK-W007S-PEDCO-110-PI-RT-0007 | BK-W007S-PEDCO-110-PI-RT-0007 | BK | W007S | PEDCO | 110 | PI | RT | 0007 | F0Z-707961 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 4 | 0 | 0 | 2.7.1.4.4 | MTO
2 | 7 | 1 | 4 | 4 | 0 | 1 | 2.7.1.4 | MTO For Pipes - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0001 | BK-W007S-PEDCO-110-PI-MT-0001 | BK | W007S | PEDCO | 110 | PI | MT | 0001 | F8Z-707962 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 4 | 0 | 2 | 2.7.1.4 | MTO For Fittings - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0002 | BK-W007S-PEDCO-110-PI-MT-0002 | BK | W007S | PEDCO | 110 | PI | MT | 0002 | F8Z-707963 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 4 | 0 | 3 | 2.7.1.4 | MTO For Flanges - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0003 | BK-W007S-PEDCO-110-PI-MT-0003 | BK | W007S | PEDCO | 110 | PI | MT | 0003 | F8Z-707964 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 4 | 0 | 4 | 2.7.1.4 | MTO For Manual Valves - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0004 | BK-W007S-PEDCO-110-PI-MT-0004 | BK | W007S | PEDCO | 110 | PI | MT | 0004 | F8Z-707965 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 4 | 0 | 5 | 2.7.1.4 | MTO For Gaskets - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0005 | BK-W007S-PEDCO-110-PI-MT-0005 | BK | W007S | PEDCO | 110 | PI | MT | 0005 | F8Z-707966 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 4 | 4 | 0 | 6 | 2.7.1.4 | MTO For Bolt & Nuts - Manifold & W007S | BK-W007S-PEDCO-110-PI-MT-0006 | BK-W007S-PEDCO-110-PI-MT-0006 | BK | W007S | PEDCO | 110 | PI | MT | 0006 | F8Z-707967 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 5 | 0 | 0 | 0 | 2.7.1.5 | Pipeline & Flow line
2 | 7 | 1 | 5 | 1 | 0 | 0 | 2.7.1.5.1 | Drawing/Diagram
2 | 7 | 1 | 5 | 1 | 0 | 1 | 2.7.1.5.1 | Flow line Transversal Drawings - W007S | BK-W007S-PEDCO-110-PL-DW-0002 | BK-W007S-PEDCO-110-PL-DW-0002 | BK | W007S | PEDCO | 110 | PL | DW | 0002 | F4A-707968 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 5 | 2 | 0 | 0 | 2.7.1.5.2 | List
2 | 7 | 1 | 5 | 2 | 0 | 1 | 2.7.1.5.2 | Road Crossing Location List | BK-W007S-PEDCO-110-PL-LI-0001 | BK-W007S-PEDCO-110-PL-LI-0001 | BK | W007S | PEDCO | 110 | PL | LI | 0001 | F0Z-707969 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 5 | 3 | 0 | 0 | 2.7.1.5.3 | MTO
2 | 7 | 1 | 5 | 3 | 0 | 1 | 2.7.1.5 | MTO For Line Pipes (Flow lines) - W007S | BK-W007S-PEDCO-110-PL-MT-0001 | BK-W007S-PEDCO-110-PL-MT-0001 | BK | W007S | PEDCO | 110 | PL | MT | 0001 | F8Z-707970 | IFI | IFI | 44444 | 44438 | 44444 | -6 | 6 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2021-08-22 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | 1400/05/31 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | 1400/05/31 | CM-C2 | [6 empty] | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM
2 | 7 | 1 | 6 | 0 | 0 | 0 | 2.7.1.6 | BK-W007S-PEDCO-110-IN-DT-0012
2 | 7 | 1 | 6 | 1 | 0 | 0 | 2.7.1.6.1 | Data Sheets
2 | 7 | 1 | 6 | 1 | 0 | 1 | 2.7.1.6.1 | Data Sheets For Temperature Gauge - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0001 | BK-W007S-PEDCO-110-IN-DT-0001 | BK | W007S | PEDCO | 110 | IN | DT | 0001 | F9Z-707971 | AFC | IFC | 2021-12-21 | 2021-12-30 | 2022-01-02 | 9 | 3 | 12 | IFA | 2022-03-21 | 2022-03-16 | 2022-03-27 | -5 | 11 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-07 | 0 |  | D01 | IFA | T-0691 | 2022-03-07 | 1400/12/16 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03649 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-453216 | 2022-03-16 | 1400/12/25 | 2022-03-27 | 1401/01/07 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0309 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-INS-00-02403 | 2021-12-22 | 1400/10/01 | CM-C3 | [6 empty] | 1400-2294-342127 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0691 | 2022-03-07 | 1400/12/16 |  |  |  | BK-SUR-ENG-INS-00-03649 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0001_D00 | [5 empty] | 1400-2294-453216 | 2022-03-16 | 1400/12/25 | 2022-03-27 | 1401/01/07 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0001_D00
2 | 7 | 1 | 6 | 1 | 0 | 2 | 2.7.1.6.1 | Data Sheets For Pressure & Diff. Pressure Gauge - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0002 | BK-W007S-PEDCO-110-IN-DT-0002 | BK | W007S | PEDCO | 110 | IN | DT | 0002 | F9Z-707972 | AFC | IFC | 2021-12-21 | 2021-12-30 | 2022-01-02 | 9 | 3 | 12 | IFA | 2022-03-22 | 2022-03-16 | 2022-03-25 | -6 | 9 | 3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-07 | 0 |  | D01 | IFA | T-0698 | 2022-03-08 | 1400/12/17 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03651 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-453217 | 2022-03-16 | 1400/12/25 | 2022-03-25 | 1401/01/08 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0304 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-INS-00-02402 | 2021-12-22 | 1400/10/01 | CM-C3 | [6 empty] | 1400-2294-342113 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0698 | 2022-03-08 | 1400/12/17 |  |  |  | BK-SUR-ENG-INS-00-03651 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0002_D00 | [5 empty] | 1400-2294-453217 | 2022-03-16 | 1400/12/25 | 2022-03-25 | 1401/01/08 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0002_D00
2 | 7 | 1 | 6 | 1 | 0 | 3 | 2.7.1.6.1 | Data Sheets For Pressure Transmitter - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0003 | BK-W007S-PEDCO-110-IN-DT-0003 | BK | W007S | PEDCO | 110 | IN | DT | 0003 | F9Z-707973 | AFC | IFC | 2021-12-21 | 2021-12-30 | 2022-01-02 | 9 | 3 | 12 | IFA | 2022-03-26 | 2022-03-26 | 2022-03-27 | 0 | 1 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-07 | 0 |  | D01 | IFA | T-0720 | 2022-03-12 | 1400/12/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-1301 | 2022-03-26 | 1401/01/06 | 2022-03-27 | 1401/01/07 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0309 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-INS-00-02403 | 2021-12-22 | 1400/10/01 | CM-C3 | [6 empty] | 1400-2294-342127 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0720 | 2022-03-12 | 1400/12/21 | [7 empty] | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0003_D00 | [5 empty] | 1400-2294-1301 | 2022-03-26 | 1401/01/06 | 2022-03-27 | 1401/01/07 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0003_D00
2 | 7 | 1 | 6 | 1 | 0 | 4 | 2.7.1.6.1 | Data Sheets For Pressure & Safety Relief Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0004 | BK-W007S-PEDCO-110-IN-DT-0004 | BK | W007S | PEDCO | 110 | IN | DT | 0004 | F9Z-707974 | AFC | IFC | 2022-06-08 | 0 | 0 | -44720 | 0 | -44720 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-25 | 0 |  | D00 | IFC | T-1007 | 2022-05-25 | 1401/03/04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1007 | 2022-05-25 | 1401/03/04
2 | 7 | 1 | 6 | 1 | 0 | 5 | 2.7.1.6.1 | Data Sheets For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0005 | BK-W007S-PEDCO-110-IN-DT-0005 | BK | W007S | PEDCO | 110 | IN | DT | 0005 | F9Z-707975 | AFC | IFC | 2022-03-23 | 2022-03-19 | 2022-03-27 | -4 | 8 | 4 | IFA | 2022-05-22 | 0 | 0 | -44703 | 0 | -44703 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-09 | 0 |  | D01 | IFA | T-0909 | 2022-05-08 | 1401/02/17 | T-0909 | 2022-05-08 | 1401/02/17 | BK-SUR-ENG-INS-01-04430 | 2022-05-25 | 1401/03/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0708 | 2022-03-09 | 1400/12/18 | [13 empty] | 1400-2294-454928 | 2022-03-19 | 1400/12/28 | 2022-03-27 | 1401/01/07 | CM | [10 empty] | D01 | IFA | T-0909 | 2022-05-08 | 1401/02/17 | T-0909 | 2022-05-08 | 1401/02/17 | BK-SUR-ENG-INS-01-04430 | 2022-05-25 | 1401/03/03 | CM-C3 | [12 empty] | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0005_D00
2 | 7 | 1 | 6 | 1 | 0 | 6 | 2.7.1.6.1 | Data Sheets For Control/Regulator valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0006 | BK-W007S-PEDCO-110-IN-DT-0006 | BK | W007S | PEDCO | 110 | IN | DT | 0006 | F9Z-707976 | AFC | IFC | 2022-03-21 | 2022-04-17 | 2022-04-19 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-07 | 0 |  | D00 | IFC | T-0695 | 2022-03-07 | 1400/12/16 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03650 | 2022-03-16 | 1400/12/25 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-453218 | 2022-03-16 | 1400/12/25 | 2022-03-27 | 1401/01/07 | CM | 0 | 1401-2294-25145 | 2022-04-17 | 1401/01/27 | 2022-04-19 | 1401/01/30 | CM | 0 | 0 |  | D00 | IFC | T-0695 | 2022-03-07 | 1400/12/16 |  |  |  | BK-SUR-ENG-INS-00-03650 | 2022-03-16 | 1400/12/25 | CM-C3 | [6 empty] | 1400-2294-453218 | 2022-03-16 | 1400/12/25 | 2022-03-27 | 1401/01/07 | CM |  | 1401-2294-25145 | 2022-04-17 | 1401/01/27 | 2022-04-19 | 1401/01/30 | CM
2 | 7 | 1 | 6 | 1 | 0 | 7 | 2.7.1.6.1 | Data Sheets For Flow Transmitter/Diff. Pressure Transmitter - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0007 | BK-W007S-PEDCO-110-IN-DT-0007 | BK | W007S | PEDCO | 110 | IN | DT | 0007 | F9Z-707977 | AFC | IFC | 2021-12-21 | 2021-12-30 | 2022-01-02 | 9 | 3 | 12 | IFA | 2022-03-26 | 2022-03-26 | 2022-03-27 | 0 | 1 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-07 | 0 |  | D01 | IFA | T-0720 | 2022-03-12 | 1400/12/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0007_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-1301 | 2022-03-26 | 1401/01/06 | 2022-03-27 | 1401/01/07 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0309 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-INS-00-02403 | 2021-12-22 | 1400/10/01 | CM-C3 | [6 empty] | 1400-2294-342127 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM | [10 empty] | D01 | IFA | T-0720 | 2022-03-12 | 1400/12/21 | [7 empty] | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0007_D00 | [5 empty] | 1400-2294-1301 | 2022-03-26 | 1401/01/06 | 2022-03-27 | 1401/01/07 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0007_D00
2 | 7 | 1 | 6 | 1 | 0 | 8 | 2.7.1.6.1 | Data Sheets For Orifice Plate/Restriction Orifice - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0008 | BK-W007S-PEDCO-110-IN-DT-0008 | BK | W007S | PEDCO | 110 | IN | DT | 0008 | F9Z-707978 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 1 | 0 | 9 | 2.7.1.6.1 | Data Sheets For Corrosion Coupon/ Probe - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0009 | BK-W007S-PEDCO-110-IN-DT-0009 | BK | W007S | PEDCO | 110 | IN | DT | 0009 | F9Z-707979 | AFC | IFC | 2022-03-23 | 2022-03-19 | 2022-03-27 | -4 | 8 | 4 | IFA | 2022-05-22 | 0 | 0 | -44703 | 0 | -44703 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-09 | 0 |  | D01 | IFA | T-0914 | 2022-05-08 | 1401/02/18 | T-0914 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-INS-01-04431 | 2022-05-25 | 1401/03/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0009_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0708 | 2022-03-09 | 1400/12/18 | [13 empty] | 1400-2294-454928 | 2022-03-19 | 1400/12/28 | 2022-03-27 | 1401/01/07 | CM | [10 empty] | D01 | IFA | T-0914 | 2022-05-08 | 1401/02/18 | T-0914 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-INS-01-04431 | 2022-05-25 | 1401/03/03 | CM-C3 | [12 empty] | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0009_D00
2 | 7 | 1 | 6 | 1 | 0 | 10 | 2.7.1.6.1 | Data Sheets For F&G Devices - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0010 | BK-W007S-PEDCO-110-IN-DT-0010 | BK | W007S | PEDCO | 110 | IN | DT | 0010 | F9Z-707980 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 1 | 0 | 11 | 2.7.1.6.1 | Data Sheets For Pressure Switch and Differential Pressure Switch - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DT-0011 | BK-W007S-PEDCO-110-IN-DT-0011 | BK | W007S | PEDCO | 110 | IN | DT | 0011 | F9Z-707981 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 1 | 0 | 11 | 2.7.1.6.1 | DATA SHEETS FOR DISPLACER LEVEL TRANSMITTER - EXTENSION OF BINAK BC MANIFOLD | BK-W007S-PEDCO-110-IN-DT-0012 | BK-W007S-PEDCO-110-IN-DT-0012 | BK | W007S | PEDCO | 110 | IN | DT | 0011 | F9Z-707982 | AFC | IFC | 2022-01-15 | 2022-01-26 | 2022-01-29 | 11 | 3 | 14 | IFA | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-01 | 0 |  | D01 | IFA | T-0752 | 2022-03-27 | 1401/01/07 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03845 | 2022-04-10 | 1401/01/21 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0012_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27193 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0012_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0415 | 2022-01-01 | 1400/10/11 |  |  |  | BK-SUR-ENG-INS-00-02692 | 2022-01-16 | 1400/10/26 | CM-C3 | [6 empty] | 1400-2294-383988 | 2022-01-26 | 1400/11/06 | 2022-01-29 | 1400/11/09 | CM | [10 empty] | D01 | IFA | T-0752 | 2022-03-27 | 1401/01/07 |  |  |  | BK-SUR-ENG-INS-01-03845 | 2022-04-10 | 1401/01/21 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0012_D00 | [5 empty] | 1401-2294-27193 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0012_D00
2 | 7 | 1 | 6 | 2 | 0 | 0 | 2.7.1.6.2 | Drawing/Diagram
2 | 7 | 1 | 6 | 2 | 0 | 1 | 2.7.1.6.2 | Typical Instrument Installation Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DW-0001 | BK-W007S-PEDCO-110-IN-DW-0001 | BK | W007S | PEDCO | 110 | IN | DW | 0001 | F2J-707983 | IFI | IFI | 2022-03-23 | 2022-04-04 | 2022-04-09 | 12 | 5 | 17 | IFI | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-09 | 2022-05-11 |  | D01 | IFI | T-0936 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04471 | 2022-05-29 | 1401/03/08 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISCO-CRS-BK-W007S-PEDCO-110-IN-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0709 | 2022-03-09 | 1400/12/18 | [13 empty] | 1401-2294-9656 | 2022-04-04 | 1401/01/15 | 2022-04-09 | 1401/01/20 | CM | [10 empty] | D01 | IFI | T-0936 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-INS-01-04471 | 2022-05-29 | 1401/03/08 | CM-C2 | [12 empty] | NISCO-CRS-BK-W007S-PEDCO-110-IN-DW-0001_D01
2 | 7 | 1 | 6 | 2 | 0 | 2 | 2.7.1.6.2 | Block Diagram Configuration For Control/ESD/F&G System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0001 | BK-W007S-PEDCO-110-IN-DG-0001 | BK | W007S | PEDCO | 110 | IN | DG | 0001 | F2J-707984 | AFC | IFC | 2021-09-15 | 2021-09-29 | 2021-10-09 | 14 | 10 | 24 | IFA | 2021-11-15 | 2021-11-21 | 2021-11-27 | 6 | 6 | 12 | IFA | 2022-01-22 | 2022-01-31 | 2022-02-01 | 9 | 1 | 10 | IFA | 2022-04-20 | 2022-05-09 | 2022-05-21 | 19 | 12 | 31 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-01 | 0 |  | D03 | IFA | T-0780 | 2022-04-06 | 1401/01/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54898 | 2022-05-09 | 1401/02/19 | 2022-05-21 | 1401/02/31 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0073 | 2021-09-01 | 1400/06/10 |  |  |  | BK-SUR-ENG-INS-00-01551 | 2021-10-19 | 1400/07/27 | CM-C3 | [6 empty] | 1400-2294-217809 | 2021-09-29 | 1400/07/07 | 2021-10-09 | 1400/07/17 | CM | [10 empty] | D01 | IFA | T-0202 | 2021-11-01 | 1400/08/10 |  |  |  | BK-SUR-ENG-INS-00-01995 | 2021-11-14 | 1400/08/23 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0001-D00 | [5 empty] | 1400-2294-283464 | 2021-11-21 | 1400/08/30 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0001-D00 | [9 empty] | D02 | IFA | T-0438 | 2022-01-08 | 1400/10/18 |  |  |  | BK-SUR-ENG-INS-00-02850 | 2022-01-29 | 1400/11/09 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0001-D01 | [5 empty] | 1400-2294-389640 | 2022-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/13 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0001-D01 | [9 empty] | D03 | IFA | T-0780 | 2022-04-06 | 1401/01/17 | [7 empty] | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0001_D02 | [5 empty] | 1401-2294-54898 | 2022-05-09 | 1401/02/19 | 2022-05-21 | 1401/02/31 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0001_D02
2 | 7 | 1 | 6 | 2 | 0 | 3 | 2.7.1.6.2 | Instrument Earthing Typical Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0002 | BK-W007S-PEDCO-110-IN-DG-0002 | BK | W007S | PEDCO | 110 | IN | DG | 0002 | F2J-707985 | IFI | IFI | 2022-01-15 | 2022-01-20 | 2022-01-22 | 5 | 2 | 7 | IFI | 2022-05-04 | 2022-05-12 | 2022-05-16 | 8 | 4 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-01 | 2022-04-20 |  | D01 | IFI | T-0849 | 2022-04-20 | 1401/01/31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59514 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0410 | 2022-01-01 | 1400/10/11 |  |  |  | BK-SUR-ENG-INS-00-02616 | 2022-01-01 | 1400/10/20 | CM-C2 | [6 empty] | 1400-2294-372857 | 2022-01-20 | 1400/10/30 | 2022-01-22 | 1400/11/22 | CM | [10 empty] | D01 | IFI | T-0849 | 2022-04-20 | 1401/01/31 | [7 empty] | PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0002_D00 | [5 empty] | 1401-2294-59514 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0002_D00
2 | 7 | 1 | 6 | 2 | 0 | 4 | 2.7.1.6.2 | Instrument Hook-up Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0003 | BK-W007S-PEDCO-110-IN-DG-0003 | BK | W007S | PEDCO | 110 | IN | DG | 0003 | F2J-707986 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 2 | 0 | 5 | 2.7.1.6.2 | ESD Level Hierarchy - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0004 | BK-W007S-PEDCO-110-IN-DG-0004 | BK | W007S | PEDCO | 110 | IN | DG | 0004 | F2J-707987 | AFC | IFC | 2022-05-08 | 0 | 0 | -44689 | 0 | -44689 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-24 | 0 |  | D00 | IFC | T-0857 | 2022-04-24 | 1401/02/04 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04192 | 2022-05-10 | 1401/02/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0857 | 2022-04-24 | 1401/02/04 |  |  |  | BK-SUR-ENG-INS-01-04192 | 2022-05-10 | 1401/02/20 | CM-C3
2 | 7 | 1 | 6 | 2 | 0 | 6 | 2.7.1.6.2 | ESD System Loop Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0005 | BK-W007S-PEDCO-110-IN-DG-0005 | BK | W007S | PEDCO | 110 | IN | DG | 0005 | F2J-707988 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 2 | 0 | 7 | 2.7.1.6.2 | Control System Loop Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0006 | BK-W007S-PEDCO-110-IN-DG-0006 | BK | W007S | PEDCO | 110 | IN | DG | 0006 | F2J-707989 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 2 | 0 | 8 | 2.7.1.6.2 | F&G System Loop Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0007 | BK-W007S-PEDCO-110-IN-DG-0007 | BK | W007S | PEDCO | 110 | IN | DG | 0007 | F2J-707990 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 2 | 0 | 9 | 2.7.1.6.2 | Instrument Air Piping and Air Header Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0008 | BK-W007S-PEDCO-110-IN-DG-0008 | BK | W007S | PEDCO | 110 | IN | DG | 0008 | F2J-707991 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 2 | 0 | 10 | 2.7.1.6.2 | Instrument & F&G Junction Box Termination Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0009 | BK-W007S-PEDCO-110-IN-DG-0009 | BK | W007S | PEDCO | 110 | IN | DG | 0009 | F2J-707992 | AFC | IFC | 2022-05-28 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-14 | 0 |  | D00 | IFC | T-0946 | 2022-05-14 | 1401/02/24 | T-0946 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-INS-01-04474 | 2022-05-29 | 1401/03/08 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0946 | 2022-05-14 | 1401/02/24 | T-0946 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-INS-01-04474 | 2022-05-29 | 1401/03/08 | CM-C3
2 | 7 | 1 | 6 | 2 | 0 | 11 | 2.7.1.6.2 | F&G Cause and Effect Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0010 | BK-W007S-PEDCO-110-IN-DG-0010 | BK | W007S | PEDCO | 110 | IN | DG | 0010 | F2J-707993 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 2 | 0 | 12 | 2.7.1.6.2 | Control System Logic Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LD-0001 | BK-W007S-PEDCO-110-IN-LD-0001 | BK | W007S | PEDCO | 110 | IN | LD | 0001 | F1J-707994 | AFC | IFC | 2022-04-24 | 2022-05-21 | 2022-05-23 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-10 | 0 |  | D00 | IFC | T-0797 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04115 | 2022-05-01 | 1401/02/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70032 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0797 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-INS-01-04115 | 2022-05-01 | 1401/02/11 | CM-C3 | [6 empty] | 1401-2294-70032 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM
2 | 7 | 1 | 6 | 2 | 0 | 13 | 2.7.1.6.2 | ESD Logic Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LD-0002 | BK-W007S-PEDCO-110-IN-LD-0002 | BK | W007S | PEDCO | 110 | IN | LD | 0002 | F1J-707995 | AFC | IFC | 2022-06-08 | 0 | 0 | -44720 | 0 | -44720 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-25 | 0 |  | D00 | IFC | T-1007 | 2022-05-25 | 1401/03/04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1007 | 2022-05-25 | 1401/03/04
2 | 7 | 1 | 6 | 2 | 0 | 14 | 2.7.1.6.2 | Control Room Layout & Arrangement Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0001 | BK-W007S-PEDCO-110-IN-PY-0001 | BK | W007S | PEDCO | 110 | IN | PY | 0001 | F2J-707996 | AFC | IFC | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-11 | 0 |  | D00 | IFC | T-0935 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04459 | 2022-05-28 | 1401//03/07 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0935 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-INS-01-04459 | 2022-05-28 | 1401//03/07 | CM-C3
2 | 7 | 1 | 6 | 2 | 0 | 15 | 2.7.1.6.2 | Control Room Cable Route Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0002 | BK-W007S-PEDCO-110-IN-PY-0002 | BK | W007S | PEDCO | 110 | IN | PY | 0002 | F2J-707997 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 2 | 0 | 16 | 2.7.1.6.2 | Instrument Location Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0003 | BK-W007S-PEDCO-110-IN-PY-0003 | BK | W007S | PEDCO | 110 | IN | PY | 0003 | F2J-707998 | AFC | IFC | 2022-05-31 | 0 | 0 | -44712 | 0 | -44712 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-17 | 0 |  | D00 | IFC | T-0967 | 2022-05-17 | 1401/02/27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0967 | 2022-05-17 | 1401/02/27
2 | 7 | 1 | 6 | 2 | 0 | 17 | 2.7.1.6.2 | Instrument/F&G Cable Trench/Route Layout Drawing - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0004 | BK-W007S-PEDCO-110-IN-PY-0004 | BK | W007S | PEDCO | 110 | IN | PY | 0004 | F2J-707999 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 2 | 0 | 18 | 2.7.1.6.2 | F&G Location Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-PY-0005 | BK-W007S-PEDCO-110-IN-PY-0005 | BK | W007S | PEDCO | 110 | IN | PY | 0005 | F2J-708000 | AFC | IFC | 2022-06-13 | 0 | 0 | -44725 | 0 | -44725 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-30 | 0 |  | D00 | IFC | T-1025 | 2022-05-30 | 1401/03/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1025 | 2022-05-30 | 1401/03/09
2 | 7 | 1 | 6 | 2 | 0 | 19 | 2.7.1.6.2 | Instrument Location Layout Drawing - W007S | BK-W007S-PEDCO-110-IN-PY-0006 | BK-W007S-PEDCO-110-IN-PY-0006 | BK | W007S | PEDCO | 110 | IN | PY | 0006 | F2J-708001 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 2 | 0 | 20 | 2.7.1.6.2 | Wiring Diagram; Interposing Relay Panel (IRP) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-DG-0011 | BK-W007S-PEDCO-110-IN-DG-0011 | BK | W007S | PEDCO | 110 | IN | DG | 0011 | F2J-708002 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 3 | 0 | 0 | 2.7.1.6.3 | List
2 | 7 | 1 | 6 | 3 | 0 | 1 | 2.7.1.6.3 | I/O List For Control System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0002 | BK-W007S-PEDCO-110-IN-LI-0002 | BK | W007S | PEDCO | 110 | IN | LI | 0002 | F0Z-708003 | AFC | IFC | 2021-11-17 | 2021-11-21 | 2021-11-27 | 4 | 6 | 10 | IFA | 2022-03-16 | 2022-03-13 | 2022-03-25 | -3 | 12 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-03 | 0 |  | D01 | IFA | T-0665 | 2022-03-02 | 1400/12/11 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03647 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-LI-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-447179 | 2022-03-13 | 1400/12/22 | 2022-03-25 | 1401/01/08 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-LI-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0208 | 2021-11-03 | 1400/08/12 |  |  |  | BK-SUR-ENG-INS-00-02036 | 2021-11-17 | 1400/08/26 | C4-RJ | [6 empty] | 1400-2294-285060 | 2021-11-21 | 1400/08/30 | 2021-11-27 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0665 | 2022-03-02 | 1400/12/11 |  |  |  | BK-SUR-ENG-INS-00-03647 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-LI-0002_D00 | [5 empty] | 1400-2294-447179 | 2022-03-13 | 1400/12/22 | 2022-03-25 | 1401/01/08 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-LI-0002_D00
2 | 7 | 1 | 6 | 3 | 0 | 2 | 2.7.1.6.3 | I/O List For ESD Systems - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0003 | BK-W007S-PEDCO-110-IN-LI-0003 | BK | W007S | PEDCO | 110 | IN | LI | 0003 | F0Z-708004 | AFC | IFC | 2021-11-17 | 2021-11-21 | 2021-11-27 | 4 | 6 | 10 | IFA | 2022-03-16 | 2022-03-13 | 2022-03-25 | -3 | 12 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-03 | 0 |  | D01 | IFA | T-0665 | 2022-03-02 | 1400/12/11 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03647 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-LI-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-447179 | 2022-03-13 | 1400/12/22 | 2022-03-25 | 1401/01/08 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-LI-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0208 | 2021-11-03 | 1400/08/12 |  |  |  | BK-SUR-ENG-INS-00-02036 | 2021-11-17 | 1400/08/26 | C4-RJ | [6 empty] | 1400-2294-285060 | 2021-11-21 | 1400/08/30 | 2021-11-27 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0665 | 2022-03-02 | 1400/12/11 |  |  |  | BK-SUR-ENG-INS-00-03647 | 2022-03-16 | 1400/12/25 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-IN-LI-0003_D00 | [5 empty] | 1400-2294-447179 | 2022-03-13 | 1400/12/22 | 2022-03-25 | 1401/01/08 | AP | NISOC-CRS-BK-W007S-PEDCO-110-IN-LI-0003_D00
2 | 7 | 1 | 6 | 3 | 0 | 3 | 2.7.1.6.3 | I/O List For F&G Systems - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0004 | BK-W007S-PEDCO-110-IN-LI-0004 | BK | W007S | PEDCO | 110 | IN | LI | 0004 | F0Z-708005 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 3 | 0 | 4 | 2.7.1.6.3 | Panels & Junction Box List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0005 | BK-W007S-PEDCO-110-IN-LI-0005 | BK | W007S | PEDCO | 110 | IN | LI | 0005 | F0Z-708006 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 3 | 0 | 5 | 2.7.1.6.3 | Set Point & Alarm List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0006 | BK-W007S-PEDCO-110-IN-LI-0006 | BK | W007S | PEDCO | 110 | IN | LI | 0006 | F0Z-708007 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 3 | 0 | 6 | 2.7.1.6.3 | I&C Power Consumption Summary - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0007 | BK-W007S-PEDCO-110-IN-LI-0007 | BK | W007S | PEDCO | 110 | IN | LI | 0007 | F0Z-708008 | AFC | IFC | 2022-03-14 | 2022-03-25 | 2022-04-01 | 11 | 7 | 18 | IFA | 2022-05-04 | 2022-05-01 | 2022-05-02 | -3 | 1 | -2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-28 | 0 |  | D01 | IFA | T-0852 | 2022-04-20 | 1401/01/31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-47232 | 2022-05-01 | 1401/02/11 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W007S-PEDCO-110-IN-LI-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0654 | 2022-02-28 | 1400/12/09 | [13 empty] | 1400-2294-453222 | 2022-03-16 | 1400/12/25 | 2022-03-27 | 1401/01/07 | CM |  | 1401-2294-4017 | 2022-03-25 | 1401/01/08 | 2022-04-01 | 1401/01/14 | CM |  |  |  | D01 | IFA | T-0852 | 2022-04-20 | 1401/01/31 | [13 empty] | 1401-2294-47232 | 2022-05-01 | 1401/02/11 | 2022-05-02 | 1401/02/12 | RJ | NISOC-CRS-BK-W007S-PEDCO-110-IN-LI-0007_D00
2 | 7 | 1 | 6 | 3 | 0 | 7 | 2.7.1.6.3 | F&G Detector List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0008 | BK-W007S-PEDCO-110-IN-LI-0008 | BK | W007S | PEDCO | 110 | IN | LI | 0008 | F0Z-708009 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 3 | 0 | 8 | 2.7.1.6.3 | Instrument /F&G Cable List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-LI-0009 | BK-W007S-PEDCO-110-IN-LI-0009 | BK | W007S | PEDCO | 110 | IN | LI | 0009 | F0Z-708010 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 4 | 0 | 0 | 2.7.1.6.4 | MTO
2 | 7 | 1 | 6 | 4 | 0 | 1 | 2.7.1.6 | MTO for Bulk Item and Installation Accessories - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0001 | BK-W007S-PEDCO-110-IN-MT-0001 | BK | W007S | PEDCO | 110 | IN | MT | 0001 | F8Z-708011 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 4 | 0 | 2 | 2.7.1.6 | MTO For Instrument/F&G Cable - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0002 | BK-W007S-PEDCO-110-IN-MT-0002 | BK | W007S | PEDCO | 110 | IN | MT | 0002 | F8Z-708012 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 4 | 0 | 3 | 2.7.1.6 | MTO For Instrument/F&G Junction box and Gland - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0003 | BK-W007S-PEDCO-110-IN-MT-0003 | BK | W007S | PEDCO | 110 | IN | MT | 0003 | F8Z-708013 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 4 | 0 | 4 | 2.7.1.6 | MTO For Instrument Tube and Fitting - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0004 | BK-W007S-PEDCO-110-IN-MT-0004 | BK | W007S | PEDCO | 110 | IN | MT | 0004 | F8Z-708014 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 6 | 4 | 0 | 5 | 2.7.1.6 | MTO For Instrument Cable Tray/Ladder - W007S & Manifold | BK-W007S-PEDCO-110-IN-MT-0005 | BK-W007S-PEDCO-110-IN-MT-0005 | BK | W007S | PEDCO | 110 | IN | MT | 0005 | F8Z-708015 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 7 | 0 | 0 | 0 | 2.7.1.7 | Safety
2 | 7 | 1 | 7 | 1 | 0 | 0 | 2.7.1.7.1 | Drawing/Diagram
2 | 7 | 1 | 7 | 1 | 0 | 1 | 2.7.1.7.1 | Hazardous Area Classification Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-SA-PY-0001 | BK-W007S-PEDCO-110-SA-PY-0001 | BK | W007S | PEDCO | 110 | SA | PY | 0001 | F2L-708016 | AFC | IFC | 2022-03-26 | 2022-04-13 | 2022-04-16 | 18 | 3 | 21 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-12 | 0 |  | D00 | IFC | T-0715 | 2022-03-12 | 1400/12/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-16831 | 2022-04-10 | 1401/01/21 | 2022-04-11 | 1401/01/22 | CM | 0 | 1401-2294-22713 | 2022-04-13 | 1401/01/24 | 2022-04-16 | 1401/01/27 | CM | 0 | 0 |  | D00 | IFC | T-0715 | 2022-03-12 | 1400/12/21 | [13 empty] | 1401-2294-16831 | 2022-04-10 | 1401/01/21 | 2022-04-11 | 1401/01/22 | CM |  | 1401-2294-22713 | 2022-04-13 | 1401/01/24 | 2022-04-16 | 1401/01/27 | CM
2 | 7 | 1 | 7 | 1 | 0 | 2 | 2.7.1.7.1 | Safety & Fire Fighting Equipment Location Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-SA-PY-0002 | BK-W007S-PEDCO-110-SA-PY-0002 | BK | W007S | PEDCO | 110 | SA | PY | 0002 | F2L-708017 | AFC | IFC | 2022-05-01 | 2022-05-21 | 2022-05-23 | 20 | 2 | 22 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-17 | 0 |  | D00 | IFC | T-0834 | 2022-04-17 | 1401/01/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70732 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0834 | 2022-04-17 | 1401/01/28 | [13 empty] | 1401-2294-70732 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM
2 | 7 | 1 | 7 | 1 | 0 | 3 | 2.7.1.7.1 | Escape Route & Safety Sign Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-SA-PY-0003 | BK-W007S-PEDCO-110-SA-PY-0003 | BK | W007S | PEDCO | 110 | SA | PY | 0003 | F2L-708018 | AFC | IFC | 2022-05-01 | 0 | 0 | -44682 | 0 | -44682 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-17 | 0 |  | D00 | IFC | T-0834 | 2022-04-17 | 1401/01/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0834 | 2022-04-17 | 1401/01/28
2 | 7 | 1 | 7 | 1 | 0 | 4 | 2.7.1.7.1 | Hazardous Area Classification Layout - W007S | BK-W007S-PEDCO-110-SA-PY-0004 | BK-W007S-PEDCO-110-SA-PY-0004 | BK | W007S | PEDCO | 110 | SA | PY | 0004 | F2L-708019 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 7 | 1 | 0 | 5 | 2.7.1.7.1 | Safety & Fire Fighting Equipment Location Layout - W007S | BK-W007S-PEDCO-110-SA-PY-0005 | BK-W007S-PEDCO-110-SA-PY-0005 | BK | W007S | PEDCO | 110 | SA | PY | 0005 | F2L-708020 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 7 | 1 | 0 | 6 | 2.7.1.7.1 | Escape Route & Safety Sign Layout - W007S | BK-W007S-PEDCO-110-SA-PY-0006 | BK-W007S-PEDCO-110-SA-PY-0006 | BK | W007S | PEDCO | 110 | SA | PY | 0006 | F2L-708021 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 7 | 2 | 0 | 0 | 2.7.1.7.2 | List
2 | 7 | 1 | 7 | 2 | 0 | 1 | 2.7.1.7.2 | Hazard Source List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-SA-LI-0001 | BK-W007S-PEDCO-110-SA-LI-0001 | BK | W007S | PEDCO | 110 | SA | LI | 0001 | F0Z-708022 | AFC | IFC | 2021-11-23 | 2021-11-30 | 2021-12-06 | 7 | 6 | 13 | IFA | 2022-03-16 | 2022-04-05 | 2022-04-09 | 20 | 4 | 24 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-09 | 0 |  | D01 | IFA | T-0663 | 2022-03-02 | 1400/12/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-10280 | 2022-04-05 | 1401/01/16 | 2022-04-09 | 1401/01/20 | CM | NISOC-CRS-BK-W007S-PEDCO-110-SA-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0220 | 2021-11-09 | 1400/08/18 | [13 empty] | 1400-2290-298651 | 2021-11-30 | 1400/09/09 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0663 | 2022-03-02 | 1400/12/11 | [13 empty] | 1401-2294-10280 | 2022-04-05 | 1401/01/16 | 2022-04-09 | 1401/01/20 | CM | NISOC-CRS-BK-W007S-PEDCO-110-SA-LI-0001_D00
2 | 7 | 1 | 7 | 2 | 0 | 2 | 2.7.1.7.2 | Hazard Source List - W007S | BK-W007S-PEDCO-110-SA-LI-0002 | BK-W007S-PEDCO-110-SA-LI-0002 | BK | W007S | PEDCO | 110 | SA | LI | 0002 | F0Z-708023 | AFC | IFC | 2021-11-23 | 2021-11-30 | 2021-12-06 | 7 | 6 | 13 | IFA | 2022-03-12 | 2022-04-05 | 2022-04-09 | 24 | 4 | 28 | IFA | 2022-05-01 | 0 | 0 | -44682 | 0 | -44682 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-09 | 0 |  | D02 | IFA | T-0827 | 2022-04-17 | 1401/01/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-SA-LI-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0220 | 2021-11-09 | 1400/08/18 | [13 empty] | 1400-2290-298651 | 2021-11-30 | 1400/09/09 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0645 | 2022-02-26 | 1400/12/07 | [13 empty] | 1401-2294-13856 | 2022-04-05 | 1401/01/18 | 2022-04-09 | 1401/01/20 | CM | NISOC-CRS-BK-W007S-PEDCO-110-SA-LI-0002_D00 | [9 empty] | D02 | IFA | T-0827 | 2022-04-17 | 1401/01/28 | [19 empty] | NISOC-CRS-BK-W007S-PEDCO-110-SA-LI-0002_D01
2 | 7 | 1 | 7 | 3 | 0 | 0 | 2.7.1.7.3 | MTO
2 | 7 | 1 | 7 | 3 | 0 | 1 | 2.7.1.7 | MTO For Fire Fighting & Safety Equipment - Manifold & W007S | BK-W007S-PEDCO-110-SA-MT-0002 | BK-W007S-PEDCO-110-SA-MT-0002 | BK | W007S | PEDCO | 110 | SA | MT | 0002 | F8Z-708024 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 7 | 3 | 0 | 2 | 2.7.1.7 | MTO For Safety Sign - W007S | BK-W007S-PEDCO-110-SA-MT-0003 | BK-W007S-PEDCO-110-SA-MT-0003 | BK | W007S | PEDCO | 110 | SA | MT | 0003 | F8Z-708025 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 8 | 0 | 0 | 0 | 2.7.1.8 | Electrical
2 | 7 | 1 | 8 | 1 | 0 | 0 | 2.7.1.8.1 | Drawing/Diagram
2 | 7 | 1 | 8 | 1 | 0 | 1 | 2.7.1.8.1 | Earthing Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-PY-0001 | BK-W007S-PEDCO-110-EL-PY-0001 | BK | W007S | PEDCO | 110 | EL | PY | 0001 | F2P-708026 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 8 | 1 | 0 | 2 | 2.7.1.8.1 | LV Switchgear/MCC Expansion SLD - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-SL-0001 | BK-W007S-PEDCO-110-EL-SL-0001 | BK | W007S | PEDCO | 110 | EL | SL | 0001 | F2P-708027 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 8 | 1 | 0 | 3 | 2.7.1.8.1 | UPS Single Line Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-SL-0002 | BK-W007S-PEDCO-110-EL-SL-0002 | BK | W007S | PEDCO | 110 | EL | SL | 0002 | F2P-708028 | AFC | IFC | 2022-04-09 | 2022-04-19 | 2022-04-25 | 10 | 6 | 16 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-26 | 0 |  | D00 | IFC | T-0737 | 2022-03-26 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-03698 | 2022-03-30 | 1401/01/10 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31452 | 2022-04-19 | 1401/01/30 | 2022-04-25 | 1401/02/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0737 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-ELE-01-03698 | 2022-03-30 | 1401/01/10 | CM-C3 | [6 empty] | 1401-2294-31452 | 2022-04-19 | 1401/01/30 | 2022-04-25 | 1401/02/05 | CM
2 | 7 | 1 | 8 | 1 | 0 | 4 | 2.7.1.8.1 | DC Charger Single Line Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-SL-0003 | BK-W007S-PEDCO-110-EL-SL-0003 | BK | W007S | PEDCO | 110 | EL | SL | 0003 | F2P-708029 | AFC | IFC | 2022-04-09 | 2022-04-19 | 2022-04-25 | 10 | 6 | 16 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-26 | 0 |  | D00 | IFC | T-0737 | 2022-03-26 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-03698 | 2022-03-30 | 1401/01/10 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31452 | 2022-04-19 | 1401/01/30 | 2022-04-25 | 1401/02/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0737 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-ELE-01-03698 | 2022-03-30 | 1401/01/10 | CM-C3 | [6 empty] | 1401-2294-31452 | 2022-04-19 | 1401/01/30 | 2022-04-25 | 1401/02/05 | CM
2 | 7 | 1 | 8 | 1 | 0 | 5 | 2.7.1.8.1 | Interconnection Wiring Diagram - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-DG-0001 | BK-W007S-PEDCO-110-EL-DG-0001 | BK | W007S | PEDCO | 110 | EL | DG | 0001 | F2P-708030 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 8 | 1 | 0 | 6 | 2.7.1.8.1 | Area Electrical Cable Route & Section Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-PY-0002 | BK-W007S-PEDCO-110-EL-PY-0002 | BK | W007S | PEDCO | 110 | EL | PY | 0002 | F2P-708031 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 8 | 1 | 0 | 7 | 2.7.1.8.1 | Electrical Equipment Arrangement Layout In Switchgear Building - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-PY-0003 | BK-W007S-PEDCO-110-EL-PY-0003 | BK | W007S | PEDCO | 110 | EL | PY | 0003 | F2P-708032 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 8 | 1 | 0 | 8 | 2.7.1.8.1 | Earthing & Lightning Layout - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-PY-0004 | BK-W007S-PEDCO-110-EL-PY-0004 | BK | W007S | PEDCO | 110 | EL | PY | 0004 | F2P-708033 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 8 | 2 | 0 | 0 | 2.7.1.8.2 | List
2 | 7 | 1 | 8 | 2 | 0 | 1 | 2.7.1.8.2 | Electrical Load List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-LI-0001 | BK-W007S-PEDCO-110-EL-LI-0001 | BK | W007S | PEDCO | 110 | EL | LI | 0001 | F0Z-708034 | AFC | IFC | 2022-03-21 | 2022-03-26 | 2022-03-27 | 5 | 1 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-07 | 0 |  | D00 | IFC | T-0692 | 2022-03-07 | 1400/12/16 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03603 | 2022-03-15 | 1400/12/24 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-1235 | 2022-03-26 | 1401/01/06 | 2022-03-27 | 1401/01/07 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0692 | 2022-03-07 | 1400/12/16 |  |  |  | BK-SUR-ENG-ELE-00-03603 | 2022-03-15 | 1400/12/24 | CM-C2 | [6 empty] | 1401-2294-1235 | 2022-03-26 | 1401/01/06 | 2022-03-27 | 1401/01/07 | CM
2 | 7 | 1 | 8 | 2 | 0 | 2 | 2.7.1.8.2 | Electrical Power & Control Cable List - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-EL-LI-0002 | BK-W007S-PEDCO-110-EL-LI-0002 | BK | W007S | PEDCO | 110 | EL | LI | 0002 | F0Z-708035 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 8 | 3 | 0 | 0 | 2.7.1.8.3 | MTO
2 | 7 | 1 | 8 | 3 | 0 | 1 | 2.7.1.8 | MTO For Earthing & Lightning Systems - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0001 | BK-W007S-PEDCO-110-EL-MT-0001 | BK | W007S | PEDCO | 110 | EL | MT | 0001 | F8Z-708036 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 8 | 3 | 0 | 2 | 2.7.1.8 | MTO For Lighting & Small Powers - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0002 | BK-W007S-PEDCO-110-EL-MT-0002 | BK | W007S | PEDCO | 110 | EL | MT | 0002 | F8Z-708037 | IFI | IFI | 2022-06-01 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-18 | 2022-05-18 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04483 | 2022-05-29 | 1401/03/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 |  |  |  | BK-SUR-ENG-ELE-01-04483 | 2022-05-29 | 1401/03/09 | CM-C2
2 | 7 | 1 | 8 | 3 | 0 | 3 | 2.7.1.8 | MTO For Power & Control Cables - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0003 | BK-W007S-PEDCO-110-EL-MT-0003 | BK | W007S | PEDCO | 110 | EL | MT | 0003 | F8Z-708038 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 8 | 3 | 0 | 4 | 2.7.1.8 | MTO For Tray/Ladder and Accessories - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0004 | BK-W007S-PEDCO-110-EL-MT-0004 | BK | W007S | PEDCO | 110 | EL | MT | 0004 | F8Z-708039 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 8 | 3 | 0 | 5 | 2.7.1.8 | MTO For Electrical Bulk Items - Manifold & W007S | BK-W007S-PEDCO-110-EL-MT-0005 | BK-W007S-PEDCO-110-EL-MT-0005 | BK | W007S | PEDCO | 110 | EL | MT | 0005 | F8Z-708040 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 8 | 3 | 0 | 6 | 2.7.1.8 | MTO For Transmission Over Head Line - W007S | BK-W007S-PEDCO-110-EL-MT-0006 | BK-W007S-PEDCO-110-EL-MT-0006 | BK | W007S | PEDCO | 110 | EL | MT | 0006 | F8Z-708041 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 9 | 0 | 0 | 0 | 2.7.1.9 | Architecture
2 | 7 | 1 | 9 | 1 | 0 | 0 | 2.7.1.9.1 | Drawing/Diagram
2 | 7 | 1 | 9 | 1 | 0 | 1 | 2.7.1.9.1 | Architectural Drawing For Diesel Generator Shelter of Well Pads - W007S | BK-W007S-PEDCO-110-AR-DW-0001 | BK-W007S-PEDCO-110-AR-DW-0001 | BK | W007S | PEDCO | 110 | AR | DW | 0001 | F4B-708042 | AFC | IFC | 2022-05-15 | 2022-05-09 | 2022-05-16 | -6 | 7 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-01 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | [13 empty] | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | CM
2 | 7 | 1 | 9 | 1 | 0 | 2 | 2.7.1.9.1 | Architectural Drawing For WHCP/HPU Shelter of Well Pads - W007S | BK-W007S-PEDCO-110-AR-DW-0002 | BK-W007S-PEDCO-110-AR-DW-0002 | BK | W007S | PEDCO | 110 | AR | DW | 0002 | F4B-708043 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 9 | 1 | 0 | 3 | 2.7.1.9.1 | Architectural Drawing For Switchgear Building of Well Pads - W007S | BK-W007S-PEDCO-110-AR-DW-0003 | BK-W007S-PEDCO-110-AR-DW-0003 | BK | W007S | PEDCO | 110 | AR | DW | 0003 | F4B-708044 | AFC | IFC | 2022-03-23 | 2022-03-15 | 2022-03-25 | -8 | 10 | 2 | IFC | 2022-06-01 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-18 | 0 |  | D01 | IFC | T-0974 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-W007S-PEDCO-110-AR-DW-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-AR-DW-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0707 | 2022-03-09 | 1400/12/18 |  |  |  | RE BK-SUR-ENG-ARC-00-03551 | 2022-03-14 | 1400/12/23 | CM | [6 empty] | 1400-2294-450549 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | RJ | [10 empty] | D01 | IFC | T-0974 | 2022-05-18 | 1401/02/28 | [7 empty] | PEDCO-CRS-BK-W007S-PEDCO-110-AR-DW-0003_D00 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-AR-DW-0003_D00
2 | 7 | 1 | 9 | 1 | 0 | 4 | 2.7.1.9.1 | Architectural Drawing For Security Building of Well Pads - W007S | BK-W007S-PEDCO-110-AR-DW-0004 | BK-W007S-PEDCO-110-AR-DW-0004 | BK | W007S | PEDCO | 110 | AR | DW | 0004 | F4B-708045 | AFC | IFC | 2022-05-15 | 2022-05-14 | 2022-05-16 | -1 | 2 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04190 | 2022-05-10 | 1401/02/20 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 2022-05-16 | 1401/02/26 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04190 | 2022-05-10 | 1401/02/20 | CM-C2 | [6 empty] | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 2022-05-16 | 1401/02/26 | RJ
2 | 7 | 1 | 9 | 2 | 0 | 0 | 2.7.1.9.2 | MTO
2 | 7 | 1 | 9 | 2 | 0 | 1 | 2.7.1.9 | MTO For Architectural Works - W007S | BK-W007S-PEDCO-110-AR-MT-0001 | BK-W007S-PEDCO-110-AR-MT-0001 | BK | W007S | PEDCO | 110 | AR | MT | 0001 | F8Z-708046 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 10 | 0 | 0 | 0 | 2.7.1.10 | Civil
2 | 7 | 1 | 10 | 1 | 0 | 0 | 2.7.1.10.1 | Drawing/Diagram
2 | 7 | 1 | 10 | 1 | 0 | 1 | 2.7.1.10.1 | General Civil Layout - W007S | BK-W007S-PEDCO-110-CV-PY-0001 | BK-W007S-PEDCO-110-CV-PY-0001 | BK | W007S | PEDCO | 110 | CV | PY | 0001 | F4A-708047 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 10 | 1 | 0 | 2 | 2.7.1.10.1 | Civil and Structural drawings - W007S | BK-W007S-PEDCO-110-CV-PY-0002 | BK-W007S-PEDCO-110-CV-PY-0002 | BK | W007S | PEDCO | 110 | CV | PY | 0002 | F4S-708048 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 10 | 1 | 0 | 3 | 2.7.1.10.1 | Rough Grading Plans -W007S | BK-W007S-PEDCO-110-CV-DW-0001 | BK-W007S-PEDCO-110-CV-DW-0001 | BK | W007S | PEDCO | 110 | CV | DW | 0001 | F4S-708049 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 10 | 2 | 0 | 0 | 2.7.1.10.2 | Calculation
2 | 7 | 1 | 10 | 2 | 0 | 1 | 2.7.1.10.2 | Calculation Note For Heli Pad, Well Pad & Diesel Storage Pad - W007S | BK-W007S-PEDCO-110-CV-CN-0001 | BK-W007S-PEDCO-110-CV-CN-0001 | BK | W007S | PEDCO | 110 | CV | CN | 0001 | F0Z-708050 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 10 | 3 | 0 | 0 | 2.7.1.10.3 | MTO
2 | 7 | 1 | 10 | 3 | 0 | 1 | 2.7.1.10.3 | MTO For Civil Works - W007S | BK-W007S-PEDCO-110-CV-MT-0001 | BK-W007S-PEDCO-110-CV-MT-0001 | BK | W007S | PEDCO | 110 | CV | MT | 0001 | F8Z-708051 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 10 | 4 | 0 | 0 | 2.7.1.10.4 | Report
2 | 7 | 1 | 10 | 4 | 0 | 1 | 2.7.1.10 | SITE VISIT REPORT - MANIFOLD EXTENSION | BK-W007S-PEDCO-110-CV-RT-0001 | BK-W007S-PEDCO-110-CV-RT-0001 | BK | W007S | PEDCO | 110 | CV | RT | 0001 | F0Z-708052 | AFC | IFC | 44683 | 44698 | 44710 | 15 | 12 | 27 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-18 | 0 |  | D00 | IFC | T-0840 | 2022-04-18 | 1401/01/29 | 0 | 0 | 0 | BK-SUR-ENG-GEN-01-04426 | 2022-05-24 | 1401/03/03 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65660 | 2022-05-17 | 1401/02/27 | 2022-05-29 | 1401/03/08 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0840 | 2022-04-18 | 1401/01/29 |  |  |  | BK-SUR-ENG-GEN-01-04426 | 2022-05-24 | 1401/03/03 | AP | [6 empty] | 1401-2294-65660 | 2022-05-17 | 1401/02/27 | 2022-05-29 | 1401/03/08 | CM
2 | 7 | 1 | 11 | 0 | 0 | 0 | 2.7.1.11 | Structure
2 | 7 | 1 | 11 | 1 | 0 | 0 | 2.7.1.11.1 | Drawing/Diagram
2 | 7 | 1 | 11 | 1 | 0 | 1 | 2.7.1.11.1 | Pipe Supports Foundation Drawing For Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ST-DW-0001 | BK-W007S-PEDCO-110-ST-DW-0001 | BK | W007S | PEDCO | 110 | ST | DW | 0001 | F4Q-708053 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 2 | 2.7.1.11.1 | Pipe Supports Structure Drawing For Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ST-DW-0002 | BK-W007S-PEDCO-110-ST-DW-0002 | BK | W007S | PEDCO | 110 | ST | DW | 0002 | F4M-708054 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 3 | 2.7.1.11.1 | Access Platforms Structure Plan & Details For Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ST-DW-0003 | BK-W007S-PEDCO-110-ST-DW-0003 | BK | W007S | PEDCO | 110 | ST | DW | 0003 | F4M-708055 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 4 | 2.7.1.11.1 | Access Platforms Foundation Drawing For Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ST-DW-0004 | BK-W007S-PEDCO-110-ST-DW-0004 | BK | W007S | PEDCO | 110 | ST | DW | 0004 | F4Q-708056 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 5 | 2.7.1.11.1 | Fuel Oil Storage Drum Detail Drawing For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0007 | BK-W007S-PEDCO-110-ST-DW-0007 | BK | W007S | PEDCO | 110 | ST | DW | 0007 | F4G-708057 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 6 | 2.7.1.11.1 | Foundation Drawing For Security Building For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0008 | BK-W007S-PEDCO-110-ST-DW-0008 | BK | W007S | PEDCO | 110 | ST | DW | 0008 | F4Q-708058 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 7 | 2.7.1.11.1 | Structural Drawing For Security Building For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0009 | BK-W007S-PEDCO-110-ST-DW-0009 | BK | W007S | PEDCO | 110 | ST | DW | 0009 | F4M-708059 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 8 | 2.7.1.11.1 | Foundation Drawing For Switchgear Building For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0010 | BK-W007S-PEDCO-110-ST-DW-0010 | BK | W007S | PEDCO | 110 | ST | DW | 0010 | F4Q-708060 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 9 | 2.7.1.11.1 | Structural Drawing For Switchgear Building For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0011 | BK-W007S-PEDCO-110-ST-DW-0011 | BK | W007S | PEDCO | 110 | ST | DW | 0011 | F4M-708061 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 10 | 2.7.1.11.1 | Foundation Drawing For Potable Water Tank For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0012 | BK-W007S-PEDCO-110-ST-DW-0012 | BK | W007S | PEDCO | 110 | ST | DW | 0012 | F4Q-708062 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 11 | 2.7.1.11.1 | Foundation Drawing For Diesel Generator Shelter For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0013 | BK-W007S-PEDCO-110-ST-DW-0013 | BK | W007S | PEDCO | 110 | ST | DW | 0013 | F4Q-708063 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 12 | 2.7.1.11.1 | Structural Drawing For Diesel Generator Shelter For Well Pads - W007S | BK-W007S-PEDCO-110-ST-DW-0014 | BK-W007S-PEDCO-110-ST-DW-0014 | BK | W007S | PEDCO | 110 | ST | DW | 0014 | F4M-708064 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 13 | 2.7.1.11.1 | Platform Structure Drawing - W007S | BK-W007S-PEDCO-110-ST-DW-0016 | BK-W007S-PEDCO-110-ST-DW-0016 | BK | W007S | PEDCO | 110 | ST | DW | 0016 | F4M-708065 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 15 | 2.7.1.11.1 | Foundation Drawing For Oil Pump | BK-W007S-PEDCO-110-ST-DW-0018 | BK-W007S-PEDCO-110-ST-DW-0018 | BK | W007S | PEDCO | 110 | ST | DW | 0018 | F4Q-708066 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 16 | 2.7.1.11.1 | Sump Pit Structural Drawing for Oil Pump | BK-W007S-PEDCO-110-ST-DW-0019 | BK-W007S-PEDCO-110-ST-DW-0019 | BK | W007S | PEDCO | 110 | ST | DW | 0019 | F4M-708067 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 1 | 0 | 17 | 2.7.1.11.1 | Foundation Drawing For Transmission Line Tower - W007S | BK-W007S-PEDCO-110-ST-DW-0020 | BK-W007S-PEDCO-110-ST-DW-0020 | BK | W007S | PEDCO | 110 | ST | DW | 0020 | F4Q-708068 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 11 | 2 | 0 | 0 | 2.7.1.11.2 | MTO
2 | 7 | 1 | 11 | 2 | 0 | 1 | 2.7.1.11 | MTO For Structural Works - W007S & Manifold Extension | BK-W007S-PEDCO-110-ST-MT-0001 | BK-W007S-PEDCO-110-ST-MT-0001 | BK | W007S | PEDCO | 110 | ST | MT | 0001 | F8Z-708069 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 12 | 0 | 0 | 0 | 2.7.1.12 | Geotechnic/Geoelectric
2 | 7 | 1 | 12 | 1 | 0 | 0 | 2.7.1.12.1 | Geotechnic
2 | 7 | 1 | 12 | 1 | 1 | 0 | 2.7.12.1.1 | Report
2 | 7 | 1 | 12 | 1 | 1 | 1 | 2.7.1.12.1.1.1 | Geotechnical Investigation Report - W007S | BK-W007S-PEDCO-110-GT-RT-0001 | BK-W007S-PEDCO-110-GT-RT-0001 | BK | W007S | PEDCO | 110 | GT | RT | 0001 | F0Z-708070 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 12 | 1 | 2 | 0 | 2.7.12.1.2 | Drawing/Diagram
2 | 7 | 1 | 12 | 1 | 2 | 1 | 2.7.1.12.1.2.1 | Flow line Plan & Profile Drawings - W007S | BK-W007S-PEDCO-110-SU-DW-0001 | BK-W007S-PEDCO-110-SU-DW-0001 | BK | W007S | PEDCO | 110 | SU | DW | 0001 | F4A-708071 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 1 | 12 | 1 | 2 | 2 | 2.7.1.12.1.2.2 | Over Head Line Plan and Profile - W007S | BK-W007S-PEDCO-110-SU-DW-0002 | BK-W007S-PEDCO-110-SU-DW-0002 | BK | W007S | PEDCO | 110 | SU | DW | 0002 | F4A-708072 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 0 | 0 | 0 | 0 | 2.7.2 | Procurement Engineering
2 | 7 | 2 | 1 | 0 | 0 | 0 | 2.7.2.1 | Mechanical
2 | 7 | 2 | 1 | 1 | 0 | 0 | 2.7.2.1.1 | Pump
2 | 7 | 2 | 1 | 1 | 1 | 0 | 2.7.1.1.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 1 | 1 | 1 | 1 | 2.7.2.1.1.1.1 | PMR For Pumps - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ME-MR-0001 | BK-W007S-PEDCO-110-ME-MR-0001 | BK | W007S | PEDCO | 110 | ME | MR | 0001 | F0Z-708073 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 1 | 1 | 2 | 0 | 2.7.1.1.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 1 | 1 | 2 | 1 | 2.7.2.1.1.2.1 | TBE For Pumps - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-ME-TB-0001 | BK-W007S-PEDCO-110-ME-TB-0001 | BK | W007S | PEDCO | 110 | ME | TB | 0001 | F0Z-708074 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 1 | 2 | 0 | 0 | 2.7.2.1.2 | Drum
2 | 7 | 2 | 1 | 2 | 1 | 0 | 2.7.1.2.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 1 | 2 | 1 | 1 | 2.7.2.1.2.1.1 | PMR For Drums - W007S | BK-W007S-PEDCO-110-ME-MR-0002 | BK-W007S-PEDCO-110-ME-MR-0002 | BK | W007S | PEDCO | 110 | ME | MR | 0002 | F0Z-708075 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 1 | 2 | 2 | 0 | 2.7.1.2.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 1 | 2 | 2 | 1 | 2.7.2.1.2.2.1 | TBE For Drums - W007S | BK-W007S-PEDCO-110-ME-TB-0002 | BK-W007S-PEDCO-110-ME-TB-0002 | BK | W007S | PEDCO | 110 | ME | TB | 0002 | F0Z-708076 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 1 | 3 | 0 | 0 | 2.7.2.1.3 | Elevated Tank
2 | 7 | 2 | 1 | 3 | 1 | 0 | 2.7.1.3.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 1 | 3 | 1 | 1 | 2.7.2.1.3.1.1 | PMR For Potable Tanks - W007S | BK-W007S-PEDCO-110-ME-MR-0003 | BK-W007S-PEDCO-110-ME-MR-0003 | BK | W007S | PEDCO | 110 | ME | MR | 0003 | F0Z-708077 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 1 | 3 | 2 | 0 | 2.7.1.3.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 1 | 3 | 2 | 1 | 2.7.2.1.3.2.1 | TBE For Potable Tanks - W007S | BK-W007S-PEDCO-110-ME-TB-0003 | BK-W007S-PEDCO-110-ME-TB-0003 | BK | W007S | PEDCO | 110 | ME | TB | 0003 | F0Z-708078 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 2 | 0 | 0 | 0 | 2.7.2.2 | HVAC
2 | 7 | 2 | 2 | 1 | 0 | 0 | 2.7.2.2.1 | Main HVAC Equipment
2 | 7 | 2 | 2 | 1 | 1 | 0 | 2.7.2.1.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 2 | 1 | 1 | 1 | 2.7.2.2.1.1.1 | PMR For Main HVAC Equipment - W007S | BK-W007S-PEDCO-110-HV-MR-0001 | BK-W007S-PEDCO-110-HV-MR-0001 | BK | W007S | PEDCO | 110 | HV | MR | 0001 | F0Z-708079 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 2 | 1 | 2 | 0 | 2.7.2.1.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 2 | 1 | 2 | 1 | 2.7.2.2.1.2.1 | TBE For Main HVAC Equipment - W007S | BK-W007S-PEDCO-110-HV-TB-0001 | BK-W007S-PEDCO-110-HV-TB-0001 | BK | W007S | PEDCO | 110 | HV | TB | 0001 | F0Z-708080 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 0 | 0 | 0 | 2.7.2.3 | Piping
2 | 7 | 2 | 3 | 1 | 0 | 0 | 2.7.2.3.1 | Pipes
2 | 7 | 2 | 3 | 1 | 1 | 0 | 2.7.3.1.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 3 | 1 | 1 | 1 | 2.7.2.3.1.1.1 | PMR For Pipes - W007S | BK-W007S-PEDCO-110-PI-MR-0001 | BK-W007S-PEDCO-110-PI-MR-0001 | BK | W007S | PEDCO | 110 | PI | MR | 0001 | F0Z-708081 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 1 | 2 | 0 | 2.7.3.1.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 1 | 2 | 1 | 2.7.2.3.1.2.1 | TBE For Pipes - W007S | BK-W007S-PEDCO-110-PI-TB-0001 | BK-W007S-PEDCO-110-PI-TB-0001 | BK | W007S | PEDCO | 110 | PI | TB | 0001 | F0Z-708082 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 2 | 0 | 0 | 2.7.2.3.2 | Fittings
2 | 7 | 2 | 3 | 2 | 1 | 0 | 2.7.3.2.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 3 | 2 | 1 | 1 | 2.7.2.3.2.1.1 | PMR For Fittings - W007S | BK-W007S-PEDCO-110-PI-MR-0002 | BK-W007S-PEDCO-110-PI-MR-0002 | BK | W007S | PEDCO | 110 | PI | MR | 0002 | F0Z-708083 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 2 | 2 | 0 | 2.7.3.2.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 2 | 2 | 1 | 2.7.2.3.2.2.1 | TBE For Fitting - W007S | BK-W007S-PEDCO-110-PI-TB-0002 | BK-W007S-PEDCO-110-PI-TB-0002 | BK | W007S | PEDCO | 110 | PI | TB | 0002 | F0Z-708084 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 3 | 0 | 0 | 2.7.2.3.3 | Flanges
2 | 7 | 2 | 3 | 3 | 1 | 0 | 2.7.3.3.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 3 | 3 | 1 | 1 | 2.7.2.3.3.1.1 | PMR For Flanges - W007S | BK-W007S-PEDCO-110-PI-MR-0003 | BK-W007S-PEDCO-110-PI-MR-0003 | BK | W007S | PEDCO | 110 | PI | MR | 0003 | F0Z-708085 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 3 | 2 | 0 | 2.7.3.3.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 3 | 2 | 1 | 2.7.2.3.3.2.1 | TBE For Flanges - W007S | BK-W007S-PEDCO-110-PI-TB-0003 | BK-W007S-PEDCO-110-PI-TB-0003 | BK | W007S | PEDCO | 110 | PI | TB | 0003 | F0Z-708086 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 4 | 0 | 0 | 2.7.2.3.4 | Manual Valves
2 | 7 | 2 | 3 | 4 | 1 | 0 | 2.7.3.4.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 3 | 4 | 1 | 1 | 2.7.2.3.4.1.1 | PMR For Manual Valves - W007S | BK-W007S-PEDCO-110-PI-MR-0004 | BK-W007S-PEDCO-110-PI-MR-0004 | BK | W007S | PEDCO | 110 | PI | MR | 0004 | F0Z-708087 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 4 | 2 | 0 | 2.7.3.4.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 4 | 2 | 1 | 2.7.2.3.4.2.1 | TBE For Manual Valves - W007S | BK-W007S-PEDCO-110-PI-TB-0004 | BK-W007S-PEDCO-110-PI-TB-0004 | BK | W007S | PEDCO | 110 | PI | TB | 0004 | F0Z-708088 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 5 | 0 | 0 | 2.7.2.3.5 | Gaskets
2 | 7 | 2 | 3 | 5 | 1 | 0 | 2.7.3.5.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 3 | 5 | 1 | 1 | 2.7.2.3.5.1.1 | PMR For Gaskets - W007S | BK-W007S-PEDCO-110-PI-MR-0005 | BK-W007S-PEDCO-110-PI-MR-0005 | BK | W007S | PEDCO | 110 | PI | MR | 0005 | F0Z-708089 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 5 | 2 | 0 | 2.7.3.5.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 5 | 2 | 1 | 2.7.2.3.5.2.1 | TBE For Gaskets - W007S | BK-W007S-PEDCO-110-PI-TB-0005 | BK-W007S-PEDCO-110-PI-TB-0005 | BK | W007S | PEDCO | 110 | PI | TB | 0005 | F0Z-708090 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 6 | 0 | 0 | 2.7.2.3.6 | Bolt & Nuts
2 | 7 | 2 | 3 | 6 | 1 | 0 | 2.7.3.6.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 3 | 6 | 1 | 1 | 2.7.2.3.6.1.1 | PMR For Bolt/Nuts - W007S | BK-W007S-PEDCO-110-PI-MR-0006 | BK-W007S-PEDCO-110-PI-MR-0006 | BK | W007S | PEDCO | 110 | PI | MR | 0006 | F0Z-708091 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 6 | 2 | 0 | 2.7.3.6.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 6 | 2 | 1 | 2.7.2.3.6.2.1 | TBE For Bolt/Nuts - W007S | BK-W007S-PEDCO-110-PI-TB-0006 | BK-W007S-PEDCO-110-PI-TB-0006 | BK | W007S | PEDCO | 110 | PI | TB | 0006 | F0Z-708092 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 7 | 0 | 0 | 2.7.2.3.7 | Sampling Connection
2 | 7 | 2 | 3 | 7 | 1 | 0 | 2.7.3.7.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 3 | 7 | 1 | 1 | 2.7.2.3.7.1.1 | PMR For Sampling Connection Set - W007S | BK-W007S-PEDCO-110-PI-MR-0007 | BK-W007S-PEDCO-110-PI-MR-0007 | BK | W007S | PEDCO | 110 | PI | MR | 0007 | F0Z-708093 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 7 | 2 | 0 | 2.7.3.7.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 7 | 2 | 1 | 2.7.2.3.7.2.1 | TBE For Sampling Connection - W007S | BK-W007S-PEDCO-110-PI-TB-0007 | BK-W007S-PEDCO-110-PI-TB-0007 | BK | W007S | PEDCO | 110 | PI | TB | 0007 | F0Z-708094 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 8 | 0 | 0 | 2.7.2.3.8 | Stone Trap
2 | 7 | 2 | 3 | 8 | 1 | 0 | 2.7.3.8.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 3 | 8 | 1 | 1 | 2.7.2.3.8.1.1 | PMR For Stone Trap - W007S | BK-W007S-PEDCO-110-PI-MR-0008 | BK-W007S-PEDCO-110-PI-MR-0008 | BK | W007S | PEDCO | 110 | PI | MR | 0008 | F0Z-708095 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 8 | 2 | 0 | 2.7.3.8.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 8 | 2 | 1 | 2.7.2.3.8.2.1 | TBE For Stone Trap - W007S | BK-W007S-PEDCO-110-PI-TB-0008 | BK-W007S-PEDCO-110-PI-TB-0008 | BK | W007S | PEDCO | 110 | PI | TB | 0008 | F0Z-708096 | IFI | IFI | 44719 | 0 | 0 | -44719 | 0 | -44719 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-24 | 2022-05-24 |  | D00 | IFI | T-0996 | 2022-05-24 | 1401/03/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0996 | 2022-05-24 | 1401/03/03
2 | 7 | 2 | 3 | 9 | 0 | 0 | 2.7.2.3.9 | Pipe Support
2 | 7 | 2 | 3 | 9 | 1 | 0 | 2.7.3.9.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 3 | 9 | 1 | 1 | 2.7.2.3.9.1.1 | PMR For Pipe Support - W007S | BK-W007S-PEDCO-110-PI-MR-0009 | BK-W007S-PEDCO-110-PI-MR-0009 | BK | W007S | PEDCO | 110 | PI | MR | 0009 | F0Z-708097 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 3 | 9 | 2 | 0 | 2.7.3.9.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 3 | 9 | 2 | 1 | 2.7.2.3.9.2.1 | TBE For Pipe Support - W007S | BK-W007S-PEDCO-110-PI-TB-0009 | BK-W007S-PEDCO-110-PI-TB-0009 | BK | W007S | PEDCO | 110 | PI | TB | 0009 | F0Z-708098 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 4 | 0 | 0 | 0 | 2.7.2.4 | Pipeline
2 | 7 | 2 | 4 | 1 | 0 | 0 | 2.7.2.4.1 | Line Pipe
2 | 7 | 2 | 4 | 1 | 1 | 0 | 2.7.4.1.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 4 | 1 | 1 | 1 | 2.7.2.4.1.1.1 | PMR For Line Pipes - W007S | BK-W007S-PEDCO-110-PL-MR-0001 | BK-W007S-PEDCO-110-PL-MR-0001 | BK | W007S | PEDCO | 110 | PL | MR | 0001 | F0Z-708099 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 4 | 1 | 2 | 0 | 2.7.4.1.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 4 | 1 | 2 | 1 | 2.7.2.4.1.2.1 | TBE FOR LINE PIPES – W007S | BK-W007S-PEDCO-110-PL-TB-0001 | BK-W007S-PEDCO-110-PL-TB-0001 | BK | W007S | PEDCO | 110 | PL | TB | 0001 | F0Z-708100 | IFI | IFI | 44625 | 44630 | 44634 | 5 | 4 | 9 | IFI | 44709 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 2022-05-14 |  | D01 | IFI | T-0944 | 2022-05-14 | 1401/02/24 | T-0944 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W008N-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-W007S-PEDCO-110-PL-TB-0001-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0604 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PPL-00-03409 | 2022-03-08 | 1400/12/17 | C4-RJ | [6 empty] | 1400-2294-443269 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/23 | CM | [10 empty] | D01 | IFI | T-0944 | 2022-05-14 | 1401/02/24 | T-0944 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-PPL-01-04412 | 2022-05-23 | 1401/03/02 | CM-C3 | PEDCO-CRS-BK-W007S-PEDCO-110-PL-TB-0001-D00 | [11 empty] | NISOC-CRS-BK-W007S-PEDCO-110-PL-TB-0001-D00
2 | 7 | 2 | 4 | 2 | 0 | 0 | 2.7.2.4.2 | Line Pipe
2 | 7 | 2 | 4 | 2 | 1 | 0 | 2.7.4.2.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 4 | 2 | 1 | 1 | 2.7.2.4.2.1.1 | PMR For Flow Line Support - W007S | BK-W007S-PEDCO-110-PL-MR-0002 | BK-W007S-PEDCO-110-PL-MR-0002 | BK | W007S | PEDCO | 110 | PL | MR | 0002 | F0Z-708101 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 4 | 2 | 2 | 0 | 2.7.4.2.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 4 | 2 | 2 | 1 | 2.7.2.4.2.2.1 | TBE For Flow Line Support - W007S | BK-W007S-PEDCO-110-PL-TB-0002 | BK-W007S-PEDCO-110-PL-TB-0002 | BK | W007S | PEDCO | 110 | PL | TB | 0002 | F0Z-708102 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 0 | 0 | 0 | 2.7.2.5 | Control & Instrumentation
2 | 7 | 2 | 5 | 1 | 0 | 0 | 2.7.2.5.1 | Control System/Console/Furniture
2 | 7 | 2 | 5 | 1 | 1 | 0 | 2.7.5.1.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 1 | 1 | 1 | 2.7.2.5.1.1.1 | PMR For Control System/Console/Furniture - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0001 | BK-W007S-PEDCO-110-IN-MR-0001 | BK | W007S | PEDCO | 110 | IN | MR | 0001 | F0Z-708103 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 1 | 2 | 0 | 2.7.5.1.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 1 | 2 | 1 | 2.7.2.5.1.2.1 | TBE/TBA For Control System/Console/Furniture - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0001 | BK-W007S-PEDCO-110-IN-TB-0001 | BK | W007S | PEDCO | 110 | IN | TB | 0001 | F0Z-708104 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 2 | 0 | 0 | 2.7.2.5.2 | ESD System
2 | 7 | 2 | 5 | 2 | 1 | 0 | 2.7.5.2.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 2 | 1 | 1 | 2.7.2.5.2.1.1 | PMR For ESD System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0002 | BK-W007S-PEDCO-110-IN-MR-0002 | BK | W007S | PEDCO | 110 | IN | MR | 0002 | F0Z-708105 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 2 | 2 | 0 | 2.7.5.2.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 2 | 2 | 1 | 2.7.2.5.2.2.1 | TBE/TBA For ESD System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0002 | BK-W007S-PEDCO-110-IN-TB-0002 | BK | W007S | PEDCO | 110 | IN | TB | 0002 | F0Z-708106 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 3 | 0 | 0 | 2.7.2.5.3 | F&G System
2 | 7 | 2 | 5 | 3 | 1 | 0 | 2.7.5.3.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 3 | 1 | 1 | 2.7.2.5.3.1.1 | PMR For F&G System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0003 | BK-W007S-PEDCO-110-IN-MR-0003 | BK | W007S | PEDCO | 110 | IN | MR | 0003 | F0Z-708107 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 3 | 2 | 0 | 2.7.5.3.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 3 | 2 | 1 | 2.7.2.5.3.2.1 | TBE/TBA For F&G System - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0003 | BK-W007S-PEDCO-110-IN-TB-0003 | BK | W007S | PEDCO | 110 | IN | TB | 0003 | F0Z-708108 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 4 | 0 | 0 | 2.7.2.5.4 | ON/OFF & Shutdown Valves
2 | 7 | 2 | 5 | 4 | 1 | 0 | 2.7.5.4.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 4 | 1 | 1 | 2.7.2.5.4.1.1 | PMR For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0004 | BK-W007S-PEDCO-110-IN-MR-0004 | BK | W007S | PEDCO | 110 | IN | MR | 0004 | F0Z-708109 | IFI | IFI | 44660 | 44660 | 44663 | 0 | 3 | 3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-26 | 2022-03-26 |  | D00 | IFI | T-0738 | 2022-03-26 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03791 | 2022-04-09 | 1401/01/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-16060 | 2022-04-09 | 1401/01/20 | 2022-04-12 | 1401/01/23 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0738 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03791 | 2022-04-09 | 1401/01/20 | CM-C3 | [6 empty] | 1401-2294-16060 | 2022-04-09 | 1401/01/20 | 2022-04-12 | 1401/01/23 | CM
2 | 7 | 2 | 5 | 4 | 2 | 0 | 2.7.5.4.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 4 | 2 | 1 | 2.7.2.5.4.2.1 | TBE/TBA For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0004 | BK-W007S-PEDCO-110-IN-TB-0004 | BK | W007S | PEDCO | 110 | IN | TB | 0004 | F0Z-708110 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 5 | 0 | 0 | 2.7.2.5.5 | Control Valves
2 | 7 | 2 | 5 | 5 | 1 | 0 | 2.7.5.5.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 5 | 1 | 1 | 2.7.2.5.5.1.1 | PMR For Control Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0005 | BK-W007S-PEDCO-110-IN-MR-0005 | BK | W007S | PEDCO | 110 | IN | MR | 0005 | F0Z-708111 | IFI | IFI | 44648 | 44662 | 44668 | 14 | 6 | 20 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-14 | 2022-03-14 |  | D00 | IFI | T-0733 | 2022-03-14 | 1400/12/23 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03732 | 2022-04-05 | 1401/01/16 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-18032 | 2022-04-11 | 1401/01/22 | 2022-04-17 | 1401/01/28 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0733 | 2022-03-14 | 1400/12/23 |  |  |  | BK-SUR-ENG-INS-01-03732 | 2022-04-05 | 1401/01/16 | CM-C3 | [6 empty] | 1401-2294-18032 | 2022-04-11 | 1401/01/22 | 2022-04-17 | 1401/01/28 | CM
2 | 7 | 2 | 5 | 5 | 2 | 0 | 2.7.5.5.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 5 | 2 | 1 | 2.7.2.5.5.2.1 | TBE/TBA For Control Valves - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0005 | BK-W007S-PEDCO-110-IN-TB-0005 | BK | W007S | PEDCO | 110 | IN | TB | 0005 | F0Z-708112 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 6 | 0 | 0 | 2.7.2.5.6 | Pressure Safety Valves (PSV)
2 | 7 | 2 | 5 | 6 | 1 | 0 | 2.7.5.6.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 6 | 1 | 1 | 2.7.2.5.6.1.1 | PMR For Pressure Safety Valves (PSV) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0006 | BK-W007S-PEDCO-110-IN-MR-0006 | BK | W007S | PEDCO | 110 | IN | MR | 0006 | F0Z-708113 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 6 | 2 | 0 | 2.7.5.6.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 6 | 2 | 1 | 2.7.2.5.6.2.1 | TBE/TBA For Pressure Safety Valves (PSV) - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0006 | BK-W007S-PEDCO-110-IN-TB-0006 | BK | W007S | PEDCO | 110 | IN | TB | 0006 | F0Z-708114 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 7 | 0 | 0 | 2.7.2.5.7 | F&G Devices
2 | 7 | 2 | 5 | 7 | 1 | 0 | 2.7.5.7.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 7 | 1 | 1 | 2.7.2.5.7.1.1 | PMR For F&G Detector - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0007 | BK-W007S-PEDCO-110-IN-MR-0007 | BK | W007S | PEDCO | 110 | IN | MR | 0007 | F0Z-708115 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 7 | 2 | 0 | 2.7.5.7.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 7 | 2 | 1 | 2.7.2.5.7.2.1 | TBE/TBA For F&G Detector - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0007 | BK-W007S-PEDCO-110-IN-TB-0007 | BK | W007S | PEDCO | 110 | IN | TB | 0007 | F0Z-708116 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 8 | 0 | 0 | 2.7.2.5.8 | Orifice and Restriction Orifice Plate
2 | 7 | 2 | 5 | 8 | 1 | 0 | 2.7.5.8.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 8 | 1 | 1 | 2.7.2.5.8.1.1 | PMR For Orifice and Restriction Orifice Plate - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0008 | BK-W007S-PEDCO-110-IN-MR-0008 | BK | W007S | PEDCO | 110 | IN | MR | 0008 | F0Z-708117 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 8 | 2 | 0 | 2.7.5.8.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 8 | 2 | 1 | 2.7.2.5.8.2.1 | TBE/TBA For Orifice and Restriction Orifice Plate - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0008 | BK-W007S-PEDCO-110-IN-TB-0008 | BK | W007S | PEDCO | 110 | IN | TB | 0008 | F0Z-708118 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 9 | 0 | 0 | 2.7.2.5.9 | Corrosion Coupon/Probe
2 | 7 | 2 | 5 | 9 | 1 | 0 | 2.7.5.9.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 9 | 1 | 1 | 2.7.2.5.9.1.1 | PMR For Corrosion Coupon/Probe - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0009 | BK-W007S-PEDCO-110-IN-MR-0009 | BK | W007S | PEDCO | 110 | IN | MR | 0009 | F0Z-708119 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 9 | 2 | 0 | 2.7.5.9.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 9 | 2 | 1 | 2.7.2.5.9.2.1 | TBE/TBA For Corrosion Coupon/Probe - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0009 | BK-W007S-PEDCO-110-IN-TB-0009 | BK | W007S | PEDCO | 110 | IN | TB | 0009 | F0Z-708120 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 10 | 0 | 0 | 2.7.2.5.10 | Pressure Transmitter
2 | 7 | 2 | 5 | 10 | 1 | 0 | 2.7.5.10.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 10 | 1 | 1 | 2.7.2.5.10.1.1 | PMR For Pressure Transmitter/Pressure Switch - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0010 | BK-W007S-PEDCO-110-IN-MR-0010 | BK | W007S | PEDCO | 110 | IN | MR | 0010 | F0Z-708121 | IFI | IFI | 44591 | 44227 | 44593 | -364 | 366 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-16 | 2022-01-16 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C3 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM
2 | 7 | 2 | 5 | 10 | 2 | 0 | 2.7.5.10.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 10 | 2 | 1 | 2.7.2.5.10.2.1 | TBE/TBA For Pressure Transmitter/Pressure Switch - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0010 | BK-W007S-PEDCO-110-IN-TB-0010 | BK | W007S | PEDCO | 110 | IN | TB | 0010 | F0Z-708122 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 11 | 0 | 0 | 2.7.2.5.11 | Flow Transmitter/ Diff. Pressure Transmitter
2 | 7 | 2 | 5 | 11 | 1 | 0 | 2.7.5.11.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 11 | 1 | 1 | 2.7.2.5.11.1.1 | PMR For Flow Transmitter/ Diff. Pressure Transmitter - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0011 | BK-W007S-PEDCO-110-IN-MR-0011 | BK | W007S | PEDCO | 110 | IN | MR | 0011 | F0Z-708123 | IFI | IFI | 44591 | 44227 | 44593 | -364 | 366 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-16 | 2022-01-16 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C3 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM
2 | 7 | 2 | 5 | 11 | 2 | 0 | 2.7.5.11.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 11 | 2 | 1 | 2.7.2.5.11.2.1 | TBE/TBA For Flow Transmitter/ Diff. Pressure Transmitter - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0011 | BK-W007S-PEDCO-110-IN-TB-0011 | BK | W007S | PEDCO | 110 | IN | TB | 0011 | F0Z-708124 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 12 | 0 | 0 | 2.7.2.5.12 | Instrument/F&G Cable
2 | 7 | 2 | 5 | 12 | 1 | 0 | 2.7.5.12.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 12 | 1 | 1 | 2.7.2.5.12.1.1 | PMR For Instrument/F&G Cable - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0012 | BK-W007S-PEDCO-110-IN-MR-0012 | BK | W007S | PEDCO | 110 | IN | MR | 0012 | F0Z-708125 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 12 | 2 | 0 | 2.7.5.12.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 12 | 2 | 1 | 2.7.2.5.12.2.1 | TBE/TBA For Instrument/F&G Cable - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0012 | BK-W007S-PEDCO-110-IN-TB-0012 | BK | W007S | PEDCO | 110 | IN | TB | 0012 | F0Z-708126 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 13 | 0 | 0 | 2.7.2.5.13 | Instrument/F&G Junction box and Gland
2 | 7 | 2 | 5 | 13 | 1 | 0 | 2.7.5.13.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 13 | 1 | 1 | 2.7.2.5.13.1.1 | PMR For Instrument/F&G Junction box and Gland - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0013 | BK-W007S-PEDCO-110-IN-MR-0013 | BK | W007S | PEDCO | 110 | IN | MR | 0013 | F0Z-708127 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 13 | 2 | 0 | 2.7.5.13.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 13 | 2 | 1 | 2.7.2.5.13.2.1 | TBE/TBA For Instrument/F&G Junction box and Gland - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0013 | BK-W007S-PEDCO-110-IN-TB-0013 | BK | W007S | PEDCO | 110 | IN | TB | 0013 | F0Z-708128 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 14 | 0 | 0 | 2.7.2.5.14 | Instrument Installation Accessories
2 | 7 | 2 | 5 | 14 | 1 | 0 | 2.7.5.14.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 14 | 1 | 1 | 2.7.2.5.14.1.1 | PMR For Bulk Item and Installation Accessories - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-MR-0014 | BK-W007S-PEDCO-110-IN-MR-0014 | BK | W007S | PEDCO | 110 | IN | MR | 0014 | F0Z-708129 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 14 | 2 | 0 | 2.7.5.14.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 14 | 2 | 1 | 2.7.2.5.14.2.1 | TBE/TBA For Bulk Item and Installation Accessories - Extension of Binak B/C Manifold | BK-W007S-PEDCO-110-IN-TB-0014 | BK-W007S-PEDCO-110-IN-TB-0014 | BK | W007S | PEDCO | 110 | IN | TB | 0014 | F0Z-708130 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 15 | 0 | 0 | 2.7.2.5.15 | Differential Pressure/Pressure Gauge
2 | 7 | 2 | 5 | 15 | 1 | 0 | 2.7.5.15.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 15 | 1 | 1 | 2.7.2.5.15.1.1 | PMR For Differential Pressure/Pressure Gauge - Manifold & W007S | BK-W007S-PEDCO-110-IN-MR-0015 | BK-W007S-PEDCO-110-IN-MR-0015 | BK | W007S | PEDCO | 110 | IN | MR | 0015 | F0Z-708131 | IFI | IFI | 44591 | 44227 | 44593 | -364 | 366 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-16 | 2022-01-16 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C3 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM
2 | 7 | 2 | 5 | 15 | 2 | 0 | 2.7.5.15.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 15 | 2 | 1 | 2.7.2.5.15.2.1 | TBE/TBA For Differential Pressure/Pressure Gauge - Manifold & W007S | BK-W007S-PEDCO-110-IN-TB-0015 | BK-W007S-PEDCO-110-IN-TB-0015 | BK | W007S | PEDCO | 110 | IN | TB | 0015 | F0Z-708132 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 16 | 0 | 0 | 2.7.2.5.16 | Temperature Gauge
2 | 7 | 2 | 5 | 16 | 1 | 0 | 2.7.5.16.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 16 | 1 | 1 | 2.7.2.5.16.1.1 | PMR For Temperature Gauge - Manifold & W007S | BK-W007S-PEDCO-110-IN-MR-0016 | BK-W007S-PEDCO-110-IN-MR-0016 | BK | W007S | PEDCO | 110 | IN | MR | 0016 | F0Z-708133 | IFI | IFI | 44591 | 44227 | 44593 | -364 | 366 | 2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-16 | 2022-01-16 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0471 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-INS-00-02831 | 2022-01-26 | 1400/11/06 | CM-C3 | [6 empty] | 1400-2294-390714 | 2021-01-31 | 1400/11/11 | 2022-02-01 | 1400/11/12 | CM
2 | 7 | 2 | 5 | 16 | 2 | 0 | 2.7.5.16.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 16 | 2 | 1 | 2.7.2.5.16.2.1 | TBE/TBA For Temperature Gauge - Manifold & W007S | BK-W007S-PEDCO-110-IN-TB-0016 | BK-W007S-PEDCO-110-IN-TB-0016 | BK | W007S | PEDCO | 110 | IN | TB | 0016 | F0Z-708134 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 17 | 0 | 0 | 2.7.2.5.17 | Instrument Tube and Fitting
2 | 7 | 2 | 5 | 17 | 1 | 0 | 2.7.5.17.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 17 | 1 | 1 | 2.7.2.5.17.1.1 | PMR For Instrument Tube and Fitting - Manifold & W007S | BK-W007S-PEDCO-110-IN-MR-0017 | BK-W007S-PEDCO-110-IN-MR-0017 | BK | W007S | PEDCO | 110 | IN | MR | 0017 | F0Z-708135 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 17 | 2 | 0 | 2.7.5.17.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 17 | 2 | 1 | 2.7.2.5.17.2.1 | TBE/TBA For Instrument Tube and Fitting - Manifold & W007S | BK-W007S-PEDCO-110-IN-TB-0017 | BK-W007S-PEDCO-110-IN-TB-0017 | BK | W007S | PEDCO | 110 | IN | TB | 0017 | F0Z-708136 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 18 | 0 | 0 | 2.7.2.5.18 | Instrument Cable Tray
2 | 7 | 2 | 5 | 18 | 1 | 0 | 2.7.5.18.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 5 | 18 | 1 | 1 | 2.7.2.5.18.1.1 | PMR For Instrument Cable Tray/Ladder - Manifold & W007S | BK-W007S-PEDCO-110-IN-MR-0018 | BK-W007S-PEDCO-110-IN-MR-0018 | BK | W007S | PEDCO | 110 | IN | MR | 0018 | F0Z-708137 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 5 | 18 | 2 | 0 | 2.7.5.18.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 5 | 18 | 2 | 1 | 2.7.2.5.18.2.1 | TBE/TBA For Instrument Cable Tray/Ladder - Manifold & W007S | BK-W007S-PEDCO-110-IN-TB-0018 | BK-W007S-PEDCO-110-IN-TB-0018 | BK | W007S | PEDCO | 110 | IN | TB | 0018 | F0Z-708138 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 6 | 0 | 0 | 0 | 2.7.2.6 | Safety & Fire Fighting
2 | 7 | 2 | 6 | 1 | 0 | 0 | 2.7.2.6.1 | Fire Fighting and Safety Equipment
2 | 7 | 2 | 6 | 1 | 1 | 0 | 2.7.6.1.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 6 | 1 | 1 | 1 | 2.7.2.6.1.1.1 | PMR For Fire Fighting and Safety Equipment - Manifold & W007S | BK-W007S-PEDCO-110-SA-MR-0001 | BK-W007S-PEDCO-110-SA-MR-0001 | BK | W007S | PEDCO | 110 | SA | MR | 0001 | F0Z-708141 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 6 | 1 | 2 | 0 | 2.7.6.1.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 6 | 1 | 2 | 1 | 2.7.2.6.1.2.1 | TBE For Fire Fighting and Safety Equipment - Manifold & W007S | BK-W007S-PEDCO-110-SA-TB-0001 | BK-W007S-PEDCO-110-SA-TB-0001 | BK | W007S | PEDCO | 110 | SA | TB | 0001 | F0Z-708142 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 6 | 2 | 0 | 0 | 2.7.2.6.2 | Safety Sign
2 | 7 | 2 | 6 | 2 | 1 | 0 | 2.7.6.2.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 6 | 2 | 1 | 1 | 2.7.2.6.2.1.1 | PMR For Fire Safety Sign - Manifold & W007S | BK-W007S-PEDCO-110-SA-MR-0002 | BK-W007S-PEDCO-110-SA-MR-0002 | BK | W007S | PEDCO | 110 | SA | MR | 0002 | F0Z-708143 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 6 | 2 | 2 | 0 | 2.7.6.2.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 6 | 2 | 2 | 1 | 2.7.2.6.2.2.1 | TBE For Fire Safety Sign - Manifold & W007S | BK-W007S-PEDCO-110-SA-TB-0002 | BK-W007S-PEDCO-110-SA-TB-0002 | BK | W007S | PEDCO | 110 | SA | TB | 0002 | F0Z-708144 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 0 | 0 | 0 | 2.7.2.7 | Electrical
2 | 7 | 2 | 7 | 1 | 0 | 0 | 2.7.2.7.1 | LV Switchgear & MCC
2 | 7 | 2 | 7 | 1 | 1 | 0 | 2.7.7.1.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 1 | 1 | 1 | 2.7.2.7.1.1.1 | PMR For LV Switchgear & MCC - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0001 | BK-W007S-PEDCO-110-EL-MR-0001 | BK | W007S | PEDCO | 110 | EL | MR | 0001 | F0Z-708145 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 1 | 2 | 0 | 2.7.7.1.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 1 | 2 | 1 | 2.7.2.7.1.2.1 | TBE For LV Switchgear & MCC - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0001 | BK-W007S-PEDCO-110-EL-TB-0001 | BK | W007S | PEDCO | 110 | EL | TB | 0001 | F0Z-708146 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 2 | 0 | 0 | 2.7.2.7.2 | UPS System
2 | 7 | 2 | 7 | 2 | 1 | 0 | 2.7.7.2.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 2 | 1 | 1 | 2.7.2.7.2.1.1 | PMR For UPS System - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0002 | BK-W007S-PEDCO-110-EL-MR-0002 | BK | W007S | PEDCO | 110 | EL | MR | 0002 | F0Z-708147 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 2 | 2 | 0 | 2.7.7.2.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 2 | 2 | 1 | 2.7.2.7.2.2.1 | TBE For UPS System - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0002 | BK-W007S-PEDCO-110-EL-TB-0002 | BK | W007S | PEDCO | 110 | EL | TB | 0002 | F0Z-708148 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 3 | 0 | 0 | 2.7.2.7.3 | DC Charger
2 | 7 | 2 | 7 | 3 | 1 | 0 | 2.7.7.3.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 3 | 1 | 1 | 2.7.2.7.3.1.1 | PMR For DC Charger - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0003 | BK-W007S-PEDCO-110-EL-MR-0003 | BK | W007S | PEDCO | 110 | EL | MR | 0003 | F0Z-708149 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 3 | 2 | 0 | 2.7.7.3.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 3 | 2 | 1 | 2.7.2.7.3.2.1 | TBE For DC Charger - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0003 | BK-W007S-PEDCO-110-EL-TB-0003 | BK | W007S | PEDCO | 110 | EL | TB | 0003 | F0Z-708150 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 4 | 0 | 0 | 2.7.2.7.4 | Earthing & Lightning System
2 | 7 | 2 | 7 | 4 | 1 | 0 | 2.7.7.4.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 4 | 1 | 1 | 2.7.2.7.4.1.1 | PMR For Earthing & Lightning System - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0004 | BK-W007S-PEDCO-110-EL-MR-0004 | BK | W007S | PEDCO | 110 | EL | MR | 0004 | F0Z-708151 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 4 | 2 | 0 | 2.7.7.4.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 4 | 2 | 1 | 2.7.2.7.4.2.1 | TBE For Earthing & Lightning System - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0004 | BK-W007S-PEDCO-110-EL-TB-0004 | BK | W007S | PEDCO | 110 | EL | TB | 0004 | F0Z-708152 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 5 | 0 | 0 | 2.7.2.7.5 | Power & Control Cables
2 | 7 | 2 | 7 | 5 | 1 | 0 | 2.7.7.5.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 5 | 1 | 1 | 2.7.2.7.5.1.1 | PMR For Power & Control Cables - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0005 | BK-W007S-PEDCO-110-EL-MR-0005 | BK | W007S | PEDCO | 110 | EL | MR | 0005 | F0Z-708153 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 5 | 2 | 0 | 2.7.7.5.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 5 | 2 | 1 | 2.7.2.7.5.2.1 | TBE For Power & Control Cables - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0005 | BK-W007S-PEDCO-110-EL-TB-0005 | BK | W007S | PEDCO | 110 | EL | TB | 0005 | F0Z-708154 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 6 | 0 | 0 | 2.7.2.7.6 | Tray/Ladder and Accessories
2 | 7 | 2 | 7 | 6 | 1 | 0 | 2.7.7.6.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 6 | 1 | 1 | 2.7.2.7.6.1.1 | PMR For Tray/Ladder and Accessories - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0006 | BK-W007S-PEDCO-110-EL-MR-0006 | BK | W007S | PEDCO | 110 | EL | MR | 0006 | F0Z-708155 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 6 | 2 | 0 | 2.7.7.6.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 6 | 2 | 1 | 2.7.2.7.6.2.1 | TBE For Tray/Ladder and Accessories - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0006 | BK-W007S-PEDCO-110-EL-TB-0006 | BK | W007S | PEDCO | 110 | EL | TB | 0006 | F0Z-708156 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 7 | 0 | 0 | 2.7.2.7.7 | Electrical Bulk Items
2 | 7 | 2 | 7 | 7 | 1 | 0 | 2.7.7.7.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 7 | 1 | 1 | 2.7.2.7.7.1.1 | PMR For Electrical Bulk Items - Manifold & W007S | BK-W007S-PEDCO-110-EL-MR-0007 | BK-W007S-PEDCO-110-EL-MR-0007 | BK | W007S | PEDCO | 110 | EL | MR | 0007 | F0Z-708157 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 7 | 2 | 0 | 2.7.7.7.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 7 | 2 | 1 | 2.7.2.7.7.2.1 | TBE For Electrical Bulk Items - Manifold & W007S | BK-W007S-PEDCO-110-EL-TB-0007 | BK-W007S-PEDCO-110-EL-TB-0007 | BK | W007S | PEDCO | 110 | EL | TB | 0007 | F0Z-708158 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 8 | 0 | 0 | 2.7.2.7.8 | Transformers
2 | 7 | 2 | 7 | 8 | 1 | 0 | 2.7.7.8.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 8 | 1 | 1 | 2.7.2.7.8.1.1 | PMR For Transformers - W007S | BK-W007S-PEDCO-110-EL-MR-0008 | BK-W007S-PEDCO-110-EL-MR-0008 | BK | W007S | PEDCO | 110 | EL | MR | 0008 | F0Z-708159 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 8 | 2 | 0 | 2.7.7.8.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 8 | 2 | 1 | 2.7.2.7.8.2.1 | TBE For Transformers - W007S | BK-W007S-PEDCO-110-EL-TB-0008 | BK-W007S-PEDCO-110-EL-TB-0008 | BK | W007S | PEDCO | 110 | EL | TB | 0008 | F0Z-708160 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 9 | 0 | 0 | 2.7.2.7.9 | Emergency Diesel Generator
2 | 7 | 2 | 7 | 9 | 1 | 0 | 2.7.7.9.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 9 | 1 | 1 | 2.7.2.7.9.1.1 | PMR For Emergency Diesel Generator - W007S | BK-W007S-PEDCO-110-EL-MR-0009 | BK-W007S-PEDCO-110-EL-MR-0009 | BK | W007S | PEDCO | 110 | EL | MR | 0009 | F0Z-708161 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 9 | 2 | 0 | 2.7.7.9.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 9 | 2 | 1 | 2.7.2.7.9.2.1 | TBE For Emergency Diesel Generator - W007S | BK-W007S-PEDCO-110-EL-TB-0009 | BK-W007S-PEDCO-110-EL-TB-0009 | BK | W007S | PEDCO | 110 | EL | TB | 0009 | F0Z-708162 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 10 | 0 | 0 | 2.7.2.7.10 | Lighting & Distribution Main Panels
2 | 7 | 2 | 7 | 10 | 1 | 0 | 2.7.7.10.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 10 | 1 | 1 | 2.7.2.7.10.1.1 | PMR For Lighting & Distribution Main Panels - W007S | BK-W007S-PEDCO-110-EL-MR-0010 | BK-W007S-PEDCO-110-EL-MR-0010 | BK | W007S | PEDCO | 110 | EL | MR | 0010 | F0Z-708163 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 10 | 2 | 0 | 2.7.7.10.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 10 | 2 | 1 | 2.7.2.7.10.2.1 | TBE For Lighting & Distribution Main Panels - W007S | BK-W007S-PEDCO-110-EL-TB-0010 | BK-W007S-PEDCO-110-EL-TB-0010 | BK | W007S | PEDCO | 110 | EL | TB | 0010 | F0Z-708164 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 11 | 0 | 0 | 2.7.2.7.11 | Lighting and Small Power Equipment
2 | 7 | 2 | 7 | 11 | 1 | 0 | 2.7.7.11.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 11 | 1 | 1 | 2.7.2.7.11.1.1 | PMR For Lighting and Small Power Equipment - W007S | BK-W007S-PEDCO-110-EL-MR-0011 | BK-W007S-PEDCO-110-EL-MR-0011 | BK | W007S | PEDCO | 110 | EL | MR | 0011 | F0Z-708165 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 11 | 2 | 0 | 2.7.7.11.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 11 | 2 | 1 | 2.7.2.7.11.2.1 | TBE For Lighting and Small Power Equipment - W007S | BK-W007S-PEDCO-110-EL-TB-0011 | BK-W007S-PEDCO-110-EL-TB-0011 | BK | W007S | PEDCO | 110 | EL | TB | 0011 | F0Z-708166 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 12 | 0 | 0 | 2.7.2.7.12 | Capacitor Bank
2 | 7 | 2 | 7 | 12 | 1 | 0 | 2.7.7.12.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 12 | 1 | 1 | 2.7.2.7.12.1.1 | PMR For Capacitor Bank - W007S | BK-W007S-PEDCO-110-EL-MR-0012 | BK-W007S-PEDCO-110-EL-MR-0012 | BK | W007S | PEDCO | 110 | EL | MR | 0012 | F0Z-708167 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 12 | 2 | 0 | 2.7.7.12.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 12 | 2 | 1 | 2.7.2.7.12.2.1 | TBE For Capacitor Bank - W007S | BK-W007S-PEDCO-110-EL-TB-0012 | BK-W007S-PEDCO-110-EL-TB-0012 | BK | W007S | PEDCO | 110 | EL | TB | 0012 | F0Z-708168 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 13 | 0 | 0 | 2.7.2.7.13 | Transmission Over Head Line Equipment
2 | 7 | 2 | 7 | 13 | 1 | 0 | 2.7.7.13.1 | Purchase Material Requisition (PMR)
2 | 7 | 2 | 7 | 13 | 1 | 1 | 2.7.2.7.13.1.1 | PMR For Transmission Over head Line Equipment - W007S | BK-W007S-PEDCO-110-EL-MR-0013 | BK-W007S-PEDCO-110-EL-MR-0013 | BK | W007S | PEDCO | 110 | EL | MR | 0013 | F0Z-708169 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 2 | 7 | 13 | 2 | 0 | 2.7.7.13.2 | Technical Bid Evaluation (TBE)
2 | 7 | 2 | 7 | 13 | 2 | 1 | 2.7.2.7.13.2.1 | TBE For Transmission Over head Line Equipment - W007S | BK-W007S-PEDCO-110-EL-TB-0013 | BK-W007S-PEDCO-110-EL-TB-0013 | BK | W007S | PEDCO | 110 | EL | TB | 0013 | F0Z-708170 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 3 | 0 | 0 | 0 | 0 | 2.7.3 | Structure
2 | 7 | 3 | 0 | 1 | 0 | 0 | 2.7.3.1 | Steel Structure Items
2 | 7 | 3 | 0 | 1 | 1 | 0 | 2.7.3.1.1 | Purchase Material Requisition (PMR)
2 | 7 | 3 | 0 | 1 | 1 | 1 | 2.7.3.1.1.1 | PMR For Steel Structure Items - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-MR-0001 | BK-W007S-PEDCO-110-ST-MR-0001 | BK | W007S | PEDCO | 110 | ST | MR | 0001 | F0Z-708171 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 3 | 0 | 1 | 2 | 0 | 2.7.3.1.2 | Technical Bid Evaluation (TBE)
2 | 7 | 3 | 0 | 1 | 2 | 1 | 2.7.3.1.2.1 | TBE For Steel Structure Items - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-TB-0001 | BK-W007S-PEDCO-110-ST-TB-0001 | BK | W007S | PEDCO | 110 | ST | TB | 0001 | F0Z-708172 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 3 | 0 | 2 | 0 | 0 | 2.7.3.2 | Anchor Bolts
2 | 7 | 3 | 0 | 2 | 1 | 0 | 2.7.3.2.1 | Purchase Material Requisition (PMR)
2 | 7 | 3 | 0 | 2 | 1 | 1 | 2.7.3.2.1.1 | PMR For Anchor Bolts - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-MR-0002 | BK-W007S-PEDCO-110-ST-MR-0002 | BK | W007S | PEDCO | 110 | ST | MR | 0002 | F0Z-708173 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 3 | 0 | 2 | 2 | 0 | 2.7.3.2.2 | Technical Bid Evaluation (TBE)
2 | 7 | 3 | 0 | 2 | 2 | 1 | 2.7.3.2.2.1 | TBE For Anchor Bolts - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-TB-0002 | BK-W007S-PEDCO-110-ST-TB-0002 | BK | W007S | PEDCO | 110 | ST | TB | 0002 | F0Z-708174 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 3 | 0 | 3 | 0 | 0 | 2.7.3.3 | Blast Proof Doors
2 | 7 | 3 | 0 | 3 | 1 | 0 | 2.7.3.3.1 | Purchase Material Requisition (PMR)
2 | 7 | 3 | 0 | 3 | 1 | 1 | 2.7.3.3.1.1 | PMR For Blast Proof Doors - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-MR-0003 | BK-W007S-PEDCO-110-ST-MR-0003 | BK | W007S | PEDCO | 110 | ST | MR | 0003 | F0Z-708175 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 3 | 0 | 3 | 2 | 0 | 2.7.3.3.2 | Technical Bid Evaluation (TBE)
2 | 7 | 3 | 0 | 3 | 2 | 1 | 2.7.3.3.2.1 | TBE For Blast Proof Doors - W007S/Manifold Extension | BK-W007S-PEDCO-110-ST-TB-0003 | BK-W007S-PEDCO-110-ST-TB-0003 | BK | W007S | PEDCO | 110 | ST | TB | 0003 | F0Z-708176 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 4 | 0 | 0 | 0 | 0 | 2.7.4 | Civil
2 | 7 | 4 | 0 | 1 | 0 | 0 | 2.7.4.1 | Geomembrane
2 | 7 | 4 | 0 | 1 | 1 | 0 | 2.7.4.1.1 | Purchase Material Requisition (PMR)
2 | 7 | 4 | 0 | 1 | 1 | 1 | 2.7.4.1.1.1 | PMR For Geomembrane - W007S | BK-W007S-PEDCO-110-CV-MR-0001 | BK-W007S-PEDCO-110-CV-MR-0001 | BK | W007S | PEDCO | 110 | CV | MR | 0001 | F0Z-708177 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 4 | 0 | 1 | 2 | 0 | 2.7.4.1.2 | Technical Bid Evaluation (TBE)
2 | 7 | 4 | 0 | 1 | 2 | 1 | 2.7.4.1.2.1 | TBE For Geomembrane - W007S | BK-W007S-PEDCO-110-CV-TB-0001 | BK-W007S-PEDCO-110-CV-TB-0001 | BK | W007S | PEDCO | 110 | CV | TB | 0001 | F0Z-708178 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 4 | 0 | 2 | 0 | 0 | 2.7.4.2 | Geotextile
2 | 7 | 4 | 0 | 2 | 1 | 0 | 2.7.4.2.1 | Purchase Material Requisition (PMR)
2 | 7 | 4 | 0 | 2 | 1 | 1 | 2.7.4.2.1.1 | PMR For Geotextile - W007S | BK-W007S-PEDCO-110-CV-MR-0002 | BK-W007S-PEDCO-110-CV-MR-0002 | BK | W007S | PEDCO | 110 | CV | MR | 0002 | F0Z-708179 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 4 | 0 | 2 | 2 | 0 | 2.7.4.2.2 | Technical Bid Evaluation (TBE)
2 | 7 | 4 | 0 | 2 | 2 | 1 | 2.7.4.2.2.1 | TBE For Geotextile - W007S | BK-W007S-PEDCO-110-CV-TB-0002 | BK-W007S-PEDCO-110-CV-TB-0002 | BK | W007S | PEDCO | 110 | CV | TB | 0002 | F0Z-708180 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 5 | 0 | 0 | 0 | 0 | 2.7.5 | Commissioning Engineering
2 | 7 | 5 | 0 | 0 | 1 | 0 | 2.7.5.1 | Procedure/Plan
2 | 7 | 5 | 0 | 0 | 1 | 1 | 2.7.5.1.1 | Pre-Commissioning, Commissioning & Startup Procedure - Manifold & W007S | BK-W007S-PEDCO-110-CO-PR-0001 | BK-W007S-PEDCO-110-CO-PR-0001 | BK | W007S | PEDCO | 110 | CO | PR | 0001 | F0Z-708181 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 6 | 0 | 0 | 0 | 0 | 2.7.6 | Field Engineering
2 | 7 | 6 | 0 | 0 | 1 | 0 | 2.7.6.1 | Query
2 | 7 | 6 | 0 | 0 | 1 | 1 | 2.7.6.1.1 | Technical/Site Queries | BK-W007S-PEDCO-110-GE-TQ-0001 | BK-W007S-PEDCO-110-GE-TQ-0001 | BK | W007S | PEDCO | 110 | GE | TQ | 0001 | F7Z-708182 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 6 | 0 | 0 | 2 | 0 | 2.7.6.2 | Dossier
2 | 7 | 6 | 0 | 0 | 2 | 1 | 2.7.6.2.1 | As-Built Document Booklets - Manifold & W007S | BK-W007S-PEDCO-110-GE-DO-0001 | BK-W007S-PEDCO-110-GE-DO-0001 | BK | W007S | PEDCO | 110 | GE | DO | 0001 | F0Z-708183 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 7 | 0 | 0 | 0 | 0 | 2.7.7 | Engineering Final Documentation
2 | 7 | 7 | 0 | 0 | 1 | 0 | 2.7.7.1 | Manual
2 | 7 | 7 | 0 | 0 | 1 | 1 | 2.7.7.1.1 | Operating Manual - Manifold & W007S | BK-W007S-PEDCO-110-GE-ML-0001 | BK-W007S-PEDCO-110-GE-ML-0001 | BK | W007S | PEDCO | 110 | GE | ML | 0001 | F0Z-708184 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 7 | 0 | 0 | 2 | 0 | 2.7.7.2 | Dossier
2 | 7 | 7 | 0 | 0 | 2 | 1 | 2.7.7.2.1 | As-Built Document Booklets - Manifold & W007S | BK-W007S-PEDCO-110-GE-DO-0001 | BK-W007S-PEDCO-110-GE-DO-0001 | BK | W007S | PEDCO | 110 | GE | DO | 0001 | F0Z-708183 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 7 | 7 | 0 | 0 | 2 | 2 | 2.7.7.2.2 | Final Engineering Dossier - Manifold & W007S | BK-W007S-PEDCO-110-GE-DO-0002 | BK-W007S-PEDCO-110-GE-DO-0002 | BK | W007S | PEDCO | 110 | GE | DO | 0002 | F0Z-708185 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 0 | 0 | 0 | 0 | 0 | 2.8 | Package 07-Workover # 14
2 | 8 | 1 | 0 | 0 | 0 | 0 | 2.8.1 | Detail Design
2 | 8 | 1 | 1 | 0 | 0 | 0 | 2.8.1.1 | Process
2 | 8 | 1 | 1 | 1 | 0 | 0 | 2.8.1.1.1 | Drawing/Diagram
2 | 8 | 1 | 1 | 1 | 0 | 1 | 2.8.1.1.1 | P&ID for Diesel Oil Drum- BK14 | BK-BK14-PEDCO-110-PR-PI-0001 | BK-BK14-PEDCO-110-PR-PI-0001 | BK | BK14 | PEDCO | 110 | PR | PI | 0001 | F2A-708186 | AFC | IFC | 2021-11-29 | 2021-12-01 | 2021-12-06 | 2 | 5 | 7 | IFA | 2022-01-17 | 2022-02-06 | 2022-02-08 | 20 | 2 | 22 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 2022-05-12 | 2022-05-16 | 18 | 4 | 22 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 0 |  | D03 | IFA | T-0795 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03986 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59474 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 2021-11-30 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0422 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02776 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-399153 | 2022-02-06 | 1400/11/17 | 2022-02-08 | 1400/11/19 | AP | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0648 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03589 | 2022-03-15 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-443282 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/24 | RJ | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0795 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03986 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-59474 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0001_D02
2 | 8 | 1 | 1 | 1 | 0 | 2 | 2.8.1.1.1 | P&ID for Potable Water Tank - BK14 | BK-BK14-PEDCO-110-PR-PI-0002 | BK-BK14-PEDCO-110-PR-PI-0002 | BK | BK14 | PEDCO | 110 | PR | PI | 0002 | F2A-708187 | AFC | IFC | 2021-11-29 | 2021-12-01 | 2021-12-06 | 2 | 5 | 7 | IFA | 2022-01-17 | 2022-02-06 | 2022-02-08 | 20 | 2 | 22 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 2022-05-12 | 2022-05-16 | 18 | 4 | 22 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 0 |  | D03 | IFA | T-0795 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03986 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59474 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 2021-11-30 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0422 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02776 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D00 | [5 empty] | 1400-2294-399153 | 2022-02-06 | 1400/11/17 | 2022-02-08 | 1400/11/19 | AP | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D00 | [9 empty] | D02 | IFA | T-0648 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03589 | 2022-03-15 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D01 | [5 empty] | 1400-2294-443282 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/24 | RJ | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D01 | [9 empty] | D03 | IFA | T-0795 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03986 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D02 | [5 empty] | 1401-2294-59474 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D02
2 | 8 | 1 | 1 | 2 | 0 | 0 | 2.8.1.1.2 | List
2 | 8 | 1 | 1 | 2 | 0 | 1 | 2.8.1.1.2 | Line List - BK14 | BK-BK14-PEDCO-110-PR-LI-0001 | BK-BK14-PEDCO-110-PR-LI-0001 | BK | BK14 | PEDCO | 110 | PR | LI | 0001 | F0Z-708188 | AFC | IFC | 44633 | 44632 | 44635 | -1 | 3 | 2 | IFA | 44695 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-27 | 0 |  | D01 | IFA | T-0877 | 2022-04-30 | 1401/02/10 | T-0877 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 2022-05-23 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK14-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0650 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03597 | 2022-03-15 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445283 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0877 | 2022-04-30 | 1401/02/10 | T-0877 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 2022-05-23 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-LI-0001_D00 | [11 empty] | NISOC-CRS-BK-BK14-PEDCO-110-PR-LI-0001_D00
2 | 8 | 1 | 1 | 3 | 0 | 0 | 2.8.1.1.3 | Data Sheet
2 | 8 | 1 | 1 | 3 | 0 | 1 | 2.8.1.1 | Process Data Sheets For Instrument Devices - BK14 | BK-BK14-PEDCO-110-PR-DT-0001 | BK-BK14-PEDCO-110-PR-DT-0001 | BK | BK14 | PEDCO | 110 | PR | DT | 0001 | F0Z-708189 | AFC | IFC | 44677 | 44695 | 44697 | 18 | 2 | 20 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-12 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03991 | 2022-04-19 | 1401/01/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 2022-05-16 | 1401/02/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 |  |  |  | BK-SUR-ENG-PCS-01-03991 | 2022-04-19 | 1401/01/30 | CM-C2 | [6 empty] | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 2022-05-16 | 1401/02/26 | AP
2 | 8 | 1 | 2 | 0 | 0 | 0 | 2.8.1.2 | HVAC/Plumbing
2 | 8 | 1 | 2 | 1 | 0 | 0 | 2.8.1.2.1 | Calculation
2 | 8 | 1 | 2 | 1 | 0 | 1 | 2.8.1.2.1 | HVAC Calculation Note For Switchgear Building - BK14 | BK-BK14-PEDCO-110-HV-CN-0001 | BK-BK14-PEDCO-110-HV-CN-0001 | BK | BK14 | PEDCO | 110 | HV | CN | 0001 | F0Z-708190 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 2 | 1 | 0 | 2 | 2.8.1.2.1 | HVAC Calculation Note For Security Building - BK14 | BK-BK14-PEDCO-110-HV-CN-0002 | BK-BK14-PEDCO-110-HV-CN-0002 | BK | BK14 | PEDCO | 110 | HV | CN | 0002 | F0Z-708191 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 2 | 2 | 0 | 0 | 2.8.1.2.2 | Data Sheets
2 | 8 | 1 | 2 | 2 | 0 | 1 | 2.8.1.2.2 | Data Sheets For Main HVAC Equipment - BK14 | BK-BK14-PEDCO-110-HV-DT-0001 | BK-BK14-PEDCO-110-HV-DT-0001 | BK | BK14 | PEDCO | 110 | HV | DT | 0001 | F0Z-708192 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 2 | 3 | 0 | 0 | 2.8.1.2.3 | Drawing/Diagram
2 | 8 | 1 | 2 | 3 | 0 | 1 | 2.8.1.2.3 | HVAC System Layout For Switchgear Building - BK14 | BK-BK14-PEDCO-110-HV-PY-0001 | BK-BK14-PEDCO-110-HV-PY-0001 | BK | BK14 | PEDCO | 110 | HV | PY | 0001 | F4B-708193 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 2 | 3 | 0 | 2 | 2.8.1.2.3 | HVAC System Layout For Security Building - BK14 | BK-BK14-PEDCO-110-HV-PY-0002 | BK-BK14-PEDCO-110-HV-PY-0002 | BK | BK14 | PEDCO | 110 | HV | PY | 0002 | F4B-708194 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 2 | 3 | 0 | 3 | 2.8.1.2.3 | Plumbing & Sewage Piping Layout For Switchgear Building - BK14 | BK-BK14-PEDCO-110-HV-PY-0003 | BK-BK14-PEDCO-110-HV-PY-0003 | BK | BK14 | PEDCO | 110 | HV | PY | 0003 | F4B-708195 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 2 | 3 | 0 | 4 | 2.8.1.2.3 | Plumbing & Sewage Piping Layout For Security Building - BK14 | BK-BK14-PEDCO-110-HV-PY-0004 | BK-BK14-PEDCO-110-HV-PY-0004 | BK | BK14 | PEDCO | 110 | HV | PY | 0004 | F4B-708196 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 2 | 4 | 0 | 0 | 2.8.1.2.4 | MTO
2 | 8 | 1 | 2 | 4 | 0 | 1 | 2.8.1.2 | MTO For Building HVAC & Plumbing Systems - BK14 | BK-BK14-PEDCO-110-HV-MT-0001 | BK-BK14-PEDCO-110-HV-MT-0001 | BK | BK14 | PEDCO | 110 | HV | MT | 0001 | F8Z-708197 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 3 | 0 | 0 | 0 | 2.8.1.3 | Piping
2 | 8 | 1 | 3 | 1 | 0 | 0 | 2.8.1.3.1 | MTO
2 | 8 | 1 | 3 | 1 | 0 | 1 | 2.8.1.3 | MTO For Pipes - BK14 | BK-BK14-PEDCO-110-PI-MT-0001 | BK-BK14-PEDCO-110-PI-MT-0001 | BK | BK14 | PEDCO | 110 | PI | MT | 0001 | F8Z-708198 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 4 | 0 | 0 | 0 | 2.8.1.4 | Electrical
2 | 8 | 1 | 4 | 1 | 0 | 0 | 2.8.1.4.1 | MTO
2 | 8 | 1 | 4 | 1 | 0 | 1 | 2.8.1.4 | MTO For Transmission Over Head Line - BK14 | BK-BK14-PEDCO-110-EL-MT-0001 | BK-BK14-PEDCO-110-EL-MT-0001 | BK | BK14 | PEDCO | 110 | EL | MT | 0001 | F8Z-708199 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 4 | 1 | 0 | 2 | 2.8.1.4 | MTO For Lighting & Small Powers - BK14 | BK-BK14-PEDCO-110-EL-MT-0002 | BK-BK14-PEDCO-110-EL-MT-0002 | BK | BK14 | PEDCO | 110 | EL | MT | 0002 | F8Z-708200 | IFI | IFI | 2022-06-01 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-18 | 2022-05-18 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04483 | 2022-05-29 | 1401/03/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 |  |  |  | BK-SUR-ENG-ELE-01-04483 | 2022-05-29 | 1401/03/09 | CM-C2
2 | 8 | 1 | 4 | 1 | 0 | 3 | 2.8.1.4 | MTO For Power & Control Cables - BK14 | BK-BK14-PEDCO-110-EL-MT-0003 | BK-BK14-PEDCO-110-EL-MT-0003 | BK | BK14 | PEDCO | 110 | EL | MT | 0003 | F8Z-708201 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 4 | 1 | 0 | 4 | 2.8.1.4 | MTO For Tray/Ladder and Accessories - BK14 | BK-BK14-PEDCO-110-EL-MT-0004 | BK-BK14-PEDCO-110-EL-MT-0004 | BK | BK14 | PEDCO | 110 | EL | MT | 0004 | F8Z-708202 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 4 | 1 | 0 | 5 | 2.8.1.4 | MTO For Electrical Bulk Items - BK14 | BK-BK14-PEDCO-110-EL-MT-0005 | BK-BK14-PEDCO-110-EL-MT-0005 | BK | BK14 | PEDCO | 110 | EL | MT | 0005 | F8Z-708203 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 4 | 1 | 0 | 6 | 2.8.1.4 | MTO For Earthing & Lightning Systems - BK14 | BK-BK14-PEDCO-110-EL-MT-0006 | BK-BK14-PEDCO-110-EL-MT-0006 | BK | BK14 | PEDCO | 110 | EL | MT | 0006 | F8Z-708204 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 5 | 0 | 0 | 0 | 2.8.1.5 | Architecture
2 | 8 | 1 | 5 | 1 | 0 | 0 | 2.8.1.5.1 | Drawing/Diagram
2 | 8 | 1 | 5 | 1 | 0 | 1 | 2.8.1.5.1 | Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-14 | BK-BK14-PEDCO-110-AR-DW-0001 | BK-BK14-PEDCO-110-AR-DW-0001 | BK | BK14 | PEDCO | 110 | AR | DW | 0001 | F4B-708205 | AFC | IFC | 2022-05-15 | 2022-05-09 | 2022-05-16 | -6 | 7 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-01 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | [13 empty] | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | CM
2 | 8 | 1 | 5 | 1 | 0 | 2 | 2.8.1.5.1 | Architectural Drawing For Switchgear Building of Well Pads - BK-14 | BK-BK14-PEDCO-110-AR-DW-0002 | BK-BK14-PEDCO-110-AR-DW-0002 | BK | BK14 | PEDCO | 110 | AR | DW | 0002 | F4B-708206 | AFC | IFC | 2022-03-23 | 2022-03-15 | 2022-03-25 | -8 | 10 | 2 | IFC | 2022-06-01 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-18 | 0 |  | D01 | IFC | T-0974 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-BK14-PEDCO-110-AR-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK14-PEDCO-110-AR-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0707 | 2022-03-09 | 1400/12/18 |  |  |  | RE BK-SUR-ENG-ARC-00-03551 | 2022-03-14 | 1400/12/23 | CM | [6 empty] | 1400-2294-450549 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | RJ | [10 empty] | D01 | IFC | T-0974 | 2022-05-18 | 1401/02/28 | [7 empty] | PEDCO-CRS-BK-BK14-PEDCO-110-AR-DW-0002_D00 | [11 empty] | NISOC-CRS-BK-BK14-PEDCO-110-AR-DW-0002_D00
2 | 8 | 1 | 5 | 1 | 0 | 3 | 2.8.1.5.1 | Architectural Drawing For Security Building of Well Pads - BK-14 | BK-BK14-PEDCO-110-AR-DW-0003 | BK-BK14-PEDCO-110-AR-DW-0003 | BK | BK14 | PEDCO | 110 | AR | DW | 0003 | F4B-708207 | AFC | IFC | 2022-05-15 | 2022-05-14 | 2022-05-16 | -1 | 2 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04190 | 2022-05-10 | 1401/02/20 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 2022-05-16 | 1401/02/26 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04190 | 2022-05-10 | 1401/02/20 | CM-C2 | [6 empty] | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 2022-05-16 | 1401/02/26 | RJ
2 | 8 | 1 | 5 | 2 | 0 | 0 | 2.8.1.5.2 | MTO
2 | 8 | 1 | 5 | 2 | 0 | 1 | 2.8.1.5 | MTO For Architectural Works - BK14 | BK-BK14-PEDCO-110-AR-MT-0001 | BK-BK14-PEDCO-110-AR-MT-0001 | BK | BK14 | PEDCO | 110 | AR | MT | 0001 | F8Z-708208 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 6 | 0 | 0 | 0 | 2.8.1.6 | Civil
2 | 8 | 1 | 6 | 1 | 0 | 0 | 2.8.1.6.1 | Drawing/Diagram
2 | 8 | 1 | 6 | 1 | 0 | 1 | 2.8.1.6.1 | Civil and Structural drawings - BK14 | BK-BK14-PEDCO-110-CV-DW-0001 | BK-BK14-PEDCO-110-CV-DW-0001 | BK | BK14 | PEDCO | 110 | CV | DW | 0001 | F4S-708209 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 6 | 1 | 0 | 2 | 2.8.1.6.1 | General Civil Layout - BK14 | BK-BK14-PEDCO-110-CV-PY-0001 | BK-BK14-PEDCO-110-CV-PY-0001 | BK | BK14 | PEDCO | 110 | CV | PY | 0001 | F4A-708210 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 6 | 1 | 0 | 3 | 2.8.1.6.1 | Rough Grading Plans -BK14 | BK-BK14-PEDCO-110-CV-PY-0003 | BK-BK14-PEDCO-110-CV-PY-0003 | BK | BK14 | PEDCO | 110 | CV | PY | 0003 | F4S-708211 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 6 | 2 | 0 | 0 | 2.8.1.6.2 | Report
2 | 8 | 1 | 6 | 2 | 0 | 1 | 2.8.1.6.2 | Site Visit Report (Civil Work) - BK14 | BK-BK14-PEDCO-110-CV-RT-0001 | BK-BK14-PEDCO-110-CV-RT-0001 | BK | BK14 | PEDCO | 110 | CV | RT | 0001 | F0Z-708212 | AFC | IFC | 44523 | 44514 | 44517 | -9 | 3 | -6 | IFA | 44627 | 44618 | 44620 | -9 | 2 | -7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-09 | 0 |  | D01 | IFA | T-0621 | 2022-02-21 | 1400/12/02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-426672 | 2022-02-26 | 1400/12/07 | 2022-02-28 | 1400/12/09 | cm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0223 | 2021-11-09 | 1400/08/17 |  |  |  | BK-SUR-ENG-CIV-00-02031 | 2021-11-17 | 1400/08/26 | CM-C2 | [6 empty] | 1400-2294-275272 | 2021-11-14 | 1400/08/23 | 2021-11-17 | 1400/08/26 | CM | [10 empty] | D01 | IFA | T-0621 | 2022-02-21 | 1400/12/02 | [13 empty] | 1400-2294-426672 | 2022-02-26 | 1400/12/07 | 2022-02-28 | 1400/12/09 | cm
2 | 8 | 1 | 6 | 3 | 0 | 0 | 2.8.1.6.3 | MTO
2 | 8 | 1 | 6 | 3 | 0 | 1 | 2.8.1.6 | MTO For Civil Works - BK14 | BK-BK14-PEDCO-110-CV-MT-0001 | BK-BK14-PEDCO-110-CV-MT-0001 | BK | BK14 | PEDCO | 110 | CV | MT | 0001 | F8Z-708213 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 7 | 0 | 0 | 0 | 2.8.1.7 | Structure
2 | 8 | 1 | 7 | 1 | 0 | 0 | 2.8.1.7.1 | Drawing/Diagram
2 | 8 | 1 | 7 | 1 | 0 | 1 | 2.8.1.7.1 | Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0001 | BK-BK14-PEDCO-110-ST-DW-0001 | BK | BK14 | PEDCO | 110 | ST | DW | 0001 | F4G-708214 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 7 | 1 | 0 | 2 | 2.8.1.7.1 | Foundation Drawing For Security Building For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0002 | BK-BK14-PEDCO-110-ST-DW-0002 | BK | BK14 | PEDCO | 110 | ST | DW | 0002 | F4Q-708215 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 7 | 1 | 0 | 3 | 2.8.1.7.1 | Structural Drawing For Security Building For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0003 | BK-BK14-PEDCO-110-ST-DW-0003 | BK | BK14 | PEDCO | 110 | ST | DW | 0003 | F4M-708216 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 7 | 1 | 0 | 4 | 2.8.1.7.1 | Foundation Drawing For Switchgear Building For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0004 | BK-BK14-PEDCO-110-ST-DW-0004 | BK | BK14 | PEDCO | 110 | ST | DW | 0004 | F4Q-708217 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 7 | 1 | 0 | 5 | 2.8.1.7.1 | Structural Drawing For Switchgear Building For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0005 | BK-BK14-PEDCO-110-ST-DW-0005 | BK | BK14 | PEDCO | 110 | ST | DW | 0005 | F4M-708218 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 7 | 1 | 0 | 6 | 2.8.1.7.1 | Foundation Drawing For Potable Water Tank For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0006 | BK-BK14-PEDCO-110-ST-DW-0006 | BK | BK14 | PEDCO | 110 | ST | DW | 0006 | F4Q-708219 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 7 | 1 | 0 | 7 | 2.8.1.7.1 | Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0007 | BK-BK14-PEDCO-110-ST-DW-0007 | BK | BK14 | PEDCO | 110 | ST | DW | 0007 | F4Q-708220 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 7 | 1 | 0 | 8 | 2.8.1.7.1 | Structural Drawing For Diesel Generator Shelter For Well Pads - BK-14 | BK-BK14-PEDCO-110-ST-DW-0008 | BK-BK14-PEDCO-110-ST-DW-0008 | BK | BK14 | PEDCO | 110 | ST | DW | 0008 | F4M-708221 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 7 | 2 | 0 | 0 | 2.8.1.7.2 | MTO
2 | 8 | 1 | 7 | 2 | 0 | 1 | 2.8.1.7 | MTO For Structural Works - BK14 | BK-BK14-PEDCO-110-ST-MT-0001 | BK-BK14-PEDCO-110-ST-MT-0001 | BK | BK14 | PEDCO | 110 | ST | MT | 0001 | F8Z-708222 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 8 | 0 | 0 | 0 | 2.8.1.8 | Survey (Topography) & Geotechnic
2 | 8 | 1 | 8 | 1 | 0 | 0 | 2.8.1.8.1 | Geotechnic
2 | 8 | 1 | 8 | 2 | 0 | 0 | 2.8.1.8.2 | Report
2 | 8 | 1 | 8 | 2 | 0 | 1 | 2.8.1.8.2 | Geotechnical Investigation Report - BK14 | BK-BK14-PEDCO-110-GT-RT-0001 | BK-BK14-PEDCO-110-GT-RT-0001 | BK | BK14 | PEDCO | 110 | GT | RT | 0001 | F0Z-708223 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 1 | 8 | 3 | 0 | 0 | 2.8.1.8.3 | Drawing/Diagram
2 | 8 | 1 | 8 | 3 | 0 | 1 | 2.8.1 | Over Head Line Plan and Profile - BK14 | BK-BK14-PEDCO-110-SU-DW-0001 | BK-BK14-PEDCO-110-SU-DW-0001 | BK | BK14 | PEDCO | 110 | SU | DW | 0001 | F4P-708224 | AFC | IFC | 44627 | 44630 | 44632 | 3 | 2 | 5 | IFA | 44676 | 0 | 0 | -44676 | 0 | -44676 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-21 | 0 |  | D01 | IFA | T-0802 | 2022-04-11 | 1401/01/22 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04010 | 2022-04-24 | 1401/01/04 | CM-C3 | PEDCO-CRS-BK-BK14-PEDCO-110-SU-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK14-PEDCO-110-SU-DW-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0616 | 2022-02-21 | 1400/12/02 |  |  |  | BK-SUR-ENG-ELE-00-03237 | 2022-02-27 | 1400/12/08 | CM-C3 | [6 empty] | 1400-2294-443158 | 2022-03-10 | 1400/12/10 | 2022-03-12 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0802 | 2022-04-11 | 1401/01/22 |  |  |  | BK-SUR-ENG-ELE-01-04010 | 2022-04-24 | 1401/01/04 | CM-C3 | PEDCO-CRS-BK-BK14-PEDCO-110-SU-DW-0001_D00 | [11 empty] | NISOC-CRS-BK-BK14-PEDCO-110-SU-DW-0001_D00
2 | 8 | 2 | 0 | 0 | 0 | 0 | 2.8.2 | Procurement Engineering
2 | 8 | 2 | 1 | 0 | 0 | 0 | 2.8.2.1 | Piping
2 | 8 | 2 | 1 | 1 | 0 | 0 | 2.8.2.1.1 | Pipe
2 | 8 | 2 | 1 | 1 | 1 | 0 | 2.8.1.1.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 1 | 1 | 1 | 1 | 2.8.2.1.1.1.1 | PMR For Pipes - BK14 | BK-BK14-PEDCO-110-PI-MR-0001 | BK-BK14-PEDCO-110-PI-MR-0001 | BK | BK14 | PEDCO | 110 | PI | MR | 0001 | F0Z-708225 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 1 | 1 | 2 | 0 | 2.8.1.1.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 1 | 1 | 2 | 1 | 2.8.2.1.1.2.1 | TBE For Pipes - BK14 | BK-BK14-PEDCO-110-PI-TB-0001 | BK-BK14-PEDCO-110-PI-TB-0001 | BK | BK14 | PEDCO | 110 | PI | TB | 0001 | F0Z-708226 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 1 | 2 | 0 | 0 | 2.8.2.1.2 | Pipe Support
2 | 8 | 2 | 1 | 2 | 1 | 0 | 2.8.1.2.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 1 | 2 | 1 | 1 | 2.8.2.1.2.1.1 | PMR For Pipe Support - BK14 | BK-BK14-PEDCO-110-PI-MR-0002 | BK-BK14-PEDCO-110-PI-MR-0002 | BK | BK14 | PEDCO | 110 | PI | MR | 0002 | F0Z-708227 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 1 | 2 | 2 | 0 | 2.8.1.2.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 1 | 2 | 2 | 1 | 2.8.2.1.2.2.1 | TBE For Pipe Support - BK14 | BK-BK14-PEDCO-110-PI-TB-0002 | BK-BK14-PEDCO-110-PI-TB-0002 | BK | BK14 | PEDCO | 110 | PI | TB | 0002 | F0Z-708228 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 2 | 0 | 0 | 0 | 2.8.2.2 | HVAC
2 | 8 | 2 | 2 | 1 | 0 | 0 | 2.8.2.2.1 | Main HVAC Equipment
2 | 8 | 2 | 2 | 1 | 1 | 0 | 2.8.2.1.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 2 | 1 | 1 | 1 | 2.8.2.2.1.1.1 | PMR For Main HVAC Equipment - BK14 | BK-BK14-PEDCO-110-HV-MR-0001 | BK-BK14-PEDCO-110-HV-MR-0001 | BK | BK14 | PEDCO | 110 | HV | MR | 0001 | F0Z-708229 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 2 | 1 | 2 | 0 | 2.8.2.1.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 2 | 1 | 2 | 1 | 2.8.2.2.1.2.1 | TBE For Main HVAC Equipment - BK14 | BK-BK14-PEDCO-110-HV-TB-0001 | BK-BK14-PEDCO-110-HV-TB-0001 | BK | BK14 | PEDCO | 110 | HV | TB | 0001 | F0Z-708230 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 0 | 0 | 0 | 2.8.2.3 | Electrical
2 | 8 | 2 | 3 | 1 | 0 | 0 | 2.8.2.3.1 | Transformers
2 | 8 | 2 | 3 | 1 | 1 | 0 | 2.8.3.1.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 1 | 1 | 1 | 2.8.2.3.1.1.1 | PMR For Transformers - BK14 | BK-BK14-PEDCO-110-EL-MR-0001 | BK-BK14-PEDCO-110-EL-MR-0001 | BK | BK14 | PEDCO | 110 | EL | MR | 0001 | F0Z-708231 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 1 | 2 | 0 | 2.8.3.1.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 1 | 2 | 1 | 2.8.2.3.1.2.1 | TBE For Transformers - BK14 | BK-BK14-PEDCO-110-EL-TB-0001 | BK-BK14-PEDCO-110-EL-TB-0001 | BK | BK14 | PEDCO | 110 | EL | TB | 0001 | F0Z-708232 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 2 | 0 | 0 | 2.8.2.3.2 | LV Switchgear & MCC
2 | 8 | 2 | 3 | 2 | 1 | 0 | 2.8.3.2.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 2 | 1 | 1 | 2.8.2.3.2.1.1 | PMR For LV Switchgear & MCC - BK14 | BK-BK14-PEDCO-110-EL-MR-0002 | BK-BK14-PEDCO-110-EL-MR-0002 | BK | BK14 | PEDCO | 110 | EL | MR | 0002 | F0Z-708233 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 2 | 2 | 0 | 2.8.3.2.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 2 | 2 | 1 | 2.8.2.3.2.2.1 | TBE For LV Switchgear & MCC - BK14 | BK-BK14-PEDCO-110-EL-TB-0002 | BK-BK14-PEDCO-110-EL-TB-0002 | BK | BK14 | PEDCO | 110 | EL | TB | 0002 | F0Z-708234 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 3 | 0 | 0 | 2.8.2.3.3 | Emergency Diesel Generator
2 | 8 | 2 | 3 | 3 | 1 | 0 | 2.8.3.3.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 3 | 1 | 1 | 2.8.2.3.3.1.1 | PMR For Emergency Diesel Generator - BK14 | BK-BK14-PEDCO-110-EL-MR-0003 | BK-BK14-PEDCO-110-EL-MR-0003 | BK | BK14 | PEDCO | 110 | EL | MR | 0003 | F0Z-708235 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 3 | 2 | 0 | 2.8.3.3.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 3 | 2 | 1 | 2.8.2.3.3.2.1 | TBE For Emergency Diesel Generator - BK14 | BK-BK14-PEDCO-110-EL-TB-0003 | BK-BK14-PEDCO-110-EL-TB-0003 | BK | BK14 | PEDCO | 110 | EL | TB | 0003 | F0Z-708236 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 4 | 0 | 0 | 2.8.2.3.4 | UPS System
2 | 8 | 2 | 3 | 4 | 1 | 0 | 2.8.3.4.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 4 | 1 | 1 | 2.8.2.3.4.1.1 | PMR For UPS System - BK14 | BK-BK14-PEDCO-110-EL-MR-0004 | BK-BK14-PEDCO-110-EL-MR-0004 | BK | BK14 | PEDCO | 110 | EL | MR | 0004 | F0Z-708237 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 4 | 2 | 0 | 2.8.3.4.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 4 | 2 | 1 | 2.8.2.3.4.2.1 | TBE For UPS System - BK14 | BK-BK14-PEDCO-110-EL-TB-0004 | BK-BK14-PEDCO-110-EL-TB-0004 | BK | BK14 | PEDCO | 110 | EL | TB | 0004 | F0Z-708238 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 5 | 0 | 0 | 2.8.2.3.5 | DC Charger
2 | 8 | 2 | 3 | 5 | 1 | 0 | 2.8.3.5.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 5 | 1 | 1 | 2.8.2.3.5.1.1 | PMR For DC Charger - BK14 | BK-BK14-PEDCO-110-EL-MR-0005 | BK-BK14-PEDCO-110-EL-MR-0005 | BK | BK14 | PEDCO | 110 | EL | MR | 0005 | F0Z-708239 | IFI | IFI | 44691 | 44710 | 44711 | 19 | 1 | 20 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-26 | 2022-04-26 |  | D00 | IFI | T-0864 | 2022-04-26 | 1401/02/06 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04211 | 2022-05-10 | 1401/02/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-78867 | 2022-05-29 | 1401/03/08 | 2022-05-30 | 1401/03/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0864 | 2022-04-26 | 1401/02/06 |  |  |  | BK-SUR-ENG-ELE-01-04211 | 2022-05-10 | 1401/02/20 | CM-C3 | [6 empty] | 1401-2294-78867 | 2022-05-29 | 1401/03/08 | 2022-05-30 | 1401/03/09 | CM
2 | 8 | 2 | 3 | 5 | 2 | 0 | 2.8.3.5.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 5 | 2 | 1 | 2.8.2.3.5.2.1 | TBE For DC Charger - BK14 | BK-BK14-PEDCO-110-EL-TB-0005 | BK-BK14-PEDCO-110-EL-TB-0005 | BK | BK14 | PEDCO | 110 | EL | TB | 0005 | F0Z-708240 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 6 | 0 | 0 | 2.8.2.3.6 | Capacitor Bank
2 | 8 | 2 | 3 | 6 | 1 | 0 | 2.8.3.6.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 6 | 1 | 1 | 2.8.2.3.6.1.1 | PMR For Capacitor Bank - BK14 | BK-BK14-PEDCO-110-EL-MR-0006 | BK-BK14-PEDCO-110-EL-MR-0006 | BK | BK14 | PEDCO | 110 | EL | MR | 0006 | F0Z-708241 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 6 | 2 | 0 | 2.8.3.6.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 6 | 2 | 1 | 2.8.2.3.6.2.1 | TBE For Capacitor Bank - BK14 | BK-BK14-PEDCO-110-EL-TB-0006 | BK-BK14-PEDCO-110-EL-TB-0006 | BK | BK14 | PEDCO | 110 | EL | TB | 0006 | F0Z-708242 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 7 | 0 | 0 | 2.8.2.3.7 | Lighting & Distribution Main Panels
2 | 8 | 2 | 3 | 7 | 1 | 0 | 2.8.3.7.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 7 | 1 | 1 | 2.8.2.3.7.1.1 | PMR For Lighting & Distribution Main Panels - BK14 | BK-BK14-PEDCO-110-EL-MR-0007 | BK-BK14-PEDCO-110-EL-MR-0007 | BK | BK14 | PEDCO | 110 | EL | MR | 0007 | F0Z-708243 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 7 | 2 | 0 | 2.8.3.7.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 7 | 2 | 1 | 2.8.2.3.7.2.1 | TBE For Lighting & Distribution Main Panels - BK14 | BK-BK14-PEDCO-110-EL-TB-0007 | BK-BK14-PEDCO-110-EL-TB-0007 | BK | BK14 | PEDCO | 110 | EL | TB | 0007 | F0Z-708244 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 8 | 0 | 0 | 2.8.2.3.8 | Earthing & Lightning System
2 | 8 | 2 | 3 | 8 | 1 | 0 | 2.8.3.8.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 8 | 1 | 1 | 2.8.2.3.8.1.1 | PMR For Earthing & Lightning System - BK14 | BK-BK14-PEDCO-110-EL-MR-0008 | BK-BK14-PEDCO-110-EL-MR-0008 | BK | BK14 | PEDCO | 110 | EL | MR | 0008 | F0Z-708245 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 8 | 2 | 0 | 2.8.3.8.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 8 | 2 | 1 | 2.8.2.3.8.2.1 | TBE For Earthing & Lightning System - BK14 | BK-BK14-PEDCO-110-EL-TB-0008 | BK-BK14-PEDCO-110-EL-TB-0008 | BK | BK14 | PEDCO | 110 | EL | TB | 0008 | F0Z-708246 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 9 | 0 | 0 | 2.8.2.3.9 | Lighting and Small Power Equipment
2 | 8 | 2 | 3 | 9 | 1 | 0 | 2.8.3.9.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 9 | 1 | 1 | 2.8.2.3.9.1.1 | PMR For Lighting and Small Power Equipment - BK14 | BK-BK14-PEDCO-110-EL-MR-0009 | BK-BK14-PEDCO-110-EL-MR-0009 | BK | BK14 | PEDCO | 110 | EL | MR | 0009 | F0Z-708247 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 9 | 2 | 0 | 2.8.3.9.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 9 | 2 | 1 | 2.8.2.3.9.2.1 | TBE For Lighting and Small Power Equipment - BK14 | BK-BK14-PEDCO-110-EL-TB-0009 | BK-BK14-PEDCO-110-EL-TB-0009 | BK | BK14 | PEDCO | 110 | EL | TB | 0009 | F0Z-708248 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 10 | 0 | 0 | 2.8.2.3.10 | Tray/Ladder and Accessories
2 | 8 | 2 | 3 | 10 | 1 | 0 | 2.8.3.10.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 10 | 1 | 1 | 2.8.2.3.10.1.1 | PMR For Tray/Ladder and Accessories - BK14 | BK-BK14-PEDCO-110-EL-MR-0010 | BK-BK14-PEDCO-110-EL-MR-0010 | BK | BK14 | PEDCO | 110 | EL | MR | 0010 | F0Z-708249 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 10 | 2 | 0 | 2.8.3.10.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 10 | 2 | 1 | 2.8.2.3.10.2.1 | TBE For Tray/Ladder and Accessories - BK14 | BK-BK14-PEDCO-110-EL-TB-0010 | BK-BK14-PEDCO-110-EL-TB-0010 | BK | BK14 | PEDCO | 110 | EL | TB | 0010 | F0Z-708250 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 11 | 0 | 0 | 2.8.2.3.11 | Power & Control Cables
2 | 8 | 2 | 3 | 11 | 1 | 0 | 2.8.3.11.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 11 | 1 | 1 | 2.8.2.3.11.1.1 | PMR For Power & Control Cables - BK14 | BK-BK14-PEDCO-110-EL-MR-0011 | BK-BK14-PEDCO-110-EL-MR-0011 | BK | BK14 | PEDCO | 110 | EL | MR | 0011 | F0Z-708251 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 11 | 2 | 0 | 2.8.3.11.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 11 | 2 | 1 | 2.8.2.3.11.2.1 | TBE For Power & Control Cables - BK14 | BK-BK14-PEDCO-110-EL-TB-0011 | BK-BK14-PEDCO-110-EL-TB-0011 | BK | BK14 | PEDCO | 110 | EL | TB | 0011 | F0Z-708252 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 12 | 0 | 0 | 2.8.2.3.12 | Electrical Bulk Items
2 | 8 | 2 | 3 | 12 | 1 | 0 | 2.8.3.12.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 12 | 1 | 1 | 2.8.2.3.12.1.1 | PMR For Electrical Bulk Items - BK14 | BK-BK14-PEDCO-110-EL-MR-0012 | BK-BK14-PEDCO-110-EL-MR-0012 | BK | BK14 | PEDCO | 110 | EL | MR | 0012 | F0Z-708253 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 12 | 2 | 0 | 2.8.3.12.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 12 | 2 | 1 | 2.8.2.3.12.2.1 | TBE For Electrical Bulk Items - BK14 | BK-BK14-PEDCO-110-EL-TB-0012 | BK-BK14-PEDCO-110-EL-TB-0012 | BK | BK14 | PEDCO | 110 | EL | TB | 0012 | F0Z-708254 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 13 | 0 | 0 | 2.8.2.3.13 | Transmission Over head Line
2 | 8 | 2 | 3 | 13 | 1 | 0 | 2.8.3.13.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 3 | 13 | 1 | 1 | 2.8.2.3.13.1.1 | PMR For Transmission Over head Line - BK14 | BK-BK14-PEDCO-110-EL-MR-0013 | BK-BK14-PEDCO-110-EL-MR-0013 | BK | BK14 | PEDCO | 110 | EL | MR | 0013 | F0Z-708255 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 3 | 13 | 2 | 0 | 2.8.3.13.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 3 | 13 | 2 | 1 | 2.8.2.3.13.2.1 | TBE For Transmission Over head Line - BK14 | BK-BK14-PEDCO-110-EL-TB-0013 | BK-BK14-PEDCO-110-EL-TB-0013 | BK | BK14 | PEDCO | 110 | EL | TB | 0013 | F0Z-708256 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 4 | 0 | 0 | 0 | 2.8.2.4 | Structure
2 | 8 | 2 | 4 | 1 | 0 | 0 | 2.8.2.4.1 | Steel Structure Items
2 | 8 | 2 | 4 | 1 | 1 | 0 | 2.8.4.1.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 4 | 1 | 1 | 1 | 2.8.2.4.1.1.1 | PMR For Steel Structure Items - BK14 | BK-BK14-PEDCO-110-ST-MR-0001 | BK-BK14-PEDCO-110-ST-MR-0001 | BK | BK14 | PEDCO | 110 | ST | MR | 0001 | F0Z-708257 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 4 | 1 | 2 | 0 | 2.8.4.1.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 4 | 1 | 2 | 1 | 2.8.2.4.1.2.1 | TBE For Steel Structure Items - BK14 | BK-BK14-PEDCO-110-ST-TB-0001 | BK-BK14-PEDCO-110-ST-TB-0001 | BK | BK14 | PEDCO | 110 | ST | TB | 0001 | F0Z-708258 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 4 | 2 | 0 | 0 | 2.8.2.4.2 | Anchor Bolts
2 | 8 | 2 | 4 | 2 | 1 | 0 | 2.8.4.2.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 4 | 2 | 1 | 1 | 2.8.2.4.2.1.1 | PMR For Anchor Bolts - BK14 | BK-BK14-PEDCO-110-ST-MR-0002 | BK-BK14-PEDCO-110-ST-MR-0002 | BK | BK14 | PEDCO | 110 | ST | MR | 0002 | F0Z-708259 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 4 | 2 | 2 | 0 | 2.8.4.2.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 4 | 2 | 2 | 1 | 2.8.2.4.2.2.1 | TBE For Anchor Bolts - BK14 | BK-BK14-PEDCO-110-ST-TB-0002 | BK-BK14-PEDCO-110-ST-TB-0002 | BK | BK14 | PEDCO | 110 | ST | TB | 0002 | F0Z-708260 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 4 | 3 | 0 | 0 | 2.8.2.4.3 | Blast Proof Doors
2 | 8 | 2 | 4 | 3 | 1 | 0 | 2.8.4.3.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 4 | 3 | 1 | 1 | 2.8.2.4.3.1.1 | PMR For Blast Proof Doors - BK14 | BK-BK14-PEDCO-110-ST-MR-0003 | BK-BK14-PEDCO-110-ST-MR-0003 | BK | BK14 | PEDCO | 110 | ST | MR | 0003 | F0Z-708261 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 4 | 3 | 2 | 0 | 2.8.4.3.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 4 | 3 | 2 | 1 | 2.8.2.4.3.2.1 | TBE For Blast Proof Doors - BK14 | BK-BK14-PEDCO-110-ST-TB-0003 | BK-BK14-PEDCO-110-ST-TB-0003 | BK | BK14 | PEDCO | 110 | ST | TB | 0003 | F0Z-708262 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 5 | 0 | 0 | 0 | 2.8.2.5 | Civil
2 | 8 | 2 | 5 | 1 | 0 | 0 | 2.8.2.5.1 | Geomembrane
2 | 8 | 2 | 5 | 1 | 1 | 0 | 2.8.5.1.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 5 | 1 | 1 | 1 | 2.8.2.5.1.1.1 | PMR For Geomembrane - BK14 | BK-BK14-PEDCO-110-CV-MR-0001 | BK-BK14-PEDCO-110-CV-MR-0001 | BK | BK14 | PEDCO | 110 | CV | MR | 0001 | F0Z-708263 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 5 | 1 | 2 | 0 | 2.8.5.1.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 5 | 1 | 2 | 1 | 2.8.2.5.1.2.1 | TBE For Geomembrane - BK14 | BK-BK14-PEDCO-110-CV-TB-0001 | BK-BK14-PEDCO-110-CV-TB-0001 | BK | BK14 | PEDCO | 110 | CV | TB | 0001 | F0Z-708264 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 5 | 2 | 0 | 0 | 2.8.2.5.2 | Geotextile
2 | 8 | 2 | 5 | 2 | 1 | 0 | 2.8.5.2.1 | Purchase Material Requisition (PMR)
2 | 8 | 2 | 5 | 2 | 1 | 1 | 2.8.2.5.2.1.1 | PMR For Geotextile - BK14 | BK-BK14-PEDCO-110-CV-MR-0002 | BK-BK14-PEDCO-110-CV-MR-0002 | BK | BK14 | PEDCO | 110 | CV | MR | 0002 | F0Z-708265 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 2 | 5 | 2 | 2 | 0 | 2.8.5.2.2 | Technical Bid Evaluation (TBE)
2 | 8 | 2 | 5 | 2 | 2 | 1 | 2.8.2.5.2.2.1 | TBE For Geotextile - BK14 | BK-BK14-PEDCO-110-CV-TB-0002 | BK-BK14-PEDCO-110-CV-TB-0002 | BK | BK14 | PEDCO | 110 | CV | TB | 0002 | F0Z-708266 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 3 | 0 | 0 | 0 | 0 | 2.8.3 | Commissioning Engineering
2 | 8 | 3 | 0 | 0 | 1 | 0 | 2.8.3.1 | Procedure/Plan
2 | 8 | 3 | 0 | 0 | 1 | 1 | 2.8.3.1.1 | Pre-Commissioning, Commissioning & Startup Procedure - BK14 | BK-BK14-PEDCO-110-CO-PR-0001 | BK-BK14-PEDCO-110-CO-PR-0001 | BK | BK14 | PEDCO | 110 | CO | PR | 0001 | F0Z-708267 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 4 | 0 | 0 | 0 | 0 | 2.8.4 | Field Engineering
2 | 8 | 4 | 0 | 0 | 1 | 0 | 2.8.4.1 | Query
2 | 8 | 4 | 0 | 0 | 1 | 1 | 2.8.4.1.1 | Technical/Site Queries | BK-BK14-PEDCO-110-GE-TQ-0001 | BK-BK14-PEDCO-110-GE-TQ-0001 | BK | BK14 | PEDCO | 110 | GE | TQ | 0001 | F7Z-708268 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 4 | 0 | 0 | 2 | 0 | 2.8.4.2 | Dossier
2 | 8 | 4 | 0 | 0 | 2 | 1 | 2.8.4.2.1 | As-Built Document Booklets - BK14 | BK-BK14-PEDCO-110-GE-DO-0001 | BK-BK14-PEDCO-110-GE-DO-0001 | BK | BK14 | PEDCO | 110 | GE | DO | 0001 | F0Z-708269 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 5 | 0 | 0 | 0 | 0 | 2.8.5 | Engineering Final Documentation
2 | 8 | 5 | 0 | 0 | 1 | 0 | 2.8.5.1 | Manual
2 | 8 | 5 | 0 | 0 | 1 | 1 | 2.8.5.1.1 | Operating Manual - BK14 | BK-BK14-PEDCO-110-GE-ML-0001 | BK-BK14-PEDCO-110-GE-ML-0001 | BK | BK14 | PEDCO | 110 | GE | ML | 0001 | F0Z-708270 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 8 | 5 | 0 | 0 | 2 | 0 | 2.8.5.2 | Dossier
2 | 8 | 5 | 0 | 0 | 2 | 1 | 2.8.5.2.1 | As-Built Document Booklets - BK14 | BK-BK14-PEDCO-110-GE-DO-0001 | BK-BK14-PEDCO-110-GE-DO-0001 | [7 empty] | F0Z-708269 | [43 empty] | Moved to Field | 0
2 | 8 | 5 | 0 | 0 | 2 | 2 | 2.8.5.2.2 | Final Engineering Dossier - BK14 | BK-BK14-PEDCO-110-GE-DO-0002 | BK-BK14-PEDCO-110-GE-DO-0002 | BK | BK14 | PEDCO | 110 | GE | DO | 0002 | F0Z-708271 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 0 | 0 | 0 | 0 | 0 | 2.9 | Package 08-Workover # 12
2 | 9 | 1 | 0 | 0 | 0 | 0 | 2.9.1 | Detail Design
2 | 9 | 1 | 1 | 0 | 0 | 0 | 2.9.1.1 | Process
2 | 9 | 1 | 1 | 1 | 0 | 0 | 2.9.1.1.1 | Drawing/Diagram |  |  | BK | BK12 | PEDCO | 110 | PR | PI | 0001
2 | 9 | 1 | 1 | 1 | 0 | 1 | 2.9.1.1.1.1 | P&ID for Diesel Oil Drum- BK12 | BK-BK12-PEDCO-110-PR-PI-0001 | BK-BK12-PEDCO-110-PR-PI-0001 | BK | BK12 | PEDCO | 110 | PR | PI | 0001 | F2A-708272 | AFC | IFC | 2021-11-29 | 2021-12-01 | 2021-12-06 | 2 | 5 | 7 | IFA | 2022-01-17 | 2022-02-06 | 2022-02-08 | 20 | 2 | 22 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 2022-05-12 | 2022-05-16 | 18 | 4 | 22 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 0 |  | D03 | IFA | T-0795 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03986 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59474 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 2021-11-30 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0422 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02776 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D00 | [5 empty] | 1400-2294-399153 | 2022-02-06 | 1400/11/17 | 2022-02-08 | 1400/11/19 | AP | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0648 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03589 | 2022-03-15 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-443282 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/24 | RJ | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0795 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03986 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-59474 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0001_D02
2 | 9 | 1 | 1 | 1 | 0 | 2 | 2.9.1.1.1.2 | P&ID for Potable Water Tank - BK12 | BK-BK12-PEDCO-110-PR-PI-0002 | BK-BK12-PEDCO-110-PR-PI-0002 | BK | BK12 | PEDCO | 110 | PR | PI | 0002 | F2A-708273 | AFC | IFC | 2021-11-29 | 2021-12-01 | 2021-12-06 | 2 | 5 | 7 | IFA | 2022-01-17 | 2022-02-06 | 2022-02-08 | 20 | 2 | 22 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 2022-05-12 | 2022-05-16 | 18 | 4 | 22 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 0 |  | D03 | IFA | T-0795 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03986 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59474 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 2021-11-30 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0422 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02776 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK14-PEDCO-110-PR-PI-0002_D00 | [5 empty] | 1400-2294-399153 | 2022-02-06 | 1400/11/17 | 2022-02-08 | 1400/11/19 | AP | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0002_D00 | [9 empty] | D02 | IFA | T-0648 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03589 | 2022-03-15 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-PI-0002_D01 | [5 empty] | 1400-2294-443282 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/24 | RJ | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0002_D01 | [9 empty] | D03 | IFA | T-0795 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03986 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-PI-0002_D02 | [5 empty] | 1401-2294-59474 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-BK12-PEDCO-110-PR-PI-0002_D02
2 | 9 | 1 | 1 | 2 | 0 | 0 | 2.9.1.1.2 | List
2 | 9 | 1 | 1 | 2 | 0 | 1 | 2.9.1.1.2.1 | Line List - BK12 | BK-BK12-PEDCO-110-PR-LI-0001 | BK-BK12-PEDCO-110-PR-LI-0001 | BK | BK12 | PEDCO | 110 | PR | LI | 0001 | F0Z-708274 | AFC | IFC | 44633 | 44632 | 44635 | -1 | 3 | 2 | IFA | 44695 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-27 | 0 |  | D01 | IFA | T-0877 | 2022-04-30 | 1401/02/10 | T-0877 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 2022-05-23 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK12-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0650 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03597 | 2022-03-15 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445283 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0877 | 2022-04-30 | 1401/02/10 | T-0877 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 2022-05-23 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK12-PEDCO-110-PR-LI-0001_D00 | [11 empty] | NISOC-CRS-BK-BK12-PEDCO-110-PR-LI-0001_D00
2 | 9 | 1 | 1 | 3 | 0 | 0 | 2.9.1.1.3 | Data Sheet
2 | 9 | 1 | 1 | 3 | 0 | 1 | 2.9.1.1.3.1 | Process Data Sheets For Instrument Devices - BK12 | BK-BK12-PEDCO-110-PR-DT-0001 | BK-BK12-PEDCO-110-PR-DT-0001 | BK | BK12 | PEDCO | 110 | PR | DT | 0001 | F0Z-708275 | AFC | IFC | 44677 | 44695 | 44697 | 18 | 2 | 20 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-12 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03991 | 2022-04-19 | 1401/01/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 2022-05-16 | 1401/02/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 |  |  |  | BK-SUR-ENG-PCS-01-03991 | 2022-04-19 | 1401/01/30 | CM-C2 | [6 empty] | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 2022-05-16 | 1401/02/26 | AP
2 | 9 | 1 | 2 | 0 | 0 | 0 | 2.9.1.2 | HVAC/Plumbing
2 | 9 | 1 | 2 | 1 | 0 | 0 | 2.9.1.2.1 | Calculation
2 | 9 | 1 | 2 | 1 | 0 | 1 | 2.9.1.2.1.1 | HVAC Calculation Note For Switchgear Building - BK12 | BK-BK12-PEDCO-110-HV-CN-0001 | BK-BK12-PEDCO-110-HV-CN-0001 | BK | BK12 | PEDCO | 110 | HV | CN | 0001 | F0Z-708276 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 2 | 1 | 0 | 2 | 2.9.1.2.1.2 | HVAC Calculation Note For Security Building - BK12 | BK-BK12-PEDCO-110-HV-CN-0002 | BK-BK12-PEDCO-110-HV-CN-0002 | BK | BK12 | PEDCO | 110 | HV | CN | 0002 | F0Z-708277 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 2 | 2 | 0 | 0 | 2.9.1.2.2 | Data Sheets
2 | 9 | 1 | 2 | 2 | 0 | 1 | 2.9.1.2.2.1 | Data Sheets For Main HVAC Equipment - BK12 | BK-BK12-PEDCO-110-HV-DT-0001 | BK-BK12-PEDCO-110-HV-DT-0001 | BK | BK12 | PEDCO | 110 | HV | DT | 0001 | F0Z-708278 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 2 | 3 | 0 | 0 | 2.9.1.2.3 | Drawing/Diagram
2 | 9 | 1 | 2 | 3 | 0 | 1 | 2.9.1.2.3.1 | HVAC System Layout For Switchgear Building - BK12 | BK-BK12-PEDCO-110-HV-PY-0001 | BK-BK12-PEDCO-110-HV-PY-0001 | BK | BK12 | PEDCO | 110 | HV | PY | 0001 | F4B-708279 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 2 | 3 | 0 | 2 | 2.9.1.2.3.2 | HVAC System Layout For Security Building - BK12 | BK-BK12-PEDCO-110-HV-PY-0002 | BK-BK12-PEDCO-110-HV-PY-0002 | BK | BK12 | PEDCO | 110 | HV | PY | 0002 | F4B-708280 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 2 | 3 | 0 | 3 | 2.9.1.2.3.3 | Plumbing & Sewage Piping Layout For Switchgear Building - BK12 | BK-BK12-PEDCO-110-HV-PY-0003 | BK-BK12-PEDCO-110-HV-PY-0003 | BK | BK12 | PEDCO | 110 | HV | PY | 0003 | F4B-708281 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 2 | 3 | 0 | 4 | 2.9.1.2.3.4 | Plumbing & Sewage Piping Layout For Security Building - BK12 | BK-BK12-PEDCO-110-HV-PY-0004 | BK-BK12-PEDCO-110-HV-PY-0004 | BK | BK12 | PEDCO | 110 | HV | PY | 0004 | F4B-708282 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 2 | 4 | 0 | 0 | 2.9.1.2.4 | MTO
2 | 9 | 1 | 2 | 4 | 0 | 1 | 2.9.1.2.4.1 | MTO For Building HVAC & Plumbing Systems - BK12 | BK-BK12-PEDCO-110-HV-MT-0001 | BK-BK12-PEDCO-110-HV-MT-0001 | BK | BK12 | PEDCO | 110 | HV | MT | 0001 | F8Z-708283 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 3 | 0 | 0 | 0 | 2.9.1.3 | Piping
2 | 9 | 1 | 3 | 1 | 0 | 0 | 2.9.1.3.1 | MTO
2 | 9 | 1 | 3 | 1 | 0 | 1 | 2.9.1.3.1.1 | MTO For Pipes - BK12 | BK-BK12-PEDCO-110-PI-MT-0001 | BK-BK12-PEDCO-110-PI-MT-0001 | BK | BK12 | PEDCO | 110 | PI | MT | 0001 | F8Z-708284 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 4 | 0 | 0 | 0 | 2.9.1.4 | Electrical
2 | 9 | 1 | 4 | 1 | 0 | 0 | 2.9.1.4.1 | MTO
2 | 9 | 1 | 4 | 1 | 0 | 1 | 2.9.1.4.1.1 | MTO For Transmission Over Head Line - BK12 | BK-BK12-PEDCO-110-EL-MT-0001 | BK-BK12-PEDCO-110-EL-MT-0001 | BK | BK12 | PEDCO | 110 | EL | MT | 0001 | F8Z-708285 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 4 | 1 | 0 | 2 | 2.9.1.4.1.2 | MTO For Lighting & Small Powers - BK12 | BK-BK12-PEDCO-110-EL-MT-0002 | BK-BK12-PEDCO-110-EL-MT-0002 | BK | BK12 | PEDCO | 110 | EL | MT | 0002 | F8Z-708286 | IFI | IFI | 2022-06-01 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-18 | 2022-05-18 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04483 | 2022-05-29 | 1401/03/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 |  |  |  | BK-SUR-ENG-ELE-01-04483 | 2022-05-29 | 1401/03/09 | CM-C2
2 | 9 | 1 | 4 | 1 | 0 | 3 | 2.9.1.4.1.3 | MTO For Power & Control Cables - BK12 | BK-BK12-PEDCO-110-EL-MT-0003 | BK-BK12-PEDCO-110-EL-MT-0003 | BK | BK12 | PEDCO | 110 | EL | MT | 0003 | F8Z-708287 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 4 | 1 | 0 | 4 | 2.9.1.4.1.4 | MTO For Tray/Ladder and Accessories - BK12 | BK-BK12-PEDCO-110-EL-MT-0004 | BK-BK12-PEDCO-110-EL-MT-0004 | BK | BK12 | PEDCO | 110 | EL | MT | 0004 | F8Z-708288 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 4 | 1 | 0 | 5 | 2.9.1.4.1.5 | MTO For Electrical Bulk Items - BK12 | BK-BK12-PEDCO-110-EL-MT-0005 | BK-BK12-PEDCO-110-EL-MT-0005 | BK | BK12 | PEDCO | 110 | EL | MT | 0005 | F8Z-708289 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 4 | 1 | 0 | 6 | 2.9.1.4.1.6 | MTO For Earthing & Lightning Systems - BK12 | BK-BK12-PEDCO-110-EL-MT-0006 | BK-BK12-PEDCO-110-EL-MT-0006 | BK | BK12 | PEDCO | 110 | EL | MT | 0006 | F8Z-708290 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 5 | 0 | 0 | 0 | 2.9.1.5 | Architecture
2 | 9 | 1 | 5 | 1 | 0 | 0 | 2.9.1.5.1 | Drawing/Diagram
2 | 9 | 1 | 5 | 1 | 0 | 1 | 2.9.1.5.1.1 | Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-12 | BK-BK12-PEDCO-110-AR-DW-0001 | BK-BK12-PEDCO-110-AR-DW-0001 | BK | BK12 | PEDCO | 110 | AR | DW | 0001 | F4A-708291 | AFC | IFC | 2022-05-15 | 2022-05-09 | 2022-05-16 | -6 | 7 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-01 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | [13 empty] | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | CM
2 | 9 | 1 | 5 | 1 | 0 | 2 | 2.9.1.5.1.2 | Architectural Drawing For Switchgear Building of Well Pads - BK-12 | BK-BK12-PEDCO-110-AR-DW-0002 | BK-BK12-PEDCO-110-AR-DW-0002 | BK | BK12 | PEDCO | 110 | AR | DW | 0002 | F4B-708292 | AFC | IFC | 2022-03-23 | 2022-03-15 | 2022-03-25 | -8 | 10 | 2 | IFC | 2022-06-01 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-18 | 0 |  | D01 | IFC | T-0974 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-BK12-PEDCO-110-AR-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK12-PEDCO-110-AR-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0707 | 2022-03-09 | 1400/12/18 |  |  |  | RE BK-SUR-ENG-ARC-00-03551 | 2022-03-14 | 1400/12/23 | CM | [6 empty] | 1400-2294-450549 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | RJ | [10 empty] | D01 | IFC | T-0974 | 2022-05-18 | 1401/02/28 | [7 empty] | PEDCO-CRS-BK-BK12-PEDCO-110-AR-DW-0002_D00 | [11 empty] | NISOC-CRS-BK-BK12-PEDCO-110-AR-DW-0002_D00
2 | 9 | 1 | 5 | 1 | 0 | 3 | 2.9.1.5.1.3 | Architectural Drawing For Security Building of Well Pads - BK-12 | BK-BK12-PEDCO-110-AR-DW-0003 | BK-BK12-PEDCO-110-AR-DW-0003 | BK | BK12 | PEDCO | 110 | AR | DW | 0003 | F4B-708293 | AFC | IFC | 2022-05-15 | 2022-05-14 | 2022-05-16 | -1 | 2 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04190 | 2022-05-10 | 1401/02/20 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 2022-05-16 | 1401/02/26 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04190 | 2022-05-10 | 1401/02/20 | CM-C2 | [6 empty] | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 2022-05-16 | 1401/02/26 | RJ
2 | 9 | 1 | 5 | 2 | 0 | 0 | 2.9.1.5.2 | MTO
2 | 9 | 1 | 5 | 2 | 0 | 1 | 2.9.1.5.2.1 | MTO For Architectural Works - BK12 | BK-BK12-PEDCO-110-AR-MT-0001 | BK-BK12-PEDCO-110-AR-MT-0001 | BK | BK12 | PEDCO | 110 | AR | MT | 0001 | F8Z-708294 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 6 | 0 | 0 | 0 | 2.9.1.6 | Civil
2 | 9 | 1 | 6 | 1 | 0 | 0 | 2.9.1.6.1 | Drawing/Diagram
2 | 9 | 1 | 6 | 1 | 0 | 1 | 2.9.1.6.1.1 | Civil and Structural drawings - BK12 | BK-BK12-PEDCO-110-CV-DW-0001 | BK-BK12-PEDCO-110-CV-DW-0001 | BK | BK12 | PEDCO | 110 | CV | DW | 0001 | F4A-708295 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 6 | 1 | 0 | 2 | 2.9.1.6.1.2 | General Civil Layout - BK12 | BK-BK12-PEDCO-110-CV-PY-0001 | BK-BK12-PEDCO-110-CV-PY-0001 | BK | BK12 | PEDCO | 110 | CV | PY | 0001 | F4A-708296 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 6 | 1 | 0 | 3 | 2.9.1.6.1.3 | Rough Grading Plans -BK12 | BK-BK12-PEDCO-110-CV-PY-0003 | BK-BK12-PEDCO-110-CV-PY-0003 | BK | BK12 | PEDCO | 110 | CV | PY | 0003 | F4A-708297 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 6 | 2 | 0 | 0 | 2.9.1.6.2 | Report
2 | 9 | 1 | 6 | 2 | 0 | 1 | 2.9.1.6.2.1 | Site Visit Report (Civil Work) - BK12 | BK-BK12-PEDCO-110-CV-RT-0001 | BK-BK12-PEDCO-110-CV-RT-0001 | BK | BK12 | PEDCO | 110 | CV | RT | 0001 | F0Z-708298 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 6 | 3 | 0 | 0 | 2.9.1.6.3 | MTO
2 | 9 | 1 | 6 | 3 | 0 | 1 | 2.9.1.6.3.1 | MTO For Civil Works - BK12 | BK-BK12-PEDCO-110-CV-MT-0001 | BK-BK12-PEDCO-110-CV-MT-0001 | BK | BK12 | PEDCO | 110 | CV | MT | 0001 | F8Z-708299 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 7 | 0 | 0 | 0 | 2.9.1.7 | Structure
2 | 9 | 1 | 7 | 1 | 0 | 0 | 2.9.1.7.1 | Drawing/Diagram
2 | 9 | 1 | 7 | 1 | 0 | 1 | 2.9.1.7.1.1 | Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0001 | BK-BK12-PEDCO-110-ST-DW-0001 | BK | BK12 | PEDCO | 110 | ST | DW | 0001 | F4G-708300 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 7 | 1 | 0 | 2 | 2.9.1.7.1.2 | Foundation Drawing For Security Building For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0002 | BK-BK12-PEDCO-110-ST-DW-0002 | BK | BK12 | PEDCO | 110 | ST | DW | 0002 | F4Q-708301 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 7 | 1 | 0 | 3 | 2.9.1.7.1.3 | Structural Drawing For Security Building For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0003 | BK-BK12-PEDCO-110-ST-DW-0003 | BK | BK12 | PEDCO | 110 | ST | DW | 0003 | F4M-708302 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 7 | 1 | 0 | 4 | 2.9.1.7.1.4 | Foundation Drawing For Switchgear Building For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0004 | BK-BK12-PEDCO-110-ST-DW-0004 | BK | BK12 | PEDCO | 110 | ST | DW | 0004 | F4Q-708303 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 7 | 1 | 0 | 5 | 2.9.1.7.1.5 | Structural Drawing For Switchgear Building For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0005 | BK-BK12-PEDCO-110-ST-DW-0005 | BK | BK12 | PEDCO | 110 | ST | DW | 0005 | F4M-708304 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 7 | 1 | 0 | 6 | 2.9.1.7.1.6 | Foundation Drawing For Potable Water Tank For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0006 | BK-BK12-PEDCO-110-ST-DW-0006 | BK | BK12 | PEDCO | 110 | ST | DW | 0006 | F4Q-708305 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 7 | 1 | 0 | 7 | 2.9.1.7.1.7 | Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0007 | BK-BK12-PEDCO-110-ST-DW-0007 | BK | BK12 | PEDCO | 110 | ST | DW | 0007 | F4Q-708306 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 7 | 1 | 0 | 8 | 2.9.1.7.1.8 | Structural Drawing For Diesel Generator Shelter For Well Pads - BK-12 | BK-BK12-PEDCO-110-ST-DW-0008 | BK-BK12-PEDCO-110-ST-DW-0008 | BK | BK12 | PEDCO | 110 | ST | DW | 0008 | F4M-708307 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 7 | 2 | 0 | 0 | 2.9.1.7.2 | MTO
2 | 9 | 1 | 7 | 2 | 0 | 1 | 2.9.1.7.2.1 | MTO For Structural Works - BK12 | BK-BK12-PEDCO-110-ST-MT-0001 | BK-BK12-PEDCO-110-ST-MT-0001 | BK | BK12 | PEDCO | 110 | ST | MT | 0001 | F8Z-708308 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 8 | 0 | 0 | 0 | 2.9.1.0 | Geotechnic
2 | 9 | 1 | 8 | 0 | 1 | 0 | 2.9.1.1 | Report
2 | 9 | 1 | 8 | 0 | 1 | 1 | 2.9.1.8.1.1 | Geotechnical Investigation Report - BK12 | BK-BK12-PEDCO-110-GT-RT-0001 | BK-BK12-PEDCO-110-GT-RT-0001 | BK | BK12 | PEDCO | 110 | GT | RT | 0001 | F0Z-708309 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 1 | 8 | 0 | 2 | 0 | 2.9.1.2 | Drawing/Diagram
2 | 9 | 1 | 8 | 0 | 2 | 1 | 2.9.1.8.2.1 | Over Head Line Plan and Profile - BK12 | BK-BK12-PEDCO-110-SU-DW-0001 | BK-BK12-PEDCO-110-SU-DW-0001 | BK | BK12 | PEDCO | 110 | SU | DW | 0001 | F4A-708310 | AFC | IFC | 44711 | 0 | 0 | -44711 | 0 | -44711 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-16 | 0 |  | D00 | IFC | T-0962 | 2022-05-16 | 1401/02/26 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04476 | 2022-05-29 | 1401/03/08 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0962 | 2022-05-16 | 1401/02/26 |  |  |  | BK-SUR-ENG-ELE-01-04476 | 2022-05-29 | 1401/03/08 | CM-C3
2 | 9 | 2 | 0 | 0 | 0 | 0 | 2.9.2 | Procurement Engineering
2 | 9 | 2 | 1 | 0 | 0 | 0 | 2.9.2.1 | Piping
2 | 9 | 2 | 1 | 1 | 0 | 0 | 2.9.2.1.1 | Pipe
2 | 9 | 2 | 1 | 1 | 1 | 0 | 2.9.1.1.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 1 | 1 | 1 | 1 | 2.9.2.1.1.1.1 | PMR For Pipes - BK12 | BK-BK12-PEDCO-110-PI-MR-0001 | BK-BK12-PEDCO-110-PI-MR-0001 | BK | BK12 | PEDCO | 110 | PI | MR | 0001 | F0Z-708311 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 1 | 1 | 2 | 0 | 2.9.1.1.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 1 | 1 | 2 | 1 | 2.9.2.1.1.2.1 | TBE For Pipes - BK12 | BK-BK12-PEDCO-110-PI-TB-0001 | BK-BK12-PEDCO-110-PI-TB-0001 | BK | BK12 | PEDCO | 110 | PI | TB | 0001 | F0Z-708312 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 1 | 2 | 0 | 0 | 2.9.2.1.2 | Pipe Support
2 | 9 | 2 | 1 | 2 | 1 | 0 | 2.9.1.2.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 1 | 2 | 1 | 1 | 2.9.2.1.2.1.1 | PMR For Pipe Support - BK12 | BK-BK12-PEDCO-110-PI-MR-0002 | BK-BK12-PEDCO-110-PI-MR-0002 | BK | BK12 | PEDCO | 110 | PI | MR | 0002 | F0Z-708313 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 1 | 2 | 2 | 0 | 2.9.1.2.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 1 | 2 | 2 | 1 | 2.9.2.1.2.2.1 | TBE For Pipe Support - BK12 | BK-BK12-PEDCO-110-PI-TB-0002 | BK-BK12-PEDCO-110-PI-TB-0002 | BK | BK12 | PEDCO | 110 | PI | TB | 0002 | F0Z-708314 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 2 | 0 | 0 | 0 | 2.9.2.2 | HVAC
2 | 9 | 2 | 2 | 1 | 0 | 0 | 2.9.2.2.1 | Main HVAC Equipment
2 | 9 | 2 | 2 | 1 | 1 | 0 | 2.9.2.1.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 2 | 1 | 1 | 1 | 2.9.2.2.1.1.1 | PMR For Main HVAC Equipment - BK12 | BK-BK12-PEDCO-110-HV-MR-0001 | BK-BK12-PEDCO-110-HV-MR-0001 | BK | BK12 | PEDCO | 110 | HV | MR | 0001 | F0Z-708315 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 2 | 1 | 2 | 0 | 2.9.2.1.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 2 | 1 | 2 | 1 | 2.9.2.2.1.2.1 | TBE For Main HVAC Equipment - BK12 | BK-BK12-PEDCO-110-HV-TB-0001 | BK-BK12-PEDCO-110-HV-TB-0001 | BK | BK12 | PEDCO | 110 | HV | TB | 0001 | F0Z-708316 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 0 | 0 | 0 | 2.9.2.3 | Electrical
2 | 9 | 2 | 3 | 1 | 0 | 0 | 2.9.2.3.1 | Transformers
2 | 9 | 2 | 3 | 1 | 1 | 0 | 2.9.3.1.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 1 | 1 | 1 | 2.9.2.3.1.1.1 | PMR For Transformers - BK12 | BK-BK12-PEDCO-110-EL-MR-0001 | BK-BK12-PEDCO-110-EL-MR-0001 | BK | BK12 | PEDCO | 110 | EL | MR | 0001 | F0Z-708317 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 1 | 2 | 0 | 2.9.3.1.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 1 | 2 | 1 | 2.9.2.3.1.2.1 | TBE For Transformers - BK12 | BK-BK12-PEDCO-110-EL-TB-0001 | BK-BK12-PEDCO-110-EL-TB-0001 | BK | BK12 | PEDCO | 110 | EL | TB | 0001 | F0Z-708318 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 2 | 0 | 0 | 2.9.2.3.2 | LV Switchgear & MCC
2 | 9 | 2 | 3 | 2 | 1 | 0 | 2.9.3.2.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 2 | 1 | 1 | 2.9.2.3.2.1.1 | PMR For LV Switchgear & MCC - BK12 | BK-BK12-PEDCO-110-EL-MR-0002 | BK-BK12-PEDCO-110-EL-MR-0002 | BK | BK12 | PEDCO | 110 | EL | MR | 0002 | F0Z-708319 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 2 | 2 | 0 | 2.9.3.2.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 2 | 2 | 1 | 2.9.2.3.2.2.1 | TBE For LV Switchgear & MCC - BK12 | BK-BK12-PEDCO-110-EL-TB-0002 | BK-BK12-PEDCO-110-EL-TB-0002 | BK | BK12 | PEDCO | 110 | EL | TB | 0002 | F0Z-708320 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 3 | 0 | 0 | 2.9.2.3.3 | Emergency Diesel Generator
2 | 9 | 2 | 3 | 3 | 1 | 0 | 2.9.3.3.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 3 | 1 | 1 | 2.9.2.3.3.1.1 | PMR For Emergency Diesel Generator - BK12 | BK-BK12-PEDCO-110-EL-MR-0003 | BK-BK12-PEDCO-110-EL-MR-0003 | BK | BK12 | PEDCO | 110 | EL | MR | 0003 | F0Z-708321 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 3 | 2 | 0 | 2.9.3.3.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 3 | 2 | 1 | 2.9.2.3.3.2.1 | TBE For Emergency Diesel Generator - BK12 | BK-BK12-PEDCO-110-EL-TB-0003 | BK-BK12-PEDCO-110-EL-TB-0003 | BK | BK12 | PEDCO | 110 | EL | TB | 0003 | F0Z-708322 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 4 | 0 | 0 | 2.9.2.3.4 | UPS System
2 | 9 | 2 | 3 | 4 | 1 | 0 | 2.9.3.4.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 4 | 1 | 1 | 2.9.2.3.4.1.1 | PMR For UPS System - BK12 | BK-BK12-PEDCO-110-EL-MR-0004 | BK-BK12-PEDCO-110-EL-MR-0004 | BK | BK12 | PEDCO | 110 | EL | MR | 0004 | F0Z-708323 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 4 | 2 | 0 | 2.9.3.4.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 4 | 2 | 1 | 2.9.2.3.4.2.1 | TBE For UPS System - BK12 | BK-BK12-PEDCO-110-EL-TB-0004 | BK-BK12-PEDCO-110-EL-TB-0004 | BK | BK12 | PEDCO | 110 | EL | TB | 0004 | F0Z-708324 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 5 | 0 | 0 | 2.9.2.3.5 | DC Charger
2 | 9 | 2 | 3 | 5 | 1 | 0 | 2.9.3.5.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 5 | 1 | 1 | 2.9.2.3.5.1.1 | PMR For DC Charger - BK12 | BK-BK12-PEDCO-110-EL-MR-0005 | BK-BK12-PEDCO-110-EL-MR-0005 | BK | BK12 | PEDCO | 110 | EL | MR | 0005 | F0Z-708325 | IFI | IFI | 44691 | 0 | 0 | -44691 | 0 | -44691 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-26 | 2022-04-26 |  | D00 | IFI | T-0864 | 2022-04-26 | 1401/02/06 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04211 | 2022-05-10 | 1401/02/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0864 | 2022-04-26 | 1401/02/06 |  |  |  | BK-SUR-ENG-ELE-01-04211 | 2022-05-10 | 1401/02/20 | CM-C3
2 | 9 | 2 | 3 | 5 | 2 | 0 | 2.9.3.5.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 5 | 2 | 1 | 2.9.2.3.5.2.1 | TBE For DC Charger - BK12 | BK-BK12-PEDCO-110-EL-TB-0005 | BK-BK12-PEDCO-110-EL-TB-0005 | BK | BK12 | PEDCO | 110 | EL | TB | 0005 | F0Z-708326 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 6 | 0 | 0 | 2.9.2.3.6 | Capacitor Bank
2 | 9 | 2 | 3 | 6 | 1 | 0 | 2.9.3.6.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 6 | 1 | 1 | 2.9.2.3.6.1.1 | PMR For Capacitor Bank - BK12 | BK-BK12-PEDCO-110-EL-MR-0006 | BK-BK12-PEDCO-110-EL-MR-0006 | BK | BK12 | PEDCO | 110 | EL | MR | 0006 | F0Z-708327 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 6 | 2 | 0 | 2.9.3.6.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 6 | 2 | 1 | 2.9.2.3.6.2.1 | TBE For Capacitor Bank - BK12 | BK-BK12-PEDCO-110-EL-TB-0006 | BK-BK12-PEDCO-110-EL-TB-0006 | BK | BK12 | PEDCO | 110 | EL | TB | 0006 | F0Z-708328 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 7 | 0 | 0 | 2.9.2.3.7 | Lighting & Distribution Main Panels
2 | 9 | 2 | 3 | 7 | 1 | 0 | 2.9.3.7.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 7 | 1 | 1 | 2.9.2.3.7.1.1 | PMR For Lighting & Distribution Main Panels - BK12 | BK-BK12-PEDCO-110-EL-MR-0007 | BK-BK12-PEDCO-110-EL-MR-0007 | BK | BK12 | PEDCO | 110 | EL | MR | 0007 | F0Z-708329 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 7 | 2 | 0 | 2.9.3.7.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 7 | 2 | 1 | 2.9.2.3.7.2.1 | TBE For Lighting & Distribution Main Panels - BK12 | BK-BK12-PEDCO-110-EL-TB-0007 | BK-BK12-PEDCO-110-EL-TB-0007 | BK | BK12 | PEDCO | 110 | EL | TB | 0007 | F0Z-708330 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 8 | 0 | 0 | 2.9.2.3.8 | Earthing & Lightning System
2 | 9 | 2 | 3 | 8 | 1 | 0 | 2.9.3.8.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 8 | 1 | 1 | 2.9.2.3.8.1.1 | PMR For Earthing & Lightning System - BK12 | BK-BK12-PEDCO-110-EL-MR-0008 | BK-BK12-PEDCO-110-EL-MR-0008 | BK | BK12 | PEDCO | 110 | EL | MR | 0008 | F0Z-708331 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 8 | 2 | 0 | 2.9.3.8.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 8 | 2 | 1 | 2.9.2.3.8.2.1 | TBE For Earthing & Lightning System - BK12 | BK-BK12-PEDCO-110-EL-TB-0008 | BK-BK12-PEDCO-110-EL-TB-0008 | BK | BK12 | PEDCO | 110 | EL | TB | 0008 | F0Z-708332 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 9 | 0 | 0 | 2.9.2.3.9 | Lighting and Small Power Equipment
2 | 9 | 2 | 3 | 9 | 1 | 0 | 2.9.3.9.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 9 | 1 | 1 | 2.9.2.3.9.1.1 | PMR For Lighting and Small Power Equipment - BK12 | BK-BK12-PEDCO-110-EL-MR-0009 | BK-BK12-PEDCO-110-EL-MR-0009 | BK | BK12 | PEDCO | 110 | EL | MR | 0009 | F0Z-708333 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 9 | 2 | 0 | 2.9.3.9.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 9 | 2 | 1 | 2.9.2.3.9.2.1 | TBE For Lighting and Small Power Equipment - BK12 | BK-BK12-PEDCO-110-EL-TB-0009 | BK-BK12-PEDCO-110-EL-TB-0009 | BK | BK12 | PEDCO | 110 | EL | TB | 0009 | F0Z-708334 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 10 | 0 | 0 | 2.9.2.3.10 | Tray/Ladder and Accessories
2 | 9 | 2 | 3 | 10 | 1 | 0 | 2.9.3.10.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 10 | 1 | 1 | 2.9.2.3.10.1.1 | PMR For Tray/Ladder and Accessories - BK12 | BK-BK12-PEDCO-110-EL-MR-0010 | BK-BK12-PEDCO-110-EL-MR-0010 | BK | BK12 | PEDCO | 110 | EL | MR | 0010 | F0Z-708335 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 10 | 2 | 0 | 2.9.3.10.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 10 | 2 | 1 | 2.9.2.3.10.2.1 | TBE For Tray/Ladder and Accessories - BK12 | BK-BK12-PEDCO-110-EL-TB-0010 | BK-BK12-PEDCO-110-EL-TB-0010 | BK | BK12 | PEDCO | 110 | EL | TB | 0010 | F0Z-708336 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 11 | 0 | 0 | 2.9.2.3.11 | Power & Control Cables
2 | 9 | 2 | 3 | 11 | 1 | 0 | 2.9.3.11.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 11 | 1 | 1 | 2.9.2.3.11.1.1 | PMR For Power & Control Cables - BK12 | BK-BK12-PEDCO-110-EL-MR-0011 | BK-BK12-PEDCO-110-EL-MR-0011 | BK | BK12 | PEDCO | 110 | EL | MR | 0011 | F0Z-708337 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 11 | 2 | 0 | 2.9.3.11.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 11 | 2 | 1 | 2.9.2.3.11.2.1 | TBE For Power & Control Cables - BK12 | BK-BK12-PEDCO-110-EL-TB-0011 | BK-BK12-PEDCO-110-EL-TB-0011 | BK | BK12 | PEDCO | 110 | EL | TB | 0011 | F0Z-708338 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 12 | 0 | 0 | 2.9.2.3.12 | Electrical Bulk Items
2 | 9 | 2 | 3 | 12 | 1 | 0 | 2.9.3.12.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 12 | 1 | 1 | 2.9.2.3.12.1.1 | PMR For Electrical Bulk Items - BK12 | BK-BK12-PEDCO-110-EL-MR-0012 | BK-BK12-PEDCO-110-EL-MR-0012 | BK | BK12 | PEDCO | 110 | EL | MR | 0012 | F0Z-708339 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 12 | 2 | 0 | 2.9.3.12.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 12 | 2 | 1 | 2.9.2.3.12.2.1 | TBE For Electrical Bulk Items - BK12 | BK-BK12-PEDCO-110-EL-TB-0012 | BK-BK12-PEDCO-110-EL-TB-0012 | BK | BK12 | PEDCO | 110 | EL | TB | 0012 | F0Z-708340 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 13 | 0 | 0 | 2.9.2.3.13 | Transmission Over head Line
2 | 9 | 2 | 3 | 13 | 1 | 0 | 2.9.3.13.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 3 | 13 | 1 | 1 | 2.9.2.3.13.1.1 | PMR For Transmission Over head Line - BK12 | BK-BK12-PEDCO-110-EL-MR-0013 | BK-BK12-PEDCO-110-EL-MR-0013 | BK | BK12 | PEDCO | 110 | EL | MR | 0013 | F0Z-708341 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 3 | 13 | 2 | 0 | 2.9.3.13.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 3 | 13 | 2 | 1 | 2.9.2.3.13.2.1 | TBE For Transmission Over head Line - BK12 | BK-BK12-PEDCO-110-EL-TB-0013 | BK-BK12-PEDCO-110-EL-TB-0013 | BK | BK12 | PEDCO | 110 | EL | TB | 0013 | F0Z-708342 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 4 | 0 | 0 | 0 | 2.9.2.4 | Structure
2 | 9 | 2 | 4 | 1 | 0 | 0 | 2.9.2.4.1 | Steel Structure Items
2 | 9 | 2 | 4 | 1 | 1 | 0 | 2.9.4.1.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 4 | 1 | 1 | 1 | 2.9.2.4.1.1.1 | PMR For Steel Structure Items - BK12 | BK-BK12-PEDCO-110-ST-MR-0001 | BK-BK12-PEDCO-110-ST-MR-0001 | BK | BK12 | PEDCO | 110 | ST | MR | 0001 | F0Z-708343 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 4 | 1 | 2 | 0 | 2.9.4.1.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 4 | 1 | 2 | 1 | 2.9.2.4.1.2.1 | TBE For Steel Structure Items - BK12 | BK-BK12-PEDCO-110-ST-TB-0001 | BK-BK12-PEDCO-110-ST-TB-0001 | BK | BK12 | PEDCO | 110 | ST | TB | 0001 | F0Z-708344 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 4 | 2 | 0 | 0 | 2.9.2.4.2 | Anchor Bolts
2 | 9 | 2 | 4 | 2 | 1 | 0 | 2.9.4.2.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 4 | 2 | 1 | 1 | 2.9.2.4.2.1.1 | PMR For Anchor Bolts - BK12 | BK-BK12-PEDCO-110-ST-MR-0002 | BK-BK12-PEDCO-110-ST-MR-0002 | BK | BK12 | PEDCO | 110 | ST | MR | 0002 | F0Z-708345 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 4 | 2 | 2 | 0 | 2.9.4.2.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 4 | 2 | 2 | 1 | 2.9.2.4.2.2.1 | TBE For Anchor Bolts - BK12 | BK-BK12-PEDCO-110-ST-TB-0002 | BK-BK12-PEDCO-110-ST-TB-0002 | BK | BK12 | PEDCO | 110 | ST | TB | 0002 | F0Z-708346 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 4 | 3 | 0 | 0 | 2.9.2.4.3 | Blast Proof Doors
2 | 9 | 2 | 4 | 3 | 1 | 0 | 2.9.4.3.1 | Purchase Material Requisition (PMR)
2 | 9 | 2 | 4 | 3 | 1 | 1 | 2.9.2.4.3.1.1 | PMR For Blast Proof Doors - BK12 | BK-BK12-PEDCO-110-ST-MR-0003 | BK-BK12-PEDCO-110-ST-MR-0003 | BK | BK12 | PEDCO | 110 | ST | MR | 0003 | F0Z-708347 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 2 | 4 | 3 | 2 | 0 | 2.9.4.3.2 | Technical Bid Evaluation (TBE)
2 | 9 | 2 | 4 | 3 | 2 | 1 | 2.9.2.4.3.2.1 | TBE For Blast Proof Doors - BK12 | BK-BK12-PEDCO-110-ST-TB-0003 | BK-BK12-PEDCO-110-ST-TB-0003 | BK | BK12 | PEDCO | 110 | ST | TB | 0003 | F0Z-708348 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 3 | 0 | 0 | 0 | 0 | 2.9.3 | Commissioning Engineering
2 | 9 | 3 | 0 | 0 | 1 | 0 | 2.9.3.1 | Procedure/Plan
2 | 9 | 3 | 0 | 0 | 1 | 1 | 2.9.3.1 | Pre-Commissioning, Commissioning & Startup Procedure - BK12 | BK-BK12-PEDCO-110-CO-PR-0001 | BK-BK12-PEDCO-110-CO-PR-0001 | BK | BK12 | PEDCO | 110 | CO | PR | 0001 | F0Z-708349 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 3 | 0 | 1 | 0 | 0 | 2.9.3.1 | Field Engineering
2 | 9 | 3 | 0 | 1 | 1 | 0 | 2.9.3.1 | Query
2 | 9 | 3 | 0 | 1 | 1 | 1 | 2.9.3.1.1.1 | Technical/Site Queries | BK-BK12-PEDCO-110-GE-TQ-0001 | BK-BK12-PEDCO-110-GE-TQ-0001 | BK | BK12 | PEDCO | 110 | GE | TQ | 0001 | F7Z-708350 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 3 | 0 | 1 | 2 | 0 | 2.9.3.2 | Dossier
2 | 9 | 3 | 0 | 1 | 2 | 1 | 2.9.3.1.2.1 | As-Built Document Booklets - BK12 | BK-BK12-PEDCO-110-GE-DO-0001 | BK-BK12-PEDCO-110-GE-DO-0001 | BK | BK12 | PEDCO | 110 | GE | DO | 0001 | F0Z-708351 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 4 | 0 | 0 | 0 | 0 | 2.9.4 | Engineering Final Documentation
2 | 9 | 4 | 0 | 0 | 1 | 0 | 2.9.4.1 | Manual
2 | 9 | 4 | 0 | 0 | 1 | 1 | 2.9.4.1 | Operating Manual - BK12 | BK-BK12-PEDCO-110-GE-ML-0001 | BK-BK12-PEDCO-110-GE-ML-0001 | BK | BK12 | PEDCO | 110 | GE | ML | 0001 | F0Z-708352 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 9 | 4 | 0 | 0 | 2 | 0 | 2.9.4.2 | Dossier
2 | 9 | 4 | 0 | 0 | 2 | 1 | 2.9.4.2 | As-Built Document Booklets - BK12 | BK-BK12-PEDCO-110-GE-DO-0001 | BK-BK12-PEDCO-110-GE-DO-0001 | [7 empty] | F0Z-708351 | [43 empty] | Moved to Field | 0
2 | 9 | 4 | 0 | 0 | 2 | 2 | 2.9.4.2 | Final Engineering Dossier - BK12 | BK-BK12-PEDCO-110-GE-DO-0002 | BK-BK12-PEDCO-110-GE-DO-0002 | BK | BK12 | PEDCO | 110 | GE | DO | 0002 | F0Z-708353 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 0 | 0 | 0 | 0 | 0 | 2.10 | Package 09-Workover # 15
2 | 10 | 1 | 0 | 0 | 0 | 0 | 2.10.1 | Detail Design
2 | 10 | 1 | 1 | 0 | 0 | 0 | 2.10.1.1 | Process
2 | 10 | 1 | 1 | 1 | 0 | 0 | 2.10.1.1.1 | Drawing/Diagram
2 | 10 | 1 | 1 | 1 | 0 | 1 | 2.10.1.1.1.1 | P&ID for Diesel Oil Drum- BK15 | BK-BK15-PEDCO-110-PR-PI-0001 | BK-BK15-PEDCO-110-PR-PI-0001 | BK | BK15 | PEDCO | 110 | PR | PI | 0001 | F2A-708354 | AFC | IFC | 2021-11-29 | 2021-12-01 | 2021-12-06 | 2 | 5 | 7 | IFA | 2022-01-17 | 2022-02-08 | 2022-02-12 | 22 | 4 | 26 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 0 | 0 | -44675 | 0 | -44675 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 0 |  | D03 | IFA | T-0794 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03985 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 2021-11-30 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0423 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02778 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-402841 | 2022-02-08 | 1400/11/19 | 2022-02-12 | 1400/11/23 | AP | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0649 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03591 | 2022-03-14 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-443282 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/24 | RJ | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0794 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03985 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D02 | [11 empty] | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0001_D02
2 | 10 | 1 | 1 | 1 | 0 | 2 | 2.10.1.1.1.2 | P&ID for Potable Water Tank - BK15 | BK-BK15-PEDCO-110-PR-PI-0002 | BK-BK15-PEDCO-110-PR-PI-0002 | BK | BK15 | PEDCO | 110 | PR | PI | 0002 | F2A-708355 | AFC | IFC | 2021-11-29 | 2021-12-01 | 2021-12-06 | 2 | 5 | 7 | IFA | 2022-01-17 | 2022-02-08 | 2022-02-12 | 22 | 4 | 26 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 0 | 0 | -44675 | 0 | -44675 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 0 |  | D03 | IFA | T-0794 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03985 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 2021-11-30 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0423 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02778 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D00 | [5 empty] | 1400-2294-402841 | 2022-02-08 | 1400/11/19 | 2022-02-12 | 1400/11/23 | AP | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D00 | [9 empty] | D02 | IFA | T-0649 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03591 | 2022-03-14 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D01 | [5 empty] | 1400-2294-443282 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/24 | RJ | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D01 | [9 empty] | D03 | IFA | T-0794 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03985 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D02 | [11 empty] | NISOC-CRS-BK-BK15-PEDCO-110-PR-PI-0002_D02
2 | 10 | 1 | 1 | 2 | 0 | 0 | 2.10.1.1.2 | List
2 | 10 | 1 | 1 | 2 | 0 | 1 | 2.10.1.1.2.1 | Line List - BK15 | BK-BK15-PEDCO-110-PR-LI-0001 | BK-BK15-PEDCO-110-PR-LI-0001 | BK | BK15 | PEDCO | 110 | PR | LI | 0001 | F0Z-708356 | AFC | IFC | 44633 | 44632 | 44635 | -1 | 3 | 2 | IFA | 44695 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-27 | 0 |  | D01 | IFA | T-0877 | 2022-04-30 | 1401/02/10 | T-0877 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 2022-05-23 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK15-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0650 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03597 | 2022-03-15 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445283 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0877 | 2022-04-30 | 1401/02/10 | T-0877 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 2022-05-23 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-PR-LI-0001_D00 | [11 empty] | NISOC-CRS-BK-BK15-PEDCO-110-PR-LI-0001_D00
2 | 10 | 1 | 1 | 3 | 0 | 0 | 2.10.1.1.3 | Data Sheet
2 | 10 | 1 | 1 | 3 | 0 | 1 | 2.10.1.1.3.1 | Process Data Sheets For Instrument Devices - BK15 | BK-BK15-PEDCO-110-PR-DT-0001 | BK-BK15-PEDCO-110-PR-DT-0001 | BK | BK15 | PEDCO | 110 | PR | DT | 0001 | F0Z-708357 | AFC | IFC | 44677 | 44695 | 44697 | 18 | 2 | 20 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-12 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03991 | 2022-04-19 | 1401/01/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 2022-05-16 | 1401/02/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 |  |  |  | BK-SUR-ENG-PCS-01-03991 | 2022-04-19 | 1401/01/30 | CM-C2 | [6 empty] | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 2022-05-16 | 1401/02/26 | AP
2 | 10 | 1 | 2 | 0 | 0 | 0 | 2.10.1.2 | HVAC/Plumbing
2 | 10 | 1 | 2 | 1 | 0 | 0 | 2.10.1.2.1 | Calculation
2 | 10 | 1 | 2 | 1 | 0 | 1 | 2.10.1.2.1.1 | HVAC Calculation Note For Switchgear Building - BK15 | BK-BK15-PEDCO-110-HV-CN-0001 | BK-BK15-PEDCO-110-HV-CN-0001 | BK | BK15 | PEDCO | 110 | HV | CN | 0001 | F0Z-708358 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 2 | 1 | 0 | 2 | 2.10.1.2.1.2 | HVAC Calculation Note For Security Building - BK15 | BK-BK15-PEDCO-110-HV-CN-0002 | BK-BK15-PEDCO-110-HV-CN-0002 | BK | BK15 | PEDCO | 110 | HV | CN | 0002 | F0Z-708359 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 2 | 2 | 0 | 0 | 2.10.1.2.2 | Data Sheets
2 | 10 | 1 | 2 | 2 | 0 | 1 | 2.10.1.2.2.1 | Data Sheets For Main HVAC Equipment - BK15 | BK-BK15-PEDCO-110-HV-DT-0001 | BK-BK15-PEDCO-110-HV-DT-0001 | BK | BK15 | PEDCO | 110 | HV | DT | 0001 | F0Z-708360 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 2 | 3 | 0 | 0 | 2.10.1.2.3 | Drawing/Diagram
2 | 10 | 1 | 2 | 3 | 0 | 1 | 2.10.1.2.3.1 | HVAC System Layout For Switchgear Building - BK15 | BK-BK15-PEDCO-110-HV-PY-0001 | BK-BK15-PEDCO-110-HV-PY-0001 | BK | BK15 | PEDCO | 110 | HV | PY | 0001 | F4B-708361 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 2 | 3 | 0 | 2 | 2.10.1.2.3.2 | HVAC System Layout For Security Building - BK15 | BK-BK15-PEDCO-110-HV-PY-0002 | BK-BK15-PEDCO-110-HV-PY-0002 | BK | BK15 | PEDCO | 110 | HV | PY | 0002 | F4B-708362 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 2 | 3 | 0 | 3 | 2.10.1.2.3.3 | Plumbing & Sewage Piping Layout For Switchgear Building - BK15 | BK-BK15-PEDCO-110-HV-PY-0003 | BK-BK15-PEDCO-110-HV-PY-0003 | BK | BK15 | PEDCO | 110 | HV | PY | 0003 | F4B-708363 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 2 | 3 | 0 | 4 | 2.10.1.2.3.4 | Plumbing & Sewage Piping Layout For Security Building - BK15 | BK-BK15-PEDCO-110-HV-PY-0004 | BK-BK15-PEDCO-110-HV-PY-0004 | BK | BK15 | PEDCO | 110 | HV | PY | 0004 | F4B-708364 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 2 | 4 | 0 | 0 | 2.10.1.2.4 | MTO
2 | 10 | 1 | 2 | 4 | 0 | 1 | 2.10.1.2.4.1 | MTO For Building HVAC & Plumbing Systems - BK15 | BK-BK15-PEDCO-110-HV-MT-0001 | BK-BK15-PEDCO-110-HV-MT-0001 | BK | BK15 | PEDCO | 110 | HV | MT | 0001 | F8Z-708365 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 3 | 0 | 0 | 0 | 2.10.1.3 | Piping
2 | 10 | 1 | 3 | 1 | 0 | 0 | 2.10.1.3.1 | MTO
2 | 10 | 1 | 3 | 1 | 0 | 1 | 2.10.1.3.1.1 | MTO For Pipes - BK15 | BK-BK15-PEDCO-110-PI-MT-0001 | BK-BK15-PEDCO-110-PI-MT-0001 | BK | BK15 | PEDCO | 110 | PI | MT | 0001 | F8Z-708366 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 4 | 0 | 0 | 0 | 2.10.1.4 | Electrical
2 | 10 | 1 | 4 | 1 | 0 | 0 | 2.10.1.4.1 | MTO
2 | 10 | 1 | 4 | 1 | 0 | 1 | 2.10.1.4.1.1 | MTO For Transmission Over Head Line - BK15 | BK-BK15-PEDCO-110-EL-MT-0001 | BK-BK15-PEDCO-110-EL-MT-0001 | BK | BK15 | PEDCO | 110 | EL | MT | 0001 | F8Z-708367 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 4 | 1 | 0 | 2 | 2.10.1.4.1.2 | MTO For Lighting & Small Powers - BK15 | BK-BK15-PEDCO-110-EL-MT-0002 | BK-BK15-PEDCO-110-EL-MT-0002 | BK | BK15 | PEDCO | 110 | EL | MT | 0002 | F8Z-708368 | IFI | IFI | 2022-06-01 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-18 | 2022-05-18 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04483 | 2022-05-29 | 1401/03/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 |  |  |  | BK-SUR-ENG-ELE-01-04483 | 2022-05-29 | 1401/03/09 | CM-C2
2 | 10 | 1 | 4 | 1 | 0 | 3 | 2.10.1.4.1.3 | MTO For Power & Control Cables - BK15 | BK-BK15-PEDCO-110-EL-MT-0003 | BK-BK15-PEDCO-110-EL-MT-0003 | BK | BK15 | PEDCO | 110 | EL | MT | 0003 | F8Z-708369 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 4 | 1 | 0 | 4 | 2.10.1.4.1.4 | MTO For Tray/Ladder and Accessories - BK15 | BK-BK15-PEDCO-110-EL-MT-0004 | BK-BK15-PEDCO-110-EL-MT-0004 | BK | BK15 | PEDCO | 110 | EL | MT | 0004 | F8Z-708370 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 4 | 1 | 0 | 5 | 2.10.1.4.1.5 | MTO For Electrical Bulk Items - BK15 | BK-BK15-PEDCO-110-EL-MT-0005 | BK-BK15-PEDCO-110-EL-MT-0005 | BK | BK15 | PEDCO | 110 | EL | MT | 0005 | F8Z-708371 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 4 | 1 | 0 | 6 | 2.10.1.4.1.6 | MTO For Earthing & Lightning Systems - BK15 | BK-BK15-PEDCO-110-EL-MT-0006 | BK-BK15-PEDCO-110-EL-MT-0006 | BK | BK15 | PEDCO | 110 | EL | MT | 0006 | F8Z-708372 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 5 | 0 | 0 | 0 | 2.10.1.5 | Architecture
2 | 10 | 1 | 5 | 1 | 0 | 0 | 2.10.1.5.1 | Drawing/Diagram
2 | 10 | 1 | 5 | 1 | 0 | 1 | 2.10.1.5.1.1 | Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-15 | BK-BK15-PEDCO-110-AR-DW-0001 | BK-BK15-PEDCO-110-AR-DW-0001 | BK | BK15 | PEDCO | 110 | AR | DW | 0001 | F4B-708373 | AFC | IFC | 2022-05-15 | 2022-05-09 | 2022-05-16 | -6 | 7 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-01 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | [13 empty] | 1401-2294-55003 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | CM
2 | 10 | 1 | 5 | 1 | 0 | 2 | 2.10.1.5.1.2 | Architectural Drawing For Switchgear Building of Well Pads - BK-15 | BK-BK15-PEDCO-110-AR-DW-0002 | BK-BK15-PEDCO-110-AR-DW-0002 | BK | BK15 | PEDCO | 110 | AR | DW | 0002 | F4B-708374 | AFC | IFC | 2022-03-23 | 2022-03-15 | 2022-03-25 | -8 | 10 | 2 | IFC | 2022-06-01 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-18 | 0 |  | D01 | IFC | T-0974 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04416 | 2022-05-24 | 1401/03/03 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-AR-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK15-PEDCO-110-AR-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0707 | 2022-03-09 | 1400/12/18 |  |  |  | RE BK-SUR-ENG-ARC-00-03551 | 2022-03-14 | 1400/12/23 | CM | [6 empty] | 1400-2294-450549 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | RJ | [10 empty] | D01 | IFC | T-0974 | 2022-05-18 | 1401/02/28 |  |  |  | BK-SUR-ENG-ARC-01-04416 | 2022-05-24 | 1401/03/03 | CM-C2 | PEDCO-CRS-BK-BK15-PEDCO-110-AR-DW-0002_D00 | [11 empty] | NISOC-CRS-BK-BK15-PEDCO-110-AR-DW-0002_D00
2 | 10 | 1 | 5 | 1 | 0 | 3 | 2.10.1.5.1.3 | Architectural Drawing For Security Building of Well Pads - BK-15 | BK-BK15-PEDCO-110-AR-DW-0003 | BK-BK15-PEDCO-110-AR-DW-0003 | BK | BK15 | PEDCO | 110 | AR | DW | 0003 | F4B-708375 | AFC | IFC | 2022-05-15 | 2022-05-14 | 2022-05-16 | -1 | 2 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04190 | 2022-05-10 | 1401/02/20 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 2022-05-16 | 1401/02/26 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04190 | 2022-05-10 | 1401/02/20 | CM-C2 | [6 empty] | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 2022-05-16 | 1401/02/26 | RJ
2 | 10 | 1 | 5 | 2 | 0 | 0 | 2.10.1.5.2 | MTO
2 | 10 | 1 | 5 | 2 | 0 | 1 | 2.10.1.5.2.1 | MTO For Architectural Works - BK15 | BK-BK15-PEDCO-110-AR-MT-0001 | BK-BK15-PEDCO-110-AR-MT-0001 | BK | BK15 | PEDCO | 110 | AR | MT | 0001 | F8Z-708376 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 6 | 0 | 0 | 0 | 2.10.1.6 | Civil
2 | 10 | 1 | 6 | 1 | 0 | 0 | 2.10.1.6.1 | Drawing/Diagram
2 | 10 | 1 | 6 | 1 | 0 | 1 | 2.10.1.6.1.1 | Civil and Structural drawings - BK15 | BK-BK15-PEDCO-110-CV-DW-0001 | BK-BK15-PEDCO-110-CV-DW-0001 | BK | BK15 | PEDCO | 110 | CV | DW | 0001 | F4S-708377 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 6 | 1 | 0 | 2 | 2.10.1.6.1.2 | General Civil Layout - BK15 | BK-BK15-PEDCO-110-CV-PY-0001 | BK-BK15-PEDCO-110-CV-PY-0001 | BK | BK15 | PEDCO | 110 | CV | PY | 0001 | F4A-708378 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 6 | 1 | 0 | 3 | 2.10.1.6.1.3 | Rough Grading Plans -BK15 | BK-BK15-PEDCO-110-CV-PY-0003 | BK-BK15-PEDCO-110-CV-PY-0003 | BK | BK15 | PEDCO | 110 | CV | PY | 0003 | F4S-708379 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 6 | 2 | 0 | 0 | 2.10.1.6.2 | Report
2 | 10 | 1 | 6 | 2 | 0 | 1 | 2.10.1.6.2.1 | Site Visit Report (Civil Work) - BK15 | BK-BK15-PEDCO-110-CV-RT-0001 | BK-BK15-PEDCO-110-CV-RT-0001 | BK | BK15 | PEDCO | 110 | CV | RT | 0001 | F0Z-708380 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 6 | 3 | 0 | 0 | 2.10.1.6.3 | MTO
2 | 10 | 1 | 6 | 3 | 0 | 1 | 2.10.1.6.3.1 | MTO For Civil Works - BK15 | BK-BK15-PEDCO-110-CV-MT-0001 | BK-BK15-PEDCO-110-CV-MT-0001 | BK | BK15 | PEDCO | 110 | CV | MT | 0001 | F8Z-708381 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 7 | 0 | 0 | 0 | 2.10.1.7 | Structure
2 | 10 | 1 | 7 | 1 | 0 | 0 | 2.10.1.7.1 | Drawing/Diagram
2 | 10 | 1 | 7 | 1 | 0 | 1 | 2.10.1.7.1.1 | Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0001 | BK-BK15-PEDCO-110-ST-DW-0001 | BK | BK15 | PEDCO | 110 | ST | DW | 0001 | F4G-708382 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 7 | 1 | 0 | 2 | 2.10.1.7.1.2 | Foundation Drawing For Security Building For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0002 | BK-BK15-PEDCO-110-ST-DW-0002 | BK | BK15 | PEDCO | 110 | ST | DW | 0002 | F4Q-708383 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 7 | 1 | 0 | 3 | 2.10.1.7.1.3 | Structural Drawing For Security Building For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0003 | BK-BK15-PEDCO-110-ST-DW-0003 | BK | BK15 | PEDCO | 110 | ST | DW | 0003 | F4M-708384 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 7 | 1 | 0 | 4 | 2.10.1.7.1.4 | Foundation Drawing For Switchgear Building For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0004 | BK-BK15-PEDCO-110-ST-DW-0004 | BK | BK15 | PEDCO | 110 | ST | DW | 0004 | F4Q-708385 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 7 | 1 | 0 | 5 | 2.10.1.7.1.5 | Structural Drawing For Switchgear Building For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0005 | BK-BK15-PEDCO-110-ST-DW-0005 | BK | BK15 | PEDCO | 110 | ST | DW | 0005 | F4M-708386 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 7 | 1 | 0 | 6 | 2.10.1.7.1.6 | Foundation Drawing For Potable Water Tank For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0006 | BK-BK15-PEDCO-110-ST-DW-0006 | BK | BK15 | PEDCO | 110 | ST | DW | 0006 | F4Q-708387 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 7 | 1 | 0 | 7 | 2.10.1.7.1.7 | Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0007 | BK-BK15-PEDCO-110-ST-DW-0007 | BK | BK15 | PEDCO | 110 | ST | DW | 0007 | F4Q-708388 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 7 | 1 | 0 | 8 | 2.10.1.7.1.8 | Structural Drawing For Diesel Generator Shelter For Well Pads - BK-15 | BK-BK15-PEDCO-110-ST-DW-0008 | BK-BK15-PEDCO-110-ST-DW-0008 | BK | BK15 | PEDCO | 110 | ST | DW | 0008 | F4M-708389 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 7 | 2 | 0 | 0 | 2.10.1.7.2 | MTO
2 | 10 | 1 | 7 | 2 | 0 | 1 | 2.10.1.7.2.1 | MTO For Structural Works - BK15 | BK-BK15-PEDCO-110-ST-MT-0001 | BK-BK15-PEDCO-110-ST-MT-0001 | BK | BK15 | PEDCO | 110 | ST | MT | 0001 | F8Z-708390 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 8 | 0 | 0 | 0 | 2.10.1.8 | Survey (Topography) & Geotechnic
2 | 10 | 1 | 8 | 0 | 1 | 0 | 2.10.1.1 | Report
2 | 10 | 1 | 8 | 0 | 1 | 1 | 2.10.1.8.1.1 | Geotechnical Investigation Report - BK15 | BK-BK15-PEDCO-110-GT-RT-0001 | BK-BK15-PEDCO-110-GT-RT-0001 | BK | BK15 | PEDCO | 110 | GT | RT | 0001 | F0Z-708391 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 1 | 8 | 0 | 2 | 0 | 2.10.1.2 | Drawing/Diagram
2 | 10 | 1 | 8 | 0 | 2 | 1 | 2.10.1.8.2.1 | Over Head Line Plan and Profile - BK15 | BK-BK15-PEDCO-110-SU-DW-0001 | BK-BK15-PEDCO-110-SU-DW-0001 | BK | BK15 | PEDCO | 110 | SU | DW | 0001 | F4P-708392 | AFC | IFC | 44711 | 0 | 0 | -44711 | 0 | -44711 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-16 | 0 |  | D00 | IFC | T-0962 | 2022-05-16 | 1401/02/26 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04476 | 2022-05-29 | 1401/03/08 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0962 | 2022-05-16 | 1401/02/26 |  |  |  | BK-SUR-ENG-ELE-01-04476 | 2022-05-29 | 1401/03/08 | CM-C3
2 | 10 | 2 | 0 | 0 | 0 | 0 | 2.10.2 | Procurement Engineering
2 | 10 | 2 | 1 | 0 | 0 | 0 | 2.10.2.1 | Piping
2 | 10 | 2 | 1 | 1 | 0 | 0 | 2.10.2.1.1 | Pipe
2 | 10 | 2 | 1 | 1 | 1 | 0 | 2.10.1.1.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 1 | 1 | 1 | 1 | 2.10.2.1.1.1.1 | PMR For Pipes - BK15 | BK-BK15-PEDCO-110-PI-MR-0001 | BK-BK15-PEDCO-110-PI-MR-0001 | BK | BK15 | PEDCO | 110 | PI | MR | 0001 | F0Z-708393 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 1 | 1 | 2 | 0 | 2.10.1.1.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 1 | 1 | 2 | 1 | 2.10.2.1.1.2.1 | TBE For Pipes - BK15 | BK-BK15-PEDCO-110-PI-TB-0001 | BK-BK15-PEDCO-110-PI-TB-0001 | BK | BK15 | PEDCO | 110 | PI | TB | 0001 | F0Z-708394 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 1 | 2 | 0 | 0 | 2.10.2.1.2 | Pipe Support
2 | 10 | 2 | 1 | 2 | 1 | 0 | 2.10.1.2.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 1 | 2 | 1 | 1 | 2.10.2.1.2.1.1 | PMR For Pipe Support - BK15 | BK-BK15-PEDCO-110-PI-MR-0002 | BK-BK15-PEDCO-110-PI-MR-0002 | BK | BK15 | PEDCO | 110 | PI | MR | 0002 | F0Z-708395 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 1 | 2 | 2 | 0 | 2.10.1.2.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 1 | 2 | 2 | 1 | 2.10.2.1.2.2.1 | TBE For Pipe Support - BK15 | BK-BK15-PEDCO-110-PI-TB-0002 | BK-BK15-PEDCO-110-PI-TB-0002 | BK | BK15 | PEDCO | 110 | PI | TB | 0002 | F0Z-708396 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 2 | 0 | 0 | 0 | 2.10.2.2 | HVAC
2 | 10 | 2 | 2 | 1 | 0 | 0 | 2.10.2.2.1 | Main HVAC Equipment
2 | 10 | 2 | 2 | 1 | 1 | 0 | 2.10.2.1.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 2 | 1 | 1 | 1 | 2.10.2.2.1.1.1 | PMR For Main HVAC Equipment - BK15 | BK-BK15-PEDCO-110-HV-MR-0001 | BK-BK15-PEDCO-110-HV-MR-0001 | BK | BK15 | PEDCO | 110 | HV | MR | 0001 | F0Z-708397 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 2 | 1 | 2 | 0 | 2.10.2.1.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 2 | 1 | 2 | 1 | 2.10.2.2.1.2.1 | TBE For Main HVAC Equipment - BK15 | BK-BK15-PEDCO-110-HV-TB-0001 | BK-BK15-PEDCO-110-HV-TB-0001 | BK | BK15 | PEDCO | 110 | HV | TB | 0001 | F0Z-708398 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 0 | 0 | 0 | 2.10.2.3 | Electrical
2 | 10 | 2 | 3 | 1 | 0 | 0 | 2.10.2.3.1 | Transformers
2 | 10 | 2 | 3 | 1 | 1 | 0 | 2.10.3.1.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 1 | 1 | 1 | 2.10.2.3.1.1.1 | PMR For Transformers - BK15 | BK-BK15-PEDCO-110-EL-MR-0001 | BK-BK15-PEDCO-110-EL-MR-0001 | BK | BK15 | PEDCO | 110 | EL | MR | 0001 | F0Z-708399 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 1 | 2 | 0 | 2.10.3.1.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 1 | 2 | 1 | 2.10.2.3.1.2.1 | TBE For Transformers - BK15 | BK-BK15-PEDCO-110-EL-TB-0001 | BK-BK15-PEDCO-110-EL-TB-0001 | BK | BK15 | PEDCO | 110 | EL | TB | 0001 | F0Z-708400 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 2 | 0 | 0 | 2.10.2.3.2 | LV Switchgear & MCC
2 | 10 | 2 | 3 | 2 | 1 | 0 | 2.10.3.2.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 2 | 1 | 1 | 2.10.2.3.2.1.1 | PMR For LV Switchgear & MCC - BK15 | BK-BK15-PEDCO-110-EL-MR-0002 | BK-BK15-PEDCO-110-EL-MR-0002 | BK | BK15 | PEDCO | 110 | EL | MR | 0002 | F0Z-708401 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 2 | 2 | 0 | 2.10.3.2.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 2 | 2 | 1 | 2.10.2.3.2.2.1 | TBE For LV Switchgear & MCC - BK15 | BK-BK15-PEDCO-110-EL-TB-0002 | BK-BK15-PEDCO-110-EL-TB-0002 | BK | BK15 | PEDCO | 110 | EL | TB | 0002 | F0Z-708402 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 3 | 0 | 0 | 2.10.2.3.3 | Emergency Diesel Generator
2 | 10 | 2 | 3 | 3 | 1 | 0 | 2.10.3.3.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 3 | 1 | 1 | 2.10.2.3.3.1.1 | PMR For Emergency Diesel Generator - BK15 | BK-BK15-PEDCO-110-EL-MR-0003 | BK-BK15-PEDCO-110-EL-MR-0003 | BK | BK15 | PEDCO | 110 | EL | MR | 0003 | F0Z-708403 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 3 | 2 | 0 | 2.10.3.3.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 3 | 2 | 1 | 2.10.2.3.3.2.1 | TBE For Emergency Diesel Generator - BK15 | BK-BK15-PEDCO-110-EL-TB-0003 | BK-BK15-PEDCO-110-EL-TB-0003 | BK | BK15 | PEDCO | 110 | EL | TB | 0003 | F0Z-708404 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 4 | 0 | 0 | 2.10.2.3.4 | UPS System
2 | 10 | 2 | 3 | 4 | 1 | 0 | 2.10.3.4.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 4 | 1 | 1 | 2.10.2.3.4.1.1 | PMR For UPS System - BK15 | BK-BK15-PEDCO-110-EL-MR-0004 | BK-BK15-PEDCO-110-EL-MR-0004 | BK | BK15 | PEDCO | 110 | EL | MR | 0004 | F0Z-708405 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 4 | 2 | 0 | 2.10.3.4.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 4 | 2 | 1 | 2.10.2.3.4.2.1 | TBE For UPS System - BK15 | BK-BK15-PEDCO-110-EL-TB-0004 | BK-BK15-PEDCO-110-EL-TB-0004 | BK | BK15 | PEDCO | 110 | EL | TB | 0004 | F0Z-708406 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 5 | 0 | 0 | 2.10.2.3.5 | DC Charger
2 | 10 | 2 | 3 | 5 | 1 | 0 | 2.10.3.5.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 5 | 1 | 1 | 2.10.2.3.5.1.1 | PMR For DC Charger - BK15 | BK-BK15-PEDCO-110-EL-MR-0005 | BK-BK15-PEDCO-110-EL-MR-0005 | BK | BK15 | PEDCO | 110 | EL | MR | 0005 | F0Z-708407 | IFI | IFI | 44692 | 44709 | 44710 | 17 | 1 | 18 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-27 | 2022-04-27 |  | D00 | IFI | T-0866 | 2022-04-27 | 1401/02/07 | T-0866 | 2022-04-27 | 1401/02/7 | BK-SUR-ENG-ELE-01-04213 | 2022-05-10 | 1401/02/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-78862 | 2022-05-28 | 1401/03/08 | 2022-05-29 | 1401/03/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0866 | 2022-04-27 | 1401/02/07 | T-0866 | 2022-04-27 | 1401/02/7 | BK-SUR-ENG-ELE-01-04213 | 2022-05-10 | 1401/02/20 | CM-C3 | [6 empty] | 1401-2294-78862 | 2022-05-28 | 1401/03/08 | 2022-05-29 | 1401/03/09 | CM
2 | 10 | 2 | 3 | 5 | 2 | 0 | 2.10.3.5.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 5 | 2 | 1 | 2.10.2.3.5.2.1 | TBE For DC Charger - BK15 | BK-BK15-PEDCO-110-EL-TB-0005 | BK-BK15-PEDCO-110-EL-TB-0005 | BK | BK15 | PEDCO | 110 | EL | TB | 0005 | F0Z-708408 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 6 | 0 | 0 | 2.10.2.3.6 | Capacitor Bank
2 | 10 | 2 | 3 | 6 | 1 | 0 | 2.10.3.6.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 6 | 1 | 1 | 2.10.2.3.6.1.1 | PMR For Capacitor Bank - BK15 | BK-BK15-PEDCO-110-EL-MR-0006 | BK-BK15-PEDCO-110-EL-MR-0006 | BK | BK15 | PEDCO | 110 | EL | MR | 0006 | F0Z-708409 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 6 | 2 | 0 | 2.10.3.6.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 6 | 2 | 1 | 2.10.2.3.6.2.1 | TBE For Capacitor Bank - BK15 | BK-BK15-PEDCO-110-EL-TB-0006 | BK-BK15-PEDCO-110-EL-TB-0006 | BK | BK15 | PEDCO | 110 | EL | TB | 0006 | F0Z-708410 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 7 | 0 | 0 | 2.10.2.3.7 | Lighting & Distribution Main Panels
2 | 10 | 2 | 3 | 7 | 1 | 0 | 2.10.3.7.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 7 | 1 | 1 | 2.10.2.3.7.1.1 | PMR For Lighting & Distribution Main Panels - BK15 | BK-BK15-PEDCO-110-EL-MR-0007 | BK-BK15-PEDCO-110-EL-MR-0007 | BK | BK15 | PEDCO | 110 | EL | MR | 0007 | F0Z-708411 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 7 | 2 | 0 | 2.10.3.7.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 7 | 2 | 1 | 2.10.2.3.7.2.1 | TBE For Lighting & Distribution Main Panels - BK15 | BK-BK15-PEDCO-110-EL-TB-0007 | BK-BK15-PEDCO-110-EL-TB-0007 | BK | BK15 | PEDCO | 110 | EL | TB | 0007 | F0Z-708412 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 8 | 0 | 0 | 2.10.2.3.8 | Earthing & Lightning System
2 | 10 | 2 | 3 | 8 | 1 | 0 | 2.10.3.8.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 8 | 1 | 1 | 2.10.2.3.8.1.1 | PMR For Earthing & Lightning System - BK15 | BK-BK15-PEDCO-110-EL-MR-0008 | BK-BK15-PEDCO-110-EL-MR-0008 | BK | BK15 | PEDCO | 110 | EL | MR | 0008 | F0Z-708413 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 8 | 2 | 0 | 2.10.3.8.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 8 | 2 | 1 | 2.10.2.3.8.2.1 | TBE For Earthing & Lightning System - BK15 | BK-BK15-PEDCO-110-EL-TB-0008 | BK-BK15-PEDCO-110-EL-TB-0008 | BK | BK15 | PEDCO | 110 | EL | TB | 0008 | F0Z-708414 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 9 | 0 | 0 | 2.10.2.3.9 | Lighting and Small Power Equipment
2 | 10 | 2 | 3 | 9 | 1 | 0 | 2.10.3.9.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 9 | 1 | 1 | 2.10.2.3.9.1.1 | PMR For Lighting and Small Power Equipment - BK15 | BK-BK15-PEDCO-110-EL-MR-0009 | BK-BK15-PEDCO-110-EL-MR-0009 | BK | BK15 | PEDCO | 110 | EL | MR | 0009 | F0Z-708415 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 9 | 2 | 0 | 2.10.3.9.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 9 | 2 | 1 | 2.10.2.3.9.2.1 | TBE For Lighting and Small Power Equipment - BK15 | BK-BK15-PEDCO-110-EL-TB-0009 | BK-BK15-PEDCO-110-EL-TB-0009 | BK | BK15 | PEDCO | 110 | EL | TB | 0009 | F0Z-708416 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 10 | 0 | 0 | 2.10.2.3.10 | Tray/Ladder and Accessories
2 | 10 | 2 | 3 | 10 | 1 | 0 | 2.10.3.10.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 10 | 1 | 1 | 2.10.2.3.10.1.1 | PMR For Tray/Ladder and Accessories - BK15 | BK-BK15-PEDCO-110-EL-MR-0010 | BK-BK15-PEDCO-110-EL-MR-0010 | BK | BK15 | PEDCO | 110 | EL | MR | 0010 | F0Z-708417 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 10 | 2 | 0 | 2.10.3.10.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 10 | 2 | 1 | 2.10.2.3.10.2.1 | TBE For Tray/Ladder and Accessories - BK15 | BK-BK15-PEDCO-110-EL-TB-0010 | BK-BK15-PEDCO-110-EL-TB-0010 | BK | BK15 | PEDCO | 110 | EL | TB | 0010 | F0Z-708418 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 11 | 0 | 0 | 2.10.2.3.11 | Power & Control Cables
2 | 10 | 2 | 3 | 11 | 1 | 0 | 2.10.3.11.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 11 | 1 | 1 | 2.10.2.3.11.1.1 | PMR For Power & Control Cables - BK15 | BK-BK15-PEDCO-110-EL-MR-0011 | BK-BK15-PEDCO-110-EL-MR-0011 | BK | BK15 | PEDCO | 110 | EL | MR | 0011 | F0Z-708419 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 11 | 2 | 0 | 2.10.3.11.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 11 | 2 | 1 | 2.10.2.3.11.2.1 | TBE For Power & Control Cables - BK15 | BK-BK15-PEDCO-110-EL-TB-0011 | BK-BK15-PEDCO-110-EL-TB-0011 | BK | BK15 | PEDCO | 110 | EL | TB | 0011 | F0Z-708420 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 12 | 0 | 0 | 2.10.2.3.12 | Electrical Bulk Items
2 | 10 | 2 | 3 | 12 | 1 | 0 | 2.10.3.12.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 12 | 1 | 1 | 2.10.2.3.12.1.1 | PMR For Electrical Bulk Items - BK15 | BK-BK15-PEDCO-110-EL-MR-0012 | BK-BK15-PEDCO-110-EL-MR-0012 | BK | BK15 | PEDCO | 110 | EL | MR | 0012 | F0Z-708421 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 12 | 2 | 0 | 2.10.3.12.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 12 | 2 | 1 | 2.10.2.3.12.2.1 | TBE For Electrical Bulk Items - BK15 | BK-BK15-PEDCO-110-EL-TB-0012 | BK-BK15-PEDCO-110-EL-TB-0012 | BK | BK15 | PEDCO | 110 | EL | TB | 0012 | F0Z-708422 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 13 | 0 | 0 | 2.10.2.3.13 | Transmission Over head Line
2 | 10 | 2 | 3 | 13 | 1 | 0 | 2.10.3.13.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 3 | 13 | 1 | 1 | 2.10.2.3.13.1.1 | PMR For Transmission Over head Line - BK15 | BK-BK15-PEDCO-110-EL-MR-0013 | BK-BK15-PEDCO-110-EL-MR-0013 | BK | BK15 | PEDCO | 110 | EL | MR | 0013 | F0Z-708423 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 3 | 13 | 2 | 0 | 2.10.3.13.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 3 | 13 | 2 | 1 | 2.10.2.3.13.2.1 | TBE For Transmission Over head Line - BK15 | BK-BK15-PEDCO-110-EL-TB-0013 | BK-BK15-PEDCO-110-EL-TB-0013 | BK | BK15 | PEDCO | 110 | EL | TB | 0013 | F0Z-708424 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 4 | 0 | 0 | 0 | 2.10.2.4 | Structure
2 | 10 | 2 | 4 | 1 | 0 | 0 | 2.10.2.4.1 | Steel Structure Items
2 | 10 | 2 | 4 | 1 | 1 | 0 | 2.10.4.1.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 4 | 1 | 1 | 1 | 2.10.2.4.1.1.1 | PMR For Steel Structure Items - BK15 | BK-BK15-PEDCO-110-ST-MR-0001 | BK-BK15-PEDCO-110-ST-MR-0001 | BK | BK15 | PEDCO | 110 | ST | MR | 0001 | F0Z-708425 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 4 | 1 | 2 | 0 | 2.10.4.1.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 4 | 1 | 2 | 1 | 2.10.2.4.1.2.1 | TBE For Steel Structure Items - BK15 | BK-BK15-PEDCO-110-ST-TB-0001 | BK-BK15-PEDCO-110-ST-TB-0001 | BK | BK15 | PEDCO | 110 | ST | TB | 0001 | F0Z-708426 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 4 | 2 | 0 | 0 | 2.10.2.4.2 | Anchor Bolts
2 | 10 | 2 | 4 | 2 | 1 | 0 | 2.10.4.2.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 4 | 2 | 1 | 1 | 2.10.2.4.2.1.1 | PMR For Anchor Bolts - BK15 | BK-BK15-PEDCO-110-ST-MR-0002 | BK-BK15-PEDCO-110-ST-MR-0002 | BK | BK15 | PEDCO | 110 | ST | MR | 0002 | F0Z-708427 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 4 | 2 | 2 | 0 | 2.10.4.2.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 4 | 2 | 2 | 1 | 2.10.2.4.2.2.1 | TBE For Anchor Bolts - BK15 | BK-BK15-PEDCO-110-ST-TB-0002 | BK-BK15-PEDCO-110-ST-TB-0002 | BK | BK15 | PEDCO | 110 | ST | TB | 0002 | F0Z-708428 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 4 | 3 | 0 | 0 | 2.10.2.4.3 | Blast Proof Doors
2 | 10 | 2 | 4 | 3 | 1 | 0 | 2.10.4.3.1 | Purchase Material Requisition (PMR)
2 | 10 | 2 | 4 | 3 | 1 | 1 | 2.10.2.4.3.1.1 | PMR For Blast Proof Doors - BK15 | BK-BK15-PEDCO-110-ST-MR-0003 | BK-BK15-PEDCO-110-ST-MR-0003 | BK | BK15 | PEDCO | 110 | ST | MR | 0003 | F0Z-708429 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 2 | 4 | 3 | 2 | 0 | 2.10.4.3.2 | Technical Bid Evaluation (TBE)
2 | 10 | 2 | 4 | 3 | 2 | 1 | 2.10.2.4.3.2.1 | TBE For Blast Proof Doors - BK15 | BK-BK15-PEDCO-110-ST-TB-0003 | BK-BK15-PEDCO-110-ST-TB-0003 | BK | BK15 | PEDCO | 110 | ST | TB | 0003 | F0Z-708430 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 3 | 0 | 0 | 0 | 0 | 2.10.3 | Commissioning Engineering
2 | 10 | 3 | 0 | 0 | 1 | 0 | 2.10.3.1 | Procedure/Plan
2 | 10 | 3 | 0 | 0 | 1 | 1 | 2.10.3.1 | Pre-Commissioning, Commissioning & Startup Procedure - BK15 | BK-BK15-PEDCO-110-CO-PR-0001 | BK-BK15-PEDCO-110-CO-PR-0001 | BK | BK15 | PEDCO | 110 | CO | PR | 0001 | F0Z-708431 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 4 | 0 | 0 | 0 | 0 | 2.10.4 | Field Engineering
2 | 10 | 4 | 0 | 0 | 1 | 0 | 2.10.4.1 | Query
2 | 10 | 4 | 0 | 0 | 1 | 1 | 2.10.4.1 | Technical/Site Queries | BK-BK15-PEDCO-110-GE-TQ-0001 | BK-BK15-PEDCO-110-GE-TQ-0001 | BK | BK15 | PEDCO | 110 | GE | TQ | 0001 | F7Z-708432 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 4 | 0 | 0 | 2 | 0 | 2.10.4.2 | Dossier
2 | 10 | 4 | 0 | 0 | 2 | 1 | 2.10.4.2 | As-Built Document Booklets - BK15 | BK-BK15-PEDCO-110-GE-DO-0001 | BK-BK15-PEDCO-110-GE-DO-0001 | BK | BK15 | PEDCO | 110 | GE | DO | 0001 | F0Z-708433 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 5 | 0 | 0 | 0 | 0 | 2.10.5 | Engineering Final Documentation
2 | 10 | 5 | 0 | 0 | 1 | 0 | 2.10.5.1 | Manual
2 | 10 | 5 | 0 | 0 | 1 | 1 | 2.10.5.1 | Operating Manual - BK15 | BK-BK15-PEDCO-110-GE-ML-0001 | BK-BK15-PEDCO-110-GE-ML-0001 | BK | BK15 | PEDCO | 110 | GE | ML | 0001 | F0Z-708434 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 10 | 5 | 0 | 0 | 2 | 0 | 2.10.5.2 | Dossier
2 | 10 | 5 | 0 | 0 | 2 | 1 | 2.10 | As-Built Document Booklets - BK15 | BK-BK15-PEDCO-110-GE-DO-0001 | BK-BK15-PEDCO-110-GE-DO-0001 | [7 empty] | F0Z-708433 | [43 empty] | Moved to Field | 0
2 | 10 | 5 | 0 | 0 | 2 | 2 | 2.10 | Final Engineering Dossier - BK15 | BK-BK15-PEDCO-110-GE-DO-0002 | BK-BK15-PEDCO-110-GE-DO-0002 | BK | BK15 | PEDCO | 110 | GE | DO | 0002 | F0Z-708435 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 0 | 0 | 0 | 0 | 0 | 2.11 | Package 10-Workover # 05
2 | 11 | 1 | 0 | 0 | 0 | 0 | 2.11.1 | Detail Design
2 | 11 | 1 | 1 | 0 | 0 | 0 | 2.11.1.1 | Process
2 | 11 | 1 | 1 | 1 | 0 | 0 | 2.11.1.1.1 | Drawing/Diagram
2 | 11 | 1 | 1 | 1 | 0 | 1 | 2.11.1.1.1 | P&ID for Diesel Oil Drum- BK05 | BK-BK05-PEDCO-110-PR-PI-0001 | BK-BK05-PEDCO-110-PR-PI-0001 | BK | BK05 | PEDCO | 110 | PR | PI | 0001 | F2A-708436 | AFC | IFC | 2021-11-29 | 2021-12-01 | 2021-12-06 | 2 | 5 | 7 | IFA | 2022-01-17 | 2022-02-06 | 2022-02-08 | 20 | 2 | 22 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 2022-05-12 | 2022-05-16 | 18 | 4 | 22 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 0 |  | D03 | IFA | T-0795 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03986 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59474 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 2021-11-30 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0422 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02776 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D00 | [5 empty] | 1400-2294-399153 | 2022-02-06 | 1400/11/17 | 2022-02-08 | 1400/11/19 | AP | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0648 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03589 | 2022-03-15 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D01 | [5 empty] | 1400-2294-443282 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/24 | RJ | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D01 | [9 empty] | D03 | IFA | T-0795 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03986 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D02 | [5 empty] | 1401-2294-59474 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0001_D02
2 | 11 | 1 | 1 | 1 | 0 | 2 | 2.11.1.1.1 | P&ID for Potable Water Tank - BK05 | BK-BK05-PEDCO-110-PR-PI-0002 | BK-BK05-PEDCO-110-PR-PI-0002 | BK | BK05 | PEDCO | 110 | PR | PI | 0002 | F2A-708437 | AFC | IFC | 2021-11-29 | 2021-12-01 | 2021-12-06 | 2 | 5 | 7 | IFA | 2022-01-17 | 2022-02-06 | 2022-02-08 | 20 | 2 | 22 | IFA | 2022-03-13 | 2022-03-10 | 2022-03-14 | -3 | 4 | 1 | IFA | 2022-04-24 | 2022-05-12 | 2022-05-16 | 18 | 4 | 22 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-15 | 0 |  | D03 | IFA | T-0795 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03986 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59474 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0241 | 2021-11-15 | 1400/08/24 |  |  |  | BK-SUR-ENG-PCS-00-02159 | 2021-11-30 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-300708 | 2021-12-01 | 1400/09/10 | 2021-12-06 | 1400/09/15 | CM | [10 empty] | D01 | IFA | T-0422 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02776 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D00 | [5 empty] | 1400-2294-399153 | 2022-02-06 | 1400/11/17 | 2022-02-08 | 1400/11/19 | AP | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D00 | [9 empty] | D02 | IFA | T-0648 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03589 | 2022-03-15 | 1400/12/24 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D01 | [5 empty] | 1400-2294-443282 | 2022-03-10 | 1400/12/19 | 2022-03-14 | 1400/12/24 | RJ | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D01 | [9 empty] | D03 | IFA | T-0795 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03986 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D02 | [5 empty] | 1401-2294-59474 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-BK05-PEDCO-110-PR-PI-0002_D02
2 | 11 | 1 | 1 | 2 | 0 | 0 | 2.11.1.1.2 | List
2 | 11 | 1 | 1 | 2 | 0 | 1 | 2.11.1.1.2 | Line List - BK05 | BK-BK05-PEDCO-110-PR-LI-0001 | BK-BK05-PEDCO-110-PR-LI-0001 | BK | BK05 | PEDCO | 110 | PR | LI | 0001 | F0Z-708438 | AFC | IFC | 44633 | 44632 | 44635 | -1 | 3 | 2 | IFA | 44695 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-27 | 0 |  | D01 | IFA | T-0877 | 2022-04-30 | 1401/02/10 | T-0877 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 2022-05-23 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK05-PEDCO-110-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0650 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-PCS-00-03597 | 2022-03-15 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445283 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0877 | 2022-04-30 | 1401/02/10 | T-0877 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04382 | 2022-05-23 | 1401/03/02 | CM-C2 | PEDCO-CRS-BK-BK05-PEDCO-110-PR-LI-0001_D00 | [11 empty] | NISOC-CRS-BK-BK05-PEDCO-110-PR-LI-0001_D00
2 | 11 | 1 | 1 | 3 | 0 | 0 | 2.11.1.1.3 | Data Sheet
2 | 11 | 1 | 1 | 3 | 0 | 1 | 2.11.1.1 | Process Data Sheets For Instrument Devices - BK05 | BK-BK05-PEDCO-110-PR-DT-0001 | BK-BK05-PEDCO-110-PR-DT-0001 | BK | BK05 | PEDCO | 110 | PR | DT | 0001 | F0Z-708439 | AFC | IFC | 44677 | 44695 | 44697 | 18 | 2 | 20 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-12 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03991 | 2022-04-19 | 1401/01/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 2022-05-16 | 1401/02/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 |  |  |  | BK-SUR-ENG-PCS-01-03991 | 2022-04-19 | 1401/01/30 | CM-C2 | [6 empty] | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 2022-05-16 | 1401/02/26 | AP
2 | 11 | 1 | 2 | 0 | 0 | 0 | 2.11.1.2 | HVAC/Plumbing
2 | 11 | 1 | 2 | 1 | 0 | 0 | 2.11.1.2.1 | Calculation
2 | 11 | 1 | 2 | 1 | 0 | 1 | 2.11.1.2.1 | HVAC Calculation Note For Switchgear Building - BK05 | BK-BK05-PEDCO-110-HV-CN-0001 | BK-BK05-PEDCO-110-HV-CN-0001 | BK | BK05 | PEDCO | 110 | HV | CN | 0001 | F0Z-708440 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 2 | 1 | 0 | 2 | 2.11.1.2.1 | HVAC Calculation Note For Security Building - BK05 | BK-BK05-PEDCO-110-HV-CN-0002 | BK-BK05-PEDCO-110-HV-CN-0002 | BK | BK05 | PEDCO | 110 | HV | CN | 0002 | F0Z-708441 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 2 | 2 | 0 | 0 | 2.11.1.2.2 | Data Sheets
2 | 11 | 1 | 2 | 2 | 0 | 1 | 2.11.1.2.2 | Data Sheets For Main HVAC Equipment - BK05 | BK-BK05-PEDCO-110-HV-DT-0001 | BK-BK05-PEDCO-110-HV-DT-0001 | BK | BK05 | PEDCO | 110 | HV | DT | 0001 | F0Z-708442 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 2 | 3 | 0 | 0 | 2.11.1.2.3 | Drawing/Diagram
2 | 11 | 1 | 2 | 3 | 0 | 1 | 2.11.1.2.3 | HVAC System Layout For Switchgear Building - BK05 | BK-BK05-PEDCO-110-HV-PY-0001 | BK-BK05-PEDCO-110-HV-PY-0001 | BK | BK05 | PEDCO | 110 | HV | PY | 0001 | F4B-708443 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 2 | 3 | 0 | 2 | 2.11.1.2.3 | HVAC System Layout For Security Building - BK05 | BK-BK05-PEDCO-110-HV-PY-0002 | BK-BK05-PEDCO-110-HV-PY-0002 | BK | BK05 | PEDCO | 110 | HV | PY | 0002 | F4B-708444 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 2 | 3 | 0 | 3 | 2.11.1.2.3 | Plumbing & Sewage Piping Layout For Switchgear Building - BK05 | BK-BK05-PEDCO-110-HV-PY-0003 | BK-BK05-PEDCO-110-HV-PY-0003 | BK | BK05 | PEDCO | 110 | HV | PY | 0003 | F4B-708445 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 2 | 3 | 0 | 4 | 2.11.1.2.3 | Plumbing & Sewage Piping Layout For Security Building - BK05 | BK-BK05-PEDCO-110-HV-PY-0004 | BK-BK05-PEDCO-110-HV-PY-0004 | BK | BK05 | PEDCO | 110 | HV | PY | 0004 | F4B-708446 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 2 | 4 | 0 | 0 | 2.11.1.2.4 | MTO
2 | 11 | 1 | 2 | 4 | 0 | 1 | 2.11.1.2 | MTO For Building HVAC & Plumbing Systems - BK05 | BK-BK05-PEDCO-110-HV-MT-0001 | BK-BK05-PEDCO-110-HV-MT-0001 | BK | BK05 | PEDCO | 110 | HV | MT | 0001 | F8Z-708447 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 3 | 0 | 0 | 0 | 2.11.1.3 | Piping
2 | 11 | 1 | 3 | 1 | 0 | 0 | 2.11.1.3.1 | MTO
2 | 11 | 1 | 3 | 1 | 0 | 1 | 2.11.1.3 | MTO For Pipes - BK05 | BK-BK05-PEDCO-110-PI-MT-0001 | BK-BK05-PEDCO-110-PI-MT-0001 | BK | BK05 | PEDCO | 110 | PI | MT | 0001 | F8Z-708448 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 4 | 0 | 0 | 0 | 2.11.1.4 | Electrical
2 | 11 | 1 | 4 | 1 | 0 | 0 | 2.11.1.4.1 | MTO
2 | 11 | 1 | 4 | 1 | 0 | 1 | 2.11.1.4 | MTO For Transmission Over Head Line - BK05 | BK-BK05-PEDCO-110-EL-MT-0001 | BK-BK05-PEDCO-110-EL-MT-0001 | BK | BK05 | PEDCO | 110 | EL | MT | 0001 | F8Z-708449 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 4 | 1 | 0 | 2 | 2.11.1.4 | MTO For Lighting & Small Powers - BK05 | BK-BK05-PEDCO-110-EL-MT-0002 | BK-BK05-PEDCO-110-EL-MT-0002 | BK | BK05 | PEDCO | 110 | EL | MT | 0002 | F8Z-708450 | IFI | IFI | 2022-06-01 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-18 | 2022-05-18 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04483 | 2022-05-29 | 1401/03/09 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0969 | 2022-05-18 | 1401/02/28 |  |  |  | BK-SUR-ENG-ELE-01-04483 | 2022-05-29 | 1401/03/09 | CM-C2
2 | 11 | 1 | 4 | 1 | 0 | 3 | 2.11.1.4 | MTO For Power & Control Cables - BK05 | BK-BK05-PEDCO-110-EL-MT-0003 | BK-BK05-PEDCO-110-EL-MT-0003 | BK | BK05 | PEDCO | 110 | EL | MT | 0003 | F8Z-708451 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 4 | 1 | 0 | 4 | 2.11.1.4 | MTO For Tray/Ladder and Accessories - BK05 | BK-BK05-PEDCO-110-EL-MT-0004 | BK-BK05-PEDCO-110-EL-MT-0004 | BK | BK05 | PEDCO | 110 | EL | MT | 0004 | F8Z-708452 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 4 | 1 | 0 | 5 | 2.11.1.4 | MTO For Electrical Bulk Items - BK05 | BK-BK05-PEDCO-110-EL-MT-0005 | BK-BK05-PEDCO-110-EL-MT-0005 | BK | BK05 | PEDCO | 110 | EL | MT | 0005 | F8Z-708453 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 4 | 1 | 0 | 6 | 2.11.1.4 | MTO For Earthing & Lightning Systems - BK05 | BK-BK05-PEDCO-110-EL-MT-0006 | BK-BK05-PEDCO-110-EL-MT-0006 | BK | BK05 | PEDCO | 110 | EL | MT | 0006 | F8Z-708454 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 5 | 0 | 0 | 0 | 2.11.1.5 | Architecture
2 | 11 | 1 | 5 | 1 | 0 | 0 | 2.11.1.5.1 | Drawing/Diagram
2 | 11 | 1 | 5 | 1 | 0 | 1 | 2.11.1.5.1 | Architectural Drawing For Diesel Generator Shelter of Well Pads - BK-05 | BK-BK05-PEDCO-110-AR-DW-0001 | BK-BK05-PEDCO-110-AR-DW-0001 | BK | BK05 | PEDCO | 110 | AR | DW | 0001 | F4B-708455 | AFC | IFC | 2022-05-15 | 0 | 0 | -44696 | 0 | -44696 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-01 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0885 | 2022-05-01 | 1401/02/11
2 | 11 | 1 | 5 | 1 | 0 | 2 | 2.11.1.5.1 | Architectural Drawing For Switchgear Building of Well Pads - BK-05 | BK-BK05-PEDCO-110-AR-DW-0002 | BK-BK05-PEDCO-110-AR-DW-0002 | BK | BK05 | PEDCO | 110 | AR | DW | 0002 | F4B-708456 | AFC | IFC | 2022-03-23 | 2022-03-15 | 2022-03-25 | -8 | 10 | 2 | IFC | 2022-06-01 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-18 | 0 |  | D01 | IFC | T-0974 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-BK05-PEDCO-110-AR-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-BK05-PEDCO-110-AR-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0707 | 2022-03-09 | 1400/12/18 |  |  |  | RE BK-SUR-ENG-ARC-00-03551 | 2022-03-14 | 1400/12/23 | CM | [6 empty] | 1400-2294-450549 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | RJ | [10 empty] | D01 | IFC | T-0974 | 2022-05-18 | 1401/02/28 | [7 empty] | PEDCO-CRS-BK-BK05-PEDCO-110-AR-DW-0002_D00 | [11 empty] | NISOC-CRS-BK-BK05-PEDCO-110-AR-DW-0002_D00
2 | 11 | 1 | 5 | 1 | 0 | 3 | 2.11.1.5.1 | Architectural Drawing For Security Building of Well Pads - BK-05 | BK-BK05-PEDCO-110-AR-DW-0003 | BK-BK05-PEDCO-110-AR-DW-0003 | BK | BK05 | PEDCO | 110 | AR | DW | 0003 | F4B-708457 | AFC | IFC | 2022-05-15 | 2022-05-14 | 2022-05-16 | -1 | 2 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04190 | 2022-05-10 | 1401/02/20 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 2022-05-16 | 1401/02/26 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04190 | 2022-05-10 | 1401/02/20 | CM-C2 | [6 empty] | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 2022-05-16 | 1401/02/26 | RJ
2 | 11 | 1 | 5 | 2 | 0 | 0 | 2.11.1.5.2 | MTO
2 | 11 | 1 | 5 | 2 | 0 | 1 | 2.11.1.5 | MTO For Architectural Works - BK05 | BK-BK05-PEDCO-110-AR-MT-0001 | BK-BK05-PEDCO-110-AR-MT-0001 | BK | BK05 | PEDCO | 110 | AR | MT | 0001 | F8Z-708458 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 6 | 0 | 0 | 0 | 2.11.1.6 | Civil
2 | 11 | 1 | 6 | 1 | 0 | 0 | 2.11.1.6.1 | Drawing/Diagram
2 | 11 | 1 | 6 | 1 | 0 | 1 | 2.11.1.6.1 | Civil and Structural drawings - BK05 | BK-BK05-PEDCO-110-CV-DW-0001 | BK-BK05-PEDCO-110-CV-DW-0001 | BK | BK05 | PEDCO | 110 | CV | DW | 0001 | F4S-708459 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 6 | 1 | 0 | 2 | 2.11.1.6.1 | General Civil Layout - BK05 | BK-BK05-PEDCO-110-CV-PY-0001 | BK-BK05-PEDCO-110-CV-PY-0001 | BK | BK05 | PEDCO | 110 | CV | PY | 0001 | F4A-708460 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 6 | 1 | 0 | 3 | 2.11.1.6.1 | Rough Grading Plans -BK05 | BK-BK05-PEDCO-110-CV-PY-0003 | BK-BK05-PEDCO-110-CV-PY-0003 | BK | BK05 | PEDCO | 110 | CV | PY | 0003 | F4S-708461 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 6 | 2 | 0 | 0 | 2.11.1.6.2 | Report
2 | 11 | 1 | 6 | 2 | 0 | 1 | 2.11.1.6.2 | Site Visit Report (Civil Work) - BK05 | BK-BK05-PEDCO-110-CV-RT-0001 | BK-BK05-PEDCO-110-CV-RT-0001 | BK | BK05 | PEDCO | 110 | CV | RT | 0001 | F0Z-708462 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 6 | 3 | 0 | 0 | 2.11.1.6.3 | MTO
2 | 11 | 1 | 6 | 3 | 0 | 1 | 2.11.1.6 | MTO For Civil Works - BK05 | BK-BK05-PEDCO-110-CV-MT-0001 | BK-BK05-PEDCO-110-CV-MT-0001 | BK | BK05 | PEDCO | 110 | CV | MT | 0001 | F8Z-708463 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 7 | 0 | 0 | 0 | 2.11.1.7 | Structure
2 | 11 | 1 | 7 | 1 | 0 | 0 | 2.11.1.7.1 | Drawing/Diagram
2 | 11 | 1 | 7 | 1 | 0 | 1 | 2.11.1.7.1 | Fuel Oil Storage Drum Detail Drawing For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0001 | BK-BK05-PEDCO-110-ST-DW-0001 | BK | BK05 | PEDCO | 110 | ST | DW | 0001 | F4G-708464 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 7 | 1 | 0 | 2 | 2.11.1.7.1 | Foundation Drawing For Security Building For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0002 | BK-BK05-PEDCO-110-ST-DW-0002 | BK | BK05 | PEDCO | 110 | ST | DW | 0002 | F4Q-708465 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 7 | 1 | 0 | 3 | 2.11.1.7.1 | Structural Drawing For Security Building For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0003 | BK-BK05-PEDCO-110-ST-DW-0003 | BK | BK05 | PEDCO | 110 | ST | DW | 0003 | F4M-708466 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 7 | 1 | 0 | 4 | 2.11.1.7.1 | Foundation Drawing For Switchgear Building For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0004 | BK-BK05-PEDCO-110-ST-DW-0004 | BK | BK05 | PEDCO | 110 | ST | DW | 0004 | F4Q-708467 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 7 | 1 | 0 | 5 | 2.11.1.7.1 | Structural Drawing For Switchgear Building For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0005 | BK-BK05-PEDCO-110-ST-DW-0005 | BK | BK05 | PEDCO | 110 | ST | DW | 0005 | F4M-708468 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 7 | 1 | 0 | 6 | 2.11.1.7.1 | Foundation Drawing For Potable Water Tank For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0006 | BK-BK05-PEDCO-110-ST-DW-0006 | BK | BK05 | PEDCO | 110 | ST | DW | 0006 | F4Q-708469 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 7 | 1 | 0 | 7 | 2.11.1.7.1 | Foundation Drawing For Diesel Generator Shelter For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0007 | BK-BK05-PEDCO-110-ST-DW-0007 | BK | BK05 | PEDCO | 110 | ST | DW | 0007 | F4Q-708470 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 7 | 1 | 0 | 8 | 2.11.1.7.1 | Structural Drawing For Diesel Generator Shelter For Well Pads - BK-05 | BK-BK05-PEDCO-110-ST-DW-0008 | BK-BK05-PEDCO-110-ST-DW-0008 | BK | BK05 | PEDCO | 110 | ST | DW | 0008 | F4M-708471 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 7 | 2 | 0 | 0 | 2.11.1.7.2 | MTO
2 | 11 | 1 | 7 | 2 | 0 | 1 | 2.11.1.7 | MTO For Structural Works - BK05 | BK-BK05-PEDCO-110-ST-MT-0001 | BK-BK05-PEDCO-110-ST-MT-0001 | BK | BK05 | PEDCO | 110 | ST | MT | 0001 | F8Z-708472 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 8 | 0 | 0 | 0 | 2.11.1.8 | Geotechnic
2 | 11 | 1 | 8 | 1 | 0 | 0 | 2.11.1.8.1 | Report
2 | 11 | 1 | 8 | 1 | 0 | 1 | 2.11.1.8.1 | Geotechnical Investigation Report - BK05 | BK-BK05-PEDCO-110-GT-RT-0001 | BK-BK05-PEDCO-110-GT-RT-0001 | BK | BK05 | PEDCO | 110 | GT | RT | 0001 | F0Z-708473 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 1 | 8 | 2 | 0 | 0 | 2.11.1.8.2 | Drawing/Diagram
2 | 11 | 1 | 8 | 2 | 0 | 1 | 2.11.1 | Over Head Line Plan and Profile - BK05 | BK-BK05-PEDCO-110-SU-DW-0001 | BK-BK05-PEDCO-110-SU-DW-0001 | BK | BK05 | PEDCO | 110 | SU | DW | 0001 | F4P-708474 | AFC | IFC | 44713 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-18 | 0 |  | D00 | IFC | T-0971 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04486 | 2022-05-29 | 1401/03/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0971 | 2022-05-18 | 1401/02/28 |  |  |  | BK-SUR-ENG-ELE-01-04486 | 2022-05-29 | 1401/03/09 | CM-C3
2 | 11 | 2 | 0 | 0 | 0 | 0 | 2.11.2 | Procurement Engineering
2 | 11 | 2 | 1 | 0 | 0 | 0 | 2.11.2.1 | Piping
2 | 11 | 2 | 1 | 1 | 0 | 0 | 2.11.2.1.1 | Pipe
2 | 11 | 2 | 1 | 1 | 1 | 0 | 2.11.1.1.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 1 | 1 | 1 | 1 | 2.11.2.1.1.1.1 | PMR For Pipes - BK05 | BK-BK05-PEDCO-110-PI-MR-0001 | BK-BK05-PEDCO-110-PI-MR-0001 | BK | BK05 | PEDCO | 110 | PI | MR | 0001 | F0Z-708475 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 1 | 1 | 2 | 0 | 2.11.1.1.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 1 | 1 | 2 | 1 | 2.11.2.1.1.2.1 | TBE For Pipes - BK05 | BK-BK05-PEDCO-110-PI-TB-0001 | BK-BK05-PEDCO-110-PI-TB-0001 | BK | BK05 | PEDCO | 110 | PI | TB | 0001 | F0Z-708476 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 1 | 2 | 0 | 0 | 2.11.2.1.2 | Pipe Support
2 | 11 | 2 | 1 | 2 | 1 | 0 | 2.11.1.2.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 1 | 2 | 1 | 1 | 2.11.2.1.2.1.1 | PMR For Pipe Support - BK05 | BK-BK05-PEDCO-110-PI-MR-0002 | BK-BK05-PEDCO-110-PI-MR-0002 | BK | BK05 | PEDCO | 110 | PI | MR | 0002 | F0Z-708477 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 1 | 2 | 2 | 0 | 2.11.1.2.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 1 | 2 | 2 | 1 | 2.11.2.1.2.2.1 | TBE For Pipe Support - BK05 | BK-BK05-PEDCO-110-PI-TB-0002 | BK-BK05-PEDCO-110-PI-TB-0002 | BK | BK05 | PEDCO | 110 | PI | TB | 0002 | F0Z-708478 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 2 | 0 | 0 | 0 | 2.11.2.2 | HVAC
2 | 11 | 2 | 2 | 1 | 0 | 0 | 2.11.2.2.1 | Main HVAC Equipment
2 | 11 | 2 | 2 | 1 | 1 | 0 | 2.11.2.1.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 2 | 1 | 1 | 1 | 2.11.2.2.1.1.1 | PMR For Main HVAC Equipment - BK05 | BK-BK05-PEDCO-110-HV-MR-0001 | BK-BK05-PEDCO-110-HV-MR-0001 | BK | BK05 | PEDCO | 110 | HV | MR | 0001 | F0Z-708479 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 2 | 1 | 2 | 0 | 2.11.2.1.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 2 | 1 | 2 | 1 | 2.11.2.2.1.2.1 | TBE For Main HVAC Equipment - BK05 | BK-BK05-PEDCO-110-HV-TB-0001 | BK-BK05-PEDCO-110-HV-TB-0001 | BK | BK05 | PEDCO | 110 | HV | TB | 0001 | F0Z-708480 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 0 | 0 | 0 | 2.11.2.3 | Electrical
2 | 11 | 2 | 3 | 1 | 0 | 0 | 2.11.2.3.1 | Transformers
2 | 11 | 2 | 3 | 1 | 1 | 0 | 2.11.3.1.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 1 | 1 | 1 | 2.11.2.3.1.1.1 | PMR For Transformers - BK05 | BK-BK05-PEDCO-110-EL-MR-0001 | BK-BK05-PEDCO-110-EL-MR-0001 | BK | BK05 | PEDCO | 110 | EL | MR | 0001 | F0Z-708481 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 1 | 2 | 0 | 2.11.3.1.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 1 | 2 | 1 | 2.11.2.3.1.2.1 | TBE For Transformers - BK05 | BK-BK05-PEDCO-110-EL-TB-0001 | BK-BK05-PEDCO-110-EL-TB-0001 | BK | BK05 | PEDCO | 110 | EL | TB | 0001 | F0Z-708482 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 2 | 0 | 0 | 2.11.2.3.2 | LV Switchgear & MCC
2 | 11 | 2 | 3 | 2 | 1 | 0 | 2.11.3.2.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 2 | 1 | 1 | 2.11.2.3.2.1.1 | PMR For LV Switchgear & MCC - BK05 | BK-BK05-PEDCO-110-EL-MR-0002 | BK-BK05-PEDCO-110-EL-MR-0002 | BK | BK05 | PEDCO | 110 | EL | MR | 0002 | F0Z-708483 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 2 | 2 | 0 | 2.11.3.2.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 2 | 2 | 1 | 2.11.2.3.2.2.1 | TBE For LV Switchgear & MCC - BK05 | BK-BK05-PEDCO-110-EL-TB-0002 | BK-BK05-PEDCO-110-EL-TB-0002 | BK | BK05 | PEDCO | 110 | EL | TB | 0002 | F0Z-708484 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 3 | 0 | 0 | 2.11.2.3.3 | Emergency Diesel Generator
2 | 11 | 2 | 3 | 3 | 1 | 0 | 2.11.3.3.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 3 | 1 | 1 | 2.11.2.3.3.1.1 | PMR For Emergency Diesel Generator - BK05 | BK-BK05-PEDCO-110-EL-MR-0003 | BK-BK05-PEDCO-110-EL-MR-0003 | BK | BK05 | PEDCO | 110 | EL | MR | 0003 | F0Z-708485 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 3 | 2 | 0 | 2.11.3.3.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 3 | 2 | 1 | 2.11.2.3.3.2.1 | TBE For Emergency Diesel Generator - BK05 | BK-BK05-PEDCO-110-EL-TB-0003 | BK-BK05-PEDCO-110-EL-TB-0003 | BK | BK05 | PEDCO | 110 | EL | TB | 0003 | F0Z-708486 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 4 | 0 | 0 | 2.11.2.3.4 | UPS System
2 | 11 | 2 | 3 | 4 | 1 | 0 | 2.11.3.4.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 4 | 1 | 1 | 2.11.2.3.4.1.1 | PMR For UPS System - BK05 | BK-BK05-PEDCO-110-EL-MR-0004 | BK-BK05-PEDCO-110-EL-MR-0004 | BK | BK05 | PEDCO | 110 | EL | MR | 0004 | F0Z-708487 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 4 | 2 | 0 | 2.11.3.4.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 4 | 2 | 1 | 2.11.2.3.4.2.1 | TBE For UPS System - BK05 | BK-BK05-PEDCO-110-EL-TB-0004 | BK-BK05-PEDCO-110-EL-TB-0004 | BK | BK05 | PEDCO | 110 | EL | TB | 0004 | F0Z-708488 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 5 | 0 | 0 | 2.11.2.3.5 | DC Charger
2 | 11 | 2 | 3 | 5 | 1 | 0 | 2.11.3.5.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 5 | 1 | 1 | 2.11.2.3.5.1.1 | PMR For DC Charger - BK05 | BK-BK05-PEDCO-110-EL-MR-0005 | BK-BK05-PEDCO-110-EL-MR-0005 | BK | BK05 | PEDCO | 110 | EL | MR | 0005 | F0Z-708489 | IFI | IFI | 44692 | 44709 | 44710 | 17 | 1 | 18 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-27 | 2022-04-27 |  | D00 | IFI | T-0866 | 2022-04-27 | 1401/02/07 | T-0866 | 2022-04-27 | 1401/02/7 | BK-SUR-ENG-ELE-01-04213 | 2022-05-10 | 1401/02/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-78862 | 2022-05-28 | 1401/03/08 | 2022-05-29 | 1401/03/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0866 | 2022-04-27 | 1401/02/07 | T-0866 | 2022-04-27 | 1401/02/7 | BK-SUR-ENG-ELE-01-04213 | 2022-05-10 | 1401/02/20 | CM-C3 | [6 empty] | 1401-2294-78862 | 2022-05-28 | 1401/03/08 | 2022-05-29 | 1401/03/09 | CM
2 | 11 | 2 | 3 | 5 | 2 | 0 | 2.11.3.5.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 5 | 2 | 1 | 2.11.2.3.5.2.1 | TBE For DC Charger - BK05 | BK-BK05-PEDCO-110-EL-TB-0005 | BK-BK05-PEDCO-110-EL-TB-0005 | BK | BK05 | PEDCO | 110 | EL | TB | 0005 | F0Z-708490 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 6 | 0 | 0 | 2.11.2.3.6 | Capacitor Bank
2 | 11 | 2 | 3 | 6 | 1 | 0 | 2.11.3.6.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 6 | 1 | 1 | 2.11.2.3.6.1.1 | PMR For Capacitor Bank - BK05 | BK-BK05-PEDCO-110-EL-MR-0006 | BK-BK05-PEDCO-110-EL-MR-0006 | BK | BK05 | PEDCO | 110 | EL | MR | 0006 | F0Z-708491 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 6 | 2 | 0 | 2.11.3.6.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 6 | 2 | 1 | 2.11.2.3.6.2.1 | TBE For Capacitor Bank - BK05 | BK-BK05-PEDCO-110-EL-TB-0006 | BK-BK05-PEDCO-110-EL-TB-0006 | BK | BK05 | PEDCO | 110 | EL | TB | 0006 | F0Z-708492 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 7 | 0 | 0 | 2.11.2.3.7 | Lighting & Distribution Main Panels
2 | 11 | 2 | 3 | 7 | 1 | 0 | 2.11.3.7.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 7 | 1 | 1 | 2.11.2.3.7.1.1 | PMR For Lighting & Distribution Main Panels - BK05 | BK-BK05-PEDCO-110-EL-MR-0007 | BK-BK05-PEDCO-110-EL-MR-0007 | BK | BK05 | PEDCO | 110 | EL | MR | 0007 | F0Z-708493 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 7 | 2 | 0 | 2.11.3.7.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 7 | 2 | 1 | 2.11.2.3.7.2.1 | TBE For Lighting & Distribution Main Panels - BK05 | BK-BK05-PEDCO-110-EL-TB-0007 | BK-BK05-PEDCO-110-EL-TB-0007 | BK | BK05 | PEDCO | 110 | EL | TB | 0007 | F0Z-708494 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 8 | 0 | 0 | 2.11.2.3.8 | Earthing & Lightning System
2 | 11 | 2 | 3 | 8 | 1 | 0 | 2.11.3.8.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 8 | 1 | 1 | 2.11.2.3.8.1.1 | PMR For Earthing & Lightning System - BK05 | BK-BK05-PEDCO-110-EL-MR-0008 | BK-BK05-PEDCO-110-EL-MR-0008 | BK | BK05 | PEDCO | 110 | EL | MR | 0008 | F0Z-708495 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 8 | 2 | 0 | 2.11.3.8.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 8 | 2 | 1 | 2.11.2.3.8.2.1 | TBE For Earthing & Lightning System - BK05 | BK-BK05-PEDCO-110-EL-TB-0008 | BK-BK05-PEDCO-110-EL-TB-0008 | BK | BK05 | PEDCO | 110 | EL | TB | 0008 | F0Z-708496 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 9 | 0 | 0 | 2.11.2.3.9 | Lighting and Small Power Equipment
2 | 11 | 2 | 3 | 9 | 1 | 0 | 2.11.3.9.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 9 | 1 | 1 | 2.11.2.3.9.1.1 | PMR For Lighting and Small Power Equipment - BK05 | BK-BK05-PEDCO-110-EL-MR-0009 | BK-BK05-PEDCO-110-EL-MR-0009 | BK | BK05 | PEDCO | 110 | EL | MR | 0009 | F0Z-708497 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 9 | 2 | 0 | 2.11.3.9.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 9 | 2 | 1 | 2.11.2.3.9.2.1 | TBE For Lighting and Small Power Equipment - BK05 | BK-BK05-PEDCO-110-EL-TB-0009 | BK-BK05-PEDCO-110-EL-TB-0009 | BK | BK05 | PEDCO | 110 | EL | TB | 0009 | F0Z-708498 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 10 | 0 | 0 | 2.11.2.3.10 | Tray/Ladder and Accessories
2 | 11 | 2 | 3 | 10 | 1 | 0 | 2.11.3.10.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 10 | 1 | 1 | 2.11.2.3.10.1.1 | PMR For Tray/Ladder and Accessories - BK05 | BK-BK05-PEDCO-110-EL-MR-0010 | BK-BK05-PEDCO-110-EL-MR-0010 | BK | BK05 | PEDCO | 110 | EL | MR | 0010 | F0Z-708499 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 10 | 2 | 0 | 2.11.3.10.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 10 | 2 | 1 | 2.11.2.3.10.2.1 | TBE For Tray/Ladder and Accessories - BK05 | BK-BK05-PEDCO-110-EL-TB-0010 | BK-BK05-PEDCO-110-EL-TB-0010 | BK | BK05 | PEDCO | 110 | EL | TB | 0010 | F0Z-708500 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 11 | 0 | 0 | 2.11.2.3.11 | Power & Control Cables
2 | 11 | 2 | 3 | 11 | 1 | 0 | 2.11.3.11.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 11 | 1 | 1 | 2.11.2.3.11.1.1 | PMR For Power & Control Cables - BK05 | BK-BK05-PEDCO-110-EL-MR-0011 | BK-BK05-PEDCO-110-EL-MR-0011 | BK | BK05 | PEDCO | 110 | EL | MR | 0011 | F0Z-708501 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 11 | 2 | 0 | 2.11.3.11.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 11 | 2 | 1 | 2.11.2.3.11.2.1 | TBE For Power & Control Cables - BK05 | BK-BK05-PEDCO-110-EL-TB-0011 | BK-BK05-PEDCO-110-EL-TB-0011 | BK | BK05 | PEDCO | 110 | EL | TB | 0011 | F0Z-708502 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 12 | 0 | 0 | 2.11.2.3.12 | Electrical Bulk Items
2 | 11 | 2 | 3 | 12 | 1 | 0 | 2.11.3.12.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 12 | 1 | 1 | 2.11.2.3.12.1.1 | PMR For Electrical Bulk Items - BK05 | BK-BK05-PEDCO-110-EL-MR-0012 | BK-BK05-PEDCO-110-EL-MR-0012 | BK | BK05 | PEDCO | 110 | EL | MR | 0012 | F0Z-708503 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 12 | 2 | 0 | 2.11.3.12.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 12 | 2 | 1 | 2.11.2.3.12.2.1 | TBE For Electrical Bulk Items - BK05 | BK-BK05-PEDCO-110-EL-TB-0012 | BK-BK05-PEDCO-110-EL-TB-0012 | BK | BK05 | PEDCO | 110 | EL | TB | 0012 | F0Z-708504 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 13 | 0 | 0 | 2.11.2.3.13 | Transmission Over head Line
2 | 11 | 2 | 3 | 13 | 1 | 0 | 2.11.3.13.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 3 | 13 | 1 | 1 | 2.11.2.3.13.1.1 | PMR For Transmission Over head Line - BK05 | BK-BK05-PEDCO-110-EL-MR-0013 | BK-BK05-PEDCO-110-EL-MR-0013 | BK | BK05 | PEDCO | 110 | EL | MR | 0013 | F0Z-708505 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 3 | 13 | 2 | 0 | 2.11.3.13.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 3 | 13 | 2 | 1 | 2.11.2.3.13.2.1 | TBE For Transmission Over head Line - BK05 | BK-BK05-PEDCO-110-EL-TB-0013 | BK-BK05-PEDCO-110-EL-TB-0013 | BK | BK05 | PEDCO | 110 | EL | TB | 0013 | F0Z-708506 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 4 | 0 | 0 | 0 | 2.11.2.4 | Structure
2 | 11 | 2 | 4 | 1 | 0 | 0 | 2.11.2.4.1 | Steel Structure Items
2 | 11 | 2 | 4 | 1 | 1 | 0 | 2.11.4.1.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 4 | 1 | 1 | 1 | 2.11.2.4.1.1.1 | PMR For Steel Structure Items - BK05 | BK-BK05-PEDCO-110-ST-MR-0001 | BK-BK05-PEDCO-110-ST-MR-0001 | BK | BK05 | PEDCO | 110 | ST | MR | 0001 | F0Z-708507 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 4 | 1 | 2 | 0 | 2.11.4.1.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 4 | 1 | 2 | 1 | 2.11.2.4.1.2.1 | TBE For Steel Structure Items - BK05 | BK-BK05-PEDCO-110-ST-TB-0001 | BK-BK05-PEDCO-110-ST-TB-0001 | BK | BK05 | PEDCO | 110 | ST | TB | 0001 | F0Z-708508 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 4 | 2 | 0 | 0 | 2.11.2.4.2 | Anchor Bolts
2 | 11 | 2 | 4 | 2 | 1 | 0 | 2.11.4.2.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 4 | 2 | 1 | 1 | 2.11.2.4.2.1.1 | PMR For Anchor Bolts - BK05 | BK-BK05-PEDCO-110-ST-MR-0002 | BK-BK05-PEDCO-110-ST-MR-0002 | BK | BK05 | PEDCO | 110 | ST | MR | 0002 | F0Z-708509 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 4 | 2 | 2 | 0 | 2.11.4.2.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 4 | 2 | 2 | 1 | 2.11.2.4.2.2.1 | TBE For Anchor Bolts - BK05 | BK-BK05-PEDCO-110-ST-TB-0002 | BK-BK05-PEDCO-110-ST-TB-0002 | BK | BK05 | PEDCO | 110 | ST | TB | 0002 | F0Z-708510 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 4 | 3 | 0 | 0 | 2.11.2.4.3 | Blast Proof Doors
2 | 11 | 2 | 4 | 3 | 1 | 0 | 2.11.4.3.1 | Purchase Material Requisition (PMR)
2 | 11 | 2 | 4 | 3 | 1 | 1 | 2.11.2.4.3.1.1 | PMR For Blast Proof Doors - BK05 | BK-BK05-PEDCO-110-ST-MR-0003 | BK-BK05-PEDCO-110-ST-MR-0003 | BK | BK05 | PEDCO | 110 | ST | MR | 0003 | F0Z-708511 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 2 | 4 | 3 | 2 | 0 | 2.11.4.3.2 | Technical Bid Evaluation (TBE)
2 | 11 | 2 | 4 | 3 | 2 | 1 | 2.11.2.4.3.2.1 | TBE For Blast Proof Doors - BK05 | BK-BK05-PEDCO-110-ST-TB-0003 | BK-BK05-PEDCO-110-ST-TB-0003 | BK | BK05 | PEDCO | 110 | ST | TB | 0003 | F0Z-708512 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 3 | 0 | 0 | 0 | 0 | 2.11.3 | Commissioning Engineering
2 | 11 | 3 | 0 | 0 | 1 | 0 | 2.11.3.1 | Procedure/Plan
2 | 11 | 3 | 0 | 0 | 1 | 1 | 2.11.3.1 | Pre-Commissioning, Commissioning & Startup Procedure - BK05 | BK-BK05-PEDCO-110-CO-PR-0001 | BK-BK05-PEDCO-110-CO-PR-0001 | BK | BK05 | PEDCO | 110 | CO | PR | 0001 | F0Z-708513 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 4 | 0 | 0 | 0 | 0 | 2.11.4 | Field Engineering
2 | 11 | 4 | 0 | 0 | 1 | 0 | 2.11.4.1 | Query
2 | 11 | 4 | 0 | 0 | 1 | 1 | 2.11.4.1 | Technical/Site Queries | BK-BK05-PEDCO-110-GE-TQ-0001 | BK-BK05-PEDCO-110-GE-TQ-0001 | BK | BK05 | PEDCO | 110 | GE | TQ | 0001 | F7Z-708514 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 4 | 0 | 0 | 2 | 0 | 2.11.4.2 | Dossier
2 | 11 | 4 | 0 | 0 | 2 | 1 | 2.11.4.2 | As-Built Document Booklets - BK05 | BK-BK05-PEDCO-110-GE-DO-0001 | BK-BK05-PEDCO-110-GE-DO-0001 | BK | BK05 | PEDCO | 110 | GE | DO | 0001 | F0Z-708515 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 5 | 0 | 0 | 0 | 0 | 2.11.5 | Engineering Final Documentation
2 | 11 | 5 | 0 | 0 | 1 | 0 | 2.11.5.1 | Manual
2 | 11 | 5 | 0 | 0 | 1 | 1 | 2.11.5.1 | Operating Manual - BK05 | BK-BK05-PEDCO-110-GE-ML-0001 | BK-BK05-PEDCO-110-GE-ML-0001 | BK | BK05 | PEDCO | 110 | GE | ML | 0001 | F0Z-708516 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 5 | 0 | 0 | 2 | 0 | 2.11.5.2 | Dossier
2 | 11 | 5 | 0 | 0 | 2 | 1 | 2.11.5.2 | As-Built Document Booklets - BK05 | BK-BK05-PEDCO-110-GE-DO-0001 | BK-BK05-PEDCO-110-GE-DO-0001 | BK | BK05 | PEDCO | 110 | GE | DO | 0001 | F0Z-708515 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
2 | 11 | 5 | 0 | 0 | 2 | 2 | 2.11.5.2 | Final Engineering Dossier - BK05 | BK-BK05-PEDCO-110-GE-DO-0002 | BK-BK05-PEDCO-110-GE-DO-0002 | BK | BK05 | PEDCO | 110 | GE | DO | 0002 | F0Z-708517 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | SURFACE DEVELOPMENT
3 | 1 | 0 | 0 | 0 | 0 | 0 | 3.1 | Package 11- EPC Pipeline 8" & 4"
3 | 1 | 1 | 0 | 0 | 0 | 0 | 3.1.1 | Basic Design Endorsement
3 | 1 | 1 | 0 | 0 | 0 | 1 | 3.1.1.1 | Endorsement Report For Basic Design & Scope of Work | BK-PPL-PEDCO-320-GE-RT-0001 | BK-PPL-PEDCO-320-GE-RT-0001 | [7 empty] | - | [43 empty] | Deleted | 2021-07-31 | 0 |  | B00 | IFC | T-0023 | 2021-07-31 | 1400/05/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-176098 | 2021-08-28 | 1400/06/06 | 2021-09-07 | 1400/06/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | B00-Reject |  | B00 | IFC | T-0023 | 2021-07-31 | 1400/05/09 | [13 empty] | 1400-2294-176098 | 2021-08-28 | 1400/06/06 | 2021-09-07 | 1400/06/16 | CM | [8 empty] | B00-Reject
3 | 1 | 2 | 0 | 0 | 0 | 0 | 3.1.2 | Value Engineering
3 | 1 | 2 | 0 | 0 | 0 | 1 | 3.1.2.1 | Value Engineering Study Report | BK-PPL-PEDCO-320-GE-RT-0002 | BK-PPL-PEDCO-320-GE-RT-0002 | BK | PPL | PEDCO | 320 | GE | RT | 0002 | F0Z-708518 | AFD | IFC | 2022-02-15 | 2022-03-10 | 2022-03-15 | 23 | 5 | 28 | IFA | 2022-04-24 | 2022-05-21 | 2022-05-23 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-01 | 0 |  | D01 | IFA | T-0785 | 2022-04-10 | 1400/01/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-PPL-PEDCO-320-GE-RT-0002-D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-68426 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-PPL-PEDCO-320-GE-RT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0531 | 2022-02-01 | 1400/11/12 |  |  |  | BK-SUR-ENG-PCS-00-03282 | 2022-03-02 | 1400/12/11 | CM-C2 | [6 empty] | 1400-2294-443284 | 2022-03-10 | 1400/12/19 | 2022-03-15 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0785 | 2022-04-10 | 1400/01/21 | [7 empty] | PEDCO-CRS-BK-PPL-PEDCO-320-GE-RT-0002-D00 | [5 empty] | 1401-2294-68426 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-PPL-PEDCO-320-GE-RT-0002_D00
3 | 1 | 2 | 0 | 0 | 0 | 2 | 3.1.2.2 | HAZID Report For Pipeline | BK-PPL-PEDCO-320-GE-RT-0003 | BK-PPL-PEDCO-320-GE-RT-0003 | BK | PPL | PEDCO | 320 | GE | RT | 0003 | F0Z-708519 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 2 | 0 | 0 | 0 | 3 | 3.1.2.3 | HAZOP Report For Pipeline | BK-PPL-PEDCO-320-GE-RT-0004 | BK-PPL-PEDCO-320-GE-RT-0004 | BK | PPL | PEDCO | 320 | GE | RT | 0004 | F0Z-708520 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 0 | 0 | 0 | 0 | 3.1.3 | Detail Design
3 | 1 | 3 | 1 | 0 | 0 | 0 | 3.1.3.1 | Process
3 | 1 | 3 | 1 | 0 | 1 | 0 | 3.1.3.1 | Philosophy
3 | 1 | 3 | 1 | 0 | 1 | 1 | 3.1.3.1.1.1 | Drainage Philosophy | BK-PPL-PEDCO-320-PR-PH-0001 | BK-PPL-PEDCO-320-PR-PH-0001 | BK | PPL | PEDCO | 320 | PR | PH | 0001 | F0Z-708521 | AFD | IFC | 2022-02-14 | 2022-02-26 | 2022-02-21 | 12 | -5 | 7 | IFA | 2022-04-24 | 2022-05-07 | 2022-05-18 | 13 | 11 | 24 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-31 | 0 |  | D01 | IFA | T-0798 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03987 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PH-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-49890 | 2022-05-07 | 1401/02/17 | 2022-05-18 | 14701/02/28 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PH-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0527 | 2022-01-31 | 1400/11/11 |  |  |  | BK-SUR-ENG-PCS-00-03180 | 2022-02-22 | 1400/12/03 | CM-C2 | [6 empty] | 1400-2294-419620 | 2022-02-26 | 1400/12/07 | 2022-02-21 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0798 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-PCS-01-03987 | 2022-04-19 | 1401/01/30 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PH-0004_D00 | [5 empty] | 1401-2294-49890 | 2022-05-07 | 1401/02/17 | 2022-05-18 | 14701/02/28 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PH-0001_D00
3 | 1 | 3 | 1 | 0 | 1 | 2 | 3.1.3.1.1.2 | Control Philosophy | BK-PPL-PEDCO-320-PR-PH-0002 | BK-PPL-PEDCO-320-PR-PH-0002 | BK | PPL | PEDCO | 320 | PR | PH | 0002 | F0Z-708522 | AFD | IFC | 2022-05-23 | 0 | 0 | -44704 | 0 | -44704 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-09 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19
3 | 1 | 3 | 1 | 0 | 1 | 3 | 3.1.3.1.1.3 | Flare,Blow Down And Relief Philosophy | BK-PPL-PEDCO-320-PR-PH-0003 | BK-PPL-PEDCO-320-PR-PH-0003 | BK | PPL | PEDCO | 320 | PR | PH | 0003 | F0Z-708523 | AFD | IFC | 2022-02-20 | 2022-03-08 | 2022-03-06 | 16 | -2 | 14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D00 | IFC | T-0555 | 2022-02-06 | 1400/11/17 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03181 | 2022-02-22 | 1400/12/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-437177 | 2022-03-08 | 1400/12/18 | 2022-03-06 | 1400/12/15 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0555 | 2022-02-06 | 1400/11/17 |  |  |  | BK-SUR-ENG-PCS-00-03181 | 2022-02-22 | 1400/12/03 | CM-C3 | [6 empty] | 1400-2294-437177 | 2022-03-08 | 1400/12/18 | 2022-03-06 | 1400/12/15 | RJ
3 | 1 | 3 | 1 | 0 | 1 | 4 | 3.1.3.1.1.4 | Isolation Philosophy | BK-PPL-PEDCO-320-PR-PH-0004 | BK-PPL-PEDCO-320-PR-PH-0004 | BK | PPL | PEDCO | 320 | PR | PH | 0004 | F0Z-708524 | AFD | IFC | 2021-12-05 | 2021-12-11 | 2021-12-14 | 6 | 3 | 9 | IFA | 2022-02-12 | 2022-03-06 | 2022-03-08 | 22 | 2 | 24 | IFA | 2022-05-09 | 0 | 0 | -44690 | 0 | -44690 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-21 | 0 |  | D02 | IFA | T-0863 | 2022-04-25 | 1401/02/06 | 0 | 0 | 0 | BK-SUR-ENG-CIV-01-04056 | 2022-04-25 | 1401/02/05 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PH-0004_D01 | BK-SUR-ENG-PCS-01-04346 | 2022-05-22 | 1401/03/01 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-PR-PH-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0262 | 2021-11-21 | 1400/08/30 |  |  |  | BK-SUR-ENG-PCS-00-02227 | 2021-12-07 | 1400/09/16 | CM-C2 | [6 empty] | 1400-2294-312238 | 2021-12-11 | 1400/09/20 | 2021-12-14 | 1400/09/23 | CM | [10 empty] | D01 | IFA | T-0520 | 2022-01-29 | 1400/11/09 |  |  |  | BK-SUR-ENG-PCS-00-03179 | 2022-02-22 | 1400/12/03 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PH-0004_D00 | [5 empty] | 1400-2294-436900 | 2022-03-06 | 1400/12/15 | 2022-03-08 | 1400/12/17 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PH-0004_D00 | [9 empty] | D02 | IFA | T-0863 | 2022-04-25 | 1401/02/06 |  |  |  | BK-SUR-ENG-CIV-01-04056 | 2022-04-25 | 1401/02/05 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PH-0004_D01 | BK-SUR-ENG-PCS-01-04346 | 2022-05-22 | 1401/03/01 | CM-C2 | [7 empty] | NISOC-CRS-BK-PPL-PEDCO-320-PR-PH-0004_D01
3 | 1 | 3 | 1 | 0 | 1 | 5 | 3.1.3.1.1.5 | ESD Philosophy | BK-PPL-PEDCO-320-PR-PH-0005 | BK-PPL-PEDCO-320-PR-PH-0005 | BK | PPL | PEDCO | 320 | PR | PH | 0005 | F0Z-708525 | AFD | IFC | 2022-05-23 | 0 | 0 | -44704 | 0 | -44704 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-09 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19
3 | 1 | 3 | 1 | 0 | 2 | 0 | 3.1.3.2 | Description
3 | 1 | 3 | 1 | 0 | 2 | 1 | 3.1.3.1.2.1 | Process Description | BK-PPL-PEDCO-320-PR-DP-0001 | BK-PPL-PEDCO-320-PR-DP-0001 | BK | PPL | PEDCO | 320 | PR | DP | 0001 | F0Z-708526 | AFD | IFC | 44625 | 44630 | 44632 | 5 | 2 | 7 | IFA | 44717 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 0 |  | D01 | IFA | T-0990 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-DP-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-PR-DP-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0607 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PCS-00-03322 | 2022-03-05 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-443237 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0990 | 2022-05-22 | 1401/03/01 | [7 empty] | PEDCO-CRS-BK-PPL-PEDCO-320-PR-DP-0001_D00 | [11 empty] | NISOC-CRS-BK-PPL-PEDCO-320-PR-DP-0001_D00
3 | 1 | 3 | 1 | 0 | 3 | 0 | 3.1.3.3 | Calculation
3 | 1 | 3 | 1 | 0 | 3 | 1 | 3.1.3.1.3.1 | Calculation Note For PSV Sizing | BK-PPL-PEDCO-320-PR-CN-0001 | BK-PPL-PEDCO-320-PR-CN-0001 | BK | PPL | PEDCO | 320 | PR | CN | 0001 | F0Z-708527 | AFD | IFC | 44625 | 44630 | 44632 | 5 | 2 | 7 | IFA | 44717 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 0 |  | D01 | IFA | T-0990 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-PR-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0607 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PCS-00-03322 | 2022-03-05 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-443237 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0990 | 2022-05-22 | 1401/03/01 | [7 empty] | PEDCO-CRS-BK-PPL-PEDCO-320-PR-CN-0001_D00 | [11 empty] | NISOC-CRS-BK-PPL-PEDCO-320-PR-CN-0001_D00
3 | 1 | 3 | 1 | 0 | 4 | 0 | 3.1.3.4 | Drawing/Diagram
3 | 1 | 3 | 1 | 0 | 4 | 1 | 3.1.3.1.4.1 | Symbol & Legend For PFD and P&ID | BK-PPL-PEDCO-320-PR-PI-0003 | BK-PPL-PEDCO-320-PR-PI-0003 | BK | PPL | PEDCO | 320 | PR | PI | 0003 | F2A-708528 | AFC | IFC | 2022-02-07 | 2022-02-12 | 2022-02-22 | 5 | 10 | 15 | IFA | 2022-03-23 | 2022-04-29 | 2022-05-01 | 37 | 2 | 39 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-24 | 0 |  | D01 | IFA | T-0713 | 2022-03-09 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03831 | 2022-04-10 | 1401/01/21 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43235 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0499 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-PCS-00-03085 | 2022-02-16 | 1400/11/27 | CM-C3 | [6 empty] | 1400-2294-407038 | 2022-02-12 | 1400/11/23 | 2022-02-22 | 1400/12/03 | CM | [10 empty] | D01 | IFA | T-0713 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03831 | 2022-04-10 | 1401/01/21 | CM-C2 | [6 empty] | 1401-2294-43235 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0003_D00
3 | 1 | 3 | 1 | 0 | 4 | 2 | 3.1.3.1.4.2 | Process Flow Diagram For pipelines | BK-PPL-PEDCO-320-PR-PF-0001 | BK-PPL-PEDCO-320-PR-PF-0001 | BK | PPL | PEDCO | 320 | PR | PF | 0001 | F2A-708529 | AFC | IFC | 2021-12-01 | 2021-12-08 | 2021-12-14 | 7 | 6 | 13 | IFA | 2022-02-08 | 2022-02-20 | 2022-02-22 | 12 | 2 | 14 | IFA | 2022-04-30 | 2022-05-12 | 2022-05-16 | 12 | 4 | 16 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-17 | 0 |  | D02 | IFA | T-0816 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04101 | 2022-05-01 | 1401/02/11 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PF-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59525 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PF-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0254 | 2021-11-17 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02171 | 2021-12-01 | 1400/09/10 | CM-C3 | [6 empty] | 1400-2294-310826 | 2021-12-08 | 1400/09/17 | 2021-12-14 | 1400/09/23 | CM | [10 empty] | D01 | IFA | T-0508 | 2022-01-25 | 1400/11/05 |  |  |  | BK-SUR-ENG-PCS-00-03124 | 2022-02-19 | 1400/11/30 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PF-0001_D00 | [5 empty] | 1400-2294-415917 | 2022-02-20 | 1400/12/01 | 2022-02-22 | 1400/12/03 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PF-0001_D00 | [9 empty] | D02 | IFA | T-0816 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PCS-01-04101 | 2022-05-01 | 1401/02/11 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PF-0001_D01 | [5 empty] | 1401-2294-59525 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PF-0001_D01
3 | 1 | 3 | 1 | 0 | 4 | 3 | 3.1.3.1.4.3 | P&ID - Gas Pipeline (to Siahmakan G.I. Station) | BK-PPL-PEDCO-320-PR-PI-0001 | BK-PPL-PEDCO-320-PR-PI-0001 | BK | PPL | PEDCO | 320 | PR | PI | 0001 | F2A-708530 | AFC | IFC | 2021-12-01 | 2021-12-08 | 2021-12-14 | 7 | 6 | 13 | IFA | 2022-02-07 | 2022-02-26 | 2022-02-20 | 19 | -6 | 13 | IFA | 2022-03-23 | 2022-04-29 | 2022-05-01 | 37 | 2 | 39 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-17 | 0 |  | D02 | IFA | T-0713 | 2022-03-09 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03831 | 2022-04-10 | 1401/01/21 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43235 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0254 | 2021-11-17 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02171 | 2021-12-01 | 1400/09/10 | CM-C3 | [6 empty] | 1400-2294-310826 | 2021-12-08 | 1400/09/17 | 2021-12-14 | 1400/09/23 | CM | [10 empty] | D01 | IFA | T-0503 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-PCS-00-03096 | 2022-02-19 | 1400/11/30 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D00 | [5 empty] | 1400-2294-416040 | 2022-02-26 | 1400/12/07 | 2022-02-20 | 1400/12/01 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D00 | [9 empty] | D02 | IFA | T-0713 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03831 | 2022-04-10 | 1401/01/21 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D01 | [5 empty] | 1401-2294-43235 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D01
3 | 1 | 3 | 1 | 0 | 4 | 4 | 3.1.3.1.4.4 | P&ID - Condensate Pipeline (to Binak PU) | BK-PPL-PEDCO-320-PR-PI-0002 | BK-PPL-PEDCO-320-PR-PI-0002 | BK | PPL | PEDCO | 320 | PR | PI | 0002 | F2A-708531 | AFC | IFC | 2021-12-01 | 2021-12-08 | 2021-12-14 | 7 | 6 | 13 | IFA | 2022-02-07 | 2022-02-26 | 2022-02-20 | 19 | -6 | 13 | IFA | 2022-03-23 | 2022-04-29 | 2022-05-01 | 37 | 2 | 39 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-17 | 0 |  | D02 | IFA | T-0713 | 2022-03-09 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03831 | 2022-04-10 | 1401/01/21 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43235 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0254 | 2021-11-17 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02171 | 2021-12-01 | 1400/09/10 | CM-C3 | [6 empty] | 1400-2294-310826 | 2021-12-08 | 1400/09/17 | 2021-12-14 | 1400/09/23 | CM | [10 empty] | D01 | IFA | T-0503 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-PCS-00-03096 | 2022-02-19 | 1400/11/30 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D00 | [5 empty] | 1400-2294-416040 | 2022-02-26 | 1400/12/07 | 2022-02-20 | 1400/12/01 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D00 | [9 empty] | D02 | IFA | T-0713 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03831 | 2022-04-10 | 1401/01/21 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D01 | [5 empty] | 1401-2294-43235 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0002_D01
3 | 1 | 3 | 1 | 0 | 4 | 5 | 3.1.3.1.4.5 | ESD Block Diagram | BK-PPL-PEDCO-320-PR-BD-0001 | BK-PPL-PEDCO-320-PR-BD-0001 | BK | PPL | PEDCO | 320 | PR | BD | 0001 | F2J-708532 | AFC | IFC | 2022-06-13 | 0 | 0 | -44725 | 0 | -44725 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-30 | 0 |  | D00 | IFC | T-1022 | 2022-05-30 | 1401/03/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1022 | 2022-05-30 | 1401/03/09
3 | 1 | 3 | 1 | 0 | 4 | 6 | 3.1.3.1.4.6 | Cause & Effect Diagram | BK-PPL-PEDCO-320-PR-CE-0001 | BK-PPL-PEDCO-320-PR-CE-0001 | BK | PPL | PEDCO | 320 | PR | CE | 0001 | F0Z-708533 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 1 | 0 | 5 | 0 | 3.1.3.5 | Report
3 | 1 | 3 | 1 | 0 | 5 | 1 | 3.1.3.1.5.1 | Pipelines Hydraulic Calculation Report | BK-PPL-PEDCO-320-PR-RT-0001 | BK-PPL-PEDCO-320-PR-RT-0001 | BK | PPL | PEDCO | 320 | PR | RT | 0001 | F0Z-708534 | AFD | IFC | 44531 | 44538 | 44544 | 7 | 6 | 13 | IFA | 44600 | 44612 | 44614 | 12 | 2 | 14 | IFA | 44681 | 44693 | 44697 | 12 | 4 | 16 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-17 | 0 |  | D02 | IFA | T-0816 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04101 | 2022-05-01 | 1401/02/11 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-RT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59525 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-RT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0254 | 2021-11-17 | 1400/08/25 |  |  |  | BK-SUR-ENG-PCS-00-02171 | 2021-12-01 | 1400/09/10 | CM-C3 | [6 empty] | 1400-2294-310826 | 2021-12-08 | 1400/09/17 | 2021-12-14 | 1400/09/23 | CM | [10 empty] | D01 | IFA | T-0508 | 2022-01-25 | 1400/11/05 |  |  |  | BK-SUR-ENG-PCS-00-03124 | 2022-02-19 | 1400/11/30 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-RT-0001_D00 | [5 empty] | 1400-2294-415917 | 2022-02-20 | 1400/12/01 | 2022-02-22 | 1400/12/03 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-RT-0001_D00 | [9 empty] | D02 | IFA | T-0816 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-PCS-01-04101 | 2022-05-01 | 1401/02/11 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-RT-0001_D01 | [5 empty] | 1401-2294-59525 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PR-RT-0001_D01
3 | 1 | 3 | 1 | 0 | 6 | 0 | 3.1.3.6 | List
3 | 1 | 3 | 1 | 0 | 6 | 1 | 3.1.3.1.6.1 | Equipment List | BK-PPL-PEDCO-320-PR-LI-0001 | BK-PPL-PEDCO-320-PR-LI-0001 | BK | PPL | PEDCO | 320 | PR | LI | 0001 | F0Z-708535 | AFC | IFC | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 0 |  | D00 | IFC | T-0607 | 2022-02-19 | 1400/11/30 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03322 | 2022-03-05 | 1400/12/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443237 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0607 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PCS-00-03322 | 2022-03-05 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-443237 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM
3 | 1 | 3 | 1 | 0 | 6 | 2 | 3.1.3.1.6.2 | Line List | BK-PPL-PEDCO-320-PR-LI-0002 | BK-PPL-PEDCO-320-PR-LI-0002 | BK | PPL | PEDCO | 320 | PR | LI | 0002 | F0Z-708536 | AFC | IFC | 2022-03-02 | 2022-03-10 | 2022-03-11 | 8 | 1 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-16 | 0 |  | D00 | IFC | T-0598 | 2022-02-16 | 1400/11/27 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03269 | 2022-02-28 | 1400/12/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443211 | 2022-03-10 | 1400/12/19 | 2022-03-11 | 1400/12/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0598 | 2022-02-16 | 1400/11/27 |  |  |  | BK-SUR-ENG-PCS-00-03269 | 2022-02-28 | 1400/12/09 | CM-C3 | [6 empty] | 1400-2294-443211 | 2022-03-10 | 1400/12/19 | 2022-03-11 | 1400/12/21 | CM
3 | 1 | 3 | 1 | 0 | 6 | 3 | 3.1.3.1.6.3 | Relief Load Summary | BK-PPL-PEDCO-320-PR-LI-0003 | BK-PPL-PEDCO-320-PR-LI-0003 | BK | PPL | PEDCO | 320 | PR | LI | 0003 | F0Z-708537 | AFC | IFC | 2022-04-26 | 2022-05-09 | 2022-05-16 | 13 | 7 | 20 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-12 | 0 |  | D00 | IFC | T-0809 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04095 | 2022-04-30 | 1401/02/10 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55025 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0809 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-PCS-01-04095 | 2022-04-30 | 1401/02/10 | CM-C3 | [6 empty] | 1401-2294-55025 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | CM
3 | 1 | 3 | 1 | 0 | 6 | 4 | 3.1.3.1.6.4 | Tie in list | BK-PPL-PEDCO-320-PR-LI-0004 | BK-PPL-PEDCO-320-PR-LI-0004 | BK | PPL | PEDCO | 320 | PR | LI | 0004 | F0Z-708538 | AFC | IFC | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | IFA | 2022-05-30 | 0 | 0 | -44711 | 0 | -44711 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 0 |  | D01 | IFA | T-0960 | 2022-05-16 | 1401/02/26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-PPL-PEDCO-320-PR-LI-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-PR-LI-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0607 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-PCS-00-03322 | 2022-03-05 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-443237 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0960 | 2022-05-16 | 1401/02/26 | [7 empty] | PEDCO-CRS-BK-PPL-PEDCO-320-PR-LI-0004_D00 | [11 empty] | NISOC-CRS-BK-PPL-PEDCO-320-PR-LI-0004_D00
3 | 1 | 3 | 1 | 0 | 7 | 0 | 3.1.3.7 | Data Sheet
3 | 1 | 3 | 1 | 0 | 7 | 1 | 3.1.3.1.7.1 | Process Data Sheets For Instrument Devices | BK-PPL-PEDCO-110-PR-DT-0001 | BK-PPL-PEDCO-110-PR-DT-0001 | BK | PPL | PEDCO | 110 | PR | DT | 0001 | F0Z-708539 | AFC | IFC | 44677 | 44695 | 44697 | 18 | 2 | 20 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-12 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03991 | 2022-04-19 | 1401/01/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 2022-05-16 | 1401/02/26 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0807 | 2022-04-12 | 1401/01/12 |  |  |  | BK-SUR-ENG-PCS-01-03991 | 2022-04-19 | 1401/01/30 | CM-C2 | [6 empty] | 1401-2294-52773 | 2022-05-14 | 1401/02/24 | 2022-05-16 | 1401/02/26 | AP
3 | 1 | 3 | 2 | 0 | 0 | 0 | 3.1.3.2 | Mechanical
3 | 1 | 3 | 2 | 0 | 1 | 0 | 3.1.3.1 | Specification
3 | 1 | 3 | 2 | 0 | 2 | 0 | 3.1.3.2.2 | Fixed Equipment
3 | 1 | 3 | 2 | 0 | 2 | 1 | 3.1.3.2.2.1 | Specification For Pig Traps | BK-PPL-PEDCO-320-ME-SP-0001 | BK-PPL-PEDCO-320-ME-SP-0001 | BK | PPL | PEDCO | 320 | ME | SP | 0001 | F0Z-708540 | AFD | IFC | 44457 | 44482 | 44486 | 25 | 4 | 29 | IFA | 44538 | 44530 | 44535 | -8 | 5 | -3 | AFD | 44606 | 44633 | 44646 | 27 | 13 | 40 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-04 | 2022-01-31 |  | D02 | AFD | T-0528 | 2022-01-31 | 1400/11/11 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02920 | 2022-02-02 | 1400/11/13 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-447211 | 2022-03-13 | 1400/12/22 | 2022-03-26 | 1401/01/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0076 | 2021-09-04 | 1400/06/13 |  |  |  | BK-SUR-ENG-FXE-00-01789 | 2021-10-19 | 1400/07/27 | CM-C3 | [6 empty] | 1400-2294-206346 | 2021-09-20 | 1400/06/29 | 2021-10-17 | 1400/07/25 | CM |  | 1400-2294-234189 | 2021-10-13 | 1400/07/21 |  |  | CM |  |  |  | D01 | IFA | T-0269 | 2021-11-24 | 1400/09/03 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-320-ME-SP-0001-D00 | [5 empty] | 1400-2290-298671 | 2021-11-30 | 1400/09/09 | 2021-12-05 | 1400/09/14 | AP | NISOC-CRS-BK-GCS-PEDCO-320-ME-SP-0001-D00 | [9 empty] | D02 | AFD | T-0528 | 2022-01-31 | 1400/11/11 |  |  |  | BK-SUR-ENG-MEC-00-02920 | 2022-02-02 | 1400/11/13 | AP | [6 empty] | 1400-2294-447211 | 2022-03-13 | 1400/12/22 | 2022-03-26 | 1401/01/09 | AP
3 | 1 | 3 | 2 | 1 | 0 | 0 | 3.1.3.2.1 | Data Sheets
3 | 1 | 3 | 2 | 1 | 1 | 0 | 3.1.2.1.1 | Fixed Equipment
3 | 1 | 3 | 2 | 1 | 1 | 1 | 3.1.3.2.1.1.1 | Data Sheets For Pig Traps | BK-PPL-PEDCO-320-ME-DT-0001 | BK-PPL-PEDCO-320-ME-DT-0001 | BK | PPL | PEDCO | 320 | ME | DT | 0001 | F0Z-708541 | AFC | IFC | 44557 | 0 | 0 | -44557 | 0 | -44557 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 0 |  | D00 | IFC | T-0338 | 2021-12-13 | 1400/09/23 | 0 | 0 | 0 | BK-SUR-ENG-FXE-00-02541 | 2022-01-03 | 1400/10/13 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0338 | 2021-12-13 | 1400/09/23 |  |  |  | BK-SUR-ENG-FXE-00-02541 | 2022-01-03 | 1400/10/13 | CM-C3
3 | 1 | 3 | 3 | 0 | 0 | 0 | 3.1.3.3 | Piping
3 | 1 | 3 | 3 | 1 | 0 | 0 | 3.1.3.3.1 | Specification
3 | 1 | 3 | 3 | 1 | 0 | 1 | 3.1.3.3.1 | Piping Material Specification | BK-PPL-PEDCO-320-PI-SP-0001 | BK-PPL-PEDCO-320-PI-SP-0001 | BK | PPL | PEDCO | 320 | PI | SP | 0001 | F0Z-708542 | AFD | IFC | 44556 | 0 | 0 | -44556 | 0 | -44556 | IFA | 44640 | 44578 | 44670 | -62 | 92 | 30 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-12 | 0 |  | D01 | IFA | T-0677 | 2022-03-06 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03538 | 2022-03-14 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PI-SP-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27248 | 2022-01-17 | 1401/01/28 | 2022-04-19 | 1401/01/30 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PI-SP-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0330 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PIP-00-02468 | 2021-12-27 | 1400/10/06 | CM-C2 | [22 empty] | D01 | IFA | T-0677 | 2022-03-06 | 1400/12/14 |  |  |  | BK-SUR-ENG-PIP-00-03538 | 2022-03-14 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PI-SP-0001_D00 | [5 empty] | 1401-2294-27248 | 2022-01-17 | 1401/01/28 | 2022-04-19 | 1401/01/30 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PI-SP-0001_D00
3 | 1 | 3 | 3 | 2 | 0 | 0 | 3.1.3.3.2 | Drawing/Diagram
3 | 1 | 3 | 3 | 2 | 0 | 1 | 3.1.3.3.2 | Unit Plot Plan For Pig Receiver Area (in Siahmakan G.I. Station) | BK-PPL-PEDCO-320-PI-PY-0001 | BK-PPL-PEDCO-320-PI-PY-0001 | BK | PPL | PEDCO | 320 | PI | PY | 0001 | F5A-708543 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 2 | 0 | 2 | 3.1.3.3.2 | A/G Piping Plan | BK-PPL-PEDCO-320-PI-DW-0001 | BK-PPL-PEDCO-320-PI-DW-0001 | BK | PPL | PEDCO | 320 | PI | DW | 0001 | F4L-708544 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 2 | 0 | 3 | 3.1.3.3.2 | A/G Piping Isometric | BK-PPL-PEDCO-320-PI-DW-0002 | BK-PPL-PEDCO-320-PI-DW-0002 | BK | PPL | PEDCO | 320 | PI | DW | 0002 | F2L-708545 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 2 | 0 | 4 | 3.1.3.3.2 | Unit Plot Plan For Binak Production Unit | BK-PPL-PEDCO-320-PI-PY-0002 | BK-PPL-PEDCO-320-PI-PY-0002 | BK | PPL | PEDCO | 320 | PI | PY | 0002 | F5A-708546 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 3 | 0 | 0 | 3.1.3.3.3 | Procedure/Plan
3 | 1 | 3 | 3 | 3 | 0 | 1 | 3.1.3.3.3 | Piping Hydrostatic Test Diagram - PPL | BK-PPL-PEDCO-320-PI-PR-0001 | BK-PPL-PEDCO-320-PI-PR-0001 | BK | PPL | PEDCO | 320 | PI | PR | 0001 | F0Z-708547 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 4 | 0 | 0 | 3.1.3.3.4 | Report
3 | 1 | 3 | 3 | 4 | 0 | 1 | 3.1.3.3.4 | Corrosion Study & Material Selection Report | BK-PPL-PEDCO-320-PI-RT-0001 | BK-PPL-PEDCO-320-PI-RT-0001 | BK | PPL | PEDCO | 320 | PI | RT | 0001 | F0Z-708548 | AFD | IFC | 2021-12-26 | 0 | 0 | -44556 | 0 | -44556 | IFA | 2022-02-19 | 2022-03-10 | 2022-03-12 | 19 | 2 | 21 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-12 | 0 |  | D01 | IFA | T-0550 | 2022-02-05 | 1400/11/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-PPL-PEDCO-320-PI-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443249 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/19 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PI-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0330 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PIP-00-02468 | 2021-12-27 | 1400/10/06 |  |  | BK-SUR-ENG-PIP-00-02544 | 2022-01-03 | 1400/10/13 | CM-C2 | [17 empty] | D01 | IFA | T-0550 | 2022-02-05 | 1400/11/16 | [7 empty] | PEDCO-CRS-BK-PPL-PEDCO-320-PI-RT-0001_D00 | [5 empty] | 1400-2294-443249 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/19 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PI-RT-0001_D00
3 | 1 | 3 | 3 | 4 | 0 | 2 | 3.1.3.3.4 | Wall Thickness Calculation Report | BK-PPL-PEDCO-320-PI-RT-0002 | BK-PPL-PEDCO-320-PI-RT-0002 | BK | PPL | PEDCO | 320 | PI | RT | 0002 | F0Z-708549 | AFC | IFC | 2021-12-26 | 2021-12-20 | 2021-12-26 | -6 | 6 | 0 | IFA | 2022-03-20 | 2022-01-17 | 2022-04-19 | -62 | 92 | 30 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-12 | 0 |  | D01 | IFA | T-0677 | 2022-03-06 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03538 | 2022-03-14 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PI-RT-0002-D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27248 | 2022-01-17 | 1401/01/28 | 2022-04-19 | 1401/01/30 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PI-RT-0002-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0330 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PIP-00-02468 | 2021-12-27 | 1400/10/06 | CM-C2 | [6 empty] | 1400-2294-327385 | 2021-12-20 | 1400/09/29 | 2021-12-26 | 1400/10/05 | CM | [10 empty] | D01 | IFA | T-0677 | 2022-03-06 | 1400/12/14 |  |  |  | BK-SUR-ENG-PIP-00-03538 | 2022-03-14 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-PI-RT-0002-D00 | [5 empty] | 1401-2294-27248 | 2022-01-17 | 1401/01/28 | 2022-04-19 | 1401/01/30 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PI-RT-0002-D00
3 | 1 | 3 | 3 | 4 | 0 | 3 | 3.1.3.3.4 | Stress Analysis Calculations Report | BK-PPL-PEDCO-320-PI-RT-0003 | BK-PPL-PEDCO-320-PI-RT-0003 | BK | PPL | PEDCO | 320 | PI | RT | 0003 | F0Z-708550 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 4 | 0 | 4 | 3.1.3.3.4 | PDMS Model Review Report (30%) | BK-PPL-PEDCO-320-PI-RT-0004 | BK-PPL-PEDCO-320-PI-RT-0004 | BK | PPL | PEDCO | 320 | PI | RT | 0004 | F0Z-708551 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 4 | 0 | 5 | 3.1.3.3.4 | PDMS Model Review Report (60%) | BK-PPL-PEDCO-320-PI-RT-0005 | BK-PPL-PEDCO-320-PI-RT-0005 | BK | PPL | PEDCO | 320 | PI | RT | 0005 | F0Z-708552 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 4 | 0 | 6 | 3.1.3.3.4 | PDMS Model Review Report (90%) | BK-PPL-PEDCO-320-PI-RT-0006 | BK-PPL-PEDCO-320-PI-RT-0006 | BK | PPL | PEDCO | 320 | PI | RT | 0006 | F0Z-708553 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 5 | 0 | 0 | 3.1.3.3.5 | List
3 | 1 | 3 | 3 | 5 | 0 | 1 | 3.1.3.3.5 | Pipe Support List | BK-PPL-PEDCO-320-PI-LI-0001 | BK-PPL-PEDCO-320-PI-LI-0001 | BK | PPL | PEDCO | 320 | PI | LI | 0001 | F0Z-708554 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 5 | 0 | 2 | 3.1.3.3.5 | Piping Tie-In List | BK-PPL-PEDCO-320-PI-LI-0002 | BK-PPL-PEDCO-320-PI-LI-0002 | BK | PPL | PEDCO | 320 | PI | LI | 0002 | F0Z-708555 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 6 | 0 | 0 | 3.1.3.3.6 | MTO
3 | 1 | 3 | 3 | 6 | 0 | 1 | 3.1.3.3 | MTO For Pipes | BK-PPL-PEDCO-320-PI-MT-0001 | BK-PPL-PEDCO-320-PI-MT-0001 | BK | PPL | PEDCO | 320 | PI | MT | 0001 | F8Z-708556 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 6 | 0 | 2 | 3.1.3.3 | MTO For Fittings | BK-PPL-PEDCO-320-PI-MT-0002 | BK-PPL-PEDCO-320-PI-MT-0002 | BK | PPL | PEDCO | 320 | PI | MT | 0002 | F8Z-708557 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 6 | 0 | 3 | 3.1.3.3 | MTO For Flanges | BK-PPL-PEDCO-320-PI-MT-0003 | BK-PPL-PEDCO-320-PI-MT-0003 | BK | PPL | PEDCO | 320 | PI | MT | 0003 | F8Z-708558 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 6 | 0 | 4 | 3.1.3.3 | MTO For Manual Valves | BK-PPL-PEDCO-320-PI-MT-0004 | BK-PPL-PEDCO-320-PI-MT-0004 | BK | PPL | PEDCO | 320 | PI | MT | 0004 | F8Z-708559 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 6 | 0 | 5 | 3.1.3.3 | MTO For Gaskets | BK-PPL-PEDCO-320-PI-MT-0005 | BK-PPL-PEDCO-320-PI-MT-0005 | BK | PPL | PEDCO | 320 | PI | MT | 0005 | F8Z-708560 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 6 | 0 | 6 | 3.1.3.3 | MTO For Bolt & Nuts | BK-PPL-PEDCO-320-PI-MT-0006 | BK-PPL-PEDCO-320-PI-MT-0006 | BK | PPL | PEDCO | 320 | PI | MT | 0006 | F8Z-708561 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 6 | 0 | 7 | 3.1.3.3 | MTO For Insulation Joints | BK-PPL-PEDCO-320-PI-MT-0007 | BK-PPL-PEDCO-320-PI-MT-0007 | [7 empty] | F8Z-708562 | [43 empty] | Deleted | 0
3 | 1 | 3 | 3 | 6 | 0 | 8 | 3.1.3.3 | MTO For Insulation | BK-PPL-PEDCO-320-PI-MT-0008 | BK-PPL-PEDCO-320-PI-MT-0008 | BK | PPL | PEDCO | 320 | PI | MT | 0008 | F8Z-708563 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 6 | 0 | 9 | 3.1.3.3 | MTO For Painting | BK-PPL-PEDCO-320-PI-MT-0009 | BK-PPL-PEDCO-320-PI-MT-0009 | BK | PPL | PEDCO | 320 | PI | MT | 0009 | F8Z-708564 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 3 | 6 | 0 | 10 | 3.1.3.3 | MTO For Coating of Underground Piping | BK-PPL-PEDCO-320-PI-MT-0010 | BK-PPL-PEDCO-320-PI-MT-0010 | BK | PPL | PEDCO | 320 | PI | MT | 0010 | F8Z-708565 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 4 | 0 | 0 | 0 | 3.1.3.4 | Pipeline
3 | 1 | 3 | 4 | 1 | 0 | 0 | 3.1.3.4.1 | Specification
3 | 1 | 3 | 4 | 1 | 0 | 1 | 3.1.3.4.1 | Pipeline Material Specification | BK-PPL-PEDCO-320-PL-SP-0001 | BK-PPL-PEDCO-320-PL-SP-0001 | BK | PPL | PEDCO | 320 | PL | SP | 0001 | F0Z-708566 | AFD | IFC | 44556 | 44581 | 44590 | 25 | 9 | 34 | IFA | 44640 | 44647 | 44654 | 7 | 7 | 14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-12 | 0 |  | D01 | IFA | T-0685 | 2022-03-06 | 1400/12/15 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-03544 | 2022-03-14 | 1400/12/23 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PL-SP-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-6239 | 2022-03-27 | 1401/01/10 | 2022-04-03 | 1401/01/14 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PL-SP-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0332 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PPL-00-02470 | 2021-12-27 | 1400/10/06 | CM-C2 | [6 empty] | 1400-2294-342111 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM |  | 1400-2294-372866 | 2022-01-20 | 1400/10/30 | 2022-01-29 | 1400/11/10 | CM |  |  |  | D01 | IFA | T-0685 | 2022-03-06 | 1400/12/15 |  |  |  | BK-SUR-ENG-PPL-00-03544 | 2022-03-14 | 1400/12/23 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PL-SP-0001_D00 | [5 empty] | 1401-2294-6239 | 2022-03-27 | 1401/01/10 | 2022-04-03 | 1401/01/14 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PL-SP-0001_D00
3 | 1 | 3 | 4 | 2 | 0 | 0 | 3.1.3.4.2 | Calculation
3 | 1 | 3 | 4 | 2 | 0 | 1 | 3.1.3.4.2 | Calculation Note For Pipeline Wall Thickness | BK-PPL-PEDCO-320-PL-CN-0001 | BK-PPL-PEDCO-320-PL-CN-0001 | BK | PPL | PEDCO | 320 | PL | CN | 0001 | F0Z-708567 | AFD | IFC | 44556 | 44581 | 44590 | 25 | 9 | 34 | IFA | 44639 | 44647 | 44654 | 8 | 7 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-12 | 0 |  | D01 | IFA | T-0672 | 2022-03-05 | 1400/12/15 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-03534 | 2022-03-13 | 1400/12/22 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PL-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-6202 | 2022-03-27 | 1401/01/10 | 2022-04-03 | 1401/01/14 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PL-CN-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0332 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-PPL-00-02470 | 2021-12-27 | 1400/10/06 | CM-C2 | [6 empty] | 1400-2294-342111 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM |  | 1400-2294-372866 | 2022-01-20 | 1400/10/30 | 2022-01-29 | 1400/11/10 | CM |  |  |  | D01 | IFA | T-0672 | 2022-03-05 | 1400/12/15 |  |  |  | BK-SUR-ENG-PPL-00-03534 | 2022-03-13 | 1400/12/22 | AP | PEDCO-CRS-BK-PPL-PEDCO-320-PL-CN-0001_D00 | [5 empty] | 1401-2294-6202 | 2022-03-27 | 1401/01/10 | 2022-04-03 | 1401/01/14 | CM | NISOC-CRS-BK-PPL-PEDCO-320-PL-CN-0001_D00
3 | 1 | 3 | 4 | 3 | 0 | 0 | 3.1.3.4.3 | Data Sheets
3 | 1 | 3 | 4 | 3 | 0 | 1 | 3.1.3.4.3 | Data Sheets For Anchor Flanges | BK-PPL-PEDCO-320-PL-DT-0001 | BK-PPL-PEDCO-320-PL-DT-0001 | BK | PPL | PEDCO | 320 | PL | DT | 0001 | F0Z-708568 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 4 | 3 | 0 | 2 | 3.1.3.4.3 | Data Sheets For Barred Tee | BK-PPL-PEDCO-320-PL-DT-0002 | BK-PPL-PEDCO-320-PL-DT-0002 | BK | PPL | PEDCO | 320 | PL | DT | 0002 | F0Z-708569 | AFC | IFC | 2022-04-10 | 2022-04-13 | 2022-04-16 | 3 | 3 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-27 | 0 |  | D00 | IFC | T-0756 | 2022-03-27 | 1401/01/07 | 0 | 0 | 0 | BK-SUR-ENG-PPL-01-03864 | 2022-04-11 | 1401/01/22 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-22785 | 2022-04-13 | 1401/01/24 | 2022-04-16 | 1401/01/27 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0756 | 2022-03-27 | 1401/01/07 |  |  |  | BK-SUR-ENG-PPL-01-03864 | 2022-04-11 | 1401/01/22 | CM-C2 | [6 empty] | 1401-2294-22785 | 2022-04-13 | 1401/01/24 | 2022-04-16 | 1401/01/27 | CM
3 | 1 | 3 | 4 | 3 | 0 | 3 | 3.1.3.4.3 | Data Sheets For Insulation Joints | BK-PPL-PEDCO-320-PL-DT-0003 | BK-PPL-PEDCO-320-PL-DT-0003 | BK | PPL | PEDCO | 320 | PL | DT | 0003 | F0Z-708570 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 4 | 3 | 0 | 4 | 3.1.3.4.3 | Data Sheets For Rock Shield | BK-PPL-PEDCO-320-PL-DT-0004 | BK-PPL-PEDCO-320-PL-DT-0004 | BK | PPL | PEDCO | 320 | PL | DT | 0004 | F0Z-708571 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 4 | 4 | 0 | 0 | 3.1.3.4.4 | Drawing/Diagram
3 | 1 | 3 | 4 | 4 | 0 | 1 | 3.1.3.4.4 | Standard Support Drawings | BK-PPL-PEDCO-320-PL-DW-0001 | BK-PPL-PEDCO-320-PL-DW-0001 | BK | PPL | PEDCO | 320 | PL | DW | 0001 | F1L-708572 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 4 | 4 | 0 | 5 | 3.1.3.4.4 | Pipeline Standard Drawings | BK-PPL-PEDCO-320-PL-DW-0006 | BK-PPL-PEDCO-320-PL-DW-0006 | BK | PPL | PEDCO | 320 | PL | DW | 0006 | F2L-708573 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 4 | 5 | 0 | 0 | 3.1.3.4.5 | Procedure/Plan
3 | 1 | 3 | 4 | 5 | 0 | 1 | 3.1.3.4.5 | Pipeline Hydrostatic Test Diagram - PPL | BK-PPL-PEDCO-320-PL-PR-0001 | BK-PPL-PEDCO-320-PL-PR-0001 | BK | PPL | PEDCO | 320 | PL | PR | 0001 | F0Z-708574 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 4 | 6 | 0 | 0 | 3.1.3.4.6 | Report
3 | 1 | 3 | 4 | 6 | 0 | 1 | 3.1.3.4.6 | Stress Analysis Calculations Report For Pipelines | BK-PPL-PEDCO-320-PL-RT-0001 | BK-PPL-PEDCO-320-PL-RT-0001 | BK | PPL | PEDCO | 320 | PL | RT | 0001 | F0Z-708575 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 4 | 7 | 0 | 0 | 3.1.3.4.7 | MTO
3 | 1 | 3 | 4 | 7 | 0 | 1 | 3.1.3.4 | MTO For Line Pipe | BK-PPL-PEDCO-320-PL-MT-0001 | BK-PPL-PEDCO-320-PL-MT-0001 | BK | PPL | PEDCO | 320 | PL | MT | 0001 | F8Z-708576 | IFI | IFI | 2021-09-05 | 2021-08-30 | 2021-09-05 | -6 | 6 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2021-08-22 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | 1400/05/31 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0058 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | 1400/05/31 | CM-C2 | [6 empty] | 1400-2294-179364 | 2021-08-30 | 1400/06/08 | 2021-09-05 | 1400/06/14 | CM
3 | 1 | 3 | 4 | 7 | 0 | 2 | 3.1.3.4 | MTO For Pipeline Field Joints Coating | BK-PPL-PEDCO-320-PL-MT-0002 | BK-PPL-PEDCO-320-PL-MT-0002 | BK | PPL | PEDCO | 320 | PL | MT | 0002 | F8Z-708577 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 4 | 7 | 0 | 3 | 3.1.3.4 | MTO For Pipeline Flange, Fittings, Gasket and Bolt | BK-PPL-PEDCO-320-PL-MT-0003 | BK-PPL-PEDCO-320-PL-MT-0003 | BK | PPL | PEDCO | 320 | PL | MT | 0003 | F8Z-708578 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 0 | 0 | 0 | 3.1.3.5 | Control & Instrumentation
3 | 1 | 3 | 5 | 1 | 0 | 0 | 3.1.3.5.1 | Basis/Criteria
3 | 1 | 3 | 5 | 1 | 0 | 1 | 3.1.3.5.1 | Instrument & Control System Basis of Design | BK-PPL-PEDCO-320-IN-DB-0001 | BK-PPL-PEDCO-320-IN-DB-0001 | [7 empty] | - | [43 empty] | Deleted | 0 | 0 |  | D00 | IFC | T-0062 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-01499 | 2021-09-12 | 1400/06/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-179382 | 2021-08-30 | 1400/06/08 | 2021-09-12 | 1400/06/21 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0062 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-INS-00-01499 | 2021-09-12 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-179382 | 2021-08-30 | 1400/06/08 | 2021-09-12 | 1400/06/21 | RJ
3 | 1 | 3 | 5 | 1 | 0 | 2 | 3.1.3.5.1 | Instrument & Control System Design Criteria | BK-PPL-PEDCO-320-IN-DC-0001 | BK-PPL-PEDCO-320-IN-DC-0001 | BK | PPL | PEDCO | 320 | IN | DC | 0001 | F0Z-708579 | AFD | IFC | 2022-01-17 | 2022-02-16 | 2022-02-21 | 30 | 5 | 35 | IFA | 2022-06-11 | 0 | 0 | -44723 | 0 | -44723 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-03 | 0 |  | D01 | IFA | T-1013 | 2022-05-28 | 1401/03/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DC-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-IN-DC-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0420 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-INS-00-02625 | 2022-01-10 | 1400/10/20 | CM-C3 | [6 empty] | 1400-2294-412682 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-1013 | 2022-05-28 | 1401/03/07 | [7 empty] | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DC-0001_D00 | [11 empty] | NISOC-CRS-BK-PPL-PEDCO-320-IN-DC-0001_D00
3 | 1 | 3 | 5 | 1 | 0 | 3 | 3.1.3.5.1 | Fire & Gas Detection Design Criteria | BK-PPL-PEDCO-320-IN-DC-0002 | BK-PPL-PEDCO-320-IN-DC-0002 | BK | PPL | PEDCO | 320 | IN | DC | 0002 | F0Z-708580 | AFD | IFC | 2022-06-14 | 0 | 0 | -44726 | 0 | -44726 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-31 | 0 |  | D00 | IFC | T-1028 | 2022-05-31 | 1401/03/10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1028 | 2022-05-31 | 1401/03/10
3 | 1 | 3 | 5 | 2 | 0 | 0 | 3.1.3.5.2 | Data Sheets
3 | 1 | 3 | 5 | 2 | 0 | 1 | 3.1.3.5.2 | Data Sheets For Pressure & Diff. Pressure Gauge | BK-PPL-PEDCO-320-IN-DT-0001 | BK-PPL-PEDCO-320-IN-DT-0001 | BK | PPL | PEDCO | 320 | IN | DT | 0001 | F9Z-708581 | AFC | IFC | 2022-02-16 | 2022-03-15 | 2022-03-25 | 27 | 10 | 37 | IFA | 2022-05-14 | 2022-05-21 | 2022-05-23 | 7 | 2 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 0 |  | D01 | IFA | T-0883 | 2022-04-30 | 1401/02/10 | T-0883 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-INS-01-04312 | 2022-05-18 | 1401/02/28 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70739 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISCO-CRS-BK-PPL-NISCO-320-IN-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0542 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03061 | 2022-02-14 | 1400/11/25 | CM-C3 | [6 empty] | 1400-2294-449416 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | CM | [10 empty] | D01 | IFA | T-0883 | 2022-04-30 | 1401/02/10 | T-0883 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-INS-01-04312 | 2022-05-18 | 1401/02/28 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0001_D00 | [5 empty] | 1401-2294-70739 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISCO-CRS-BK-PPL-NISCO-320-IN-DT-0001_D00
3 | 1 | 3 | 5 | 2 | 0 | 2 | 3.1.3.5.2 | Data Sheets For Temperature Gauge | BK-PPL-PEDCO-320-IN-DT-0002 | BK-PPL-PEDCO-320-IN-DT-0002 | BK | PPL | PEDCO | 320 | IN | DT | 0002 | F9Z-708582 | AFC | IFC | 2022-02-19 | 2022-03-09 | 2022-03-12 | 18 | 3 | 21 | IFA | 2022-05-15 | 2022-05-17 | 2022-05-23 | 2 | 6 | 8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-05 | 0 |  | D01 | IFA | T-0888 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04313 | 2022-05-22 | 1401/03/01 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65632 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0549 | 2022-02-05 | 1400/11/16 |  |  |  | BK-SUR-ENG-INS-00-03113 | 2022-02-19 | 1400/11/30 | CM-C3 | [6 empty] | 1400-2294-442081 | 2022-03-09 | 1400/12/18 | 2022-03-12 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0888 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-INS-01-04313 | 2022-05-22 | 1401/03/01 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0002_D00 | [5 empty] | 1401-2294-65632 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0002_D00
3 | 1 | 3 | 5 | 2 | 0 | 3 | 3.1.3.5.2 | Data Sheets For Pressure/Diff. Pressure Transmitter | BK-PPL-PEDCO-320-IN-DT-0003 | BK-PPL-PEDCO-320-IN-DT-0003 | BK | PPL | PEDCO | 320 | IN | DT | 0003 | F9Z-708583 | AFC | IFC | 2022-02-27 | 2022-03-03 | 2022-03-08 | 4 | 5 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-13 | 0 |  | D00 | IFC | T-0587 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03250 | 2022-02-27 | 1400/12/08 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-432761 | 2022-03-03 | 1400/12/12 | 2022-03-08 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0587 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-INS-00-03250 | 2022-02-27 | 1400/12/08 | CM-C3 | [6 empty] | 1400-2294-432761 | 2022-03-03 | 1400/12/12 | 2022-03-08 | 1400/12/17 | CM
3 | 1 | 3 | 5 | 2 | 0 | 5 | 3.1.3.5.2 | Data Sheets For Pressure & Safety Relief Valves | BK-PPL-PEDCO-320-IN-DT-0005 | BK-PPL-PEDCO-320-IN-DT-0005 | BK | PPL | PEDCO | 320 | IN | DT | 0005 | F9Z-708584 | AFC | IFC | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | IFA | 2022-06-11 | 0 | 0 | -44723 | 0 | -44723 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-27 | 0 |  | D01 | IFA | T-1015 | 2022-05-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-PPL-PEDCO-320-IN-DT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0749 | 2022-03-27 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | 1401/01/27 | CM-C3 | [6 empty] | 1401-2294-27269 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM | [10 empty] | D01 | IFA | T-1015 | 2022-05-28 | [8 empty] | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0005_D00 | [11 empty] | NISOC-CRS-BK-PPL-PEDCO-320-IN-DT-0005_D00
3 | 1 | 3 | 5 | 2 | 0 | 6 | 3.1.3.5.2 | Data Sheets For ON/OFF & Shutdown Valves | BK-PPL-PEDCO-320-IN-DT-0006 | BK-PPL-PEDCO-320-IN-DT-0006 | BK | PPL | PEDCO | 320 | IN | DT | 0006 | F9Z-708585 | AFC | IFC | 2022-06-11 | 0 | 0 | -44723 | 0 | -44723 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-28 | 0 |  | D00 | IFC | T-1014 | 2022-05-28 | 1401/03/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1014 | 2022-05-28 | 1401/03/07
3 | 1 | 3 | 5 | 2 | 0 | 7 | 3.1.3.5.2 | Data Sheets For Corrosion Coupon/ Probe | BK-PPL-PEDCO-320-IN-DT-0009 | BK-PPL-PEDCO-320-IN-DT-0009 | BK | PPL | PEDCO | 320 | IN | DT | 0009 | F9Z-708586 | AFC | IFC | 2022-02-16 | 2022-03-15 | 2022-03-25 | 27 | 10 | 37 | IFA | 2022-05-22 | 0 | 0 | -44703 | 0 | -44703 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 0 |  | D01 | IFA | T-0907 | 2022-05-08 | 1401/02/18 | T-0907 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-INS-01-04429 | 2022-05-25 | 1401/03/03 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0009_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0009_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0542 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03061 | 2022-02-14 | 1400/11/25 | CM-C3 | [6 empty] | 1400-2294-449416 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | CM | [10 empty] | D01 | IFA | T-0907 | 2022-05-08 | 1401/02/18 | T-0907 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-INS-01-04429 | 2022-05-25 | 1401/03/03 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0009_D00 | [11 empty] | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0009_D00
3 | 1 | 3 | 5 | 2 | 0 | 8 | 3.1.3.5.2 | Data Sheets For Pig Signaler | BK-PPL-PEDCO-320-IN-DT-0010 | BK-PPL-PEDCO-320-IN-DT-0010 | BK | PPL | PEDCO | 320 | IN | DT | 0010 | F9Z-708587 | AFC | IFC | 2022-02-16 | 2022-03-15 | 2022-03-25 | 27 | 10 | 37 | IFA | 2022-05-15 | 2022-05-17 | 2022-05-23 | 2 | 6 | 8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 0 |  | D01 | IFA | T-0888 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04313 | 2022-05-22 | 1401/03/01 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0010_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65632 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0010_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0542 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03061 | 2022-02-14 | 1400/11/25 | CM-C3 | [6 empty] | 1400-2294-449416 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | CM | [10 empty] | D01 | IFA | T-0888 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-INS-01-04313 | 2022-05-22 | 1401/03/01 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0010_D00 | [5 empty] | 1401-2294-65632 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM | NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0010_D00
3 | 1 | 3 | 5 | 2 | 0 | 9 | 3.1.3.5.2 | Data Sheets For F&G Detectors & Equipment | BK-PPL-PEDCO-320-IN-DT-0011 | BK-PPL-PEDCO-320-IN-DT-0011 | BK | PPL | PEDCO | 320 | IN | DT | 0011 | F9Z-708588 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 2 | 0 | 10 | 3.1.3.5.2 | Data Sheets For LBV | BK-PPL-PEDCO-320-IN-DT-0012 | BK-PPL-PEDCO-320-IN-DT-0012 | BK | PPL | PEDCO | 320 | IN | DT | 0012 | F9Z-708589 | AFC | IFC | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-27 | 0 |  | D00 | IFC | T-0749 | 2022-03-27 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | 1401/01/27 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27269 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0749 | 2022-03-27 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03938 | 2022-04-16 | 1401/01/27 | CM-C3 | [6 empty] | 1401-2294-27269 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM
3 | 1 | 3 | 5 | 3 | 0 | 0 | 3.1.3.5.3 | Drawing/Diagram
3 | 1 | 3 | 5 | 3 | 0 | 1 | 3.1.3.5.3 | Typical Instrument Installation Drawing | BK-PPL-PEDCO-320-IN-DW-0001 | BK-PPL-PEDCO-320-IN-DW-0001 | BK | PPL | PEDCO | 320 | IN | DW | 0001 | F2J-708590 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 3 | 0 | 2 | 3.1.3.5.3 | Block Diagram Configuration For Control/ESD/F&G System | BK-PPL-PEDCO-320-IN-BD-0001 | BK-PPL-PEDCO-320-IN-BD-0001 | BK | PPL | PEDCO | 320 | IN | BD | 0001 | F2J-708591 | AFC | IFC | 2021-09-15 | 2021-09-29 | 2021-10-09 | 14 | 10 | 24 | IFA | 2021-11-15 | 2021-11-21 | 2021-11-27 | 6 | 6 | 12 | IFA | 2022-01-24 | 2022-01-29 | 2022-01-30 | 5 | 1 | 6 | IFA | 2022-04-24 | 2022-05-16 | 2022-05-16 | 22 | 0 | 22 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-01 | 0 |  | D03 | IFA | T-0801 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04119 | 2022-05-01 | 1401/02/11 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-BD-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59533 | 2022-05-16 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-BD-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0074 | 2021-09-01 | 1400/06/10 |  |  |  | BK-SUR-ENG-INS-00BK-SUR-ENG-INS-00-01552 | 2021-09-20 | 1400/06/024 | CM-C3 | [6 empty] | 1400-2294-217809 | 2021-09-29 | 1400/07/07 | 2021-10-09 | 1400/07/17 | CM | [10 empty] | D01 | IFA | T-0202 | 2021-11-01 | 1400/08/10 |  |  |  | BK-SUR-ENG-INS-00-01995 | 2021-11-14 | 1400/08/23 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-BD-0001-D00 | [5 empty] | 1400-2294-283464 | 2021-11-21 | 1400/08/30 | 2021-11-27 | 1400/09/06 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-BD-0001-D00 | [9 empty] | D02 | IFA | T-0444 | 2022-01-10 | 1400/10/20 |  |  |  | BK-SUR-ENG-INS-00-02815 | 2022-01-25 | 1400/11/05 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-BD-0001-D01 | [5 empty] | 1400-2294-385430 | 2022-01-29 | 1400/11/09 | 2022-01-30 | 1400/11/10 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-BD-0001-D01 | [9 empty] | D03 | IFA | T-0801 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-INS-01-04119 | 2022-05-01 | 1401/02/11 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-BD-0001_D02 | [5 empty] | 1401-2294-59533 | 2022-05-16 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-BD-0001_D02
3 | 1 | 3 | 5 | 3 | 0 | 3 | 3.1.3.5.3 | Instrument Earthing Typical Diagram | BK-PPL-PEDCO-320-IN-DG-0001 | BK-PPL-PEDCO-320-IN-DG-0001 | BK | PPL | PEDCO | 320 | IN | DG | 0001 | F2J-708592 | IFI | IFI | 2022-01-12 | 2022-01-13 | 2022-01-15 | 1 | 2 | 3 | IFI | 2022-05-01 | 2022-05-12 | 2022-05-16 | 11 | 4 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-29 | 2022-04-17 |  | D01 | IFI | T-0828 | 2022-04-17 | 1401/01/28 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04154 | 2022-05-07 | 1401/02/17 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59512 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0408 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-INS-00-02612 | 2022-01-09 | 1400/10/19 | CM-C2 | [6 empty] | 1400-2294-362541 | 2022-01-13 | 1400/10/23 | 2022-01-15 | 1400/10/25 | CM | [10 empty] | D01 | IFI | T-0828 | 2022-04-17 | 1401/01/28 |  |  |  | BK-SUR-ENG-INS-01-04154 | 2022-05-07 | 1401/02/17 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-DG-0001_D00 | [5 empty] | 1401-2294-59512 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-DG-0001_D00
3 | 1 | 3 | 5 | 3 | 0 | 4 | 3.1.3.5.3 | Instrument Hook-up Diagram | BK-PPL-PEDCO-320-IN-DG-0002 | BK-PPL-PEDCO-320-IN-DG-0002 | BK | PPL | PEDCO | 320 | IN | DG | 0002 | F2J-708593 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 3 | 0 | 5 | 3.1.3.5.3 | ESD Level Hierarchy | BK-PPL-PEDCO-320-IN-DG-0003 | BK-PPL-PEDCO-320-IN-DG-0003 | BK | PPL | PEDCO | 320 | IN | DG | 0003 | F2J-708594 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 3 | 0 | 6 | 3.1.3.5.3 | ESD System Loop Diagram | BK-PPL-PEDCO-320-IN-DG-0004 | BK-PPL-PEDCO-320-IN-DG-0004 | BK | PPL | PEDCO | 320 | IN | DG | 0004 | F2J-708595 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 3 | 0 | 7 | 3.1.3.5.3 | Control System Loop Diagram | BK-PPL-PEDCO-320-IN-DG-0005 | BK-PPL-PEDCO-320-IN-DG-0005 | BK | PPL | PEDCO | 320 | IN | DG | 0005 | F2J-708596 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 3 | 0 | 8 | 3.1.3.5.3 | Instrument Air Piping and Air Header Diagram | BK-PPL-PEDCO-320-IN-DG-0006 | BK-PPL-PEDCO-320-IN-DG-0006 | BK | PPL | PEDCO | 320 | IN | DG | 0006 | F2J-708597 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 3 | 0 | 9 | 3.1.3.5.3 | Instrument & F&G Junction Box Termination Diagram | BK-PPL-PEDCO-320-IN-DG-0007 | BK-PPL-PEDCO-320-IN-DG-0007 | BK | PPL | PEDCO | 320 | IN | DG | 0007 | F2J-708598 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 3 | 0 | 10 | 3.1.3.5.3 | Control System Logic Diagram | BK-PPL-PEDCO-320-IN-LD-0001 | BK-PPL-PEDCO-320-IN-LD-0001 | BK | PPL | PEDCO | 320 | IN | LD | 0001 | F1J-708599 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 3 | 0 | 11 | 3.1.3.5.3 | ESD Logic Diagram | BK-PPL-PEDCO-320-IN-LD-0002 | BK-PPL-PEDCO-320-IN-LD-0002 | BK | PPL | PEDCO | 320 | IN | LD | 0002 | F1J-708600 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 3 | 0 | 12 | 3.1.3.5.3 | Control Room Cable Route Layout | BK-PPL-PEDCO-320-IN-PY-0001 | BK-PPL-PEDCO-320-IN-PY-0001 | BK | PPL | PEDCO | 320 | IN | PY | 0001 | F2J-708601 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 3 | 0 | 13 | 3.1.3.5.3 | Instrument Location Layout | BK-PPL-PEDCO-320-IN-PY-0002 | BK-PPL-PEDCO-320-IN-PY-0002 | BK | PPL | PEDCO | 320 | IN | PY | 0002 | F2J-708602 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 3 | 0 | 14 | 3.1.3.5.3 | Instrument Cable Trench/Route Layout Drawing | BK-PPL-PEDCO-320-IN-PY-0003 | BK-PPL-PEDCO-320-IN-PY-0003 | BK | PPL | PEDCO | 320 | IN | PY | 0003 | F2J-708603 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 3 | 0 | 15 | 3.1.3.5.3 | Control Room Arrangement Layout | BK-PPL-PEDCO-320-IN-PY-0006 | BK-PPL-PEDCO-320-IN-PY-0006 | BK | PPL | PEDCO | 320 | IN | PY | 0006 | F2J-708604 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 3 | 0 | 16 | 3.1.3.5.3 | F&G System Loop Diagram | BK-PPL-PEDCO-320-IN-PY-0007 | BK-PPL-PEDCO-320-IN-PY-0007 | [7 empty] | F2J-708605 | [43 empty] | Deleted | 0
3 | 1 | 3 | 5 | 3 | 0 | 17 | 3.1.3.5.3 | F&G Cause and Effect Diagram | BK-PPL-PEDCO-320-IN-PY-0008 | BK-PPL-PEDCO-320-IN-PY-0008 | [7 empty] | F2J-708606 | [43 empty] | Deleted | 0
3 | 1 | 3 | 5 | 3 | 0 | 18 | 3.1.3.5.3 | F&G Location Layout For Process Area | BK-PPL-PEDCO-320-IN-PY-0009 | BK-PPL-PEDCO-320-IN-PY-0009 | BK | PPL | PEDCO | 320 | IN | PY | 0009 | F2J-708607 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 4 | 0 | 0 | 3.1.3.5.4 | List
3 | 1 | 3 | 5 | 4 | 0 | 1 | 3.1.3.5.4 | Instrument Index | BK-PPL-PEDCO-320-IN-LI-0001 | BK-PPL-PEDCO-320-IN-LI-0001 | BK | PPL | PEDCO | 320 | IN | LI | 0001 | F0Z-708608 | AFC | IFC | 2022-02-16 | 2022-03-15 | 2022-03-25 | 27 | 10 | 37 | IFA | 2022-05-15 | 2022-05-17 | 2022-05-23 | 2 | 6 | 8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 0 |  | D01 | IFA | T-0888 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04313 | 2022-05-22 | 1401/03/01 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65632 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0542 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03061 | 2022-02-14 | 1400/11/25 | CM-C3 | [6 empty] | 1400-2294-449416 | 2022-03-15 | 1400/12/24 | 2022-03-25 | 1401/01/08 | CM | [10 empty] | D01 | IFA | T-0888 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-INS-01-04313 | 2022-05-22 | 1401/03/01 | CM-C3 | PEDCO-CRS-BK-PPL-PEDCO-320-IN-LI-0001_D00 | [5 empty] | 1401-2294-65632 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-PPL-PEDCO-320-IN-LI-0001_D00
3 | 1 | 3 | 5 | 4 | 0 | 2 | 3.1.3.5.4 | I/O List For Control System | BK-PPL-PEDCO-320-IN-LI-0002 | BK-PPL-PEDCO-320-IN-LI-0002 | BK | PPL | PEDCO | 320 | IN | LI | 0002 | F0Z-708609 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 4 | 0 | 3 | 3.1.3.5.4 | I/O List For ESD /F&G System | BK-PPL-PEDCO-320-IN-LI-0003 | BK-PPL-PEDCO-320-IN-LI-0003 | BK | PPL | PEDCO | 320 | IN | LI | 0003 | F0Z-708610 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 4 | 0 | 4 | 3.1.3.5.4 | Panels & Junction Box List | BK-PPL-PEDCO-320-IN-LI-0004 | BK-PPL-PEDCO-320-IN-LI-0004 | BK | PPL | PEDCO | 320 | IN | LI | 0004 | F0Z-708611 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 4 | 0 | 5 | 3.1.3.5.4 | Set Point & Alarm List | BK-PPL-PEDCO-320-IN-LI-0005 | BK-PPL-PEDCO-320-IN-LI-0005 | BK | PPL | PEDCO | 320 | IN | LI | 0005 | F0Z-708612 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 4 | 0 | 6 | 3.1.3.5.4 | I&C Power Consumption Summary | BK-PPL-PEDCO-320-IN-LI-0006 | BK-PPL-PEDCO-320-IN-LI-0006 | BK | PPL | PEDCO | 320 | IN | LI | 0006 | F0Z-708613 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 4 | 0 | 7 | 3.1.3.5.4 | Instrument and F&G Cable List | BK-PPL-PEDCO-320-IN-LI-0007 | BK-PPL-PEDCO-320-IN-LI-0007 | BK | PPL | PEDCO | 320 | IN | LI | 0007 | F0Z-708614 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 4 | 0 | 8 | 3.1.3.5.4 | F&G Detector List | BK-PPL-PEDCO-320-IN-LI-0008 | BK-PPL-PEDCO-320-IN-LI-0008 | BK | PPL | PEDCO | 320 | IN | LI | 0008 | F0Z-708615 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 5 | 0 | 0 | 3.1.3.5.5 | MTO
3 | 1 | 3 | 5 | 5 | 0 | 1 | 3.1.3.5 | MTO for Bulk Item and Installation Accessories | BK-PPL-PEDCO-320-IN-MT-0001 | BK-PPL-PEDCO-320-IN-MT-0001 | BK | PPL | PEDCO | 320 | IN | MT | 0001 | F8Z-708616 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 5 | 0 | 2 | 3.1.3.5 | MTO For Instrument/F&G Cable | BK-PPL-PEDCO-320-IN-MT-0002 | BK-PPL-PEDCO-320-IN-MT-0002 | BK | PPL | PEDCO | 320 | IN | MT | 0002 | F8Z-708617 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 5 | 0 | 3 | 3.1.3.5 | MTO For Instrument/F&G Junction box and Gland | BK-PPL-PEDCO-320-IN-MT-0003 | BK-PPL-PEDCO-320-IN-MT-0003 | BK | PPL | PEDCO | 320 | IN | MT | 0003 | F8Z-708618 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 5 | 0 | 4 | 3.1.3.5 | MTO For Instrument Tube and Fitting | BK-PPL-PEDCO-320-IN-MT-0004 | BK-PPL-PEDCO-320-IN-MT-0004 | BK | PPL | PEDCO | 320 | IN | MT | 0004 | F8Z-708619 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 5 | 0 | 5 | 3.1.3.5 | MTO For Instrument Cable Tray/Ladder | BK-PPL-PEDCO-320-IN-MT-0005 | BK-PPL-PEDCO-320-IN-MT-0005 | BK | PPL | PEDCO | 320 | IN | MT | 0005 | F8Z-708620 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 5 | 5 | 0 | 6 | 3.1.3.5 | MTO For Safety Sign | BK-PPL-PEDCO-320-SA-MT-0002 | BK-PPL-PEDCO-320-SA-MT-0002 | BK | PPL | PEDCO | 320 | SA | MT | 0002 | F8Z-708621 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 6 | 0 | 0 | 0 | 3.1.3.6 | Safety & Fire Fighting
3 | 1 | 3 | 6 | 1 | 0 | 0 | 3.1.3.6.1 | Basis/Criteria
3 | 1 | 3 | 6 | 1 | 0 | 1 | 3.1.3.6.1 | Active Fire Protection and Safety Concept | BK-PPL-PEDCO-320-SA-DB-0001 | BK-PPL-PEDCO-320-SA-DB-0001 | BK | PPL | PEDCO | 320 | SA | DB | 0001 | F0Z-708622 | AFD | IFC | 44530 | 0 | 0 | -44530 | 0 | -44530 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-16 | 0 |  | D00 | IFC | T-0252 | 2021-11-16 | 1400/08/25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0252 | 2021-11-16 | 1400/08/25
3 | 1 | 3 | 6 | 2 | 0 | 0 | 3.1.3.6.2 | Data Sheets
3 | 1 | 3 | 6 | 2 | 0 | 1 | 3.1.3.6.2 | Data Sheets For Safety Equipment | BK-PPL-PEDCO-320-SA-DT-0002 | BK-PPL-PEDCO-320-SA-DT-0002 | BK | PPL | PEDCO | 320 | SA | DT | 0002 | F0Z-708623 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 6 | 2 | 0 | 2 | 3.1.3.6.2 | Data Sheets For fire fighting Equipment | BK-PPL-PEDCO-320-SA-DT-0003 | BK-PPL-PEDCO-320-SA-DT-0003 | BK | PPL | PEDCO | 320 | SA | DT | 0003 | F0Z-708624 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 6 | 2 | 0 | 3 | 3.1.3.6.2 | Data Sheets For safety sign | BK-PPL-PEDCO-320-SA-DT-0004 | BK-PPL-PEDCO-320-SA-DT-0004 | BK | PPL | PEDCO | 320 | SA | DT | 0004 | F0Z-708625 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 6 | 3 | 0 | 0 | 3.1.3.6.3 | Drawing/Diagram
3 | 1 | 3 | 6 | 3 | 0 | 1 | 3.1.3.6.3 | Hazardous Area Classification Layout | BK-PPL-PEDCO-320-SA-PY-0001 | BK-PPL-PEDCO-320-SA-PY-0001 | BK | PPL | PEDCO | 320 | SA | PY | 0001 | F2L-708626 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 6 | 3 | 0 | 2 | 3.1.3.6.3 | Safety & Fire Fighting Equipment Location Layout | BK-PPL-PEDCO-320-SA-PY-0002 | BK-PPL-PEDCO-320-SA-PY-0002 | BK | PPL | PEDCO | 320 | SA | PY | 0002 | F2L-708627 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 6 | 3 | 0 | 3 | 3.1.3.6.3 | Escape Route & Safety Sign Layout | BK-PPL-PEDCO-320-SA-PY-0003 | BK-PPL-PEDCO-320-SA-PY-0003 | BK | PPL | PEDCO | 320 | SA | PY | 0003 | F2L-708628 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 6 | 4 | 0 | 0 | 3.1.3.6.4 | Report
3 | 1 | 3 | 6 | 4 | 0 | 1 | 3.1.3.6.4 | QRA Report | BK-PPL-PEDCO-320-SA-RT-0003 | BK-PPL-PEDCO-320-SA-RT-0003 | BK | PPL | PEDCO | 320 | SA | RT | 0003 | F0Z-708629 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 6 | 5 | 0 | 0 | 3.1.3.6.5 | List
3 | 1 | 3 | 6 | 5 | 0 | 1 | 3.1.3.6.5 | Hazard Source List | BK-PPL-PEDCO-320-SA-LI-0001 | BK-PPL-PEDCO-320-SA-LI-0001 | BK | PPL | PEDCO | 320 | SA | LI | 0001 | F0Z-708630 | AFC | IFC | 44530 | 0 | 0 | -44530 | 0 | -44530 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-16 | 0 |  | D00 | IFC | T-0252 | 2021-11-16 | 1400/08/25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0252 | 2021-11-16 | 1400/08/25
3 | 1 | 3 | 6 | 6 | 0 | 0 | 3.1.3.6.6 | MTO
3 | 1 | 3 | 6 | 6 | 0 | 1 | 3.1.3.6 | MTO For Safety & Fire Fighting Equipment | BK-PPL-PEDCO-320-SA-MT-0001 | BK-PPL-PEDCO-320-SA-MT-0001 | BK | PPL | PEDCO | 320 | SA | MT | 0001 | F8Z-708631 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 7 | 0 | 0 | 0 | 3.1.3.7 | Electrical
3 | 1 | 3 | 7 | 1 | 0 | 0 | 3.1.3.7.1 | Calculation
3 | 1 | 3 | 7 | 1 | 0 | 1 | 3.1.3.7.1 | Calculation Note For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-CN-0001 | BK-PPL-PEDCO-320-EL-CN-0001 | BK | PPL | PEDCO | 320 | EL | CN | 0001 | F0Z-708632 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 7 | 2 | 0 | 0 | 3.1.3.7.2 | Data Sheets
3 | 1 | 3 | 7 | 2 | 0 | 1 | 3.1.3.7.2 | Data Sheets For Expansion of LV Switchgear in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-DT-0001 | BK-PPL-PEDCO-320-EL-DT-0001 | BK | PPL | PEDCO | 320 | EL | DT | 0001 | F0Z-708633 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 7 | 2 | 0 | 2 | 3.1.3.7.2 | Data Sheets For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-DT-0002 | BK-PPL-PEDCO-320-EL-DT-0002 | BK | PPL | PEDCO | 320 | EL | DT | 0002 | F0Z-708634 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 7 | 3 | 0 | 0 | 3.1.3.7.3 | Drawing/Diagram
3 | 1 | 3 | 7 | 3 | 0 | 1 | 3.1.3.7.3 | Single Line Diagram For Expansion Of Upstream LV Switchgear in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-SL-0001 | BK-PPL-PEDCO-320-EL-SL-0001 | BK | PPL | PEDCO | 320 | EL | SL | 0001 | F2P-708635 | AFC | IFC | 2022-06-14 | 0 | 0 | -44726 | 0 | -44726 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-31 | 0 |  | D00 | IFC | T-1026 | 2022-05-31 | 1401/03/10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1026 | 2022-05-31 | 1401/03/10
3 | 1 | 3 | 7 | 3 | 0 | 2 | 3.1.3.7.3 | Interconnection Wiring Diagram in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-DG-0002 | BK-PPL-PEDCO-320-EL-DG-0002 | BK | PPL | PEDCO | 320 | EL | DG | 0002 | F2P-708636 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 7 | 3 | 0 | 3 | 3.1.3.7.3 | Interconnection Wiring Diagrams For Cathodic Protection Systems for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-DG-0003 | BK-PPL-PEDCO-320-EL-DG-0003 | BK | PPL | PEDCO | 320 | EL | DG | 0003 | F2P-708637 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 7 | 3 | 0 | 4 | 3.1.3.7.3 | Area Earthing Layout in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-PY-0001 | BK-PPL-PEDCO-320-EL-PY-0001 | BK | PPL | PEDCO | 320 | EL | PY | 0001 | F2P-708638 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 7 | 3 | 0 | 5 | 3.1.3.7.3 | Area Electrical Cable Route & Section Layout in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-PY-0002 | BK-PPL-PEDCO-320-EL-PY-0002 | BK | PPL | PEDCO | 320 | EL | PY | 0002 | F2P-708639 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 7 | 3 | 0 | 6 | 3.1.3.7.3 | Layout For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-PY-0003 | BK-PPL-PEDCO-320-EL-PY-0003 | BK | PPL | PEDCO | 320 | EL | PY | 0003 | F2P-708640 | AFC | IFC | 2022-05-16 | 0 | 0 | -44697 | 0 | -44697 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-02 | 0 |  | D00 | IFC | T-0898 | 2022-05-02 | 1401/02/12 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04280 | 2022-05-15 | 1401/02/25 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0898 | 2022-05-02 | 1401/02/12 |  |  |  | BK-SUR-ENG-ELE-01-04280 | 2022-05-15 | 1401/02/25 | CM-C3
3 | 1 | 3 | 7 | 4 | 0 | 0 | 3.1.3.7.4 | List
3 | 1 | 3 | 7 | 4 | 0 | 1 | 3.1.3.7.4 | Electrical Load List in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-LI-0001 | BK-PPL-PEDCO-320-EL-LI-0001 | BK | PPL | PEDCO | 320 | EL | LI | 0001 | F0Z-708641 | AFC | IFC | 2022-06-13 | 0 | 0 | -44725 | 0 | -44725 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-30 | 0 |  | D00 | IFC | T-1024 | 2022-05-30 | 1401/03/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1024 | 2022-05-30 | 1401/03/09
3 | 1 | 3 | 7 | 4 | 0 | 2 | 3.1.3.7.4 | Electrical Power & Control Cable List in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-LI-0002 | BK-PPL-PEDCO-320-EL-LI-0002 | BK | PPL | PEDCO | 320 | EL | LI | 0002 | F0Z-708642 | AFC | IFC | 2022-06-14 | 0 | 0 | -44726 | 0 | -44726 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-31 | 0 |  | D00 | IFC | T-1026 | 2022-05-31 | 1401/03/10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1026 | 2022-05-31 | 1401/03/10
3 | 1 | 3 | 7 | 4 | 0 | 3 | 3.1.3.7.4 | Cable Schedule For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-LI-0003 | BK-PPL-PEDCO-320-EL-LI-0003 | BK | PPL | PEDCO | 320 | EL | LI | 0003 | F0Z-708643 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 7 | 5 | 0 | 0 | 3.1.3.7.5 | MTO
3 | 1 | 3 | 7 | 5 | 0 | 1 | 3.1.3.7 | MTO For Earthing & Lightning Systems in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0001 | BK-PPL-PEDCO-320-EL-MT-0001 | BK | PPL | PEDCO | 320 | EL | MT | 0001 | F8Z-708644 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 7 | 5 | 0 | 2 | 3.1.3.7 | MTO For Power & Control Cables in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0002 | BK-PPL-PEDCO-320-EL-MT-0002 | BK | PPL | PEDCO | 320 | EL | MT | 0002 | F8Z-708645 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 7 | 5 | 0 | 3 | 3.1.3.7 | MTO For Cathodic Protection System for Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0003 | BK-PPL-PEDCO-320-EL-MT-0003 | BK | PPL | PEDCO | 320 | EL | MT | 0003 | F8Z-708646 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 7 | 5 | 0 | 4 | 3.1.3.7 | MTO For Electrical Bulk Items in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0004 | BK-PPL-PEDCO-320-EL-MT-0004 | BK | PPL | PEDCO | 320 | EL | MT | 0004 | F8Z-708647 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 7 | 5 | 0 | 5 | 3.1.3.7 | MTO For Lighting & Small Powers in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MT-0006 | BK-PPL-PEDCO-320-EL-MT-0006 | BK | PPL | PEDCO | 320 | EL | MT | 0006 | F8Z-708648 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 8 | 0 | 0 | 0 | 3.1.3.8 | Civil
3 | 1 | 3 | 8 | 1 | 0 | 0 | 3.1.3.8.1 | Drawing/Diagram
3 | 1 | 3 | 8 | 1 | 0 | 1 | 3.1.3.8.1 | Civil Layout For Pig Receiver Area (In Siahmakan G.I. Station) | BK-PPL-PEDCO-320-CV-PY-0001 | BK-PPL-PEDCO-320-CV-PY-0001 | BK | PPL | PEDCO | 320 | CV | PY | 0001 | F4A-708649 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 8 | 1 | 0 | 2 | 3.1.3.8.1 | Civil Layout For LBV Stations | BK-PPL-PEDCO-320-CV-PY-0002 | BK-PPL-PEDCO-320-CV-PY-0002 | BK | PPL | PEDCO | 320 | CV | PY | 0002 | F4A-708650 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 8 | 2 | 0 | 0 | 3.1.3.8.2 | Report
3 | 1 | 3 | 8 | 2 | 0 | 1 | 3.1.3.8 | Site Visit Report (Civil Work) - 8" & 4" Pipelines | BK-PPL-PEDCO-110-CV-RT-0001 | BK-PPL-PEDCO-110-CV-RT-0001 | BK | PPL | PEDCO | 110 | CV | RT | 0001 | F0Z-708651 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 9 | 0 | 0 | 0 | 3.1.3.9 | Structure
3 | 1 | 3 | 9 | 1 | 0 | 0 | 3.1.3.9.1 | Drawing/Diagram
3 | 1 | 3 | 9 | 1 | 0 | 1 | 3.1.3.9 | Foundation Drawing For Pig Receiver (PL-3101 In Siahmakan G.I. Station) | BK-PPL-PEDCO-320-ST-DW-0001 | BK-PPL-PEDCO-320-ST-DW-0001 | BK | PPL | PEDCO | 320 | ST | DW | 0001 | F4Q-708652 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 9 | 1 | 0 | 2 | 3.1.3.9 | Structural Drawing For LBV Pits | BK-PPL-PEDCO-320-ST-DW-0002 | BK-PPL-PEDCO-320-ST-DW-0002 | BK | PPL | PEDCO | 320 | ST | DW | 0002 | F4M-708653 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 10 | 0 | 0 | 0 | 3.1.3.10 | Survey (Topography) & Geotechnic/Geoelectric
3 | 1 | 3 | 10 | 0 | 1 | 0 | 3.1.3.10.1 | Procedure/Plan
3 | 1 | 3 | 10 | 0 | 1 | 1 | 3.1.3.10.1.1 | Geotechnical Investigation Plan for Pipelines | BK-PPL-PEDCO-320-GT-PR-0001 | BK-PPL-PEDCO-320-GT-PR-0001 | BK | PPL | PEDCO | 320 | GT | PR | 0001 | F0Z-708654 | AFC | IFC | 44433 | 44423 | 44431 | -10 | 8 | -2 | IFA | 44460 | 44452 | 0 | -8 | -44452 | -44460 | IFA | 44485 | 44476 | 44480 | -9 | 4 | -5 | AFC | 44508 | 44498 | 44502 | -10 | 4 | -6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-11 | 2021-10-25 |  | D03 | AFC | T-0181 | 2021-10-25 | 1400/08/03 | 0 | 0 | 0 | BK-SUR-ENG-GEN-00-01893 | 2021-11-02 | 1400/08/11 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1400-2294-251689 | 2021-10-29 | 1400/08/07 | 2021-11-02 | 1400/08/11 | AP | NISOC-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0043 | 2021-08-11 | 1400/05/20 |  |  |  | BK-SUR-ENG-CIV-00-01344 | 2021-08-17 | 1400/05/26 | CM-C3 | [6 empty] | 1400/2294/166479 | 2021-08-15 | 1400/05/24 | 2021-08-23 | 1400/06/01 | CM | [8 empty] | L-7572 |  | D01 | IFA | T-0082 | 2021-09-07 | 1400/06/16 |  |  |  | BK-SUR-ENG-GEN-00-01491 | 2021-09-11 | 1400/06/20 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D00 | [5 empty] | 1400-2294-197155 | 2021-09-13 | 1400/06/22 |  |  | CM | NISOC-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D00 | [9 empty] | D02 | IFA | T-0127 | 2021-10-02 | 1400/07/10 |  |  |  | BK-SUR-ENG-GEN-00-01679 | 2021-10-06 | 1400/07/14 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D01 | [5 empty] | 1400-2290-225564 | 2021-10-07 | 1400/07/15 | 2021-10-11 | 1400/07/19 | CM | NISOC-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D01 | [9 empty] | D03 | AFC | T-0181 | 2021-10-25 | 1400/08/03 |  |  |  | BK-SUR-ENG-GEN-00-01893 | 2021-11-02 | 1400/08/11 | CM-C2 | PEDCO-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D02 | [5 empty] | 1400-2294-251689 | 2021-10-29 | 1400/08/07 | 2021-11-02 | 1400/08/11 | AP | NISOC-CRS-BK-PPL-PEDCO-320-GT-PR-0001_D02
3 | 1 | 3 | 10 | 0 | 2 | 0 | 3.1.3.10.2 | Report
3 | 1 | 3 | 10 | 0 | 2 | 1 | 3.1.3.10.2.1 | Geotechnical Investigation Report for Pipelines | BK-PPL-PEDCO-320-GT-RT-0001 | BK-PPL-PEDCO-320-GT-RT-0001 | BK | PPL | PEDCO | 320 | GT | RT | 0001 | F0Z-708655 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 10 | 0 | 3 | 0 | 3.1.3.10.3 | Drawing/Diagram
3 | 1 | 3 | 10 | 0 | 3 | 1 | 3.1.3.10.3.1 | Plan & Profile Drawings For Gas Pipeline (to Siahmakan) | BK-PPL-PEDCO-320-SU-DW-0001 | BK-PPL-PEDCO-320-SU-DW-0001 | BK | PPL | PEDCO | 320 | SU | DW | 0001 | F4A-708656 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 3 | 10 | 0 | 3 | 2 | 3.1.3.10.3.2 | Plan & Profile Drawings For Condensate Pipeline (to Binak PU) | BK-PPL-PEDCO-320-SU-DW-0002 | BK-PPL-PEDCO-320-SU-DW-0002 | BK | PPL | PEDCO | 320 | SU | DW | 0002 | F4A-708657 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 0 | 0 | 0 | 0 | 3.1.4 | Procurement Engineering
3 | 1 | 4 | 1 | 0 | 0 | 0 | 3.1.4.1 | Mechanical
3 | 1 | 4 | 1 | 1 | 0 | 0 | 3.1.4.1.1 | Pig Traps
3 | 1 | 4 | 1 | 1 | 1 | 0 | 3.1.1.1.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 1 | 1 | 1 | 1 | 3.1.4.1.1.1.1 | PMR For Pig Traps | BK-PPL-PEDCO-320-ME-MR-0001 | BK-PPL-PEDCO-320-ME-MR-0001 | BK | PPL | PEDCO | 320 | ME | MR | 0001 | F0Z-708660 | IFI | IFI | 44627 | 44628 | 44632 | 1 | 4 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-02-21 |  | D00 | IFI | T-0618 | 2022-02-21 | 1400/11/02 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03302 | 2022-03-02 | 1400/12/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-440957 | 2022-03-08 | 1400/12/17 | 2022-03-12 | 1400/12/21 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0618 | 2022-02-21 | 1400/11/02 |  |  |  | BK-SUR-ENG-MEC-00-03302 | 2022-03-02 | 1400/12/11 | CM-C3 | [6 empty] | 1400-2294-440957 | 2022-03-08 | 1400/12/17 | 2022-03-12 | 1400/12/21 | RJ
3 | 1 | 4 | 1 | 1 | 2 | 0 | 3.1.1.1.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 1 | 1 | 2 | 1 | 3.1.4.1.1.2.1 | TBE For Pig Traps | BK-PPL-PEDCO-320-ME-TB-0001 | BK-PPL-PEDCO-320-ME-TB-0001 | BK | PPL | PEDCO | 320 | ME | TB | 0001 | F0Z-708661 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 2 | 0 | 0 | 0 | 3.1.4.2 | Pipeline
3 | 1 | 4 | 2 | 1 | 0 | 0 | 3.1.4.2.1 | Line Pipe
3 | 1 | 4 | 2 | 1 | 1 | 0 | 3.1.2.1.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 2 | 1 | 1 | 1 | 3.1.4.2.1.1.1 | PMR For Line Pipe | BK-PPL-PEDCO-320-PL-MR-0001 | BK-PPL-PEDCO-320-PL-MR-0001 | BK | PPL | PEDCO | 320 | PL | MR | 0001 | F0Z-708662 | IFI | IFI | 44550 | 44549 | 44551 | -1 | 2 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-06 | 2021-12-06 |  | D00 | IFI | T-0300 | 2021-12-06 | 1400/09/15 | 0 | 0 | 0 | BK-SUR-ENG-PPL-00-02309 | 2021-12-15 | 1400/09/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-323356 | 2021-12-19 | 1400/09/28 | 2021-12-21 | 1400/09/30 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0300 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PPL-00-02309 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-323356 | 2021-12-19 | 1400/09/28 | 2021-12-21 | 1400/09/30 | AP
3 | 1 | 4 | 2 | 1 | 2 | 0 | 3.1.2.1.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 2 | 1 | 2 | 1 | 3.1.4.2.1.2.1 | TBE For Line Pipe | BK-PPL-PEDCO-320-PL-TB-0001 | BK-PPL-PEDCO-320-PL-TB-0001 | BK | PPL | PEDCO | 320 | PL | TB | 0001 | F0Z-708663 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 2 | 2 | 0 | 0 | 3.1.4.2.2 | Insulation Joints
3 | 1 | 4 | 2 | 2 | 1 | 0 | 3.1.2.2.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 2 | 2 | 1 | 1 | 3.1.4.2.2.1.1 | PMR For Line Insulation Joints | BK-PPL-PEDCO-320-PL-MR-0002 | BK-PPL-PEDCO-320-PL-MR-0002 | BK | PPL | PEDCO | 320 | PL | MR | 0002 | F0Z-708664 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 2 | 2 | 2 | 0 | 3.1.2.2.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 2 | 2 | 2 | 1 | 3.1.4.2.2.2.1 | TBE For Line Insulation Joints | BK-PPL-PEDCO-320-PL-TB-0002 | BK-PPL-PEDCO-320-PL-TB-0002 | BK | PPL | PEDCO | 320 | PL | TB | 0002 | F0Z-708665 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 2 | 3 | 0 | 0 | 3.1.4.2.3 | Anchor Flanges
3 | 1 | 4 | 2 | 3 | 1 | 0 | 3.1.2.3.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 2 | 3 | 1 | 1 | 3.1.4.2.3.1.1 | PMR For Anchor Flanges | BK-PPL-PEDCO-320-PL-MR-0003 | BK-PPL-PEDCO-320-PL-MR-0003 | BK | PPL | PEDCO | 320 | PL | MR | 0003 | F0Z-708666 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 2 | 3 | 2 | 0 | 3.1.2.3.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 2 | 3 | 2 | 1 | 3.1.4.2.3.2.1 | TBE For Anchor Flanges | BK-PPL-PEDCO-320-PL-TB-0003 | BK-PPL-PEDCO-320-PL-TB-0003 | BK | PPL | PEDCO | 320 | PL | TB | 0003 | F0Z-708667 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 2 | 4 | 0 | 0 | 3.1.4.2.4 | Pipeline Flange, Fittings, Gasket and Bolt
3 | 1 | 4 | 2 | 4 | 1 | 0 | 3.1.2.4.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 2 | 4 | 1 | 1 | 3.1.4.2.4.1.1 | PMR For Pipeline Flange, Fittings, Gasket and Bolt | BK-PPL-PEDCO-320-PL-MR-0004 | BK-PPL-PEDCO-320-PL-MR-0004 | BK | PPL | PEDCO | 320 | PL | MR | 0004 | F0Z-708668 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 2 | 4 | 2 | 0 | 3.1.2.4.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 2 | 4 | 2 | 1 | 3.1.4.2.4.2.1 | TBE For Pipeline Flange, Fittings, Gasket and Bolt | BK-PPL-PEDCO-320-PL-TB-0004 | BK-PPL-PEDCO-320-PL-TB-0004 | BK | PPL | PEDCO | 320 | PL | TB | 0004 | F0Z-708669 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 2 | 5 | 0 | 0 | 3.1.4.2.5 | Pipeline Rock Shield
3 | 1 | 4 | 2 | 5 | 1 | 0 | 3.1.2.5.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 2 | 5 | 1 | 1 | 3.1.4.2.5.1.1 | PMR For Pipeline Rock Shield | BK-PPL-PEDCO-320-PL-MR-0005 | BK-PPL-PEDCO-320-PL-MR-0005 | BK | PPL | PEDCO | 320 | PL | MR | 0005 | F0Z-708670 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 2 | 5 | 2 | 0 | 3.1.2.5.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 2 | 5 | 2 | 1 | 3.1.4.2.5.2.1 | TBE For Pipeline Rock Shield | BK-PPL-PEDCO-320-PL-TB-0005 | BK-PPL-PEDCO-320-PL-TB-0005 | BK | PPL | PEDCO | 320 | PL | TB | 0005 | F0Z-708671 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 0 | 0 | 0 | 3.1.4.3 | Control & Instrumentation
3 | 1 | 4 | 3 | 1 | 0 | 0 | 3.1.4.3.1 | Control System/Console/Furniture
3 | 1 | 4 | 3 | 1 | 1 | 0 | 3.1.3.1.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 1 | 1 | 1 | 3.1.4.3.1.1.1 | PMR For Control System/Console/Furniture | BK-PPL-PEDCO-320-IN-MR-0001 | BK-PPL-PEDCO-320-IN-MR-0001 | BK | PPL | PEDCO | 320 | IN | MR | 0001 | F0Z-708672 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 1 | 2 | 0 | 3.1.3.1.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 1 | 2 | 1 | 3.1.4.3.1.2.1 | TBE For Control System/Console/Furniture | BK-PPL-PEDCO-320-IN-TB-0001 | BK-PPL-PEDCO-320-IN-TB-0001 | BK | PPL | PEDCO | 320 | IN | TB | 0001 | F0Z-708673 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 2 | 0 | 0 | 3.1.4.3.2 | ESD System
3 | 1 | 4 | 3 | 2 | 1 | 0 | 3.1.3.2.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 2 | 1 | 1 | 3.1.4.3.2.1.1 | PMR For ESD System | BK-PPL-PEDCO-320-IN-MR-0002 | BK-PPL-PEDCO-320-IN-MR-0002 | BK | PPL | PEDCO | 320 | IN | MR | 0002 | F0Z-708674 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 2 | 2 | 0 | 3.1.3.2.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 2 | 2 | 1 | 3.1.4.3.2.2.1 | TBE For ESD System | BK-PPL-PEDCO-320-IN-TB-0002 | BK-PPL-PEDCO-320-IN-TB-0002 | BK | PPL | PEDCO | 320 | IN | TB | 0002 | F0Z-708675 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 3 | 0 | 0 | 3.1.4.3.3 | Corrosion Probe/Coupon
3 | 1 | 4 | 3 | 3 | 1 | 0 | 3.1.3.3.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 3 | 1 | 1 | 3.1.4.3.3.1.1 | PMR For Corrosion Probe/Coupon | BK-PPL-PEDCO-320-IN-MR-0003 | BK-PPL-PEDCO-320-IN-MR-0003 | BK | PPL | PEDCO | 320 | IN | MR | 0003 | F0Z-708676 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 3 | 2 | 0 | 3.1.3.3.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 3 | 2 | 1 | 3.1.4.3.3.2.1 | TBE For Corrosion Probe/Coupon | BK-PPL-PEDCO-320-IN-TB-0003 | BK-PPL-PEDCO-320-IN-TB-0003 | BK | PPL | PEDCO | 320 | IN | TB | 0003 | F0Z-708677 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 4 | 0 | 0 | 3.1.4.3.4 | ON/OFF & Shutdown Valves
3 | 1 | 4 | 3 | 4 | 1 | 0 | 3.1.3.4.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 4 | 1 | 1 | 3.1.4.3.4.1.1 | PMR For ON/OFF & Shutdown Valves | BK-PPL-PEDCO-320-IN-MR-0004 | BK-PPL-PEDCO-320-IN-MR-0004 | BK | PPL | PEDCO | 320 | IN | MR | 0004 | F0Z-708678 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 4 | 2 | 0 | 3.1.3.4.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 4 | 2 | 1 | 3.1.4.3.4.2.1 | TBE For ON/OFF & Shutdown Valves | BK-PPL-PEDCO-320-IN-TB-0004 | BK-PPL-PEDCO-320-IN-TB-0004 | BK | PPL | PEDCO | 320 | IN | TB | 0004 | F0Z-708679 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 5 | 0 | 0 | 3.1.4.3.5 | Pressure Safety Valves (PSV)
3 | 1 | 4 | 3 | 5 | 1 | 0 | 3.1.3.5.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 5 | 1 | 1 | 3.1.4.3.5.1.1 | PMR For Pressure Safety Valves (PSV) | BK-PPL-PEDCO-320-IN-MR-0006 | BK-PPL-PEDCO-320-IN-MR-0006 | BK | PPL | PEDCO | 320 | IN | MR | 0006 | F0Z-708680 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 5 | 2 | 0 | 3.1.3.5.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 5 | 2 | 1 | 3.1.4.3.5.2.1 | TBE For Pressure Safety Valves (PSV) | BK-PPL-PEDCO-320-IN-TB-0006 | BK-PPL-PEDCO-320-IN-TB-0006 | BK | PPL | PEDCO | 320 | IN | TB | 0006 | F0Z-708681 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 6 | 0 | 0 | 3.1.4.3.6 | Differential Pressure/Pressure Gauge
3 | 1 | 4 | 3 | 6 | 1 | 0 | 3.1.3.6.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 6 | 1 | 1 | 3.1.4.3.6.1.1 | PMR For Differential Pressure/Pressure Gauge | BK-PPL-PEDCO-320-IN-MR-0008 | BK-PPL-PEDCO-320-IN-MR-0008 | BK | PPL | PEDCO | 320 | IN | MR | 0008 | F0Z-708682 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 6 | 2 | 0 | 3.1.3.6.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 6 | 2 | 1 | 3.1.4.3.6.2.1 | TBE For Differential Pressure/Pressure Gauge | BK-PPL-PEDCO-320-IN-TB-0008 | BK-PPL-PEDCO-320-IN-TB-0008 | BK | PPL | PEDCO | 320 | IN | TB | 0008 | F0Z-708683 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 7 | 0 | 0 | 3.1.4.3.7 | Pressure/Diff. Pressure Transmitter
3 | 1 | 4 | 3 | 7 | 1 | 0 | 3.1.3.7.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 7 | 1 | 1 | 3.1.4.3.7.1.1 | PMR For Pressure/Diff. Pressure Transmitter | BK-PPL-PEDCO-320-IN-MR-0009 | BK-PPL-PEDCO-320-IN-MR-0009 | BK | PPL | PEDCO | 320 | IN | MR | 0009 | F0Z-708684 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 7 | 2 | 0 | 3.1.3.7.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 7 | 2 | 1 | 3.1.4.3.7.2.1 | TBE For Pressure/Diff. Pressure Transmitter | BK-PPL-PEDCO-320-IN-TB-0009 | BK-PPL-PEDCO-320-IN-TB-0009 | BK | PPL | PEDCO | 320 | IN | TB | 0009 | F0Z-708685 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 8 | 0 | 0 | 3.1.4.3.8 | Temperature Gauge
3 | 1 | 4 | 3 | 8 | 1 | 0 | 3.1.3.8.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 8 | 1 | 1 | 3.1.4.3.8.1.1 | PMR For Temperature Gauge | BK-PPL-PEDCO-320-IN-MR-0010 | BK-PPL-PEDCO-320-IN-MR-0010 | BK | PPL | PEDCO | 320 | IN | MR | 0010 | F0Z-708686 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 8 | 2 | 0 | 3.1.3.8.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 8 | 2 | 1 | 3.1.4.3.8.2.1 | TBE For Temperature Gauge | BK-PPL-PEDCO-320-IN-TB-0010 | BK-PPL-PEDCO-320-IN-TB-0010 | BK | PPL | PEDCO | 320 | IN | TB | 0010 | F0Z-708687 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 9 | 0 | 0 | 3.1.4.3.9 | Pig Signaler
3 | 1 | 4 | 3 | 9 | 1 | 0 | 3.1.3.9.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 9 | 1 | 1 | 3.1.4.3.9.1.1 | PMR For Pig Signaler | BK-PPL-PEDCO-320-IN-MR-0013 | BK-PPL-PEDCO-320-IN-MR-0013 | BK | PPL | PEDCO | 320 | IN | MR | 0013 | F0Z-708688 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 9 | 2 | 0 | 3.1.3.9.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 9 | 2 | 1 | 3.1.4.3.9.2.1 | TBE For Pig Signaler | BK-PPL-PEDCO-320-IN-TB-0013 | BK-PPL-PEDCO-320-IN-TB-0013 | BK | PPL | PEDCO | 320 | IN | TB | 0013 | F0Z-708689 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 10 | 0 | 0 | 3.1.4.3.10 | Instrument Installation Accessories
3 | 1 | 4 | 3 | 10 | 1 | 0 | 3.1.3.10.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 10 | 1 | 1 | 3.1.4.3.10.1.1 | PMR For Instrument Installation Accessories | BK-PPL-PEDCO-320-IN-MR-0014 | BK-PPL-PEDCO-320-IN-MR-0014 | BK | PPL | PEDCO | 320 | IN | MR | 0014 | F0Z-708690 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 10 | 2 | 0 | 3.1.3.10.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 10 | 2 | 1 | 3.1.4.3.10.2.1 | TBE For Instrument Installation Accessories | BK-PPL-PEDCO-320-IN-TB-0014 | BK-PPL-PEDCO-320-IN-TB-0014 | BK | PPL | PEDCO | 320 | IN | TB | 0014 | F0Z-708691 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 11 | 0 | 0 | 3.1.4.3.11 | Instrument Cable Tray
3 | 1 | 4 | 3 | 11 | 1 | 0 | 3.1.3.11.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 11 | 1 | 1 | 3.1.4.3.11.1.1 | PMR For Instrument Cable Tray | BK-PPL-PEDCO-320-IN-MR-0015 | BK-PPL-PEDCO-320-IN-MR-0015 | BK | PPL | PEDCO | 320 | IN | MR | 0015 | F0Z-708692 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 11 | 2 | 0 | 3.1.3.11.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 11 | 2 | 1 | 3.1.4.3.11.2.1 | TBE For Instrument Cable Tray | BK-PPL-PEDCO-320-IN-TB-0015 | BK-PPL-PEDCO-320-IN-TB-0015 | BK | PPL | PEDCO | 320 | IN | TB | 0015 | F0Z-708693 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 12 | 0 | 0 | 3.1.4.3.12 | Instrument Junction box and Gland
3 | 1 | 4 | 3 | 12 | 1 | 0 | 3.1.3.12.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 12 | 1 | 1 | 3.1.4.3.12.1.1 | PMR For Instrument and F&G Junction box and Gland | BK-PPL-PEDCO-320-IN-MR-0016 | BK-PPL-PEDCO-320-IN-MR-0016 | BK | PPL | PEDCO | 320 | IN | MR | 0016 | F0Z-708694 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 12 | 2 | 0 | 3.1.3.12.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 12 | 2 | 1 | 3.1.4.3.12.2.1 | TBE For Instrument and F&G Junction box and Gland | BK-PPL-PEDCO-320-IN-TB-0016 | BK-PPL-PEDCO-320-IN-TB-0016 | BK | PPL | PEDCO | 320 | IN | TB | 0016 | F0Z-708695 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 13 | 0 | 0 | 3.1.4.3.13 | Instrument Tube and Fitting
3 | 1 | 4 | 3 | 13 | 1 | 0 | 3.1.3.13.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 13 | 1 | 1 | 3.1.4.3.13.1.1 | PMR For Instrument Tube and Fitting | BK-PPL-PEDCO-320-IN-MR-0017 | BK-PPL-PEDCO-320-IN-MR-0017 | BK | PPL | PEDCO | 320 | IN | MR | 0017 | F0Z-708696 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 13 | 2 | 0 | 3.1.3.13.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 13 | 2 | 1 | 3.1.4.3.13.2.1 | TBE For Instrument Tube and Fitting | BK-PPL-PEDCO-320-IN-TB-0017 | BK-PPL-PEDCO-320-IN-TB-0017 | BK | PPL | PEDCO | 320 | IN | TB | 0017 | F0Z-708697 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 14 | 0 | 0 | 3.1.4.3.14 | Instrument Cable
3 | 1 | 4 | 3 | 14 | 1 | 0 | 3.1.3.14.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 14 | 1 | 1 | 3.1.4.3.14.1.1 | PMR For Instrument and F&G Cable | BK-PPL-PEDCO-320-IN-MR-0018 | BK-PPL-PEDCO-320-IN-MR-0018 | BK | PPL | PEDCO | 320 | IN | MR | 0018 | F0Z-708698 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 14 | 2 | 0 | 3.1.3.14.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 14 | 2 | 1 | 3.1.4.3.14.2.1 | TBE For Instrument and F&G Cable | BK-PPL-PEDCO-320-IN-TB-0018 | BK-PPL-PEDCO-320-IN-TB-0018 | BK | PPL | PEDCO | 320 | IN | TB | 0018 | F0Z-708699 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 15 | 0 | 0 | 3.1.4.3.15 | F&G Devices
3 | 1 | 4 | 3 | 15 | 1 | 0 | 3.1.3.15.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 15 | 1 | 1 | 3.1.4.3.15.1.1 | PMR For F&G Devices | BK-PPL-PEDCO-320-IN-MR-0019 | BK-PPL-PEDCO-320-IN-MR-0019 | BK | PPL | PEDCO | 320 | IN | MR | 0019 | F0Z-708700 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 15 | 2 | 0 | 3.1.3.15.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 15 | 2 | 1 | 3.1.4.3.15.2.1 | TBE For F&G Devices | BK-PPL-PEDCO-320-IN-TB-0019 | BK-PPL-PEDCO-320-IN-TB-0019 | BK | PPL | PEDCO | 320 | IN | TB | 0019 | F0Z-708701 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 16 | 0 | 0 | 3.1.4.3.16 | LBV
3 | 1 | 4 | 3 | 16 | 1 | 0 | 3.1.3.16.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 3 | 16 | 1 | 1 | 3.1.4.3.16.1.1 | PMR For LBV | BK-PPL-PEDCO-320-IN-MR-0020 | BK-PPL-PEDCO-320-IN-MR-0020 | BK | PPL | PEDCO | 320 | IN | MR | 0020 | F0Z-708702 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 3 | 16 | 2 | 0 | 3.1.3.16.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 3 | 16 | 2 | 1 | 3.1.4.3.16.2.1 | TBE For LBV | BK-PPL-PEDCO-320-IN-TB-0020 | BK-PPL-PEDCO-320-IN-TB-0020 | BK | PPL | PEDCO | 320 | IN | TB | 0020 | F0Z-708703 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 4 | 0 | 0 | 0 | 3.1.4.4 | Safety & Fire Fighting
3 | 1 | 4 | 4 | 1 | 0 | 0 | 3.1.4.4.1 | Safety Equipment
3 | 1 | 4 | 4 | 1 | 1 | 0 | 3.1.4.1.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 4 | 1 | 1 | 1 | 3.1.4.4.1.1.1 | PMR For Safety Equipment | BK-PPL-PEDCO-320-SA-MR-0001 | BK-PPL-PEDCO-320-SA-MR-0001 | BK | PPL | PEDCO | 320 | SA | MR | 0001 | F0Z-708704 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 4 | 1 | 2 | 0 | 3.1.4.1.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 4 | 1 | 2 | 1 | 3.1.4.4.1.2.1 | TBE For Safety Equipment | BK-PPL-PEDCO-320-SA-TB-0001 | BK-PPL-PEDCO-320-SA-TB-0001 | BK | PPL | PEDCO | 320 | SA | TB | 0001 | F0Z-708705 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 4 | 2 | 0 | 0 | 3.1.4.4.2 | Fire Fighting Equipment
3 | 1 | 4 | 4 | 2 | 1 | 0 | 3.1.4.2.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 4 | 2 | 1 | 1 | 3.1.4.4.2.1.1 | PMR For Fire Fighting Equipment | BK-PPL-PEDCO-320-SA-MR-0002 | BK-PPL-PEDCO-320-SA-MR-0002 | BK | PPL | PEDCO | 320 | SA | MR | 0002 | F0Z-708706 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 4 | 2 | 2 | 0 | 3.1.4.2.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 4 | 2 | 2 | 1 | 3.1.4.4.2.2.1 | TBE For Fire Fighting Equipment | BK-PPL-PEDCO-320-SA-TB-0002 | BK-PPL-PEDCO-320-SA-TB-0002 | BK | PPL | PEDCO | 320 | SA | TB | 0002 | F0Z-708707 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 4 | 3 | 0 | 0 | 3.1.4.4.3 | Safety Signs
3 | 1 | 4 | 4 | 3 | 1 | 0 | 3.1.4.3.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 4 | 3 | 1 | 1 | 3.1.4.4.3.1.1 | PMR For Safety Signs | BK-PPL-PEDCO-320-SA-MR-0003 | BK-PPL-PEDCO-320-SA-MR-0003 | BK | PPL | PEDCO | 320 | SA | MR | 0003 | F0Z-708708 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 4 | 3 | 2 | 0 | 3.1.4.3.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 4 | 3 | 2 | 1 | 3.1.4.4.3.2.1 | TBE For Safety Signs | BK-PPL-PEDCO-320-SA-TB-0003 | BK-PPL-PEDCO-320-SA-TB-0003 | BK | PPL | PEDCO | 320 | SA | TB | 0003 | F0Z-708709 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 5 | 0 | 0 | 0 | 3.1.4.5 | Electrical
3 | 1 | 4 | 5 | 1 | 0 | 0 | 3.1.4.5.1 | Expansion Of LV Switchgear
3 | 1 | 4 | 5 | 1 | 1 | 0 | 3.1.5.1.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 5 | 1 | 1 | 1 | 3.1.4.5.1.1.1 | PMR For Expansion Of LV Switchgear in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MR-0001 | BK-PPL-PEDCO-320-EL-MR-0001 | BK | PPL | PEDCO | 320 | EL | MR | 0001 | F0Z-708710 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 5 | 1 | 2 | 0 | 3.1.5.1.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 5 | 1 | 2 | 1 | 3.1.4.5.1.2.1 | TBE For Expansion Of LV Switchgear in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-TB-0001 | BK-PPL-PEDCO-320-EL-TB-0001 | BK | PPL | PEDCO | 320 | EL | TB | 0001 | F0Z-708711 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 5 | 2 | 0 | 0 | 3.1.4.5.2 | Power & Control Cables
3 | 1 | 4 | 5 | 2 | 1 | 0 | 3.1.5.2.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 5 | 2 | 1 | 1 | 3.1.4.5.2.1.1 | PMR For Power & Control Cables in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MR-0002 | BK-PPL-PEDCO-320-EL-MR-0002 | BK | PPL | PEDCO | 320 | EL | MR | 0002 | F0Z-708712 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 5 | 2 | 2 | 0 | 3.1.5.2.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 5 | 2 | 2 | 1 | 3.1.4.5.2.2.1 | TBE For Power & Control Cables in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-TB-0002 | BK-PPL-PEDCO-320-EL-TB-0002 | BK | PPL | PEDCO | 320 | EL | TB | 0002 | F0Z-708713 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 5 | 3 | 0 | 0 | 3.1.4.5.3 | Cathodic Protection System
3 | 1 | 4 | 5 | 3 | 1 | 0 | 3.1.5.3.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 5 | 3 | 1 | 1 | 3.1.4.5.3.1.1 | PMR For Cathodic Protection System | BK-PPL-PEDCO-320-EL-MR-0003 | BK-PPL-PEDCO-320-EL-MR-0003 | BK | PPL | PEDCO | 320 | EL | MR | 0003 | F0Z-708714 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 5 | 3 | 2 | 0 | 3.1.5.3.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 5 | 3 | 2 | 1 | 3.1.4.5.3.2.1 | TBE For Cathodic Protection System | BK-PPL-PEDCO-320-EL-TB-0003 | BK-PPL-PEDCO-320-EL-TB-0003 | BK | PPL | PEDCO | 320 | EL | TB | 0003 | F0Z-708715 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 5 | 4 | 0 | 0 | 3.1.4.5.4 | Electrical Bulk Items & Earthing
3 | 1 | 4 | 5 | 4 | 1 | 0 | 3.1.5.4.1 | Purchase Material Requisition (PMR)
3 | 1 | 4 | 5 | 4 | 1 | 1 | 3.1.4.5.4.1.1 | PMR For Electrical Bulk Items in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-MR-0004 | BK-PPL-PEDCO-320-EL-MR-0004 | BK | PPL | PEDCO | 320 | EL | MR | 0004 | F0Z-708716 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 4 | 5 | 4 | 2 | 0 | 3.1.5.4.2 | Technical Bid Evaluation (TBE)
3 | 1 | 4 | 5 | 4 | 2 | 1 | 3.1.4.5.4.2.1 | TBE For Electrical Bulk Items in Siahmakan Gas Injection | BK-PPL-PEDCO-320-EL-TB-0004 | BK-PPL-PEDCO-320-EL-TB-0004 | BK | PPL | PEDCO | 320 | EL | TB | 0004 | F0Z-708717 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 5 | 0 | 0 | 0 | 0 | 3.1.5 | Commissioning Engineering
3 | 1 | 5 | 0 | 1 | 0 | 0 | 3.1.5.1 | Procedure/Plan
3 | 1 | 5 | 0 | 1 | 0 | 1 | 3.1.5 | Pre-Commissioning, Commissioning & Startup Procedure | BK-PPL-PEDCO-320-CO-PR-0001 | BK-PPL-PEDCO-320-CO-PR-0001 | BK | PPL | PEDCO | 320 | CO | PR | 0001 | F0Z-708718 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 6 | 0 | 0 | 0 | 0 | 3.1.6 | Field Engineering
3 | 1 | 6 | 0 | 1 | 0 | 0 | 3.1.6.1 | Query
3 | 1 | 6 | 0 | 1 | 0 | 1 | 3.1.6.1.1 | Technical/Site Queries | BK-PPL-PEDCO-320-GE-TQ-0001 | BK-PPL-PEDCO-320-GE-TQ-0001 | BK | PPL | PEDCO | 320 | GE | TQ | 0001 | F7Z-708719 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 6 | 0 | 2 | 0 | 0 | 3.1.6.2 | Dossier
3 | 1 | 6 | 0 | 2 | 0 | 1 | 3.1.6 | As-Built Document Booklets | BK-PPL-PEDCO-320-GE-DO-0001 | BK-PPL-PEDCO-320-GE-DO-0001 | BK | PPL | PEDCO | 320 | GE | DO | 0001 | F0Z-708720 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 7 | 0 | 0 | 0 | 0 | 3.1.7 | Engineering Final Documentation
3 | 1 | 7 | 0 | 1 | 0 | 0 | 3.1.7.1 | Manual
3 | 1 | 7 | 0 | 1 | 0 | 1 | 3.1.7.1.1 | Operating Manual | BK-PPL-PEDCO-320-GE-ML-0001 | BK-PPL-PEDCO-320-GE-ML-0001 | BK | PPL | PEDCO | 320 | GE | ML | 0001 | F0Z-708721 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 7 | 0 | 2 | 0 | 0 | 3.1.7.2 | Dossier
3 | 1 | 7 | 0 | 2 | 0 | 1 | 3.1 | As-Built Document Booklets | BK-PPL-PEDCO-320-GE-DO-0001 | BK-PPL-PEDCO-320-GE-DO-0001 | BK | PPL | [5 empty] | F0Z-708720 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 1 | 7 | 0 | 2 | 0 | 2 | 3.1 | Final Engineering Dossier | BK-PPL-PEDCO-320-GE-DO-0002 | BK-PPL-PEDCO-320-GE-DO-0002 | BK | PPL | PEDCO | 320 | GE | DO | 0002 | F0Z-708722 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 0 | 0 | 0 | 0 | 0 | 3.2 | Package 12- EPC # Compressor Station
3 | 2 | 1 | 0 | 0 | 0 | 0 | 3.2.1 | Basic Design Endorsement
3 | 2 | 1 | 0 | 0 | 0 | 1 | 3.2.1 | Endorsement Report For Basic Design & Scope of Work | BK-GCS-PEDCO-120-GE-RT-0001 | BK-GCS-PEDCO-120-GE-RT-0001 | [7 empty] | - | [43 empty] | Deleted | 2021-07-31 | 0 |  | B00 | IFC | T-0023 | 2021-07-31 | 1400/05/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-176098 | 2021-08-28 | 1400/06/06 | 2021-09-07 | 1400/06/16 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | B00-Reject |  | B00 | IFC | T-0023 | 2021-07-31 | 1400/05/09 | [13 empty] | 1400-2294-176098 | 2021-08-28 | 1400/06/06 | 2021-09-07 | 1400/06/16 | CM | [8 empty] | B00-Reject
3 | 2 | 2 | 0 | 0 | 0 | 0 | 3.2.2 | Value Engineering
3 | 2 | 2 | 0 | 0 | 0 | 1 | 3.2.2 | Value Engineering Study Report | BK-GCS-PEDCO-120-GE-RT-0002 | BK-GCS-PEDCO-120-GE-RT-0002 | BK | GCS | PEDCO | 120 | GE | RT | 0002 | F0Z-708723 | AFD | IFC | 2022-02-15 | 2022-03-10 | 2022-03-15 | 23 | 5 | 28 | IFA | 2022-04-24 | 2022-05-21 | 2022-05-23 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-01 | 0 |  | D01 | IFA | T-0785 | 2022-04-10 | 1400/01/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-GE-RT-0002-D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-68426 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-GE-RT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0531 | 2022-02-01 | 1400/11/12 |  |  |  | BK-SUR-ENG-PCS-00-03282 | 2022-03-02 | 1400/12/11 | CM-C2 | [6 empty] | 1400-2294-443284 | 2022-03-10 | 1400/12/19 | 2022-03-15 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0785 | 2022-04-10 | 1400/01/21 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-GE-RT-0002-D00 | [5 empty] | 1401-2294-68426 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-GE-RT-0002_D00
3 | 2 | 2 | 0 | 0 | 0 | 2 | 3.2.2 | HAZID Report For Compressor Station | BK-GCS-PEDCO-120-GE-RT-0003 | BK-GCS-PEDCO-120-GE-RT-0003 | BK | GCS | PEDCO | 120 | GE | RT | 0003 | F0Z-708724 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 2 | 0 | 0 | 0 | 3 | 3.2.2 | HAZOP Report For Compressor Station | BK-GCS-PEDCO-120-GE-RT-0004 | BK-GCS-PEDCO-120-GE-RT-0004 | BK | GCS | PEDCO | 120 | GE | RT | 0004 | F0Z-708725 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 2 | 0 | 0 | 0 | 4 | 3.2.2 | SIL Report For Compressor Station | BK-GCS-PEDCO-120-GE-RT-0005 | BK-GCS-PEDCO-120-GE-RT-0005 | BK | GCS | PEDCO | 120 | GE | RT | 0005 | F0Z-708726 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 0 | 0 | 0 | 0 | 3.2.3 | Detail Design
3 | 2 | 3 | 1 | 0 | 0 | 0 | 3.2.3.1 | Process
3 | 2 | 3 | 1 | 1 | 0 | 0 | 3.2.3.1.1 | Philosophy
3 | 2 | 3 | 1 | 1 | 0 | 1 | 3.2.3.1.1 | Drainage Philosophy | BK-GCS-PEDCO-120-PR-PH-0001 | BK-GCS-PEDCO-120-PR-PH-0001 | BK | GCS | PEDCO | 120 | PR | PH | 0001 | F0Z-708727 | AFD | IFC | 2021-12-05 | 2021-12-11 | 2021-12-14 | 6 | 3 | 9 | IFA | 2022-02-12 | 2022-03-06 | 2022-03-08 | 22 | 2 | 24 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-21 | 0 |  | D01 | IFA | T-0520 | 2022-01-29 | 1400/11/09 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03179 | 2022-02-22 | 1400/12/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PH-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-436900 | 2022-03-06 | 1400/12/15 | 2022-03-08 | 1400/12/17 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PH-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0262 | 2021-11-21 | 1400/08/30 |  |  |  | BK-SUR-ENG-PCS-00-02227 | 2021-12-07 | 1400/09/16 | CM-C2 | [6 empty] | 1400-2294-312238 | 2021-12-11 | 1400/09/20 | 2021-12-14 | 1400/09/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PH-0001_D00 | [9 empty] | D01 | IFA | T-0520 | 2022-01-29 | 1400/11/09 |  |  |  | BK-SUR-ENG-PCS-00-03179 | 2022-02-22 | 1400/12/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PH-0001_D00 | [5 empty] | 1400-2294-436900 | 2022-03-06 | 1400/12/15 | 2022-03-08 | 1400/12/17 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PH-0001_D00
3 | 2 | 3 | 1 | 1 | 0 | 2 | 3.2.3.1.1 | Control Philosophy | BK-GCS-PEDCO-120-PR-PH-0002 | BK-GCS-PEDCO-120-PR-PH-0002 | BK | GCS | PEDCO | 120 | PR | PH | 0002 | F0Z-708728 | AFD | IFC | 2022-03-06 | 2022-03-13 | 2022-04-01 | 7 | 19 | 26 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-20 | 0 |  | D00 | IFC | T-0612 | 2022-02-20 | 1400/12/01 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03621 | 2022-03-15 | 1400/12/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445277 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | CM | 0 | 1400-2294-447187 | 2022-03-13 | 1400/12/22 | 2022-04-01 | 1401/01/14 | CM | 0 | 0 |  | D00 | IFC | T-0612 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-PCS-00-03621 | 2022-03-15 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445277 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | CM |  | 1400-2294-447187 | 2022-03-13 | 1400/12/22 | 2022-04-01 | 1401/01/14 | CM
3 | 2 | 3 | 1 | 1 | 0 | 3 | 3.2.3.1.1 | Flare,Blow Down And Relief Philosophy | BK-GCS-PEDCO-120-PR-PH-0003 | BK-GCS-PEDCO-120-PR-PH-0003 | BK | GCS | PEDCO | 120 | PR | PH | 0003 | F0Z-708729 | AFD | IFC | 2021-12-05 | 2021-12-11 | 2021-12-14 | 6 | 3 | 9 | IFA | 2022-05-09 | 2022-05-22 | 2022-05-23 | 13 | 1 | 14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-21 | 0 |  | D01 | IFA | T-0862 | 2022-04-25 | 1401/02/06 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04334 | 2022-05-21 | 1401/02/31 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PH-0003_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70050 | 2022-05-22 | 1401/02/31 | 2022-05-23 | 1401/03/02 | AP | NISOC-CRS-BK-GCS-PEDCO-000-PR-PH-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0262 | 2021-11-21 | 1400/08/30 |  |  |  | BK-SUR-ENG-PCS-00-02227 | 2021-12-07 | 1400/09/16 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-000-PR-PH-0001_D00 | [5 empty] | 1400-2294-312238 | 2021-12-11 | 1400/09/20 | 2021-12-14 | 1400/09/23 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-PH-0001_D00 | [9 empty] | D01 | IFA | T-0862 | 2022-04-25 | 1401/02/06 |  |  |  | BK-SUR-ENG-PCS-01-04334 | 2022-05-21 | 1401/02/31 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PH-0003_D00 | [5 empty] | 1401-2294-70050 | 2022-05-22 | 1401/02/31 | 2022-05-23 | 1401/03/02 | AP | NISOC-CRS-BK-GCS-PEDCO-000-PR-PH-0003_D00
3 | 2 | 3 | 1 | 1 | 0 | 4 | 3.2.3.1.1 | Isolation Philosophy | BK-GCS-PEDCO-120-PR-PH-0004 | BK-GCS-PEDCO-120-PR-PH-0004 | BK | GCS | PEDCO | 120 | PR | PH | 0004 | F0Z-708730 | AFD | IFC | 2021-12-05 | 2022-03-21 | 2021-12-14 | 106 | -97 | 9 | IFA | 2022-05-02 | 2022-05-12 | 2022-05-16 | 10 | 4 | 14 | AFD | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-21 | 2022-05-22 |  | D02 | AFD | T-0945 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0262 | 2021-11-21 | 1400/08/30 |  |  |  | BK-SUR-ENG-PCS-00-02227 | 2021-12-07 | 1400/09/16 | CM-C2 | [6 empty] | 1400-2294-312238 | 2021-12-11 | 1400/09/20 | 2021-12-14 | 1400/09/23 | CM | NISOC-CRS-BK-GNRAL-PEDCO-000-PR-PH-0004_D00 | 00/2294/419621 | 2022-03-21 | 1400/12/02 |  |  | CM |  |  |  | D01 | IFA | T-0838 | 2022-04-18 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04189 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D00 | [5 empty] | 1401-2294-59548 | 2022-05-12 | 1400/02/22 | 2022-05-16 | 1400/02/26 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D00 | [9 empty] | D02 | AFD | T-0945 | 2022-05-22 | 1401/03/01
3 | 2 | 3 | 1 | 1 | 0 | 5 | 3.2.3.1.1 | ESD Philosophy | BK-GCS-PEDCO-120-PR-PH-0005 | BK-GCS-PEDCO-120-PR-PH-0005 | BK | GCS | PEDCO | 120 | PR | PH | 0005 | F0Z-708731 | AFD | IFC | 2022-03-06 | 2022-03-13 | 2022-04-01 | 7 | 19 | 26 | IFA | 2022-06-11 | 0 | 0 | -44723 | 0 | -44723 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-20 | 0 |  | D01 | IFA | T-1010 | 2022-05-28 | 1401/03/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PH-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-PH-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0612 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-PCS-00-03621 | 2022-03-15 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445277 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | CM |  | 1400-2294-447187 | 2022-03-13 | 1400/12/22 | 2022-04-01 | 1401/01/14 | CM |  |  |  | D01 | IFA | T-1010 | 2022-05-28 | 1401/03/07 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PH-0005_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-PH-0005_D00
3 | 2 | 3 | 1 | 2 | 0 | 0 | 3.2.3.1.2 | Procedure
3 | 2 | 3 | 1 | 2 | 0 | 1 | 3.2.3.1.2 | Chemical Regeneration Procedure | BK-GCS-PEDCO-120-PR-PR-0001 | BK-GCS-PEDCO-120-PR-PR-0001 | BK | GCS | PEDCO | 120 | PR | PR | 0001 | F0Z-708732 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 1 | 2 | 0 | 2 | 3.2.3.1.2 | Startup And Shutdown Procedure | BK-GCS-PEDCO-120-PR-PR-0002 | BK-GCS-PEDCO-120-PR-PR-0002 | BK | GCS | PEDCO | 120 | PR | PR | 0002 | F0Z-708733 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 1 | 3 | 0 | 0 | 3.2.3.1.3 | Description
3 | 2 | 3 | 1 | 3 | 0 | 1 | 3.2.3.1.3 | Process & Utility Description | BK-GCS-PEDCO-120-PR-DP-0001 | BK-GCS-PEDCO-120-PR-DP-0001 | BK | GCS | PEDCO | 120 | PR | DP | 0001 | F0Z-708734 | AFD | IFC | 44626 | 44633 | 44652 | 7 | 19 | 26 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-20 | 0 |  | D00 | IFC | T-0612 | 2022-02-20 | 1400/12/01 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-03621 | 2022-03-15 | 1400/12/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445277 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | CM | 0 | 1400-2294-447187 | 2022-03-13 | 1400/12/22 | 2022-04-01 | 1401/01/14 | CM | 0 | 0 |  | D00 | IFC | T-0612 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-PCS-00-03621 | 2022-03-15 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445277 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | CM |  | 1400-2294-447187 | 2022-03-13 | 1400/12/22 | 2022-04-01 | 1401/01/14 | CM
3 | 2 | 3 | 1 | 4 | 0 | 0 | 3.2.3.1.4 | Duty Specification
3 | 2 | 3 | 1 | 4 | 0 | 1 | 3.2.3.1.4 | Duty Specification For Gas Dehydration Package | BK-GCS-PEDCO-120-PR-SP-0001 | BK-GCS-PEDCO-120-PR-SP-0001 | BK | GCS | PEDCO | 120 | PR | SP | 0001 | F0Z-708735 | AFD | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 | IFC | 2021-12-22 | 2021-12-26 | 2021-12-28 | 4 | 2 | 6 | IFA | 2022-02-05 | 2022-03-10 | 2022-03-13 | 33 | 3 | 36 | IFA | 2022-05-28 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-08 | 0 |  | D03 | IFA | T-0940 | 2022-05-14 | 1401/02/24 | T-0940 | 2022-05-14 | 1401/02/24 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0056 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-PCS-00-01415 | 2021-08-28 | 1400/06/06 | CM-C3 | [6 empty] | 1400/2290/181042 | 2021-08-31 | 1400/06/09 | 2021-09-08 | 1400/06/17 | RJ | [10 empty] | D01 | IFC | T-0324 | 2021-12-08 | 1400/09/17 |  |  |  | BK-SUR-ENG-PCS-00-02423 | 2021-12-26 | 1400/10/05 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D00 | [5 empty] | 1400-2294-336102 | 2021-12-26 | 1400/10/05 | 2021-12-28 | 1400/10/07 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D00 | [9 empty] | D02 | IFA | T-0486 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-PCS-00-03083 | 2022-02-16 | 1400/11/27 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D01 | [5 empty] | 1400-2294-412912 | 2022-02-16 | 1400/11/27 | 2022-02-22 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D01 | 1400-2294-443242 | 2022-03-10 | 1400/12/19 | 2022-03-13 | 1400/12/22 | CM |  |  |  | D03 | IFA | T-0940 | 2022-05-14 | 1401/02/24 | T-0940 | 2022-05-14 | 1401/02/24 |  |  |  |  | PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0001_D02
3 | 2 | 3 | 1 | 4 | 0 | 2 | 3.2.3.1.4 | Duty Specification for Instrument/Plant Air & Nitrogen Packages | BK-GCS-PEDCO-120-PR-SP-0002 | BK-GCS-PEDCO-120-PR-SP-0002 | BK | GCS | PEDCO | 120 | PR | SP | 0002 | F0Z-708736 | AFD | IFC | 2022-01-11 | 2022-01-01 | 2022-01-04 | -10 | 3 | -7 | IFA | 2022-03-23 | 0 | 0 | -44643 | 0 | -44643 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-28 | 0 |  | D01 | IFA | T-0702 | 2022-03-09 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03818 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0390 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02559 | 2022-01-04 | 1400/10/14 | CM-C3 | [6 empty] | 1400-2294-344439 | 2022-01-01 | 1400/10/11 | 2022-01-04 | 1400/10/14 | CM | [10 empty] | D01 | IFA | T-0702 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03818 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0002_D00
3 | 2 | 3 | 1 | 4 | 0 | 3 | 3.2.3.1.4 | Duty Specification for LP Flare Package | BK-GCS-PEDCO-120-PR-SP-0003 | BK-GCS-PEDCO-120-PR-SP-0003 | BK | GCS | PEDCO | 120 | PR | SP | 0003 | F0Z-708737 | AFD | IFC | 2022-03-23 | 2022-04-29 | 2022-05-01 | 37 | 2 | 39 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-09 | 0 |  | D00 | IFC | T-0703 | 2022-03-09 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | 1401/01/23 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43236 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0703 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | 1401/01/23 | CM-C3 | [6 empty] | 1401-2294-43236 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM
3 | 2 | 3 | 1 | 4 | 0 | 4 | 3.2.3.1.4 | Duty Specification for Chemical Injection Package | BK-GCS-PEDCO-120-PR-SP-0004 | BK-GCS-PEDCO-120-PR-SP-0004 | BK | GCS | PEDCO | 120 | PR | SP | 0004 | F0Z-708738 | AFD | IFC | 2022-03-23 | 2022-04-29 | 2022-05-01 | 37 | 2 | 39 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-09 | 0 |  | D00 | IFC | T-0703 | 2022-03-09 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | 1401/01/23 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43236 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0703 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | 1401/01/23 | CM-C3 | [6 empty] | 1401-2294-43236 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM
3 | 2 | 3 | 1 | 5 | 0 | 0 | 3.2.3.1.5 | Calculation
3 | 2 | 3 | 1 | 5 | 0 | 1 | 3.2.3.1.5 | Calculation Note For Pumps | BK-GCS-PEDCO-120-PR-CN-0001 | BK-GCS-PEDCO-120-PR-CN-0001 | BK | GCS | PEDCO | 120 | PR | CN | 0001 | F0Z-708739 | AFD | IFC | 2021-12-27 | 2022-01-03 | 2022-01-05 | 7 | 2 | 9 | IFA | 2022-02-12 | 2022-03-06 | 2022-03-08 | 22 | 2 | 24 | IFA | 2022-04-09 | 2022-05-04 | 2022-05-08 | 25 | 4 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 0 |  | D02 | IFA | T-0744 | 2022-03-26 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03974 | 2022-04-18 | 1401/01/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0335 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-PCS-00-02475 | 2021-12-28 | 1400/10/07 | CM-C3 | [6 empty] | 1400-2294-348115 | 2022-01-03 | 1400/10/13 | 2022-01-05 | 1400/10/15 | CM | [10 empty] | D01 | IFA | T-0520 | 2022-01-29 | 1400/11/09 |  |  |  | BK-SUR-ENG-PCS-00-03179 | 2022-02-22 | 1400/12/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D00 | [5 empty] | 1400-2294-436900 | 2022-03-06 | 1400/12/15 | 2022-03-08 | 1400/12/17 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D00 | [9 empty] | D02 | IFA | T-0744 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-PCS-01-03974 | 2022-04-18 | 1401/01/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D01 | [5 empty] | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D01
3 | 2 | 3 | 1 | 5 | 0 | 2 | 3.2.3.1.5 | Calculation Note For Drum Sizing | BK-GCS-PEDCO-120-PR-CN-0002 | BK-GCS-PEDCO-120-PR-CN-0002 | BK | GCS | PEDCO | 120 | PR | CN | 0002 | F0Z-708740 | AFD | IFC | 2021-10-10 | 2021-10-31 | 2021-11-06 | 21 | 6 | 27 | IFA | 2021-11-23 | 2021-11-27 | 2021-11-29 | 4 | 2 | 6 | IFA | 2022-01-11 | 2022-01-26 | 2022-01-29 | 15 | 3 | 18 | IFA | 2022-05-02 | 2022-05-12 | 2022-05-16 | 10 | 4 | 14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D03 | IFA | T-0838 | 2022-04-18 | 1401/01/29 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04189 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59548 | 2022-05-12 | 1400/02/22 | 2022-05-16 | 1400/02/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0122 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01824 | 2021-10-23 | 1400/08/01 | C4-RJ | [6 empty] | 1400-2294-255291 | 2021-10-31 | 1400/08/09 | 2021-11-06 | 1400/08/15 | CM | [10 empty] | D01 | IFA | T-0221 | 2021-11-09 | 1400/08/18 |  |  |  | BK-SUR-ENG-PCS-00-02145 | 2021-11-29 | 1400/09/08 | C4-RJ | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0002-D00 | [5 empty] | 1400-2290-293081 | 2021-11-27 | 1400/09/06 | 2021-11-29 | 1400/09/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002-D00 | [9 empty] | D02 | IFA | T-0391 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02636 | 2022-01-11 | 1400/10/21 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D01 | [5 empty] | 1400-2294-383221 | 2022-01-26 | 1400/11/06 | 2022-01-29 | 1400/11/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D01 | [9 empty] | D03 | IFA | T-0838 | 2022-04-18 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04189 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D02 | [5 empty] | 1401-2294-59548 | 2022-05-12 | 1400/02/22 | 2022-05-16 | 1400/02/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0002_D02
3 | 2 | 3 | 1 | 5 | 0 | 3 | 3.2.3.1.5 | Calculation Note For Flow Element Sizing | BK-GCS-PEDCO-120-PR-CN-0003 | BK-GCS-PEDCO-120-PR-CN-0003 | BK | GCS | PEDCO | 120 | PR | CN | 0003 | F0Z-708741 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 1 | 5 | 0 | 4 | 3.2.3.1.5 | Calculation Note For PSV Sizing | BK-GCS-PEDCO-120-PR-CN-0004 | BK-GCS-PEDCO-120-PR-CN-0004 | BK | GCS | PEDCO | 120 | PR | CN | 0004 | F0Z-708742 | AFD | IFC | 2021-10-10 | 2021-10-31 | 2021-11-06 | 21 | 6 | 27 | IFA | 2022-02-09 | 2022-03-06 | 2022-03-08 | 25 | 2 | 27 | IFA | 2022-05-30 | 0 | 0 | -44711 | 0 | -44711 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0960 | 2022-05-16 | 1401/02/26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0122 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01824 | 2021-10-23 | 1400/08/01 | C4-RJ | [6 empty] | 1400-2294-255291 | 2021-10-31 | 1400/08/09 | 2021-11-06 | 1400/08/15 | CM | [10 empty] | D01 | IFA | T-0516 | 2022-01-26 | 1400/11/06 |  |  |  | BK-SUR-ENG-PCS-00-03137 | 2022-02-20 | 1400/12/01 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D00 | [5 empty] | 1400-2294-436867 | 2022-03-06 | 1400/12/15 | 2022-03-08 | 1400/12/17 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D00 | [9 empty] | D02 | IFA | T-0960 | 2022-05-16 | 1401/02/26 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0004_D01
3 | 2 | 3 | 1 | 5 | 0 | 5 | 3.2.3.1.5 | Calculation Note For Line Sizing | BK-GCS-PEDCO-120-PR-CN-0005 | BK-GCS-PEDCO-120-PR-CN-0005 | BK | GCS | PEDCO | 120 | PR | CN | 0005 | F0Z-708743 | AFD | IFC | 2021-10-10 | 2021-10-31 | 2021-11-06 | 21 | 6 | 27 | IFA | 2022-01-19 | 2022-02-12 | 2022-02-22 | 24 | 10 | 34 | IFA | 2022-05-28 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0940 | 2022-05-14 | 1401/02/24 | T-0940 | 2022-05-14 | 1401/02/24 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0122 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01824 | 2021-10-23 | 1400/08/01 | C4-RJ | [6 empty] | 1400-2294-255291 | 2021-10-31 | 1400/08/09 | 2021-11-06 | 1400/08/15 | CM | [10 empty] | D01 | IFA | T-0433 | 2022-01-05 | 1400/10/15 |  |  |  | BK-SUR-ENG-PCS-00-02769 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0005_D00 | [5 empty] | 1400-2294-405206 | 2022-02-12 | 1400/11/23 | 2022-02-22 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0005_D00 | [9 empty] | D02 | IFA | T-0940 | 2022-05-14 | 1401/02/24 | T-0940 | 2022-05-14 | 1401/02/24 |  |  |  |  | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0005_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0005_D01
3 | 2 | 3 | 1 | 5 | 0 | 6 | 3.2.3.1.5 | Calculation Note For Control Valve Sizing | BK-GCS-PEDCO-120-PR-CN-0006 | BK-GCS-PEDCO-120-PR-CN-0006 | BK | GCS | PEDCO | 120 | PR | CN | 0006 | F0Z-708744 | AFD | IFC | 2021-10-10 | 2021-10-31 | 2021-11-06 | 21 | 6 | 27 | IFA | 2022-01-19 | 2022-02-12 | 2022-02-22 | 24 | 10 | 34 | IFA | 2022-05-23 | 0 | 0 | -44704 | 0 | -44704 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0917 | 2022-05-09 | 1401/02/19 | T-0917 | 2022-05-09 | 1401/02/19 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0122 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01824 | 2021-10-23 | 1400/08/01 | C4-RJ | [6 empty] | 1400-2294-255291 | 2021-10-31 | 1400/08/09 | 2021-11-06 | 1400/08/15 | CM | [10 empty] | D01 | IFA | T-0433 | 2022-01-05 | 1400/10/15 |  |  |  | BK-SUR-ENG-PCS-00-02769 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0006_D00 | [5 empty] | 1400-2294-405206 | 2022-02-12 | 1400/11/23 | 2022-02-22 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0006_D00 | [9 empty] | D02 | IFA | T-0917 | 2022-05-09 | 1401/02/19 | T-0917 | 2022-05-09 | 1401/02/19 |  |  |  |  | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0006_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0006_D01
3 | 2 | 3 | 1 | 5 | 0 | 7 | 3.2.3.1.5 | Calculation Note For Depressurizing (Min. Design Temperature ) | BK-GCS-PEDCO-120-PR-CN-0007 | BK-GCS-PEDCO-120-PR-CN-0007 | BK | GCS | PEDCO | 120 | PR | CN | 0007 | F0Z-708745 | AFD | IFC | 2021-12-27 | 2022-01-08 | 2022-01-10 | 12 | 2 | 14 | IFA | 2022-05-09 | 2022-05-22 | 2022-05-23 | 13 | 1 | 14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 0 |  | D01 | IFA | T-0862 | 2022-04-25 | 1401/02/06 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04334 | 2022-05-21 | 1401/02/31 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0007_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70050 | 2022-05-22 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0343 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-PCS-00-02501 | 2022-01-01 | 1400/10/11 | CM-C3 | [6 empty] | 1400-2294-354591 | 2022-01-08 | 1400/10/18 | 2022-01-10 | 1400/10/20 | CM | [10 empty] | D01 | IFA | T-0862 | 2022-04-25 | 1401/02/06 |  |  |  | BK-SUR-ENG-PCS-01-04334 | 2022-05-21 | 1401/02/31 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0007_D00 | [5 empty] | 1401-2294-70050 | 2022-05-22 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0007_D00
3 | 2 | 3 | 1 | 6 | 0 | 0 | 3.2.3.1.6 | Data Sheets
3 | 2 | 3 | 1 | 6 | 1 | 0 | 3.2.1.6.1 | Fixed Equipment
3 | 2 | 3 | 1 | 6 | 1 | 1 | 3.2.3.1.6.1.1 | Process Data Sheets For Inlet Gas K.O. Drum | BK-GCS-PEDCO-120-PR-DT-0001 | BK-GCS-PEDCO-120-PR-DT-0001 | BK | GCS | PEDCO | 120 | PR | DT | 0001 | F0Z-708746 | AFC | IFC | 2021-11-24 | 2021-11-29 | 2021-12-01 | 5 | 2 | 7 | IFA | 2022-01-11 | 2022-01-16 | 2022-01-17 | 5 | 1 | 6 | IFA | 2022-05-02 | 2022-05-21 | 2022-05-23 | 19 | 2 | 21 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D02 | IFA | T-0839 | 2022-04-18 | 1401/01/29 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-68573 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0227 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02128 | 2021-11-28 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2290-296926 | 2021-11-29 | 1400/09/08 | 2021-12-01 | 1400/09/10 | CM | [10 empty] | D01 | IFA | T-0392 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02643 | 2022-01-11 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D00 | [5 empty] | 1400-2294-365761 | 2022-01-16 | 1400/10/26 | 2022-01-17 | 1400/10/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D00 | [9 empty] | D02 | IFA | T-0839 | 2022-04-18 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D01 | [5 empty] | 1401-2294-68573 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D01
3 | 2 | 3 | 1 | 6 | 1 | 2 | 3.2.3.1.6.1.2 | Process Data Sheets For 1st Stage G.C. Suction Drums | BK-GCS-PEDCO-120-PR-DT-0002 | BK-GCS-PEDCO-120-PR-DT-0002 | BK | GCS | PEDCO | 120 | PR | DT | 0002 | F0Z-708747 | AFC | IFC | 2021-11-24 | 2021-11-29 | 2021-12-01 | 5 | 2 | 7 | IFA | 2022-01-11 | 2022-01-16 | 2022-01-16 | 5 | 0 | 5 | IFA | 2022-05-02 | 2022-05-21 | 2022-05-23 | 19 | 2 | 21 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D02 | IFA | T-0839 | 2022-04-18 | 1401/01/29 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-68573 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0227 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02128 | 2021-11-28 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2290-296926 | 2021-11-29 | 1400/09/08 | 2021-12-01 | 1400/09/10 | CM | [10 empty] | D01 | IFA | T-0395 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02644 | 2022-01-11 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D00 | [5 empty] | 1400-2294-365755 | 2022-01-16 | 1400/10/26 | 2022-01-16 | 1400/10/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D00 | [9 empty] | D02 | IFA | T-0839 | 2022-04-18 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D01 | [5 empty] | 1401-2294-68573 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D01
3 | 2 | 3 | 1 | 6 | 1 | 3 | 3.2.3.1.6.1.3 | Process Data Sheets For 1st Stage Gas Air Coolers | BK-GCS-PEDCO-120-PR-DT-0003 | BK-GCS-PEDCO-120-PR-DT-0003 | BK | GCS | PEDCO | 120 | PR | DT | 0003 | F0Z-708748 | AFC | IFC | 2021-11-21 | 2021-11-18 | 2021-11-27 | -3 | 9 | 6 | IFA | 2021-12-21 | 0 | 0 | -44551 | 0 | -44551 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-07 | 0 |  | D01 | IFA | T-0302 | 2021-12-07 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02395 | 2021-12-21 | 1400/09/30 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0215 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-PCS-00-02121 | 2021-11-27 | 1400/09/06 | CM-C3 | [6 empty] | 1400-2294-281414 | 2021-11-18 | 1400/08/27 | 2021-11-27 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0302 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-PCS-00-02395 | 2021-12-21 | 1400/09/30 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0003_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0003_D00
3 | 2 | 3 | 1 | 6 | 1 | 4 | 3.2.3.1.6.1.4 | Process Data Sheets For 2nd Stage G.C. Suction Drums | BK-GCS-PEDCO-120-PR-DT-0004 | BK-GCS-PEDCO-120-PR-DT-0004 | BK | GCS | PEDCO | 120 | PR | DT | 0004 | F0Z-708749 | AFC | IFC | 2021-11-24 | 2021-11-29 | 2021-12-01 | 5 | 2 | 7 | IFA | 2022-01-11 | 2022-01-16 | 2022-01-16 | 5 | 0 | 5 | IFA | 2022-05-02 | 2022-05-21 | 2022-05-23 | 19 | 2 | 21 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D02 | IFA | T-0839 | 2022-04-18 | 1401/01/29 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-68573 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0227 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02128 | 2021-11-28 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2290-296926 | 2021-11-29 | 1400/09/08 | 2021-12-01 | 1400/09/10 | CM | [10 empty] | D01 | IFA | T-0395 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02644 | 2022-01-11 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D00 | [5 empty] | 1400-2294-365755 | 2022-01-16 | 1400/10/26 | 2022-01-16 | 1400/10/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D00 | [9 empty] | D02 | IFA | T-0839 | 2022-04-18 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D01 | [5 empty] | 1401-2294-68573 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0004_D01
3 | 2 | 3 | 1 | 6 | 1 | 5 | 3.2.3.1.6.1.5 | Process Data Sheets For 2nd Stage Gas Air Coolers | BK-GCS-PEDCO-120-PR-DT-0005 | BK-GCS-PEDCO-120-PR-DT-0005 | BK | GCS | PEDCO | 120 | PR | DT | 0005 | F0Z-708750 | AFC | IFC | 2021-11-21 | 2021-11-18 | 2021-11-27 | -3 | 9 | 6 | IFA | 2021-12-21 | 0 | 0 | -44551 | 0 | -44551 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-07 | 0 |  | D01 | IFA | T-0302 | 2021-12-07 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02395 | 2021-12-21 | 1400/09/30 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0215 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-PCS-00-02121 | 2021-11-27 | 1400/09/06 | CM-C3 | [6 empty] | 1400-2294-281414 | 2021-11-18 | 1400/08/27 | 2021-11-27 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0302 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-PCS-00-02395 | 2021-12-21 | 1400/09/30 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D00
3 | 2 | 3 | 1 | 6 | 1 | 6 | 3.2.3.1.6.1.6 | Process Data Sheets For Discharge Gas K.O. Drum | BK-GCS-PEDCO-120-PR-DT-0006 | BK-GCS-PEDCO-120-PR-DT-0006 | BK | GCS | PEDCO | 120 | PR | DT | 0006 | F0Z-708751 | AFC | IFC | 2021-11-24 | 2021-11-29 | 2021-12-01 | 5 | 2 | 7 | IFA | 2022-01-11 | 2022-01-16 | 2022-01-16 | 5 | 0 | 5 | IFA | 2022-05-02 | 2022-05-21 | 2022-05-23 | 19 | 2 | 21 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D02 | IFA | T-0839 | 2022-04-18 | 1401/01/29 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-68573 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0227 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02128 | 2021-11-28 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2290-296926 | 2021-11-29 | 1400/09/08 | 2021-12-01 | 1400/09/10 | CM | [10 empty] | D01 | IFA | T-0395 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02644 | 2022-01-11 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D00 | [5 empty] | 1400-2294-365755 | 2022-01-16 | 1400/10/26 | 2022-01-16 | 1400/10/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D00 | [9 empty] | D02 | IFA | T-0839 | 2022-04-18 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D01 | [5 empty] | 1401-2294-68573 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D01
3 | 2 | 3 | 1 | 6 | 1 | 7 | 3.2.3.1.6.1.7 | Process Data Sheets For Diesel Oil Drum | BK-GCS-PEDCO-120-PR-DT-0007 | BK-GCS-PEDCO-120-PR-DT-0007 | BK | GCS | PEDCO | 120 | PR | DT | 0007 | F0Z-708752 | AFC | IFC | 2021-11-24 | 2021-11-29 | 2021-12-01 | 5 | 2 | 7 | IFA | 2022-01-12 | 2022-01-17 | 2022-01-23 | 5 | 6 | 11 | IFA | 2022-05-02 | 2022-05-21 | 2022-05-23 | 19 | 2 | 21 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D02 | IFA | T-0839 | 2022-04-18 | 1401/01/29 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-68573 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0227 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02128 | 2021-11-28 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2290-296926 | 2021-11-29 | 1400/09/08 | 2021-12-01 | 1400/09/10 | CM | [10 empty] | D01 | IFA | T-0404 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02657 | 2022-01-12 | 1400/10/22 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D00 | [5 empty] | 1400-2294-368480 | 2022-01-17 | 1400/10/27 | 2022-01-23 | 1400/11/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D00 | [9 empty] | D02 | IFA | T-0839 | 2022-04-18 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D01 | [5 empty] | 1401-2294-68573 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D01
3 | 2 | 3 | 1 | 6 | 1 | 8 | 3.2.3.1.6.1.8 | Process Data Sheets For Instrument Air Receiver | BK-GCS-PEDCO-120-PR-DT-0008 | BK-GCS-PEDCO-120-PR-DT-0008 | BK | GCS | PEDCO | 120 | PR | DT | 0008 | F0Z-708753 | AFC | IFC | 2021-11-24 | 2021-11-29 | 2021-12-01 | 5 | 2 | 7 | IFA | 2022-01-12 | 2022-01-17 | 2022-01-23 | 5 | 6 | 11 | IFA | 2022-05-02 | 2022-05-21 | 2022-05-23 | 19 | 2 | 21 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D02 | IFA | T-0839 | 2022-04-18 | 1401/01/29 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-68573 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0227 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02128 | 2021-11-28 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2290-296926 | 2021-11-29 | 1400/09/08 | 2021-12-01 | 1400/09/10 | CM | [10 empty] | D01 | IFA | T-0404 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02657 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D00 | [5 empty] | 1400-2294-368480 | 2022-01-17 | 1400/10/27 | 2022-01-23 | 1400/11/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D00 | [9 empty] | D02 | IFA | T-0839 | 2022-04-18 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D01 | [5 empty] | 1401-2294-68573 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0008_D01
3 | 2 | 3 | 1 | 6 | 1 | 9 | 3.2.3.1.6.1.9 | Process Data Sheets For Nitrogen Receiver | BK-GCS-PEDCO-120-PR-DT-0009 | BK-GCS-PEDCO-120-PR-DT-0009 | BK | GCS | PEDCO | 120 | PR | DT | 0009 | F0Z-708754 | AFC | IFC | 2021-11-24 | 0 | 0 | -44524 | 0 | -44524 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | 1400/09/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | 1400/09/09 | CM-C3
3 | 2 | 3 | 1 | 6 | 1 | 10 | 3.2.3.1.6.1.10 | Process Data Sheets For Close Drain Drum | BK-GCS-PEDCO-120-PR-DT-0010 | BK-GCS-PEDCO-120-PR-DT-0010 | BK | GCS | PEDCO | 120 | PR | DT | 0010 | F0Z-708755 | AFC | IFC | 2021-11-24 | 0 | 0 | -44524 | 0 | -44524 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | 1400/09/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | 1400/09/09 | CM-C3
3 | 2 | 3 | 1 | 6 | 1 | 11 | 3.2.3.1.6.1.11 | Process Data Sheets For Elevated Potable Water Tank | BK-GCS-PEDCO-120-PR-DT-0011 | BK-GCS-PEDCO-120-PR-DT-0011 | BK | GCS | PEDCO | 120 | PR | DT | 0011 | F0Z-708756 | AFC | IFC | 2021-11-24 | 0 | 0 | -44524 | 0 | -44524 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | 1400/09/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | 1400/09/09 | CM-C3
3 | 2 | 3 | 1 | 6 | 1 | 12 | 3.2.3.1.6.1.12 | Process Data Sheets For Flare K.O. Drum | BK-GCS-PEDCO-120-PR-DT-0012 | BK-GCS-PEDCO-120-PR-DT-0012 | BK | GCS | PEDCO | 120 | PR | DT | 0012 | F0Z-708757 | AFC | IFC | 2021-11-24 | 0 | 0 | -44524 | 0 | -44524 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | 1400/09/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | 1400/09/09 | CM-C3
3 | 2 | 3 | 1 | 6 | 1 | 13 | 3.2.3.1.6.1.13 | Process Data Sheets For Fuel Gas K.O. Drum | BK-GCS-PEDCO-120-PR-DT-0013 | BK-GCS-PEDCO-120-PR-DT-0013 | BK | GCS | PEDCO | 120 | PR | DT | 0013 | F0Z-708758 | AFC | IFC | 2021-11-24 | 0 | 0 | -44524 | 0 | -44524 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | 1400/09/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | 1400/09/09 | CM-C3
3 | 2 | 3 | 1 | 6 | 1 | 14 | 3.2.3.1.6.1.14 | Process Data Sheets For Slug Catcher | BK-GCS-PEDCO-120-PR-DT-0014 | BK-GCS-PEDCO-120-PR-DT-0014 | BK | GCS | PEDCO | 120 | PR | DT | 0014 | F0Z-708759 | AFC | IFC | 2021-11-24 | 0 | 0 | -44524 | 0 | -44524 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | 1400/09/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | 1400/09/09 | CM-C3
3 | 2 | 3 | 1 | 6 | 1 | 15 | 3.2.3.1.6.1.15 | Process Data Sheets For Degassing Vessel | BK-GCS-PEDCO-120-PR-DT-0015 | BK-GCS-PEDCO-120-PR-DT-0015 | BK | GCS | PEDCO | 120 | PR | DT | 0015 | F0Z-708760 | AFC | IFC | 2021-11-24 | 0 | 0 | -44524 | 0 | -44524 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-10 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | 1400/09/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0228 | 2021-11-10 | 1400/08/19 |  |  |  | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | 1400/09/09 | CM-C3
3 | 2 | 3 | 1 | 6 | 1 | 16 | 3.2.3.1.6.1.16 | Process Data Sheets For Lean Glycol Storage Tank | BK-GCS-PEDCO-120-PR-DT-0016 | BK-GCS-PEDCO-120-PR-DT-0016 | BK | GCS | PEDCO | 120 | PR | DT | 0016 | F0Z-708761 | AFC | IFC | 2021-12-11 | 0 | 0 | -44541 | 0 | -44541 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-27 | 0 |  | D00 | IFC | T-0271 | 2021-11-27 | 1400/09/06 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02232 | 2021-12-08 | 1400/09/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0271 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-PCS-00-02232 | 2021-12-08 | 1400/09/17 | CM-C3
3 | 2 | 3 | 1 | 6 | 1 | 17 | 3.2.3.1.6.1.17 | Process Data Sheets For Slug Storage Tank | BK-GCS-PEDCO-120-PR-DT-0018 | BK-GCS-PEDCO-120-PR-DT-0018 | BK | GCS | PEDCO | 120 | PR | DT | 0018 | F0Z-708762 | AFC | IFC | 2021-12-11 | 0 | 0 | -44541 | 0 | -44541 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-27 | 0 |  | D00 | IFC | T-0271 | 2021-11-27 | 1400/09/06 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02232 | 2021-12-08 | 1400/09/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0271 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-PCS-00-02232 | 2021-12-08 | 1400/09/17 | CM-C3
3 | 2 | 3 | 1 | 6 | 1 | 18 | 3.2.3.1.6.1.18 | Process Data Sheets For Glycol Sump Drum | BK-GCS-PEDCO-120-PR-DT-0019 | BK-GCS-PEDCO-120-PR-DT-0019 | BK | GCS | PEDCO | 120 | PR | DT | 0019 | F0Z-708763 | AFC | IFC | 2022-01-11 | 2022-01-16 | 2022-01-23 | 5 | 7 | 12 | IFA | 2022-05-02 | 2022-05-21 | 2022-05-23 | 19 | 2 | 21 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-28 | 0 |  | D01 | IFA | T-0839 | 2022-04-18 | 1401/01/29 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0019_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-68573 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0019_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0396 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02645 | 2022-01-11 | 1400/10/22 | CM-C3 | [6 empty] | 1400-2294-366632 | 2022-01-16 | 1400/10/26 | 2022-01-23 | 1400/11/03 | CM | [10 empty] | D01 | IFA | T-0839 | 2022-04-18 | 1401/01/29 |  |  |  | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0019_D00 | [5 empty] | 1401-2294-68573 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0019_D00
3 | 2 | 3 | 1 | 6 | 2 | 0 | 3.2.1.6.2 | Rotary Equipment
3 | 2 | 3 | 1 | 6 | 2 | 1 | 3.2.3.1.6.2.1 | Process Data Sheets For Slug Pumps | BK-GCS-PEDCO-120-PR-DT-0020 | BK-GCS-PEDCO-120-PR-DT-0020 | BK | GCS | PEDCO | 120 | PR | DT | 0020 | F0Z-708764 | AFC | IFC | 2021-12-12 | 2021-12-11 | 2022-02-13 | -1 | 64 | 63 | IFC | 2022-04-10 | 2022-05-07 | 2022-05-09 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-27 | 0 |  | D01 | IFC | T-0754 | 2022-03-27 | 1401/01/07 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03942 | 2022-04-17 | 1401/01/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0020_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-49829 | 2022-05-07 | 1401/02/17 | 2022-05-09 | 1401/02/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0020_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0276 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02298 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-313161 | 2021-12-11 | 1400/09/20 | 2022-02-13 | 1400/11/24 | RJ | [10 empty] | D01 | IFC | T-0754 | 2022-03-27 | 1401/01/07 |  |  |  | BK-SUR-ENG-PCS-01-03942 | 2022-04-17 | 1401/01/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0020_D00 | [5 empty] | 1401-2294-49829 | 2022-05-07 | 1401/02/17 | 2022-05-09 | 1401/02/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0020_D00
3 | 2 | 3 | 1 | 6 | 2 | 2 | 3.2.3.1.6.2.2 | Process Data Sheets For Glycol Transfer Pumps | BK-GCS-PEDCO-120-PR-DT-0021 | BK-GCS-PEDCO-120-PR-DT-0021 | BK | GCS | PEDCO | 120 | PR | DT | 0021 | F0Z-708765 | AFC | IFC | 2021-12-12 | 2021-12-11 | 2022-02-13 | -1 | 64 | 63 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-28 | 0 |  | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0021_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0021_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0276 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02298 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-313161 | 2021-12-11 | 1400/09/20 | 2022-02-13 | 1400/11/24 | RJ | [10 empty] | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0021_D00 | [5 empty] | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0021_D00
3 | 2 | 3 | 1 | 6 | 2 | 3 | 3.2.3.1.6.2.3 | Process Data Sheets For Glycol Manual Pump | BK-GCS-PEDCO-120-PR-DT-0022 | BK-GCS-PEDCO-120-PR-DT-0022 | BK | GCS | PEDCO | 120 | PR | DT | 0022 | F0Z-708766 | AFC | IFC | 2021-12-12 | 2021-12-11 | 2022-02-13 | -1 | 64 | 63 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-28 | 0 |  | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0022_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0022_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0276 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02298 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-313161 | 2021-12-11 | 1400/09/20 | 2022-02-13 | 1400/11/24 | RJ | [10 empty] | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0022_D00 | [5 empty] | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0022_D00
3 | 2 | 3 | 1 | 6 | 2 | 4 | 3.2.3.1.6.2.4 | Process Data Sheets For Closed Drain Pumps | BK-GCS-PEDCO-120-PR-DT-0023 | BK-GCS-PEDCO-120-PR-DT-0023 | BK | GCS | PEDCO | 120 | PR | DT | 0023 | F0Z-708767 | AFC | IFC | 2021-12-12 | 2021-12-11 | 2022-02-13 | -1 | 64 | 63 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-28 | 0 |  | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0023_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0023_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0276 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02298 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-313161 | 2021-12-11 | 1400/09/20 | 2022-02-13 | 1400/11/24 | RJ | [10 empty] | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0023_D00 | [5 empty] | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0023_D00
3 | 2 | 3 | 1 | 6 | 2 | 5 | 3.2.3.1.6.2.5 | Process Data Sheets For Sump Pumps | BK-GCS-PEDCO-120-PR-DT-0024 | BK-GCS-PEDCO-120-PR-DT-0024 | BK | GCS | PEDCO | 120 | PR | DT | 0024 | F0Z-708768 | AFC | IFC | 2021-12-12 | 2021-12-11 | 2022-02-13 | -1 | 64 | 63 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-28 | 0 |  | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0024_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0024_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0276 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02298 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-313161 | 2021-12-11 | 1400/09/20 | 2022-02-13 | 1400/11/24 | RJ | [10 empty] | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0024_D00 | [5 empty] | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0024_D00
3 | 2 | 3 | 1 | 6 | 2 | 6 | 3.2.3.1.6.2.6 | Process Data Sheets For Flare KO Drum Pumps | BK-GCS-PEDCO-120-PR-DT-0025 | BK-GCS-PEDCO-120-PR-DT-0025 | BK | GCS | PEDCO | 120 | PR | DT | 0025 | F0Z-708769 | AFC | IFC | 2021-12-12 | 2021-12-15 | 2021-12-18 | 3 | 3 | 6 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-28 | 0 |  | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0025_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0025_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0275 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02245 | 2021-12-11 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-319047 | 2021-12-15 | 1400/09/24 | 2021-12-18 | 1400/09/27 | RJ | [10 empty] | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0025_D00 | [5 empty] | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0025_D00
3 | 2 | 3 | 1 | 6 | 2 | 7 | 3.2.3.1.6.2.7 | Process Data Sheets For Potable Water Pump | BK-GCS-PEDCO-120-PR-DT-0026 | BK-GCS-PEDCO-120-PR-DT-0026 | BK | GCS | PEDCO | 120 | PR | DT | 0026 | F0Z-708770 | AFC | IFC | 2021-12-12 | 2021-12-15 | 2021-12-18 | 3 | 3 | 6 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-28 | 0 |  | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0026_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0026_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0275 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02245 | 2021-12-11 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-319047 | 2021-12-15 | 1400/09/24 | 2021-12-18 | 1400/09/27 | RJ | [10 empty] | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0026_D00 | [5 empty] | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0026_D00
3 | 2 | 3 | 1 | 6 | 2 | 8 | 3.2.3.1.6.2.8 | Process Data Sheets For Glycol Sump Pumps | BK-GCS-PEDCO-120-PR-DT-0027 | BK-GCS-PEDCO-120-PR-DT-0027 | BK | GCS | PEDCO | 120 | PR | DT | 0027 | F0Z-708771 | AFC | IFC | 2021-12-12 | 2021-12-15 | 2021-12-18 | 3 | 3 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D00 | IFC | T-0275 | 2021-11-28 | 1400/09/07 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02245 | 2021-12-11 | 1400/09/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-319047 | 2021-12-15 | 1400/09/24 | 2021-12-18 | 1400/09/27 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0275 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02245 | 2021-12-11 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-319047 | 2021-12-15 | 1400/09/24 | 2021-12-18 | 1400/09/27 | RJ
3 | 2 | 3 | 1 | 6 | 2 | 9 | 3.2.3.1.6.2.9 | Process Data Sheets For Glycol Drain Pump | BK-GCS-PEDCO-120-PR-DT-0028 | BK-GCS-PEDCO-120-PR-DT-0028 | BK | GCS | PEDCO | 120 | PR | DT | 0028 | F0Z-708772 | AFC | IFC | 2021-12-12 | 2021-12-15 | 2021-12-18 | 3 | 3 | 6 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-28 | 0 |  | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0028_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0028_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0275 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02245 | 2021-12-11 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-319047 | 2021-12-15 | 1400/09/24 | 2021-12-18 | 1400/09/27 | RJ | [10 empty] | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0028_D00 | [5 empty] | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0028_D00
[7 empty] | 3.2.3.1.6.2.10 | Process Data Sheets of Diesel Pump | BK-GCS-PEDCO-120-PR-DT-0028 | BK-GCS-PEDCO-120-PR-DT-0028 | BK | GCS | PEDCO | 120 | PR | DT | 0028 | F0Z-708773 | AFC | IFC | 2021-12-12 | 2021-12-15 | 2021-12-18 | 3 | 3 | 6 | IFC | 2022-04-11 | 2022-05-04 | 2022-05-08 | 23 | 4 | 27 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-28 | 0 |  | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0029_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0029_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0275 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-PCS-00-02245 | 2021-12-11 | 1400/09/20 | CM-C3 | [6 empty] | 1400-2294-319047 | 2021-12-15 | 1400/09/24 | 2021-12-18 | 1400/09/27 | RJ | [10 empty] | D01 | IFC | T-0739 | 2022-03-28 | 1401/01/08 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0029_D00 | [5 empty] | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0029_D00
3 | 2 | 3 | 1 | 6 | 3 | 0 | 3.2.1.6.3 | Packaged Equipment
3 | 2 | 3 | 1 | 6 | 3 | 1 | 3.2.3.1.6.3.1 | Process Data Sheets For Gas Compressors Packages | BK-GCS-PEDCO-120-PR-DT-0030 | BK-GCS-PEDCO-120-PR-DT-0030 | BK | GCS | PEDCO | 120 | PR | DT | 0030 | F0Z-708774 | AFC | IFC | 2021-11-21 | 2021-11-18 | 2021-11-27 | -3 | 9 | 6 | IFA | 2022-01-15 | 2022-01-22 | 2022-01-29 | 7 | 7 | 14 | IFA | 2022-04-09 | 2022-05-04 | 2022-05-08 | 25 | 4 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-07 | 0 |  | D02 | IFA | T-0744 | 2022-03-26 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03974 | 2022-04-18 | 1401/01/29 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0030_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0030_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0215 | 2021-11-07 | 1400/08/16 |  |  |  | BK-SUR-ENG-PCS-00-02121 | 2021-11-27 | 1400/09/06 | CM-C3 | [6 empty] | 1400-2294-281414 | 2021-11-18 | 1400/08/27 | 2021-11-27 | 1400/09/06 | CM | [10 empty] | D01 | IFA | T-0412 | 2022-01-01 | 1400/10/11 |  |  |  | BK-SUR-ENG-PCS-00-02668 | 2022-01-15 | 1400/10/25 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0030-D00 | [5 empty] | 1400-2294-375064 | 2022-01-22 | 1400/11/02 | 2022-01-29 | 1400/11/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0030-D00 | [9 empty] | D02 | IFA | T-0744 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-PCS-01-03974 | 2022-04-18 | 1401/01/29 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0030_D01 | [5 empty] | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0030_D01
3 | 2 | 3 | 1 | 6 | 3 | 2 | 3.2.3.1.6.3.2 | Process Data Sheets For Chemical Injection Packages | BK-GCS-PEDCO-120-PR-DT-0031 | BK-GCS-PEDCO-120-PR-DT-0031 | BK | GCS | PEDCO | 120 | PR | DT | 0031 | F0Z-708775 | AFC | IFC | 2022-05-23 | 0 | 0 | -44704 | 0 | -44704 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-09 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0921 | 2022-05-09 | 1401/02/19
3 | 2 | 3 | 1 | 6 | 4 | 0 | 3.2.1.6.4 | Instruments
3 | 2 | 3 | 1 | 6 | 4 | 1 | 3.2.3.1.6.4.1 | Process Data Sheets For Instrument Devices | BK-GCS-PEDCO-120-PR-DT-0032 | BK-GCS-PEDCO-120-PR-DT-0032 | BK | GCS | PEDCO | 120 | PR | DT | 0032 | F0Z-708776 | AFC | IFC | 44685 | 44702 | 44704 | 17 | 2 | 19 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-20 | 0 |  | D00 | IFC | T-0848 | 2022-04-20 | 1401/01/31 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | 1401/02/31 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70086 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0848 | 2022-04-20 | 1401/01/31 |  |  |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | 1401/02/31 | CM-C3 | [6 empty] | 1401-2294-70086 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM
3 | 2 | 3 | 1 | 7 | 0 | 0 | 3.2.3.1.7 | Drawing/Diagram
3 | 2 | 3 | 1 | 7 | 0 | 1 | 3.2.3.1.7 | Process Flow Diagram (PFD) | BK-GCS-PEDCO-120-PR-PF-0001 | BK-GCS-PEDCO-120-PR-PF-0001 | BK | GCS | PEDCO | 120 | PR | PF | 0001 | F2A-708777 | AFC | IFC | 2021-08-28 | 2021-09-01 | 2021-09-06 | 4 | 5 | 9 | IFA | 2021-10-31 | 2021-11-28 | 2021-11-14 | 28 | -14 | 14 | IFA | 2021-12-14 | 2021-12-30 | 2022-01-02 | 16 | 3 | 19 | IFA | 2022-01-22 | 2022-02-12 | 2022-02-22 | 21 | 10 | 31 | IFA | 2022-03-26 | 2022-04-21 | 2022-04-30 | 26 | 9 | 35 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-14 | 0 |  | D04 | IFA | T-0716 | 2022-03-12 | 1400/12/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03873 | 2022-04-12 | 1401/01/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PF-0001_D03 | 0 | 0 | 0 | 0 | 0 | 1401-2294-33692 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PF-0001_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0049 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-PCS-00-01445 | 2021-09-01 | 1400/06/10 | CM-C3 | [6 empty] | 1400/2294/181163 | 2021-09-01 | 1400/06/10 | 2021-09-06 | 1400/06/15 | CM | [10 empty] | D01 | IFA | T-0161 | 2021-10-17 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01884 | 2021-11-01 | 1400/08/10 | CM-C3 | PEDCO-BK-GCS-PEDCO-120-PR-PF-0001_D00 | [5 empty] | 1400-2294-270371 | 2021-11-10 | 1400/08/19 | 2021-11-14 | 1400/08/23 | CM | NISOC-BK-GCS-PEDCO-120-PR-PF-0001_D00 | 1400-2290-294976 | 2021-11-28 | 1400/09/07 |  |  | CM |  |  |  | D02 | IFA | T-0285 | 2021-11-30 | 1400/09/09 |  |  |  | BK-SUR-ENG-PCS-00-02363 | 2021-12-19 | 1400/09/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PF-0001_D01 | [5 empty] | 1400-2294-342083 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PF-0001_D01 | [9 empty] | D03 | IFA | T-0437 | 2022-01-08 | 1400/10/18 |  |  |  | BK-SUR-ENG-PCS-00-02784 | 2022-01-23 | 1400/11/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PF-0001_D02 | [5 empty] | 1400-2294-405260 | 2022-02-12 | 1400/11/23 | 2022-02-22 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PF-0001_D02 | [9 empty] | D04 | IFA | T-0716 | 2022-03-12 | 1400/12/21 |  |  |  | BK-SUR-ENG-PCS-01-03873 | 2022-04-12 | 1401/01/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PF-0001_D03 | [5 empty] | 1401-2294-33692 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PF-0001_D03
3 | 2 | 3 | 1 | 7 | 0 | 2 | 3.2.3.1.7 | Utility Flow Diagrams (UFD) | BK-GCS-PEDCO-120-PR-UF-0001 | BK-GCS-PEDCO-120-PR-UF-0001 | BK | GCS | PEDCO | 120 | PR | UF | 0001 | F2A-708778 | AFC | IFC | 2021-11-01 | 2021-11-28 | 2021-11-14 | 27 | -14 | 13 | IFA | 2022-01-12 | 2022-01-17 | 2022-01-23 | 5 | 6 | 11 | IFA | 2022-03-23 | 2022-04-22 | 2022-04-30 | 30 | 8 | 38 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-18 | 0 |  | D02 | IFA | T-0702 | 2022-03-09 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03818 | 2022-04-09 | 1401/01/20 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-33758 | 2022-04-22 | 1401/02/02 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0169 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-PCS-00-01935 | 2021-11-07 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-270393 | 2021-11-10 | 1400/08/19 | 2021-11-14 | 1400/08/23 | CM |  | 1400-2290-294882 | 2021-11-28 | 1400/09/07 |  |  | CM |  |  |  | D01 | IFA | T-0404 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-PCS-00-02657 | 2022-01-12 | 1400/10/22 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D00 | [5 empty] | 1400-2294-368480 | 2022-01-17 | 1400/10/27 | 2022-01-23 | 1400/11/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D00 | [9 empty] | D02 | IFA | T-0702 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03818 | 2022-04-09 | 1401/01/20 |  | PEDCO-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D01 | [5 empty] | 1401-2294-33758 | 2022-04-22 | 1401/02/02 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D01
3 | 2 | 3 | 1 | 7 | 0 | 3 | 3.2.3.1.7 | Symbol & Legend For PFD and P&ID | BK-GCS-PEDCO-120-PR-PI-0001 | BK-GCS-PEDCO-120-PR-PI-0001 | BK | GCS | PEDCO | 120 | PR | PI | 0001 | F2A-708779 | AFC | IFC | 2021-10-18 | 2021-11-09 | 2021-10-30 | 22 | -10 | 12 | IFA | 2022-01-25 | 2022-03-07 | 2022-03-09 | 41 | 2 | 43 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-04 | 0 |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0134 | 2021-10-04 | 1400/07/12 |  |  |  | BK-SUR-ENG-PCS-00-01867 | 2021-10-30 | 1400/08/08 | CM-C3 | PEDCO-CRS- BK-GNRAL-PEDCO-000-PR-PI-0001-D00 | [5 empty] | 1400-2294-269245 | 2021-11-09 | 1400/08/18 | 2021-10-30 | 1400/08/08 | CM | NISOC-CRS- BK-GNRAL-PEDCO-000-PR-PI-0001-D00 | [9 empty] | D01 | IFA | T-0450 | 2022-01-11 | 1400/10/20 |  |  |  | BK-SUR-ENG-PCS-00-02827 | 2022-01-26 | 1400/11/06 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0001_D00 | [5 empty] | 1400-2294-407038 | 2022-02-12 | 1400/11/23 | 2022-02-22 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0001_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0001_D01 | [5 empty] | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0001_D01
3 | 2 | 3 | 1 | 7 | 0 | 4 | 3.2.3.1.7 | P&ID - Gas Compression Inlet Gas Pipeline (Binak) | BK-GCS-PEDCO-120-PR-PI-0002 | BK-GCS-PEDCO-120-PR-PI-0002 | BK | GCS | PEDCO | 120 | PR | PI | 0002 | F2A-708780 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0120 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01743 | 2021-10-16 | 1400/07/24 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 2021-10-26 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0416 | 2022-01-02 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02748 | 2022-01-19 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D00 | [5 empty] | 1400-2294-397290 | 2022-02-05 | 1400/11/16 | 2022-02-16 | 1400/11/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D01 | [5 empty] | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0002_D01
3 | 2 | 3 | 1 | 7 | 0 | 5 | 3.2.3.1.7 | P&ID - Gas Compression Inlet Gas Pipeline (Golkhari) | BK-GCS-PEDCO-120-PR-PI-0003 | BK-GCS-PEDCO-120-PR-PI-0003 | BK | GCS | PEDCO | 120 | PR | PI | 0003 | F2A-708781 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0120 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01743 | 2021-10-16 | 1400/07/24 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 2021-10-26 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0416 | 2022-01-02 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02748 | 2022-01-19 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D00 | [5 empty] | 1400-2294-397290 | 2022-02-05 | 1400/11/16 | 2022-02-16 | 1400/11/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D01 | [5 empty] | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D01
3 | 2 | 3 | 1 | 7 | 0 | 6 | 3.2.3.1.7 | P&ID - Slug Catcher System | BK-GCS-PEDCO-120-PR-PI-0004 | BK-GCS-PEDCO-120-PR-PI-0004 | BK | GCS | PEDCO | 120 | PR | PI | 0004 | F2A-708782 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0120 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01743 | 2021-10-16 | 1400/07/24 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 2021-10-26 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0416 | 2022-01-02 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02748 | 2022-01-19 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D00 | [5 empty] | 1400-2294-397290 | 2022-02-05 | 1400/11/16 | 2022-02-16 | 1400/11/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D01 | [5 empty] | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D01
3 | 2 | 3 | 1 | 7 | 0 | 7 | 3.2.3.1.7 | P&ID - Gas Compression Inlet Knock Out Drum | BK-GCS-PEDCO-120-PR-PI-0005 | BK-GCS-PEDCO-120-PR-PI-0005 | BK | GCS | PEDCO | 120 | PR | PI | 0005 | F2A-708783 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0120 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01743 | 2021-10-16 | 1400/07/24 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 2021-10-26 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0416 | 2022-01-02 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02748 | 2022-01-19 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D00 | [5 empty] | 1400-2294-397290 | 2022-02-05 | 1400/11/16 | 2022-02-16 | 1400/11/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D01 | [5 empty] | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D01
3 | 2 | 3 | 1 | 7 | 0 | 8 | 3.2.3.1.7 | P&ID - 1st Stage Gas Compression Suction Drums | BK-GCS-PEDCO-120-PR-PI-0006 | BK-GCS-PEDCO-120-PR-PI-0006 | BK | GCS | PEDCO | 120 | PR | PI | 0006 | F2A-708784 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0120 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01743 | 2021-10-16 | 1400/07/24 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 2021-10-26 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0416 | 2022-01-02 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02748 | 2022-01-19 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D00 | [5 empty] | 1400-2294-397290 | 2022-02-05 | 1400/11/16 | 2022-02-16 | 1400/11/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D01 | [5 empty] | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D01
3 | 2 | 3 | 1 | 7 | 0 | 9 | 3.2.3.1.7 | P&ID - 1st Stage Gas Compression Compressors | BK-GCS-PEDCO-120-PR-PI-0007 | BK-GCS-PEDCO-120-PR-PI-0007 | BK | GCS | PEDCO | 120 | PR | PI | 0007 | F2A-708785 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0120 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01743 | 2021-10-16 | 1400/07/24 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 2021-10-26 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0416 | 2022-01-02 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02748 | 2022-01-19 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D00 | [5 empty] | 1400-2294-397290 | 2022-02-05 | 1400/11/16 | 2022-02-16 | 1400/11/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D01 | [5 empty] | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D01
3 | 2 | 3 | 1 | 7 | 0 | 10 | 3.2.3.1.7 | P&ID - 1st Stage Gas Compression Air Coolers | BK-GCS-PEDCO-120-PR-PI-0008 | BK-GCS-PEDCO-120-PR-PI-0008 | BK | GCS | PEDCO | 120 | PR | PI | 0008 | F2A-708786 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0120 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01743 | 2021-10-16 | 1400/07/24 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 2021-10-26 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0416 | 2022-01-02 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02748 | 2022-01-19 | 1400/10/29 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D00 | [5 empty] | 1400-2294-397290 | 2022-02-05 | 1400/11/16 | 2022-02-16 | 1400/11/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D01 | [5 empty] | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D01
3 | 2 | 3 | 1 | 7 | 0 | 11 | 3.2.3.1.7 | P&ID - 2nd Stage Gas Compression Suction Drums | BK-GCS-PEDCO-120-PR-PI-0009 | BK-GCS-PEDCO-120-PR-PI-0009 | BK | GCS | PEDCO | 120 | PR | PI | 0009 | F2A-708787 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-15 | 2022-04-17 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0121 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01819 | 2021-10-23 | 1400/08/01 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 2021-10-26 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0417 | 2022-01-02 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02773 | 2022-01-19 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D00 | [5 empty] | 1400-2294-395122 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0668 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03755 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D01 | [5 empty] | 1401-2294-23096 | 2022-04-15 | 1401/01/26 | 2022-04-17 | 1401/01/28 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D01
3 | 2 | 3 | 1 | 7 | 0 | 12 | 3.2.3.1.7 | P&ID - 2nd Stage Gas Compression Compressors | BK-GCS-PEDCO-120-PR-PI-0010 | BK-GCS-PEDCO-120-PR-PI-0010 | BK | GCS | PEDCO | 120 | PR | PI | 0010 | F2A-708788 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0121 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01819 | 2021-10-23 | 1400/08/01 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 2021-10-26 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0417 | 2022-01-02 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02773 | 2022-01-19 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D00 | [5 empty] | 1400-2294-395122 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D01 | [5 empty] | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0010_D01
3 | 2 | 3 | 1 | 7 | 0 | 13 | 3.2.3.1.7 | P&ID - 2nd Stage Gas Compression Air Coolers | BK-GCS-PEDCO-120-PR-PI-0011 | BK-GCS-PEDCO-120-PR-PI-0011 | BK | GCS | PEDCO | 120 | PR | PI | 0011 | F2A-708789 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0121 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01819 | 2021-10-23 | 1400/08/01 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 2021-10-26 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0417 | 2022-01-02 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02773 | 2022-01-19 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D00 | [5 empty] | 1400-2294-395122 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D01 | [5 empty] | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D01
3 | 2 | 3 | 1 | 7 | 0 | 14 | 3.2.3.1.7 | P&ID - 2nd Stage Gas Compression Discharge Drum | BK-GCS-PEDCO-120-PR-PI-0012 | BK-GCS-PEDCO-120-PR-PI-0012 | BK | GCS | PEDCO | 120 | PR | PI | 0012 | F2A-708790 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0121 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01819 | 2021-10-23 | 1400/08/01 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 2021-10-26 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0417 | 2022-01-02 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02773 | 2022-01-19 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D00 | [5 empty] | 1400-2294-395122 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D01 | [5 empty] | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D01
3 | 2 | 3 | 1 | 7 | 0 | 15 | 3.2.3.1.7 | P&ID - Gas Compression Dehydration Package | BK-GCS-PEDCO-120-PR-PI-0013 | BK-GCS-PEDCO-120-PR-PI-0013 | BK | GCS | PEDCO | 120 | PR | PI | 0013 | F2A-708791 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0121 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01819 | 2021-10-23 | 1400/08/01 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 2021-10-26 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0417 | 2022-01-02 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02773 | 2022-01-19 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D00 | [5 empty] | 1400-2294-395122 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D01 | [5 empty] | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D01
3 | 2 | 3 | 1 | 7 | 0 | 16 | 3.2.3.1.7 | P&ID - Lean Glycol Storage Tank | BK-GCS-PEDCO-120-PR-PI-0014 | BK-GCS-PEDCO-120-PR-PI-0014 | BK | GCS | PEDCO | 120 | PR | PI | 0014 | F2A-708792 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-16 | 2022-03-07 | 2022-03-09 | 50 | 2 | 52 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0121 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01819 | 2021-10-23 | 1400/08/01 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/28 | 2021-10-26 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0417 | 2022-01-02 | 1400/10/12 |  |  |  | BK-SUR-ENG-PCS-00-02773 | 2022-01-19 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D00 | [5 empty] | 1400-2294-395122 | 2022-02-04 | 1400/11/15 | 2022-02-08 | 1400/11/19 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D01 | [5 empty] | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D01
3 | 2 | 3 | 1 | 7 | 0 | 17 | 3.2.3.1.7 | P&ID - Instrument & Plant Air System | BK-GCS-PEDCO-120-PR-PI-0015 | BK-GCS-PEDCO-120-PR-PI-0015 | BK | GCS | PEDCO | 120 | PR | PI | 0015 | F2A-708793 | AFC | IFC | 2021-11-01 | 2021-11-08 | 2021-11-10 | 7 | 2 | 9 | IFC | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-03 | 0 |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0167 | 2021-10-18 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01930 | 2021-11-07 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 2021-11-10 | 1400/08/19 | RJ | [10 empty] | D01 | IFC | T-0418 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02780 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D00 | [5 empty] | 1400-2294-401008 | 2022-02-07 | 1400/11/18 | 2022-02-09 | 1400/11/20 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D01 | [5 empty] | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0015_D01
3 | 2 | 3 | 1 | 7 | 0 | 18 | 3.2.3.1.7 | P&ID - Nitrogen Generation System | BK-GCS-PEDCO-120-PR-PI-0016 | BK-GCS-PEDCO-120-PR-PI-0016 | BK | GCS | PEDCO | 120 | PR | PI | 0016 | F2A-708794 | AFC | IFC | 2021-11-01 | 2021-11-28 | 2021-11-10 | 27 | -18 | 9 | IFC | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-03 | 0 |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0167 | 2021-10-18 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01930 | 2021-11-07 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 2021-11-10 | 1400/08/19 | RJ |  | 1400-2290-294882 | 2021-11-28 | 1400/09/07 |  |  | CM |  |  |  | D01 | IFC | T-0418 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02780 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D00 | [5 empty] | 1400-2294-401008 | 2022-02-07 | 1400/11/18 | 2022-02-09 | 1400/11/20 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D01 | [5 empty] | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0016_D01
3 | 2 | 3 | 1 | 7 | 0 | 19 | 3.2.3.1.7 | P&ID - Close Drain System | BK-GCS-PEDCO-120-PR-PI-0017 | BK-GCS-PEDCO-120-PR-PI-0017 | BK | GCS | PEDCO | 120 | PR | PI | 0017 | F2A-708795 | AFC | IFC | 2021-11-01 | 2021-11-28 | 2021-11-10 | 27 | -18 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-19 | 2022-04-30 | 31 | 11 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-18 | 0 |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0167 | 2021-10-18 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01930 | 2021-11-07 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 2021-11-10 | 1400/08/19 | CM |  | 1400-2290-294882 | 2021-11-28 | 1400/09/07 |  |  | CM |  |  |  | D01 | IFA | T-0418 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02780 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D00 | [5 empty] | 1400-2294-401008 | 2022-02-07 | 1400/11/18 | 2022-02-09 | 1400/11/20 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0669 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03738 | 2022-04-05 | 1401/01/16 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D01 | [5 empty] | 1401-2294-31443 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0017_D01
3 | 2 | 3 | 1 | 7 | 0 | 20 | 3.2.3.1.7 | P&ID - Corrosion Inhibitor Package | BK-GCS-PEDCO-120-PR-PI-0018 | BK-GCS-PEDCO-120-PR-PI-0018 | BK | GCS | PEDCO | 120 | PR | PI | 0018 | F2A-708796 | AFC | IFC | 2021-11-01 | 2021-11-08 | 2021-11-10 | 7 | 2 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-18 | 0 |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0167 | 2021-10-18 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01930 | 2021-11-07 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 2021-11-10 | 1400/08/19 | CM | [10 empty] | D01 | IFA | T-0418 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02780 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D00 | [5 empty] | 1400-2294-401008 | 2022-02-07 | 1400/11/18 | 2022-02-09 | 1400/11/20 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D01 | [5 empty] | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D01
3 | 2 | 3 | 1 | 7 | 0 | 21 | 3.2.3.1.7 | P&ID - Methanol Injection Package | BK-GCS-PEDCO-120-PR-PI-0019 | BK-GCS-PEDCO-120-PR-PI-0019 | BK | GCS | PEDCO | 120 | PR | PI | 0019 | F2A-708797 | AFC | IFC | 2021-11-01 | 2021-11-08 | 2021-11-10 | 7 | 2 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-18 | 0 |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0167 | 2021-10-18 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01930 | 2021-11-07 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 2021-11-10 | 1400/08/19 | CM | [10 empty] | D01 | IFA | T-0418 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02780 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D00 | [5 empty] | 1400-2294-401008 | 2022-02-07 | 1400/11/18 | 2022-02-09 | 1400/11/20 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D01 | [5 empty] | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0019_D01
3 | 2 | 3 | 1 | 7 | 0 | 22 | 3.2.3.1.7 | P&ID - LP Flare System | BK-GCS-PEDCO-120-PR-PI-0020 | BK-GCS-PEDCO-120-PR-PI-0020 | BK | GCS | PEDCO | 120 | PR | PI | 0020 | F2A-708798 | AFC | IFC | 2021-11-01 | 2021-11-28 | 2021-11-10 | 27 | -18 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-18 | 0 |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0168 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-PCS-00-01932 | 2021-11-07 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 2021-11-10 | 1400/08/19 | CM |  | 1400-2290-294882 | 2021-11-28 | 1400/09/07 |  |  | CM |  |  |  | D01 | IFA | T-0419 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02782 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D00 | [5 empty] | 1400-2294-402839 | 2022-02-08 | 1400/11/19 | 2022-02-12 | 1400/11/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D01 | [5 empty] | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D01
3 | 2 | 3 | 1 | 7 | 0 | 23 | 3.2.3.1.7 | P&ID - Oily Water Sewer | BK-GCS-PEDCO-120-PR-PI-0021 | BK-GCS-PEDCO-120-PR-PI-0021 | BK | GCS | PEDCO | 120 | PR | PI | 0021 | F2A-708799 | AFC | IFC | 2021-11-01 | 2021-11-08 | 2021-11-10 | 7 | 2 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-18 | 0 |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0168 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-PCS-00-01932 | 2021-11-07 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 2021-11-10 | 1400/08/19 | CM | [10 empty] | D01 | IFA | T-0419 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02782 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D00 | [5 empty] | 1400-2294-402839 | 2022-02-08 | 1400/11/19 | 2022-02-12 | 1400/11/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D01 | [5 empty] | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0021_D01
3 | 2 | 3 | 1 | 7 | 0 | 24 | 3.2.3.1.7 | P&ID - Fuel Gas System | BK-GCS-PEDCO-120-PR-PI-0022 | BK-GCS-PEDCO-120-PR-PI-0022 | BK | GCS | PEDCO | 120 | PR | PI | 0022 | F2A-708800 | AFC | IFC | 2021-11-01 | 2021-11-08 | 2021-11-10 | 7 | 2 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-18 | 0 |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0168 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-PCS-00-01932 | 2021-11-07 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 2021-11-10 | 1400/08/19 | CM | [10 empty] | D01 | IFA | T-0419 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02782 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D00 | [5 empty] | 1400-2294-402839 | 2022-02-08 | 1400/11/19 | 2022-02-12 | 1400/11/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D01 | [5 empty] | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0022_D01
3 | 2 | 3 | 1 | 7 | 0 | 25 | 3.2.3.1.7 | P&ID - Diesel Oil System | BK-GCS-PEDCO-120-PR-PI-0023 | BK-GCS-PEDCO-120-PR-PI-0023 | BK | GCS | PEDCO | 120 | PR | PI | 0023 | F2A-708801 | AFC | IFC | 2021-11-01 | 2021-11-28 | 2021-11-10 | 27 | -18 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-18 | 0 |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0168 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-PCS-00-01932 | 2021-11-07 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 2021-11-10 | 1400/08/19 | CM |  | 1400-2290-294882 | 2021-11-28 | 1400/09/07 |  |  | CM |  |  |  | D01 | IFA | T-0419 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02782 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D00 | [5 empty] | 1400-2294-402839 | 2022-02-08 | 1400/11/19 | 2022-02-12 | 1400/11/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D01 | [5 empty] | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0023_D01
3 | 2 | 3 | 1 | 7 | 0 | 26 | 3.2.3.1.7 | P&ID - Potable Water System | BK-GCS-PEDCO-120-PR-PI-0024 | BK-GCS-PEDCO-120-PR-PI-0024 | BK | GCS | PEDCO | 120 | PR | PI | 0024 | F2A-708802 | AFC | IFC | 2021-11-01 | 2021-11-08 | 2021-11-10 | 7 | 2 | 9 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-18 | 0 |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0168 | 2021-10-18 | 1400/07/26 |  |  |  | BK-SUR-ENG-PCS-00-01932 | 2021-11-07 | 1400/08/16 | CM-C3 | [6 empty] | 1400-2294-267462 | 2021-11-08 | 1400/08/17 | 2021-11-10 | 1400/08/19 | CM | [10 empty] | D01 | IFA | T-0419 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02782 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D00 | [5 empty] | 1400-2294-402839 | 2022-02-08 | 1400/11/19 | 2022-02-12 | 1400/11/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D01 | [5 empty] | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D01
3 | 2 | 3 | 1 | 7 | 0 | 27 | 3.2.3.1.7 | P&ID - Glycol Sump Drum | BK-GCS-PEDCO-120-PR-PI-0025 | BK-GCS-PEDCO-120-PR-PI-0025 | BK | GCS | PEDCO | 120 | PR | PI | 0025 | F2A-708803 | AFC | IFC | 2021-10-10 | 2021-10-19 | 2021-10-26 | 9 | 7 | 16 | IFA | 2022-01-17 | 2022-03-07 | 2022-03-09 | 49 | 2 | 51 | IFA | 2022-03-19 | 2022-04-21 | 2022-04-30 | 33 | 9 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-26 | 0 |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0121 | 2021-09-26 | 1400/07/04 |  |  |  | BK-SUR-ENG-PCS-00-01819 | 2021-10-23 | 1400/08/01 | CM-C3 | [6 empty] | 1400-2294-243649 | 2021-10-19 | 1400/07/27 | 2021-10-26 | 1400/08/04 | CM | [10 empty] | D01 | IFA | T-0419 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-PCS-00-02782 | 2022-01-22 | 1400/11/02 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D00 | [5 empty] | 1400-2294-402839 | 2022-02-08 | 1400/11/19 | 2022-02-12 | 1400/11/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D00 | 1400-2294-438936 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | CM |  |  |  | D02 | IFA | T-0670 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-PCS-01-03722 | 2022-04-04 | 1401/01/15 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D01 | [5 empty] | 1401-2294-33690 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D01
3 | 2 | 3 | 1 | 7 | 0 | 28 | 3.2.3.1.7 | ESD Block Diagram | BK-GCS-PEDCO-120-PR-BD-0001 | BK-GCS-PEDCO-120-PR-BD-0001 | BK | GCS | PEDCO | 120 | PR | BD | 0001 | F2J-708804 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 1 | 7 | 0 | 29 | 3.2.3.1.7 | Cause & Effect Diagram | BK-GCS-PEDCO-120-PR-CE-0001 | BK-GCS-PEDCO-120-PR-CE-0001 | BK | GCS | PEDCO | 120 | PR | CE | 0001 | F0Z-708805 | AFC | IFC | 2022-06-13 | 0 | 0 | -44725 | 0 | -44725 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-30 | 0 |  | D00 | IFC | T-1022 | 2022-05-30 | 1401/03/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1022 | 2022-05-30 | 1401/03/09
3 | 2 | 3 | 1 | 7 | 0 | 30 | 3.2.3.1.7 | Chemical Injection Points Diagram | BK-GCS-PEDCO-120-PR-DG-0001 | BK-GCS-PEDCO-120-PR-DG-0001 | BK | GCS | PEDCO | 120 | PR | DG | 0001 | F2A-708806 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 1 | 8 | 0 | 0 | 3.2.3.1.8 | List
3 | 2 | 3 | 1 | 8 | 0 | 1 | 3.2.3.1.8 | Process Main Equipment List | BK-GCS-PEDCO-120-PR-LI-0001 | BK-GCS-PEDCO-120-PR-LI-0001 | BK | GCS | PEDCO | 120 | PR | LI | 0001 | F0Z-708807 | AFC | IFC | 2022-03-06 | 2022-03-13 | 2022-04-01 | 7 | 19 | 26 | IFA | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-20 | 0 |  | D01 | IFA | T-0990 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0612 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-PCS-00-03621 | 2022-03-15 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445277 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | CM |  | 1400-2294-447187 | 2022-03-13 | 1400/12/22 | 2022-04-01 | 1401/01/14 | CM |  |  |  | D01 | IFA | T-0990 | 2022-05-22 | 1401/03/01 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0001_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0001_D00
3 | 2 | 3 | 1 | 8 | 0 | 2 | 3.2.3.1.8 | Process Electrical Load List | BK-GCS-PEDCO-120-PR-LI-0002 | BK-GCS-PEDCO-120-PR-LI-0002 | BK | GCS | PEDCO | 120 | PR | LI | 0002 | F0Z-708808 | AFC | IFC | 2022-02-02 | 2022-03-10 | 2022-03-12 | 36 | 2 | 38 | IFA | 2022-03-27 | 2022-05-04 | 2022-05-08 | 38 | 4 | 42 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-19 | 0 |  | D01 | IFA | T-0723 | 2022-03-13 | 1400/12/21 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03876 | 2022-04-12 | 1401/01/23 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0482 | 2022-01-19 | 1400/10/29 |  |  |  | BK-SUR-ENG-PCS-00-03080 | 2022-02-16 | 1400/11/27 | CM-C3 | [6 empty] | 1400-2294-412902 | 2022-02-16 | 1400/11/27 | 2022-02-22 | 1400/12/03 | CM |  | 1400-2294-443212 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM |  |  |  | D01 | IFA | T-0723 | 2022-03-13 | 1400/12/21 |  |  |  | BK-SUR-ENG-PCS-01-03876 | 2022-04-12 | 1401/01/23 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0002_D00 | [5 empty] | 1401-2294-48128 | 2022-05-04 | 1401/02/14 | 2022-05-08 | 1401/02/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0002_D00
3 | 2 | 3 | 1 | 8 | 0 | 3 | 3.2.3.1.8 | Tie in list | BK-GCS-PEDCO-120-PR-LI-0003 | BK-GCS-PEDCO-120-PR-LI-0003 | BK | GCS | PEDCO | 120 | PR | LI | 0003 | F0Z-708809 | AFC | IFC | 2022-03-06 | 2022-03-12 | 2022-03-15 | 6 | 3 | 9 | IFA | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-20 | 0 |  | D01 | IFA | T-0990 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0612 | 2022-02-20 | 1400/12/01 |  |  |  | BK-SUR-ENG-PCS-00-03621 | 2022-03-15 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-445277 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0990 | 2022-05-22 | 1401/03/01 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D00
3 | 2 | 3 | 1 | 8 | 0 | 4 | 3.2.3.1.8 | Line List | BK-GCS-PEDCO-120-PR-LI-0004 | BK-GCS-PEDCO-120-PR-LI-0004 | BK | GCS | PEDCO | 120 | PR | LI | 0004 | F0Z-708810 | AFC | IFC | 2022-05-14 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-30 | 0 |  | D00 | IFC | T-0876 | 2022-04-30 | 1401/02/10 | T-0876 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04370 | 2022-05-22 | 1401/03/01 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0876 | 2022-04-30 | 1401/02/10 | T-0876 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-PCS-01-04370 | 2022-05-22 | 1401/03/01 | CM-C3
3 | 2 | 3 | 1 | 8 | 0 | 5 | 3.2.3.1.8 | Chemical Consumption List | BK-GCS-PEDCO-120-PR-LI-0005 | BK-GCS-PEDCO-120-PR-LI-0005 | BK | GCS | PEDCO | 120 | PR | LI | 0005 | F0Z-708811 | AFC | IFC | 2022-03-23 | 2022-04-29 | 2022-05-01 | 37 | 2 | 39 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-09 | 0 |  | D00 | IFC | T-0703 | 2022-03-09 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | 1401/01/23 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43236 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0703 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | 1401/01/23 | CM-C3 | [6 empty] | 1401-2294-43236 | 2022-04-29 | 1401/02/09 | 2022-05-01 | 1401/02/11 | CM
3 | 2 | 3 | 1 | 8 | 0 | 6 | 3.2.3.1.8 | Utility Consumption List | BK-GCS-PEDCO-120-PR-LI-0006 | BK-GCS-PEDCO-120-PR-LI-0006 | BK | GCS | PEDCO | 120 | PR | LI | 0006 | F0Z-708812 | AFC | IFC | 2022-01-11 | 2022-01-16 | 2022-01-23 | 5 | 7 | 12 | IFA | 2022-03-23 | 2022-04-22 | 2022-04-30 | 30 | 8 | 38 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-28 | 0 |  | D01 | IFA | T-0702 | 2022-03-09 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03818 | 2022-04-09 | 1401/01/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-33758 | 2022-04-22 | 1401/02/02 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0396 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-ENG-PCS-00-02645 | 2022-01-11 | 1400/10/22 | CM-C3 | [6 empty] | 1400-2294-366632 | 2022-01-16 | 1400/10/26 | 2022-01-23 | 1400/11/03 | CM | [10 empty] | D01 | IFA | T-0702 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-PCS-01-03818 | 2022-04-09 | 1401/01/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0006_D00 | [5 empty] | 1401-2294-33758 | 2022-04-22 | 1401/02/02 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0006_D00
3 | 2 | 3 | 1 | 8 | 0 | 7 | 3.2.3.1.8 | Emission and Effluent Summary | BK-GCS-PEDCO-120-PR-LI-0007 | BK-GCS-PEDCO-120-PR-LI-0007 | BK | GCS | PEDCO | 120 | PR | LI | 0007 | F0Z-708813 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 1 | 8 | 0 | 8 | 3.2.3.1.8 | Relief Load Summery | BK-GCS-PEDCO-120-PR-LI-0008 | BK-GCS-PEDCO-120-PR-LI-0008 | BK | GCS | PEDCO | 120 | PR | LI | 0008 | F0Z-708814 | AFC | IFC | 2022-02-09 | 2022-02-26 | 2022-02-21 | 17 | -5 | 12 | IFA | 2022-05-23 | 0 | 0 | -44704 | 0 | -44704 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-26 | 0 |  | D01 | IFA | T-0917 | 2022-05-09 | 1401/02/19 | T-0917 | 2022-05-09 | 1401/02/19 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0513 | 2022-01-26 | 1400/11/06 |  |  |  | BK-SUR-ENG-PCS-00-03135 | 2022-02-20 | 1400/12/01 | CM-C3 | [6 empty] | 1400-2294-419565 | 2022-02-26 | 1400/12/07 | 2022-02-21 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0917 | 2022-05-09 | 1401/02/19 | T-0917 | 2022-05-09 | 1401/02/19 |  |  |  |  | PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0008_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0008_D00
3 | 2 | 3 | 1 | 9 | 0 | 0 | 3.2.3.1.9 | Report
3 | 2 | 3 | 1 | 9 | 0 | 1 | 3.2.3.1 | Flare Network Study Report | BK-GCS-PEDCO-120-PR-RT-0001 | BK-GCS-PEDCO-120-PR-RT-0001 | BK | GCS | PEDCO | 120 | PR | RT | 0001 | F0Z-708815 | AFD | IFC | 2022-01-19 | 2022-02-12 | 2022-02-22 | 24 | 10 | 34 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-05 | 0 |  | D00 | IFC | T-0434 | 2022-01-05 | 1400/10/15 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02801 | 2022-01-24 | 1400/11/04 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-405516 | 2022-02-12 | 1400/11/23 | 2022-02-22 | 1400/12/03 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0434 | 2022-01-05 | 1400/10/15 |  |  |  | BK-SUR-ENG-PCS-00-02801 | 2022-01-24 | 1400/11/04 | CM-C3 | [6 empty] | 1400-2294-405516 | 2022-02-12 | 1400/11/23 | 2022-02-22 | 1400/12/03 | CM
3 | 2 | 3 | 1 | 9 | 0 | 2 | 3.2.3.1 | Flare Radiation & Dispersion Study Report | BK-GCS-PEDCO-120-PR-RT-0002 | BK-GCS-PEDCO-120-PR-RT-0002 | BK | GCS | PEDCO | 120 | PR | RT | 0002 | F0Z-708816 | AFD | IFC | 2022-01-19 | 2022-02-12 | 2022-02-22 | 24 | 10 | 34 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-05 | 0 |  | D00 | IFC | T-0431 | 2022-01-05 | 1400/10/15 | 0 | 0 | 0 | BK-SUR-ENG-PCS-00-02802 | 2022-01-24 | 1400/11/04 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-405516 | 2022-02-12 | 1400/11/23 | 2022-02-22 | 1400/12/03 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0431 | 2022-01-05 | 1400/10/15 |  |  |  | BK-SUR-ENG-PCS-00-02802 | 2022-01-24 | 1400/11/04 | CM-C3 | [6 empty] | 1400-2294-405516 | 2022-02-12 | 1400/11/23 | 2022-02-22 | 1400/12/03 | CM
3 | 2 | 3 | 1 | 9 | 0 | 3 | 3.2.3.1 | Process Simulation Report | BK-GCS-PEDCO-120-PR-RT-0003 | BK-GCS-PEDCO-120-PR-RT-0003 | BK | GCS | PEDCO | 120 | PR | RT | 0003 | F0Z-708817 | AFD | IFC | 2021-10-31 | 2021-11-28 | 2021-11-14 | 28 | -14 | 14 | IFA | 2021-12-14 | 2021-12-30 | 2022-01-02 | 16 | 3 | 19 | IFA | 2022-01-22 | 2022-02-12 | 2022-02-22 | 21 | 10 | 31 | IFA | 2022-03-22 | 2022-04-21 | 2022-04-30 | 30 | 9 | 39 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-17 | 0 |  | D03 | IFA | T-0700 | 2022-03-08 | 1400/12/17 | 0 | 0 | 0 | BK-SUR-ENG-PCS-01-03783 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-33692 | 2022-04-19 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D02 | 1401-2294-33692 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | 0 | 0 |  | D00 | IFC | T-0162 | 2021-10-17 | 1400/07/25 |  |  |  | BK-SUR-ENG-PCS-00-01937 | 2021-11-07 | 1400/08/16 | CM-C2 | [6 empty] | 1400-2294-270371 | 2021-11-10 | 1400/08/19 | 2021-11-14 | 1400/08/23 | CM |  | 1400-2290-294976 | 2021-11-28 | 1400/09/07 |  |  | CM |  |  |  | D01 | IFA | T-0285 | 2021-11-30 | 1400/09/09 |  |  |  | BK-SUR-ENG-PCS-00-02363 | 2021-12-19 | 1400/09/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D00 | [5 empty] | 1400-2294-342083 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D00 | [9 empty] | D02 | IFA | T-0437 | 2022-01-08 | 1400/10/18 |  |  |  | BK-SUR-ENG-PCS-00-02784 | 2022-01-23 | 1400/11/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D01 | [5 empty] | 1400-2294-405260 | 2022-02-12 | 1400/11/23 | 2022-02-22 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D01 | [9 empty] | D03 | IFA | T-0700 | 2022-03-08 | 1400/12/17 |  |  |  | BK-SUR-ENG-PCS-01-03783 | 2022-04-09 | 1401/01/20 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D02 | [5 empty] | 1401-2294-33692 | 2022-04-19 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0003_D02 | 1401-2294-33692 | 2022-04-21 | 1401/02/01 | 2022-04-30 | 1401/02/10 | CM
3 | 2 | 3 | 2 | 0 | 0 | 0 | 3.2.3.2 | Mechanical
3 | 2 | 3 | 2 | 1 | 0 | 0 | 3.2.3.2.1 | Specification
3 | 2 | 3 | 2 | 1 | 1 | 0 | 3.2.2.1.1 | Fixed Equipment
3 | 2 | 3 | 2 | 1 | 1 | 1 | 3.2.3.2.1.1.1 | Specification For Air Cooled Heat Exchangers | BK-GCS-PEDCO-120-ME-SP-0001 | BK-GCS-PEDCO-120-ME-SP-0001 | BK | GCS | PEDCO | 120 | ME | SP | 0001 | F0Z-708818 | AFD | IFC | 2021-08-28 | 0 | 0 | -44436 | 0 | -44436 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-14 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 | 0 | 0 | 0 | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | 1400/06/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | 1400/06/15 | CM-C3
3 | 2 | 3 | 2 | 1 | 1 | 2 | 3.2.3.2.1.1.2 | Specification For Large Welded Low Pressure Storage Tanks | BK-GCS-PEDCO-120-ME-SP-0010 | BK-GCS-PEDCO-120-ME-SP-0010 | BK | GCS | PEDCO | 120 | ME | SP | 0010 | F0Z-708819 | AFD | IFC | 2021-09-07 | 2021-09-15 | 2021-09-26 | 8 | 11 | 19 | IFA | 2021-10-18 | 2021-10-20 | 2021-10-25 | 2 | 5 | 7 | IFA | 2021-11-13 | 2021-11-03 | 2021-11-08 | -10 | 5 | -5 | IFA | 2021-11-24 | 2021-11-18 | 2021-11-24 | -6 | 6 | 0 | AFD | 2022-02-14 | 2022-03-13 | 2022-03-26 | 27 | 13 | 40 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-24 | 2022-01-31 |  | D04 | AFD | T-0528 | 2022-01-31 | 1400/11/11 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02920 | 2022-02-02 | 1400/11/13 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-447211 | 2022-03-13 | 1400/12/22 | 2022-03-26 | 1401/01/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0064 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-FXE-00-01501 | 2021-09-12 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-200596 | 2021-09-15 | 1400/06/24 | 2021-09-26 | 1400/07/04 | CM | [10 empty] | D01 | IFA | T-0133 | 2021-10-04 | 1400/07/12 |  |  |  | BK-SUR-ENG-FXE-00-01832 | 2021-10-25 | 1400/08/03 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0010-D00 | [5 empty] | 1400-2294-243550 | 2021-10-20 | 1400/07/28 | 2021-10-25 | 1400/08/03 | CM | NISOC-CRS-BK-GCS-NISOC-120-ME-SP-0010-D00 | [9 empty] | D02 | IFA | T-0196 | 2021-10-30 | 1400/08/08 |  |  |  | BK-SUR-ENG-MEC-00-02126 | 2021-11-28 | 1400/09/07 | CM-C3 | [6 empty] | 1400-2294-260986 | 2021-11-03 | 1400/08/12 | 2021-11-08 | 1400/08/17 | CM | NISOC-CRS-BK-GCS-NISOC-120-ME-SP-0010-D01 | [9 empty] | D03 | IFA | T-0231 | 2021-11-10 | 1400/08/19 | [13 empty] | 1400-2294-281393 | 2021-11-18 | 1400/08/27 | 2021-11-24 | 1400/09/03 | AP | NISOC-CRS-BK-GCS-NISOC-120-ME-SP-0010_D02 | [9 empty] | D04 | AFD | T-0528 | 2022-01-31 | 1400/11/11 |  |  |  | BK-SUR-ENG-MEC-00-02920 | 2022-02-02 | 1400/11/13 | AP | [6 empty] | 1400-2294-447211 | 2022-03-13 | 1400/12/22 | 2022-03-26 | 1401/01/09 | AP
3 | 2 | 3 | 2 | 1 | 2 | 0 | 3.2.2.1.2 | Rotary Equipment
3 | 2 | 3 | 2 | 1 | 2 | 1 | 3.2.3.2.1.2.1 | Specification For Reciprocating Compressor (API 618) | BK-GCS-PEDCO-120-ME-SP-0002 | BK-GCS-PEDCO-120-ME-SP-0002 | BK | GCS | PEDCO | 120 | ME | SP | 0002 | F0Z-708820 | AFD | IFC | 2021-08-28 | 2021-08-31 | 0 | 3 | -44439 | -44436 | IFA | 2021-10-18 | 2021-11-02 | 2021-11-07 | 15 | 5 | 20 | IFA | 2021-11-28 | 2021-12-13 | 2021-12-18 | 15 | 5 | 20 | IFA | 2022-01-12 | 2022-01-20 | 2022-01-24 | 8 | 4 | 12 | IFA | 2022-02-12 | 2022-02-26 | 2022-03-02 | 14 | 4 | 18 | AFD | 2022-03-21 | 0 | 0 | -44641 | 0 | -44641 | Modify | 2021-08-14 | 2022-03-07 |  | D05 | AFD | T-0690 | 2022-03-07 | 1400/12/16 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03453 | 2022-03-12 | 1400/12/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | 1400/06/15 | CM-C3 | [6 empty] | 1400/2294/181003 | 2021-08-31 | 1400/06/09 |  |  | CM | [10 empty] | D01 | IFA | T-0135 | 2021-10-04 | 1400/07/12 |  |  |  | BK-SUR-ENG-ROE-00-01844 | 2021-10-26 | 1400/08/04 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0002_D00 | [5 empty] | 1400-2294-259326 | 2021-11-02 | 1400/08/11 | 2021-11-07 | 1400/08/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0002_D00 | [9 empty] | D02 | IFA | T-0232 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-MEC-00-02102 | 2021-11-27 | 1400/09/06 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0002-D01 | [5 empty] | 1400-2294-316960 | 2021-12-13 | 1400/09/22 | 2021-12-18 | 1400/09/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0002-D01 | [9 empty] | D03 | IFA | T-0400 | 2021-12-29 | 1400/10/08 | [13 empty] | 1400-2294-372899 | 2022-01-20 | 1400/10/30 | 2022-01-24 | 1400/11/04 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0002_D02 | [9 empty] | D04 | IFA | T-0518 | 2022-01-29 | 1400/11/09 | [13 empty] | 1400-2294-426614 | 2022-02-26 | 1400/12/07 | 2022-03-02 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0002_D03 | [9 empty] | D05 | AFD | T-0690 | 2022-03-07 | 1400/12/16 |  |  |  | BK-SUR-ENG-MEC-00-03453 | 2022-03-12 | 1400/12/21 | CM-C3
3 | 2 | 3 | 2 | 1 | 2 | 2 | 3.2.3.2.1.2.2 | Specification For Centrifugal Pumps For Process Services (API610) | BK-GCS-PEDCO-120-ME-SP-0003 | BK-GCS-PEDCO-120-ME-SP-0003 | BK | GCS | PEDCO | 120 | ME | SP | 0003 | F0Z-708821 | AFD | IFC | 2021-09-05 | 2021-08-31 | 2021-09-12 | -5 | 12 | 7 | IFA | 2021-10-20 | 2021-12-29 | 2021-10-30 | 70 | -60 | 10 | IFA | 2022-01-25 | 2022-02-26 | 2022-03-02 | 32 | 4 | 36 | IFA | 2022-03-20 | 2022-04-12 | 2022-04-18 | 23 | 6 | 29 | AFD | 2022-05-03 | 2022-04-28 | 2022-05-01 | -5 | 3 | -2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2022-04-19 |  | D04 | AFD | T-0841 | 2022-04-19 | 1401/01/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42947 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0053 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-ROE-00-01493 | 2021-09-12 | 1400/06/21 | CM-C3 | [6 empty] | 1400/2294/181002 | 2021-08-31 | 1400/06/09 | 2021-09-12 | 1400/06/21 | AP | [10 empty] | D01 | IFA | T-0138 | 2021-10-06 | 1400/07/14 |  |  |  | BK-SUR-ENG-MEC-00-01868 | 2021-10-30 | 1400/08/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0003-D00 | [5 empty] | 1400-2294-257419 | 2021-12-29 | 1400/10/10 | 2021-10-30 | 1400/08/08 | CM | [10 empty] | D02 | IFA | T-0447 | 2022-01-11 | 1400/10/20 |  |  |  | BK-SUR-ENG-MEC-00-02798 | 2022-01-24 | 1400/11/04 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0003_D01 | [5 empty] | 1400-2294-426688 | 2022-02-26 | 1400/12/07 | 2022-03-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0003_D01 | [9 empty] | D03 | IFA | T-0681 | 2022-03-06 | 1400/12/15 | [13 empty] | 1401-2294-20728 | 2022-04-12 | 1401/01/23 | 2022-04-18 | 1401/01/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0003_D02 | [9 empty] | D04 | AFD | T-0841 | 2022-04-19 | 1401/01/30 | [13 empty] | 1401-2294-42947 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | AP
3 | 2 | 3 | 2 | 1 | 2 | 3 | 3.2.3.2.1.2.3 | Specification For Centrifugal Pumps For General Services | BK-GCS-PEDCO-120-ME-SP-0004 | BK-GCS-PEDCO-120-ME-SP-0004 | BK | GCS | PEDCO | 120 | ME | SP | 0004 | F0Z-708822 | AFD | IFC | 2021-08-28 | 2021-08-31 | 0 | 3 | -44439 | -44436 | IFA | 2021-10-18 | 2021-11-02 | 2021-11-07 | 15 | 5 | 20 | IFA | 2021-11-28 | 2021-12-13 | 2021-12-18 | 15 | 5 | 20 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-14 | 0 |  | D02 | IFA | T-0232 | 2021-11-14 | 1400/08/23 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02102 | 2021-11-27 | 1400/09/06 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0004_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-316960 | 2021-12-13 | 1400/09/23 | 2021-12-18 | 1400/09/27 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0004-D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | 1400/06/15 | CM-C3 | [6 empty] | 1400/2294/181003 | 2021-08-31 | 1400/06/09 |  |  | CM | [10 empty] | D01 | IFA | T-0135 | 2021-10-04 | 1400/07/12 |  |  |  | BK-SUR-ENG-ROE-00-01844 | 2021-10-26 | 1400/08/04 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0004_D00 | [5 empty] | 1400-2294-259326 | 2021-11-02 | 1400/08/11 | 2021-11-07 | 1400/08/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0004-D00 | [9 empty] | D02 | IFA | T-0232 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-MEC-00-02102 | 2021-11-27 | 1400/09/06 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0004_D01 | [5 empty] | 1400-2294-316960 | 2021-12-13 | 1400/09/23 | 2021-12-18 | 1400/09/27 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0004-D01
3 | 2 | 3 | 2 | 1 | 2 | 4 | 3.2.3.2.1.2.4 | Specification For Fire Water Pumps | BK-GCS-PEDCO-120-ME-SP-0005 | BK-GCS-PEDCO-120-ME-SP-0005 | BK | GCS | PEDCO | 120 | ME | SP | 0005 | F0Z-708823 | AFD | IFC | 2021-09-05 | 2021-08-31 | 2021-09-12 | -5 | 12 | 7 | IFA | 2021-10-20 | 2021-12-29 | 2021-10-30 | 70 | -60 | 10 | IFA | 2022-01-25 | 2022-02-26 | 2022-03-02 | 32 | 4 | 36 | IFA | 2022-03-20 | 2022-04-12 | 2022-04-18 | 23 | 6 | 29 | AFD | 2022-05-03 | 2022-04-28 | 2022-05-01 | -5 | 3 | -2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-22 | 2022-04-19 |  | D04 | AFD | T-0841 | 2022-04-19 | 1401/01/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42947 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0053 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-ROE-00-01493 | 2021-09-12 | 1400/06/21 | CM-C3 | [6 empty] | 1400/2294/181002 | 2021-08-31 | 1400/06/09 | 2021-09-12 | 1400/06/21 | AP | [10 empty] | D01 | IFA | T-0138 | 2021-10-06 | 1400/07/14 |  |  |  | BK-SUR-ENG-MEC-00-01868 | 2021-10-30 | 1400/08/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0005-D00 | [5 empty] | 1400-2294-257419 | 2021-12-29 | 1400/10/10 | 2021-10-30 | 1400/08/08 | CM | [10 empty] | D02 | IFA | T-0447 | 2022-01-11 | 1400/10/20 |  |  |  | BK-SUR-ENG-MEC-00-02798 | 2022-01-24 | 1400/11/04 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0005_D01 | [5 empty] | 1400-2294-426688 | 2022-02-26 | 1400/12/07 | 2022-03-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0005_D01 | [9 empty] | D03 | IFA | T-0681 | 2022-03-06 | 1400/12/15 | [13 empty] | 1401-2294-20728 | 2022-04-12 | 1401/01/23 | 2022-04-18 | 1401/01/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0005_D02 | [9 empty] | D04 | AFD | T-0841 | 2022-04-19 | 1401/01/30 | [13 empty] | 1401-2294-42947 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | AP
3 | 2 | 3 | 2 | 1 | 2 | 5 | 3.2.3.2.1.2.5 | Specification For Overhead Travelling Cranes | BK-GCS-PEDCO-120-ME-SP-0009 | BK-GCS-PEDCO-120-ME-SP-0009 | BK | GCS | PEDCO | 120 | ME | SP | 0009 | F0Z-708824 | AFD | IFC | 2021-08-28 | 0 | 0 | -44436 | 0 | -44436 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-14 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 | 0 | 0 | 0 | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | 1400/06/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | 1400/06/15 | CM-C3
3 | 2 | 3 | 2 | 1 | 2 | 6 | 3.2.3.2.1.2.6 | Specification for Control Volume Pump (API 675) | BK-GCS-PEDCO-120-ME-SP-0011 | BK-GCS-PEDCO-120-ME-SP-0011 | BK | GCS | PEDCO | 120 | ME | SP | 0011 | F0Z-708825 | AFD | IFC | 2021-09-07 | 2021-09-15 | 2021-09-26 | 8 | 11 | 19 | IFA | 2021-10-20 | 2021-12-29 | 2021-10-30 | 70 | -60 | 10 | IFA | 2022-01-25 | 2022-02-26 | 2022-03-02 | 32 | 4 | 36 | IFA | 2022-03-20 | 2022-04-12 | 2022-04-18 | 23 | 6 | 29 | AFD | 2022-05-03 | 2022-04-28 | 2022-05-01 | -5 | 3 | -2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-24 | 2022-04-19 |  | D04 | AFD | T-0841 | 2022-04-19 | 1401/01/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42947 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0064 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-FXE-00-01501 | 2021-09-12 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-200596 | 2021-09-15 | 1400/06/24 | 2021-09-26 | 1400/07/04 | CM | [10 empty] | D01 | IFA | T-0138 | 2021-10-06 | 1400/07/14 |  |  |  | BK-SUR-ENG-MEC-00-01868 | 2021-10-30 | 1400/08/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0011-D00 | [5 empty] | 1400-2294-257419 | 2021-12-29 | 1400/10/10 | 2021-10-30 | 1400/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0011-D00 | [9 empty] | D02 | IFA | T-0447 | 2022-01-11 | 1400/10/20 |  |  |  | BK-SUR-ENG-MEC-00-02798 | 2022-01-24 | 1400/11/04 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0011-D01 | [5 empty] | 1400-2294-426688 | 2022-02-26 | 1400/12/07 | 2022-03-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0011_D01 | [9 empty] | D03 | IFA | T-0681 | 2022-03-06 | 1400/12/15 | [13 empty] | 1401-2294-20728 | 2022-04-12 | 1401/01/23 | 2022-04-18 | 1401/01/29 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0011_D02 | [9 empty] | D04 | AFD | T-0841 | 2022-04-19 | 1401/01/30 | [13 empty] | 1401-2294-42947 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | AP
3 | 2 | 3 | 2 | 1 | 2 | 7 | 3.2.3.2.1.2.7 | Specification For Diesel Engines | BK-GCS-PEDCO-120-ME-SP-0012 | BK-GCS-PEDCO-120-ME-SP-0012 | BK | GCS | PEDCO | 120 | ME | SP | 0012 | F0Z-708826 | AFD | IFC | 2021-09-07 | 2021-09-15 | 2021-09-26 | 8 | 11 | 19 | IFA | 2021-10-20 | 2021-12-29 | 2021-10-30 | 70 | -60 | 10 | IFA | 2022-02-01 | 2022-02-05 | 2022-02-05 | 4 | 0 | 4 | AFD | 2022-03-20 | 2022-03-10 | 2022-03-12 | -10 | 2 | -8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-24 | 2022-03-06 |  | D03 | AFD | T-0678 | 2022-03-06 | 1400/12/15 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03528 | 2022-03-13 | 1400/12/22 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443202 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0064 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-FXE-00-01501 | 2021-09-12 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-200596 | 2021-09-15 | 1400/06/24 | 2021-09-26 | 1400/07/04 | CM | [10 empty] | D01 | IFA | T-0138 | 2021-10-06 | 1400/07/14 |  |  |  | BK-SUR-ENG-MEC-00-01868 | 2021-10-30 | 1400/08/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0012-D00 | [5 empty] | 1400-2294-257419 | 2021-12-29 | 1400/10/08 | 2021-10-30 | 1400/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0012-D00 | [9 empty] | D02 | IFA | T-0477 | 2022-01-18 | 1400/10/28 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0012_D01 | [5 empty] | 1400-2294-397224 | 2022-02-05 | 1400/11/16 | 2022-02-05 | 1400/11/16 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0012_D01 | [9 empty] | D03 | AFD | T-0678 | 2022-03-06 | 1400/12/15 |  |  |  | BK-SUR-ENG-MEC-00-03528 | 2022-03-13 | 1400/12/22 | AP | [6 empty] | 1400-2294-443202 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | AP
3 | 2 | 3 | 2 | 1 | 3 | 0 | 3.2.2.1.3 | Packaged Equipment
3 | 2 | 3 | 2 | 1 | 3 | 1 | 3.2.3.2.1.3.1 | Specification For Air Compressor Package | BK-GCS-PEDCO-120-ME-SP-0006 | BK-GCS-PEDCO-120-ME-SP-0006 | BK | GCS | PEDCO | 120 | ME | SP | 0006 | F0Z-708827 | AFD | IFC | 2021-08-28 | 2021-08-31 | 0 | 3 | -44439 | -44436 | IFA | 2021-10-18 | 2021-11-02 | 2021-11-07 | 15 | 5 | 20 | IFA | 2021-11-28 | 2021-12-13 | 2021-12-18 | 15 | 5 | 20 | IFA | 2022-01-12 | 2022-01-20 | 2022-01-24 | 8 | 4 | 12 | IFA | 2022-02-12 | 2022-02-26 | 2022-03-02 | 14 | 4 | 18 | AFD | 2022-03-21 | 0 | 0 | -44641 | 0 | -44641 | Modify | 2021-08-14 | 2022-03-07 |  | D05 | AFD | T-0690 | 2022-03-07 | 1400/12/16 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03453 | 2022-03-12 | 1400/12/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | 1400/06/15 | CM-C3 | [6 empty] | 1400/2294/181003 | 2021-08-31 | 1400/06/09 |  |  | CM | [10 empty] | D01 | IFA | T-0135 | 2021-10-04 | 1400/07/12 |  |  |  | BK-SUR-ENG-ROE-00-01844 | 2021-10-26 | 1400/08/04 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0006_D00 | [5 empty] | 1400-2294-259326 | 2021-11-02 | 1400/08/11 | 2021-11-07 | 1400/08/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0006_D00 | [9 empty] | D02 | IFA | T-0232 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-MEC-00-02102 | 2021-11-27 | 1400/09/06 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0006_D01 | [5 empty] | 1400-2294-316960 | 2021-12-13 | 1400/09/22 | 2021-12-18 | 1400/09/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0006-D01 | [9 empty] | D03 | IFA | T-0400 | 2021-12-29 | 1400/10/08 | [13 empty] | 1400-2294-372899 | 2022-01-20 | 1400/10/30 | 2022-01-24 | 1400/11/04 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0006_D02 | [9 empty] | D04 | IFA | T-0518 | 2022-01-29 | 1400/11/09 | [13 empty] | 1400-2294-426614 | 2022-02-26 | 1400/12/07 | 2022-03-02 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0006_D03 | [9 empty] | D05 | AFD | T-0690 | 2022-03-07 | 1400/12/16 |  |  |  | BK-SUR-ENG-MEC-00-03453 | 2022-03-12 | 1400/12/21 | CM-C3
3 | 2 | 3 | 2 | 1 | 3 | 2 | 3.2.3.2.1.3.2 | Specification For Air Dryer Package | BK-GCS-PEDCO-120-ME-SP-0007 | BK-GCS-PEDCO-120-ME-SP-0007 | BK | GCS | PEDCO | 120 | ME | SP | 0007 | F0Z-708828 | AFD | IFC | 2021-08-28 | 0 | 0 | -44436 | 0 | -44436 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-14 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 | 0 | 0 | 0 | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | 1400/06/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0048 | 2021-08-14 | 1400/05/23 |  |  |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | 1400/06/15 | CM-C3
3 | 2 | 3 | 2 | 1 | 3 | 3 | 3.2.3.2.1.3.3 | Specification For Chemical Injection Package | BK-GCS-PEDCO-120-ME-SP-0008 | BK-GCS-PEDCO-120-ME-SP-0008 | BK | GCS | PEDCO | 120 | ME | SP | 0008 | F0Z-708829 | AFD | IFC | 2021-09-05 | 2021-08-22 | 2022-04-17 | -14 | 238 | 224 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D00 | IFC | T-0053 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-ROE-00-01493 | 2021-09-12 | 1400/06/21 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-81002 | 2021-08-22 | 1400/06/09 | 2022-04-17 | 1401/01/28 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0053 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-ROE-00-01493 | 2021-09-12 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-81002 | 2021-08-22 | 1400/06/09 | 2022-04-17 | 1401/01/28 | RJ
3 | 2 | 3 | 2 | 1 | 3 | 4 | 3.2.3.2.1.3.4 | Specification For Flare Package | BK-GCS-PEDCO-120-ME-SP-0013 | BK-GCS-PEDCO-120-ME-SP-0013 | BK | GCS | PEDCO | 120 | ME | SP | 0013 | F0Z-708830 | AFD | IFC | 2021-09-07 | 2021-09-15 | 2021-09-26 | 8 | 11 | 19 | IFA | 2021-10-20 | 2021-12-29 | 2021-10-30 | 70 | -60 | 10 | IFA | 2022-02-05 | 0 | 0 | -44597 | 0 | -44597 | AFD | 2022-03-23 | 0 | 0 | -44643 | 0 | -44643 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-24 | 2022-03-09 |  | D03 | AFD | T-0710 | 2022-03-09 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03458 | 2022-03-12 | 1400/12/21 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0013_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0064 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-FXE-00-01501 | 2021-09-12 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-200596 | 2021-09-15 | 1400/06/24 | 2021-09-26 | 1400/07/04 | CM | [10 empty] | D01 | IFA | T-0138 | 2021-10-06 | 1400/07/14 |  |  |  | BK-SUR-ENG-MEC-00-01868 | 2021-10-30 | 1400/08/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0013-D00 | [5 empty] | 1400-2294-257419 | 2021-12-29 | 1400/08/10 | 2021-10-30 | 1400/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0013-D00 | [9 empty] | D02 | IFA | T-0493 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-MEC-00-03348 | 2022-03-05 | 1400/12/14 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0013_D01 | [10 empty] | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0013_D01 | [9 empty] | D03 | AFD | T-0710 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-MEC-00-03458 | 2022-03-12 | 1400/12/21 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0013_D02
3 | 2 | 3 | 2 | 1 | 3 | 5 | 3.2.3.2.1.3.5 | Specification For Nitrogen Package | BK-GCS-PEDCO-120-ME-SP-0014 | BK-GCS-PEDCO-120-ME-SP-0014 | BK | GCS | PEDCO | 120 | ME | SP | 0014 | F0Z-708831 | AFD | IFC | 2021-09-07 | 2021-09-22 | 2021-09-26 | 15 | 4 | 19 | IFA | 2021-10-20 | 2021-12-29 | 2021-10-30 | 70 | -60 | 10 | IFA | 2022-02-21 | 2022-03-01 | 2022-03-05 | 8 | 4 | 12 | IFA | 2022-04-09 | 2022-04-16 | 2022-01-18 | 7 | -88 | -81 | IFA | 2022-05-03 | 2022-04-30 | 2022-05-07 | -3 | 7 | 4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-06 | 0 |  | D04 | IFA | T-0847 | 2022-04-19 | 1401/01/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-45435 | 2022-04-30 | 1401/02/10 | 2022-05-07 | 14014/02/17 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0014_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0064 | 2021-08-24 | 1400/06/02 |  |  |  | BK-SUR-ENG-FXE-00-01501 | 2021-09-12 | 1400/06/21 | CM-C3 | [6 empty] | 1400-2294-208212 | 2021-09-22 | 1400/06/31 | 2021-09-26 | 1400/07/04 | RJ | [10 empty] | D01 | IFA | T-0138 | 2021-10-06 | 1400/07/14 |  |  |  | BK-SUR-ENG-MEC-00-01868 | 2021-10-30 | 1400/08/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0014-D00 | [5 empty] | 1400-2294-257419 | 2021-12-29 | 1400/08/10 | 2021-10-30 | 1400/08/08 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0014-D00 | [9 empty] | D02 | IFA | T-0559 | 2022-02-07 | 1400/11/18 |  |  |  | BK-SUR-ENG-MEC-00-03350 | 2022-03-05 | 1400/12/15 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0014_D01 | [5 empty] | 1400-2294-430719 | 2022-03-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0014_D01 | [9 empty] | D03 | IFA | T_0740 | 2022-03-26 | 1401/01/06 | [13 empty] | 1401-2294-25146 | 2022-04-16 | 1401/01/27 | 2022-01-18 | 1401/01/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0014_D02 | [9 empty] | D04 | IFA | T-0847 | 2022-04-19 | 1401/01/30 | [13 empty] | 1401-2294-45435 | 2022-04-30 | 1401/02/10 | 2022-05-07 | 14014/02/17 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0014_D03
3 | 2 | 3 | 2 | 2 | 0 | 0 | 3.2.3.2.2 | Data Sheets
3 | 2 | 3 | 2 | 2 | 1 | 0 | 3.2.2.2.1 | Fixed Equipment
3 | 2 | 3 | 2 | 2 | 1 | 1 | 3.2.3.2.2.1.1 | Mechanical Data Sheets For Inlet Gas K.O. Drum | BK-GCS-PEDCO-120-ME-DT-0001 | BK-GCS-PEDCO-120-ME-DT-0001 | BK | GCS | PEDCO | 120 | ME | DT | 0001 | F0Z-708832 | AFC | IFC | 2021-12-21 | 2021-12-20 | 2021-12-27 | -1 | 7 | 6 | IFA | 2022-01-26 | 2022-01-29 | 2022-02-05 | 3 | 7 | 10 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-07 | 0 |  | D01 | IFA | T-0456 | 2022-01-12 | 1400/10/22 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03587 | 2022-03-15 | 1400/12/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-386693 | 2022-01-29 | 1400/11/09 | 2022-02-05 | 1400/11/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0306 | 2021-12-07 | 1400/09/17 | [13 empty] | 1400-2294-327362 | 2021-12-20 | 1400/09/29 | 2021-12-27 | 1400/10/06 | CM | [10 empty] | D01 | IFA | T-0456 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-MEC-00-03587 | 2022-03-15 | 1400/12/24 | CM-C3 | [6 empty] | 1400-2294-386693 | 2022-01-29 | 1400/11/09 | 2022-02-05 | 1400/11/16 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0001_D00
3 | 2 | 3 | 2 | 2 | 1 | 2 | 3.2.3.2.2.1.2 | Mechanical Data Sheets For 1st Stage G.C. Suction Drums | BK-GCS-PEDCO-120-ME-DT-0002 | BK-GCS-PEDCO-120-ME-DT-0002 | BK | GCS | PEDCO | 120 | ME | DT | 0002 | F0Z-708833 | AFC | IFC | 2021-12-27 | 2021-12-26 | 2022-01-05 | -1 | 10 | 9 | IFA | 2022-02-01 | 2022-01-29 | 2022-04-19 | -3 | 80 | 77 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 0 |  | D01 | IFA | T-0473 | 2022-01-18 | 1400/10/28 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03607 | 2022-03-15 | 1400/12/24 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-386730 | 2022-01-29 | 1400/11/09 | 2022-04-19 | 1401/01/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0342 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-MEC-00-02543 | 2022-01-03 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-336157 | 2021-12-26 | 1400/10/05 | 2022-01-05 | 1400/10/15 | CM | [10 empty] | D01 | IFA | T-0473 | 2022-01-18 | 1400/10/28 |  |  |  | BK-SUR-ENG-MEC-00-03607 | 2022-03-15 | 1400/12/24 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0002_D00 | [5 empty] | 1400-2294-386730 | 2022-01-29 | 1400/11/09 | 2022-04-19 | 1401/01/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0002_D00
3 | 2 | 3 | 2 | 2 | 1 | 3 | 3.2.3.2.2.1.3 | Mechanical Data Sheets For 1st Stage Gas Air Coolers | BK-GCS-PEDCO-120-ME-DT-0003 | BK-GCS-PEDCO-120-ME-DT-0003 | BK | GCS | PEDCO | 120 | ME | DT | 0003 | F0Z-708834 | AFC | IFC | 2022-01-12 | 0 | 0 | -44573 | 0 | -44573 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-29 | 0 |  | D00 | IFC | T-0401 | 2021-12-29 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02838 | 2022-01-29 | 1400/11/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0401 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-MEC-00-02838 | 2022-01-29 | 1400/11/09 | CM-C3
3 | 2 | 3 | 2 | 2 | 1 | 4 | 3.2.3.2.2.1.4 | Mechanical Data Sheets For 2nd Stage G.C. Suction Drums | BK-GCS-PEDCO-120-ME-DT-0004 | BK-GCS-PEDCO-120-ME-DT-0004 | BK | GCS | PEDCO | 120 | ME | DT | 0004 | F0Z-708835 | AFC | IFC | 2021-12-27 | 2021-12-26 | 2022-01-05 | -1 | 10 | 9 | IFA | 2022-02-01 | 2022-02-24 | 2022-03-02 | 23 | 6 | 29 | IFA | 2022-05-21 | 0 | 0 | -44702 | 0 | -44702 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 0 |  | D02 | IFA | T-0902 | 2022-05-07 | 1401/02/17 | T-0902 | 2022-05-07 | 1401/02/17 | BK-SUR-ENG-MEC-01-04179 | 2022-05-09 | 1401/02/19 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0342 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-MEC-00-02543 | 2022-01-03 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-336157 | 2021-12-26 | 1400/10/05 | 2022-01-05 | 1400/10/15 | CM | [10 empty] | D01 | IFA | T-0476 | 2022-01-18 | 1400/10/28 |  |  |  | BK-SUR-ENG-MEC-00-03539 | 2022-03-14 | 1400/12/23 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0004_D00 | [5 empty] | 1400-2294-424206 | 2022-02-24 | 1400/12/05 | 2022-03-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0004_D00 | [9 empty] | D02 | IFA | T-0902 | 2022-05-07 | 1401/02/17 | T-0902 | 2022-05-07 | 1401/02/17 | BK-SUR-ENG-MEC-01-04179 | 2022-05-09 | 1401/02/19 | CM-C3 | [12 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0004_D01
3 | 2 | 3 | 2 | 2 | 1 | 5 | 3.2.3.2.2.1.5 | Mechanical Data Sheets For 2nd Stage Gas Air Coolers | BK-GCS-PEDCO-120-ME-DT-0005 | BK-GCS-PEDCO-120-ME-DT-0005 | BK | GCS | PEDCO | 120 | ME | DT | 0005 | F0Z-708836 | AFC | IFC | 2022-01-12 | 0 | 0 | -44573 | 0 | -44573 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-29 | 0 |  | D00 | IFC | T-0401 | 2021-12-29 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02838 | 2022-01-29 | 1400/11/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0401 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-MEC-00-02838 | 2022-01-29 | 1400/11/09 | CM-C3
3 | 2 | 3 | 2 | 2 | 1 | 6 | 3.2.3.2.2.1.6 | Mechanical Data Sheets For Discharge Gas K.O. Drum | BK-GCS-PEDCO-120-ME-DT-0006 | BK-GCS-PEDCO-120-ME-DT-0006 | BK | GCS | PEDCO | 120 | ME | DT | 0006 | F0Z-708837 | AFC | IFC | 2022-01-10 | 2022-01-03 | 2022-01-04 | -7 | 1 | -6 | IFA | 2022-01-25 | 2022-02-26 | 2022-03-02 | 32 | 4 | 36 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-27 | 0 |  | D01 | IFA | T-0447 | 2022-01-11 | 1400/10/20 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02798 | 2022-01-24 | 1400/11/04 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-426688 | 2022-02-26 | 1400/12/07 | 2022-03-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0386 | 2021-12-27 | 1400/10/06 |  |  |  | BK-SUR-ENG-MEC-00-02552 | 2022-01-03 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-346502 | 2022-01-03 | 1400/10/13 | 2022-01-04 | 1400/10/14 | CM | [10 empty] | D01 | IFA | T-0447 | 2022-01-11 | 1400/10/20 |  |  |  | BK-SUR-ENG-MEC-00-02798 | 2022-01-24 | 1400/11/04 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0006_D00 | [5 empty] | 1400-2294-426688 | 2022-02-26 | 1400/12/07 | 2022-03-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0006_D00
3 | 2 | 3 | 2 | 2 | 1 | 7 | 3.2.3.2.2.1.7 | Mechanical Data Sheets For Diesel Oil Drum | BK-GCS-PEDCO-120-ME-DT-0007 | BK-GCS-PEDCO-120-ME-DT-0007 | BK | GCS | PEDCO | 120 | ME | DT | 0007 | F0Z-708838 | AFC | IFC | 2021-12-27 | 0 | 0 | -44557 | 0 | -44557 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 0 |  | D00 | IFC | T-0338 | 2021-12-13 | 1400/09/23 | 0 | 0 | 0 | BK-SUR-ENG-FXE-00-02541 | 2022-01-03 | 1400/10/13 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0338 | 2021-12-13 | 1400/09/23 |  |  |  | BK-SUR-ENG-FXE-00-02541 | 2022-01-03 | 1400/10/13 | CM-C3
3 | 2 | 3 | 2 | 2 | 1 | 8 | 3.2.3.2.2.1.8 | Mechanical Data Sheets For Instrument Air Receiver | BK-GCS-PEDCO-120-ME-DT-0008 | BK-GCS-PEDCO-120-ME-DT-0008 | BK | GCS | PEDCO | 120 | ME | DT | 0008 | F0Z-708839 | AFC | IFC | 2021-12-21 | 0 | 0 | -44551 | 0 | -44551 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-07 | 0 |  | D00 | IFC | T-0311 | 2021-12-07 | 1400/09/16 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02824 | 2022-01-26 | 1400/11/09 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0311 | 2021-12-07 | 1400/09/16 |  |  |  | BK-SUR-ENG-MEC-00-02824 | 2022-01-26 | 1400/11/09 | CM-C3
3 | 2 | 3 | 2 | 2 | 1 | 9 | 3.2.3.2.2.1.9 | Mechanical Data Sheets For Nitrogen Receiver | BK-GCS-PEDCO-120-ME-DT-0009 | BK-GCS-PEDCO-120-ME-DT-0009 | BK | GCS | PEDCO | 120 | ME | DT | 0009 | F0Z-708840 | AFC | IFC | 2021-12-11 | 2021-12-14 | 2021-12-20 | 3 | 6 | 9 | IFA | 2022-01-09 | 2021-12-30 | 2022-01-05 | -10 | 6 | -4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-27 | 0 |  | D01 | IFA | T-0381 | 2021-12-26 | 1400/10/05 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03340 | 2022-03-05 | 1400/12/14 | CM-C3 | PEDCO_CRS-BK-GCS-PEDCO-120-ME-DT-0009_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-342154 | 2021-12-30 | 1400/10/09 | 2022-01-05 | 1400/10/15 | CM | NISOC_CRS-BK-GCS-PEDCO-120-ME-DT-0009_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0270 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-MEC-00-02294 | 2021-12-15 | 1400/09/24 | CM-C2 | [6 empty] | 1400-2294-318812 | 2021-12-14 | 1400/09/23 | 2021-12-20 | 1400/09/29 | CM | [10 empty] | D01 | IFA | T-0381 | 2021-12-26 | 1400/10/05 |  |  |  | BK-SUR-ENG-MEC-00-03340 | 2022-03-05 | 1400/12/14 | CM-C3 | PEDCO_CRS-BK-GCS-PEDCO-120-ME-DT-0009_D00 | [5 empty] | 1400-2294-342154 | 2021-12-30 | 1400/10/09 | 2022-01-05 | 1400/10/15 | CM | NISOC_CRS-BK-GCS-PEDCO-120-ME-DT-0009_D00
3 | 2 | 3 | 2 | 2 | 1 | 10 | 3.2.3.2.2.1.10 | Mechanical Data Sheets For Close Drain Drum | BK-GCS-PEDCO-120-ME-DT-0010 | BK-GCS-PEDCO-120-ME-DT-0010 | BK | GCS | PEDCO | 120 | ME | DT | 0010 | F0Z-708841 | AFC | IFC | 2021-12-27 | 2021-12-22 | 2021-12-27 | -5 | 5 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 0 |  | D00 | IFC | T-0339 | 2021-12-13 | 1400/09/23 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02542 | 2022-01-03 | 1400/10/13 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-331625 | 2021-12-22 | 1400/10/01 | 2021-12-27 | 1400/10/06 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0339 | 2021-12-13 | 1400/09/23 |  |  |  | BK-SUR-ENG-MEC-00-02542 | 2022-01-03 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-331625 | 2021-12-22 | 1400/10/01 | 2021-12-27 | 1400/10/06 | CM
3 | 2 | 3 | 2 | 2 | 1 | 11 | 3.2.3.2.2.1.11 | Mechanical Data Sheets For Elevated Potable Water Tank | BK-GCS-PEDCO-120-ME-DT-0011 | BK-GCS-PEDCO-120-ME-DT-0011 | BK | GCS | PEDCO | 120 | ME | DT | 0011 | F0Z-708842 | AFC | IFC | 2021-12-11 | 2021-12-14 | 2021-12-20 | 3 | 6 | 9 | IFA | 2022-01-08 | 2022-01-03 | 2022-01-04 | -5 | 1 | -4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-27 | 0 |  | D01 | IFA | T-0377 | 2021-12-25 | 1400/10/04 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03338 | 2022-03-05 | 1400/12/14 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0011_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-347297 | 2022-01-03 | 1400/10/13 | 2022-01-04 | 1400/10/14 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0011_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0270 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-MEC-00-02294 | 2021-12-15 | 1400/09/24 | CM-C2 | [6 empty] | 1400-2294-318813 | 2021-12-14 | 1400/09/23 | 2021-12-20 | 1400/09/29 | CM | [10 empty] | D01 | IFA | T-0377 | 2021-12-25 | 1400/10/04 |  |  |  | BK-SUR-ENG-MEC-00-03338 | 2022-03-05 | 1400/12/14 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0011_D00 | [5 empty] | 1400-2294-347297 | 2022-01-03 | 1400/10/13 | 2022-01-04 | 1400/10/14 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0011_D00
3 | 2 | 3 | 2 | 2 | 1 | 12 | 3.2.3.2.2.1.12 | Mechanical Data Sheets For Flare K.O. Drum | BK-GCS-PEDCO-120-ME-DT-0012 | BK-GCS-PEDCO-120-ME-DT-0012 | BK | GCS | PEDCO | 120 | ME | DT | 0012 | F0Z-708843 | AFC | IFC | 2022-01-17 | 2022-01-18 | 2022-01-24 | 1 | 6 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-03 | 0 |  | D00 | IFC | T-0421 | 2022-01-03 | 1400/10/13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-368388 | 2022-01-18 | 1400/10/27 | 2022-01-24 | 1400/11/04 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0421 | 2022-01-03 | 1400/10/13 | [13 empty] | 1400-2294-368388 | 2022-01-18 | 1400/10/27 | 2022-01-24 | 1400/11/04 | CM
3 | 2 | 3 | 2 | 2 | 1 | 13 | 3.2.3.2.2.1.13 | Mechanical Data Sheets For Fuel Gas K.O. Drum | BK-GCS-PEDCO-120-ME-DT-0013 | BK-GCS-PEDCO-120-ME-DT-0013 | BK | GCS | PEDCO | 120 | ME | DT | 0013 | F0Z-708844 | AFC | IFC | 2021-12-27 | 2021-12-26 | 2022-01-05 | -1 | 10 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 0 |  | D00 | IFC | T-0342 | 2021-12-13 | 1400/09/22 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02543 | 2022-01-03 | 1400/10/13 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-336157 | 2021-12-26 | 1400/10/05 | 2022-01-05 | 1400/10/15 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0342 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-MEC-00-02543 | 2022-01-03 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-336157 | 2021-12-26 | 1400/10/05 | 2022-01-05 | 1400/10/15 | CM
3 | 2 | 3 | 2 | 2 | 1 | 14 | 3.2.3.2.2.1.14 | Mechanical Data Sheets For Slug Catcher | BK-GCS-PEDCO-120-ME-DT-0014 | BK-GCS-PEDCO-120-ME-DT-0014 | BK | GCS | PEDCO | 120 | ME | DT | 0014 | F0Z-708845 | AFC | IFC | 2022-01-11 | 2021-06-06 | 2022-04-19 | -219 | 317 | 98 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-28 | 0 |  | D00 | IFC | T-0389 | 2021-12-28 | 1400/10/07 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03364 | 2022-03-06 | 1400/12/15 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-352384 | 2021-06-06 | 1400/10/16 | 2022-04-19 | 1401/01/30 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0389 | 2021-12-28 | 1400/10/07 |  |  |  | BK-SUR-ENG-MEC-00-03364 | 2022-03-06 | 1400/12/15 | CM-C3 | [6 empty] | 1400-2294-352384 | 2021-06-06 | 1400/10/16 | 2022-04-19 | 1401/01/30 | CM
3 | 2 | 3 | 2 | 2 | 1 | 15 | 3.2.3.2.2.1.15 | Mechanical Data Sheets For Degassing Vessel | BK-GCS-PEDCO-120-ME-DT-0015 | BK-GCS-PEDCO-120-ME-DT-0015 | BK | GCS | PEDCO | 120 | ME | DT | 0015 | F0Z-708846 | AFC | IFC | 2022-03-20 | 2022-03-15 | 2022-03-26 | -5 | 11 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-06 | 0 |  | D00 | IFC | T-0680 | 2022-03-06 | 1400/12/15 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-03746 | 2022-04-06 | 1401/01/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-451028 | 2022-03-15 | 1400/12/24 | 2022-03-26 | 1401/01/09 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0680 | 2022-03-06 | 1400/12/15 |  |  |  | BK-SUR-ENG-MEC-01-03746 | 2022-04-06 | 1401/01/17 | CM-C3 | [6 empty] | 1400-2294-451028 | 2022-03-15 | 1400/12/24 | 2022-03-26 | 1401/01/09 | AP
3 | 2 | 3 | 2 | 2 | 1 | 16 | 3.2.3.2.2.1.16 | Mechanical Data Sheets For Lean Glycol Storage Tank | BK-GCS-PEDCO-120-ME-DT-0016 | BK-GCS-PEDCO-120-ME-DT-0016 | BK | GCS | PEDCO | 120 | ME | DT | 0016 | F0Z-708847 | AFC | IFC | 2021-12-12 | 2021-12-14 | 2021-12-20 | 2 | 6 | 8 | IFA | 2022-01-12 | 2022-01-06 | 2022-01-04 | -6 | -2 | -8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-28 | 0 |  | D01 | IFA | T-0406 | 2021-12-29 | 1400/10/08 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02824 | 2022-01-26 | 1400/11/09 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0016_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-352427 | 2022-01-06 | 1400/10/16 | 2022-01-04 | 1400/10/14 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0016_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0279 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-MEC-00-02303 | 2021-12-15 | 1400/09/24 | CM-C2 | [6 empty] | 1400-2294-318686 | 2021-12-14 | 1400/09/23 | 2021-12-20 | 1400/09/29 | CM | [10 empty] | D01 | IFA | T-0406 | 2021-12-29 | 1400/10/08 |  |  |  | BK-SUR-ENG-MEC-00-02824 | 2022-01-26 | 1400/11/09 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0016_D00 | [5 empty] | 1400-2294-352427 | 2022-01-06 | 1400/10/16 | 2022-01-04 | 1400/10/14 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0016_D00
3 | 2 | 3 | 2 | 2 | 1 | 17 | 3.2.3.2.2.1.17 | Mechanical Data Sheets For Fire Water Storage Tank | BK-GCS-PEDCO-120-ME-DT-0017 | BK-GCS-PEDCO-120-ME-DT-0017 | BK | GCS | PEDCO | 120 | ME | DT | 0017 | F0Z-708848 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 2 | 2 | 1 | 18 | 3.2.3.2.2.1.18 | Mechanical Data Sheets For Slug Storage Tank | BK-GCS-PEDCO-120-ME-DT-0018 | BK-GCS-PEDCO-120-ME-DT-0018 | BK | GCS | PEDCO | 120 | ME | DT | 0018 | F0Z-708849 | AFC | IFC | 2021-12-28 | 2021-12-22 | 2021-12-27 | -6 | 5 | -1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-14 | 0 |  | D00 | IFC | T-0344 | 2021-12-14 | 1400/09/23 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02551 | 2022-01-03 | 1400/10/13 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-330580 | 2021-12-22 | 1400/10/01 | 2021-12-27 | 1400/10/06 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0344 | 2021-12-14 | 1400/09/23 |  |  |  | BK-SUR-ENG-MEC-00-02551 | 2022-01-03 | 1400/10/13 | CM-C3 | [6 empty] | 1400-2294-330580 | 2021-12-22 | 1400/10/01 | 2021-12-27 | 1400/10/06 | CM
3 | 2 | 3 | 2 | 2 | 2 | 0 | 3.2.2.2.2 | Rotary Equipment
3 | 2 | 3 | 2 | 2 | 2 | 1 | 3.2.3.2.2.2.1 | Mechanical Data Sheets For Slug Pumps | BK-GCS-PEDCO-120-ME-DT-0019 | BK-GCS-PEDCO-120-ME-DT-0019 | BK | GCS | PEDCO | 120 | ME | DT | 0019 | F0Z-708850 | AFC | IFC | 2021-12-21 | 2021-12-20 | 2021-12-27 | -1 | 7 | 6 | IFA | 2022-02-05 | 2022-02-24 | 2022-03-02 | 19 | 6 | 25 | AFC | 2022-04-26 | 0 | 0 | -44677 | 0 | -44677 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-07 | 2022-04-12 |  | D02 | AFC | T-0811 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-03989 | 2022-04-19 | 1401/01/30 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0019_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0306 | 2021-12-07 | 1400/09/17 | [13 empty] | 1400-2294-327362 | 2021-12-20 | 1400/09/29 | 2021-12-27 | 1400/10/06 | CM | [10 empty] | D01 | IFA | T-0493 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-MEC-00-03348 | 2022-03-05 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-424207 | 2022-02-24 | 1400/12/05 | 2022-03-02 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0019_D00 | [9 empty] | D02 | AFC | T-0811 | 2022-04-12 | 1401/01/23 |  |  |  | BK-SUR-ENG-MEC-01-03989 | 2022-04-19 | 1401/01/30 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0019_D01
3 | 2 | 3 | 2 | 2 | 2 | 2 | 3.2.3.2.2.2.2 | Mechanical Data Sheets For Glycol Transfer Pumps | BK-GCS-PEDCO-120-ME-DT-0020 | BK-GCS-PEDCO-120-ME-DT-0020 | BK | GCS | PEDCO | 120 | ME | DT | 0020 | F0Z-708851 | AFC | IFC | 2021-12-11 | 2021-12-20 | 2021-12-27 | 9 | 7 | 16 | IFA | 2022-02-07 | 2022-02-24 | 2022-03-02 | 17 | 6 | 23 | IFA | 2022-03-23 | 2022-03-16 | 2022-03-29 | -7 | 13 | 6 | AFC | 2022-04-26 | 2022-05-12 | 2022-05-22 | 16 | 10 | 26 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-27 | 2022-04-12 |  | D03 | AFC | T-0778 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59445 | 2022-05-12 | 1401/02/22 | 2022-05-22 | 1401/03/01 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0270 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-MEC-00-02294 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-318812 | 2021-12-14 | 1400/09/23 | 2021-12-20 | 1400/09/29 | CM |  | 1400-2294-327356 | 2021-12-20 | 1400/09/29 | 2021-12-27 | 1400/10/06 | CM |  |  |  | D01 | IFA | T-0497 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-MEC-00-02887 | 2022-01-31 | 1400/11/11 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0020_D00 | [5 empty] | 1400-2294-424141 | 2022-02-24 | 1400/12/05 | 2022-03-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0020_D00 | [9 empty] | D02 | IFA | T-0706 | 2022-03-09 | 1400/12/18 | [13 empty] | 1400-2294-453306 | 2022-03-16 | 1400/12/25 | 2022-03-29 | 1401/01/09 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0020_D01 | [9 empty] | D03 | AFC | T-0778 | 2022-04-12 | 1401/01/23 | [13 empty] | 1401-2294-59445 | 2022-05-12 | 1401/02/22 | 2022-05-22 | 1401/03/01 | AP
3 | 2 | 3 | 2 | 2 | 2 | 3 | 3.2.3.2.2.2.3 | Mechanical Data Sheets For Glycol Manual Pump | BK-GCS-PEDCO-120-ME-DT-0021 | BK-GCS-PEDCO-120-ME-DT-0021 | BK | GCS | PEDCO | 120 | ME | DT | 0021 | F0Z-708852 | AFC | IFC | 2021-12-11 | 2021-12-20 | 2021-12-27 | 9 | 7 | 16 | IFA | 2022-02-07 | 2022-02-24 | 2022-03-02 | 17 | 6 | 23 | IFA | 2022-03-23 | 2022-03-16 | 2022-03-29 | -7 | 13 | 6 | AFC | 2022-04-26 | 2022-05-12 | 2022-05-22 | 16 | 10 | 26 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-27 | 2022-04-12 |  | D03 | AFC | T-0778 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59445 | 2022-05-12 | 1401/02/22 | 2022-05-22 | 1401/03/01 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0270 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-MEC-00-02294 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-318812 | 2021-12-14 | 1400/09/23 | 2021-12-20 | 1400/09/29 | CM |  | 1400-2294-327356 | 2021-12-20 | 1400/09/29 | 2021-12-27 | 1400/10/06 | CM |  |  |  | D01 | IFA | T-0497 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-MEC-00-02887 | 2022-01-31 | 1400/11/11 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0021_D00 | [5 empty] | 1400-2294-424141 | 2022-02-24 | 1400/12/05 | 2022-03-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0021_D00 | [9 empty] | D02 | IFA | T-0706 | 2022-03-09 | 1400/12/18 | [13 empty] | 1400-2294-453306 | 2022-03-16 | 1400/12/25 | 2022-03-29 | 1401/01/09 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0021_D01 | [9 empty] | D03 | AFC | T-0778 | 2022-04-12 | 1401/01/23 | [13 empty] | 1401-2294-59445 | 2022-05-12 | 1401/02/22 | 2022-05-22 | 1401/03/01 | AP
3 | 2 | 3 | 2 | 2 | 2 | 4 | 3.2.3.2.2.2.4 | Mechanical Data Sheets For Closed Drain Pumps | BK-GCS-PEDCO-120-ME-DT-0022 | BK-GCS-PEDCO-120-ME-DT-0022 | BK | GCS | PEDCO | 120 | ME | DT | 0022 | F0Z-708853 | AFC | IFC | 2021-12-11 | 2021-12-20 | 2021-12-27 | 9 | 7 | 16 | IFA | 2022-02-07 | 2022-02-24 | 2022-03-02 | 17 | 6 | 23 | IFA | 2022-03-22 | 2022-03-23 | 2022-03-26 | 1 | 3 | 4 | IFA | 2022-04-25 | 2022-04-28 | 2022-05-01 | 3 | 3 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-27 | 0 |  | D03 | IFA | T-0800 | 2022-04-11 | 1401/01/22 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-03932 | 2022-04-16 | 1401/01/27 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42955 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0022_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0270 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-MEC-00-02294 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-318812 | 2021-12-14 | 1400/09/23 | 2021-12-20 | 1400/09/29 | CM |  | 1400-2294-327356 | 2021-12-20 | 1400/09/29 | 2021-12-27 | 1400/10/06 | CM |  |  |  | D01 | IFA | T-0497 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-MEC-00-02887 | 2022-01-31 | 1400/11/11 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0022_D00 | [5 empty] | 1400-2294-424141 | 2022-02-24 | 1400/12/05 | 2022-03-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0022_D00 | [9 empty] | D02 | IFA | T-0701 | 2022-03-08 | 1400/12/17 | [13 empty] | 1401-2294-1324 | 2022-03-23 | 1401/01/06 | 2022-03-26 | 1401/01/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0022_D01 | 1400-2294-447218 | 2022-03-13 | 1400/12/22 | 2022-03-26 | 1401/01/09 | AP |  |  |  | D03 | IFA | T-0800 | 2022-04-11 | 1401/01/22 |  |  |  | BK-SUR-ENG-MEC-01-03932 | 2022-04-16 | 1401/01/27 | CM-C2 | [6 empty] | 1401-2294-42955 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0022_D02
3 | 2 | 3 | 2 | 2 | 2 | 5 | 3.2.3.2.2.2.5 | Mechanical Data Sheets For Sump Pumps | BK-GCS-PEDCO-120-ME-DT-0023 | BK-GCS-PEDCO-120-ME-DT-0023 | BK | GCS | PEDCO | 120 | ME | DT | 0023 | F0Z-708854 | AFC | IFC | 2021-12-21 | 2021-12-20 | 2021-12-27 | -1 | 7 | 6 | IFA | 2022-02-05 | 2022-02-24 | 2022-03-02 | 19 | 6 | 25 | AFC | 2022-04-10 | 0 | 0 | -44661 | 0 | -44661 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-07 | 2022-03-27 |  | D02 | AFC | T-0753 | 2022-03-27 | 1401/01/07 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-03729 | 2022-04-05 | 1401/01/16 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0023_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0306 | 2021-12-07 | 1400/09/17 | [13 empty] | 1400-2294-327362 | 2021-12-20 | 1400/09/29 | 2021-12-27 | 1400/10/06 | CM | [10 empty] | D01 | IFA | T-0493 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-MEC-00-03348 | 2022-03-05 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-424207 | 2022-02-24 | 1400/12/05 | 2022-03-02 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0023_D00 | [9 empty] | D02 | AFC | T-0753 | 2022-03-27 | 1401/01/07 |  |  |  | BK-SUR-ENG-MEC-01-03729 | 2022-04-05 | 1401/01/16 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0023_D01
3 | 2 | 3 | 2 | 2 | 2 | 6 | 3.2.3.2.2.2.6 | Mechanical Data Sheets For Flare KO Drum Pumps | BK-GCS-PEDCO-120-ME-DT-0024 | BK-GCS-PEDCO-120-ME-DT-0024 | BK | GCS | PEDCO | 120 | ME | DT | 0024 | F0Z-708855 | AFC | IFC | 2021-12-11 | 2021-12-20 | 2021-12-27 | 9 | 7 | 16 | IFA | 2022-02-07 | 2022-02-24 | 2022-03-02 | 17 | 6 | 23 | IFA | 2022-03-22 | 2022-03-23 | 2022-03-26 | 1 | 3 | 4 | IFA | 2022-04-25 | 2022-04-28 | 2022-05-01 | 3 | 3 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-27 | 0 |  | D03 | IFA | T-0800 | 2022-04-11 | 1401/01/22 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-03932 | 2022-04-16 | 1401/01/27 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-42955 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0024_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0270 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-MEC-00-02294 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-318812 | 2021-12-14 | 1400/09/23 | 2021-12-20 | 1400/09/29 | CM |  | 1400-2294-327356 | 2021-12-20 | 1400/09/29 | 2021-12-27 | 1400/10/06 | CM |  |  |  | D01 | IFA | T-0497 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-MEC-00-02887 | 2022-01-31 | 1400/11/11 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0024_D00 | [5 empty] | 1400-2294-424141 | 2022-02-24 | 1400/12/05 | 2022-03-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0024_D00 | [9 empty] | D02 | IFA | T-0701 | 2022-03-08 | 1400/12/17 | [13 empty] | 1401-2294-1324 | 2022-03-23 | 1401/01/06 | 2022-03-26 | 1401/01/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0024_D01 | 1400-2294-447218 | 2022-03-13 | 1400/12/22 | 2022-03-26 | 1401/01/09 | AP |  |  |  | D03 | IFA | T-0800 | 2022-04-11 | 1401/01/22 |  |  |  | BK-SUR-ENG-MEC-01-03932 | 2022-04-16 | 1401/01/27 | CM-C2 | [6 empty] | 1401-2294-42955 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0024_D02
3 | 2 | 3 | 2 | 2 | 2 | 7 | 3.2.3.2.2.2.7 | Mechanical Data Sheets For Potable Water Pump | BK-GCS-PEDCO-120-ME-DT-0025 | BK-GCS-PEDCO-120-ME-DT-0025 | BK | GCS | PEDCO | 120 | ME | DT | 0025 | F0Z-708856 | AFC | IFC | 2021-12-21 | 2021-12-20 | 2021-12-27 | -1 | 7 | 6 | IFA | 2022-02-05 | 2022-02-24 | 2022-03-02 | 19 | 6 | 25 | AFC | 2022-04-09 | 0 | 0 | -44660 | 0 | -44660 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-07 | 2022-03-26 |  | D02 | AFC | T-0742 | 2022-03-26 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-03728 | 2022-04-05 | 1401/01/16 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0025_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0306 | 2021-12-07 | 1400/09/17 | [13 empty] | 1400-2294-327362 | 2021-12-20 | 1400/09/29 | 2021-12-27 | 1400/10/06 | CM | [10 empty] | D01 | IFA | T-0493 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-MEC-00-03348 | 2022-03-05 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-424207 | 2022-02-24 | 1400/12/05 | 2022-03-02 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0025_D00 | [9 empty] | D02 | AFC | T-0742 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-MEC-01-03728 | 2022-04-05 | 1401/01/16 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0025_D01
3 | 2 | 3 | 2 | 2 | 2 | 8 | 3.2.3.2.2.2.8 | Mechanical Data Sheets For Diesel Pump | BK-GCS-PEDCO-120-ME-DT-0026 | BK-GCS-PEDCO-120-ME-DT-0026 | BK | GCS | PEDCO | 120 | ME | DT | 0026 | F0Z-708857 | AFC | IFC | 2021-12-11 | 2021-12-20 | 2021-12-27 | 9 | 7 | 16 | IFA | 2022-02-07 | 2022-02-24 | 2022-03-02 | 17 | 6 | 23 | IFA | 2022-03-23 | 2022-03-16 | 2022-03-29 | -7 | 13 | 6 | AFC | 2022-04-26 | 2022-05-12 | 2022-05-22 | 16 | 10 | 26 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-27 | 2022-04-12 |  | D03 | AFC | T-0778 | 2022-04-12 | 1401/01/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59445 | 2022-05-12 | 1401/02/22 | 2022-05-22 | 1401/03/01 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0270 | 2021-11-27 | 1400/09/06 |  |  |  | BK-SUR-ENG-MEC-00-02294 | 2021-12-15 | 1400/09/24 | CM-C3 | [6 empty] | 1400-2294-318812 | 2021-12-14 | 1400/09/23 | 2021-12-20 | 1400/09/29 | CM |  | 1400-2294-327356 | 2021-12-20 | 1400/09/29 | 2021-12-27 | 1400/10/06 | CM |  |  |  | D01 | IFA | T-0497 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-MEC-00-02887 | 2022-01-31 | 1400/11/11 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0026_D00 | [5 empty] | 1400-2294-424141 | 2022-02-24 | 1400/12/05 | 2022-03-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0026_D00 | [9 empty] | D02 | IFA | T-0706 | 2022-03-09 | 1400/12/18 | [13 empty] | 1400-2294-453306 | 2022-03-16 | 1400/12/25 | 2022-03-29 | 1401/01/09 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0026_D01 | [9 empty] | D03 | AFC | T-0778 | 2022-04-12 | 1401/01/23 | [13 empty] | 1401-2294-59445 | 2022-05-12 | 1401/02/22 | 2022-05-22 | 1401/03/01 | AP
3 | 2 | 3 | 2 | 2 | 2 | 9 | 3.2.3.2.2.2.9 | Mechanical Data Sheets For Overhead Traveling Cranes | BK-GCS-PEDCO-120-ME-DT-0027 | BK-GCS-PEDCO-120-ME-DT-0027 | BK | GCS | PEDCO | 120 | ME | DT | 0027 | F0Z-708858 | AFC | IFC | 2022-02-27 | 2022-03-10 | 2022-03-12 | 11 | 2 | 13 | IFA | 2022-04-09 | 2022-04-16 | 2022-01-18 | 7 | -88 | -81 | IFA | 2022-05-04 | 2022-05-09 | 2022-05-22 | 5 | 13 | 18 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-13 | 0 |  | D02 | IFA | T-0851 | 2022-04-20 | 1401/01/31 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-04152 | 2022-05-07 | 1401/02/17 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-54998 | 2022-05-09 | 1401/02/19 | 2022-05-22 | 1401/03/01 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0027_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0591 | 2022-02-13 | 1400/11/24 | [13 empty] | 1400-2294-443255 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/22 | CM | [10 empty] | D01 | IFA | T-0740 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-MEC-01-03895 | 2022-04-13 | 1401/01/24 | AP | [6 empty] | 1401-2294-25146 | 2022-04-16 | 1401/01/27 | 2022-01-18 | 1401/01/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0027_D00 | [9 empty] | D02 | IFA | T-0851 | 2022-04-20 | 1401/01/31 |  |  |  | BK-SUR-ENG-MEC-01-04152 | 2022-05-07 | 1401/02/17 | AP | [6 empty] | 1401-2294-54998 | 2022-05-09 | 1401/02/19 | 2022-05-22 | 1401/03/01 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0027_D01
3 | 2 | 3 | 2 | 2 | 2 | 10 | 3.2.3.2.2.2.10 | Mechanical Data Sheets For Fire Water Jockey Pumps | BK-GCS-PEDCO-120-ME-DT-0028 | BK-GCS-PEDCO-120-ME-DT-0028 | BK | GCS | PEDCO | 120 | ME | DT | 0028 | F0Z-708859 | AFC | IFC | 2022-03-07 | 2022-03-14 | 2022-03-26 | 7 | 12 | 19 | IFA | 2022-04-30 | 2022-05-09 | 2022-05-22 | 9 | 13 | 22 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-21 | 0 |  | D01 | IFA | T-0815 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-04138 | 2022-05-07 | 1401/02/17 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0028_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55015 | 2022-05-09 | 1401/02/19 | 2022-05-22 | 1401/03/01 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0028_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0622 | 2022-02-21 | 1400/12/02 |  |  |  | BK-SUR-ENG-MEC-00-03490 | 2022-03-13 | 1400/12/22 | CM-C2 | [6 empty] | 1400-2294-448470 | 2022-03-14 | 1400/12/23 | 2022-03-26 | 1401/01/09 | CM | [10 empty] | D01 | IFA | T-0815 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-MEC-01-04138 | 2022-05-07 | 1401/02/17 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0028_D00 | [5 empty] | 1401-2294-55015 | 2022-05-09 | 1401/02/19 | 2022-05-22 | 1401/03/01 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0028_D00
3 | 2 | 3 | 2 | 2 | 2 | 11 | 3.2.3.2.2.2.11 | Mechanical Data Sheets For Fire Water Main Pumps - Elect. Motor Driven | BK-GCS-PEDCO-120-ME-DT-0029 | BK-GCS-PEDCO-120-ME-DT-0029 | BK | GCS | PEDCO | 120 | ME | DT | 0029 | F0Z-708860 | AFC | IFC | 2022-03-07 | 2022-04-06 | 2022-04-13 | 30 | 7 | 37 | IFA | 2022-05-31 | 0 | 0 | -44712 | 0 | -44712 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-21 | 0 |  | D01 | IFA | T-0964 | 2022-05-17 | 1401/02/27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0029_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0029_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0614 | 2022-02-21 | 1400/11/02 |  |  |  | BK-SUR-ENG-MEC-00-03504 | 2022-03-13 | 1400/12/22 | CM-C3 | [6 empty] | 1401-2294-13623 | 2022-04-06 | 1401/01/17 | 2022-04-13 | 1401/01/24 | CM | [10 empty] | D01 | IFA | T-0964 | 2022-05-17 | 1401/02/27 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0029_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0029_D00
3 | 2 | 3 | 2 | 2 | 2 | 12 | 3.2.3.2.2.2.12 | Mechanical Data Sheets For Fire Water Main Pumps - Diesel Engine Driven | BK-GCS-PEDCO-120-ME-DT-0030 | BK-GCS-PEDCO-120-ME-DT-0030 | BK | GCS | PEDCO | 120 | ME | DT | 0030 | F0Z-708861 | AFC | IFC | 2022-03-02 | 2022-03-09 | 2022-03-12 | 7 | 3 | 10 | IFA | 2022-04-30 | 2022-05-09 | 2022-05-22 | 9 | 13 | 22 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-16 | 0 |  | D01 | IFA | T-0815 | 2022-04-16 | 1401/01/27 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-04138 | 2022-05-07 | 1401/02/17 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0030_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55015 | 2022-05-09 | 1401/02/19 | 2022-05-22 | 1401/03/01 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0030_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0597 | 2022-02-16 | 1400/11/26 |  |  |  | BK-SUR-ENG-MEC-00-03352 | 2022-03-05 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-442060 | 2022-03-09 | 1400/12/18 | 2022-03-12 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0815 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-MEC-01-04138 | 2022-05-07 | 1401/02/17 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0030_D00 | [5 empty] | 1401-2294-55015 | 2022-05-09 | 1401/02/19 | 2022-05-22 | 1401/03/01 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0030_D00
3 | 2 | 3 | 2 | 2 | 3 | 0 | 3.2.2.2.3 | Packaged Equipment
3 | 2 | 3 | 2 | 2 | 3 | 1 | 3.2.3.2.2.3.1 | Mechanical Data Sheets For Gas Compressors Packages | BK-GCS-PEDCO-120-ME-DT-0031 | BK-GCS-PEDCO-120-ME-DT-0031 | BK | GCS | PEDCO | 120 | ME | DT | 0031 | F0Z-708864 | AFC | IFC | 2021-09-26 | 2021-10-07 | 2021-10-11 | 11 | 4 | 15 | IFA | 2021-10-31 | 2021-11-04 | 2021-11-08 | 4 | 4 | 8 | IFA | 2021-11-28 | 2021-12-14 | 2021-12-20 | 16 | 6 | 22 | IFA | 2022-01-26 | 2022-02-22 | 2022-02-22 | 27 | 0 | 27 | IFA | 2022-03-19 | 2022-03-23 | 2022-03-26 | 4 | 3 | 7 | AFC | 2022-05-04 | 2022-04-28 | 2022-05-01 | -6 | 3 | -3 | Modify | 2021-09-12 | 2022-05-08 |  | D06 | AFC | T-0913 | 2022-05-08 | 1401/02/18 | T-0913 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-MEC-01-04470 | 2022-05-29 | 1401/03/8 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70331 | 2022-05-21 | 1401/02/31 | 2022-05-24 | 1401/03/03 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0031_D05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0088 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-ROE-00-01647 | 2021-10-02 | 1400/07/10 | C4-RJ | [6 empty] | 1400-2290-225541 | 2021-10-07 | 1400/07/15 | 2021-10-11 | 1400/07/19 | CM | [10 empty] | D01 | IFA | T-0164 | 2021-10-17 | 1400/07/25 |  |  |  | BK-SUR-ENG-ROE-00-01848 | 2021-10-26 | 1400/08/04 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0031-D00 | [5 empty] | 1400-2294-261501 | 2021-11-04 | 1400/08/13 | 2021-11-08 | 1400/08/17 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0031-D00 | [9 empty] | D02 | IFA | T-0233 | 2021-11-14 | 1400/08/23 |  |  |  | BK-SUR-ENG-ROE-00-02100 | 2021-11-27 | 1400/09/06 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0031-D01 | [5 empty] | 1400-2294-318813 | 2021-12-14 | 1400/09/23 | 2021-12-20 | 1400/09/29 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0031-D01 | [9 empty] | D03 | IFA | T-0454 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-MEC-00-02857 | 2022-01-30 | 1400/11/10 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0031_D02 | [5 empty] | 1400-2294-421701 | 2022-02-22 | 1400/12/03 | 2022-02-22 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0031_D02 | [9 empty] | D04 | IFA | T-0675 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-MEC-00-03410 | 2022-03-08 | 1400/12/17 | CM-C3 | [6 empty] | 1401-2294-1309 | 2022-03-23 | 1401/01/06 | 2022-03-26 | 1401/01/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0031_D03 | [9 empty] | D05 | AFC | T-0818 | 2022-04-20 | 1401/01/31 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0031-D04 | [5 empty] | 1401-2299-33757 | 2022-04-22 | 1401/02/02 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0031_D04 | 1401-2294-43097 | 2022-04-28 | 1401/02/08 | 1-M1Y-2022 | 1401/02/11 | AP |  |  |  | D06 | AFC | T-0913 | 2022-05-08 | 1401/02/18 | T-0913 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-MEC-01-04470 | 2022-05-29 | 1401/03/8 | AP | [6 empty] | 1401-2294-70331 | 2022-05-21 | 1401/02/31 | 2022-05-24 | 1401/03/03 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0031_D05
3 | 2 | 3 | 2 | 2 | 3 | 4 | 3.2.3.2.2.3.4 | Mechanical Data Sheets For Glycol Sump Pumps | BK-GCS-PEDCO-120-ME-DT-0034 | BK-GCS-PEDCO-120-ME-DT-0034 | BK | GCS | PEDCO | 120 | ME | DT | 0034 | F0Z-708862 | AFC | IFC | 2021-12-22 | 2021-12-30 | 2022-01-05 | 8 | 6 | 14 | IFA | 2022-02-01 | 2022-02-24 | 2022-03-02 | 23 | 6 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-08 | 0 |  | D01 | IFA | T-0476 | 2022-01-18 | 1400/10/28 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03539 | 2022-03-14 | 1400/12/23 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-424206 | 2022-02-24 | 1400/12/05 | 2022-03-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0034_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0319 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-342155 | 2021-12-30 | 1400/10/09 | 2022-01-05 | 1400/10/15 | CM | [10 empty] | D01 | IFA | T-0476 | 2022-01-18 | 1400/10/28 |  |  |  | BK-SUR-ENG-MEC-00-03539 | 2022-03-14 | 1400/12/23 | CM-C3 | [6 empty] | 1400-2294-424206 | 2022-02-24 | 1400/12/05 | 2022-03-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0034_D00
3 | 2 | 3 | 2 | 2 | 3 | 5 | 3.2.3.2.2.3.5 | Mechanical Data Sheets For Glycol Drain Pump | BK-GCS-PEDCO-120-ME-DT-0035 | BK-GCS-PEDCO-120-ME-DT-0035 | BK | GCS | PEDCO | 120 | ME | DT | 0035 | F0Z-708863 | AFC | IFC | 2021-12-22 | 2021-12-30 | 2022-01-05 | 8 | 6 | 14 | IFA | 2022-02-01 | 2022-02-24 | 2022-03-02 | 23 | 6 | 29 | IFA | 2022-03-21 | 2022-05-08 | 2022-05-11 | 48 | 3 | 51 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-08 | 0 |  | D02 | IFA | T-0694 | 2022-03-07 | 1400/12/16 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03398 | 2022-03-08 | 1400/12/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52759 | 2022-05-08 | 1401/02/18 | 2022-05-11 | 1401/02/21 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0035_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0319 | 2021-12-08 | 1400/09/17 | [13 empty] | 1400-2294-342155 | 2021-12-30 | 1400/10/09 | 2022-01-05 | 1400/10/15 | CM | [10 empty] | D01 | IFA | T-0476 | 2022-01-18 | 1400/10/28 | [13 empty] | 1400-2294-424206 | 2022-02-24 | 1400/12/05 | 2022-03-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0035_D00 | [9 empty] | D02 | IFA | T-0694 | 2022-03-07 | 1400/12/16 |  |  |  | BK-SUR-ENG-MEC-00-03398 | 2022-03-08 | 1400/12/17 | CM-C3 | [6 empty] | 1401-2294-52759 | 2022-05-08 | 1401/02/18 | 2022-05-11 | 1401/02/21 | AP | NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0035_D01
[7 empty] | 3.2.3.2.2.3.6 | Mechanical Data Sheets For Glycol Sump Drum | BK-GCS-PEDCO-120-ME-DT-0036 | BK-GCS-PEDCO-120-ME-DT-0036 | BK | GCS | PEDCO | 120 | ME | DT | 0036 |  | AFC | IFC | 2022-01-19 | 0 | 0 | -44580 | 0 | -44580 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-05 | 0 |  | D00 | IFC | T-0436 | 2022-01-05 | 1400/10/15 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-02941 | 2022-02-05 | 1400/11/16 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0436 | 2022-01-05 | 1400/10/15 |  |  |  | BK-SUR-ENG-MEC-00-02941 | 2022-02-05 | 1400/11/16 | CM-C3
3 | 2 | 3 | 3 | 0 | 0 | 0 | 3.2.3.3 | HVAC/Plumbing
3 | 2 | 3 | 3 | 1 | 0 | 0 | 3.2.3.3.1 | Calculation
3 | 2 | 3 | 3 | 1 | 0 | 1 | 3.2.3.3.1 | HVAC Calculation Note For Control Building | BK-GCS-PEDCO-120-HV-CN-0001 | BK-GCS-PEDCO-120-HV-CN-0001 | BK | GCS | PEDCO | 120 | HV | CN | 0001 | F0Z-708865 | AFD | IFC | 2022-04-13 | 2022-04-17 | 2022-04-25 | 4 | 8 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-30 | 0 |  | D00 | IFC | T-0767 | 2022-03-30 | 1401/01/10 | 0 | 0 | 0 | BK-SUR-ENG-HVC-01-03862 | 2022-04-11 | 1401/01/22 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27253 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0767 | 2022-03-30 | 1401/01/10 |  |  |  | BK-SUR-ENG-HVC-01-03862 | 2022-04-11 | 1401/01/22 | CM-C3 | [6 empty] | 1401-2294-27253 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM
3 | 2 | 3 | 3 | 1 | 0 | 2 | 3.2.3.3.1 | HVAC Calculation Note For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-CN-0002 | BK-GCS-PEDCO-120-HV-CN-0002 | BK | GCS | PEDCO | 120 | HV | CN | 0002 | F0Z-708866 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 2 | 0 | 0 | 3.2.3.3.2 | Data Sheets
3 | 2 | 3 | 3 | 2 | 0 | 1 | 3.2.3.3.2 | Data Sheets For Main HVAC Equipment of Control Building | BK-GCS-PEDCO-120-HV-DT-0001 | BK-GCS-PEDCO-120-HV-DT-0001 | BK | GCS | PEDCO | 120 | HV | DT | 0001 | F0Z-708867 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 2 | 0 | 2 | 3.2.3.3.2 | Data Sheets For Main HVAC Equipment of Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-DT-0002 | BK-GCS-PEDCO-120-HV-DT-0002 | BK | GCS | PEDCO | 120 | HV | DT | 0002 | F0Z-708868 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 3 | 0 | 0 | 3.2.3.3.3 | Drawing/Diagram
3 | 2 | 3 | 3 | 3 | 0 | 1 | 3.2.3.3.3 | Plumbing & Sewage Piping Layout For Control Building | BK-GCS-PEDCO-120-HV-PY-0001 | BK-GCS-PEDCO-120-HV-PY-0001 | BK | GCS | PEDCO | 120 | HV | PY | 0001 | F4B-708869 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 3 | 0 | 2 | 3.2.3.3.3 | HVAC Flow Diagram For Control Building | BK-GCS-PEDCO-120-HV-DG-0001 | BK-GCS-PEDCO-120-HV-DG-0001 | BK | GCS | PEDCO | 120 | HV | DG | 0001 | F4A-708870 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 3 | 0 | 3 | 3.2.3.3.3 | HVAC Room Layout & Section For Control Building | BK-GCS-PEDCO-120-HV-PY-0002 | BK-GCS-PEDCO-120-HV-PY-0002 | BK | GCS | PEDCO | 120 | HV | PY | 0002 | F4B-708871 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 3 | 0 | 4 | 3.2.3.3.3 | HVAC System Duct Plan For Control Building | BK-GCS-PEDCO-120-HV-PY-0003 | BK-GCS-PEDCO-120-HV-PY-0003 | BK | GCS | PEDCO | 120 | HV | PY | 0003 | F4B-708872 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 3 | 0 | 5 | 3.2.3.3.3 | HVAC System Roof Layout For Control Building | BK-GCS-PEDCO-120-HV-PY-0004 | BK-GCS-PEDCO-120-HV-PY-0004 | BK | GCS | PEDCO | 120 | HV | PY | 0004 | F4B-708873 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 3 | 0 | 6 | 3.2.3.3.3 | HVAC I&C Diagram For Control Building | BK-GCS-PEDCO-120-HV-DG-0002 | BK-GCS-PEDCO-120-HV-DG-0002 | BK | GCS | PEDCO | 120 | HV | DG | 0002 | F4B-708874 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 3 | 0 | 7 | 3.2.3.3.3 | Plumbing & Sewage Piping Layout For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-PY-0005 | BK-GCS-PEDCO-120-HV-PY-0005 | BK | GCS | PEDCO | 120 | HV | PY | 0005 | F4B-708875 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 3 | 0 | 8 | 3.2.3.3.3 | HVAC Flow Diagram For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-DG-0003 | BK-GCS-PEDCO-120-HV-DG-0003 | BK | GCS | PEDCO | 120 | HV | DG | 0003 | F4A-708876 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 3 | 0 | 9 | 3.2.3.3.3 | HVAC System Layout & Section For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-PY-0006 | BK-GCS-PEDCO-120-HV-PY-0006 | BK | GCS | PEDCO | 120 | HV | PY | 0006 | F4B-708877 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 3 | 0 | 10 | 3.2.3.3.3 | HVAC System Duct Plan For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-PY-0007 | BK-GCS-PEDCO-120-HV-PY-0007 | BK | GCS | PEDCO | 120 | HV | PY | 0007 | F4B-708878 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 3 | 0 | 11 | 3.2.3.3.3 | HVAC System Roof Layout For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-PY-0008 | BK-GCS-PEDCO-120-HV-PY-0008 | BK | GCS | PEDCO | 120 | HV | PY | 0008 | F4B-708879 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 3 | 0 | 12 | 3.2.3.3.3 | HVAC I&C Diagram For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-DG-0004 | BK-GCS-PEDCO-120-HV-DG-0004 | BK | GCS | PEDCO | 120 | HV | DG | 0004 | F4B-708880 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 4 | 0 | 0 | 3.2.3.3.4 | MTO
3 | 2 | 3 | 3 | 4 | 0 | 1 | 3.2.3.3 | MTO For HVAC & Plumbing For Control Building | BK-GCS-PEDCO-120-HV-MT-0001 | BK-GCS-PEDCO-120-HV-MT-0001 | BK | GCS | PEDCO | 120 | HV | MT | 0001 | F8Z-708881 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 3 | 4 | 0 | 2 | 3.2.3.3 | MTO For HVAC & Plumbing For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-HV-MT-0002 | BK-GCS-PEDCO-120-HV-MT-0002 | BK | GCS | PEDCO | 120 | HV | MT | 0002 | F8Z-708882 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 0 | 0 | 0 | 3.2.3.4 | Piping
3 | 2 | 3 | 4 | 1 | 0 | 0 | 3.2.3.4.1 | Specification
3 | 2 | 3 | 4 | 1 | 0 | 1 | 3.2.3.4.1 | Piping Material Specification | BK-GCS-PEDCO-120-PI-SP-0001 | BK-GCS-PEDCO-120-PI-SP-0001 | BK | GCS | PEDCO | 120 | PI | SP | 0001 | F0Z-708883 | AFD | IFC | 44550 | 0 | 0 | -44550 | 0 | -44550 | IFA | 44640 | 44578 | 44670 | -62 | 92 | 30 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-06 | 0 |  | D01 | IFA | T-0677 | 2022-03-06 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03538 | 2022-03-14 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-SP-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27248 | 2022-01-17 | 1401/01/28 | 2022-04-19 | 1401/01/30 | CM | NOSIC-CRS-BK-GCS-PEDCO-120-PI-SP-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0295 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PIP-00-02466 | 2021-12-27 | 1400/10/06 | CM-C2 | [22 empty] | D01 | IFA | T-0677 | 2022-03-06 | 1400/12/14 |  |  |  | BK-SUR-ENG-PIP-00-03538 | 2022-03-14 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-SP-0001_D00 | [5 empty] | 1401-2294-27248 | 2022-01-17 | 1401/01/28 | 2022-04-19 | 1401/01/30 | CM | NOSIC-CRS-BK-GCS-PEDCO-120-PI-SP-0001_D00
3 | 2 | 3 | 4 | 2 | 0 | 0 | 3.2.3.4.2 | Data Sheets
3 | 2 | 3 | 4 | 2 | 0 | 1 | 3.2.3.4.2 | Data Sheets For Strainers | BK-GCS-PEDCO-120-PI-DT-0001 | BK-GCS-PEDCO-120-PI-DT-0001 | BK | GCS | PEDCO | 120 | PI | DT | 0001 | F0Z-708884 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 2 | 0 | 2 | 3.2.3.4.2 | Data Sheets For Manual valves | BK-GCS-PEDCO-120-PI-DT-0002 | BK-GCS-PEDCO-120-PI-DT-0002 | BK | GCS | PEDCO | 120 | PI | DT | 0002 | F0Z-708885 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 2 | 0 | 3 | 3.2.3.4.2 | Data Sheets and MTO For Piping Special Items | BK-GCS-PEDCO-120-PI-DT-0003 | BK-GCS-PEDCO-120-PI-DT-0003 | BK | GCS | PEDCO | 120 | PI | DT | 0003 | F0Z-708886 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 2 | 0 | 4 | 3.2.3.4.2 | Data Sheets For Special Pipe Supports | BK-GCS-PEDCO-120-PI-DT-0004 | BK-GCS-PEDCO-120-PI-DT-0004 | BK | GCS | PEDCO | 120 | PI | DT | 0004 | F0Z-708887 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 2 | 0 | 5 | 3.2.3.4.2 | Data Sheets For Piping Insulation Joints | BK-GCS-PEDCO-120-PI-DT-0005 | BK-GCS-PEDCO-120-PI-DT-0005 | BK | GCS | PEDCO | 120 | PI | DT | 0005 | F0Z-708888 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 2 | 0 | 6 | 3.2.3.4.2 | Data Sheets For Expansion Joints | BK-GCS-PEDCO-120-PI-DT-0006 | BK-GCS-PEDCO-120-PI-DT-0006 | BK | GCS | PEDCO | 120 | PI | DT | 0006 | F0Z-708889 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 3 | 0 | 0 | 3.2.3.4.3 | Drawing/Diagram
3 | 2 | 3 | 4 | 3 | 0 | 1 | 3.2.3.4.3 | Unit Plot Plan Drawing | BK-GCS-PEDCO-120-PI-PY-0001 | BK-GCS-PEDCO-120-PI-PY-0001 | BK | GCS | PEDCO | 120 | PI | PY | 0001 | F5A-708890 | AFC | IFC | 2021-09-26 | 2021-10-13 | 2021-10-12 | 17 | -1 | 16 | IFA | 2021-12-14 | 2021-12-20 | 2021-12-21 | 6 | 1 | 7 | IFA | 2022-02-05 | 2022-02-24 | 2022-02-28 | 19 | 4 | 23 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-12 | 0 |  | D02 | IFA | T-0491 | 2022-01-22 | 1400/11/02 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-02796 | 2022-01-24 | 1400/11/04 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-424188 | 2022-02-24 | 1400/12/05 | 2022-02-28 | 1400/12/09 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PI-PY-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0084 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-PIP-00-01607 | 2021-09-26 | 1400/07/04 | CM-C3 | [6 empty] | 1400-2290-225538 | 2021-10-07 | 1400/07/15 | 2021-10-12 | 1400/07/20 | CM |  | 1400-2294-234196 | 2021-10-13 | 1400/07/21 |  |  | CM |  |  |  | D01 | IFA | T-0283 | 2021-11-30 | 1400/09/09 |  |  |  | BK-SUR-ENG-PIP-00-02237 | 2021-12-08 | 1400/09/17 | CM-C3 | PEDCO-CRS-BK-GNRAL-PEDCO-120-PI-PY-0001-D00 | [5 empty] | 1400-2294-327388 | 2021-12-20 | 1400/09/29 | 2021-12-21 | 1400/09/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PI-PY-0001-D00 | [9 empty] | D02 | IFA | T-0491 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-PIP-00-02796 | 2022-01-24 | 1400/11/04 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-PY-0001_D01 | [5 empty] | 1400-2294-424188 | 2022-02-24 | 1400/12/05 | 2022-02-28 | 1400/12/09 | AP | NISOC-CRS-BK-GCS-PEDCO-120-PI-PY-0001_D01
3 | 2 | 3 | 4 | 3 | 0 | 2 | 3.2.3.4.3 | Standard Pipe Support Drawings | BK-GCS-PEDCO-120-PI-DW-0001 | BK-GCS-PEDCO-120-PI-DW-0001 | BK | GCS | PEDCO | 120 | PI | DW | 0001 | F1L-708891 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 3 | 0 | 3 | 3.2.3.4.3 | Piping Assembly Drawing | BK-GCS-PEDCO-120-PI-DW-0002 | BK-GCS-PEDCO-120-PI-DW-0002 | BK | GCS | PEDCO | 120 | PI | DW | 0002 | F1L-708892 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 3 | 0 | 4 | 3.2.3.4.3 | Piping Key Plan | BK-GCS-PEDCO-120-PI-DW-0003 | BK-GCS-PEDCO-120-PI-DW-0003 | BK | GCS | PEDCO | 120 | PI | DW | 0003 | F5L-708893 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 3 | 0 | 5 | 3.2.3.4.3 | A/G Piping Plan | BK-GCS-PEDCO-120-PI-DW-0004 | BK-GCS-PEDCO-120-PI-DW-0004 | BK | GCS | PEDCO | 120 | PI | DW | 0004 | F4L-708894 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 3 | 0 | 6 | 3.2.3.4.3 | U/G Piping Plan | BK-GCS-PEDCO-120-PI-DW-0005 | BK-GCS-PEDCO-120-PI-DW-0005 | BK | GCS | PEDCO | 120 | PI | DW | 0005 | F4L-708895 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 3 | 0 | 7 | 3.2.3.4.3 | A/G Piping Isometric | BK-GCS-PEDCO-120-PI-DW-0006 | BK-GCS-PEDCO-120-PI-DW-0006 | BK | GCS | PEDCO | 120 | PI | DW | 0006 | F2L-708896 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 3 | 0 | 8 | 3.2.3.4.3 | U/G Piping Isometric | BK-GCS-PEDCO-120-PI-DW-0007 | BK-GCS-PEDCO-120-PI-DW-0007 | BK | GCS | PEDCO | 120 | PI | DW | 0007 | F2L-708897 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 3 | 0 | 9 | 3.2.3.4.3 | Overall Plot Plan Drawing | BK-GCS-PEDCO-120-PI-DW-0008 | BK-GCS-PEDCO-120-PI-DW-0008 | BK | GCS | PEDCO | 120 | PI | DW | 0008 | F5A-708898 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 3 | 0 | 10 | 3.2.3.4.3 | Special Pipe Support Drawings | BK-GCS-PEDCO-120-PI-DW-0009 | BK-GCS-PEDCO-120-PI-DW-0009 | BK | GCS | PEDCO | 120 | PI | DW | 0009 | F1L-708899 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 3 | 0 | 11 | 3.2.3.4.3 | Material flow Diagram | BK-GCS-PEDCO-120-PI-DG-0001 | BK-GCS-PEDCO-120-PI-DG-0001 | BK | GCS | PEDCO | 120 | PI | DG | 0001 | F2A-708900 | AFC | IFC | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-11 | 0 |  | D00 | IFC | T-0934 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-04380 | 2022-05-23 | 1401-03/02 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0934 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-PIP-01-04380 | 2022-05-23 | 1401-03/02 | CM-C3
3 | 2 | 3 | 4 | 4 | 0 | 0 | 3.2.3.4.4 | Procedure/Plan
3 | 2 | 3 | 4 | 4 | 0 | 1 | 3.2.3.4.4 | Piping Hydrostatic Test Diagram - GCS | BK-GCS-PEDCO-120-PI-DW-0010 | BK-GCS-PEDCO-120-PI-DW-0010 | BK | GCS | PEDCO | 120 | PI | DW | 0010 | F2L-708901 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 5 | 0 | 0 | 3.2.3.4.5 | List
3 | 2 | 3 | 4 | 5 | 0 | 1 | 3.2.3.4.5 | Critical Line List | BK-GCS-PEDCO-120-PI-LI-0001 | BK-GCS-PEDCO-120-PI-LI-0001 | BK | GCS | PEDCO | 120 | PI | LI | 0001 | F0Z-708902 | AFC | IFC | 2022-06-11 | 0 | 0 | -44723 | 0 | -44723 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-28 | 0 |  | D00 | IFC | T-1009 | 2022-05-28 | 1401/03/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1009 | 2022-05-28 | 1401/03/07
3 | 2 | 3 | 4 | 5 | 0 | 2 | 3.2.3.4.5 | Pipe Support List | BK-GCS-PEDCO-120-PI-LI-0002 | BK-GCS-PEDCO-120-PI-LI-0002 | BK | GCS | PEDCO | 120 | PI | LI | 0002 | F0Z-708903 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 5 | 0 | 3 | 3.2.3.4.5 | Piping Tie-In Schedule List | BK-GCS-PEDCO-120-PI-LI-0003 | BK-GCS-PEDCO-120-PI-LI-0003 | BK | GCS | PEDCO | 120 | PI | LI | 0003 | F0Z-708904 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 6 | 0 | 0 | 3.2.3.4.6 | Report
3 | 2 | 3 | 4 | 6 | 0 | 1 | 3.2.3.4.6 | Piping Corrosion Study & Material Selection Report | BK-GCS-PEDCO-120-PI-RT-0001 | BK-GCS-PEDCO-120-PI-RT-0001 | BK | GCS | PEDCO | 120 | PI | RT | 0001 | F0Z-708905 | AFD | IFC | 2021-12-20 | 0 | 0 | -44550 | 0 | -44550 | IFA | 2022-05-21 | 0 | 0 | -44702 | 0 | -44702 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-06 | 0 |  | D01 | IFA | T-0904 | 2022-05-07 | 1401/02/17 | T-0904 | 2022-05-07 | 1401/02/17 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-PI-RT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0295 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PIP-00-02466 | 2021-12-27 | 1400/10/06 | CM-C2 | [22 empty] | D01 | IFA | T-0904 | 2022-05-07 | 1401/02/17 | T-0904 | 2022-05-07 | 1401/02/17 |  |  |  |  | PEDCO-CRS-BK-GCS-PEDCO-120-PI-RT-0001_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-PI-RT-0001_D00
3 | 2 | 3 | 4 | 6 | 0 | 2 | 3.2.3.4.6 | Stress Analysis Calculations Report | BK-GCS-PEDCO-120-PI-RT-0002 | BK-GCS-PEDCO-120-PI-RT-0002 | BK | GCS | PEDCO | 120 | PI | RT | 0002 | F0Z-708906 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 6 | 0 | 3 | 3.2.3.4.6 | PDMS Model Review Report (30%) | BK-GCS-PEDCO-120-PI-RT-0003 | BK-GCS-PEDCO-120-PI-RT-0003 | BK | GCS | PEDCO | 120 | PI | RT | 0003 | F0Z-708907 | AFC | IFC | 2022-04-09 | 2022-04-17 | 2022-04-25 | 8 | 8 | 16 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-26 | 0 |  | D00 | IFC | T-0741 | 2022-03-26 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-PIP-01-03858 | 2022-04-11 | 1401/01/22 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27190 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0741 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-PIP-01-03858 | 2022-04-11 | 1401/01/22 | CM-C2 | [6 empty] | 1401-2294-27190 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM
3 | 2 | 3 | 4 | 6 | 0 | 4 | 3.2.3.4.6 | PDMS Model Review Report (60%) | BK-GCS-PEDCO-120-PI-RT-0004 | BK-GCS-PEDCO-120-PI-RT-0004 | BK | GCS | PEDCO | 120 | PI | RT | 0004 | F0Z-708908 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 6 | 0 | 5 | 3.2.3.4.6 | PDMS Model Review Report (90%) | BK-GCS-PEDCO-120-PI-RT-0005 | BK-GCS-PEDCO-120-PI-RT-0005 | BK | GCS | PEDCO | 120 | PI | RT | 0005 | F0Z-708909 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 6 | 0 | 6 | 3.2.3.4.6 | Wall Thickness Calculation Report | BK-GCS-PEDCO-120-PI-RT-0006 | BK-GCS-PEDCO-120-PI-RT-0006 | BK | GCS | PEDCO | 120 | PI | RT | 0006 | F0Z-708910 | AFC | IFC | 2021-12-20 | 0 | 0 | -44550 | 0 | -44550 | IFA | 2022-03-20 | 2022-01-17 | 2022-04-19 | -62 | 92 | 30 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-06 | 0 |  | D01 | IFA | T-0677 | 2022-03-06 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-PIP-00-03538 | 2022-03-14 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-RT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27248 | 2022-01-17 | 1401/01/28 | 2022-04-19 | 1401/01/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PI-RT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0295 | 2021-12-06 | 1400/09/15 |  |  |  | BK-SUR-ENG-PIP-00-02466 | 2021-12-27 | 1400/10/06 | CM-C2 | [22 empty] | D01 | IFA | T-0677 | 2022-03-06 | 1400/12/14 |  |  |  | BK-SUR-ENG-PIP-00-03538 | 2022-03-14 | 1400/12/23 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-PI-RT-0006_D00 | [5 empty] | 1401-2294-27248 | 2022-01-17 | 1401/01/28 | 2022-04-19 | 1401/01/30 | CM | NISOC-CRS-BK-GCS-PEDCO-120-PI-RT-0006_D00
3 | 2 | 3 | 4 | 7 | 0 | 0 | 3.2.3.4.7 | MTO
3 | 2 | 3 | 4 | 7 | 0 | 1 | 3.2.3.4 | MTO For Pipes | BK-GCS-PEDCO-120-PI-MT-0001 | BK-GCS-PEDCO-120-PI-MT-0001 | BK | GCS | PEDCO | 120 | PI | MT | 0001 | F8Z-708911 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 7 | 0 | 2 | 3.2.3.4 | MTO For Fittings | BK-GCS-PEDCO-120-PI-MT-0002 | BK-GCS-PEDCO-120-PI-MT-0002 | BK | GCS | PEDCO | 120 | PI | MT | 0002 | F8Z-708912 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 7 | 0 | 3 | 3.2.3.4 | MTO For Flanges | BK-GCS-PEDCO-120-PI-MT-0003 | BK-GCS-PEDCO-120-PI-MT-0003 | BK | GCS | PEDCO | 120 | PI | MT | 0003 | F8Z-708913 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 7 | 0 | 4 | 3.2.3.4 | MTO For Manual Valves | BK-GCS-PEDCO-120-PI-MT-0004 | BK-GCS-PEDCO-120-PI-MT-0004 | BK | GCS | PEDCO | 120 | PI | MT | 0004 | F8Z-708914 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 7 | 0 | 5 | 3.2.3.4 | MTO For Gaskets | BK-GCS-PEDCO-120-PI-MT-0005 | BK-GCS-PEDCO-120-PI-MT-0005 | BK | GCS | PEDCO | 120 | PI | MT | 0005 | F8Z-708915 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 7 | 0 | 6 | 3.2.3.4 | MTO For Bolt & Nuts | BK-GCS-PEDCO-120-PI-MT-0006 | BK-GCS-PEDCO-120-PI-MT-0006 | BK | GCS | PEDCO | 120 | PI | MT | 0006 | F8Z-708916 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 7 | 0 | 7 | 3.2.3.4 | MTO For Insulation | BK-GCS-PEDCO-120-PI-MT-0008 | BK-GCS-PEDCO-120-PI-MT-0008 | BK | GCS | PEDCO | 120 | PI | MT | 0008 | F8Z-708917 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 7 | 0 | 8 | 3.2.3.4 | MTO For Painting | BK-GCS-PEDCO-120-PI-MT-0009 | BK-GCS-PEDCO-120-PI-MT-0009 | BK | GCS | PEDCO | 120 | PI | MT | 0009 | F8Z-708918 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 4 | 7 | 0 | 9 | 3.2.3.4 | MTO For Coating of Underground Piping | BK-GCS-PEDCO-120-PI-MT-0010 | BK-GCS-PEDCO-120-PI-MT-0010 | BK | GCS | PEDCO | 120 | PI | MT | 0010 | F8Z-708919 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 0 | 0 | 0 | 3.2.3.5 | Control & Instrumentation
3 | 2 | 3 | 5 | 1 | 0 | 0 | 3.2.3.5.1 | Basis/Criteria
3 | 2 | 3 | 5 | 1 | 0 | 1 | 3.2.3.5.1 | Instrument & Control System Basis of Design | BK-GCS-PEDCO-120-IN-DB-0001 | BK-GCS-PEDCO-120-IN-DB-0001 | [7 empty] | - | [43 empty] | Deleted | 2021-08-22 | 0 |  | D00 | IFC | T-0060 | 2021-08-22 | 1400/05/31 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-01427 | 2021-08-29 | 1400/06/07 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-200135 | 2021-09-15 | 1400/06/24 | 2021-09-20 | 1400/06/29 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0060 | 2021-08-22 | 1400/05/31 |  |  |  | BK-SUR-ENG-INS-00-01427 | 2021-08-29 | 1400/06/07 | CM-C3 | [6 empty] | 1400-2294-200135 | 2021-09-15 | 1400/06/24 | 2021-09-20 | 1400/06/29 | CM
3 | 2 | 3 | 5 | 1 | 0 | 2 | 3.2.3.5.1 | Fire & Gas Detection Design Criteria | BK-GCS-PEDCO-120-IN-DC-0001 | BK-GCS-PEDCO-120-IN-DC-0001 | BK | GCS | PEDCO | 120 | IN | DC | 0001 | F0Z-708920 | AFD | IFC | 2021-09-13 | 2021-10-26 | 2021-10-02 | 43 | -24 | 19 | IFA | 2021-10-25 | 2021-11-21 | 2021-11-27 | 27 | 6 | 33 | IFA | 2022-01-18 | 2022-02-13 | 2022-02-13 | 26 | 0 | 26 | IFA | 2022-06-06 | 0 | 0 | -44718 | 0 | -44718 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-30 | 0 |  | D03 | IFA | T-0993 | 2022-05-23 | 1401/03/02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DC-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-IN-DC-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0071 | 2021-08-30 | 1400/06/08 | [13 empty] | 1400-2294-213820 | 2021-10-26 | 1400/07/04 | 2021-10-02 | 1400/07/10 | CM |  | 1400-2294-234028 | 2021-10-13 | 1400/07/21 |  |  | CM |  |  |  | D01 | IFA | T-0151 | 2021-10-11 | 1400/07/19 |  |  |  | BK-SUR-ENG-INS-00-01859 | 2021-10-27 | 1400/08/05 | CM-C3 | [6 empty] | 1400-2294-283466 | 2021-11-21 | 1400/08/30 | 2021-11-27 | 1400/09/06 | CM | NISOC-BK-GCS-PEDCO-120-IN-DC-0001-D00 | [9 empty] | D02 | IFA | T-0427 | 2022-01-04 | 1400/10/14 |  |  |  | BK-SUR-ENG-INS-00-02730 | 2022-01-18 | 1400/10/28 | CM-C3 | PEDCO-BK-GCS-PEDCO-120-IN-DC-0001-D01 | [5 empty] | 1400-2294-407520 | 2022-02-13 | 1400/11/24 | 2022-02-13 | 1400/11/24 | CM | NISOC-BK-GCS-PEDCO-120-IN-DC-0001-D01 | [9 empty] | D03 | IFA | T-0993 | 2022-05-23 | 1401/03/02 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DC-0001_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-IN-DC-0001_D02
3 | 2 | 3 | 5 | 1 | 0 | 3 | 3.2.3.5.1 | Instrument & Control System Design Criteria | BK-GCS-PEDCO-120-IN-DC-0002 | BK-GCS-PEDCO-120-IN-DC-0002 | BK | GCS | PEDCO | 120 | IN | DC | 0002 | F0Z-708921 | AFD | IFC | 2022-01-17 | 2022-02-16 | 2022-02-21 | 30 | 5 | 35 | IFA | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-03 | 0 |  | D01 | IFA | T-0931 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04458 | 2022-05-28 | 1401/03/07 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DC-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-IN-DC-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0420 | 2022-01-03 | 1400/10/13 |  |  |  | BK-SUR-ENG-INS-00-02625 | 2022-01-10 | 1400/10/20 | CM-C3 | [6 empty] | 1400-2294-412682 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0931 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-INS-01-04458 | 2022-05-28 | 1401/03/07 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-DC-0002_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-IN-DC-0002_D00
3 | 2 | 3 | 5 | 2 | 0 | 0 | 3.2.3.5.2 | Data Sheets
3 | 2 | 3 | 5 | 2 | 0 | 1 | 3.2.3.5.2 | Data Sheets For Pressure & Diff. Pressure Gauge | BK-GCS-PEDCO-120-IN-DT-0001 | BK-GCS-PEDCO-120-IN-DT-0001 | BK | GCS | PEDCO | 120 | IN | DT | 0001 | F9Z-708922 | AFC | IFC | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-27 | 0 |  | D00 | IFC | T-0750 | 2022-03-27 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03950 | 2022-04-17 | 1401/01/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27197 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0750 | 2022-03-27 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03950 | 2022-04-17 | 1401/01/28 | CM-C3 | [6 empty] | 1401-2294-27197 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM
3 | 2 | 3 | 5 | 2 | 0 | 2 | 3.2.3.5.2 | Data Sheets For Temperature Gauge | BK-GCS-PEDCO-120-IN-DT-0002 | BK-GCS-PEDCO-120-IN-DT-0002 | BK | GCS | PEDCO | 120 | IN | DT | 0002 | F9Z-708923 | AFC | IFC | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-27 | 0 |  | D00 | IFC | T-0750 | 2022-03-27 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03950 | 2022-04-17 | 1401/01/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27197 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0750 | 2022-03-27 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03950 | 2022-04-17 | 1401/01/28 | CM-C3 | [6 empty] | 1401-2294-27197 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM
3 | 2 | 3 | 5 | 2 | 0 | 3 | 3.2.3.5.2 | Data Sheets For Level Gauges | BK-GCS-PEDCO-120-IN-DT-0003 | BK-GCS-PEDCO-120-IN-DT-0003 | BK | GCS | PEDCO | 120 | IN | DT | 0003 | F9Z-708924 | AFC | IFC | 2022-04-19 | 2022-05-17 | 2022-05-23 | 28 | 6 | 34 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-05 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | [13 empty] | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM
3 | 2 | 3 | 5 | 2 | 0 | 4 | 3.2.3.5.2 | Data Sheets For Pressure/Diff. Pressure Transmitter | BK-GCS-PEDCO-120-IN-DT-0004 | BK-GCS-PEDCO-120-IN-DT-0004 | BK | GCS | PEDCO | 120 | IN | DT | 0004 | F9Z-708925 | AFC | IFC | 2022-04-24 | 2022-05-21 | 2022-05-23 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-10 | 0 |  | D00 | IFC | T-0797 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04115 | 2022-05-01 | 1401/02/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70032 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0797 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-INS-01-04115 | 2022-05-01 | 1401/02/11 | CM-C3 | [6 empty] | 1401-2294-70032 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM
3 | 2 | 3 | 5 | 2 | 0 | 5 | 3.2.3.5.2 | Data Sheets For Temperature Transmitter/Switch | BK-GCS-PEDCO-120-IN-DT-0005 | BK-GCS-PEDCO-120-IN-DT-0005 | BK | GCS | PEDCO | 120 | IN | DT | 0005 | F9Z-708926 | AFC | IFC | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-27 | 0 |  | D00 | IFC | T-0750 | 2022-03-27 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03950 | 2022-04-17 | 1401/01/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27197 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0750 | 2022-03-27 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03950 | 2022-04-17 | 1401/01/28 | CM-C3 | [6 empty] | 1401-2294-27197 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM
3 | 2 | 3 | 5 | 2 | 0 | 6 | 3.2.3.5.2 | Data Sheets For Displacer Level Transmitter | BK-GCS-PEDCO-120-IN-DT-0006 | BK-GCS-PEDCO-120-IN-DT-0006 | BK | GCS | PEDCO | 120 | IN | DT | 0006 | F9Z-708927 | AFC | IFC | 2022-04-19 | 2022-05-17 | 2022-05-23 | 28 | 6 | 34 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-05 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | [13 empty] | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM
3 | 2 | 3 | 5 | 2 | 0 | 7 | 3.2.3.5.2 | Data Sheets For Pressure/ Differential Pressure Switch | BK-GCS-PEDCO-120-IN-DT-0007 | BK-GCS-PEDCO-120-IN-DT-0007 | BK | GCS | PEDCO | 120 | IN | DT | 0007 | F9Z-708928 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 2 | 0 | 8 | 3.2.3.5.2 | Data Sheets For Level Switch | BK-GCS-PEDCO-120-IN-DT-0008 | BK-GCS-PEDCO-120-IN-DT-0008 | BK | GCS | PEDCO | 120 | IN | DT | 0008 | F9Z-708929 | AFC | IFC | 2022-04-24 | 2022-05-21 | 2022-05-23 | 27 | 2 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-10 | 0 |  | D00 | IFC | T-0797 | 2022-04-10 | 1401/01/21 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04115 | 2022-05-01 | 1401/02/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-70032 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0797 | 2022-04-10 | 1401/01/21 |  |  |  | BK-SUR-ENG-INS-01-04115 | 2022-05-01 | 1401/02/11 | CM-C3 | [6 empty] | 1401-2294-70032 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | CM
3 | 2 | 3 | 5 | 2 | 0 | 9 | 3.2.3.5.2 | Data Sheets For Pressure & Safety Relief Valves | BK-GCS-PEDCO-120-IN-DT-0009 | BK-GCS-PEDCO-120-IN-DT-0009 | BK | GCS | PEDCO | 120 | IN | DT | 0009 | F9Z-708930 | AFC | IFC | 2022-05-31 | 0 | 0 | -44712 | 0 | -44712 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-17 | 0 |  | D00 | IFC | T-0967 | 2022-05-17 | 1401/02/27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0967 | 2022-05-17 | 1401/02/27
3 | 2 | 3 | 5 | 2 | 0 | 10 | 3.2.3.5.2 | Data Sheets For ON/OFF & Shutdown Valves | BK-GCS-PEDCO-120-IN-DT-0010 | BK-GCS-PEDCO-120-IN-DT-0010 | BK | GCS | PEDCO | 120 | IN | DT | 0010 | F9Z-708931 | AFC | IFC | 2022-05-22 | 0 | 0 | -44703 | 0 | -44703 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-08 | 0 |  | D00 | IFC | T-0906 | 2022-05-08 | 1401/02/18 | T-0906 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-INS-01-04428 | 2022-05-24 | 1401/03/03 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0906 | 2022-05-08 | 1401/02/18 | T-0906 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-INS-01-04428 | 2022-05-24 | 1401/03/03 | CM-C3
3 | 2 | 3 | 5 | 2 | 0 | 11 | 3.2.3.5.2 | Data Sheets For Control/Regulator Valves | BK-GCS-PEDCO-120-IN-DT-0011 | BK-GCS-PEDCO-120-IN-DT-0011 | BK | GCS | PEDCO | 120 | IN | DT | 0011 | F9Z-708932 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 2 | 0 | 12 | 3.2.3.5.2 | Data Sheets For Diff. Pressure Flow Transmitter | BK-GCS-PEDCO-120-IN-DT-0012 | BK-GCS-PEDCO-120-IN-DT-0012 | BK | GCS | PEDCO | 120 | IN | DT | 0012 | F9Z-708933 | AFC | IFC | 2022-04-19 | 2022-05-17 | 2022-05-23 | 28 | 6 | 34 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-05 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | [13 empty] | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM
3 | 2 | 3 | 5 | 2 | 0 | 13 | 3.2.3.5.2 | Data Sheets For Orifice Plate/Restriction Orifice | BK-GCS-PEDCO-120-IN-DT-0013 | BK-GCS-PEDCO-120-IN-DT-0013 | BK | GCS | PEDCO | 120 | IN | DT | 0013 | F9Z-708934 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 2 | 0 | 14 | 3.2.3.5.2 | Data Sheets For Corrosion Coupon/ Probe | BK-GCS-PEDCO-120-IN-DT-0014 | BK-GCS-PEDCO-120-IN-DT-0014 | BK | GCS | PEDCO | 120 | IN | DT | 0014 | F9Z-708935 | AFC | IFC | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-27 | 0 |  | D00 | IFC | T-0750 | 2022-03-27 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03950 | 2022-04-17 | 1401/01/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-27197 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0750 | 2022-03-27 | 1401/01/06 |  |  |  | BK-SUR-ENG-INS-01-03950 | 2022-04-17 | 1401/01/28 | CM-C3 | [6 empty] | 1401-2294-27197 | 2022-04-17 | 1401/01/28 | 2022-04-25 | 1401/02/05 | CM
3 | 2 | 3 | 5 | 2 | 0 | 15 | 3.2.3.5.2 | Data Sheets For F&G Detectors & Equipment | BK-GCS-PEDCO-120-IN-DT-0016 | BK-GCS-PEDCO-120-IN-DT-0016 | BK | GCS | PEDCO | 120 | IN | DT | 0016 | F9Z-708936 | AFC | IFC | 2022-05-23 | 0 | 0 | -44704 | 0 | -44704 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-09 | 0 |  | D00 | IFC | T-0920 | 2022-05-09 | 1401/02/19 | T-0920 | 2022-05-09 | 1401/02/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0920 | 2022-05-09 | 1401/02/19 | T-0920 | 2022-05-09 | 1401/02/19
3 | 2 | 3 | 5 | 2 | 0 | 16 | 3.2.3.5.2 | Data Sheets For ESD Console/F&G Matrix Panel | BK-GCS-PEDCO-120-IN-DT-0017 | BK-GCS-PEDCO-120-IN-DT-0017 | BK | GCS | PEDCO | 120 | IN | DT | 0017 | F9Z-708937 | AFC | IFC | 2022-05-14 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-30 | 0 |  | D00 | IFC | T-0882 | 2022-04-30 | 1401/02/10 | T-0882 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-INS-01-04305 | 2022-05-18 | 1401/02/28 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0882 | 2022-04-30 | 1401/02/10 | T-0882 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-INS-01-04305 | 2022-05-18 | 1401/02/28 | CM-C3
3 | 2 | 3 | 5 | 2 | 0 | 17 | 3.2.3.5.2 | Data Sheets For Rotameter | BK-GCS-PEDCO-120-IN-DT-0018 | BK-GCS-PEDCO-120-IN-DT-0018 | BK | GCS | PEDCO | 120 | IN | DT | 0018 | F9Z-708938 | AFC | IFC | 2022-04-19 | 2022-05-17 | 2022-05-23 | 28 | 6 | 34 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-05 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | [13 empty] | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM
3 | 2 | 3 | 5 | 2 | 0 | 18 | 3.2.3.5.2 | Data Sheets For Diff. Pressure Type Level Transmitter | BK-GCS-PEDCO-120-IN-DT-0019 | BK-GCS-PEDCO-120-IN-DT-0019 | BK | GCS | PEDCO | 120 | IN | DT | 0019 | F9Z-708939 | AFC | IFC | 2022-04-19 | 2022-05-17 | 2022-05-23 | 28 | 6 | 34 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-05 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0776 | 2022-04-05 | 1401/01/16 | [13 empty] | 1401-2294-65638 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM
3 | 2 | 3 | 5 | 2 | 0 | 19 | 3.2.3.5.2 | Data Sheets For CCTV | BK-GCS-PEDCO-120-IN-DT-0020 | BK-GCS-PEDCO-120-IN-DT-0020 | BK | GCS | PEDCO | 120 | IN | DT | 0020 | F9Z-708940 | AFC | IFC | 2021-10-27 | 2021-10-27 | 2021-11-07 | 0 | 11 | 11 | IFA | 2022-05-16 | 2022-05-21 | 2022-05-23 | 5 | 2 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-13 | 0 |  | D01 | IFA | T-0895 | 2022-05-02 | 1401/02/12 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04224 | 2022-05-10 | 1401/02/20 | AP | PEDCO-BK-GCS-PEDCO-120-IN-DT-0020_D00 | BK-SUR-ENG-INS-01-04258 | 2022-05-14 | 1401/02/24 | AP | 0 | 1401-2294-70035 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | AP | NISOC-BK-GCS-PEDCO-120-IN-DT-0020_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0158 | 2021-10-13 | 1400/07/21 |  |  |  | BK-SUR-ENG-INS-00-01835 | 2021-10-25 | 1400/08/03 | C4-RJ |  | BK-SUR-ENG-TEL-00-01926 | 2021-11-07 | 1400/08/16 | C4-RJ |  | 1400-2294-251389 | 2021-10-27 | 1400/08/05 | 2021-11-07 | 1400/08/16 | CM | [10 empty] | D01 | IFA | T-0895 | 2022-05-02 | 1401/02/12 |  |  |  | BK-SUR-ENG-INS-01-04224 | 2022-05-10 | 1401/02/20 | AP | PEDCO-BK-GCS-PEDCO-120-IN-DT-0020_D00 | BK-SUR-ENG-INS-01-04258 | 2022-05-14 | 1401/02/24 | AP |  | 1401-2294-70035 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | AP | NISOC-BK-GCS-PEDCO-120-IN-DT-0020_D00
3 | 2 | 3 | 5 | 2 | 0 | 20 | 3.2.3.5.2 | Data Sheets For IRP Panel | BK-GCS-PEDCO-120-IN-DT-0021 | BK-GCS-PEDCO-120-IN-DT-0021 | BK | GCS | PEDCO | 120 | IN | DT | 0021 | F9Z-708941 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 3 | 0 | 0 | 3.2.3.5.3 | Drawing/Diagram
3 | 2 | 3 | 5 | 3 | 0 | 1 | 3.2.3.5.3 | Typical Instrument Installation Drawing | BK-GCS-PEDCO-120-IN-DW-0001 | BK-GCS-PEDCO-120-IN-DW-0001 | BK | GCS | PEDCO | 120 | IN | DW | 0001 | F2J-708942 | IFI | IFI | 2022-03-23 | 2022-04-04 | 2022-04-09 | 12 | 5 | 17 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-09 | 2022-03-09 |  | D00 | IFI | T-0709 | 2022-03-09 | 1400/12/18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-9656 | 2022-04-04 | 1401/01/15 | 2022-04-09 | 1401/01/20 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0709 | 2022-03-09 | 1400/12/18 | [13 empty] | 1401-2294-9656 | 2022-04-04 | 1401/01/15 | 2022-04-09 | 1401/01/20 | CM
3 | 2 | 3 | 5 | 3 | 0 | 2 | 3.2.3.5.3 | Control/ESD/F&G System Block Diagram Configuration | BK-GCS-PEDCO-120-IN-BD-0001 | BK-GCS-PEDCO-120-IN-BD-0001 | BK | GCS | PEDCO | 120 | IN | BD | 0001 | F2J-708943 | AFC | IFC | 2021-09-13 | 2021-10-26 | 2021-10-02 | 43 | -24 | 19 | IFA | 2021-11-23 | 2021-11-21 | 2021-11-27 | -2 | 6 | 4 | IFA | 2022-01-24 | 2022-01-29 | 2022-01-30 | 5 | 1 | 6 | IFA | 2022-04-13 | 2022-05-10 | 2022-05-15 | 27 | 5 | 32 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-08-30 | 0 |  | D03 | IFA | T-0765 | 2022-03-30 | 1401/01/10 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03960 | 2022-04-17 | 1401/01/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D02 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55898 | 2022-05-10 | 1401/02/20 | 2022-05-15 | 1401/02/24 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0071 | 2021-08-30 | 1400/06/08 | [13 empty] | 1400-2294-213820 | 2021-10-26 | 1400/07/04 | 2021-10-02 | 1400/07/10 | CM |  | 1400-2294-234028 | 2021-10-13 | 1400/07/21 |  |  | CM |  |  |  | D01 | IFA | T-0218 | 2021-11-09 | 1400/08/18 |  |  |  | BK-SUR-ENG-INS-00-02067 | 2021-11-21 | 1400/08/30 | C4-RJ | [6 empty] | 1400-2294-283482 | 2021-11-21 | 1400/08/30 | 2021-11-27 | 1400/09/06 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D00 | [9 empty] | D02 | IFA | T-0444 | 2022-01-10 | 1400/10/20 |  |  |  | BK-SUR-ENG-INS-00-02815 | 2022-01-25 | 1400/11/05 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D01 | [5 empty] | 1400-2294-385430 | 2022-01-29 | 1400/11/09 | 2022-01-30 | 1400/11/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D01 | [9 empty] | D03 | IFA | T-0765 | 2022-03-30 | 1401/01/10 |  |  |  | BK-SUR-ENG-INS-01-03960 | 2022-04-17 | 1401/01/28 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D02 | [5 empty] | 1401-2294-55898 | 2022-05-10 | 1401/02/20 | 2022-05-15 | 1401/02/24 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D02
3 | 2 | 3 | 5 | 3 | 0 | 3 | 3.2.3.5.3 | Instrument Earthing Typical Diagram | BK-GCS-PEDCO-120-IN-DG-0001 | BK-GCS-PEDCO-120-IN-DG-0001 | BK | GCS | PEDCO | 120 | IN | DG | 0001 | F2J-708944 | IFI | IFI | 2022-01-12 | 2022-01-13 | 2022-01-15 | 1 | 2 | 3 | IFI | 2022-05-01 | 2022-05-12 | 2022-05-16 | 11 | 4 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-29 | 2022-04-17 |  | D01 | IFI | T-0828 | 2022-04-17 | 1401/01/28 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04154 | 2022-05-07 | 1401/02/17 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59512 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0408 | 2021-12-29 | 1400/10/08 | [13 empty] | 1400-2294-362541 | 2022-01-13 | 1400/10/23 | 2022-01-15 | 1400/10/25 | CM | [10 empty] | D01 | IFI | T-0828 | 2022-04-17 | 1401/01/28 |  |  |  | BK-SUR-ENG-INS-01-04154 | 2022-05-07 | 1401/02/17 | CM-C2 | [6 empty] | 1401-2294-59512 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0001_D00
3 | 2 | 3 | 5 | 3 | 0 | 4 | 3.2.3.5.3 | Instrument Hook-up Diagram | BK-GCS-PEDCO-120-IN-DG-0002 | BK-GCS-PEDCO-120-IN-DG-0002 | BK | GCS | PEDCO | 120 | IN | DG | 0002 | F2J-708945 | AFC | IFC | 2022-03-16 | 2022-04-19 | 2022-04-30 | 34 | 11 | 45 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-02 | 0 |  | D00 | IFC | T-0757 | 2022-03-02 | 1401/01/07 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03980 | 2022-04-19 | 1401/01/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31183 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0757 | 2022-03-02 | 1401/01/07 |  |  |  | BK-SUR-ENG-INS-01-03980 | 2022-04-19 | 1401/01/30 | CM-C2 | [6 empty] | 1401-2294-31183 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM
3 | 2 | 3 | 5 | 3 | 0 | 5 | 3.2.3.5.3 | ESD Level Hierarchy | BK-GCS-PEDCO-120-IN-DG-0003 | BK-GCS-PEDCO-120-IN-DG-0003 | BK | GCS | PEDCO | 120 | IN | DG | 0003 | F2J-708946 | AFC | IFC | 2022-06-11 | 0 | 0 | -44723 | 0 | -44723 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-28 | 0 |  | D00 | IFC | T-1014 | 2022-05-28 | 1401/03/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1014 | 2022-05-28 | 1401/03/07
3 | 2 | 3 | 5 | 3 | 0 | 6 | 3.2.3.5.3 | ESD System Loop Diagram | BK-GCS-PEDCO-120-IN-DG-0004 | BK-GCS-PEDCO-120-IN-DG-0004 | BK | GCS | PEDCO | 120 | IN | DG | 0004 | F2J-708947 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 3 | 0 | 7 | 3.2.3.5.3 | Control System Loop Diagram | BK-GCS-PEDCO-120-IN-DG-0005 | BK-GCS-PEDCO-120-IN-DG-0005 | BK | GCS | PEDCO | 120 | IN | DG | 0005 | F2J-708948 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 3 | 0 | 8 | 3.2.3.5.3 | F&G System Loop Diagram | BK-GCS-PEDCO-120-IN-DG-0006 | BK-GCS-PEDCO-120-IN-DG-0006 | BK | GCS | PEDCO | 120 | IN | DG | 0006 | F2J-708949 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 3 | 0 | 9 | 3.2.3.5.3 | Instrument Air Piping and Air Header Diagram | BK-GCS-PEDCO-120-IN-DG-0007 | BK-GCS-PEDCO-120-IN-DG-0007 | BK | GCS | PEDCO | 120 | IN | DG | 0007 | F2J-708950 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 3 | 0 | 10 | 3.2.3.5.3 | Instrument & F&G Junction Box Termination Diagram | BK-GCS-PEDCO-120-IN-DG-0008 | BK-GCS-PEDCO-120-IN-DG-0008 | BK | GCS | PEDCO | 120 | IN | DG | 0008 | F2J-708951 | AFC | IFC | 2022-02-27 | 2022-02-27 | 2022-03-05 | 0 | 6 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-13 | 0 |  | D00 | IFC | T-0581 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03247 | 2022-02-27 | 1400/12/08 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-428474 | 2022-02-27 | 1400/12/08 | 2022-03-05 | 1400/12/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0581 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-INS-00-03247 | 2022-02-27 | 1400/12/08 | C4-RJ | [6 empty] | 1400-2294-428474 | 2022-02-27 | 1400/12/08 | 2022-03-05 | 1400/12/14 | CM
3 | 2 | 3 | 5 | 3 | 0 | 11 | 3.2.3.5.3 | F&G Cause and Effect Diagram For Process Area | BK-GCS-PEDCO-120-IN-DG-0009 | BK-GCS-PEDCO-120-IN-DG-0009 | BK | GCS | PEDCO | 120 | IN | DG | 0009 | F2J-708952 | AFC | IFC | 2022-06-13 | 0 | 0 | -44725 | 0 | -44725 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-30 | 0 |  | D00 | IFC | T-1025 | 2022-05-30 | 1401/03/09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1025 | 2022-05-30 | 1401/03/09
3 | 2 | 3 | 5 | 3 | 0 | 12 | 3.2.3.5.3 | F&G Cause and Effect Diagram For Buildings | BK-GCS-PEDCO-120-IN-DG-0010 | BK-GCS-PEDCO-120-IN-DG-0010 | BK | GCS | PEDCO | 120 | IN | DG | 0010 | F2J-708953 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 3 | 0 | 13 | 3.2.3.5.3 | Control System Logic Diagram | BK-GCS-PEDCO-120-IN-LD-0001 | BK-GCS-PEDCO-120-IN-LD-0001 | BK | GCS | PEDCO | 120 | IN | LD | 0001 | F1J-708954 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 3 | 0 | 14 | 3.2.3.5.3 | ESD Logic Diagram | BK-GCS-PEDCO-120-IN-LD-0002 | BK-GCS-PEDCO-120-IN-LD-0002 | BK | GCS | PEDCO | 120 | IN | LD | 0002 | F1J-708955 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 3 | 0 | 15 | 3.2.3.5.3 | Control Room Layout & Arrangement Drawing | BK-GCS-PEDCO-120-IN-PY-0001 | BK-GCS-PEDCO-120-IN-PY-0001 | BK | GCS | PEDCO | 120 | IN | PY | 0001 | F2J-708956 | AFC | IFC | 2022-02-16 | 2022-03-15 | 2022-03-15 | 27 | 0 | 27 | IFA | 2022-06-01 | 0 | 0 | -44713 | 0 | -44713 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 0 |  | D01 | IFA | T-0973 | 2022-05-18 | 1401/02/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0542 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-INS-00-03061 | 2022-02-14 | 1400/11/25 | CM-C3 | [6 empty] | 1401-2294-449416 | 2022-03-15 | 1400/12/24 | 2022-03-15 | 1400/12/24 | CM | [10 empty] | D01 | IFA | T-0973 | 2022-05-18 | 1401/02/28 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0001_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0001_D00
3 | 2 | 3 | 5 | 3 | 0 | 16 | 3.2.3.5.3 | Control Room Cable Route Layout | BK-GCS-PEDCO-120-IN-PY-0002 | BK-GCS-PEDCO-120-IN-PY-0002 | BK | GCS | PEDCO | 120 | IN | PY | 0002 | F2J-708957 | AFC | IFC | 2022-06-06 | 0 | 0 | -44718 | 0 | -44718 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-23 | 0 |  | D00 | IFC | T-0991 | 2022-05-23 | 1401/03/02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0991 | 2022-05-23 | 1401/03/02
3 | 2 | 3 | 5 | 3 | 0 | 17 | 3.2.3.5.3 | Instrument Location Layout | BK-GCS-PEDCO-120-IN-PY-0003 | BK-GCS-PEDCO-120-IN-PY-0003 | BK | GCS | PEDCO | 120 | IN | PY | 0003 | F2J-708958 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 3 | 0 | 18 | 3.2.3.5.3 | Instrument/F&G Cable Trench/Route Layout Drawing | BK-GCS-PEDCO-120-IN-PY-0004 | BK-GCS-PEDCO-120-IN-PY-0004 | BK | GCS | PEDCO | 120 | IN | PY | 0004 | F2J-708959 | AFC | IFC | 2022-02-08 | 2022-03-09 | 2022-03-12 | 29 | 3 | 32 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-25 | 0 |  | D00 | IFC | T-0509 | 2022-01-25 | 1400/11/05 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03017 | 2022-02-09 | 1400/11/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-442053 | 2022-03-09 | 1400/12/18 | 2022-03-12 | 1400/12/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0509 | 2022-01-25 | 1400/11/05 |  |  |  | BK-SUR-ENG-INS-00-03017 | 2022-02-09 | 1400/11/20 | CM-C3 | [6 empty] | 1400-2294-442053 | 2022-03-09 | 1400/12/18 | 2022-03-12 | 1400/12/21 | CM
3 | 2 | 3 | 5 | 3 | 0 | 19 | 3.2.3.5.3 | F&G Location Layout For Process Area | BK-GCS-PEDCO-120-IN-PY-0005 | BK-GCS-PEDCO-120-IN-PY-0005 | BK | GCS | PEDCO | 120 | IN | PY | 0005 | F2J-708960 | AFC | IFC | 2022-02-21 | 2022-05-10 | 2022-03-13 | 78 | -58 | 20 | IFA | 2022-05-22 | 0 | 0 | -44703 | 0 | -44703 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-07 | 0 |  | D01 | IFA | T-0914 | 2022-05-08 | 1401/02/18 | T-0914 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-INS-01-04431 | 2022-05-25 | 1401/03/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0561 | 2022-02-07 | 1400/11/18 |  |  |  | BK-SUR-ENG-INS-00-03136 | 2022-02-20 | 1400/12/01 | CM-C3 | [6 empty] | 1400-2294-421738 | 2022-02-22 | 1400/12/03 | 2022-03-02 | 1400/12/11 | CM |  | 1400-2294-443233 | 2022-05-10 | 1400/12/19 | 2022-03-13 | 1400/12/22 | CM |  |  |  | D01 | IFA | T-0914 | 2022-05-08 | 1401/02/18 | T-0914 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-INS-01-04431 | 2022-05-25 | 1401/03/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0005_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0005_D00
3 | 2 | 3 | 5 | 3 | 0 | 20 | 3.2.3.5.3 | F&G Location Layout For Buildings | BK-GCS-PEDCO-120-IN-PY-0006 | BK-GCS-PEDCO-120-IN-PY-0006 | BK | GCS | PEDCO | 120 | IN | PY | 0006 | F2J-708961 | AFC | IFC | 2022-05-02 | 2022-05-17 | 2022-05-23 | 15 | 6 | 21 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-18 | 0 |  | D00 | IFC | T-0836 | 2022-04-18 | 1401/01/29 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04157 | 2022-05-07 | 1401/02/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65627 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0836 | 2022-04-18 | 1401/01/29 |  |  |  | BK-SUR-ENG-INS-01-04157 | 2022-05-07 | 1401/02/17 | CM-C3 | [6 empty] | 1401-2294-65627 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM
3 | 2 | 3 | 5 | 3 | 0 | 21 | 3.2.3.5.3 | Block Diagram For CCTV | BK-GCS-PEDCO-120-IN-BD-0002 | BK-GCS-PEDCO-120-IN-BD-0002 | BK | GCS | PEDCO | 120 | IN | BD | 0002 | F2T-708962 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 3 | 0 | 22 | 3.2.3.5.3 | Block Diagram For CCTV in Binak DU | BK-GCS-PEDCO-120-IN-BD-0003 | BK-GCS-PEDCO-120-IN-BD-0003 | BK | GCS | PEDCO | 120 | IN | BD | 0003 | F2T-708963 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 3 | 0 | 23 | 3.2.3.5.3 | CCTV Equipment Layout for GCS Area | BK-GCS-PEDCO-120-IN-PY-0007 | BK-GCS-PEDCO-120-IN-PY-0007 | BK | GCS | PEDCO | 120 | IN | PY | 0007 | F2J-708964 | AFC | IFC | 2022-04-23 | 0 | 0 | -44674 | 0 | -44674 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-09 | 0 |  | D00 | IFC | T-0792 | 2022-04-09 | 1401/01/20 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-03896 | 2022-04-27 | 1401/02/07 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0792 | 2022-04-09 | 1401/01/20 |  |  |  | BK-SUR-ENG-INS-01-03896 | 2022-04-27 | 1401/02/07 | AP
3 | 2 | 3 | 5 | 3 | 0 | 24 | 3.2.3.5.3 | CCTV Equipment Layout For Desalting Unit Area | BK-GCS-PEDCO-120-IN-PY-0008 | BK-GCS-PEDCO-120-IN-PY-0008 | BK | GCS | PEDCO | 120 | IN | PY | 0008 | F2J-708965 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 3 | 0 | 25 | 3.2.3.5.3 | Wiring Diagram For Interposing Relay Panel (IRP) | BK-GCS-PEDCO-120-EL-DG-0011 | BK-GCS-PEDCO-120-EL-DG-0011 | BK | GCS | PEDCO | 120 | EL | DG | 0011 | F2P-708966 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 4 | 0 | 0 | 3.2.3.5.4 | List
3 | 2 | 3 | 5 | 4 | 0 | 1 | 3.2.3.5.4 | Instrument Index | BK-GCS-PEDCO-120-IN-LI-0001 | BK-GCS-PEDCO-120-IN-LI-0001 | BK | GCS | PEDCO | 120 | IN | LI | 0001 | F0Z-708967 | AFC | IFC | 2022-05-11 | 0 | 0 | -44692 | 0 | -44692 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-27 | 0 |  | D00 | IFC | T-0867 | 2022-04-27 | 1401/02/07 | T-0867 | 2022-04-27 | 1401/02/07 | BK-SUR-ENG-INS-01-04195 | 2022-05-10 | 1401/02/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0867 | 2022-04-27 | 1401/02/07 | T-0867 | 2022-04-27 | 1401/02/07 | BK-SUR-ENG-INS-01-04195 | 2022-05-10 | 1401/02/20 | CM-C3
3 | 2 | 3 | 5 | 4 | 0 | 2 | 3.2.3.5.4 | I/O List For Control System | BK-GCS-PEDCO-120-IN-LI-0002 | BK-GCS-PEDCO-120-IN-LI-0002 | BK | GCS | PEDCO | 120 | IN | LI | 0002 | F0Z-708968 | AFC | IFC | 2022-02-08 | 2022-03-09 | 2022-03-12 | 29 | 3 | 32 | IFA | 2022-05-24 | 0 | 0 | -44705 | 0 | -44705 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-25 | 0 |  | D01 | IFA | T-0926 | 2022-05-10 | 1401/02/20 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04433 | 2022-05-24 | 1401/03/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISCO-CRS-BK-GCS-NISCO-120-IN-LI-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0509 | 2022-01-25 | 1400/11/05 |  |  |  | BK-SUR-ENG-INS-00-03017 | 2022-02-09 | 1400/11/20 | CM-C3 | [6 empty] | 1400-2294-442053 | 2022-03-09 | 1400/12/18 | 2022-03-12 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0926 | 2022-05-10 | 1401/02/20 |  |  |  | BK-SUR-ENG-INS-01-04433 | 2022-05-24 | 1401/03/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0002_D00 | [11 empty] | NISCO-CRS-BK-GCS-NISCO-120-IN-LI-0002_D00
3 | 2 | 3 | 5 | 4 | 0 | 3 | 3.2.3.5.4 | I/O List For ESD Systems | BK-GCS-PEDCO-120-IN-LI-0003 | BK-GCS-PEDCO-120-IN-LI-0003 | BK | GCS | PEDCO | 120 | IN | LI | 0003 | F0Z-708969 | AFC | IFC | 2022-02-08 | 2022-03-09 | 2022-03-12 | 29 | 3 | 32 | IFA | 2022-05-28 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-25 | 0 |  | D01 | IFA | T-0941 | 2022-05-14 | 1401/02/24 | T-0941 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-INS-01-04473 | 2022-05-29 | 1401/03/08 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0509 | 2022-01-25 | 1400/11/05 |  |  |  | BK-SUR-ENG-INS-00-03017 | 2022-02-09 | 1400/11/20 | CM-C3 | [6 empty] | 1400-2294-442053 | 2022-03-09 | 1400/12/18 | 2022-03-12 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0941 | 2022-05-14 | 1401/02/24 | T-0941 | 2022-05-14 | 1401/02/24 | BK-SUR-ENG-INS-01-04473 | 2022-05-29 | 1401/03/08 | CM-C3 | [34 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0003_D00 | [11 empty] | NISCO-CRS-BK-GCS-NISCO-120-IN-LI-0003_D00
3 | 2 | 3 | 5 | 4 | 0 | 4 | 3.2.3.5.4 | I/O List For F&G Systems | BK-GCS-PEDCO-120-IN-LI-0004 | BK-GCS-PEDCO-120-IN-LI-0004 | BK | GCS | PEDCO | 120 | IN | LI | 0004 | F0Z-708970 | AFC | IFC | 2022-02-21 | 2022-05-10 | 2022-03-13 | 78 | -58 | 20 | IFA | 2022-05-25 | 0 | 0 | -44706 | 0 | -44706 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-07 | 0 |  | D01 | IFA | T-0931 | 2022-05-11 | 1401/02/21 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04458 | 2022-05-28 | 1401/03/07 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0561 | 2022-02-07 | 1400/11/18 |  |  |  | BK-SUR-ENG-INS-00-03136 | 2022-02-20 | 1400/12/01 | CM-C3 | [6 empty] | 1400-2294-421738 | 2022-02-22 | 1400/12/03 | 2022-03-02 | 1400/12/11 | CM |  | 1400-2294-443333 | 2022-05-10 | 1400/12/19 | 2022-03-13 | 1400/12/22 | CM |  |  |  | D01 | IFA | T-0931 | 2022-05-11 | 1401/02/21 |  |  |  | BK-SUR-ENG-INS-01-04458 | 2022-05-28 | 1401/03/07 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0004_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0004_D00
3 | 2 | 3 | 5 | 4 | 0 | 5 | 3.2.3.5.4 | Panels & Junction Box List | BK-GCS-PEDCO-120-IN-LI-0005 | BK-GCS-PEDCO-120-IN-LI-0005 | BK | GCS | PEDCO | 120 | IN | LI | 0005 | F0Z-708971 | AFC | IFC | 2022-02-27 | 2022-03-03 | 2022-03-08 | 4 | 5 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-13 | 0 |  | D00 | IFC | T-0587 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03250 | 2022-02-27 | 1400/12/08 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-432761 | 2022-03-03 | 1400/12/12 | 2022-03-08 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0587 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-INS-00-03250 | 2022-02-27 | 1400/12/08 | C4-RJ | [6 empty] | 1400-2294-432761 | 2022-03-03 | 1400/12/12 | 2022-03-08 | 1400/12/17 | CM
3 | 2 | 3 | 5 | 4 | 0 | 6 | 3.2.3.5.4 | Set Point & Alarm List | BK-GCS-PEDCO-120-IN-LI-0006 | BK-GCS-PEDCO-120-IN-LI-0006 | BK | GCS | PEDCO | 120 | IN | LI | 0006 | F0Z-708972 | AFC | IFC | 2022-05-23 | 0 | 0 | -44704 | 0 | -44704 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-09 | 0 |  | D00 | IFC | T-0920 | 2022-05-09 | 1401/02/19 | T-0920 | 2022-05-09 | 1401/02/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0920 | 2022-05-09 | 1401/02/19 | T-0920 | 2022-05-09 | 1401/02/19
3 | 2 | 3 | 5 | 4 | 0 | 7 | 3.2.3.5.4 | I&C Power Consumption Summary | BK-GCS-PEDCO-120-IN-LI-0007 | BK-GCS-PEDCO-120-IN-LI-0007 | BK | GCS | PEDCO | 120 | IN | LI | 0007 | F0Z-708973 | AFC | IFC | 2022-03-09 | 2022-03-16 | 2022-03-27 | 7 | 11 | 18 | IFA | 2022-05-04 | 0 | 0 | -44685 | 0 | -44685 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-23 | 0 |  | D01 | IFA | T-0852 | 2022-04-20 | 1401/01/31 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04170 | 2022-05-08 | 1401/02/18 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0633 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-INS-00-03437 | 2022-03-09 | 1400/12/18 | CM-C3 | [6 empty] | 1400-2294-453220 | 2022-03-16 | 1400/12/25 | 2022-03-27 | 1401/01/07 | CM | [10 empty] | D01 | IFA | T-0852 | 2022-04-20 | 1401/01/31 |  |  |  | BK-SUR-ENG-INS-01-04170 | 2022-05-08 | 1401/02/18 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0007_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0007_D00
3 | 2 | 3 | 5 | 4 | 0 | 8 | 3.2.3.5.4 | F&G Detector List | BK-GCS-PEDCO-120-IN-LI-0008 | BK-GCS-PEDCO-120-IN-LI-0008 | BK | GCS | PEDCO | 120 | IN | LI | 0008 | F0Z-708974 | AFC | IFC | 2022-02-21 | 2022-05-10 | 2022-03-13 | 78 | -58 | 20 | IFA | 2022-05-24 | 0 | 0 | -44705 | 0 | -44705 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-07 | 0 |  | D01 | IFA | T-0926 | 2022-05-10 | 1401/02/20 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04433 | 2022-05-24 | 1401/03/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0008_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0561 | 2022-02-07 | 1400/11/18 |  |  |  | BK-SUR-ENG-INS-00-03136 | 2022-02-20 | 1400/12/01 | CM-C3 | [6 empty] | 1400-2294-421738 | 2022-02-22 | 1400/12/03 | 2022-03-02 | 1400/12/11 | CM |  | 1400-2294-443233 | 2022-05-10 | 1400/12/19 | 2022-03-13 | 1400/12/22 | CM |  |  |  | D01 | IFA | T-0926 | 2022-05-10 | 1401/02/20 |  |  |  | BK-SUR-ENG-INS-01-04433 | 2022-05-24 | 1401/03/03 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0008_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0008_D00
3 | 2 | 3 | 5 | 4 | 0 | 9 | 3.2.3.5.4 | Instrument /F&G Cable List | BK-GCS-PEDCO-120-IN-LI-0009 | BK-GCS-PEDCO-120-IN-LI-0009 | BK | GCS | PEDCO | 120 | IN | LI | 0009 | F0Z-708975 | AFC | IFC | 2022-02-27 | 2022-03-03 | 2022-03-08 | 4 | 5 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-13 | 0 |  | D00 | IFC | T-0587 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03250 | 2022-02-27 | 1400/12/08 | C4-RJ | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-432761 | 2022-03-03 | 1400/12/12 | 2022-03-08 | 1400/12/17 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0587 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-INS-00-03250 | 2022-02-27 | 1400/12/08 | C4-RJ | [6 empty] | 1400-2294-432761 | 2022-03-03 | 1400/12/12 | 2022-03-08 | 1400/12/17 | CM
3 | 2 | 3 | 5 | 4 | 0 | 10 | 3.2.3.5.4 | Cable Schedule For CCTV | BK-GCS-PEDCO-120-IN-LI-0010 | BK-GCS-PEDCO-120-IN-LI-0010 | BK | GCS | PEDCO | 120 | IN | LI | 0010 | F0Z-708976 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 4 | 0 | 11 | 3.2.3.5.4 | Cable Schedule For CCTV in Binak DU Area | BK-GCS-PEDCO-120-IN-LI-0011 | BK-GCS-PEDCO-120-IN-LI-0011 | BK | GCS | PEDCO | 120 | IN | LI | 0011 | F0Z-708977 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 5 | 0 | 0 | 3.2.3.5.5 | MTO
3 | 2 | 3 | 5 | 5 | 0 | 1 | 3.2.3.5 | MTO for Bulk Item and Installation Accessories | BK-GCS-PEDCO-120-IN-MT-0001 | BK-GCS-PEDCO-120-IN-MT-0001 | BK | GCS | PEDCO | 120 | IN | MT | 0001 | F8Z-708978 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 5 | 0 | 2 | 3.2.3.5 | MTO For Instrument/F&G Cable | BK-GCS-PEDCO-120-IN-MT-0002 | BK-GCS-PEDCO-120-IN-MT-0002 | BK | GCS | PEDCO | 120 | IN | MT | 0002 | F8Z-708979 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 5 | 0 | 3 | 3.2.3.5 | MTO For Instrument/F&G Junction box and Gland | BK-GCS-PEDCO-120-IN-MT-0003 | BK-GCS-PEDCO-120-IN-MT-0003 | BK | GCS | PEDCO | 120 | IN | MT | 0003 | F8Z-708980 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 5 | 0 | 4 | 3.2.3.5 | MTO For Instrument Tube and Fitting | BK-GCS-PEDCO-120-IN-MT-0004 | BK-GCS-PEDCO-120-IN-MT-0004 | BK | GCS | PEDCO | 120 | IN | MT | 0004 | F8Z-708981 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 5 | 0 | 5 | 3.2.3.5 | MTO For Instrument Cable Tray/Ladder | BK-GCS-PEDCO-120-IN-MT-0005 | BK-GCS-PEDCO-120-IN-MT-0005 | BK | GCS | PEDCO | 120 | IN | MT | 0005 | F8Z-708982 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 5 | 5 | 0 | 6 | 3.2.3.5 | MTO For CCTV | BK-GCS-PEDCO-120-IN-MT-0006 | BK-GCS-PEDCO-120-IN-MT-0006 | BK | GCS | PEDCO | 120 | IN | MT | 0006 | F8Z-708983 | IFI | IFI | 2021-12-26 | 2021-12-22 | 2021-12-26 | -4 | 4 | 0 | IFI | 2022-02-26 | 2022-02-22 | 2022-02-02 | -4 | -20 | -24 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-12 | 2022-02-12 |  | D01 | IFI | T-0572 | 2022-02-12 | 1400/11/23 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03147 | 2022-02-21 | 1400/12/02 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-421739 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-MT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0329 | 2021-12-12 | 1400/09/21 |  |  |  | BK-SUR-ENG-INS-00-02405 | 2021-12-22 | 1400/10/01 | AP | [6 empty] | 1400-2294-330916 | 2021-12-22 | 1400/10/01 | 2021-12-26 | 1400/10/05 | CM | [10 empty] | D01 | IFI | T-0572 | 2022-02-12 | 1400/11/23 |  |  |  | BK-SUR-ENG-INS-00-03147 | 2022-02-21 | 1400/12/02 | AP | [6 empty] | 1400-2294-421739 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-MT-0006_D00
3 | 2 | 3 | 5 | 5 | 0 | 7 | 3.2.3.5 | MTO For CCTV in Binak DU Area | BK-GCS-PEDCO-120-IN-MT-0007 | BK-GCS-PEDCO-120-IN-MT-0007 | BK | GCS | PEDCO | 120 | IN | MT | 0007 | F8Z-708984 | IFI | IFI | 2021-12-27 | 2021-12-22 | 2021-12-26 | -5 | 4 | -1 | IFI | 2022-05-16 | 2022-05-21 | 2022-05-23 | 5 | 2 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 2022-05-02 |  | D01 | IFI | T-0897 | 2022-05-02 | 1401/02/12 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04223 | 2022-05-10 | 1401/02/20 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-IN-MT-0007_D00 | BK-SUR-ENG-INS-01-04259 | 2022-05-14 | 1401/02/24 | AP | 0 | 1401-2294-70041 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-MT-0007_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0336 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-INS-00-02419 | 2021-12-25 | 1400/10/05 | AP | [6 empty] | 1400-2294-330942 | 2021-12-22 | 1400/10/01 | 2021-12-26 | 1400/10/05 | CM | [10 empty] | D01 | IFI | T-0897 | 2022-05-02 | 1401/02/12 |  |  |  | BK-SUR-ENG-INS-01-04223 | 2022-05-10 | 1401/02/20 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-IN-MT-0007_D00 | BK-SUR-ENG-INS-01-04259 | 2022-05-14 | 1401/02/24 | AP |  | 1401-2294-70041 | 2022-05-21 | 1401/02/31 | 2022-05-23 | 1401/03/02 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-MT-0007_D00
3 | 2 | 3 | 6 | 0 | 0 | 0 | 3.2.3.6 | Safety & Fire Fighting
3 | 2 | 3 | 6 | 1 | 0 | 0 | 3.2.3.6.1 | Basis/Criteria
3 | 2 | 3 | 6 | 1 | 0 | 1 | 3.2.3.6.1 | Active Fire Protection and Safety Concept | BK-GCS-PEDCO-120-SA-DB-0001 | BK-GCS-PEDCO-120-SA-DB-0001 | BK | GCS | PEDCO | 120 | SA | DB | 0001 | F0Z-708985 | AFD | IFC | 44467 | 44478 | 44482 | 11 | 4 | 15 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-14 | 0 |  | D00 | IFC | T-0093 | 2021-09-14 | 1400/06/23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2290-225647 | 2021-10-09 | 1400/07/17 | 2021-10-13 | 1400/07/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0093 | 2021-09-14 | 1400/06/23 | [13 empty] | 1400-2290-225647 | 2021-10-09 | 1400/07/17 | 2021-10-13 | 1400/07/21 | CM
3 | 2 | 3 | 6 | 2 | 0 | 0 | 3.2.3.6.2 | Calculation
3 | 2 | 3 | 6 | 2 | 0 | 1 | 3.2.3.6.2 | Calculation Note For Total Flooding Demand For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-SA-CN-0001 | BK-GCS-PEDCO-120-SA-CN-0001 | BK | GCS | PEDCO | 120 | SA | CN | 0001 | F0Z-708986 | AFD | IFC | 2022-01-30 | 2022-02-16 | 2022-02-22 | 17 | 6 | 23 | AFD | 2022-03-23 | 2022-03-12 | 2022-03-15 | -11 | 3 | -8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-16 | 2022-03-09 |  | D01 | AFD | T-0704 | 2022-03-09 | 1400/12/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445301 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0465 | 2022-01-16 | 1400/10/26 | [13 empty] | 1400-2294-412869 | 2022-02-16 | 1400/11/27 | 2022-02-22 | 1400/12/03 | AP | [10 empty] | D01 | AFD | T-0704 | 2022-03-09 | 1400/12/19 | [13 empty] | 1400-2294-445301 | 2022-03-12 | 1400/12/21 | 2022-03-15 | 1400/12/24 | AP
3 | 2 | 3 | 6 | 2 | 0 | 2 | 3.2.3.6.2 | Calculation Note For Fire Water Demand | BK-GCS-PEDCO-120-SA-CN-0002 | BK-GCS-PEDCO-120-SA-CN-0002 | BK | GCS | PEDCO | 120 | SA | CN | 0002 | F0Z-708987 | AFD | IFC | 2021-12-27 | 2021-01-02 | 2022-01-04 | -359 | 367 | 8 | IFA | 2022-01-29 | 2022-02-16 | 2022-02-22 | 18 | 6 | 24 | IFA | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 0 |  | D02 | IFA | T-0985 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-SA-CN-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0333 | 2021-12-13 | 1400/09/22 | [13 empty] | 1400-2294-345121 | 2021-01-02 | 1400/10/12 | 2022-01-04 | 1400/10/14 | CM | [10 empty] | D01 | IFA | T-0457 | 2022-01-15 | 1400/10/22 | [13 empty] | 1400-2294-412382 | 2022-02-16 | 1400/11/27 | 2022-02-22 | 1400/12/03 | CM | NISOC-CRS-BK-GCS-PEDCO-120-SA-CN-0002_D00 | [9 empty] | D02 | IFA | T-0985 | 2022-05-22 | 1401/03/01 | [19 empty] | NISOC-CRS-BK-GCS-PEDCO-120-SA-CN-0002_D01
3 | 2 | 3 | 6 | 2 | 0 | 3 | 3.2.3.6.2 | Fire Water Hydraulic Calculation Note | BK-GCS-PEDCO-120-SA-CN-0003 | BK-GCS-PEDCO-120-SA-CN-0003 | BK | GCS | PEDCO | 120 | SA | CN | 0003 | F0Z-708988 | AFD | IFC | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-22 | 0 |  | D00 | IFC | T-0986 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0986 | 2022-05-22 | 1401/03/01
3 | 2 | 3 | 6 | 3 | 0 | 0 | 3.2.3.6.3 | Data Sheets
3 | 2 | 3 | 6 | 3 | 0 | 1 | 3.2.3.6.3 | Data Sheets For Safety Equipment | BK-GCS-PEDCO-120-SA-DT-0002 | BK-GCS-PEDCO-120-SA-DT-0002 | BK | GCS | PEDCO | 120 | SA | DT | 0002 | F0Z-708989 | AFC | IFC | 2022-05-03 | 0 | 0 | -44684 | 0 | -44684 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-19 | 0 |  | D00 | IFC | T-0842 | 2022-04-19 | 1401/01/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0842 | 2022-04-19 | 1401/01/30
3 | 2 | 3 | 6 | 3 | 0 | 2 | 3.2.3.6.3 | Data Sheets For Fire Fighting Equipment | BK-GCS-PEDCO-120-SA-DT-0003 | BK-GCS-PEDCO-120-SA-DT-0003 | BK | GCS | PEDCO | 120 | SA | DT | 0003 | F0Z-708990 | AFC | IFC | 2022-05-02 | 2022-05-17 | 2022-05-23 | 15 | 6 | 21 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-18 | 0 |  | D00 | IFC | T-0837 | 2022-04-18 | 1401/01/29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-65658 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0837 | 2022-04-18 | 1401/01/29 | [13 empty] | 1401-2294-65658 | 2022-05-17 | 1401/02/27 | 2022-05-23 | 1401/03/02 | CM
3 | 2 | 3 | 6 | 3 | 0 | 3 | 3.2.3.6.3 | Data Sheets For Deluge valves | BK-GCS-PEDCO-120-SA-DT-0004 | BK-GCS-PEDCO-120-SA-DT-0004 | BK | GCS | PEDCO | 120 | SA | DT | 0004 | F0Z-708991 | AFC | IFC | 2022-01-30 | 2022-02-16 | 2022-02-22 | 17 | 6 | 23 | IFA | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-16 | 0 |  | D01 | IFA | T-0985 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-SA-DT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0465 | 2022-01-16 | 1400/10/26 | [13 empty] | 1400-2294-412869 | 2022-02-16 | 1400/11/27 | 2022-02-22 | 1400/12/03 | CM | [10 empty] | D01 | IFA | T-0985 | 2022-05-22 | 1401/03/01 | [19 empty] | NISOC-CRS-BK-GCS-PEDCO-120-SA-DT-0004_D00
3 | 2 | 3 | 6 | 3 | 0 | 4 | 3.2.3.6.3 | Data Sheets For Water Spray Nozzles | BK-GCS-PEDCO-120-SA-DT-0005 | BK-GCS-PEDCO-120-SA-DT-0005 | BK | GCS | PEDCO | 120 | SA | DT | 0005 | F0Z-708992 | AFC | IFC | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-22 | 0 |  | D00 | IFC | T-0986 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0986 | 2022-05-22 | 1401/03/01
3 | 2 | 3 | 6 | 3 | 0 | 5 | 3.2.3.6.3 | Data Sheets For Safety Sign | BK-GCS-PEDCO-120-SA-DT-0006 | BK-GCS-PEDCO-120-SA-DT-0006 | BK | GCS | PEDCO | 120 | SA | DT | 0006 | F0Z-708993 | AFC | IFC | 2021-10-04 | 2021-10-10 | 2021-10-13 | 6 | 3 | 9 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-20 | 0 |  | D00 | IFC | T-0106 | 2021-09-20 | 1400/06/29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2290-227968 | 2021-10-10 | 1400/07/18 | 2021-10-13 | 1400/07/21 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0106 | 2021-09-20 | 1400/06/29 | [13 empty] | 1400-2290-227968 | 2021-10-10 | 1400/07/18 | 2021-10-13 | 1400/07/21 | CM
3 | 2 | 3 | 6 | 4 | 0 | 0 | 3.2.3.6.4 | Drawing/Diagram
3 | 2 | 3 | 6 | 4 | 0 | 1 | 3.2.3.6.4 | PFD - Fire Water System | BK-GCS-PEDCO-120-SA-PF-0001 | BK-GCS-PEDCO-120-SA-PF-0001 | BK | GCS | PEDCO | 120 | SA | PF | 0001 | F2A-708994 | AFC | IFC | 2021-12-27 | 2021-01-02 | 2022-01-04 | -359 | 367 | 8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 0 |  | D00 | IFC | T-0333 | 2021-12-13 | 1400/08/22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-345121 | 2021-01-02 | 1400/10/12 | 2022-01-04 | 1400/10/14 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0333 | 2021-12-13 | 1400/08/22 | [13 empty] | 1400-2294-345121 | 2021-01-02 | 1400/10/12 | 2022-01-04 | 1400/10/14 | CM
3 | 2 | 3 | 6 | 4 | 0 | 2 | 3.2.3.6.4 | P&ID - Fire Water Network | BK-GCS-PEDCO-120-SA-PI-0001 | BK-GCS-PEDCO-120-SA-PI-0001 | BK | GCS | PEDCO | 120 | SA | PI | 0001 | F2A-708995 | AFC | IFC | 2022-02-26 | 2022-04-19 | 2022-04-30 | 52 | 11 | 63 | IFA | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-12 | 0 |  | D01 | IFA | T-0985 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-SA-PI-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0571 | 2022-02-12 | 1400/11/23 | [13 empty] | 1400-2294-451052 | 2022-03-15 | 1400/12/24 | 2022-04-01 | 1401/01/14 | CM |  | 1401-2294-31220 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM |  |  |  | D01 | IFA | T-0985 | 2022-05-22 | 1401/03/01 | [19 empty] | NISOC-CRS-BK-GCS-PEDCO-120-SA-PI-0001_D00
3 | 2 | 3 | 6 | 4 | 0 | 3 | 3.2.3.6.4 | P&ID - Total Flooding System For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-SA-PI-0002 | BK-GCS-PEDCO-120-SA-PI-0002 | BK | GCS | PEDCO | 120 | SA | PI | 0002 | F2A-708996 | AFC | IFC | 2022-01-30 | 2022-02-16 | 2022-02-22 | 17 | 6 | 23 | IFA | 2022-04-20 | 2022-05-09 | 2022-05-16 | 19 | 7 | 26 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-16 | 0 |  | D01 | IFA | T-0779 | 2022-04-06 | 1401/01/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-55024 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | AP | NISOC-CRS-BK-GCS-PEDCO-120-SA-PI-0002-D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0465 | 2022-01-16 | 1400/10/26 | [13 empty] | 1400-2294-412869 | 2022-02-16 | 1400/11/27 | 2022-02-22 | 1400/12/03 | CM | [10 empty] | D01 | IFA | T-0779 | 2022-04-06 | 1401/01/17 | [13 empty] | 1401-2294-55024 | 2022-05-09 | 1401/02/19 | 2022-05-16 | 1401/02/26 | AP | NISOC-CRS-BK-GCS-PEDCO-120-SA-PI-0002-D00
3 | 2 | 3 | 6 | 4 | 0 | 4 | 3.2.3.6.4 | Fire Water Network Layout | BK-GCS-PEDCO-120-SA-PY-0001 | BK-GCS-PEDCO-120-SA-PY-0001 | BK | GCS | PEDCO | 120 | SA | PY | 0001 | F2A-708997 | AFC | IFC | 2021-12-27 | 2021-01-02 | 2022-01-04 | -359 | 367 | 8 | IFA | 2022-05-11 | 0 | 0 | -44692 | 0 | -44692 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 0 |  | D01 | IFA | T-0865 | 2022-04-27 | 1401/02/07 | T-0865 | 2022-04-27 | 1401/02/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-SA-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0333 | 2021-12-13 | 1400/08/22 | [13 empty] | 1400-2294-345121 | 2021-01-02 | 1400/10/12 | 2022-01-04 | 1400/10/14 | CM | [10 empty] | D01 | IFA | T-0865 | 2022-04-27 | 1401/02/07 | T-0865 | 2022-04-27 | 1401/02/07 | [16 empty] | NISOC-CRS-BK-GCS-PEDCO-120-SA-PY-0001_D00
3 | 2 | 3 | 6 | 4 | 0 | 5 | 3.2.3.6.4 | Hazardous Area Classification Layout | BK-GCS-PEDCO-120-SA-PY-0002 | BK-GCS-PEDCO-120-SA-PY-0002 | BK | GCS | PEDCO | 120 | SA | PY | 0002 | F2L-708998 | AFC | IFC | 2022-03-26 | 2022-04-13 | 2022-04-16 | 18 | 3 | 21 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-12 | 0 |  | D00 | IFC | T-0715 | 2022-03-12 | 1400/12/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-16831 | 2022-04-10 | 1401/01/21 | 2022-04-11 | 1401/01/22 | CM | 0 | 1401-2294-22713 | 2022-04-13 | 1401/01/24 | 2022-04-16 | 1401/01/27 | CM | 0 | 0 |  | D00 | IFC | T-0715 | 2022-03-12 | 1400/12/21 | [13 empty] | 1401-2294-16831 | 2022-04-10 | 1401/01/21 | 2022-04-11 | 1401/01/22 | CM |  | 1401-2294-22713 | 2022-04-13 | 1401/01/24 | 2022-04-16 | 1401/01/27 | CM
3 | 2 | 3 | 6 | 4 | 0 | 6 | 3.2.3.6.4 | Fire Proofing Zone Layout | BK-GCS-PEDCO-120-SA-PY-0003 | BK-GCS-PEDCO-120-SA-PY-0003 | BK | GCS | PEDCO | 120 | SA | PY | 0003 | F2L-708999 | AFC | IFC | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-22 | 0 |  | D00 | IFC | T-0986 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0986 | 2022-05-22 | 1401/03/01
3 | 2 | 3 | 6 | 4 | 0 | 7 | 3.2.3.6.4 | Safety & Fire Fighting Equipment Location Layout | BK-GCS-PEDCO-120-SA-PY-0004 | BK-GCS-PEDCO-120-SA-PY-0004 | BK | GCS | PEDCO | 120 | SA | PY | 0004 | F2L-709000 | AFC | IFC | 2022-02-26 | 2022-04-19 | 2022-04-30 | 52 | 11 | 63 | IFA | 2022-05-28 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-12 | 0 |  | D01 | IFA | T-0943 | 2022-05-14 | 1401/02/24 | T-0943 | 2022-05-14 | 1401/02/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-SA-PY-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0571 | 2022-02-12 | 1400/11/23 | [13 empty] | 1400-2294-451052 | 2022-03-15 | 1400/12/24 | 2022-04-01 | 1401/01/14 | CM |  | 1401-2294-31220 | 2022-04-19 | 1401/01/30 | 2022-04-30 | 1401/02/10 | CM |  |  |  | D01 | IFA | T-0943 | 2022-05-14 | 1401/02/24 | T-0943 | 2022-05-14 | 1401/02/24 | [16 empty] | NISOC-CRS-BK-GCS-PEDCO-120-SA-PY-0004_D00
3 | 2 | 3 | 6 | 4 | 0 | 8 | 3.2.3.6.4 | Escape Route & Safety Sign Layout | BK-GCS-PEDCO-120-SA-PY-0005 | BK-GCS-PEDCO-120-SA-PY-0005 | BK | GCS | PEDCO | 120 | SA | PY | 0005 | F2L-709001 | AFC | IFC | 2022-05-24 | 0 | 0 | -44705 | 0 | -44705 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-10 | 0 |  | D00 | IFC | T-0923 | 2022-05-10 | 1401/02/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0923 | 2022-05-10 | 1401/02/20
3 | 2 | 3 | 6 | 5 | 0 | 0 | 3.2.3.6.5 | List
3 | 2 | 3 | 6 | 5 | 0 | 1 | 3.2.3.6.5 | Hazard Source List | BK-GCS-PEDCO-120-SA-LI-0001 | BK-GCS-PEDCO-120-SA-LI-0001 | BK | GCS | PEDCO | 120 | SA | LI | 0001 | F0Z-709002 | AFC | IFC | 2022-03-09 | 2022-04-07 | 2022-04-07 | 29 | 0 | 29 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-23 | 0 |  | D00 | IFC | T-0634 | 2022-02-23 | 1400/12/04 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03328 | 2022-03-05 | 1400/12/14 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-431005 | 2022-03-02 | 1400/12/11 | 2022-03-05 | 1400/12/15 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0634 | 2022-02-23 | 1400/12/04 |  |  |  | BK-SUR-ENG-CIV-00-03328 | 2022-03-05 | 1400/12/14 | AP | [6 empty] | 1401-2294-13860 | 2022-04-07 | 1401/01/18 | 2022-04-07 | 1401/01/18 | CM
3 | 2 | 3 | 6 | 5 | 0 | 2 | 3.2.3.6.5 | Fire Fighting Line List | BK-GCS-PEDCO-120-SA-LI-0002 | BK-GCS-PEDCO-120-SA-LI-0002 | BK | GCS | PEDCO | 120 | SA | LI | 0002 | F0Z-709003 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 6 | 6 | 0 | 0 | 3.2.3.6.6 | Report
3 | 2 | 3 | 6 | 6 | 0 | 1 | 3.2.3.6.6 | Consequence Modeling Report | BK-GCS-PEDCO-120-SA-RT-0003 | BK-GCS-PEDCO-120-SA-RT-0003 | BK | GCS | PEDCO | 120 | SA | RT | 0003 | F0Z-709004 | AFD | IFC | 44535 | 44545 | 44548 | 10 | 3 | 13 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-21 | 0 |  | D00 | IFC | T-0261 | 2021-11-21 | 1400/08/30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-319725 | 2021-12-15 | 1400/09/24 | 2021-12-18 | 1400/09/27 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0261 | 2021-11-21 | 1400/08/30 | [13 empty] | 1400-2294-319725 | 2021-12-15 | 1400/09/24 | 2021-12-18 | 1400/09/27 | AP
3 | 2 | 3 | 6 | 7 | 0 | 0 | 3.2.3.6.7 | MTO
3 | 2 | 3 | 6 | 7 | 0 | 1 | 3.2.3.6 | MTO For Safety & Fire Fighting Equipment | BK-GCS-PEDCO-120-SA-MT-0001 | BK-GCS-PEDCO-120-SA-MT-0001 | BK | GCS | PEDCO | 120 | SA | MT | 0001 | F8Z-709005 | IFI | IFI | 2022-06-05 | 0 | 0 | -44717 | 0 | -44717 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-22 | 2022-05-22 |  | D00 | IFI | T-0987 | 2022-05-22 | 1401/03/01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0987 | 2022-05-22 | 1401/03/01
3 | 2 | 3 | 6 | 7 | 0 | 2 | 3.2.3.6 | MTO For Safety Sign | BK-GCS-PEDCO-120-SA-MT-0002 | BK-GCS-PEDCO-120-SA-MT-0002 | BK | GCS | PEDCO | 120 | SA | MT | 0002 | F8Z-709006 | IFI | IFI | 2022-05-29 | 0 | 0 | -44710 | 0 | -44710 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-15 | 2022-05-15 |  | D00 | IFI | T-0952 | 2022-05-15 | 1401/02/25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0952 | 2022-05-15 | 1401/02/25
3 | 2 | 3 | 7 | 0 | 0 | 0 | 3.2.3.7 | Electrical
3 | 2 | 3 | 7 | 1 | 0 | 0 | 3.2.3.7.1 | Calculation
3 | 2 | 3 | 7 | 1 | 0 | 1 | 3.2.3.7.1 | Calculation Note For Outdoor Area Lighting System | BK-GCS-PEDCO-120-EL-CN-0001 | BK-GCS-PEDCO-120-EL-CN-0001 | BK | GCS | PEDCO | 120 | EL | CN | 0001 | F0Z-709007 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 1 | 0 | 2 | 3.2.3.7.1 | Calculation Note For Indoor Area Lighting System | BK-GCS-PEDCO-120-EL-CN-0002 | BK-GCS-PEDCO-120-EL-CN-0002 | BK | GCS | PEDCO | 120 | EL | CN | 0002 | F0Z-709008 | AFD | IFC | 2022-05-11 | 0 | 0 | -44692 | 0 | -44692 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-27 | 0 |  | D00 | IFC | T-0873 | 2022-04-27 | 1401/02/07 | T-0873 | 2022-04-27 | 1401/02/07 | BK-SUR-ENG-ELE-01-04184 | 2022-05-09 | 1401/02/19 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0873 | 2022-04-27 | 1401/02/07 | T-0873 | 2022-04-27 | 1401/02/07 | BK-SUR-ENG-ELE-01-04184 | 2022-05-09 | 1401/02/19 | CM-C3
3 | 2 | 3 | 7 | 1 | 0 | 3 | 3.2.3.7.1 | Calculation Note For Cable Sizing | BK-GCS-PEDCO-120-EL-CN-0003 | BK-GCS-PEDCO-120-EL-CN-0003 | BK | GCS | PEDCO | 120 | EL | CN | 0003 | F0Z-709009 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 1 | 0 | 4 | 3.2.3.7.1 | Calculation Note For UPS System | BK-GCS-PEDCO-120-EL-CN-0004 | BK-GCS-PEDCO-120-EL-CN-0004 | BK | GCS | PEDCO | 120 | EL | CN | 0004 | F0Z-709010 | AFD | IFC | 2021-12-06 | 2021-12-17 | 2021-12-18 | 11 | 1 | 12 | IFA | 2022-01-09 | 2022-01-22 | 2022-01-25 | 13 | 3 | 16 | IFA | 2022-05-09 | 0 | 0 | -44690 | 0 | -44690 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-22 | 0 |  | D02 | IFA | T-0861 | 2022-04-25 | 1401/02/06 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04178 | 2022-05-09 | 1401/02/19 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0004_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0266 | 2021-11-22 | 1400/09/01 |  |  |  | BK-SUR-ENG-ELE-00-02183 | 2021-12-04 | 1400/09/13 | CM-C2 | [6 empty] | 1400-2294-320825 | 2021-12-17 | 1400/09/26 | 2021-12-18 | 1400/09/27 | CM | [10 empty] | D01 | IFA | T-0379 | 2021-12-26 | 1400/10/05 |  |  |  | BK-SUR-ENG-ELE-00-02560 | 2022-01-04 | 1400/10/14 | CM-C3 | PEDCO-CRS- BK-GCS-PEDCO-120-EL-CN-0004_D00 | [5 empty] | 1400-2294-375310 | 2022-01-22 | 1400/11/02 | 2022-01-25 | 1400/11/05 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0004_D00 | [9 empty] | D02 | IFA | T-0861 | 2022-04-25 | 1401/02/06 |  |  |  | BK-SUR-ENG-ELE-01-04178 | 2022-05-09 | 1401/02/19 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0004_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0004_D01
3 | 2 | 3 | 7 | 1 | 0 | 5 | 3.2.3.7.1 | Calculation Note For DC Charger System | BK-GCS-PEDCO-120-EL-CN-0005 | BK-GCS-PEDCO-120-EL-CN-0005 | BK | GCS | PEDCO | 120 | EL | CN | 0005 | F0Z-709011 | AFD | IFC | 2021-12-29 | 2022-01-06 | 2022-01-08 | 8 | 2 | 10 | IFA | 2022-02-02 | 2022-02-16 | 2022-02-21 | 14 | 5 | 19 | IFA | 2022-06-12 | 0 | 0 | -44724 | 0 | -44724 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-15 | 0 |  | D02 | IFA | T-1018 | 2022-05-29 | 1401/03/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0005_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0346 | 2021-12-15 | 1400/09/24 |  |  |  | BK-SUR-ENG-ELE-00-02432 | 2021-12-26 | 1400/10/05 | CM-C3 | [6 empty] | 1400-2294-352428 | 2022-01-06 | 1400/10/16 | 2022-01-08 | 1400/10/18 | CM | [10 empty] | D01 | IFA | T-0481 | 2022-01-19 | 1400/10/29 |  |  |  | BK-SUR-ENG-ELE-00-02888 | 2022-01-31 | 1400/11/11 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0005_D00 | [5 empty] | 1400-2294-412403 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/11/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0005-D00 | [9 empty] | D02 | IFA | T-1018 | 2022-05-29 | 1401/03/08 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0005_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0005_D01
3 | 2 | 3 | 7 | 1 | 0 | 6 | 3.2.3.7.1 | Calculation Note For Earthing & Lightning System | BK-GCS-PEDCO-120-EL-CN-0006 | BK-GCS-PEDCO-120-EL-CN-0006 | BK | GCS | PEDCO | 120 | EL | CN | 0006 | F0Z-709012 | AFD | IFC | 2022-05-14 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-30 | 0 |  | D00 | IFC | T-0879 | 2022-04-30 | 1401/02/10 | T-0879 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-ELE-01-04215 | 2022-05-10 | 1401/02/20 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0879 | 2022-04-30 | 1401/02/10 | T-0879 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-ELE-01-04215 | 2022-05-10 | 1401/02/20 | CM-C3
3 | 2 | 3 | 7 | 1 | 0 | 7 | 3.2.3.7.1 | Calculation Note For Diesel Generator Sizing | BK-GCS-PEDCO-120-EL-CN-0007 | BK-GCS-PEDCO-120-EL-CN-0007 | BK | GCS | PEDCO | 120 | EL | CN | 0007 | F0Z-709013 | AFD | IFC | 2021-11-30 | 2022-02-07 | 2022-02-13 | 69 | 6 | 75 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-16 | 0 |  | D00 | IFC | T-0255 | 2021-11-16 | 1400/08/25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2290-312153 | 2021-12-11 | 1400/09/20 | 2021-12-12 | 1400/09/21 | CM | 0 | 1400-2294-400926 | 2022-02-07 | 1400/11/18 | 2022-02-13 | 1400/11/24 | AP | 0 | 0 |  | D00 | IFC | T-0255 | 2021-11-16 | 1400/08/25 | [13 empty] | 1400-2290-312153 | 2021-12-11 | 1400/09/20 | 2021-12-12 | 1400/09/21 | CM |  | 1400-2294-400926 | 2022-02-07 | 1400/11/18 | 2022-02-13 | 1400/11/24 | AP
3 | 2 | 3 | 7 | 1 | 0 | 8 | 3.2.3.7.1 | Calculation Note For Cathodic Protection System | BK-GCS-PEDCO-120-EL-CN-0008 | BK-GCS-PEDCO-120-EL-CN-0008 | BK | GCS | PEDCO | 120 | EL | CN | 0008 | F0Z-709014 | AFD | IFC | 2022-05-15 | 0 | 0 | -44696 | 0 | -44696 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-01 | 0 |  | D00 | IFC | T-0891 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04253 | 2022-05-14 | 1401/02/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0891 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ELE-01-04253 | 2022-05-14 | 1401/02/24 | CM-C3
3 | 2 | 3 | 7 | 1 | 0 | 9 | 3.2.3.7.1 | Calculation Note For NGR Sizing | BK-GCS-PEDCO-120-EL-CN-0009 | BK-GCS-PEDCO-120-EL-CN-0009 | BK | GCS | PEDCO | 120 | EL | CN | 0009 | F0Z-709015 | AFD | IFC | 2022-04-25 | 2022-04-19 | 2022-04-25 | -6 | 6 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-11 | 0 |  | D00 | IFC | T-0804 | 2022-04-11 | 1401/01/22 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04013 | 2022-04-24 | 1401/01/04 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31345 | 2022-04-19 | 1401/01/30 | 2022-04-25 | 1401/02/05 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0804 | 2022-04-11 | 1401/01/22 |  |  |  | BK-SUR-ENG-ELE-01-04013 | 2022-04-24 | 1401/01/04 | AP | [6 empty] | 1401-2294-31345 | 2022-04-19 | 1401/01/30 | 2022-04-25 | 1401/02/05 | AP
3 | 2 | 3 | 7 | 1 | 0 | 10 | 3.2.3.7.1 | Calculation Note for UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-CN-0010 | BK-GCS-PEDCO-120-EL-CN-0010 | BK | GCS | PEDCO | 120 | EL | CN | 0010 | F0Z-709016 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 1 | 0 | 11 | 3.2.3.7.1 | Calculation Note for Capacitor Banks | BK-GCS-PEDCO-120-EL-CN-0011 | BK-GCS-PEDCO-120-EL-CN-0011 | BK | GCS | PEDCO | 120 | EL | CN | 0011 | F0Z-709017 | AFD | IFC | 2021-12-06 | 2021-12-17 | 2021-12-18 | 11 | 1 | 12 | IFA | 2022-02-27 | 2022-02-28 | 2022-03-05 | 1 | 5 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-22 | 0 |  | D01 | IFA | T-0590 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03236 | 2022-02-27 | 1400/12/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0011_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430282 | 2022-02-28 | 1400/12/09 | 2022-03-05 | 1400/12/15 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0011_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0266 | 2021-11-22 | 1400/09/01 |  |  |  | BK-SUR-ENG-ELE-00-02183 | 2021-12-04 | 1400/09/13 | CM-C3 | [6 empty] | 1400-2294-320825 | 2021-12-17 | 1400/09/26 | 2021-12-18 | 1400/09/27 | CM | [10 empty] | D01 | IFA | T-0590 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-ELE-00-03236 | 2022-02-27 | 1400/12/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-CN-0011_D00 | [5 empty] | 1400-2294-430282 | 2022-02-28 | 1400/12/09 | 2022-03-05 | 1400/12/15 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0011_D00
3 | 2 | 3 | 7 | 2 | 0 | 0 | 3.2.3.7.2 | Data Sheets
3 | 2 | 3 | 7 | 2 | 0 | 1 | 3.2.3.7.2 | Data Sheets For UPS | BK-GCS-PEDCO-120-EL-DT-0001 | BK-GCS-PEDCO-120-EL-DT-0001 | BK | GCS | PEDCO | 120 | EL | DT | 0001 | F0Z-709018 | AFC | IFC | 2022-01-09 | 2022-01-22 | 2022-01-25 | 13 | 3 | 16 | IFA | 2022-05-09 | 0 | 0 | -44690 | 0 | -44690 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-26 | 0 |  | D01 | IFA | T-0861 | 2022-04-25 | 1401/02/06 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04178 | 2022-05-09 | 1401/02/19 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0379 | 2021-12-26 | 1400/10/05 |  |  |  | BK-SUR-ENG-ELE-00-02560 | 2022-01-04 | 1400/10/14 | CM-C3 | [6 empty] | 1400-2294-375310 | 2022-01-22 | 1400/11/02 | 2022-01-25 | 1400/11/05 | CM | [10 empty] | D01 | IFA | T-0861 | 2022-04-25 | 1401/02/06 |  |  |  | BK-SUR-ENG-ELE-01-04178 | 2022-05-09 | 1401/02/19 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0001_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0001_D00
3 | 2 | 3 | 7 | 2 | 0 | 2 | 3.2.3.7.2 | Data Sheets For DC Charger | BK-GCS-PEDCO-120-EL-DT-0002 | BK-GCS-PEDCO-120-EL-DT-0002 | BK | GCS | PEDCO | 120 | EL | DT | 0002 | F0Z-709019 | AFC | IFC | 2022-01-02 | 2021-01-06 | 2022-01-08 | -361 | 367 | 6 | IFA | 2022-02-02 | 2022-02-16 | 2022-02-21 | 14 | 5 | 19 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-19 | 0 |  | D01 | IFA | T-0481 | 2022-01-19 | 1400/10/29 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-02888 | 2022-01-31 | 1400/11/11 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-412403 | 2022-02-16 | 1400/12/02 | 2022-02-21 | 1400/11/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0366 | 2021-12-19 | 1400/09/28 |  |  |  | BK-SUR-ENG-ELE-00-02474 | 2021-12-28 | 1400/10/07 | CM-C3 | [6 empty] | 1400-2294-352432 | 2021-01-06 | 1400/10/16 | 2022-01-08 | 1400/10/18 | CM | [10 empty] | D01 | IFA | T-0481 | 2022-01-19 | 1400/10/29 |  |  |  | BK-SUR-ENG-ELE-00-02888 | 2022-01-31 | 1400/11/11 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0002_D00 | [5 empty] | 1400-2294-412403 | 2022-02-16 | 1400/12/02 | 2022-02-21 | 1400/11/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0002_D00
3 | 2 | 3 | 7 | 2 | 0 | 3 | 3.2.3.7.2 | Data Sheets For Diesel Generator | BK-GCS-PEDCO-120-EL-DT-0003 | BK-GCS-PEDCO-120-EL-DT-0003 | BK | GCS | PEDCO | 120 | EL | DT | 0003 | F0Z-709020 | AFC | IFC | 2022-06-14 | 0 | 0 | -44726 | 0 | -44726 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-31 | 0 |  | D00 | IFC | T-1026 | 2022-05-31 | 1401/03/10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1026 | 2022-05-31 | 1401/03/10
3 | 2 | 3 | 7 | 2 | 0 | 4 | 3.2.3.7.2 | Data Sheets For Expansion of MV Switchgear | BK-GCS-PEDCO-120-EL-DT-0004 | BK-GCS-PEDCO-120-EL-DT-0004 | BK | GCS | PEDCO | 120 | EL | DT | 0004 | F0Z-709021 | AFC | IFC | 2022-02-05 | 2022-02-06 | 2022-03-21 | 1 | 43 | 44 | IFA | 2022-03-23 | 2022-04-09 | 2022-04-13 | 17 | 4 | 21 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-22 | 0 |  | D01 | IFA | T-0705 | 2022-03-09 | 1400/12/18 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03635 | 2022-03-16 | 1400/12/25 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0004_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-443266 | 2022-03-10 | 1400/12/19 | 2022-03-16 | 1400/12/25 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0004_D00 | 1401-2294-16105 | 2022-04-09 | 1401/01/20 | 2022-04-13 | 1401/01/24 | CM | 0 | 0 |  | D00 | IFC | T-0488 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-ELE-00-02906 | 2022-02-01 | 1400/11/12 | CM-C2 | [6 empty] | 1400-2294-399223 | 2022-02-06 | 1400/11/17 | 2022-03-21 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0705 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-ELE-00-03635 | 2022-03-16 | 1400/12/25 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0004_D00 | [5 empty] | 1400-2294-443266 | 2022-03-10 | 1400/12/19 | 2022-03-16 | 1400/12/25 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0004_D00 | 1401-2294-16105 | 2022-04-09 | 1401/01/20 | 2022-04-13 | 1401/01/24 | CM
3 | 2 | 3 | 7 | 2 | 0 | 5 | 3.2.3.7.2 | Data Sheets For LV Switchgear | BK-GCS-PEDCO-120-EL-DT-0005 | BK-GCS-PEDCO-120-EL-DT-0005 | BK | GCS | PEDCO | 120 | EL | DT | 0005 | F0Z-709022 | AFC | IFC | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | IFA | 2022-06-07 | 0 | 0 | -44719 | 0 | -44719 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 0 |  | D01 | IFA | T-0998 | 2022-05-24 | 1401/03/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0601 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-ELE-00-03320 | 2022-03-05 | 1400/12/14 | CM-C2 | [6 empty] | 1400-2294-443157 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0998 | 2022-05-24 | 1401/03/03 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0005_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0005_D00
3 | 2 | 3 | 7 | 2 | 0 | 6 | 3.2.3.7.2 | Data Sheets For Local Control Stations (LCS) | BK-GCS-PEDCO-120-EL-DT-0006 | BK-GCS-PEDCO-120-EL-DT-0006 | BK | GCS | PEDCO | 120 | EL | DT | 0006 | F0Z-709023 | AFC | IFC | 2022-02-20 | 2022-02-24 | 2022-02-28 | 4 | 4 | 8 | IFA | 2022-06-04 | 0 | 0 | -44716 | 0 | -44716 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-06 | 0 |  | D01 | IFA | T-0975 | 2022-05-21 | 1401/02/31 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04489 | 2022-05-29 | 1401/03/09 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0554 | 2022-02-06 | 1400/11/17 |  |  |  | BK-SUR-ENG-ELE-00-03087 | 2022-02-19 | 1400/11/30 | CM-C3 | [6 empty] | 1400-2294-424218 | 2022-02-24 | 1400/12/05 | 2022-02-28 | 1400/12/09 | CM | [10 empty] | D01 | IFA | T-0975 | 2022-05-21 | 1401/02/31 |  |  |  | BK-SUR-ENG-ELE-01-04489 | 2022-05-29 | 1401/03/09 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0006_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0006_D00
3 | 2 | 3 | 7 | 2 | 0 | 7 | 3.2.3.7.2 | Data Sheets For Capacitor Bank | BK-GCS-PEDCO-120-EL-DT-0007 | BK-GCS-PEDCO-120-EL-DT-0007 | BK | GCS | PEDCO | 120 | EL | DT | 0007 | F0Z-709024 | AFC | IFC | 2022-03-13 | 0 | 0 | -44633 | 0 | -44633 | 0 | 14 | 2022-03-13 | 2022-03-26 | 2022-02-27 | 13 | 2022-03-12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-27 | 0 |  | D00 | IFC | T-0652 | 2022-02-27 | 1400/12/08 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03418 | 2022-03-08 | 1400/12/17 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0652 | 2022-02-27 | 1400/12/08 |  |  |  | BK-SUR-ENG-ELE-00-03418 | 2022-03-08 | 1400/12/17 | CM-C3 | [40 empty] | 1400-2294-447230 | 2022-03-13 | 1400/12/22 | 2022-03-26 | 1401/01/06 | CM
3 | 2 | 3 | 7 | 2 | 0 | 8 | 3.2.3.7.2 | Data Sheets For LV Induction Motors | BK-GCS-PEDCO-120-EL-DT-0008 | BK-GCS-PEDCO-120-EL-DT-0008 | BK | GCS | PEDCO | 120 | EL | DT | 0008 | F0Z-709025 | AFC | IFC | 2021-09-26 | 2021-09-28 | 2021-10-02 | 2 | 4 | 6 | IFA | 2022-02-21 | 2022-03-10 | 2022-03-12 | 17 | 2 | 19 | IFA | 2022-06-11 | 0 | 0 | -44723 | 0 | -44723 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-12 | 0 |  | D02 | IFA | T-1011 | 2022-05-28 | 140/03/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0008_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0008_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0087 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-ELE-00-01560 | 2021-09-25 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-213958 | 2021-09-28 | 1400/07/05 | 2021-10-02 | 1400/07/10 | CM | [10 empty] | D01 | IFA | T-0558 | 2022-02-07 | 1400/11/18 |  |  |  | BK-SUR-ENG-ELE-00-03090 | 2022-02-19 | 1400/11/30 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0008_D00 | [5 empty] | 1400-2294-443253 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0008_D00 | [9 empty] | D02 | IFA | T-1011 | 2022-05-28 | 140/03/07 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0008_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0008_D01
3 | 2 | 3 | 7 | 2 | 0 | 9 | 3.2.3.7.2 | Data Sheets For MV Induction Motors | BK-GCS-PEDCO-120-EL-DT-0009 | BK-GCS-PEDCO-120-EL-DT-0009 | BK | GCS | PEDCO | 120 | EL | DT | 0009 | F0Z-709026 | AFC | IFC | 2021-09-26 | 2021-09-28 | 2021-10-02 | 2 | 4 | 6 | IFA | 2022-02-22 | 2022-02-24 | 2022-02-28 | 2 | 4 | 6 | IFA | 2022-06-11 | 0 | 0 | -44723 | 0 | -44723 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-09-12 | 0 |  | D02 | IFA | T-1011 | 2022-05-28 | 140/03/07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0009_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0009_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0087 | 2021-09-12 | 1400/06/21 |  |  |  | BK-SUR-ENG-ELE-00-01560 | 2021-09-25 | 1400/07/03 | CM-C3 | [6 empty] | 1400-2294-213958 | 2021-09-28 | 1400/07/05 | 2021-10-02 | 1400/07/10 | CM | [10 empty] | D01 | IFA | T-0563 | 2022-02-08 | 1400/11/19 |  |  |  | BK-SUR-ENG-ELE-00-03126 | 2022-02-20 | 1400/12/01 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0009_D00 | [5 empty] | 1400-2294-424217 | 2022-02-24 | 1400/12/05 | 2022-02-28 | 1400/12/09 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0009_D00 | [9 empty] | D02 | IFA | T-1011 | 2022-05-28 | 140/03/07 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0009_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0009_D01
3 | 2 | 3 | 7 | 2 | 0 | 10 | 3.2.3.7.2 | Data Sheets For Power & Control Cables | BK-GCS-PEDCO-120-EL-DT-0010 | BK-GCS-PEDCO-120-EL-DT-0010 | BK | GCS | PEDCO | 120 | EL | DT | 0010 | F0Z-709027 | AFC | IFC | 2022-03-05 | 2022-03-10 | 2022-03-12 | 5 | 2 | 7 | IFA | 2022-06-04 | 0 | 0 | -44716 | 0 | -44716 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-19 | 0 |  | D01 | IFA | T-0975 | 2022-05-21 | 1401/02/31 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04489 | 2022-05-29 | 1401/03/09 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0010_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0010_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0601 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-ELE-00-03320 | 2022-03-05 | 1400/12/14 | CM-C2 | [6 empty] | 1400-2294-443157 | 2022-03-10 | 1400/12/19 | 2022-03-12 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0975 | 2022-05-21 | 1401/02/31 |  |  |  | BK-SUR-ENG-ELE-01-04489 | 2022-05-29 | 1401/03/09 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0010_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0010_D00
3 | 2 | 3 | 7 | 2 | 0 | 11 | 3.2.3.7.2 | Data Sheets For Power Transformers | BK-GCS-PEDCO-120-EL-DT-0011 | BK-GCS-PEDCO-120-EL-DT-0011 | BK | GCS | PEDCO | 120 | EL | DT | 0011 | F0Z-709028 | AFC | IFC | 2022-02-16 | 2022-03-09 | 2022-03-12 | 21 | 3 | 24 | IFA | 2022-06-04 | 0 | 0 | -44716 | 0 | -44716 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 0 |  | D01 | IFA | T-0975 | 2022-05-21 | 1401/02/31 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04489 | 2022-05-29 | 1401/03/09 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0011_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0011_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0541 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-ELE-00-03060 | 2022-02-14 | 1400/11/25 | [7 empty] | 1400-2294-442066 | 2022-03-09 | 1400/12/18 | 2022-03-12 | 1400/12/21 | CM | [10 empty] | D01 | IFA | T-0975 | 2022-05-21 | 1401/02/31 |  |  |  | BK-SUR-ENG-ELE-01-04489 | 2022-05-29 | 1401/03/09 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DT-0011_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-DT-0011_D00
3 | 2 | 3 | 7 | 2 | 0 | 12 | 3.2.3.7.2 | Data Sheets For Cathodic Protection System | BK-GCS-PEDCO-120-EL-DT-0012 | BK-GCS-PEDCO-120-EL-DT-0012 | BK | GCS | PEDCO | 120 | EL | DT | 0012 | F0Z-709029 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 2 | 0 | 13 | 3.2.3.7.2 | Data Sheets For NGR | BK-GCS-PEDCO-120-EL-DT-0013 | BK-GCS-PEDCO-120-EL-DT-0013 | BK | GCS | PEDCO | 120 | EL | DT | 0013 | F0Z-709030 | AFC | IFC | 2022-04-25 | 2022-04-19 | 2022-04-25 | -6 | 6 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-11 | 0 |  | D00 | IFC | T-0804 | 2022-04-11 | 1401/01/22 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04013 | 2022-04-24 | 1401/01/04 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31345 | 2022-04-19 | 1401/01/30 | 2022-04-25 | 1401/02/05 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0804 | 2022-04-11 | 1401/01/22 |  |  |  | BK-SUR-ENG-ELE-01-04013 | 2022-04-24 | 1401/01/04 | CM-C2 | [6 empty] | 1401-2294-31345 | 2022-04-19 | 1401/01/30 | 2022-04-25 | 1401/02/05 | AP
3 | 2 | 3 | 7 | 2 | 0 | 14 | 3.2.3.7.2 | Data Sheets For Remote Control Panel | BK-GCS-PEDCO-120-EL-DT-0015 | BK-GCS-PEDCO-120-EL-DT-0015 | BK | GCS | PEDCO | 120 | EL | DT | 0015 | F0Z-709031 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 2 | 0 | 15 | 3.2.3.7.2 | Data Sheets For Distribution & Lighting Panels | BK-GCS-PEDCO-120-EL-DT-0016 | BK-GCS-PEDCO-120-EL-DT-0016 | BK | GCS | PEDCO | 120 | EL | DT | 0016 | F0Z-709032 | AFC | IFC | 2022-05-31 | 0 | 0 | -44712 | 0 | -44712 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-17 | 0 |  | D00 | IFC | T-0965 | 2022-05-17 | 1401/02/26 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04477 | 2022-05-29 | 1401/03/08 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0965 | 2022-05-17 | 1401/02/26 |  |  |  | BK-SUR-ENG-ELE-01-04477 | 2022-05-29 | 1401/03/08 | CM-C2
3 | 2 | 3 | 7 | 2 | 0 | 16 | 3.2.3.7.2 | Data Sheet for UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-DT-0017 | BK-GCS-PEDCO-120-EL-DT-0017 | BK | GCS | PEDCO | 120 | EL | DT | 0017 | F0Z-709033 | AFC | IFC | 2022-03-16 | 2022-04-09 | 2022-04-13 | 24 | 4 | 28 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-02 | 0 |  | D00 | IFC | T-0662 | 2022-03-02 | 1400/12/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03469 | 2022-03-12 | 1400/12/21 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-16106 | 2022-04-09 | 1401/01/20 | 2022-04-13 | 1401/01/24 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0662 | 2022-03-02 | 1400/12/11 |  |  |  | BK-SUR-ENG-ELE-00-03469 | 2022-03-12 | 1400/12/21 | CM-C2 | [6 empty] | 1401-2294-16106 | 2022-04-09 | 1401/01/20 | 2022-04-13 | 1401/01/24 | AP
3 | 2 | 3 | 7 | 3 | 0 | 0 | 3.2.3.7.3 | Drawing/Diagram
3 | 2 | 3 | 7 | 3 | 0 | 1 | 3.2.3.7.3 | Electrical Overall Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0001 | BK-GCS-PEDCO-120-EL-SL-0001 | BK | GCS | PEDCO | 120 | EL | SL | 0001 | F2P-709034 | AFC | IFC | 2022-02-07 | 2022-02-12 | 2022-02-21 | 5 | 9 | 14 | IFA | 2022-04-30 | 2022-05-09 | 2022-05-18 | 9 | 9 | 18 | IFA | 2022-05-31 | 0 | 0 | -44712 | 0 | -44712 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-24 | 0 |  | D02 | IFA | T-0966 | 2022-05-17 | 1401/02/27 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04478 | 2022-05-29 | 1401/03/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISCO-CRS-BK-GCS-PEDCO-120-EL-SL-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0498 | 2022-01-24 | 1400/11/04 |  |  |  | BK-SUR-ENG-ELE-00-02907 | 2022-02-01 | 1400/11/13 | CM-C2 | [6 empty] | 1400-2294-406648 | 2022-02-12 | 1400/11/23 | 2022-02-21 | 1400/12/02 | CM | [10 empty] | D01 | IFA | T-0817 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-ELE-01-04067 | 2022-04-26 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0001_D00 | [5 empty] | 1401-2294-43191 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0001_D00 | 1401-2294-54910 | 2022-05-09 | 1401/02/19 | 2022-05-18 | 1401/02/28 | CM |  |  |  | D02 | IFA | T-0966 | 2022-05-17 | 1401/02/27 |  |  |  | BK-SUR-ENG-ELE-01-04478 | 2022-05-29 | 1401/03/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0001_D01 | [11 empty] | NISCO-CRS-BK-GCS-PEDCO-120-EL-SL-0001_D01
3 | 2 | 3 | 7 | 3 | 0 | 2 | 3.2.3.7.3 | LV Switchgear/MCC Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0002 | BK-GCS-PEDCO-120-EL-SL-0002 | BK | GCS | PEDCO | 120 | EL | SL | 0002 | F2P-709035 | AFC | IFC | 2022-01-10 | 2022-02-17 | 2022-02-20 | 38 | 3 | 41 | IFA | 2022-04-23 | 2022-04-19 | 2022-04-25 | -4 | 6 | 2 | IFA | 2022-05-30 | 0 | 0 | -44711 | 0 | -44711 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-27 | 0 |  | D02 | IFA | T-0957 | 2022-05-16 | 1401/02/26 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04466 | 2022-05-29 | 1401/03/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0002 _D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0002 _D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0385 | 2021-12-27 | 1400/10/06 |  |  |  | BK-SUR-ENG-ELE-00-02611 | 2022-01-09 | 1400/10/19 | CM-C3 | [6 empty] | 1400-2294-368606 | 2021-01-17 | 1400/10/27 | 2022-01-21 | 1400/11/01 | CM |  | 1400-2294-413210 | 2022-02-17 | 1400/11/28 | 2022-02-20 | 1400/12/02 | CM |  |  |  | D01 | IFA | T-0788 | 2022-04-09 | 1401/01/20 |  |  |  | BK-SUR-ENG-ELE-01-03999 | 2022-04-20 | 1400/01/31 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0002 _D00 | [5 empty] | 1401-2294-31358 | 2022-04-19 | 1401/01/30 | 2022-04-25 | 1401/02/05 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0002 _D00 | [9 empty] | D02 | IFA | T-0957 | 2022-05-16 | 1401/02/26 |  |  |  | BK-SUR-ENG-ELE-01-04466 | 2022-05-29 | 1401/03/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0002 _D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0002 _D01
3 | 2 | 3 | 7 | 3 | 0 | 3 | 3.2.3.7.3 | Existent MV Switchgear Expansion Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0003 | BK-GCS-PEDCO-120-EL-SL-0003 | BK | GCS | PEDCO | 120 | EL | SL | 0003 | F2P-709036 | AFC | IFC | 2022-01-26 | 2022-02-17 | 2022-02-20 | 22 | 3 | 25 | IFA | 2022-03-23 | 2022-04-09 | 2022-04-13 | 17 | 4 | 21 | IFA | 2022-05-14 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-12 | 0 |  | D02 | IFA | T-0880 | 2022-04-30 | 1401/02/10 | T-0880 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-ELE-01-04218 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0452 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-ELE-00-02785 | 2022-01-23 | 1400/11/03 | CM-C2 | [6 empty] | 1400-2294-413209 | 2022-02-17 | 1400/11/28 | 2022-02-20 | 1400/12/01 | CM | [10 empty] | D01 | IFA | T-0705 | 2022-03-09 | 1400/12/18 |  |  |  | BK-SUR-ENG-ELE-00-03635 | 2022-03-16 | 1400/12/25 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0003_D00 | [5 empty] | 1400-2294-443266 | 2022-03-10 | 1400/12/19 | 2022-03-16 | 1400/12/25 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0003_D00 | 1401-2294-16105 | 2022-04-09 | 1401/01/20 | 2022-04-13 | 1401/01/24 | CM |  |  |  | D02 | IFA | T-0880 | 2022-04-30 | 1401/02/10 | T-0880 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-ELE-01-04218 | 2022-05-10 | 1401/02/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0003_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0003_D01
3 | 2 | 3 | 7 | 3 | 0 | 4 | 3.2.3.7.3 | Distribution and Lighting Panels Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0004 | BK-GCS-PEDCO-120-EL-SL-0004 | BK | GCS | PEDCO | 120 | EL | SL | 0004 | F2P-709037 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 5 | 3.2.3.7.3 | UPS Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0005 | BK-GCS-PEDCO-120-EL-SL-0005 | BK | GCS | PEDCO | 120 | EL | SL | 0005 | F2P-709038 | AFC | IFC | 2022-01-09 | 2022-01-22 | 2022-01-25 | 13 | 3 | 16 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-26 | 0 |  | D00 | IFC | T-0379 | 2021-12-26 | 1400/10/05 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-02560 | 2022-01-04 | 1400/10/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-375310 | 2022-01-22 | 1400/11/02 | 2022-01-25 | 1400/11/05 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0379 | 2021-12-26 | 1400/10/05 |  |  |  | BK-SUR-ENG-ELE-00-02560 | 2022-01-04 | 1400/10/14 | CM-C3 | [6 empty] | 1400-2294-375310 | 2022-01-22 | 1400/11/02 | 2022-01-25 | 1400/11/05 | CM
3 | 2 | 3 | 7 | 3 | 0 | 6 | 3.2.3.7.3 | DC Charger Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0006 | BK-GCS-PEDCO-120-EL-SL-0006 | BK | GCS | PEDCO | 120 | EL | SL | 0006 | F2P-709039 | AFC | IFC | 2022-01-01 | 2022-01-06 | 2022-01-08 | 5 | 2 | 7 | IFA | 2022-02-02 | 2022-02-16 | 2022-02-21 | 14 | 5 | 19 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-18 | 0 |  | D01 | IFA | T-0481 | 2022-01-19 | 1400/10/29 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-02888 | 2022-01-31 | 1400/11/11 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0006_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-412403 | 2022-02-16 | 1400/12/02 | 2022-02-21 | 1400/11/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0357 | 2021-12-18 | 1400/09/27 |  |  |  | BK-SUR-ENG-ELE-00-02471 | 2021-12-28 | 1400/10/07 | CM-C3 | [6 empty] | 1400-2294-352430 | 2022-01-06 | 1400/10/16 | 2022-01-08 | 1400/10/18 | CM | [10 empty] | D01 | IFA | T-0481 | 2022-01-19 | 1400/10/29 |  |  |  | BK-SUR-ENG-ELE-00-02888 | 2022-01-31 | 1400/11/11 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-SL-0006_D00 | [5 empty] | 1400-2294-412403 | 2022-02-16 | 1400/12/02 | 2022-02-21 | 1400/11/27 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-SL-0006_D00
3 | 2 | 3 | 7 | 3 | 0 | 7 | 3.2.3.7.3 | Electrical Typical Schematic Diagrams For MV panel | BK-GCS-PEDCO-120-EL-DG-0001 | BK-GCS-PEDCO-120-EL-DG-0001 | BK | GCS | PEDCO | 120 | EL | DG | 0001 | F2P-709040 | IFI | IFI | 2022-01-26 | 2022-02-17 | 2022-02-20 | 22 | 3 | 25 | IFI | 2022-03-22 | 2022-04-09 | 2022-04-13 | 18 | 4 | 22 | IFI | 2022-05-14 | 0 | 0 | -44695 | 0 | -44695 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-12 | 2022-04-30 |  | D02 | IFI | T-0884 | 2022-04-30 | 1401/02/10 | T-0884 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-ELE-01-04237 | 2022-05-11 | 1401/02/21 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0453 | 2022-01-12 | 1400/10/22 |  |  |  | BK-SUR-ENG-ELE-00-02786 | 2022-01-23 | 1400/11/03 | CM-C2 | [6 empty] | 1400-2294-413208 | 2022-02-17 | 1400/11/28 | 2022-02-20 | 1400/12/01 | CM | [10 empty] | D01 | IFI | T-0697 | 2022-03-08 | 1400/12/17 |  |  |  | BK-SUR-ENG-ELE-00-03606 | 2022-03-15 | 1400/12/24 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DG-0001_D00 | [5 empty] | 1401-2294-16099 | 2022-04-09 | 1401/01/20 | 2022-04-13 | 1401/01/24 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0001_D00 | [9 empty] | D02 | IFI | T-0884 | 2022-04-30 | 1401/02/10 | T-0884 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-ELE-01-04237 | 2022-05-11 | 1401/02/21 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DG-0001_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0001_D01
3 | 2 | 3 | 7 | 3 | 0 | 8 | 3.2.3.7.3 | Electrical Typical Schematic Diagrams For LV panel | BK-GCS-PEDCO-120-EL-DG-0002 | BK-GCS-PEDCO-120-EL-DG-0002 | BK | GCS | PEDCO | 120 | EL | DG | 0002 | F2P-709041 | IFI | IFI | 2021-12-27 | 2022-02-02 | 2022-02-08 | 37 | 6 | 43 | IFI | 2022-04-23 | 2022-05-01 | 2022-05-02 | 8 | 1 | 9 | IFI | 2022-05-29 | 0 | 0 | -44710 | 0 | -44710 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 2022-05-15 |  | D02 | IFI | T-0949 | 2022-05-15 | 1401/02/25 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04447 | 2022-05-28 | 1401/03/07 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0340 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-ELE-00-02412 | 2021-12-26 | 1400/10/05 | C4-RJ | [6 empty] | 1400-2294-393495 | 2022-02-02 | 1400/11/13 | 2022-02-08 | 1400/11/19 | CM | [10 empty] | D01 | IFI | T-0789 | 2022-04-09 | 1401/01/20 |  |  |  | BK-SUR-ENG-ELE-00-02412 | 2022-12-25 | 1401/10/04 | C4-RJ | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D00 | [5 empty] | 1401-2294-47908 | 2022-05-01 | 1401/02/11 | 2022-05-02 | 1401/02/12 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D00 | [9 empty] | D02 | IFI | T-0949 | 2022-05-15 | 1401/02/25 |  |  |  | BK-SUR-ENG-ELE-01-04447 | 2022-05-28 | 1401/03/07 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-DG-0002_D01
3 | 2 | 3 | 7 | 3 | 0 | 9 | 3.2.3.7.3 | Interconnection Wiring Diagram | BK-GCS-PEDCO-120-EL-DG-0003 | BK-GCS-PEDCO-120-EL-DG-0003 | BK | GCS | PEDCO | 120 | EL | DG | 0003 | F2P-709042 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 10 | 3.2.3.7.3 | Wiring Diagram For Remote Control Panel (RCP) | BK-GCS-PEDCO-120-EL-DG-0005 | BK-GCS-PEDCO-120-EL-DG-0005 | BK | GCS | PEDCO | 120 | EL | DG | 0005 | F2P-709043 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 11 | 3.2.3.7.3 | Wiring Diagrams For Cathodic Protection Systems | BK-GCS-PEDCO-120-EL-DG-0006 | BK-GCS-PEDCO-120-EL-DG-0006 | BK | GCS | PEDCO | 120 | EL | DG | 0006 | F2P-709044 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 12 | 3.2.3.7.3 | Control Logic Diagram For LV Incomers and bus tie | BK-GCS-PEDCO-120-EL-LD-0001 | BK-GCS-PEDCO-120-EL-LD-0001 | BK | GCS | PEDCO | 120 | EL | LD | 0001 | F2P-709045 | AFC | IFC | 2022-01-30 | 2022-02-23 | 2022-02-27 | 24 | 4 | 28 | IFA | 2022-04-30 | 2022-05-09 | 2022-05-18 | 9 | 9 | 18 | IFA | 2022-05-31 | 0 | 0 | -44712 | 0 | -44712 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-16 | 0 |  | D02 | IFA | T-0966 | 2022-05-17 | 1401/02/27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LD-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-LD-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0463 | 2022-01-16 | 1400/10/26 |  |  |  | BK-SUR-ENG-ELE-00-02840 | 2022-01-29 | 1400/11/09 | CM-C2 | [6 empty] | 1400-2294-423219 | 2022-02-23 | 1400/12/04 | 2022-02-27 | 1400/12/08 | CM | [10 empty] | D01 | IFA | T-0817 | 2022-04-16 | 1401/01/27 |  |  |  | BK-SUR-ENG-ELE-01-04067 | 2022-04-26 | 1401/02/06 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LD-0001_D00 | [5 empty] | 1401-2294-43191 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-LD-0001_D00 | 1401-2294-54910 | 2022-05-09 | 1401/02/19 | 2022-05-18 | 1401/02/28 | CM |  |  |  | D02 | IFA | T-0966 | 2022-05-17 | 1401/02/27 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LD-0001_D01 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-LD-0001_D01
3 | 2 | 3 | 7 | 3 | 0 | 13 | 3.2.3.7.3 | Overall Earthing Layout | BK-GCS-PEDCO-120-EL-PY-0001 | BK-GCS-PEDCO-120-EL-PY-0001 | BK | GCS | PEDCO | 120 | EL | PY | 0001 | F4P-709046 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 14 | 3.2.3.7.3 | Earthing & Lightning Layout For Building & Shelter | BK-GCS-PEDCO-120-EL-PY-0002 | BK-GCS-PEDCO-120-EL-PY-0002 | BK | GCS | PEDCO | 120 | EL | PY | 0002 | F2P-709047 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 15 | 3.2.3.7.3 | Area Lighting & Small Power Layout | BK-GCS-PEDCO-120-EL-PY-0003 | BK-GCS-PEDCO-120-EL-PY-0003 | BK | GCS | PEDCO | 120 | EL | PY | 0003 | F2P-709048 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 16 | 3.2.3.7.3 | Lighting & Small Power Layout For Building & Shelter | BK-GCS-PEDCO-120-EL-PY-0004 | BK-GCS-PEDCO-120-EL-PY-0004 | BK | GCS | PEDCO | 120 | EL | PY | 0004 | F2P-709049 | AFC | IFC | 2022-05-29 | 0 | 0 | -44710 | 0 | -44710 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-15 | 0 |  | D00 | IFC | T-0950 | 2022-05-15 | 1401/02/25 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04448 | 2022-05-28 | 1401/03/07 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0950 | 2022-05-15 | 1401/02/25 |  |  |  | BK-SUR-ENG-ELE-01-04448 | 2022-05-28 | 1401/03/07 | CM-C3
3 | 2 | 3 | 7 | 3 | 0 | 17 | 3.2.3.7.3 | Area Electrical Cable Route & Section Layout | BK-GCS-PEDCO-120-EL-PY-0005 | BK-GCS-PEDCO-120-EL-PY-0005 | BK | GCS | PEDCO | 120 | EL | PY | 0005 | F2P-709050 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 18 | 3.2.3.7.3 | Electrical Cable Route & Section Layout For Building & Shelter | BK-GCS-PEDCO-120-EL-PY-0006 | BK-GCS-PEDCO-120-EL-PY-0006 | BK | GCS | PEDCO | 120 | EL | PY | 0006 | F2P-709051 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 19 | 3.2.3.7.3 | HVAC Power Cabling Arrangement Layout For Building | BK-GCS-PEDCO-120-EL-PY-0007 | BK-GCS-PEDCO-120-EL-PY-0007 | BK | GCS | PEDCO | 120 | EL | PY | 0007 | F2P-709052 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 20 | 3.2.3.7.3 | Electrical Equipment Arrangement Layout For Building | BK-GCS-PEDCO-120-EL-PY-0008 | BK-GCS-PEDCO-120-EL-PY-0008 | BK | GCS | PEDCO | 120 | EL | PY | 0008 | F2P-709053 | AFC | IFC | 2022-05-23 | 2022-05-28 | 2022-05-29 | 5 | 1 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-09 | 0 |  | D00 | IFC | T-0915 | 2022-05-09 | 1401/02/19 | T-0915 | 2022-05-09 | 1401/02/19 | BK-SUR-ENG-ELE-01-04330 | 2022-05-21 | 1401/02/31 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-78935 | 2022-05-28 | 1401/03/08 | 2022-05-29 | 1401/03/09 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0915 | 2022-05-09 | 1401/02/19 | T-0915 | 2022-05-09 | 1401/02/19 | BK-SUR-ENG-ELE-01-04330 | 2022-05-21 | 1401/02/31 | CM-C3 | [6 empty] | 1401-2294-78935 | 2022-05-28 | 1401/03/08 | 2022-05-29 | 1401/03/09 | CM
3 | 2 | 3 | 7 | 3 | 0 | 21 | 3.2.3.7.3 | Cathodic Protection System Layout | BK-GCS-PEDCO-120-EL-PY-0009 | BK-GCS-PEDCO-120-EL-PY-0009 | BK | GCS | PEDCO | 120 | EL | PY | 0009 | F2P-709054 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 22 | 3.2.3.7.3 | Capacitor Banks Single Line Diagram | BK-GCS-PEDCO-120-EL-SL-0007 | BK-GCS-PEDCO-120-EL-SL-0007 | BK | GCS | PEDCO | 120 | EL | SL | 0007 | F2P-709055 | AFC | IFC | 2022-03-16 | 2022-04-09 | 2022-04-13 | 24 | 4 | 28 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-02 | 0 |  | D00 | IFC | T-0662 | 2022-03-02 | 1400/12/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-00-03469 | 2022-03-12 | 1400/12/21 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-16106 | 2022-04-09 | 1401/01/20 | 2022-04-13 | 1401/01/24 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0662 | 2022-03-02 | 1400/12/11 |  |  |  | BK-SUR-ENG-ELE-00-03469 | 2022-03-12 | 1400/12/21 | CM-C2 | [6 empty] | 1401-2294-16106 | 2022-04-09 | 1401/01/20 | 2022-04-13 | 1401/01/24 | CM
3 | 2 | 3 | 7 | 3 | 0 | 23 | 3.2.3.7.3 | Power & Control Cables Termination Diagrams | BK-GCS-PEDCO-120-EL-DG-0007 | BK-GCS-PEDCO-120-EL-DG-0007 | BK | GCS | PEDCO | 120 | EL | DG | 0007 | F2P-709056 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 24 | 3.2.3.7.3 | Single Line Diagram for UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-SL-0009 | BK-GCS-PEDCO-120-EL-SL-0009 | BK | GCS | PEDCO | 120 | EL | SL | 0009 | F2P-709057 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 25 | 3.2.3.7.3 | SLD for Supplying UPS of CCTV Panel in Desalting Unit | BK-GCS-PEDCO-120-EL-SL-0008 | BK-GCS-PEDCO-120-EL-SL-0008 | BK | GCS | PEDCO | 120 | EL | SL | 0008 | F2P-709058 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 26 | 3.2.3.7.3 | SLD for Supplying UPS of CCTV Panel in Production Unit | BK-GCS-PEDCO-120-EL-SL-0010 | BK-GCS-PEDCO-120-EL-SL-0010 | BK | GCS | PEDCO | 120 | EL | SL | 0010 | F2P-709059 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 27 | 3.2.3.7.3 | Equipment Arrangement Layout for UPS of CCTV in Desalting Unit | BK-GCS-PEDCO-120-EL-PY-0010 | BK-GCS-PEDCO-120-EL-PY-0010 | BK | GCS | PEDCO | 120 | EL | PY | 0010 | F2P-709060 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 28 | 3.2.3.7.3 | Equipment Arrangement Layout for UPS of CCTV in Production Unit | BK-GCS-PEDCO-120-EL-PY-0011 | BK-GCS-PEDCO-120-EL-PY-0011 | BK | GCS | PEDCO | 120 | EL | PY | 0011 | F2P-709061 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 29 | 3.2.3.7.3 | Cable Route Layout for Desalting Unit | BK-GCS-PEDCO-120-EL-PY-0012 | BK-GCS-PEDCO-120-EL-PY-0012 | BK | GCS | PEDCO | 120 | EL | PY | 0012 | F4P-709062 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 30 | 3.2.3.7.3 | Cable Route layout for Production Unit | BK-GCS-PEDCO-120-EL-PY-0013 | BK-GCS-PEDCO-120-EL-PY-0013 | BK | GCS | PEDCO | 120 | EL | PY | 0013 | F4P-709063 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 31 | 3.2.3.7.3 | Earthing Layout for Desalting Unit | BK-GCS-PEDCO-120-EL-PY-0014 | BK-GCS-PEDCO-120-EL-PY-0014 | BK | GCS | PEDCO | 120 | EL | PY | 0014 | F2P-709064 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 3 | 0 | 32 | 3.2.3.7.3 | Earthing Layout for Production Unit | BK-GCS-PEDCO-120-EL-PY-0015 | BK-GCS-PEDCO-120-EL-PY-0015 | BK | GCS | PEDCO | 120 | EL | PY | 0015 | F2P-709065 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 4 | 0 | 0 | 3.2.3.7.4 | List
3 | 2 | 3 | 7 | 4 | 0 | 1 | 3.2.3.7.4 | Electrical Load List | BK-GCS-PEDCO-120-EL-LI-0001 | BK-GCS-PEDCO-120-EL-LI-0001 | BK | GCS | PEDCO | 120 | EL | LI | 0001 | F0Z-709066 | AFC | IFC | 2021-11-30 | 2021-11-28 | 2021-12-01 | -2 | 3 | 1 | IFA | 2022-02-16 | 2022-02-16 | 2022-02-21 | 0 | 5 | 5 | IFA | 2022-04-09 | 2022-04-05 | 2022-04-09 | -4 | 4 | 0 | IFA | 2022-05-30 | 0 | 0 | -44711 | 0 | -44711 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-16 | 0 |  | D03 | IFA | T-0957 | 2022-05-16 | 1401/02/26 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04466 | 2022-05-29 | 1401/03/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0250 | 2021-11-16 | 1400/08/25 |  |  |  | BK-SUR-ENG-ELE-00-02157 | 2021-11-30 | 1400/09/09 | CM-C3 | [6 empty] | 1400-2290-294877 | 2021-11-28 | 1400/09/07 | 2021-12-01 | 1400/09/10 | CM | [10 empty] | D01 | IFA | T-0532 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-ELE-00-03082 | 2022-02-16 | 1400/11/27 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D00 | [5 empty] | 1400-2294-412906 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D00 | [9 empty] | D02 | IFA | T-0736 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-ELE-01-03789 | 2022-04-09 | 1401/01/20 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D01 | [5 empty] | 1401-2294-13858 | 2022-04-05 | 1401/01/18 | 2022-04-09 | 1401/01/20 | CM | NISOC-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D01 | [9 empty] | D03 | IFA | T-0957 | 2022-05-16 | 1401/02/26 |  |  |  | BK-SUR-ENG-ELE-01-04466 | 2022-05-29 | 1401/03/08 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-EL-LI-0001_D02
3 | 2 | 3 | 7 | 4 | 0 | 2 | 3.2.3.7.4 | Electrical Power & Control Cable Schedule | BK-GCS-PEDCO-120-EL-LI-0002 | BK-GCS-PEDCO-120-EL-LI-0002 | BK | GCS | PEDCO | 120 | EL | LI | 0002 | F0Z-709067 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 4 | 0 | 3 | 3.2.3.7.4 | Electrical Power & Control Drum Schedule & Cutting List | BK-GCS-PEDCO-120-EL-LI-0003 | BK-GCS-PEDCO-120-EL-LI-0003 | BK | GCS | PEDCO | 120 | EL | LI | 0003 | F0Z-709068 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 4 | 0 | 4 | 3.2.3.7.4 | Cable Schedule For Cathodic Protection System | BK-GCS-PEDCO-120-EL-LI-0004 | BK-GCS-PEDCO-120-EL-LI-0004 | BK | GCS | PEDCO | 120 | EL | LI | 0004 | F0Z-709069 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 4 | 0 | 5 | 3.2.3.7.4 | Electrical I/O Signal List | BK-GCS-PEDCO-120-EL-LI-0005 | BK-GCS-PEDCO-120-EL-LI-0005 | BK | GCS | PEDCO | 120 | EL | LI | 0005 | F0Z-709070 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 5 | 0 | 0 | 3.2.3.7.5 | Report
3 | 2 | 3 | 7 | 5 | 0 | 1 | 3.2.3.7.5 | Electrical Network (Load Flow, Motor Starting & Short Circuit) Study Report | BK-GCS-PEDCO-120-EL-RT-0001 | BK-GCS-PEDCO-120-EL-RT-0001 | BK | GCS | PEDCO | 120 | EL | RT | 0001 | F0Z-709071 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 5 | 0 | 2 | 3.2.3.7.5 | Relay Coordination & Setting Study Report | BK-GCS-PEDCO-120-EL-RT-0002 | BK-GCS-PEDCO-120-EL-RT-0002 | BK | GCS | PEDCO | 120 | EL | RT | 0002 | F0Z-709072 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 6 | 0 | 0 | 3.2.3.7.6 | MTO
3 | 2 | 3 | 7 | 6 | 0 | 1 | 3.2.3.7 | MTO For Earthing & Lightning Systems | BK-GCS-PEDCO-120-EL-MT-0001 | BK-GCS-PEDCO-120-EL-MT-0001 | BK | GCS | PEDCO | 120 | EL | MT | 0001 | F8Z-709073 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 6 | 0 | 2 | 3.2.3.7 | MTO For Lighting & Small Powers | BK-GCS-PEDCO-120-EL-MT-0002 | BK-GCS-PEDCO-120-EL-MT-0002 | BK | GCS | PEDCO | 120 | EL | MT | 0002 | F8Z-709074 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 6 | 0 | 3 | 3.2.3.7 | MTO For Power & Control Cables | BK-GCS-PEDCO-120-EL-MT-0003 | BK-GCS-PEDCO-120-EL-MT-0003 | BK | GCS | PEDCO | 120 | EL | MT | 0003 | F8Z-709075 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 6 | 0 | 4 | 3.2.3.7 | MTO For Tray/Ladder and Accessories | BK-GCS-PEDCO-120-EL-MT-0004 | BK-GCS-PEDCO-120-EL-MT-0004 | BK | GCS | PEDCO | 120 | EL | MT | 0004 | F8Z-709076 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 7 | 6 | 0 | 5 | 3.2.3.7 | MTO For Cathodic Protection System | BK-GCS-PEDCO-120-EL-MT-0005 | BK-GCS-PEDCO-120-EL-MT-0005 | BK | GCS | PEDCO | 120 | EL | MT | 0005 | F8Z-709077 | IFI | IFI | 2022-05-15 | 0 | 0 | -44696 | 0 | -44696 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-01 | 2022-05-01 |  | D00 | IFI | T-0892 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ELE-01-04255 | 2022-05-14 | 1401/02/24 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0892 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ELE-01-04255 | 2022-05-14 | 1401/02/24 | CM-C3
3 | 2 | 3 | 7 | 6 | 0 | 6 | 3.2.3.7 | MTO For Electrical Bulk Items | BK-GCS-PEDCO-120-EL-MT-0006 | BK-GCS-PEDCO-120-EL-MT-0006 | BK | GCS | PEDCO | 120 | EL | MT | 0006 | F8Z-709078 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 8 | 0 | 0 | 0 | 3.2.3.8 | Intercom. & Telecomm.
3 | 2 | 3 | 8 | 1 | 0 | 0 | 3.2.3.8.1 | Data Sheets
3 | 2 | 3 | 8 | 1 | 0 | 1 | 3.2.3.8.1 | Data Sheets For CCTV | BK-GCS-PEDCO-120-TE-DT-0001 | BK-GCS-PEDCO-120-TE-DT-0001 | [7 empty] | - | [43 empty] | Moved to IN | 0
3 | 2 | 3 | 8 | 1 | 0 | 2 | 3.2.3.8.1 | Data Sheets For PABX | BK-GCS-PEDCO-120-TE-DT-0002 | BK-GCS-PEDCO-120-TE-DT-0002 | BK | GCS | PEDCO | 120 | TE | DT | 0002 | F0Z-709079 | AFC | IFC | 2021-10-27 | 2021-11-04 | 2021-11-07 | 8 | 3 | 11 | IFA | 2021-11-30 | 2022-01-27 | 2022-01-31 | 58 | 4 | 62 | AFC | 2022-02-16 | 2022-02-22 | 2022-02-21 | 6 | -1 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-13 | 2022-02-02 |  | D02 | AFC | T-0536 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-411808 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | RJ | 0 | 1400-2294-421733 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | CM | 0 | 0 |  | D00 | IFC | T-0157 | 2021-10-13 | 1400/07/21 | [13 empty] | 1400-2294-261488 | 2021-11-04 | 1400/08/12 | 2021-11-07 | 1400/08/16 | CM | [10 empty] | D01 | IFA | T-0253 | 2021-11-16 | 1400/08/25 |  |  |  | BK-SUR-ENG-TEL-00-02392 | 2021-12-21 | 1400/09/30 | AP | [6 empty] | 1400-2294-384188 | 2022-01-27 | 1400/11/07 | 2022-01-31 | 1400/11/11 | AP | NISOC-BK-GCS-PEDCO-120-TE-DT-0002_D00 | [9 empty] | D02 | AFC | T-0536 | 2022-02-02 | 1400/11/13 | [13 empty] | 1400-2294-411808 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | RJ |  | 1400-2294-421733 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | CM
3 | 2 | 3 | 8 | 1 | 0 | 3 | 3.2.3.8.1 | Data Sheets For PAGA | BK-GCS-PEDCO-120-TE-DT-0003 | BK-GCS-PEDCO-120-TE-DT-0003 | BK | GCS | PEDCO | 120 | TE | DT | 0003 | F0Z-709080 | AFC | IFC | 2021-10-27 | 2021-11-04 | 2021-11-07 | 8 | 3 | 11 | IFA | 2021-11-30 | 2022-01-27 | 2022-01-31 | 58 | 4 | 62 | AFC | 2022-02-27 | 2022-02-22 | 2022-02-02 | -5 | -20 | -25 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-13 | 2022-02-13 |  | D02 | AFC | T-0584 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-DT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-421732 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-TE-DT-0003_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0157 | 2021-10-13 | 1400/07/21 | [13 empty] | 1400-2294-261488 | 2021-11-04 | 1400/08/12 | 2021-11-07 | 1400/08/16 | CM | [10 empty] | D01 | IFA | T-0253 | 2021-11-16 | 1400/08/25 |  |  |  | BK-SUR-ENG-TEL-00-02392 | 2021-12-21 | 1400/09/30 | CM-C2 | [6 empty] | 1400-2294-384188 | 2022-01-27 | 1400/11/07 | 2022-01-31 | 1400/11/11 | AP | NISOC-BK-GCS-PEDCO-120-TE-DT-0003_D00 | [9 empty] | D02 | AFC | T-0584 | 2022-02-13 | 1400/11/24 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-TE-DT-0003_D01 | [5 empty] | 1400-2294-421732 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | CM | NISOC-CRS-BK-GCS-PEDCO-120-TE-DT-0003_D01
3 | 2 | 3 | 8 | 1 | 0 | 4 | 3.2.3.8.1 | Data Sheets For Radio | BK-GCS-PEDCO-120-TE-DT-0004 | BK-GCS-PEDCO-120-TE-DT-0004 | BK | GCS | PEDCO | 120 | TE | DT | 0004 | F0Z-709081 | AFC | IFC | 2021-12-05 | 2021-12-03 | 2022-01-05 | -2 | 33 | 31 | IFA | 2022-01-24 | 2022-01-26 | 2022-01-31 | 2 | 5 | 7 | AFC | 2022-02-16 | 2022-02-22 | 2022-02-21 | 6 | -1 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-21 | 2022-02-02 |  | D02 | AFC | T-0536 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-411808 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | RJ | 0 | 1400-2294-421733 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | CM | 0 | 0 |  | D00 | IFC | T-0263 | 2021-11-21 | 1400/08/30 |  |  |  | BK-SUR-ENG-TEL-00-02393 | 2021-12-21 | 1400/09/30 | AP | [6 empty] | 1400-2294-348118 | 2021-12-03 | 1400/10/13 | 2022-01-05 | 1400/10/15 | CM | [10 empty] | D01 | IFA | T-0445 | 2022-01-10 | 1400/10/20 |  |  |  | BK-SUR-ENG-TEL-00-02618 | 2022-01-10 | 1400/10/20 | AP | [6 empty] | 1400-2294-383245 | 2022-01-26 | 1400/11/06 | 2022-01-31 | 1400/11/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-DT-0004_D00 | [9 empty] | D02 | AFC | T-0536 | 2022-02-02 | 1400/11/13 | [13 empty] | 1400-2294-411808 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | RJ |  | 1400-2294-421733 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | CM
3 | 2 | 3 | 8 | 1 | 0 | 5 | 3.2.3.8.1 | Data Sheets For Telecom. Cable | BK-GCS-PEDCO-120-TE-DT-0005 | BK-GCS-PEDCO-120-TE-DT-0005 | BK | GCS | PEDCO | 120 | TE | DT | 0005 | F0Z-709082 | AFC | IFC | 2021-10-27 | 2021-11-04 | 2021-11-07 | 8 | 3 | 11 | IFA | 2021-12-01 | 2022-01-29 | 2022-01-31 | 59 | 2 | 61 | AFC | 2022-02-16 | 2022-02-22 | 2022-02-21 | 6 | -1 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-13 | 2022-02-02 |  | D02 | AFC | T-0536 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-411808 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | RJ | 0 | 1400-2294-421733 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | CM | 0 | 0 |  | D00 | IFC | T-0156 | 2021-10-13 | 1400/07/21 | [13 empty] | 1400-2294-261481 | 2021-11-04 | 1400/08/13 | 2021-11-07 | 1400/08/16 | CM | [10 empty] | D01 | IFA | T-0251 | 2021-11-17 | 1400/08/26 |  |  |  | BK-SUR-ENG-TEL-00-02391 | 2021-12-21 | 1400/09/30 | AP | [6 empty] | 1400-2294-386717 | 2022-01-29 | 1400/11/09 | 2022-01-31 | 1400/11/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-DT-0005 | [9 empty] | D02 | AFC | T-0536 | 2022-02-02 | 1400/11/13 | [13 empty] | 1400-2294-411808 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | RJ |  | 1400-2294-421733 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | CM
3 | 2 | 3 | 8 | 1 | 0 | 6 | 3.2.3.8.1 | Data Sheets For Telecommunication Tower | BK-GCS-PEDCO-120-TE-DT-0006 | BK-GCS-PEDCO-120-TE-DT-0006 | BK | GCS | PEDCO | 120 | TE | DT | 0006 | F0Z-709083 | AFC | IFC | 2021-10-27 | 2021-11-04 | 2021-11-07 | 8 | 3 | 11 | IFA | 2021-12-01 | 2022-01-29 | 2022-01-31 | 59 | 2 | 61 | AFC | 2022-02-16 | 2022-02-22 | 2022-02-21 | 6 | -1 | 5 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-10-13 | 2022-02-02 |  | D02 | AFC | T-0536 | 2022-02-02 | 1400/11/13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-411808 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | RJ | 0 | 1400-2294-421733 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | CM | 0 | 0 |  | D00 | IFC | T-0156 | 2021-10-13 | 1400/07/21 | [13 empty] | 1400-2294-261481 | 2021-11-04 | 1400/08/13 | 2021-11-07 | 1400/08/16 | CM | [10 empty] | D01 | IFA | T-0251 | 2021-11-17 | 1400/08/26 |  |  |  | BK-SUR-ENG-TEL-00-02391 | 2021-12-21 | 1400/09/30 | AP | [6 empty] | 1400-2294-386717 | 2022-01-29 | 1400/11/09 | 2022-01-31 | 1400/11/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-DT-0006 | [9 empty] | D02 | AFC | T-0536 | 2022-02-02 | 1400/11/13 | [13 empty] | 1400-2294-411808 | 2022-02-16 | 1400/11/27 | 2022-02-21 | 1400/12/02 | RJ |  | 1400-2294-421733 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | CM
3 | 2 | 3 | 8 | 2 | 0 | 0 | 3.2.3.8.2 | Drawing/Diagram
3 | 2 | 3 | 8 | 2 | 0 | 1 | 3.2.3.8.2 | Telecom Overall Block Diagram | BK-GCS-PEDCO-120-TE-BD-0001 | BK-GCS-PEDCO-120-TE-BD-0001 | BK | GCS | PEDCO | 120 | TE | BD | 0001 | F2T-709084 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 8 | 2 | 0 | 2 | 3.2.3.8.2 | Typical Installation Details & Notes For Telecommunication Tower | BK-GCS-PEDCO-120-TE-DW-0001 | BK-GCS-PEDCO-120-TE-DW-0001 | BK | GCS | PEDCO | 120 | TE | DW | 0001 | F2T-709085 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 8 | 2 | 0 | 3 | 3.2.3.8.2 | Block Diagram For CCTV | BK-GCS-PEDCO-120-TE-BD-0002 | BK-GCS-PEDCO-120-TE-BD-0002 | [7 empty] | - | [43 empty] | Moved to IN | 0
3 | 2 | 3 | 8 | 2 | 0 | 4 | 3.2.3.8.2 | Block Diagram For CCTV in Binak DU | BK-GCS-PEDCO-120-TE-BD-0003 | BK-GCS-PEDCO-120-TE-BD-0003 | [7 empty] | - | [43 empty] | Moved to IN | 0
3 | 2 | 3 | 8 | 2 | 0 | 5 | 3.2.3.8.2 | Block Diagram For PABX | BK-GCS-PEDCO-120-TE-BD-0004 | BK-GCS-PEDCO-120-TE-BD-0004 | BK | GCS | PEDCO | 120 | TE | BD | 0004 | F2T-709086 | AFC | IFC | 2021-08-11 | 2021-09-12 | 2021-09-14 | 32 | 2 | 34 | IFA | 2021-10-05 | 2021-10-06 | 2021-10-10 | 1 | 4 | 5 | IFA | 2021-11-15 | 2021-12-28 | 2021-12-05 | 43 | -23 | 20 | AFC | 2022-03-09 | 2022-03-06 | 2022-03-01 | -3 | -5 | -8 | AFC | 2022-03-22 | 2022-03-14 | 2022-04-01 | -8 | 18 | 10 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 2022-03-08 |  | D04 | AFC | T-0699 | 2022-03-08 | 1400/12/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448924 | 2022-03-14 | 1400/12/23 | 2022-04-01 | 1401/01/14 | AP | NISOC-BK-GCS-PEDCO-120-TE-BD-0004_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0019 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-TEL-00-01305 | 2021-08-10 | 1400/05/19 | CM-C2 | [6 empty] | 1400/2294/194238 | 2021-09-12 | 1400/06/21 | 2021-09-14 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0112 | 2021-09-21 | 1400/06/30 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-TE-BD-0004_D00 | [5 empty] | 1400-2290-223856 | 2021-10-06 | 1400/07/14 | 2021-10-10 | 1400/07/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-TE-BD-0004_D00 | [9 empty] | D02 | IFA | T-0200 | 2021-11-01 | 1400/08/10 |  |  |  | BK-SUR-ENG-TEL-00-02390 | 2021-12-21 | 1400/09/30 | CM-C2 | [6 empty] | 1400-2290-294875 | 2021-12-28 | 1400/09/07 | 2021-12-05 | 1400/09/14 | AP | NISOC-CRS-D01-BK-GCS-PEDCO-120-TE-BD-0004_D01 | [9 empty] | D03 | AFC | T-0631 | 2022-02-23 | 1400/12/04 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-TE-BD-0004_D02 | [5 empty] | 1400-2294-430787 | 2022-03-06 | 1400/12/15 | 2022-03-01 | 1400/12/10 | CM | [10 empty] | D04 | AFC | T-0699 | 2022-03-08 | 1400/12/17 | [13 empty] | 1400-2294-448924 | 2022-03-14 | 1400/12/23 | 2022-04-01 | 1401/01/14 | AP | NISOC-BK-GCS-PEDCO-120-TE-BD-0004_D03
3 | 2 | 3 | 8 | 2 | 0 | 6 | 3.2.3.8.2 | Block Diagram For PAGA | BK-GCS-PEDCO-120-TE-BD-0005 | BK-GCS-PEDCO-120-TE-BD-0005 | BK | GCS | PEDCO | 120 | TE | BD | 0005 | F2T-709087 | AFC | IFC | 2021-08-11 | 2021-09-12 | 2021-09-14 | 32 | 2 | 34 | IFA | 2021-10-05 | 2021-10-06 | 2021-10-10 | 1 | 4 | 5 | IFA | 2021-11-15 | 2021-12-28 | 2021-12-05 | 43 | -23 | 20 | AFC | 2022-03-08 | 2022-03-06 | 2022-03-01 | -2 | -5 | -7 | AFC | 2022-03-22 | 2022-03-14 | 2022-04-01 | -8 | 18 | 10 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 2022-03-08 |  | D04 | AFC | T-0699 | 2022-03-08 | 1400/12/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-448924 | 2022-03-14 | 1400/12/23 | 2022-04-01 | 1401/01/14 | AP | NISOC-BK-GCS-PEDCO-120-TE-BD-0005_D03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0019 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-TEL-00-01305 | 2021-08-10 | 1400/05/19 | CM-C2 | [6 empty] | 1400/2294/194238 | 2021-09-12 | 1400/06/21 | 2021-09-14 | 1400/06/23 | CM | [10 empty] | D01 | IFA | T-0112 | 2021-09-21 | 1400/06/30 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-TE-BD-0005_D00 | [5 empty] | 1400-2290-223856 | 2021-10-06 | 1400/07/14 | 2021-10-10 | 1400/07/18 | CM | NISOC-CRS-BK-GCS-PEDCO-120-TE-BD-0005_D00 | [9 empty] | D02 | IFA | T-0200 | 2021-11-01 | 1400/08/10 |  |  |  | BK-SUR-ENG-TEL-00-02390 | 2021-12-21 | 1400/09/30 | CM-C2 | [6 empty] | 1400-2290-294875 | 2021-12-28 | 1400/09/07 | 2021-12-05 | 1400/09/14 | CM | NISOC-CRS-BK-GCS-PEDCO-120-TE-BD-0005-D01 | [9 empty] | D03 | AFC | T-0626 | 2022-02-22 | 1400/12/03 | [13 empty] | 1400-2294-430786 | 2022-03-06 | 1400/12/15 | 2022-03-01 | 1400/12/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-TE-BD-0005_D02 | [9 empty] | D04 | AFC | T-0699 | 2022-03-08 | 1400/12/17 | [13 empty] | 1400-2294-448924 | 2022-03-14 | 1400/12/23 | 2022-04-01 | 1401/01/14 | AP | NISOC-BK-GCS-PEDCO-120-TE-BD-0005_D03
3 | 2 | 3 | 8 | 2 | 0 | 7 | 3.2.3.8.2 | Block Diagram For Radio | BK-GCS-PEDCO-120-TE-BD-0006 | BK-GCS-PEDCO-120-TE-BD-0006 | BK | GCS | PEDCO | 120 | TE | BD | 0006 | F2T-709088 | AFC | IFC | 2021-08-11 | 2021-09-12 | 2021-09-14 | 32 | 2 | 34 | AFC | 2021-10-09 | 2021-10-09 | 2021-10-12 | 0 | 3 | 3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-07-28 | 2021-09-25 |  | D01 | AFC | T-0118 | 2021-09-25 | 1400/07/03 | 0 | 0 | 0 | BK-SUR-ENG-TEL-00-02387 | 2021-12-21 | 1400/09/30 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2290-227454 | 2021-10-09 | 1400/07/17 | 2021-10-12 | 1400/07/20 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0019 | 2021-07-28 | 1400/05/06 |  |  |  | BK-SUR-ENG-TEL-00-01305 | 2021-08-10 | 1400/05/19 | AP | [6 empty] | 1400/2294/194238 | 2021-09-12 | 1400/06/21 | 2021-09-14 | 1400/06/23 | AP | [10 empty] | D01 | AFC | T-0118 | 2021-09-25 | 1400/07/03 |  |  |  | BK-SUR-ENG-TEL-00-02387 | 2021-12-21 | 1400/09/30 | CM-C2 | [6 empty] | 1400-2290-227454 | 2021-10-09 | 1400/07/17 | 2021-10-12 | 1400/07/20 | AP
3 | 2 | 3 | 8 | 2 | 0 | 8 | 3.2.3.8.2 | Telecomm. Equipment Layout For Electrical Building | BK-GCS-PEDCO-120-TE-PY-0001 | BK-GCS-PEDCO-120-TE-PY-0001 | BK | GCS | PEDCO | 120 | TE | PY | 0001 | F2T-709089 | AFC | IFC | 2022-05-01 | 2022-04-28 | 2022-05-01 | -3 | 3 | 0 | IFA | 2022-05-22 | 0 | 0 | -44703 | 0 | -44703 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-17 | 0 |  | D01 | IFA | T-0912 | 2022-05-08 | 1401/02/18 | T-0912 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-TEL-01-04214 | 2022-05-10 | 1401/02/20 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0001_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0833 | 2022-04-17 | 1401/01/28 |  |  |  | BK-SUR-ENG-TEL-01-03971 | 2022-04-18 | 1401/01/29 | C4-RJ | [6 empty] | 1401-2294-42934 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | [10 empty] | D01 | IFA | T-0912 | 2022-05-08 | 1401/02/18 | T-0912 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-TEL-01-04214 | 2022-05-10 | 1401/02/20 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0001_D00 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0001_D00
3 | 2 | 3 | 8 | 2 | 0 | 9 | 3.2.3.8.2 | Telecomm. Equipment Layout For Control Building | BK-GCS-PEDCO-120-TE-PY-0002 | BK-GCS-PEDCO-120-TE-PY-0002 | BK | GCS | PEDCO | 120 | TE | PY | 0002 | F2T-709090 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 8 | 2 | 0 | 10 | 3.2.3.8.2 | CCTV Equipment Layout For Area | BK-GCS-PEDCO-120-TE-PY-0003 | BK-GCS-PEDCO-120-TE-PY-0003 | [7 empty] | - | [43 empty] | Moved to IN | 0
3 | 2 | 3 | 8 | 2 | 0 | 11 | 3.2.3.8.2 | CCTV Equipment Layout For Desalting Unit Area | BK-GCS-PEDCO-120-TE-PY-0004 | BK-GCS-PEDCO-120-TE-PY-0004 | [7 empty] | - | [43 empty] | Moved to IN | 0
3 | 2 | 3 | 8 | 2 | 0 | 12 | 3.2.3.8.2 | Telecomm Equipment Layout For Area | BK-GCS-PEDCO-120-TE-PY-0005 | BK-GCS-PEDCO-120-TE-PY-0005 | BK | GCS | PEDCO | 120 | TE | PY | 0005 | F2T-709091 | AFC | IFC | 2022-04-18 | 2022-04-28 | 2022-05-01 | 10 | 3 | 13 | IFA | 2022-05-22 | 0 | 0 | -44703 | 0 | -44703 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-04 | 0 |  | D01 | IFA | T-0912 | 2022-05-08 | 1401/02/18 | T-0912 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-TEL-01-04214 | 2022-05-10 | 1401/02/20 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0775 | 2022-04-04 | 1401/01/15 | [13 empty] | 1401-2294-42940 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | [10 empty] | D01 | IFA | T-0912 | 2022-05-08 | 1401/02/18 | T-0912 | 2022-05-08 | 1401/02/18 | BK-SUR-ENG-TEL-01-04214 | 2022-05-10 | 1401/02/20 | AP | [12 empty] | NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0005_D00
3 | 2 | 3 | 8 | 2 | 0 | 13 | 3.2.3.8.2 | PAGA Equipment Layout For Area | BK-GCS-PEDCO-120-TE-PY-0006 | BK-GCS-PEDCO-120-TE-PY-0006 | BK | GCS | PEDCO | 120 | TE | PY | 0006 | F2T-709092 | AFC | IFC | 2022-04-20 | 2022-04-28 | 2022-05-01 | 8 | 3 | 11 | IFA | 2022-05-29 | 0 | 0 | -44710 | 0 | -44710 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-06 | 0 |  | D01 | IFA | T-0954 | 2022-05-15 | 1401/02/25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-NISOC-120-TE-PY-0006_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0784 | 2022-04-06 | 1401/01/17 |  |  |  | BK-SUR-ENG-TEL-01-03852 | 2022-04-11 | 1401/01/22 | C4-RJ | [6 empty] | 1401-2294-43096 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | [10 empty] | D01 | IFA | T-0954 | 2022-05-15 | 1401/02/25 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0006_D00 | [11 empty] | NISOC-CRS-BK-GCS-NISOC-120-TE-PY-0006_D00
3 | 2 | 3 | 8 | 3 | 0 | 0 | 3.2.3.8.3 | List
3 | 2 | 3 | 8 | 3 | 0 | 1 | 3.2.3.8.3 | Cable Schedule For CCTV | BK-GCS-PEDCO-120-TE-LI-0001 | BK-GCS-PEDCO-120-TE-LI-0001 | [7 empty] | - | [43 empty] | Moved to IN | 0
3 | 2 | 3 | 8 | 3 | 0 | 3 | 3.2.3.8.3 | Cable Schedule For PABX | BK-GCS-PEDCO-120-TE-LI-0003 | BK-GCS-PEDCO-120-TE-LI-0003 | BK | GCS | PEDCO | 120 | TE | LI | 0003 | F0Z-709093 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 8 | 3 | 0 | 4 | 3.2.3.8.3 | Cable Schedule For PAGA | BK-GCS-PEDCO-120-TE-LI-0004 | BK-GCS-PEDCO-120-TE-LI-0004 | BK | GCS | PEDCO | 120 | TE | LI | 0004 | F0Z-709094 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 8 | 4 | 0 | 0 | 3.2.3.8.4 | MTO
3 | 2 | 3 | 8 | 4 | 0 | 1 | 3.2.3.8 | MTO For CCTV | BK-GCS-PEDCO-120-TE-MT-0001 | BK-GCS-PEDCO-120-TE-MT-0001 | [7 empty] | - | [43 empty] | Moved to IN | 0
3 | 2 | 3 | 8 | 4 | 0 | 2 | 3.2.3.8 | MTO For CCTV in Binak DU Area | BK-GCS-PEDCO-120-TE-MT-0002 | BK-GCS-PEDCO-120-TE-MT-0002 | [7 empty] | - | [43 empty] | Moved to IN | 0
3 | 2 | 3 | 8 | 4 | 0 | 3 | 3.2.3.8 | MTO For PABX | BK-GCS-PEDCO-120-TE-MT-0003 | BK-GCS-PEDCO-120-TE-MT-0003 | BK | GCS | PEDCO | 120 | TE | MT | 0003 | F8Z-709095 | IFI | IFI | 2022-06-08 | 0 | 0 | -44720 | 0 | -44720 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-25 | 2022-05-25 |  | D00 | IFI | T-1004 | 2022-05-25 | 1401/03/04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1004 | 2022-05-25 | 1401/03/04
3 | 2 | 3 | 8 | 4 | 0 | 4 | 3.2.3.8 | MTO For PAGA | BK-GCS-PEDCO-120-TE-MT-0004 | BK-GCS-PEDCO-120-TE-MT-0004 | BK | GCS | PEDCO | 120 | TE | MT | 0004 | F8Z-709096 | IFI | IFI | 2022-06-08 | 0 | 0 | -44720 | 0 | -44720 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-25 | 2022-05-25 |  | D00 | IFI | T-1004 | 2022-05-25 | 1401/03/04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-1004 | 2022-05-25 | 1401/03/04
3 | 2 | 3 | 8 | 4 | 0 | 5 | 3.2.3.8 | MTO For Radio | BK-GCS-PEDCO-120-TE-MT-0005 | BK-GCS-PEDCO-120-TE-MT-0005 | BK | GCS | PEDCO | 120 | TE | MT | 0005 | F8Z-709097 | IFI | IFI | 2021-12-27 | 2022-01-03 | 2022-01-05 | 7 | 2 | 9 | IFI | 2022-01-23 | 2022-01-26 | 2022-01-31 | 3 | 5 | 8 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-13 | 2022-01-09 |  | D01 | IFI | T-0443 | 2022-01-09 | 1400/10/19 | 0 | 0 | 0 | BK-SUR-ENG-TEL-00-02617 | 2022-01-10 | 1400/10/20 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-382553 | 2022-01-26 | 1400/11/06 | 2022-01-31 | 1400/11/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-MT-0005_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0337 | 2021-12-13 | 1400/09/22 | [13 empty] | 1400-2294-348051 | 2022-01-03 | 1400/10/13 | 2022-01-05 | 1400/10/15 | CM | [10 empty] | D01 | IFI | T-0443 | 2022-01-09 | 1400/10/19 |  |  |  | BK-SUR-ENG-TEL-00-02617 | 2022-01-10 | 1400/10/20 | AP | [6 empty] | 1400-2294-382553 | 2022-01-26 | 1400/11/06 | 2022-01-31 | 1400/11/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-MT-0005_D00
3 | 2 | 3 | 8 | 4 | 0 | 6 | 3.2.3.8 | MTO For Telecom. Cable | BK-GCS-PEDCO-120-TE-MT-0006 | BK-GCS-PEDCO-120-TE-MT-0006 | BK | GCS | PEDCO | 120 | TE | MT | 0006 | F8Z-709098 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 9 | 0 | 0 | 0 | 3.2.3.9 | Architecture
3 | 2 | 3 | 9 | 1 | 0 | 0 | 3.2.3.9.1 | Drawing/Diagram
3 | 2 | 3 | 9 | 1 | 0 | 1 | 3.2.3.9.1 | Architectural Detail Drawing For Control Building | BK-GCS-PEDCO-120-AR-DW-0001 | BK-GCS-PEDCO-120-AR-DW-0001 | BK | GCS | PEDCO | 120 | AR | DW | 0001 | F4B-709099 | AFC | IFC | 2021-12-27 | 2021-12-23 | 2021-12-26 | -4 | 3 | -1 | IFC | 2022-02-05 | 2022-01-31 | 2022-02-02 | -5 | 2 | -3 | IFC | 2022-04-09 | 2022-04-13 | 2022-04-16 | 4 | 3 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D02 | IFC | T-0734 | 2022-03-26 | 1401/01/06 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-03743 | 2022-04-07 | 1401/01/17 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1401-2294-22850 | 2022-04-13 | 1401/01/24 | 2022-04-16 | 1401/01/27 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0341 | 2021-12-13 | 1400/09/22 |  |  |  | BK-SUR-ENG-ARC-00-02364 | 2021-12-18 | 1400/09/27 | CM-C2 | [6 empty] | 1400-2294-331874 | 2021-12-23 | 1400/10/02 | 2021-12-26 | 1400/10/05 | RJ | [10 empty] | D01 | IFC | T-0480 | 2022-01-22 | 1400/11/02 |  |  |  | BK-SUR-ENG-ARC-00-02799 | 2022-01-24 | 1400/11/04 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0001-D00 | [5 empty] | 1400-2294-390554 | 2022-01-31 | 1400/11/11 | 2022-02-02 | 1400/11/13 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0001-D00 | [9 empty] | D02 | IFC | T-0734 | 2022-03-26 | 1401/01/06 |  |  |  | BK-SUR-ENG-ARC-01-03743 | 2022-04-07 | 1401/01/17 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0001_D01 | [5 empty] | 1401-2294-22850 | 2022-04-13 | 1401/01/24 | 2022-04-16 | 1401/01/27 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0001_D01
3 | 2 | 3 | 9 | 1 | 0 | 2 | 3.2.3.9.1 | Architectural Detail Drawing For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-AR-DW-0002 | BK-GCS-PEDCO-120-AR-DW-0002 | BK | GCS | PEDCO | 120 | AR | DW | 0002 | F4B-709100 | AFC | IFC | 2022-01-29 | 2022-01-26 | 2022-01-23 | -3 | -3 | -6 | IFA | 2022-04-23 | 2022-04-19 | 2022-04-24 | -4 | 5 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-01-15 | 0 |  | D01 | IFA | T-0786 | 2022-04-09 | 1401/01/20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-31077 | 2022-04-19 | 1401/01/30 | 2022-04-24 | 1401/01/04 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0459 | 2022-01-15 | 1400/10/25 |  |  |  | BK-SUR-ENG-ARC-00-02755 | 2022-01-22 | 1400/11/01 | CM-C2 |  | BK-SUR-ENG-ARC-00-02818 | 2022-01-26 | 1400/11/06 | CM |  | 1400-2294-377543 | 2022-01-26 | 1400/11/06 | 2022-01-23 | 1400/11/03 | CM | [10 empty] | D01 | IFA | T-0786 | 2022-04-09 | 1401/01/20 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-AR-DW-0002_D00 | [5 empty] | 1401-2294-31077 | 2022-04-19 | 1401/01/30 | 2022-04-24 | 1401/01/04 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0002_D00
3 | 2 | 3 | 9 | 1 | 0 | 3 | 3.2.3.9.1 | Architectural Drawing For Gas Compressors Shelter | BK-GCS-PEDCO-120-AR-DW-0003 | BK-GCS-PEDCO-120-AR-DW-0003 | BK | GCS | PEDCO | 120 | AR | DW | 0003 | F4K-709101 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 9 | 1 | 0 | 4 | 3.2.3.9.1 | Architectural Drawing For Chemical Inj. Packages/Chemical Storage Shelter | BK-GCS-PEDCO-120-AR-DW-0004 | BK-GCS-PEDCO-120-AR-DW-0004 | BK | GCS | PEDCO | 120 | AR | DW | 0004 | F4B-709102 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 9 | 1 | 0 | 5 | 3.2.3.9.1 | Architectural Drawing For Utility Shelter | BK-GCS-PEDCO-120-AR-DW-0005 | BK-GCS-PEDCO-120-AR-DW-0005 | BK | GCS | PEDCO | 120 | AR | DW | 0005 | F4B-709103 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 9 | 1 | 0 | 6 | 3.2.3.9.1 | Architectural Drawing For Fire Water Pumps Shelter | BK-GCS-PEDCO-120-AR-DW-0006 | BK-GCS-PEDCO-120-AR-DW-0006 | BK | GCS | PEDCO | 120 | AR | DW | 0006 | F4B-709104 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 9 | 1 | 0 | 7 | 3.2.3.9.1 | Architectural Drawing For Fire Shed | BK-GCS-PEDCO-120-AR-DW-0007 | BK-GCS-PEDCO-120-AR-DW-0007 | BK | GCS | PEDCO | 120 | AR | DW | 0007 | F4B-709105 | AFC | IFC | 2022-05-15 | 2022-05-14 | 2022-05-16 | -1 | 2 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 | 0 | 0 | 0 | BK-SUR-ENG-ARC-01-04190 | 2022-05-10 | 1401/02/20 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 2022-05-16 | 1401/02/26 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0886 | 2022-05-01 | 1401/02/11 |  |  |  | BK-SUR-ENG-ARC-01-04190 | 2022-05-10 | 1401/02/20 | CM-C2 | [6 empty] | 1401-2294-58919 | 2022-05-14 | 1401/02/21 | 2022-05-16 | 1401/02/26 | RJ
3 | 2 | 3 | 9 | 2 | 0 | 0 | 3.2.3.9.2 | MTO
3 | 2 | 3 | 9 | 2 | 0 | 1 | 3.2.3.9 | MTO For Architectural Works | BK-GCS-PEDCO-120-AR-MT-0001 | BK-GCS-PEDCO-120-AR-MT-0001 | BK | GCS | PEDCO | 120 | AR | MT | 0001 | F8Z-709106 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 9 | 2 | 0 | 2 | 3.2.3.9 | MTO For Blast Proof Doors | BK-GCS-PEDCO-120-AR-MT-0002 | BK-GCS-PEDCO-120-AR-MT-0002 | BK | GCS | PEDCO | 120 | AR | MT | 0002 | F8Z-709107 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 10 | 0 | 0 | 0 | 3.2.3.10 | Civil
3 | 2 | 3 | 10 | 1 | 0 | 0 | 3.2.3.10.1 | Drawing/Diagram
3 | 2 | 3 | 10 | 1 | 0 | 1 | 3.2.3.10.1 | Site Sewarage System Layout & Details | BK-GCS-PEDCO-120-CV-PY-0001 | BK-GCS-PEDCO-120-CV-PY-0001 | BK | GCS | PEDCO | 120 | CV | PY | 0001 | F4S-709108 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 10 | 1 | 0 | 2 | 3.2.3.10.1 | Cable Trench and Duct Bank Layout | BK-GCS-PEDCO-120-CV-PY-0002 | BK-GCS-PEDCO-120-CV-PY-0002 | BK | GCS | PEDCO | 120 | CV | PY | 0002 | F4S-709109 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 10 | 1 | 0 | 3 | 3.2.3.10.1 | Oil Contaminated Water System Layout | BK-GCS-PEDCO-120-CV-PY-0003 | BK-GCS-PEDCO-120-CV-PY-0003 | BK | GCS | PEDCO | 120 | CV | PY | 0003 | F4S-709110 | AFC | IFC | 2022-06-12 | 0 | 0 | -44724 | 0 | -44724 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-29 | 0 |  | D00 | IFC | T-1019 | 2022-05-29 | 1401/03/08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1019 | 2022-05-29 | 1401/03/08
3 | 2 | 3 | 10 | 1 | 0 | 4 | 3.2.3.10.1 | Plant Clean Water Drainage System Layout & Details | BK-GCS-PEDCO-120-CV-PY-0004 | BK-GCS-PEDCO-120-CV-PY-0004 | BK | GCS | PEDCO | 120 | CV | PY | 0004 | F4S-709111 | AFC | IFC | 2022-06-14 | 0 | 0 | -44726 | 0 | -44726 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-31 | 0 |  | D00 | IFC | T-1027 | 2022-05-31 | 1401/03/10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-1027 | 2022-05-31 | 1401/03/10
3 | 2 | 3 | 10 | 1 | 0 | 5 | 3.2.3.10.1 | Road, Paving And Plant Finish Grading Layout & Sections | BK-GCS-PEDCO-120-CV-PY-0005 | BK-GCS-PEDCO-120-CV-PY-0005 | BK | GCS | PEDCO | 120 | CV | PY | 0005 | F4S-709112 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 10 | 1 | 0 | 6 | 3.2.3.10.1 | Plant Underground Composite Layout | BK-GCS-PEDCO-120-CV-PY-0006 | BK-GCS-PEDCO-120-CV-PY-0006 | BK | GCS | PEDCO | 120 | CV | PY | 0006 | F4S-709113 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
[7 empty] | 3.2.3.10.2 | Rough Grading Plan and Details | BK-GCS-PEDCO-120-CV-PY-0007 | BK-GCS-PEDCO-120-CV-PY-0007 | BK | GCS | PEDCO | 120 | CV | PY | 0007 | F5S-709395 | AFC | IFC | 2022-06-06 | 0 | 0 | -44718 | 0 | -44718 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-23 | 0 | [35 empty] | D00 | IFC | T-0995 | 2022-05-23 | 1401/03/02
3 | 2 | 3 | 10 | 2 | 0 | 0 | 3.2.3.10.2 | Calculation
3 | 2 | 3 | 10 | 2 | 0 | 1 | 3.2.3.10.2 | Calculation Note For Inside Surface Water Drainage Channels | BK-GCS-PEDCO-120-CV-CN-0001 | BK-GCS-PEDCO-120-CV-CN-0001 | BK | GCS | PEDCO | 120 | CV | CN | 0001 | F0Z-709114 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 10 | 2 | 0 | 2 | 3.2.3.10.2 | Calculation Note for offsite flood control system | BK-GCS-PEDCO-120-CV-CN-0002 | BK-GCS-PEDCO-120-CV-CN-0002 | BK | GCS | PEDCO | 120 | CV | CN | 0002 | F0Z-709115 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 10 | 3 | 0 | 0 | 3.2.3.10.3 | Report
3 | 2 | 3 | 10 | 3 | 0 | 1 | 3.2.3.10.3 | Site Visit Report (Civil Work) - GCS | BK-GCS-PEDCO-110-CV-RT-0001 | BK-GCS-PEDCO-110-CV-RT-0001 | BK | GCS | PEDCO | 110 | CV | RT | 0001 | F0Z-709116 | AFC | IFC | 44647 | 44636 | 44645 | -11 | 9 | -2 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0 |  | D00 | IFC | T-0722 | 2022-03-13 | 1400/12/21 | 0 | 0 | 0 | BK-SUR-ENG-CIV-00-03622 | 2022-03-16 | 1400/12/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-452219 | 2022-03-16 | 1400/12/25 | 2022-03-25 | 1401/01/08 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0722 | 2022-03-13 | 1400/12/21 |  |  |  | BK-SUR-ENG-CIV-00-03622 | 2022-03-16 | 1400/12/25 | CM-C2 | [6 empty] | 1400-2294-452219 | 2022-03-16 | 1400/12/25 | 2022-03-25 | 1401/01/08 | RJ
3 | 2 | 3 | 10 | 4 | 0 | 0 | 3.2.3.10.4 | MTO
3 | 2 | 3 | 10 | 4 | 0 | 1 | 3.2.3.10 | MTO For Civil Work | BK-GCS-PEDCO-120-CV-MT-0001 | BK-GCS-PEDCO-120-CV-MT-0001 | BK | GCS | PEDCO | 120 | CV | MT | 0001 | F8Z-709117 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 0 | 0 | 0 | 3.2.3.11 | Structure
3 | 2 | 3 | 11 | 1 | 0 | 0 | 3.2.3.11.1 | Calculation
3 | 2 | 3 | 11 | 1 | 0 | 1 | 3.2.3.11.1 | Structural Calculation Note For Control Building | BK-GCS-PEDCO-120-ST-CN-0002 | BK-GCS-PEDCO-120-ST-CN-0002 | BK | GCS | PEDCO | 120 | ST | CN | 0002 | F0Z-709118 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 2 | 3.2.3.11.1 | Calculation Report for Gas Compressors Shelter | BK-GCS-PEDCO-120-ST-CN-0003 | BK-GCS-PEDCO-120-ST-CN-0003 | BK | GCS | PEDCO | 120 | ST | CN | 0003 | F0Z-709119 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 3 | 3.2.3.11.1 | Calculation Report for Extension of Existing Elect. Building | BK-GCS-PEDCO-120-ST-CN-0005 | BK-GCS-PEDCO-120-ST-CN-0005 | BK | GCS | PEDCO | 120 | ST | CN | 0005 | F0Z-709120 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 4 | 3.2.3.11.1 | Calculation Note for Gas Compressors Foundation | BK-GCS-PEDCO-120-ST-CN-0006 | BK-GCS-PEDCO-120-ST-CN-0006 | BK | GCS | PEDCO | 120 | ST | CN | 0006 | F0Z-709121 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 5 | 3.2.3.11.1 | Calculation Note for Tank Foundation (TK-2301 A/B) | BK-GCS-PEDCO-120-ST-CN-0007 | BK-GCS-PEDCO-120-ST-CN-0007 | BK | GCS | PEDCO | 120 | ST | CN | 0007 | F0Z-709122 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 6 | 3.2.3.11.1 | Calculation Note for Utility Shelter | BK-GCS-PEDCO-120-ST-CN-0008 | BK-GCS-PEDCO-120-ST-CN-0008 | BK | GCS | PEDCO | 120 | ST | CN | 0008 | F0Z-709123 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 7 | 3.2.3.11.1 | Calculation Note for Fire Water Pump Shelter | BK-GCS-PEDCO-120-ST-CN-0009 | BK-GCS-PEDCO-120-ST-CN-0009 | BK | GCS | PEDCO | 120 | ST | CN | 0009 | F0Z-709124 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 8 | 3.2.3.11.1 | Calculation Note for Foundation of Slug Catcher Drum (V-2104) | BK-GCS-PEDCO-120-ST-CN-0010 | BK-GCS-PEDCO-120-ST-CN-0010 | BK | GCS | PEDCO | 120 | ST | CN | 0010 | F0Z-709125 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 9 | 3.2.3.11.1 | Calculation Note for Foundation of Dehydration Package (PK-2101) | BK-GCS-PEDCO-120-ST-CN-0011 | BK-GCS-PEDCO-120-ST-CN-0011 | BK | GCS | PEDCO | 120 | ST | CN | 0011 | F0Z-709126 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 10 | 3.2.3.11.1 | Calculation Note for Close Drain Sump Pit (SU-2201 A) | BK-GCS-PEDCO-120-ST-CN-0012 | BK-GCS-PEDCO-120-ST-CN-0012 | BK | GCS | PEDCO | 120 | ST | CN | 0012 | F0Z-709127 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 11 | 3.2.3.11.1 | Calculation Note for Oily Water Sump Pit (SU-2201 B) | BK-GCS-PEDCO-120-ST-CN-0013 | BK-GCS-PEDCO-120-ST-CN-0013 | BK | GCS | PEDCO | 120 | ST | CN | 0013 | F0Z-709128 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 12 | 3.2.3.11.1 | Calculation Note For Compressor Area Main Sleepers | BK-GCS-PEDCO-120-ST-CN-0014 | BK-GCS-PEDCO-120-ST-CN-0014 | BK | GCS | PEDCO | 120 | ST | CN | 0014 | F0Z-709129 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 13 | 3.2.3.11.1 | Calculation Note For Flare Area Sleepers | BK-GCS-PEDCO-120-ST-CN-0015 | BK-GCS-PEDCO-120-ST-CN-0015 | BK | GCS | PEDCO | 120 | ST | CN | 0015 | F0Z-709130 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 14 | 3.2.3.11.1 | Calculation Note For Special Pipe Supports | BK-GCS-PEDCO-120-ST-CN-0016 | BK-GCS-PEDCO-120-ST-CN-0016 | BK | GCS | PEDCO | 120 | ST | CN | 0016 | F0Z-709131 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 15 | 3.2.3.11.1 | Calculation Note for1st Stage Air Coolers (AE-2101 A/B/C) | BK-GCS-PEDCO-120-ST-CN-0017 | BK-GCS-PEDCO-120-ST-CN-0017 | BK | GCS | PEDCO | 120 | ST | CN | 0017 | F0Z-709132 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 16 | 3.2.3.11.1 | Calculation Note for 2nd Stage Air Coolers (AE-2102 A/B/C) | BK-GCS-PEDCO-120-ST-CN-0018 | BK-GCS-PEDCO-120-ST-CN-0018 | BK | GCS | PEDCO | 120 | ST | CN | 0018 | F0Z-709133 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 17 | 3.2.3.11.1 | Calculation Note for Elevated Potable Water Tank (TK-2209) | BK-GCS-PEDCO-120-ST-CN-0019 | BK-GCS-PEDCO-120-ST-CN-0019 | BK | GCS | PEDCO | 120 | ST | CN | 0019 | F0Z-709134 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 18 | 3.2.3.11.1 | Calculation Note for Lean Glycol Storage Tank (TK-2102) | BK-GCS-PEDCO-120-ST-CN-0020 | BK-GCS-PEDCO-120-ST-CN-0020 | BK | GCS | PEDCO | 120 | ST | CN | 0020 | F0Z-709135 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 19 | 3.2.3.11.1 | Calculation Note for Nitrogen Package (PK-2204A/B) | BK-GCS-PEDCO-120-ST-CN-0021 | BK-GCS-PEDCO-120-ST-CN-0021 | BK | GCS | PEDCO | 120 | ST | CN | 0021 | F0Z-709136 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 20 | 3.2.3.11.1 | Calculation Note for Glycol Sump Pit (SU-2101) | BK-GCS-PEDCO-120-ST-CN-0022 | BK-GCS-PEDCO-120-ST-CN-0022 | BK | GCS | PEDCO | 120 | ST | CN | 0022 | F0Z-709137 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 21 | 3.2.3.11.1 | Calculation Note for Slug Pumps (P-2101A/B) | BK-GCS-PEDCO-120-ST-CN-0023 | BK-GCS-PEDCO-120-ST-CN-0023 | BK | GCS | PEDCO | 120 | ST | CN | 0023 | F0Z-709138 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 22 | 3.2.3.11.1 | Calculation Note for Utility Area Sleepers | BK-GCS-PEDCO-120-ST-CN-0024 | BK-GCS-PEDCO-120-ST-CN-0024 | BK | GCS | PEDCO | 120 | ST | CN | 0024 | F0Z-709139 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 23 | 3.2.3.11.1 | Calculation Note for Pipe rack | BK-GCS-PEDCO-120-ST-CN-0025 | BK-GCS-PEDCO-120-ST-CN-0025 | BK | GCS | PEDCO | 120 | ST | CN | 0025 | F0Z-709140 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 1 | 0 | 24 | 3.2.3.11.1 | Calculation Note for Chemical Injection and Storage Shelter | BK-GCS-PEDCO-120-ST-CN-0026 | BK-GCS-PEDCO-120-ST-CN-0026 | BK | GCS | PEDCO | 120 | ST | CN | 0026 | F0Z-709141 | AFD | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 0 | 3.2.3.11.2 | Drawing/Diagram
3 | 2 | 3 | 11 | 2 | 0 | 1 | 3.2.3.11.2 | Foundation Location Plan | BK-GCS-PEDCO-120-ST-DW-0003 | BK-GCS-PEDCO-120-ST-DW-0003 | BK | GCS | PEDCO | 120 | ST | DW | 0003 | F4Q-709142 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 2 | 3.2.3.11.2 | Foundation Drawing For 1st Stage Gas Compressor (C-2101A/B/C) | BK-GCS-PEDCO-120-ST-DW-0004 | BK-GCS-PEDCO-120-ST-DW-0004 | BK | GCS | PEDCO | 120 | ST | DW | 0004 | F4Q-709143 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 3 | 3.2.3.11.2 | Foundation Drawing For 2nd Stage Gas Compressor (C-2102A/B/C) | BK-GCS-PEDCO-120-ST-DW-0005 | BK-GCS-PEDCO-120-ST-DW-0005 | BK | GCS | PEDCO | 120 | ST | DW | 0005 | F4Q-709144 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 4 | 3.2.3.11.2 | Foundation Drawing For 1st Stage Air Coolers (AE-2101 A/B/C) | BK-GCS-PEDCO-120-ST-DW-0007 | BK-GCS-PEDCO-120-ST-DW-0007 | BK | GCS | PEDCO | 120 | ST | DW | 0007 | F4Q-709145 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 5 | 3.2.3.11.2 | Foundation Drawing For 2nd Stage Air Coolers (AE-2102 A/B/C) | BK-GCS-PEDCO-120-ST-DW-0008 | BK-GCS-PEDCO-120-ST-DW-0008 | BK | GCS | PEDCO | 120 | ST | DW | 0008 | F4Q-709146 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 6 | 3.2.3.11.2 | Foundation Drawing For Inlet Gas K.O. Drum (V-2105) | BK-GCS-PEDCO-120-ST-DW-0009 | BK-GCS-PEDCO-120-ST-DW-0009 | BK | GCS | PEDCO | 120 | ST | DW | 0009 | F4Q-709147 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 7 | 3.2.3.11.2 | Foundation Drawing For For 1st Stage G.C. Suction Drums (V-2101 A/B/C) | BK-GCS-PEDCO-120-ST-DW-0010 | BK-GCS-PEDCO-120-ST-DW-0010 | BK | GCS | PEDCO | 120 | ST | DW | 0010 | F4Q-709148 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 8 | 3.2.3.11.2 | Foundation Drawing For For 2nd Stage G.C. Suction Drums (V-2102 A/B/C) | BK-GCS-PEDCO-120-ST-DW-0011 | BK-GCS-PEDCO-120-ST-DW-0011 | BK | GCS | PEDCO | 120 | ST | DW | 0011 | F4Q-709149 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 9 | 3.2.3.11.2 | Foundation Drawing For 2nd Stage G.C. Discharge Drum (V-2103) | BK-GCS-PEDCO-120-ST-DW-0012 | BK-GCS-PEDCO-120-ST-DW-0012 | BK | GCS | PEDCO | 120 | ST | DW | 0012 | F4Q-709150 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 10 | 3.2.3.11.2 | Foundation Drawing For Fuel Oil Drum (V-2206) | BK-GCS-PEDCO-120-ST-DW-0013 | BK-GCS-PEDCO-120-ST-DW-0013 | BK | GCS | PEDCO | 120 | ST | DW | 0013 | F4Q-709151 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 11 | 3.2.3.11.2 | Foundation Drawing For Instrument Air Receiver (V-2203) | BK-GCS-PEDCO-120-ST-DW-0014 | BK-GCS-PEDCO-120-ST-DW-0014 | BK | GCS | PEDCO | 120 | ST | DW | 0014 | F4Q-709152 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 12 | 3.2.3.11.2 | Foundation Drawing For Elevated Potable Water Tank (TK-2209) | BK-GCS-PEDCO-120-ST-DW-0015 | BK-GCS-PEDCO-120-ST-DW-0015 | BK | GCS | PEDCO | 120 | ST | DW | 0015 | F4Q-709153 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 13 | 3.2.3.11.2 | Structural Drawing For Close Drain Sump Pit (SU-2201 A) | BK-GCS-PEDCO-120-ST-DW-0016 | BK-GCS-PEDCO-120-ST-DW-0016 | BK | GCS | PEDCO | 120 | ST | DW | 0016 | F4M-709154 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 14 | 3.2.3.11.2 | Foundation Drawing For Fuel Gas K.O Drum (V-2205) | BK-GCS-PEDCO-120-ST-DW-0017 | BK-GCS-PEDCO-120-ST-DW-0017 | BK | GCS | PEDCO | 120 | ST | DW | 0017 | F4Q-709155 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 15 | 3.2.3.11.2 | Foundation Drawing For Slug Catcher Drum (V-2104) | BK-GCS-PEDCO-120-ST-DW-0018 | BK-GCS-PEDCO-120-ST-DW-0018 | BK | GCS | PEDCO | 120 | ST | DW | 0018 | F4Q-709156 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 16 | 3.2.3.11.2 | Foundation Drawing For Degassing Drum (V-2106) | BK-GCS-PEDCO-120-ST-DW-0019 | BK-GCS-PEDCO-120-ST-DW-0019 | BK | GCS | PEDCO | 120 | ST | DW | 0019 | F4Q-709157 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 17 | 3.2.3.11.2 | Foundation Drawing For Nitrogen Receiver Drum (V-2204) | BK-GCS-PEDCO-120-ST-DW-0020 | BK-GCS-PEDCO-120-ST-DW-0020 | BK | GCS | PEDCO | 120 | ST | DW | 0020 | F4Q-709158 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 18 | 3.2.3.11.2 | Structural Drawing For Oily Water Sump Pit (SU-2201 B) | BK-GCS-PEDCO-120-ST-DW-0021 | BK-GCS-PEDCO-120-ST-DW-0021 | BK | GCS | PEDCO | 120 | ST | DW | 0021 | F4M-709159 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 19 | 3.2.3.11.2 | Foundation Drawing For Lean Glycol Storage Tank (TK-2102) | BK-GCS-PEDCO-120-ST-DW-0023 | BK-GCS-PEDCO-120-ST-DW-0023 | BK | GCS | PEDCO | 120 | ST | DW | 0023 | F4Q-709160 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 20 | 3.2.3.11.2 | Foundation Drawing For Fire Water Storage Tanks (TK-2301A/B) | BK-GCS-PEDCO-120-ST-DW-0024 | BK-GCS-PEDCO-120-ST-DW-0024 | BK | GCS | PEDCO | 120 | ST | DW | 0024 | F4Q-709161 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 21 | 3.2.3.11.2 | Foundation Drawing For Slug Storage Tank (TK-2101) | BK-GCS-PEDCO-120-ST-DW-0025 | BK-GCS-PEDCO-120-ST-DW-0025 | BK | GCS | PEDCO | 120 | ST | DW | 0025 | F4Q-709162 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 22 | 3.2.3.11.2 | Foundation Drawing For Dehydration Package (PK-2101) | BK-GCS-PEDCO-120-ST-DW-0026 | BK-GCS-PEDCO-120-ST-DW-0026 | BK | GCS | PEDCO | 120 | ST | DW | 0026 | F4Q-709163 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 23 | 3.2.3.11.2 | Foundation Drawing For Diesel Generator (PK-2206) | BK-GCS-PEDCO-120-ST-DW-0027 | BK-GCS-PEDCO-120-ST-DW-0027 | BK | GCS | PEDCO | 120 | ST | DW | 0027 | F4Q-709164 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 24 | 3.2.3.11.2 | Foundation Drawing For Instrument & Plant Air Package (PK-C-2203A/B) | BK-GCS-PEDCO-120-ST-DW-0028 | BK-GCS-PEDCO-120-ST-DW-0028 | BK | GCS | PEDCO | 120 | ST | DW | 0028 | F4Q-709165 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 25 | 3.2.3.11.2 | Foundation Drawing For Corrosion Inhibitor Injection Package (PK-2207) | BK-GCS-PEDCO-120-ST-DW-0029 | BK-GCS-PEDCO-120-ST-DW-0029 | BK | GCS | PEDCO | 120 | ST | DW | 0029 | F4Q-709166 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 26 | 3.2.3.11.2 | Foundation Drawing For Methanol Injection Package (PK-2208) | BK-GCS-PEDCO-120-ST-DW-0030 | BK-GCS-PEDCO-120-ST-DW-0030 | BK | GCS | PEDCO | 120 | ST | DW | 0030 | F4Q-709167 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 27 | 3.2.3.11.2 | Foundation Drawing For LP Flare Package (PK-2201) | BK-GCS-PEDCO-120-ST-DW-0031 | BK-GCS-PEDCO-120-ST-DW-0031 | BK | GCS | PEDCO | 120 | ST | DW | 0031 | F4Q-709168 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 28 | 3.2.3.11.2 | Foundation Drawing For Nitrogen Package (PK-2204A/B) | BK-GCS-PEDCO-120-ST-DW-0032 | BK-GCS-PEDCO-120-ST-DW-0032 | BK | GCS | PEDCO | 120 | ST | DW | 0032 | F4Q-709169 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 29 | 3.2.3.11.2 | Dike Wall Drawing For Lean Glycol Storage Tank (TK-2102) | BK-GCS-PEDCO-120-ST-DW-0033 | BK-GCS-PEDCO-120-ST-DW-0033 | BK | GCS | PEDCO | 120 | ST | DW | 0033 | F4M-709170 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 30 | 3.2.3.11.2 | Dike Wall Drawing For Slug Storage Tank (TK-2101) | BK-GCS-PEDCO-120-ST-DW-0034 | BK-GCS-PEDCO-120-ST-DW-0034 | BK | GCS | PEDCO | 120 | ST | DW | 0034 | F4M-709171 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 31 | 3.2.3.11.2 | Foundation Drawing For Glycol Sump Pit (SU-2101) | BK-GCS-PEDCO-120-ST-DW-0035 | BK-GCS-PEDCO-120-ST-DW-0035 | BK | GCS | PEDCO | 120 | ST | DW | 0035 | F4Q-709172 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 32 | 3.2.3.11.2 | Foundation Drawing For Glycol Transfer Pumps (P-2103 A/B) | BK-GCS-PEDCO-120-ST-DW-0036 | BK-GCS-PEDCO-120-ST-DW-0036 | BK | GCS | PEDCO | 120 | ST | DW | 0036 | F4Q-709173 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 33 | 3.2.3.11.2 | Foundation Drawing For Glycol Manual Pump (P-2102) | BK-GCS-PEDCO-120-ST-DW-0037 | BK-GCS-PEDCO-120-ST-DW-0037 | BK | GCS | PEDCO | 120 | ST | DW | 0037 | F4Q-709174 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 34 | 3.2.3.11.2 | Foundation Drawing For Fire Water Jockey Pumps (P-2302A/B) | BK-GCS-PEDCO-120-ST-DW-0038 | BK-GCS-PEDCO-120-ST-DW-0038 | BK | GCS | PEDCO | 120 | ST | DW | 0038 | F4Q-709175 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 35 | 3.2.3.11.2 | Foundation Drawing For Fire Water Electrical Pump (P-2301 A) | BK-GCS-PEDCO-120-ST-DW-0039 | BK-GCS-PEDCO-120-ST-DW-0039 | BK | GCS | PEDCO | 120 | ST | DW | 0039 | F4Q-709176 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 36 | 3.2.3.11.2 | Foundation Drawing For Fire Water Diesel Pumps (P-2302 B/C) | BK-GCS-PEDCO-120-ST-DW-0040 | BK-GCS-PEDCO-120-ST-DW-0040 | BK | GCS | PEDCO | 120 | ST | DW | 0040 | F4Q-709177 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 37 | 3.2.3.11.2 | Foundation Drawing For Potable Water Pump (P-2209) | BK-GCS-PEDCO-120-ST-DW-0041 | BK-GCS-PEDCO-120-ST-DW-0041 | BK | GCS | PEDCO | 120 | ST | DW | 0041 | F4Q-709178 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 38 | 3.2.3.11.2 | Foundation Drawing For Fuel Oil Pump (P-2206) | BK-GCS-PEDCO-120-ST-DW-0042 | BK-GCS-PEDCO-120-ST-DW-0042 | BK | GCS | PEDCO | 120 | ST | DW | 0042 | F4Q-709179 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 39 | 3.2.3.11.2 | Foundation Drawing For Slug Pumps (P-2101A/B) | BK-GCS-PEDCO-120-ST-DW-0043 | BK-GCS-PEDCO-120-ST-DW-0043 | BK | GCS | PEDCO | 120 | ST | DW | 0043 | F4Q-709180 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 40 | 3.2.3.11.2 | Foundation Drawing For Compressor Area Main Sleepers | BK-GCS-PEDCO-120-ST-DW-0044 | BK-GCS-PEDCO-120-ST-DW-0044 | BK | GCS | PEDCO | 120 | ST | DW | 0044 | F4Q-709181 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 41 | 3.2.3.11.2 | Foundation Drawing For Compressor Area Secondary Sleepers | BK-GCS-PEDCO-120-ST-DW-0045 | BK-GCS-PEDCO-120-ST-DW-0045 | BK | GCS | PEDCO | 120 | ST | DW | 0045 | F4Q-709182 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 42 | 3.2.3.11.2 | Foundation Drawing For Utility Area Sleepers | BK-GCS-PEDCO-120-ST-DW-0046 | BK-GCS-PEDCO-120-ST-DW-0046 | BK | GCS | PEDCO | 120 | ST | DW | 0046 | F4Q-709183 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 43 | 3.2.3.11.2 | Foundation Drawing For Flare Area Sleepers | BK-GCS-PEDCO-120-ST-DW-0047 | BK-GCS-PEDCO-120-ST-DW-0047 | BK | GCS | PEDCO | 120 | ST | DW | 0047 | F4Q-709184 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 44 | 3.2.3.11.2 | Foundation Drawing For Transformer & Shelters | BK-GCS-PEDCO-120-ST-DW-0048 | BK-GCS-PEDCO-120-ST-DW-0048 | BK | GCS | PEDCO | 120 | ST | DW | 0048 | F4Q-709185 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 45 | 3.2.3.11.2 | Foundation Drawing For Pipe Supports | BK-GCS-PEDCO-120-ST-DW-0049 | BK-GCS-PEDCO-120-ST-DW-0049 | BK | GCS | PEDCO | 120 | ST | DW | 0049 | F4Q-709186 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 46 | 3.2.3.11.2 | Structural Drawing For Special Pipe Supports | BK-GCS-PEDCO-120-ST-DW-0050 | BK-GCS-PEDCO-120-ST-DW-0050 | BK | GCS | PEDCO | 120 | ST | DW | 0050 | F4M-709187 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 47 | 3.2.3.11.2 | Culvert Detail Drawing | BK-GCS-PEDCO-120-ST-DW-0051 | BK-GCS-PEDCO-120-ST-DW-0051 | BK | GCS | PEDCO | 120 | ST | DW | 0051 | F4M-709188 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 48 | 3.2.3.11.2 | Foundation Drawing For Access Platforms | BK-GCS-PEDCO-120-ST-DW-0052 | BK-GCS-PEDCO-120-ST-DW-0052 | BK | GCS | PEDCO | 120 | ST | DW | 0052 | F4Q-709189 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 49 | 3.2.3.11.2 | Structural Drawing For Access Platforms | BK-GCS-PEDCO-120-ST-DW-0053 | BK-GCS-PEDCO-120-ST-DW-0053 | BK | GCS | PEDCO | 120 | ST | DW | 0053 | F4M-709190 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 50 | 3.2.3.11.2 | Foundation Drawing For Pipe rack | BK-GCS-PEDCO-120-ST-DW-0054 | BK-GCS-PEDCO-120-ST-DW-0054 | BK | GCS | PEDCO | 120 | ST | DW | 0054 | F4Q-709191 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 51 | 3.2.3.11.2 | Structural Drawing For Pipe rack | BK-GCS-PEDCO-120-ST-DW-0055 | BK-GCS-PEDCO-120-ST-DW-0055 | BK | GCS | PEDCO | 120 | ST | DW | 0055 | F4M-709192 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 52 | 3.2.3.11.2 | Foundation Drawing For Lighting Poles and Towers | BK-GCS-PEDCO-120-ST-DW-0056 | BK-GCS-PEDCO-120-ST-DW-0056 | BK | GCS | PEDCO | 120 | ST | DW | 0056 | F4Q-709193 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 53 | 3.2.3.11.2 | Foundation Drawing For Chemical Injection and Storage Shelter | BK-GCS-PEDCO-120-ST-DW-0057 | BK-GCS-PEDCO-120-ST-DW-0057 | BK | GCS | PEDCO | 120 | ST | DW | 0057 | F4Q-709194 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 54 | 3.2.3.11.2 | Structural Drawing For Chemical Injection and Storage Shelter | BK-GCS-PEDCO-120-ST-DW-0058 | BK-GCS-PEDCO-120-ST-DW-0058 | BK | GCS | PEDCO | 120 | ST | DW | 0058 | F4M-709195 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 55 | 3.2.3.11.2 | Foundation Drawing For Gas Compressor Shelter | BK-GCS-PEDCO-120-ST-DW-0059 | BK-GCS-PEDCO-120-ST-DW-0059 | BK | GCS | PEDCO | 120 | ST | DW | 0059 | F4Q-709196 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 56 | 3.2.3.11.2 | Structural Drawing For Gas Compressor Shelter | BK-GCS-PEDCO-120-ST-DW-0060 | BK-GCS-PEDCO-120-ST-DW-0060 | BK | GCS | PEDCO | 120 | ST | DW | 0060 | F4M-709197 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 57 | 3.2.3.11.2 | Foundation Drawing For Control Building | BK-GCS-PEDCO-120-ST-DW-0061 | BK-GCS-PEDCO-120-ST-DW-0061 | BK | GCS | PEDCO | 120 | ST | DW | 0061 | F4Q-709198 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 58 | 3.2.3.11.2 | Structural Drawing For Control Building | BK-GCS-PEDCO-120-ST-DW-0062 | BK-GCS-PEDCO-120-ST-DW-0062 | BK | GCS | PEDCO | 120 | ST | DW | 0062 | F4M-709199 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 59 | 3.2.3.11.2 | Foundation Drawing For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-ST-DW-0063 | BK-GCS-PEDCO-120-ST-DW-0063 | BK | GCS | PEDCO | 120 | ST | DW | 0063 | F4Q-709200 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 60 | 3.2.3.11.2 | Structural Drawing For Extension of Existing Elect. Building | BK-GCS-PEDCO-120-ST-DW-0064 | BK-GCS-PEDCO-120-ST-DW-0064 | BK | GCS | PEDCO | 120 | ST | DW | 0064 | F4M-709201 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 61 | 3.2.3.11.2 | Foundation Drawing For Fire Water Pump Shelter | BK-GCS-PEDCO-120-ST-DW-0065 | BK-GCS-PEDCO-120-ST-DW-0065 | BK | GCS | PEDCO | 120 | ST | DW | 0065 | F4Q-709202 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 62 | 3.2.3.11.2 | Structural Drawing For Fire Water Pump Shelter | BK-GCS-PEDCO-120-ST-DW-0066 | BK-GCS-PEDCO-120-ST-DW-0066 | BK | GCS | PEDCO | 120 | ST | DW | 0066 | F4M-709203 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 63 | 3.2.3.11.2 | Foundation Drawing For Utility Shelter | BK-GCS-PEDCO-120-ST-DW-0067 | BK-GCS-PEDCO-120-ST-DW-0067 | BK | GCS | PEDCO | 120 | ST | DW | 0067 | F4Q-709204 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 64 | 3.2.3.11.2 | Structural Drawing For Utility Shelter | BK-GCS-PEDCO-120-ST-DW-0068 | BK-GCS-PEDCO-120-ST-DW-0068 | BK | GCS | PEDCO | 120 | ST | DW | 0068 | F4M-709205 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 65 | 3.2.3.11.2 | Foundation Drawing For Air Dryer Packages (PK-D-2203A/B) | BK-GCS-PEDCO-120-ST-DW-0069 | BK-GCS-PEDCO-120-ST-DW-0069 | BK | GCS | PEDCO | 120 | ST | DW | 0069 | F4Q-709206 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 66 | 3.2.3.11.2 | Foundation Drawing For Pig Launcher (PL-3101) | BK-GCS-PEDCO-120-ST-DW-0070 | BK-GCS-PEDCO-120-ST-DW-0070 | BK | GCS | PEDCO | 120 | ST | DW | 0070 | F4Q-709207 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 67 | 3.2.3.11.2 | Foundation Drawing For Ignition Package | BK-GCS-PEDCO-120-ST-DW-0071 | BK-GCS-PEDCO-120-ST-DW-0071 | BK | GCS | PEDCO | 120 | ST | DW | 0071 | F4Q-709208 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 2 | 0 | 68 | 3.2.3.11.2 | Foundation Drawing For Fire Shed | BK-GCS-PEDCO-120-ST-DW-0072 | BK-GCS-PEDCO-120-ST-DW-0072 | BK | GCS | PEDCO | 120 | ST | DW | 0072 | F4Q-709209 | AFC | IFC | 2022-02-13 | 2022-02-03 | 2022-02-13 | -10 | 10 | 0 | IFA | 2022-03-21 | 2022-03-12 | 2022-03-14 | -9 | 2 | -7 | IFA | 2022-04-27 | 2022-04-17 | 2022-04-19 | -10 | 2 | -8 | IFA | 2022-06-07 | 0 | 0 | -44719 | 0 | -44719 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-07 | 0 |  | D03 | IFA | T-1000 | 2022-05-24 | 1401/03/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-ST-DW-0072_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0072_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0522 | 2022-01-30 | 1400/11/10 |  |  |  | BK-SUR-ENG-STR-00-02949 | 2022-02-06 | 1400/11/17 | C4-RJ | [6 empty] | 1400-2294-395081 | 2022-02-03 | 1400/11/14 | 2022-02-13 | 1400/11/13 | RJ | [10 empty] | D01 | IFA | T-0689 | 2022-03-07 | 1400/12/16 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-ST-DW-0072_D00 | [5 empty] | 1400-2294-445295 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0072_D00 | [9 empty] | D02 | IFA | T-0812 | 2022-04-13 | 1401/01/24 |  |  |  | BK-SUR-ENG-STR-01-03988 | 2022-04-20 | 1401/01/31 | CM-C3 | [6 empty] | 1401-2294-27199 | 2022-04-17 | 1401/01/28 | 2022-04-19 | 1401/01/30 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0072_D01 | [9 empty] | D03 | IFA | T-1000 | 2022-05-24 | 1401/03/03 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-ST-DW-0072_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0072_D02
3 | 2 | 3 | 11 | 2 | 0 | 69 | 3.2.3.11.2 | Structural Drawing For Fire Shed | BK-GCS-PEDCO-120-ST-DW-0073 | BK-GCS-PEDCO-120-ST-DW-0073 | BK | GCS | PEDCO | 120 | ST | DW | 0073 | F4M-709210 | AFC | IFC | 2022-02-13 | 2022-02-03 | 2022-02-13 | -10 | 10 | 0 | IFA | 2022-03-21 | 2022-03-12 | 2022-03-14 | -9 | 2 | -7 | IFA | 2022-04-27 | 2022-04-17 | 2022-04-19 | -10 | 2 | -8 | IFA | 2022-06-07 | 0 | 0 | -44719 | 0 | -44719 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-07 | 0 |  | D03 | IFA | T-1000 | 2022-05-24 | 1401/03/03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GCS-PEDCO-120-ST-DW-0073_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0073_D02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0522 | 2022-01-30 | 1400/11/10 |  |  |  | BK-SUR-ENG-STR-00-02949 | 2022-02-06 | 1400/11/17 | C4-RJ | [6 empty] | 1400-2294-395081 | 2022-02-03 | 1400/11/14 | 2022-02-13 | 1400/11/13 | RJ | [10 empty] | D01 | IFA | T-0689 | 2022-03-07 | 1400/12/16 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-ST-DW-0073_D00 | [5 empty] | 1400-2294-445295 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0073_D00 | [9 empty] | D02 | IFA | T-0812 | 2022-04-13 | 1401/01/24 |  |  |  | BK-SUR-ENG-STR-01-03988 | 2022-04-20 | 1401/01/31 | CM-C3 | [6 empty] | 1401-2294-27199 | 2022-04-17 | 1401/01/28 | 2022-04-19 | 1401/01/30 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0073_D01 | [9 empty] | D03 | IFA | T-1000 | 2022-05-24 | 1401/03/03 | [7 empty] | PEDCO-CRS-BK-GCS-PEDCO-120-ST-DW-0073_D02 | [11 empty] | NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0073_D02
3 | 2 | 3 | 11 | 2 | 0 | 70 | 3.2.3.11.2 | Structural Drawing For Shelter of Transformers | BK-GCS-PEDCO-120-ST-DW-0074 | BK-GCS-PEDCO-120-ST-DW-0074 | BK | GCS | PEDCO | 120 | ST | DW | 0074 | F4M-709211 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 3 | 0 | 0 | 3.2.3.11.3 | MTO
3 | 2 | 3 | 11 | 3 | 0 | 1 | 3.2.3.11 | MTO For Steel Structures Works | BK-GCS-PEDCO-120-ST-MT-0001 | BK-GCS-PEDCO-120-ST-MT-0001 | BK | GCS | PEDCO | 120 | ST | MT | 0001 | F8Z-709212 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 11 | 3 | 0 | 2 | 3.2.3.11 | MTO For Structural Concrete Works | BK-GCS-PEDCO-120-ST-MT-0002 | BK-GCS-PEDCO-120-ST-MT-0002 | BK | GCS | PEDCO | 120 | ST | MT | 0002 | F8Z-709213 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 3 | 12 | 0 | 0 | 0 | 3.2.3.12 | Survey (Topography) & Geotechnic/Geoelectric
3 | 2 | 3 | 12 | 1 | 0 | 0 | 3.2.3.12.1 | Survey (Topography)
3 | 2 | 3 | 12 | 1 | 0 | 1 | 3.2.3.12.1 | Topographical Map | BK-GCS-PEDCO-120-SU-MP-0001 | BK-GCS-PEDCO-120-SU-MP-0001 | BK | GCS | PEDCO | 120 | SU | MP | 0001 | F0A-709214 | IFI | IFI | 44695 | 44689 | 44692 | -6 | 3 | -3 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-04-30 | 2022-04-30 |  | D00 | IFI | T-0881 | 2022-04-30 | 1401/02/10 | T-0881 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-CIV-01-04279 | 2022-05-15 | 1401/02/25 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-52724 | 2022-05-08 | 1401/02/18 | 2022-05-11 | 1401/02/21 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0881 | 2022-04-30 | 1401/02/10 | T-0881 | 2022-04-30 | 1401/02/10 | BK-SUR-ENG-CIV-01-04279 | 2022-05-15 | 1401/02/25 | CM-C2 | [6 empty] | 1401-2294-52724 | 2022-05-08 | 1401/02/18 | 2022-05-11 | 1401/02/21 | AP
3 | 2 | 3 | 12 | 2 | 0 | 0 | 3.2.3.12.2 | Geotechnic
3 | 2 | 3 | 12 | 2 | 1 | 0 | 3.2.12.2.1 | Procedure/Plan
3 | 2 | 3 | 12 | 2 | 1 | 1 | 3.2.3.12.2.1.1 | Geotechnical Investigation Plan for Compressor Station | BK-GCS-PEDCO-120-GT-PR-0001 | BK-GCS-PEDCO-120-GT-PR-0001 | BK | GCS | PEDCO | 120 | GT | PR | 0001 | F0Z-709215 | AFC | IFC | 44563 | 44557 | 44559 | -6 | 2 | -4 | IFA | 44584 | 44573 | 44576 | -11 | 3 | -8 | AFC | 44593 | 44632 | 44634 | 39 | 2 | 41 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-19 | 2022-01-18 |  | D02 | AFC | T-0479 | 2022-01-18 | 1400/10/28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PEDCO-CRS-BK-GNRAL-PEDCO-120-GT-PR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445100 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-120-GT-PR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0361 | 2021-12-19 | 1400/09/28 |  |  |  | BK-SUR-ENG-CIV-00-02384 | 2021-12-20 | 1400/09/29 | CM-C2 | [6 empty] | 1400-2294-338029 | 2021-12-27 | 1400/10/06 | 2021-12-29 | 1400/10/08 | CM | [10 empty] | D01 | IFA | T-0442 | 2022-01-09 | 1400/10/19 |  |  |  | BK-SUR-ENG-GEN-00-02686 | 2022-01-15 | 1400/10/25 | CM-C2 | PEDCO-CRS-BK-GNRAL-PEDCO-120-GT-PR-0001_D00 | [5 empty] | 1400-2294-362348 | 2022-01-12 | 1400/10/22 | 2022-01-15 | 1400/10/25 | AP | NISOC-CRS-BK-GNRAL-PEDCO-120-GT-PR-0001_D00 | [9 empty] | D02 | AFC | T-0479 | 2022-01-18 | 1400/10/28 | [7 empty] | PEDCO-CRS-BK-GNRAL-PEDCO-120-GT-PR-0001_D01 | [5 empty] | 1400-2294-445100 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | AP | NISOC-CRS-BK-GNRAL-PEDCO-120-GT-PR-0001_D01
3 | 2 | 3 | 12 | 2 | 2 | 0 | 3.2.12.2.2 | Report
3 | 2 | 3 | 12 | 2 | 2 | 1 | 3.2.3.12.2.2.1 | Geotechnical Investigation Report for Compressor Station | BK-GCS-PEDCO-120-GT-RT-0001 | BK-GCS-PEDCO-120-GT-RT-0001 | BK | GCS | PEDCO | 120 | GT | RT | 0001 | F0Z-709216 | AFC | IFC | 44712 | 0 | 0 | -44712 | 0 | -44712 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-17 | 0 |  | D00 | IFC | T-0963 | 2022-05-17 | 1401/02/27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0963 | 2022-05-17 | 1401/02/27
3 | 2 | 4 | 0 | 0 | 0 | 0 | 3.2.4 | Procurement Engineering
3 | 2 | 4 | 1 | 0 | 0 | 0 | 3.2.4.1 | Mechanical
3 | 2 | 4 | 1 | 1 | 0 | 0 | 3.2.4.1.1 | Gas Compressors
3 | 2 | 4 | 1 | 1 | 1 | 0 | 3.2.1.1.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 1 | 1 | 1 | 3.2.4.1.1.1.1 | PMR For Gas Compressors | BK-GCS-PEDCO-120-ME-MR-0001 | BK-GCS-PEDCO-120-ME-MR-0001 | BK | GCS | PEDCO | 120 | ME | MR | 0001 | F0Z-709217 | IFI | IFC | 44542 | 44543 | 44545 | 1 | 2 | 3 | IFI | 44579 | 44211 | 44591 | -368 | 380 | 12 | IFI | 44619 | 44621 | 44625 | 2 | 4 | 6 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-11-28 | 2022-02-13 |  | D02 | IFI | T-0582 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03353 | 2022-03-05 | 1400/12/14 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430723 | 2022-03-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFC | T-0277 | 2021-11-28 | 1400/09/07 |  |  |  | BK-SUR-ENG-MEC-00-02300 | 2021-12-15 | 1400/09/24 | AP | [6 empty] | 1400-2294-315112 | 2021-12-13 | 1400/09/21 | 2021-12-15 | 1400/09/24 | CM | [10 empty] | D01 | IFI | T-0429 | 2022-01-04 | 1400/10/14 |  |  |  | BK-SUR-ENG-MEC-00-02803 | 2022-01-25 | 1400/11/05 | CM-C2 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D00 | [5 empty] | 1400-2294-365715 | 2021-01-15 | 1400/10/26 | 2022-01-30 | 1400/11/10 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D00 | [9 empty] | D02 | IFI | T-0582 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-MEC-00-03353 | 2022-03-05 | 1400/12/14 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D01 | [5 empty] | 1400-2294-430723 | 2022-03-01 | 1400/12/10 | 2022-03-05 | 1400/12/14 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0001_D01
3 | 2 | 4 | 1 | 1 | 2 | 0 | 3.2.1.1.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 1 | 2 | 1 | 3.2.4.1.1.2.1 | TBE For Gas Compressors | BK-GCS-PEDCO-120-ME-TB-0001 | BK-GCS-PEDCO-120-ME-TB-0001 | BK | GCS | PEDCO | 120 | ME | TB | 0001 | F0Z-709218 | IFI | IFI | 44608 | 44615 | 44619 | 7 | 4 | 11 | IFI | 44639 | 44682 | 44688 | 43 | 6 | 49 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-02-02 | 2022-03-05 |  | D01 | IFI | T-0676 | 2022-03-05 | 1400/12/14 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03608 | 2022-03-15 | 1400/12/24 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-TB-0001_D00 | 0 | 0 | 0 | 0 | 0 | 1401-2294-47400 | 2022-05-01 | 1401/02/11 | 2022-05-02 | 1401/02/12 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-TB-0001_D00 | 1401-2294-47400 | 2022-05-01 | 1401/02/11 | 2022-05-07 | 1401/02/17 | CM | 0 | 0 |  | D00 | IFI | T-0540 | 2022-02-02 | 1400/11/13 |  |  |  | BK-SUR-ENG-ROE-00-03258 | 2022-02-27 | 1400/12/08 | CM-C3 | [6 empty] | 1400-2294-421986 | 2022-02-23 | 1400/12/04 | 2022-02-27 | 1400/12/08 | CM | [10 empty] | D01 | IFI | T-0676 | 2022-03-05 | 1400/12/14 |  |  |  | BK-SUR-ENG-MEC-00-03608 | 2022-03-15 | 1400/12/24 | CM-C3 | PEDCO-CRS-BK-GCS-PEDCO-120-ME-TB-0001_D00 | [5 empty] | 1401-2294-47400 | 2022-05-01 | 1401/02/11 | 2022-05-02 | 1401/02/12 | CM | NISOC-CRS-BK-GCS-PEDCO-120-ME-TB-0001_D00 | 1401-2294-47400 | 2022-05-01 | 1401/02/11 | 2022-05-07 | 1401/02/17 | CM
3 | 2 | 4 | 1 | 2 | 0 | 0 | 3.2.4.1.2 | Gas Dehydration Package
3 | 2 | 4 | 1 | 2 | 1 | 0 | 3.2.1.2.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 2 | 1 | 1 | 3.2.4.1.2.1.1 | PMR For Gas Dehydration Package | BK-GCS-PEDCO-120-ME-MR-0002 | BK-GCS-PEDCO-120-ME-MR-0002 | BK | GCS | PEDCO | 120 | ME | MR | 0002 | F0Z-709219 | IFI | IFI | 44563 | 44557 | 44566 | -6 | 9 | 3 | IFI | 44601 | 44632 | 44634 | 31 | 2 | 33 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-19 | 2022-01-26 |  | D01 | IFI | T-0512 | 2022-01-26 | 1400/11/06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-445084 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0002_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0362 | 2021-12-19 | 1400/09/28 | [13 empty] | 1400-2294-336397 | 2021-12-27 | 1400/10/06 | 2022-01-05 | 1400/10/15 | CM | [10 empty] | D01 | IFI | T-0512 | 2022-01-26 | 1400/11/06 | [13 empty] | 1400-2294-445084 | 2022-03-12 | 1400/12/21 | 2022-03-14 | 1400/12/23 | RJ | NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0002_D00
3 | 2 | 4 | 1 | 2 | 2 | 0 | 3.2.1.2.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 2 | 2 | 1 | 3.2.4.1.2.2.1 | TBE For Gas Dehydration Package | BK-GCS-PEDCO-120-ME-TB-0002 | BK-GCS-PEDCO-120-ME-TB-0002 | BK | GCS | PEDCO | 120 | ME | TB | 0002 | F0Z-709220 | IFI | IFI | 44662 | 44679 | 44682 | 17 | 3 | 20 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-03-28 | 2022-03-28 |  | D00 | IFI | T-0759 | 2022-03-28 | 1401/01/08 | 0 | 0 | 0 | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | 1401/02/05 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-43107 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0759 | 2022-03-28 | 1401/01/08 |  |  |  | BK-SUR-ENG-MEC-01-04047 | 2022-04-25 | 1401/02/05 | CM-C3 | [6 empty] | 1401-2294-43107 | 2022-04-28 | 1401/02/08 | 2022-05-01 | 1401/02/11 | CM
3 | 2 | 4 | 1 | 3 | 0 | 0 | 3.2.4.1.3 | Pressure Vessels
3 | 2 | 4 | 1 | 3 | 1 | 0 | 3.2.1.3.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 3 | 1 | 1 | 3.2.4.1.3.1.1 | PMR For Pressure Vessels | BK-GCS-PEDCO-120-ME-MR-0003 | BK-GCS-PEDCO-120-ME-MR-0003 | BK | GCS | PEDCO | 120 | ME | MR | 0003 | F0Z-709221 | IFI | IFI | 44628 | 44627 | 44629 | -1 | 2 | 1 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-02-22 |  | D00 | IFI | T-0623 | 2022-02-22 | 1400/12/03 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03301 | 2022-03-02 | 1400/12/11 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-438942 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0623 | 2022-02-22 | 1400/12/03 |  |  |  | BK-SUR-ENG-MEC-00-03301 | 2022-03-02 | 1400/12/11 | CM-C3 | [6 empty] | 1400-2294-438942 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | RJ
3 | 2 | 4 | 1 | 3 | 2 | 0 | 3.2.1.3.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 3 | 2 | 1 | 3.2.4.1.3.2.1 | TBE For Pressure Vessels | BK-GCS-PEDCO-120-ME-TB-0003 | BK-GCS-PEDCO-120-ME-TB-0003 | BK | GCS | PEDCO | 120 | ME | TB | 0003 | F0Z-709222 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 1 | 4 | 0 | 0 | 3.2.4.1.4 | Gas Air Coolers
3 | 2 | 4 | 1 | 4 | 1 | 0 | 3.2.1.4.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 4 | 1 | 1 | 3.2.4.1.4.1.1 | PMR For Gas Air Coolers | BK-GCS-PEDCO-120-ME-MR-0004 | BK-GCS-PEDCO-120-ME-MR-0004 | BK | GCS | PEDCO | 120 | ME | MR | 0004 | F0Z-709223 | IFI | IFI | 44625 | 44627 | 44629 | 2 | 2 | 4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-02-19 |  | D00 | IFI | T-0603 | 2022-02-19 | 1400/11/30 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03257 | 2022-02-27 | 1400/12/08 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-438865 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0603 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-MEC-00-03257 | 2022-02-27 | 1400/12/08 | CM-C2 | [6 empty] | 1400-2294-438865 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | RJ
3 | 2 | 4 | 1 | 4 | 2 | 0 | 3.2.1.4.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 4 | 2 | 1 | 3.2.4.1.4.2.1 | TBE For Gas Air Coolers | BK-GCS-PEDCO-120-ME-TB-0004 | BK-GCS-PEDCO-120-ME-TB-0004 | BK | GCS | PEDCO | 120 | ME | TB | 0004 | F0Z-709224 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 1 | 5 | 0 | 0 | 3.2.4.1.5 | Storage Tanks
3 | 2 | 4 | 1 | 5 | 1 | 0 | 3.2.1.5.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 5 | 1 | 1 | 3.2.4.1.5.1.1 | PMR For Storage Tanks | BK-GCS-PEDCO-120-ME-MR-0005 | BK-GCS-PEDCO-120-ME-MR-0005 | BK | GCS | PEDCO | 120 | ME | MR | 0005 | F0Z-709225 | IFI | IFI | 44613 | 44621 | 44625 | 8 | 4 | 12 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-02-07 |  | D00 | IFI | T-0562 | 2022-02-07 | 1400/11/18 | 0 | 0 | 0 | BK-SUR-ENG-000-00-03256 | 2022-02-27 | 1400/12/08 | CM-C3 | 0 | BK-SUR-ENG-MEC-00-03351 | 2022-03-05 | 1400/12/15 | CM-C3 | 0 | 1400-2294-430776 | 2022-03-01 | 1400/12/14 | 2022-03-05 | 1400/12/14 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0562 | 2022-02-07 | 1400/11/18 |  |  |  | BK-SUR-ENG-000-00-03256 | 2022-02-27 | 1400/12/08 | CM-C3 |  | BK-SUR-ENG-MEC-00-03351 | 2022-03-05 | 1400/12/15 | CM-C3 |  | 1400-2294-430776 | 2022-03-01 | 1400/12/14 | 2022-03-05 | 1400/12/14 | RJ
3 | 2 | 4 | 1 | 5 | 2 | 0 | 3.2.1.5.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 5 | 2 | 1 | 3.2.4.1.5.2.1 | TBE For Storage Tanks | BK-GCS-PEDCO-120-ME-TB-0005 | BK-GCS-PEDCO-120-ME-TB-0005 | BK | GCS | PEDCO | 120 | ME | TB | 0005 | F0Z-709226 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 1 | 6 | 0 | 0 | 3.2.4.1.6 | Instrument/Plant Air & Nitrogen Packages
3 | 2 | 4 | 1 | 6 | 1 | 0 | 3.2.1.6.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 6 | 1 | 1 | 3.2.4.1.6.1.1 | PMR For Instrument/Plant Air & Nitrogen Packages | BK-GCS-PEDCO-120-ME-MR-0006 | BK-GCS-PEDCO-120-ME-MR-0006 | BK | GCS | PEDCO | 120 | ME | MR | 0006 | F0Z-709227 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 1 | 6 | 2 | 0 | 3.2.1.6.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 6 | 2 | 1 | 3.2.4.1.6.2.1 | TBE For Instrument/Plant Air & Nitrogen Packages | BK-GCS-PEDCO-120-ME-TB-0006 | BK-GCS-PEDCO-120-ME-TB-0006 | BK | GCS | PEDCO | 120 | ME | TB | 0006 | F0Z-709228 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 1 | 7 | 0 | 0 | 3.2.4.1.7 | Chemical Injection Packages
3 | 2 | 4 | 1 | 7 | 1 | 0 | 3.2.1.7.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 7 | 1 | 1 | 3.2.4.1.7.1.1 | PMR For Chemical Injection Packages | BK-GCS-PEDCO-120-ME-MR-0008 | BK-GCS-PEDCO-120-ME-MR-0008 | BK | GCS | PEDCO | 120 | ME | MR | 0008 | F0Z-709229 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 1 | 7 | 2 | 0 | 3.2.1.7.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 7 | 2 | 1 | 3.2.4.1.7.2.1 | TBE For Chemical Injection Packages | BK-GCS-PEDCO-120-ME-TB-0008 | BK-GCS-PEDCO-120-ME-TB-0008 | BK | GCS | PEDCO | 120 | ME | TB | 0008 | F0Z-709230 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 1 | 8 | 0 | 0 | 3.2.4.1.8 | Pumps - Process Services
3 | 2 | 4 | 1 | 8 | 1 | 0 | 3.2.1.8.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 8 | 1 | 1 | 3.2.4.1.8.1.1 | PMR For Centrifugal Pumps For Process Services | BK-GCS-PEDCO-120-ME-MR-0009 | BK-GCS-PEDCO-120-ME-MR-0009 | BK | GCS | PEDCO | 120 | ME | MR | 0009 | F0Z-709231 | IFI | IFI | 44619 | 44621 | 44644 | 2 | 23 | 25 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-02-13 |  | D00 | IFI | T-0588 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03354 | 2022-03-05 | 1400/12/14 | CM-C3 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-430725 | 2022-03-01 | 1400/12/10 | 2022-03-24 | 1400/12/05 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0588 | 2022-02-13 | 1400/11/24 |  |  |  | BK-SUR-ENG-MEC-00-03354 | 2022-03-05 | 1400/12/14 | CM-C3 | [6 empty] | 1400-2294-430725 | 2022-03-01 | 1400/12/10 | 2022-03-24 | 1400/12/05 | RJ
3 | 2 | 4 | 1 | 8 | 2 | 0 | 3.2.1.8.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 8 | 2 | 1 | 3.2.4.1.8.2.1 | TBE For Centrifugal Pumps For Process Services | BK-GCS-PEDCO-120-ME-TB-0009 | BK-GCS-PEDCO-120-ME-TB-0009 | BK | GCS | PEDCO | 120 | ME | TB | 0009 | F0Z-709232 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 1 | 9 | 0 | 0 | 3.2.4.1.9 | Pumps - General Services
3 | 2 | 4 | 1 | 9 | 1 | 0 | 3.2.1.9.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 9 | 1 | 1 | 3.2.4.1.9.1.1 | PMR For Centrifugal Pumps For General Services | BK-GCS-PEDCO-120-ME-MR-0010 | BK-GCS-PEDCO-120-ME-MR-0010 | BK | GCS | PEDCO | 120 | ME | MR | 0010 | F0Z-709233 | IFI | IFI | 44622 | 44629 | 44629 | 7 | 0 | 7 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-02-16 |  | D00 | IFI | T-0599 | 2022-02-16 | 1400/11/27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-432765 | 2022-03-09 | 1400/12/12 | 2022-03-09 | 1400/12/18 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0599 | 2022-02-16 | 1400/11/27 | [13 empty] | 1400-2294-432765 | 2022-03-09 | 1400/12/12 | 2022-03-09 | 1400/12/18 | RJ
3 | 2 | 4 | 1 | 9 | 2 | 0 | 3.2.1.9.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 9 | 2 | 1 | 3.2.4.1.9.2.1 | TBE For Centrifugal Pumps For General Services | BK-GCS-PEDCO-120-ME-TB-0010 | BK-GCS-PEDCO-120-ME-TB-0010 | BK | GCS | PEDCO | 120 | ME | TB | 0010 | F0Z-709234 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 1 | 10 | 0 | 0 | 3.2.4.1.10 | Fire Water Pumps
3 | 2 | 4 | 1 | 10 | 1 | 0 | 3.2.1.10.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 10 | 1 | 1 | 3.2.4.1.10.1.1 | PMR For Fire Water Pump | BK-GCS-PEDCO-120-ME-MR-0011 | BK-GCS-PEDCO-120-ME-MR-0011 | BK | GCS | PEDCO | 120 | ME | MR | 0011 | F0Z-709235 | IFI | IFI | 44625 | 44627 | 44629 | 2 | 2 | 4 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 2022-02-19 |  | D00 | IFI | T-0603 | 2022-02-19 | 1400/11/30 | 0 | 0 | 0 | BK-SUR-ENG-MEC-00-03257 | 2022-02-27 | 1400/12/08 | CM-C2 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-438865 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | RJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0603 | 2022-02-19 | 1400/11/30 |  |  |  | BK-SUR-ENG-MEC-00-03257 | 2022-02-27 | 1400/12/08 | CM-C2 | [6 empty] | 1400-2294-438865 | 2022-03-07 | 1400/12/16 | 2022-03-09 | 1400/12/18 | RJ
3 | 2 | 4 | 1 | 10 | 2 | 0 | 3.2.1.10.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 10 | 2 | 1 | 3.2.4.1.10.2.1 | TBE For Fire Water Pump | BK-GCS-PEDCO-120-ME-TB-0011 | BK-GCS-PEDCO-120-ME-TB-0011 | BK | GCS | PEDCO | 120 | ME | TB | 0011 | F0Z-709236 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 1 | 11 | 0 | 0 | 3.2.4.1.11 | Flare Packages
3 | 2 | 4 | 1 | 11 | 1 | 0 | 3.2.1.11.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 11 | 1 | 1 | 3.2.4.1.11.1.1 | PMR For Flare Packages | BK-GCS-PEDCO-120-ME-MR-0012 | BK-GCS-PEDCO-120-ME-MR-0012 | BK | GCS | PEDCO | 120 | ME | MR | 0012 | F0Z-709237 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 1 | 11 | 2 | 0 | 3.2.1.11.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 11 | 2 | 1 | 3.2.4.1.11.2.1 | TBE For Flare Packages | BK-GCS-PEDCO-120-ME-TB-0012 | BK-GCS-PEDCO-120-ME-TB-0012 | BK | GCS | PEDCO | 120 | ME | TB | 0012 | F0Z-709238 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 1 | 12 | 0 | 0 | 3.2.4.1.12 | Overhead Travelling Cranes
3 | 2 | 4 | 1 | 12 | 1 | 0 | 3.2.1.12.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 1 | 12 | 1 | 1 | 3.2.4.1.12.1.1 | PMR For Overhead Travelling Cranes | BK-GCS-PEDCO-120-ME-MR-0013 | BK-GCS-PEDCO-120-ME-MR-0013 | BK | GCS | PEDCO | 120 | ME | MR | 0013 | F0Z-709239 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 1 | 12 | 2 | 0 | 3.2.1.12.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 1 | 12 | 2 | 1 | 3.2.4.1.12.2.1 | TBE For Overhead Travelling Cranes | BK-GCS-PEDCO-120-ME-TB-0013 | BK-GCS-PEDCO-120-ME-TB-0013 | BK | GCS | PEDCO | 120 | ME | TB | 0013 | F0Z-709240 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 2 | 0 | 0 | 0 | 3.2.4.2 | HVAC
3 | 2 | 4 | 2 | 1 | 0 | 0 | 3.2.4.2.1 | Main HVAC Equipment
3 | 2 | 4 | 2 | 1 | 1 | 0 | 3.2.2.1.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 2 | 1 | 1 | 1 | 3.2.4.2.1.1.1 | PMR For Main HVAC Equipment | BK-GCS-PEDCO-120-HV-MR-0001 | BK-GCS-PEDCO-120-HV-MR-0001 | BK | GCS | PEDCO | 120 | HV | MR | 0001 | F0Z-709241 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 2 | 1 | 2 | 0 | 3.2.2.1.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 2 | 1 | 2 | 1 | 3.2.4.2.1.2.1 | TBE For Main HVAC Equipment | BK-GCS-PEDCO-120-HV-TB-0001 | BK-GCS-PEDCO-120-HV-TB-0001 | BK | GCS | PEDCO | 120 | HV | TB | 0001 | F0Z-709242 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 0 | 0 | 0 | 3.2.4.3 | Piping
3 | 2 | 4 | 3 | 1 | 0 | 0 | 3.2.4.3.1 | Pipes
3 | 2 | 4 | 3 | 1 | 1 | 0 | 3.2.3.1.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 3 | 1 | 1 | 1 | 3.2.4.3.1.1.1 | PMR For Pipes | BK-GCS-PEDCO-120-PI-MR-0001 | BK-GCS-PEDCO-120-PI-MR-0001 | BK | GCS | PEDCO | 120 | PI | MR | 0001 | F0Z-709243 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 1 | 2 | 0 | 3.2.3.1.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 3 | 1 | 2 | 1 | 3.2.4.3.1.2.1 | TBE For Pipes | BK-GCS-PEDCO-120-PI-TB-0001 | BK-GCS-PEDCO-120-PI-TB-0001 | BK | GCS | PEDCO | 120 | PI | TB | 0001 | F0Z-709244 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 2 | 0 | 0 | 3.2.4.3.2 | Fittings
3 | 2 | 4 | 3 | 2 | 1 | 0 | 3.2.3.2.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 3 | 2 | 1 | 1 | 3.2.4.3.2.1.1 | PMR For Fittings | BK-GCS-PEDCO-120-PI-MR-0002 | BK-GCS-PEDCO-120-PI-MR-0002 | BK | GCS | PEDCO | 120 | PI | MR | 0002 | F0Z-709245 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 2 | 2 | 0 | 3.2.3.2.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 3 | 2 | 2 | 1 | 3.2.4.3.2.2.1 | TBE For Fitting | BK-GCS-PEDCO-120-PI-TB-0002 | BK-GCS-PEDCO-120-PI-TB-0002 | BK | GCS | PEDCO | 120 | PI | TB | 0002 | F0Z-709246 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 3 | 0 | 0 | 3.2.4.3.3 | Flanges
3 | 2 | 4 | 3 | 3 | 1 | 0 | 3.2.3.3.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 3 | 3 | 1 | 1 | 3.2.4.3.3.1.1 | PMR For Flanges | BK-GCS-PEDCO-120-PI-MR-0003 | BK-GCS-PEDCO-120-PI-MR-0003 | BK | GCS | PEDCO | 120 | PI | MR | 0003 | F0Z-709247 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 3 | 2 | 0 | 3.2.3.3.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 3 | 3 | 2 | 1 | 3.2.4.3.3.2.1 | TBE For Flanges | BK-GCS-PEDCO-120-PI-TB-0003 | BK-GCS-PEDCO-120-PI-TB-0003 | BK | GCS | PEDCO | 120 | PI | TB | 0003 | F0Z-709248 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 4 | 0 | 0 | 3.2.4.3.4 | Manual Valves
3 | 2 | 4 | 3 | 4 | 1 | 0 | 3.2.3.4.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 3 | 4 | 1 | 1 | 3.2.4.3.4.1.1 | PMR For Manual Valves | BK-GCS-PEDCO-120-PI-MR-0004 | BK-GCS-PEDCO-120-PI-MR-0004 | BK | GCS | PEDCO | 120 | PI | MR | 0004 | F0Z-709249 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 4 | 2 | 0 | 3.2.3.4.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 3 | 4 | 2 | 1 | 3.2.4.3.4.2.1 | TBE For Manual Valves | BK-GCS-PEDCO-120-PI-TB-0004 | BK-GCS-PEDCO-120-PI-TB-0004 | BK | GCS | PEDCO | 120 | PI | TB | 0004 | F0Z-709250 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 5 | 0 | 0 | 3.2.4.3.5 | Gaskets
3 | 2 | 4 | 3 | 5 | 1 | 0 | 3.2.3.5.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 3 | 5 | 1 | 1 | 3.2.4.3.5.1.1 | PMR For Gaskets | BK-GCS-PEDCO-120-PI-MR-0005 | BK-GCS-PEDCO-120-PI-MR-0005 | BK | GCS | PEDCO | 120 | PI | MR | 0005 | F0Z-709251 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 5 | 2 | 0 | 3.2.3.5.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 3 | 5 | 2 | 1 | 3.2.4.3.5.2.1 | TBE For Gaskets | BK-GCS-PEDCO-120-PI-TB-0005 | BK-GCS-PEDCO-120-PI-TB-0005 | BK | GCS | PEDCO | 120 | PI | TB | 0005 | F0Z-709252 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 6 | 0 | 0 | 3.2.4.3.6 | Bolt & Nuts
3 | 2 | 4 | 3 | 6 | 1 | 0 | 3.2.3.6.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 3 | 6 | 1 | 1 | 3.2.4.3.6.1.1 | PMR For Bolt/Nuts | BK-GCS-PEDCO-120-PI-MR-0006 | BK-GCS-PEDCO-120-PI-MR-0006 | BK | GCS | PEDCO | 120 | PI | MR | 0006 | F0Z-709253 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 6 | 2 | 0 | 3.2.3.6.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 3 | 6 | 2 | 1 | 3.2.4.3.6.2.1 | PMR For Bolt/Nuts | BK-GCS-PEDCO-120-PI-TB-0006 | BK-GCS-PEDCO-120-PI-TB-0006 | BK | GCS | PEDCO | 120 | PI | TB | 0006 | F0Z-709254 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 7 | 0 | 0 | 3.2.4.3.7 | Insulation Joints
3 | 2 | 4 | 3 | 7 | 1 | 0 | 3.2.3.7.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 3 | 7 | 1 | 1 | 3.2.4.3.7.1.1 | PMR For Insulation Joints | BK-GCS-PEDCO-120-PI-MR-0007 | BK-GCS-PEDCO-120-PI-MR-0007 | BK | GCS | PEDCO | 120 | PI | MR | 0007 | F0Z-709255 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 7 | 2 | 0 | 3.2.3.7.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 3 | 7 | 2 | 1 | 3.2.4.3.7.2.1 | TBE For Insulation Joints | BK-GCS-PEDCO-120-PI-TB-0007 | BK-GCS-PEDCO-120-PI-TB-0007 | BK | GCS | PEDCO | 120 | PI | TB | 0007 | F0Z-709256 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 8 | 0 | 0 | 3.2.4.3.8 | Strainers
3 | 2 | 4 | 3 | 8 | 1 | 0 | 3.2.3.8.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 3 | 8 | 1 | 1 | 3.2.4.3.8.1.1 | PMR For Strainers | BK-GCS-PEDCO-120-PI-MR-0008 | BK-GCS-PEDCO-120-PI-MR-0008 | BK | GCS | PEDCO | 120 | PI | MR | 0008 | F0Z-709257 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 8 | 2 | 0 | 3.2.3.8.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 3 | 8 | 2 | 1 | 3.2.4.3.8.2.1 | TBE For Strainers | BK-GCS-PEDCO-120-PI-TB-0008 | BK-GCS-PEDCO-120-PI-TB-0008 | BK | GCS | PEDCO | 120 | PI | TB | 0008 | F0Z-709258 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 9 | 0 | 0 | 3.2.4.3.9 | Special Pipe Supports
3 | 2 | 4 | 3 | 9 | 1 | 0 | 3.2.3.9.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 3 | 9 | 1 | 1 | 3.2.4.3.9.1.1 | PMR For Special Pipe Supports | BK-GCS-PEDCO-120-PI-MR-0009 | BK-GCS-PEDCO-120-PI-MR-0009 | BK | GCS | PEDCO | 120 | PI | MR | 0009 | F0Z-709259 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 9 | 2 | 0 | 3.2.3.9.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 3 | 9 | 2 | 1 | 3.2.4.3.9.2.1 | TBE For Special Pipe Supports | BK-GCS-PEDCO-120-PI-TB-0009 | BK-GCS-PEDCO-120-PI-TB-0009 | BK | GCS | PEDCO | 120 | PI | TB | 0009 | F0Z-709260 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 10 | 0 | 0 | 3.2.4.3.10 | Insulation
3 | 2 | 4 | 3 | 10 | 1 | 0 | 3.2.3.10.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 3 | 10 | 1 | 1 | 3.2.4.3.10.1.1 | PMR For Insulation | BK-GCS-PEDCO-120-PI-MR-0010 | BK-GCS-PEDCO-120-PI-MR-0010 | BK | GCS | PEDCO | 120 | PI | MR | 0010 | F0Z-709261 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 10 | 2 | 0 | 3.2.3.10.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 3 | 10 | 2 | 1 | 3.2.4.3.10.2.1 | TBE For Insulation | BK-GCS-PEDCO-120-PI-TB-0010 | BK-GCS-PEDCO-120-PI-TB-0010 | BK | GCS | PEDCO | 120 | PI | TB | 0010 | F0Z-709262 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 11 | 0 | 0 | 3.2.4.3.11 | Painting
3 | 2 | 4 | 3 | 11 | 1 | 0 | 3.2.3.11.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 3 | 11 | 1 | 1 | 3.2.4.3.11.1.1 | PMR For Painting | BK-GCS-PEDCO-120-PI-MR-0011 | BK-GCS-PEDCO-120-PI-MR-0011 | BK | GCS | PEDCO | 120 | PI | MR | 0011 | F0Z-709263 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 11 | 2 | 0 | 3.2.3.11.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 3 | 11 | 2 | 1 | 3.2.4.3.11.2.1 | TBE For Painting | BK-GCS-PEDCO-120-PI-TB-0011 | BK-GCS-PEDCO-120-PI-TB-0011 | BK | GCS | PEDCO | 120 | PI | TB | 0011 | F0Z-709264 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 12 | 0 | 0 | 3.2.4.3.12 | Coating of Underground Piping
3 | 2 | 4 | 3 | 12 | 1 | 0 | 3.2.3.12.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 3 | 12 | 1 | 1 | 3.2.4.3.12.1.1 | PMR For Coating of Underground Piping | BK-GCS-PEDCO-120-PI-MR-0012 | BK-GCS-PEDCO-120-PI-MR-0012 | BK | GCS | PEDCO | 120 | PI | MR | 0012 | F0Z-709265 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 3 | 12 | 2 | 0 | 3.2.3.12.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 3 | 12 | 2 | 1 | 3.2.4.3.12.2.1 | TBE For Coating of Underground Piping | BK-GCS-PEDCO-120-PI-TB-0012 | BK-GCS-PEDCO-120-PI-TB-0012 | BK | GCS | PEDCO | 120 | PI | TB | 0012 | F0Z-709266 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 0 | 0 | 0 | 3.2.4.4 | Control & Instrumentation
3 | 2 | 4 | 4 | 1 | 0 | 0 | 3.2.4.4.1 | Control System/Console/Furniture
3 | 2 | 4 | 4 | 1 | 1 | 0 | 3.2.4.1.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 1 | 1 | 1 | 3.2.4.4.1.1.1 | PMR For Control System/Console/Furniture | BK-GCS-PEDCO-120-IN-MR-0001 | BK-GCS-PEDCO-120-IN-MR-0001 | BK | GCS | PEDCO | 120 | IN | MR | 0001 | F0Z-709267 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 1 | 2 | 0 | 3.2.4.1.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 1 | 2 | 1 | 3.2.4.4.1.2.1 | TBE For Control System/Console/Furniture | BK-GCS-PEDCO-120-IN-TB-0001 | BK-GCS-PEDCO-120-IN-TB-0001 | BK | GCS | PEDCO | 120 | IN | TB | 0001 | F0Z-709268 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 2 | 0 | 0 | 3.2.4.4.2 | ESD System
3 | 2 | 4 | 4 | 2 | 1 | 0 | 3.2.4.2.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 2 | 1 | 1 | 3.2.4.4.2.1.1 | PMR For ESD System | BK-GCS-PEDCO-120-IN-MR-0002 | BK-GCS-PEDCO-120-IN-MR-0002 | BK | GCS | PEDCO | 120 | IN | MR | 0002 | F0Z-709269 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 2 | 2 | 0 | 3.2.4.2.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 2 | 2 | 1 | 3.2.4.4.2.2.1 | TBE For ESD System | BK-GCS-PEDCO-120-IN-TB-0002 | BK-GCS-PEDCO-120-IN-TB-0002 | BK | GCS | PEDCO | 120 | IN | TB | 0002 | F0Z-709270 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 3 | 0 | 0 | 3.2.4.4.3 | F&G System
3 | 2 | 4 | 4 | 3 | 1 | 0 | 3.2.4.3.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 3 | 1 | 1 | 3.2.4.4.3.1.1 | PMR For F&G System | BK-GCS-PEDCO-120-IN-MR-0003 | BK-GCS-PEDCO-120-IN-MR-0003 | BK | GCS | PEDCO | 120 | IN | MR | 0003 | F0Z-709271 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 3 | 2 | 0 | 3.2.4.3.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 3 | 2 | 1 | 3.2.4.4.3.2.1 | TBE For F&G System | BK-GCS-PEDCO-120-IN-TB-0003 | BK-GCS-PEDCO-120-IN-TB-0003 | BK | GCS | PEDCO | 120 | IN | TB | 0003 | F0Z-709272 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 4 | 0 | 0 | 3.2.4.4.4 | ON/OFF & Shutdown Valves
3 | 2 | 4 | 4 | 4 | 1 | 0 | 3.2.4.4.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 4 | 1 | 1 | 3.2.4.4.4.1.1 | PMR For On/off & Shutdown Valves | BK-GCS-PEDCO-120-IN-MR-0004 | BK-GCS-PEDCO-120-IN-MR-0004 | BK | GCS | PEDCO | 120 | IN | MR | 0004 | F0Z-709273 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 4 | 2 | 0 | 3.2.4.4.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 4 | 2 | 1 | 3.2.4.4.4.2.1 | TBE For On/off & Shutdown Valves | BK-GCS-PEDCO-120-IN-TB-0004 | BK-GCS-PEDCO-120-IN-TB-0004 | BK | GCS | PEDCO | 120 | IN | TB | 0004 | F0Z-709274 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 5 | 0 | 0 | 3.2.4.4.5 | Control Valves
3 | 2 | 4 | 4 | 5 | 1 | 0 | 3.2.4.5.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 5 | 1 | 1 | 3.2.4.4.5.1.1 | PMR For Control Valves | BK-GCS-PEDCO-120-IN-MR-0005 | BK-GCS-PEDCO-120-IN-MR-0005 | BK | GCS | PEDCO | 120 | IN | MR | 0005 | F0Z-709275 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 5 | 2 | 0 | 3.2.4.5.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 5 | 2 | 1 | 3.2.4.4.5.2.1 | TBE For Control Valves | BK-GCS-PEDCO-120-IN-TB-0005 | BK-GCS-PEDCO-120-IN-TB-0005 | BK | GCS | PEDCO | 120 | IN | TB | 0005 | F0Z-709276 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 6 | 0 | 0 | 3.2.4.4.6 | Pressure Safety Valves (PSV)
3 | 2 | 4 | 4 | 6 | 1 | 0 | 3.2.4.6.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 6 | 1 | 1 | 3.2.4.4.6.1.1 | PMR For Pressure Safety Valves (PSV) | BK-GCS-PEDCO-120-IN-MR-0006 | BK-GCS-PEDCO-120-IN-MR-0006 | BK | GCS | PEDCO | 120 | IN | MR | 0006 | F0Z-709277 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 6 | 2 | 0 | 3.2.4.6.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 6 | 2 | 1 | 3.2.4.4.6.2.1 | TBE For Pressure Safety Valves (PSV) | BK-GCS-PEDCO-120-IN-TB-0006 | BK-GCS-PEDCO-120-IN-TB-0006 | BK | GCS | PEDCO | 120 | IN | TB | 0006 | F0Z-709278 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 7 | 0 | 0 | 3.2.4.4.7 | F&G Devices
3 | 2 | 4 | 4 | 7 | 1 | 0 | 3.2.4.7.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 7 | 1 | 1 | 3.2.4.4.7.1.1 | PMR For F&G Devices | BK-GCS-PEDCO-120-IN-MR-0007 | BK-GCS-PEDCO-120-IN-MR-0007 | BK | GCS | PEDCO | 120 | IN | MR | 0007 | F0Z-709279 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 7 | 2 | 0 | 3.2.4.7.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 7 | 2 | 1 | 3.2.4.4.7.2.1 | TBE For F&G Devices | BK-GCS-PEDCO-120-IN-TB-0007 | BK-GCS-PEDCO-120-IN-TB-0007 | BK | GCS | PEDCO | 120 | IN | TB | 0007 | F0Z-709280 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 8 | 0 | 0 | 3.2.4.4.8 | Corrosion Probe/Coupon
3 | 2 | 4 | 4 | 8 | 1 | 0 | 3.2.4.8.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 8 | 1 | 1 | 3.2.4.4.8.1.1 | PMR For Corrosion Probe/Coupon | BK-GCS-PEDCO-120-IN-MR-0008 | BK-GCS-PEDCO-120-IN-MR-0008 | BK | GCS | PEDCO | 120 | IN | MR | 0008 | F0Z-709281 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 8 | 2 | 0 | 3.2.4.8.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 8 | 2 | 1 | 3.2.4.4.8.2.1 | TBE For Corrosion Probe/Coupon | BK-GCS-PEDCO-120-IN-TB-0008 | BK-GCS-PEDCO-120-IN-TB-0008 | BK | GCS | PEDCO | 120 | IN | TB | 0008 | F0Z-709282 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 9 | 0 | 0 | 3.2.4.4.9 | Orifice and Restriction Orifice Plate
3 | 2 | 4 | 4 | 9 | 1 | 0 | 3.2.4.9.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 9 | 1 | 1 | 3.2.4.4.9.1.1 | PMR For Orifice and Restriction Orifice Plate | BK-GCS-PEDCO-120-IN-MR-0009 | BK-GCS-PEDCO-120-IN-MR-0009 | BK | GCS | PEDCO | 120 | IN | MR | 0009 | F0Z-709283 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 9 | 2 | 0 | 3.2.4.9.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 9 | 2 | 1 | 3.2.4.4.9.2.1 | TBE For Orifice and Restriction Orifice Plate | BK-GCS-PEDCO-120-IN-TB-0009 | BK-GCS-PEDCO-120-IN-TB-0009 | BK | GCS | PEDCO | 120 | IN | TB | 0009 | F0Z-709284 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 10 | 0 | 0 | 3.2.4.4.10 | Differential Pressure/Pressure Gauge
3 | 2 | 4 | 4 | 10 | 1 | 0 | 3.2.4.10.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 10 | 1 | 1 | 3.2.4.4.10.1.1 | PMR For Differential Pressure/Pressure Gauge | BK-GCS-PEDCO-120-IN-MR-0010 | BK-GCS-PEDCO-120-IN-MR-0010 | BK | GCS | PEDCO | 120 | IN | MR | 0010 | F0Z-709285 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 10 | 2 | 0 | 3.2.4.10.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 10 | 2 | 1 | 3.2.4.4.10.2.1 | TBE For Differential Pressure/Pressure Gauge | BK-GCS-PEDCO-120-IN-TB-0010 | BK-GCS-PEDCO-120-IN-TB-0010 | BK | GCS | PEDCO | 120 | IN | TB | 0010 | F0Z-709286 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 11 | 0 | 0 | 3.2.4.4.11 | Flow/Level /Pressure/Diff. Pressure Transmitter
3 | 2 | 4 | 4 | 11 | 1 | 0 | 3.2.4.11.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 11 | 1 | 1 | 3.2.4.4.11.1.1 | PMR For DP Flow /DP Level /Pressure/Diff. Pressure Transmitter | BK-GCS-PEDCO-120-IN-MR-0011 | BK-GCS-PEDCO-120-IN-MR-0011 | BK | GCS | PEDCO | 120 | IN | MR | 0011 | F0Z-709287 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 11 | 2 | 0 | 3.2.4.11.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 11 | 2 | 1 | 3.2.4.4.11.2.1 | TBE For DP Flow /DP Level /Pressure/Diff. Pressure Transmitter" | BK-GCS-PEDCO-120-IN-TB-0011 | BK-GCS-PEDCO-120-IN-TB-0011 | BK | GCS | PEDCO | 120 | IN | TB | 0011 | F0Z-709288 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 12 | 0 | 0 | 3.2.4.4.12 | Pressure/ Differential Pressure Switch
3 | 2 | 4 | 4 | 12 | 1 | 0 | 3.2.4.12.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 12 | 1 | 1 | 3.2.4.4.12.1.1 | PMR For Pressure/ Differential Pressure Switch | BK-GCS-PEDCO-120-IN-MR-0012 | BK-GCS-PEDCO-120-IN-MR-0012 | BK | GCS | PEDCO | 120 | IN | MR | 0012 | F0Z-709289 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 12 | 2 | 0 | 3.2.4.12.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 12 | 2 | 1 | 3.2.4.4.12.2.1 | TBE For Pressure/ Differential Pressure Switch | BK-GCS-PEDCO-120-IN-TB-0012 | BK-GCS-PEDCO-120-IN-TB-0012 | BK | GCS | PEDCO | 120 | IN | TB | 0012 | F0Z-709290 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 13 | 0 | 0 | 3.2.4.4.13 | Temperature Gauge
3 | 2 | 4 | 4 | 13 | 1 | 0 | 3.2.4.13.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 13 | 1 | 1 | 3.2.4.4.13.1.1 | PMR For Temperature Gauge | BK-GCS-PEDCO-120-IN-MR-0013 | BK-GCS-PEDCO-120-IN-MR-0013 | BK | GCS | PEDCO | 120 | IN | MR | 0013 | F0Z-709291 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 13 | 2 | 0 | 3.2.4.13.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 13 | 2 | 1 | 3.2.4.4.13.2.1 | TBE For Temperature Gauge | BK-GCS-PEDCO-120-IN-TB-0013 | BK-GCS-PEDCO-120-IN-TB-0013 | BK | GCS | PEDCO | 120 | IN | TB | 0013 | F0Z-709292 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 14 | 0 | 0 | 3.2.4.4.14 | Temperature Transmitter/Switch
3 | 2 | 4 | 4 | 14 | 1 | 0 | 3.2.4.14.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 14 | 1 | 1 | 3.2.4.4.14.1.1 | PMR For Temperature Transmitter/Switch | BK-GCS-PEDCO-120-IN-MR-0014 | BK-GCS-PEDCO-120-IN-MR-0014 | BK | GCS | PEDCO | 120 | IN | MR | 0014 | F0Z-709293 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 14 | 2 | 0 | 3.2.4.14.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 14 | 2 | 1 | 3.2.4.4.14.2.1 | TBE For Temperature Transmitter/Switch | BK-GCS-PEDCO-120-IN-TB-0014 | BK-GCS-PEDCO-120-IN-TB-0014 | BK | GCS | PEDCO | 120 | IN | TB | 0014 | F0Z-709294 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 15 | 0 | 0 | 3.2.4.4.15 | Level Gauge
3 | 2 | 4 | 4 | 15 | 1 | 0 | 3.2.4.15.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 15 | 1 | 1 | 3.2.4.4.15.1.1 | PMR For Level Gauge | BK-GCS-PEDCO-120-IN-MR-0015 | BK-GCS-PEDCO-120-IN-MR-0015 | BK | GCS | PEDCO | 120 | IN | MR | 0015 | F0Z-709295 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 15 | 2 | 0 | 3.2.4.15.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 15 | 2 | 1 | 3.2.4.4.15.2.1 | TBE For Level Gauge | BK-GCS-PEDCO-120-IN-TB-0015 | BK-GCS-PEDCO-120-IN-TB-0015 | BK | GCS | PEDCO | 120 | IN | TB | 0015 | F0Z-709296 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 16 | 0 | 0 | 3.2.4.4.16 | Level Switch
3 | 2 | 4 | 4 | 16 | 1 | 0 | 3.2.4.16.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 16 | 1 | 1 | 3.2.4.4.16.1.1 | PMR For Level Switch | BK-GCS-PEDCO-120-IN-MR-0016 | BK-GCS-PEDCO-120-IN-MR-0016 | BK | GCS | PEDCO | 120 | IN | MR | 0016 | F0Z-709297 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 16 | 2 | 0 | 3.2.4.16.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 16 | 2 | 1 | 3.2.4.4.16.2.1 | TBE For Level Switch | BK-GCS-PEDCO-120-IN-TB-0016 | BK-GCS-PEDCO-120-IN-TB-0016 | BK | GCS | PEDCO | 120 | IN | TB | 0016 | F0Z-709298 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 17 | 0 | 0 | 3.2.4.4.17 | Displacer Level Transmitter
3 | 2 | 4 | 4 | 17 | 1 | 0 | 3.2.4.17.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 17 | 1 | 1 | 3.2.4.4.17.1.1 | PMR For Displacer Level Transmitter | BK-GCS-PEDCO-120-IN-MR-0017 | BK-GCS-PEDCO-120-IN-MR-0017 | BK | GCS | PEDCO | 120 | IN | MR | 0017 | F0Z-709299 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 17 | 2 | 0 | 3.2.4.17.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 17 | 2 | 1 | 3.2.4.4.17.2.1 | TBE For Displacer Level Transmitter | BK-GCS-PEDCO-120-IN-TB-0017 | BK-GCS-PEDCO-120-IN-TB-0017 | BK | GCS | PEDCO | 120 | IN | TB | 0017 | F0Z-709300 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 18 | 0 | 0 | 3.2.4.4.18 | Rotameter
3 | 2 | 4 | 4 | 18 | 1 | 0 | 3.2.4.18.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 18 | 1 | 1 | 3.2.4.4.18.1.1 | PMR For Rotameter | BK-GCS-PEDCO-120-IN-MR-0019 | BK-GCS-PEDCO-120-IN-MR-0019 | BK | GCS | PEDCO | 120 | IN | MR | 0019 | F0Z-709301 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 18 | 2 | 0 | 3.2.4.18.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 18 | 2 | 1 | 3.2.4.4.18.2.1 | TBE For Rotameter | BK-GCS-PEDCO-120-IN-TB-0019 | BK-GCS-PEDCO-120-IN-TB-0019 | BK | GCS | PEDCO | 120 | IN | TB | 0019 | F0Z-709302 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 19 | 0 | 0 | 3.2.4.4.19 | Instrument/F&G Cable
3 | 2 | 4 | 4 | 19 | 1 | 0 | 3.2.4.19.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 19 | 1 | 1 | 3.2.4.4.19.1.1 | PMR For Instrument/F&G cable | BK-GCS-PEDCO-120-IN-MR-0020 | BK-GCS-PEDCO-120-IN-MR-0020 | BK | GCS | PEDCO | 120 | IN | MR | 0020 | F0Z-709303 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 19 | 2 | 0 | 3.2.4.19.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 19 | 2 | 1 | 3.2.4.4.19.2.1 | TBE For Instrument/F&G cable | BK-GCS-PEDCO-120-IN-TB-0020 | BK-GCS-PEDCO-120-IN-TB-0020 | BK | GCS | PEDCO | 120 | IN | TB | 0020 | F0Z-709304 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 20 | 0 | 0 | 3.2.4.4.20 | Instrument Cable Tray
3 | 2 | 4 | 4 | 20 | 1 | 0 | 3.2.4.20.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 20 | 1 | 1 | 3.2.4.4.20.1.1 | PMR For Instrument Cable Tray | BK-GCS-PEDCO-120-IN-MR-0021 | BK-GCS-PEDCO-120-IN-MR-0021 | BK | GCS | PEDCO | 120 | IN | MR | 0021 | F0Z-709305 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 20 | 2 | 0 | 3.2.4.20.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 20 | 2 | 1 | 3.2.4.4.20.2.1 | TBE For Instrument Cable Tray | BK-GCS-PEDCO-120-IN-TB-0021 | BK-GCS-PEDCO-120-IN-TB-0021 | BK | GCS | PEDCO | 120 | IN | TB | 0021 | F0Z-709306 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 21 | 0 | 0 | 3.2.4.4.21 | Instrument/F&G Junction box and Gland
3 | 2 | 4 | 4 | 21 | 1 | 0 | 3.2.4.21.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 21 | 1 | 1 | 3.2.4.4.21.1.1 | PMR For Instrument/F&G Junction box and Gland | BK-GCS-PEDCO-120-IN-MR-0022 | BK-GCS-PEDCO-120-IN-MR-0022 | BK | GCS | PEDCO | 120 | IN | MR | 0022 | F0Z-709307 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 21 | 2 | 0 | 3.2.4.21.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 21 | 2 | 1 | 3.2.4.4.21.2.1 | TBE For Instrument/F&G Junction box and Gland | BK-GCS-PEDCO-120-IN-TB-0022 | BK-GCS-PEDCO-120-IN-TB-0022 | BK | GCS | PEDCO | 120 | IN | TB | 0022 | F0Z-709308 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 22 | 0 | 0 | 3.2.4.4.22 | Instrument Tube and Fitting
3 | 2 | 4 | 4 | 22 | 1 | 0 | 3.2.4.22.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 22 | 1 | 1 | 3.2.4.4.22.1.1 | PMR For Instrument Tube and Fitting | BK-GCS-PEDCO-120-IN-MR-0023 | BK-GCS-PEDCO-120-IN-MR-0023 | BK | GCS | PEDCO | 120 | IN | MR | 0023 | F0Z-709309 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 22 | 2 | 0 | 3.2.4.22.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 22 | 2 | 1 | 3.2.4.4.22.2.1 | TBE For Instrument Tube and Fitting | BK-GCS-PEDCO-120-IN-TB-0023 | BK-GCS-PEDCO-120-IN-TB-0023 | BK | GCS | PEDCO | 120 | IN | TB | 0023 | F0Z-709310 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 23 | 0 | 0 | 3.2.4.4.23 | Instrument Installation Accessories
3 | 2 | 4 | 4 | 23 | 1 | 0 | 3.2.4.23.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 23 | 1 | 1 | 3.2.4.4.23.1.1 | PMR For Instrument Installation Accessories | BK-GCS-PEDCO-120-IN-MR-0024 | BK-GCS-PEDCO-120-IN-MR-0024 | BK | GCS | PEDCO | 120 | IN | MR | 0024 | F0Z-709311 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 23 | 2 | 0 | 3.2.4.23.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 23 | 2 | 1 | 3.2.4.4.23.2.1 | TBE For Instrument Installation Accessories | BK-GCS-PEDCO-120-IN-TB-0024 | BK-GCS-PEDCO-120-IN-TB-0024 | BK | GCS | PEDCO | 120 | IN | TB | 0024 | F0Z-709312 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 24 | 0 | 0 | 3.2.4.4.24 | CCTV System
3 | 2 | 4 | 4 | 24 | 1 | 0 | 3.2.4.24.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 24 | 1 | 1 | 3.2.4.4.24.1.1 | PMR For CCTV System | BK-GCS-PEDCO-120-IN-MR-0025 | BK-GCS-PEDCO-120-IN-MR-0025 | BK | GCS | PEDCO | 120 | IN | MR | 0025 | F0Z-709313 | IFI | IFI | 44564 | 44560 | 44563 | -4 | 3 | -1 | IFI | 44618 | 44614 | 44594 | -4 | -20 | -24 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-20 | 2022-02-12 |  | D01 | IFI | T-0578 | 2022-02-12 | 1400/11/23 | 0 | 0 | 0 | BK-SUR-ENG-INS-00-03148 | 2022-02-21 | 1400/12/02 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-IN-MR-0025_D00 | 0 | 0 | 0 | 0 | 0 | 1400-2294-421740 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0025_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0371 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-INS-00-02496 | 2022-01-01 | 1400/10/11 | C4-RJ | [6 empty] | 1400-2294-342126 | 2021-12-30 | 1400/10/09 | 2022-01-02 | 1400/10/12 | CM | [10 empty] | D01 | IFI | T-0578 | 2022-02-12 | 1400/11/23 |  |  |  | BK-SUR-ENG-INS-00-03148 | 2022-02-21 | 1400/12/02 | AP | PEDCO-CRS-BK-GCS-PEDCO-120-IN-MR-0025_D00 | [5 empty] | 1400-2294-421740 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0025_D00
3 | 2 | 4 | 4 | 24 | 2 | 0 | 3.2.4.24.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 24 | 2 | 1 | 3.2.4.4.24.2.1 | TBE For CCTV System | BK-GCS-PEDCO-120-IN-TB-0025 | BK-GCS-PEDCO-120-IN-TB-0025 | BK | GCS | PEDCO | 120 | IN | TB | 0025 | F0Z-709314 | IFI | IFI | 44697 | 44693 | 44697 | -4 | 4 | 0 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-02 | 2022-05-02 |  | D00 | IFI | T-0901 | 2022-05-02 | 1401/02/12 | 0 | 0 | 0 | BK-SUR-ENG-INS-01-04222 | 2022-05-10 | 1401/02/0 | AP | 0 | 0 | 0 | 0 | 0 | 0 | 1401-2294-59528 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0901 | 2022-05-02 | 1401/02/12 |  |  |  | BK-SUR-ENG-INS-01-04222 | 2022-05-10 | 1401/02/0 | AP | [6 empty] | 1401-2294-59528 | 2022-05-12 | 1401/02/22 | 2022-05-16 | 1401/02/26 | CM
3 | 2 | 4 | 4 | 25 | 0 | 0 | 3.2.4.4.25 | IRP Panel
3 | 2 | 4 | 4 | 25 | 1 | 0 | 3.2.4.25.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 4 | 25 | 1 | 1 | 3.2.4.4.25.1.1 | PMR For IRP Panel | BK-GCS-PEDCO-120-IN-MR-0026 | BK-GCS-PEDCO-120-IN-MR-0026 | BK | GCS | PEDCO | 120 | IN | MR | 0026 | F0Z-709315 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 4 | 25 | 2 | 0 | 3.2.4.25.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 4 | 25 | 2 | 1 | 3.2.4.4.25.2.1 | TBE For IRP Panel | BK-GCS-PEDCO-120-IN-TB-0026 | BK-GCS-PEDCO-120-IN-TB-0026 | BK | GCS | PEDCO | 120 | IN | TB | 0026 | F0Z-709316 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 5 | 0 | 0 | 0 | 3.2.4.5 | Safety & Fire Fighting
3 | 2 | 4 | 5 | 1 | 0 | 0 | 3.2.4.5.1 | Total Flooding System
3 | 2 | 4 | 5 | 1 | 1 | 0 | 3.2.5.1.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 5 | 1 | 1 | 1 | 3.2.4.5.1.1.1 | PMR For Total Flooding System | BK-GCS-PEDCO-120-SA-MR-0001 | BK-GCS-PEDCO-120-SA-MR-0001 | BK | GCS | PEDCO | 120 | SA | MR | 0001 | F0Z-709317 | IFI | IFI | 44709 | 0 | 0 | -44709 | 0 | -44709 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2022-05-14 | 2022-05-14 |  | D00 | IFI | T-0942 | 2022-05-14 | 1401/02/24 | T-0942 | 2022-05-14 | 1401/02/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0942 | 2022-05-14 | 1401/02/24 | T-0942 | 2022-05-14 | 1401/02/24
3 | 2 | 4 | 5 | 1 | 2 | 0 | 3.2.5.1.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 5 | 1 | 2 | 1 | 3.2.4.5.1.2.1 | TBE For Total Flooding System | BK-GCS-PEDCO-120-SA-TB-0001 | BK-GCS-PEDCO-120-SA-TB-0001 | BK | GCS | PEDCO | 120 | SA | TB | 0001 | F0Z-709318 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 5 | 2 | 0 | 0 | 3.2.4.5.2 | Deluge Valve & Water Spray
3 | 2 | 4 | 5 | 2 | 1 | 0 | 3.2.5.2.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 5 | 2 | 1 | 1 | 3.2.4.5.2.1.1 | PMR For Deluge Valve & Water Spray | BK-GCS-PEDCO-120-SA-MR-0002 | BK-GCS-PEDCO-120-SA-MR-0002 | BK | GCS | PEDCO | 120 | SA | MR | 0002 | F0Z-709319 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 5 | 2 | 2 | 0 | 3.2.5.2.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 5 | 2 | 2 | 1 | 3.2.4.5.2.2.1 | TBE For Deluge Valve & Water Spray | BK-GCS-PEDCO-120-SA-TB-0002 | BK-GCS-PEDCO-120-SA-TB-0002 | BK | GCS | PEDCO | 120 | SA | TB | 0002 | F0Z-709320 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 5 | 3 | 0 | 0 | 3.2.4.5.3 | Safety Equipment
3 | 2 | 4 | 5 | 3 | 1 | 0 | 3.2.5.3.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 5 | 3 | 1 | 1 | 3.2.4.5.3.1.1 | PMR For Safety Equipment | BK-GCS-PEDCO-120-SA-MR-0003 | BK-GCS-PEDCO-120-SA-MR-0003 | BK | GCS | PEDCO | 120 | SA | MR | 0003 | F0Z-709321 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 5 | 3 | 2 | 0 | 3.2.5.3.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 5 | 3 | 2 | 1 | 3.2.4.5.3.2.1 | TBE For Safety Equipment | BK-GCS-PEDCO-120-SA-TB-0003 | BK-GCS-PEDCO-120-SA-TB-0003 | BK | GCS | PEDCO | 120 | SA | TB | 0003 | F0Z-709322 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 5 | 4 | 0 | 0 | 3.2.4.5.4 | Fire Fighting Equipment
3 | 2 | 4 | 5 | 4 | 1 | 0 | 3.2.5.4.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 5 | 4 | 1 | 1 | 3.2.4.5.4.1.1 | PMR For Fire Fighting Equipment | BK-GCS-PEDCO-120-SA-MR-0004 | BK-GCS-PEDCO-120-SA-MR-0004 | BK | GCS | PEDCO | 120 | SA | MR | 0004 | F0Z-709323 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 5 | 4 | 2 | 0 | 3.2.5.4.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 5 | 4 | 2 | 1 | 3.2.4.5.4.2.1 | TBE For Fire Fighting Equipment | BK-GCS-PEDCO-120-SA-TB-0004 | BK-GCS-PEDCO-120-SA-TB-0004 | BK | GCS | PEDCO | 120 | SA | TB | 0004 | F0Z-709324 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 5 | 5 | 0 | 0 | 3.2.4.5.5 | Safety Signs
3 | 2 | 4 | 5 | 5 | 1 | 0 | 3.2.5.5.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 5 | 5 | 1 | 1 | 3.2.4.5.5.1.1 | PMR For Safety Signs | BK-GCS-PEDCO-120-SA-MR-0005 | BK-GCS-PEDCO-120-SA-MR-0005 | BK | GCS | PEDCO | 120 | SA | MR | 0005 | F0Z-709325 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 5 | 5 | 2 | 0 | 3.2.5.5.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 5 | 5 | 2 | 1 | 3.2.4.5.5.2.1 | TBE For Safety Signs | BK-GCS-PEDCO-120-SA-TB-0005 | BK-GCS-PEDCO-120-SA-TB-0005 | BK | GCS | PEDCO | 120 | SA | TB | 0005 | F0Z-709326 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 0 | 0 | 0 | 3.2.4.6 | Electrical
3 | 2 | 4 | 6 | 1 | 0 | 0 | 3.2.4.6.1 | Transformers
3 | 2 | 4 | 6 | 1 | 1 | 0 | 3.2.6.1.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 1 | 1 | 1 | 3.2.4.6.1.1.1 | PMR For Transformers | BK-GCS-PEDCO-120-EL-MR-0001 | BK-GCS-PEDCO-120-EL-MR-0001 | BK | GCS | PEDCO | 120 | EL | MR | 0001 | F0Z-709327 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 1 | 2 | 0 | 3.2.6.1.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 1 | 2 | 1 | 3.2.4.6.1.2.1 | TBE For Transformers | BK-GCS-PEDCO-120-EL-TB-0001 | BK-GCS-PEDCO-120-EL-TB-0001 | BK | GCS | PEDCO | 120 | EL | TB | 0001 | F0Z-709328 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 2 | 0 | 0 | 3.2.4.6.2 | LV Switchgear & MCC
3 | 2 | 4 | 6 | 2 | 1 | 0 | 3.2.6.2.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 2 | 1 | 1 | 3.2.4.6.2.1.1 | PMR For LV Switchgear, MCC | BK-GCS-PEDCO-120-EL-MR-0002 | BK-GCS-PEDCO-120-EL-MR-0002 | BK | GCS | PEDCO | 120 | EL | MR | 0002 | F0Z-709329 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 2 | 2 | 0 | 3.2.6.2.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 2 | 2 | 1 | 3.2.4.6.2.2.1 | TBE For LV Switchgear, MCC | BK-GCS-PEDCO-120-EL-TB-0002 | BK-GCS-PEDCO-120-EL-TB-0002 | BK | GCS | PEDCO | 120 | EL | TB | 0002 | F0Z-709330 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 3 | 0 | 0 | 3.2.4.6.3 | Existent MV Switchgear Expansion
3 | 2 | 4 | 6 | 3 | 1 | 0 | 3.2.6.3.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 3 | 1 | 1 | 3.2.4.6.3.1.1 | PMR For Existent MV Switchgear Expansion & RCP | BK-GCS-PEDCO-120-EL-MR-0003 | BK-GCS-PEDCO-120-EL-MR-0003 | BK | GCS | PEDCO | 120 | EL | MR | 0003 | F0Z-709331 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 3 | 2 | 0 | 3.2.6.3.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 3 | 2 | 1 | 3.2.4.6.3.2.1 | TBE For Existent MV Switchgear Expansion & RCP | BK-GCS-PEDCO-120-EL-TB-0003 | BK-GCS-PEDCO-120-EL-TB-0003 | BK | GCS | PEDCO | 120 | EL | TB | 0003 | F0Z-709332 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 4 | 0 | 0 | 3.2.4.6.4 | Emergency Diesel Generator
3 | 2 | 4 | 6 | 4 | 1 | 0 | 3.2.6.4.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 4 | 1 | 1 | 3.2.4.6.4.1.1 | PMR For Emergency Diesel Generator | BK-GCS-PEDCO-120-EL-MR-0004 | BK-GCS-PEDCO-120-EL-MR-0004 | BK | GCS | PEDCO | 120 | EL | MR | 0004 | F0Z-709333 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 4 | 2 | 0 | 3.2.6.4.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 4 | 2 | 1 | 3.2.4.6.4.2.1 | TBE For Emergency Diesel Generator | BK-GCS-PEDCO-120-EL-TB-0004 | BK-GCS-PEDCO-120-EL-TB-0004 | BK | GCS | PEDCO | 120 | EL | TB | 0004 | F0Z-709334 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 5 | 0 | 0 | 3.2.4.6.5 | UPS System
3 | 2 | 4 | 6 | 5 | 1 | 0 | 3.2.6.5.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 5 | 1 | 1 | 3.2.4.6.5.1.1 | PMR For UPS System | BK-GCS-PEDCO-120-EL-MR-0005 | BK-GCS-PEDCO-120-EL-MR-0005 | BK | GCS | PEDCO | 120 | EL | MR | 0005 | F0Z-709335 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 5 | 2 | 0 | 3.2.6.5.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 5 | 2 | 1 | 3.2.4.6.5.2.1 | TBE For UPS System | BK-GCS-PEDCO-120-EL-TB-0005 | BK-GCS-PEDCO-120-EL-TB-0005 | BK | GCS | PEDCO | 120 | EL | TB | 0005 | F0Z-709336 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 6 | 0 | 0 | 3.2.4.6.6 | DC Charger
3 | 2 | 4 | 6 | 6 | 1 | 0 | 3.2.6.6.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 6 | 1 | 1 | 3.2.4.6.6.1.1 | PMR For DC Charger | BK-GCS-PEDCO-120-EL-MR-0006 | BK-GCS-PEDCO-120-EL-MR-0006 | BK | GCS | PEDCO | 120 | EL | MR | 0006 | F0Z-709337 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 6 | 2 | 0 | 3.2.6.6.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 6 | 2 | 1 | 3.2.4.6.6.2.1 | TBE For DC Charger | BK-GCS-PEDCO-120-EL-TB-0006 | BK-GCS-PEDCO-120-EL-TB-0006 | BK | GCS | PEDCO | 120 | EL | TB | 0006 | F0Z-709338 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 7 | 0 | 0 | 3.2.4.6.7 | Lighting & Distribution Panels
3 | 2 | 4 | 6 | 7 | 1 | 0 | 3.2.6.7.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 7 | 1 | 1 | 3.2.4.6.7.1.1 | PMR For Lighting & Distribution Panels | BK-GCS-PEDCO-120-EL-MR-0007 | BK-GCS-PEDCO-120-EL-MR-0007 | BK | GCS | PEDCO | 120 | EL | MR | 0007 | F0Z-709339 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 7 | 2 | 0 | 3.2.6.7.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 7 | 2 | 1 | 3.2.4.6.7.2.1 | TBE For Lighting & Distribution Panels | BK-GCS-PEDCO-120-EL-TB-0007 | BK-GCS-PEDCO-120-EL-TB-0007 | BK | GCS | PEDCO | 120 | EL | TB | 0007 | F0Z-709340 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 8 | 0 | 0 | 3.2.4.6.8 | Lighting and Small Power Equipment
3 | 2 | 4 | 6 | 8 | 1 | 0 | 3.2.6.8.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 8 | 1 | 1 | 3.2.4.6.8.1.1 | PMR For Lighting and Small Power Equipment | BK-GCS-PEDCO-120-EL-MR-0008 | BK-GCS-PEDCO-120-EL-MR-0008 | BK | GCS | PEDCO | 120 | EL | MR | 0008 | F0Z-709341 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 8 | 2 | 0 | 3.2.6.8.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 8 | 2 | 1 | 3.2.4.6.8.2.1 | TBE For Lighting and Small Power Equipment | BK-GCS-PEDCO-120-EL-TB-0008 | BK-GCS-PEDCO-120-EL-TB-0008 | BK | GCS | PEDCO | 120 | EL | TB | 0008 | F0Z-709342 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 9 | 0 | 0 | 3.2.4.6.9 | Earthing & Lightning System
3 | 2 | 4 | 6 | 9 | 1 | 0 | 3.2.6.9.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 9 | 1 | 1 | 3.2.4.6.9.1.1 | PMR For Earthing & Lightning System | BK-GCS-PEDCO-120-EL-MR-0009 | BK-GCS-PEDCO-120-EL-MR-0009 | BK | GCS | PEDCO | 120 | EL | MR | 0009 | F0Z-709343 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 9 | 2 | 0 | 3.2.6.9.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 9 | 2 | 1 | 3.2.4.6.9.2.1 | TBE For Earthing & Lightning System | BK-GCS-PEDCO-120-EL-TB-0009 | BK-GCS-PEDCO-120-EL-TB-0009 | BK | GCS | PEDCO | 120 | EL | TB | 0009 | F0Z-709344 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 10 | 0 | 0 | 3.2.4.6.10 | Local Control Station (LCS)
3 | 2 | 4 | 6 | 10 | 1 | 0 | 3.2.6.10.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 10 | 1 | 1 | 3.2.4.6.10.1.1 | PMR For Local Control Station (LCS) | BK-GCS-PEDCO-120-EL-MR-0010 | BK-GCS-PEDCO-120-EL-MR-0010 | BK | GCS | PEDCO | 120 | EL | MR | 0010 | F0Z-709345 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 10 | 2 | 0 | 3.2.6.10.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 10 | 2 | 1 | 3.2.4.6.10.2.1 | TBE For Local Control Station (LCS) | BK-GCS-PEDCO-120-EL-TB-0010 | BK-GCS-PEDCO-120-EL-TB-0010 | BK | GCS | PEDCO | 120 | EL | TB | 0010 | F0Z-709346 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 11 | 0 | 0 | 3.2.4.6.11 | Capacitor Bank
3 | 2 | 4 | 6 | 11 | 1 | 0 | 3.2.6.11.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 11 | 1 | 1 | 3.2.4.6.11.1.1 | PMR For Capacitor Bank | BK-GCS-PEDCO-120-EL-MR-0011 | BK-GCS-PEDCO-120-EL-MR-0011 | BK | GCS | PEDCO | 120 | EL | MR | 0011 | F0Z-709347 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 11 | 2 | 0 | 3.2.6.11.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 11 | 2 | 1 | 3.2.4.6.11.2.1 | TBE For Capacitor Bank | BK-GCS-PEDCO-120-EL-TB-0011 | BK-GCS-PEDCO-120-EL-TB-0011 | BK | GCS | PEDCO | 120 | EL | TB | 0011 | F0Z-709348 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 12 | 0 | 0 | 3.2.4.6.12 | NGR System
3 | 2 | 4 | 6 | 12 | 1 | 0 | 3.2.6.12.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 12 | 1 | 1 | 3.2.4.6.12.1.1 | PMR For NGR | BK-GCS-PEDCO-120-EL-MR-0012 | BK-GCS-PEDCO-120-EL-MR-0012 | BK | GCS | PEDCO | 120 | EL | MR | 0012 | F0Z-709349 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 12 | 2 | 0 | 3.2.6.12.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 12 | 2 | 1 | 3.2.4.6.12.2.1 | TBE For NGR | BK-GCS-PEDCO-120-EL-TB-0012 | BK-GCS-PEDCO-120-EL-TB-0012 | BK | GCS | PEDCO | 120 | EL | TB | 0012 | F0Z-709350 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 13 | 0 | 0 | 3.2.4.6.13 | Cathodic Protection System
3 | 2 | 4 | 6 | 13 | 1 | 0 | 3.2.6.13.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 13 | 1 | 1 | 3.2.4.6.13.1.1 | PMR For Cathodic Protection System | BK-GCS-PEDCO-120-EL-MR-0013 | BK-GCS-PEDCO-120-EL-MR-0013 | BK | GCS | PEDCO | 120 | EL | MR | 0013 | F0Z-709351 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 13 | 2 | 0 | 3.2.6.13.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 13 | 2 | 1 | 3.2.4.6.13.2.1 | TBE For Cathodic Protection System | BK-GCS-PEDCO-120-EL-TB-0013 | BK-GCS-PEDCO-120-EL-TB-0013 | BK | GCS | PEDCO | 120 | EL | TB | 0013 | F0Z-709352 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 14 | 0 | 0 | 3.2.4.6.14 | Power & Control Cables
3 | 2 | 4 | 6 | 14 | 1 | 0 | 3.2.6.14.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 14 | 1 | 1 | 3.2.4.6.14.1.1 | PMR For Power & Control Cables | BK-GCS-PEDCO-120-EL-MR-0014 | BK-GCS-PEDCO-120-EL-MR-0014 | BK | GCS | PEDCO | 120 | EL | MR | 0014 | F0Z-709353 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 14 | 2 | 0 | 3.2.6.14.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 14 | 2 | 1 | 3.2.4.6.14.2.1 | TBE For Power & Control Cables | BK-GCS-PEDCO-120-EL-TB-0014 | BK-GCS-PEDCO-120-EL-TB-0014 | BK | GCS | PEDCO | 120 | EL | TB | 0014 | F0Z-709354 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 15 | 0 | 0 | 3.2.4.6.15 | Tray/Ladder and Accessories
3 | 2 | 4 | 6 | 15 | 1 | 0 | 3.2.6.15.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 15 | 1 | 1 | 3.2.4.6.15.1.1 | PMR For Tray/Ladder and Accessories | BK-GCS-PEDCO-120-EL-MR-0015 | BK-GCS-PEDCO-120-EL-MR-0015 | BK | GCS | PEDCO | 120 | EL | MR | 0015 | F0Z-709355 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 15 | 2 | 0 | 3.2.6.15.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 15 | 2 | 1 | 3.2.4.6.15.2.1 | TBE For Tray/Ladder and Accessories | BK-GCS-PEDCO-120-EL-TB-0015 | BK-GCS-PEDCO-120-EL-TB-0015 | BK | GCS | PEDCO | 120 | EL | TB | 0015 | F0Z-709356 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 16 | 0 | 0 | 3.2.4.6.16 | Electrical Bulk Items
3 | 2 | 4 | 6 | 16 | 1 | 0 | 3.2.6.16.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 16 | 1 | 1 | 3.2.4.6.16.1.1 | PMR For Electrical Bulk Items | BK-GCS-PEDCO-120-EL-MR-0016 | BK-GCS-PEDCO-120-EL-MR-0016 | BK | GCS | PEDCO | 120 | EL | MR | 0016 | F0Z-709357 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 16 | 2 | 0 | 3.2.6.16.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 16 | 2 | 1 | 3.2.4.6.16.2.1 | TBE For Electrical Bulk Items | BK-GCS-PEDCO-120-EL-TB-0016 | BK-GCS-PEDCO-120-EL-TB-0016 | BK | GCS | PEDCO | 120 | EL | TB | 0016 | F0Z-709358 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 16 | 2 | 2 | 3.2.4.6.16.2.2 | Telecomm UPS
3 | 2 | 4 | 6 | 16 | 2 | 3 | 3.2.4.6.16.2.3 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 6 | 16 | 2 | 4 | 3.2.4.6.16.2.4 | PMR For UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-MR-0017 | BK-GCS-PEDCO-120-EL-MR-0017 | BK | GCS | PEDCO | 120 | EL | MR | 0017 | F0Z-709359 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 6 | 16 | 2 | 5 | 3.2.4.6.16.2.5 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 6 | 16 | 2 | 6 | 3.2.4.6.16.2.6 | TBE for UPS of CCTV in Desalting, Production & CS Unit | BK-GCS-PEDCO-120-EL-TB-0017 | BK-GCS-PEDCO-120-EL-TB-0017 | BK | GCS | PEDCO | 120 | EL | TB | 0017 | F0Z-709360 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 7 | 0 | 0 | 0 | 3.2.4.7 | Intercom. & Telecomm.
3 | 2 | 4 | 7 | 1 | 0 | 0 | 3.2.4.7.1 | CCTV System
3 | 2 | 4 | 7 | 1 | 1 | 0 | 3.2.7.1.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 7 | 1 | 1 | 1 | 3.2.4.7.1.1.1 | PMR For CCTV System | BK-GCS-PEDCO-120-TE-MR-0001 | BK-GCS-PEDCO-120-TE-MR-0001 | [7 empty] | - | [43 empty] | Moved to IN | 0
3 | 2 | 4 | 7 | 1 | 2 | 0 | 3.2.7.1.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 7 | 1 | 2 | 1 | 3.2.4.7.1.2.1 | TBE For CCTV System | BK-GCS-PEDCO-120-TE-TB-0001 | BK-GCS-PEDCO-120-TE-TB-0001 | [7 empty] | - | [43 empty] | Moved to IN | 0
3 | 2 | 4 | 7 | 2 | 0 | 0 | 3.2.4.7.2 | PAGA System
3 | 2 | 4 | 7 | 2 | 1 | 0 | 3.2.7.2.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 7 | 2 | 1 | 1 | 3.2.4.7.2.1.1 | PMR For PAGA System | BK-GCS-PEDCO-120-TE-MR-0002 | BK-GCS-PEDCO-120-TE-MR-0002 | BK | GCS | PEDCO | 120 | TE | MR | 0002 | F0Z-709361 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 7 | 2 | 2 | 0 | 3.2.7.2.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 7 | 2 | 2 | 1 | 3.2.4.7.2.2.1 | TBE For PAGA System | BK-GCS-PEDCO-120-TE-TB-0002 | BK-GCS-PEDCO-120-TE-TB-0002 | BK | GCS | PEDCO | 120 | TE | TB | 0002 | F0Z-709362 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 7 | 3 | 0 | 0 | 3.2.4.7.3 | PABX System
3 | 2 | 4 | 7 | 3 | 1 | 0 | 3.2.7.3.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 7 | 3 | 1 | 1 | 3.2.4.7.3.1.1 | PMR For PABX System | BK-GCS-PEDCO-120-TE-MR-0003 | BK-GCS-PEDCO-120-TE-MR-0003 | BK | GCS | PEDCO | 120 | TE | MR | 0003 | F0Z-709363 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 7 | 3 | 2 | 0 | 3.2.7.3.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 7 | 3 | 2 | 1 | 3.2.4.7.3.2.1 | TBE For PABX System | BK-GCS-PEDCO-120-TE-TB-0003 | BK-GCS-PEDCO-120-TE-TB-0003 | BK | GCS | PEDCO | 120 | TE | TB | 0003 | F0Z-709364 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 7 | 4 | 0 | 0 | 3.2.4.7.4 | Radio System
3 | 2 | 4 | 7 | 4 | 1 | 0 | 3.2.7.4.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 7 | 4 | 1 | 1 | 3.2.4.7.4.1.1 | PMR For Radio System | BK-GCS-PEDCO-120-TE-MR-0004 | BK-GCS-PEDCO-120-TE-MR-0004 | BK | GCS | PEDCO | 120 | TE | MR | 0004 | F0Z-709365 | IFI | IFI | 44564 | 44578 | 44583 | 14 | 5 | 19 | IFI | 44618 | 44614 | 44594 | -4 | -20 | -24 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 2021-12-20 | 2022-02-12 |  | D01 | IFI | T-0573 | 2022-02-12 | 1400/11/23 | 0 | 0 | 0 | BK-SUR-ENG-TEL-00-03038 | 2022-02-13 | 1400/11/24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400-2294-421706 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-MR-0004_D00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | D00 | IFI | T-0370 | 2021-12-20 | 1400/09/29 |  |  |  | BK-SUR-ENG-TEL-00-02394 | 2021-12-21 | 1400/09/30 | AP | [6 empty] | 1400-2294-368603 | 2022-01-17 | 1400/10/27 | 2022-01-22 | 1400/11/22 | CM | [10 empty] | D01 | IFI | T-0573 | 2022-02-12 | 1400/11/23 |  |  |  | BK-SUR-ENG-TEL-00-03038 | 2022-02-13 | 1400/11/24 | [7 empty] | 1400-2294-421706 | 2022-02-22 | 1400/12/03 | 2022-02-02 | 1400/12/11 | AP | NISOC-CRS-BK-GCS-PEDCO-120-TE-MR-0004_D00
3 | 2 | 4 | 7 | 4 | 2 | 0 | 3.2.7.4.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 7 | 4 | 2 | 1 | 3.2.4.7.4.2.1 | TBE For Radio System | BK-GCS-PEDCO-120-TE-TB-0004 | BK-GCS-PEDCO-120-TE-TB-0004 | BK | GCS | PEDCO | 120 | TE | TB | 0004 | F0Z-709366 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 7 | 5 | 0 | 0 | 3.2.4.7.5 | Telecomm. Cable
3 | 2 | 4 | 7 | 5 | 1 | 0 | 3.2.7.5.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 7 | 5 | 1 | 1 | 3.2.4.7.5.1.1 | PMR For Telecomm. Cable | BK-GCS-PEDCO-120-TE-MR-0005 | BK-GCS-PEDCO-120-TE-MR-0005 | BK | GCS | PEDCO | 120 | TE | MR | 0005 | F0Z-709367 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 7 | 5 | 2 | 0 | 3.2.7.5.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 7 | 5 | 2 | 1 | 3.2.4.7.5.2.1 | TBE For Telecomm. Cable | BK-GCS-PEDCO-120-TE-TB-0005 | BK-GCS-PEDCO-120-TE-TB-0005 | BK | GCS | PEDCO | 120 | TE | TB | 0005 | F0Z-709368 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 7 | 6 | 0 | 0 | 3.2.4.7.6 | Telecommunication Tower
3 | 2 | 4 | 7 | 6 | 1 | 0 | 3.2.7.6.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 7 | 6 | 1 | 1 | 3.2.4.7.6.1.1 | PMR For Telecommunication Tower | BK-GCS-PEDCO-120-TE-MR-0006 | BK-GCS-PEDCO-120-TE-MR-0006 | BK | GCS | PEDCO | 120 | TE | MR | 0006 | F0Z-709369 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 7 | 6 | 2 | 0 | 3.2.7.6.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 7 | 6 | 2 | 1 | 3.2.4.7.6.2.1 | TBE For Telecommunication Tower | BK-GCS-PEDCO-120-TE-TB-0006 | BK-GCS-PEDCO-120-TE-TB-0006 | BK | GCS | PEDCO | 120 | TE | TB | 0006 | F0Z-709370 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 8 | 0 | 0 | 0 | 3.2.4.8 | Structure
3 | 2 | 4 | 8 | 1 | 0 | 0 | 3.2.4.8.1 | Steel Structure
3 | 2 | 4 | 8 | 1 | 1 | 0 | 3.2.8.1.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 8 | 1 | 1 | 1 | 3.2.4.8.1.1.1 | PMR For Steel Structure Items | BK-GCS-PEDCO-120-ST-MR-0001 | BK-GCS-PEDCO-120-ST-MR-0001 | BK | GCS | PEDCO | 120 | ST | MR | 0001 | F0Z-709371 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 8 | 1 | 2 | 0 | 3.2.8.1.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 8 | 1 | 2 | 1 | 3.2.4.8.1.2.1 | TBE For Steel Structure Items | BK-GCS-PEDCO-120-ST-TB-0001 | BK-GCS-PEDCO-120-ST-TB-0001 | BK | GCS | PEDCO | 120 | ST | TB | 0001 | F0Z-709372 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 8 | 2 | 0 | 0 | 3.2.4.8.2 | Anchor Bolts
3 | 2 | 4 | 8 | 2 | 1 | 0 | 3.2.8.2.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 8 | 2 | 1 | 1 | 3.2.4.8.2.1.1 | PMR For Anchor Bolts | BK-GCS-PEDCO-120-ST-MR-0002 | BK-GCS-PEDCO-120-ST-MR-0002 | BK | GCS | PEDCO | 120 | ST | MR | 0002 | F0Z-709373 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 8 | 2 | 2 | 0 | 3.2.8.2.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 8 | 2 | 2 | 1 | 3.2.4.8.2.2.1 | TBE For Anchor Bolts | BK-GCS-PEDCO-120-ST-TB-0002 | BK-GCS-PEDCO-120-ST-TB-0002 | BK | GCS | PEDCO | 120 | ST | TB | 0002 | F0Z-709374 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 8 | 3 | 0 | 0 | 3.2.4.8.3 | Blast Proof Doors
3 | 2 | 4 | 8 | 3 | 1 | 0 | 3.2.8.3.1 | Purchase Material Requisition (PMR)
3 | 2 | 4 | 8 | 3 | 1 | 1 | 3.2.4.8.3.1.1 | PMR For Blast Proof Doors | BK-GCS-PEDCO-120-ST-MR-0003 | BK-GCS-PEDCO-120-ST-MR-0003 | BK | GCS | PEDCO | 120 | ST | MR | 0003 | F0Z-709375 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 4 | 8 | 3 | 2 | 0 | 3.2.8.3.2 | Technical Bid Evaluation (TBE)
3 | 2 | 4 | 8 | 3 | 2 | 1 | 3.2.4.8.3.2.1 | TBE For Blast Proof Doors | BK-GCS-PEDCO-120-ST-TB-0003 | BK-GCS-PEDCO-120-ST-TB-0003 | BK | GCS | PEDCO | 120 | ST | TB | 0003 | F0Z-709376 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 5 | 0 | 0 | 0 | 0 | 3.2.5 | Commissioning Engineering
3 | 2 | 5 | 0 | 1 | 0 | 0 | 3.2.5.1 | Procedure/Plan
3 | 2 | 5 | 0 | 1 | 0 | 1 | 3.2.5 | Pre-Commissioning, Commissioning & Startup Procedure | BK-GCS-PEDCO-120-CO-PR-0001 | BK-GCS-PEDCO-120-CO-PR-0001 | BK | GCS | PEDCO | 120 | CO | PR | 0001 | F0Z-709377 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 6 | 0 | 0 | 0 | 0 | 3.2.6 | Field Engineering
3 | 2 | 6 | 0 | 1 | 0 | 0 | 3.2.6.1 | Query
3 | 2 | 6 | 0 | 1 | 0 | 1 | 3.2.6.1.1 | Technical/Site Queries | BK-GCS-PEDCO-120-GE-TQ-0001 | BK-GCS-PEDCO-120-GE-TQ-0001 | BK | GCS | PEDCO | 120 | GE | TQ | 0001 | F0Z-709378 | AFC | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 6 | 0 | 2 | 0 | 0 | 3.2.6.2 | Dossier
3 | 2 | 6 | 0 | 2 | 0 | 1 | 3.2.6 | As-Built Document Booklets | BK-GCS-PEDCO-120-GE-DO-0001 | BK-GCS-PEDCO-120-GE-DO-0001 | BK | GCS | PEDCO | 120 | GE | DO | 0001 | F0Z-709379 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 7 | 0 | 0 | 0 | 0 | 3.2.7 | Engineering Final Documentation
3 | 2 | 7 | 0 | 1 | 0 | 0 | 3.2.7.1 | Manual
3 | 2 | 7 | 0 | 1 | 0 | 1 | 3.2.7.1.1 | Operating Manual | BK-GCS-PEDCO-120-GE-ML-0001 | BK-GCS-PEDCO-120-GE-ML-0001 | BK | GCS | PEDCO | 120 | GE | ML | 0001 | F0Z-709380 | IFI | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
3 | 2 | 7 | 0 | 2 | 0 | 0 | 3.2.7.2 | Dossier
3 | 2 | 7 | 0 | 2 | 0 | 1 | 3 | As-Built Document Booklets | BK-GCS-PEDCO-120-GE-DO-0001 | BK-GCS-PEDCO-120-GE-DO-0001 | [7 empty] | F0Z-709379 | [43 empty] | Moved to Field | 0
3 | 2 | 7 | 0 | 2 | 0 | 2 | 3 | Final Engineering Dossier | BK-GCS-PEDCO-120-GE-DO-0002 | BK-GCS-PEDCO-120-GE-DO-0002 | BK | GCS | PEDCO | 120 | GE | DO | 0002 | F0Z-709381 | AB-A | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | 0 | 14 | 0 | 0 | -14 | 0 | -14 | Modify | 0 | 0
[142 empty] | BK-SUR-ENG-ELE-01-04489 | 2022-05-29 | 1401/03/09 | AP
[145 empty] | 0 | [26 empty] | 0
Formulas:
Issue+14 = [Issue Date]+14
NISOC Date = MAX([NISOC Comment Date],[NISOC Comment Date])
Email Date = MAX([EMAIL DATE],[EMAIL DATE])
NISOC Delay = [NISOC Date]-[Issue+14]
Total Delay = [Email Delay]+[NISOC Delay]
Status = [Last POI]
Actual Start Date = IF(ISNUMBER(SEARCH("PEDCO",[Doc. No.])),IF([NISOC Comment Status]<>"RJ",[Issue Date],IF([NISOC Comment Status]<>"RJ",[Issue Date],IF([NISOC Comment Status]<>"RJ",[Issue Date],IF([NISOC Comment Status]<>"RJ",[Issue Date],"H")))),IF([PEDCO Comment Status]<>"C4-RJ",[Issue Date],IF([PEDCO Comment Status]<>"C4-RJ",[Issue Date],IF([PEDCO Comment Status]<>"C4-RJ",[Issue Date],IF([PEDCO Comment Status]<>"C4-RJ",[Issue Date])))))
Actual Finish Date = IF([Last POI]=[Final Status],[Issue Date],)
Issue Date = IF([Rev. D10]<>"",[Issue Date],(IF([Rev. D09]<>"",[Issue Date],(IF([Rev. D08]<>"",[Issue Date],(IF([Rev. D07]<>"",[Issue Date],(IF([Rev. D06]<>"",[Issue Date],(IF([Rev. D05]<>"",[Issue Date],(IF([Rev. D04]<>"",[Issue Date],(IF([Rev. D03]<>"",[Issue Date],(IF([Rev. D02]<>"",[Issue Date],(IF([Rev. D01]<>"",[Issue Date],(IF([Rev. D00]<>"",[Issue Date],"")))))))))))))))))))))
NISOC Transmittal NO. = IF([Last POI]<>"",[NISOC Transmittal NO.],(IF([Last POI]<>"",[NISOC Transmittal NO.],(IF([Last POI]<>"",[NISOC Transmittal NO.],(IF([Last POI]<>"",[NISOC Transmittal NO.],(IF([Last POI]<>"",[NISOC Transmittal NO.],(IF([Last POI]<>"",[NISOC Transmittal NO.],(IF([Last POI]<>"",[NISOC Transmittal NO.],(IF([Last POI]<>"",[NISOC Transmittal NO.],(IF([Last POI]<>"",[NISOC Transmittal NO.],(IF([Last POI]<>"",[NISOC Transmittal NO.],(IF([Last POI]<>"",[NISOC Transmittal NO.],"")))))))))))))))))))))
NISOC Issue Date = IF([Last Transmittal NO.]<>"",[NISOC Issue Date],(IF([Last Transmittal NO.]<>"",[NISOC Issue Date],(IF([Last Transmittal NO.]<>"",[NISOC Issue Date],(IF([Last Transmittal NO.]<>"",[NISOC Issue Date],(IF([Last Transmittal NO.]<>"",[NISOC Issue Date],(IF([Last Transmittal NO.]<>"",[NISOC Issue Date],(IF([Last Transmittal NO.]<>"",[NISOC Issue Date],(IF([Last Transmittal NO.]<>"",[NISOC Issue Date],(IF([Last Transmittal NO.]<>"",[NISOC Issue Date],(IF([Last Transmittal NO.]<>"",[NISOC Issue Date],(IF([Last Transmittal NO.]<>"",[NISOC Issue Date],"")))))))))))))))))))))
NISOC Issue Date (Farsi) = IF([Issue Date]<>"",[NISOC Issue Date (Farsi)],(IF([Issue Date]<>"",[NISOC Issue Date (Farsi)],(IF([Issue Date]<>"",[NISOC Issue Date (Farsi)],(IF([Issue Date]<>"",[NISOC Issue Date (Farsi)],(IF([Issue Date]<>"",[NISOC Issue Date (Farsi)],(IF([Issue Date]<>"",[NISOC Issue Date (Farsi)],(IF([Issue Date]<>"",[NISOC Issue Date (Farsi)],(IF([Issue Date]<>"",[NISOC Issue Date (Farsi)],(IF([Issue Date]<>"",[NISOC Issue Date (Farsi)],(IF([Issue Date]<>"",[NISOC Issue Date (Farsi)],(IF([Issue Date]<>"",[NISOC Issue Date (Farsi)],"")))))))))))))))))))))
PEDCO Comment Date = IF([Rev. D10]<>"",[PEDCO Comment Date],(IF([Rev. D09]<>"",[PEDCO Comment Date],(IF([Rev. D08]<>"",[PEDCO Comment Date],(IF([Rev. D07]<>"",[PEDCO Comment Date],(IF([Rev. D06]<>"",[PEDCO Comment Date],(IF([Rev. D05]<>"",[PEDCO Comment Date],(IF([Rev. D04]<>"",[PEDCO Comment Date],(IF([Rev. D03]<>"",[PEDCO Comment Date],(IF([Rev. D02]<>"",[PEDCO Comment Date],(IF([Rev. D01]<>"",[PEDCO Comment Date],(IF([Rev. D00]<>"",[PEDCO Comment Date],"")))))))))))))))))))))
PEDCO Comment Date (Farsi) = IF([Rev. D10]<>"",[PEDCO Comment Date (Farsi)],(IF([Rev. D09]<>"",[PEDCO Comment Date (Farsi)],(IF([Rev. D08]<>"",[PEDCO Comment Date (Farsi)],(IF([Rev. D07]<>"",[PEDCO Comment Date (Farsi)],(IF([Rev. D06]<>"",[PEDCO Comment Date (Farsi)],(IF([Rev. D05]<>"",[PEDCO Comment Date (Farsi)],(IF([Rev. D04]<>"",[PEDCO Comment Date (Farsi)],(IF([Rev. D03]<>"",[PEDCO Comment Date (Farsi)],(IF([Rev. D02]<>"",[PEDCO Comment Date (Farsi)],(IF([Rev. D01]<>"",[PEDCO Comment Date (Farsi)],(IF([Rev. D00]<>"",[PEDCO Comment Date (Farsi)],"")))))))))))))))))))))
NISOC Comment Date = IF([Rev. D10]<>"",[NISOC Comment Date],(IF([Rev. D09]<>"",[NISOC Comment Date],(IF([Rev. D08]<>"",[NISOC Comment Date],(IF([Rev. D07]<>"",[NISOC Comment Date],(IF([Rev. D06]<>"",[NISOC Comment Date],(IF([Rev. D05]<>"",[NISOC Comment Date],(IF([Rev. D04]<>"",[NISOC Comment Date],(IF([Rev. D03]<>"",[NISOC Comment Date],(IF([Rev. D02]<>"",[NISOC Comment Date],(IF([Rev. D01]<>"",[NISOC Comment Date],(IF([Rev. D00]<>"",[NISOC Comment Date],"")))))))))))))))))))))
NISOC Comment Date (Farsi) = IF([Rev. D10]<>"",[NISOC Comment Date (Farsi)],(IF([Rev. D09]<>"",[NISOC Comment Date (Farsi)],(IF([Rev. D08]<>"",[NISOC Comment Date (Farsi)],(IF([Rev. D07]<>"",[NISOC Comment Date (Farsi)],(IF([Rev. D06]<>"",[NISOC Comment Date (Farsi)],(IF([Rev. D05]<>"",[NISOC Comment Date (Farsi)],(IF([Rev. D04]<>"",[NISOC Comment Date (Farsi)],(IF([Rev. D03]<>"",[NISOC Comment Date (Farsi)],(IF([Rev. D02]<>"",[NISOC Comment Date (Farsi)],(IF([Rev. D01]<>"",[NISOC Comment Date (Farsi)],(IF([Rev. D00]<>"",[NISOC Comment Date (Farsi)],"")))))))))))))))))))))
EMAIL DATE = IF([Last POI]<>"",[c],(IF([Last POI]<>"",[EMAIL DATE],(IF([Last POI]<>"",[EMAIL DATE],(IF([Last POI]<>"",[EMAIL DATE],(IF([Last POI]<>"",[EMAIL DATE],(IF([Last POI]<>"",[EMAIL DATE],(IF([Last POI]<>"",[EMAIL DATE],(IF([Last POI]<>"",[EMAIL DATE],(IF([Last POI]<>"",[EMAIL DATE],(IF([Last POI]<>"",[EMAIL DATE],(IF([Last POI]<>"",[EMAIL DATE],"")))))))))))))))))))))
EMAIL DATE(FARSI) = IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE (FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE (FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE (FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE (FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],"")))))))))))))))))))))
EMAIL DATE(FARSI) = IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE (FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],(IF([Last Transmittal NO.]<>"",[EMAIL DATE(FARSI)],"")))))))))))))))))))))
Email Delay = [Email Date]-[NISOC Date]
total Delay = [Email Delay]+[NISOC Delay]
PEDCO Comment Status = [PEDCO Comment Date (Farsi), row below]

## NISOC Delay-DOCS (hidden)
|  |  |  | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 19 | 20 | 21 | 22 | 23 | 24 | 25 |  | 26 | 27 | 28 | 29 | 30 | 31 | 32 |  | 33 | 34 | 35 | 36 | 37 | 38 | 39 |  | 40 | 41 | 42 | 43 | 44 | 45 | 46 |  | 47 | 48 | 49 | 50 | 51 | 52 | 53
شماره (ID A s) | نام بسته كاري | نام فعالیت اصلی | Doc code | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Note | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Note | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Note | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Note | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Note | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  |  | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | Total Delay |  | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | Total Delay |  | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay |  | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay |  | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay |  | Status | Issue+14 | NISOC Date | Email Date | NISOC Delay | Email Delay | total Delay
P12-EPC-E1000 | ايستگاه گاز | Endorsement Report For Basic Design & Scope of Work | BK-GNRAL-PEDCO-000-PM-RT-0001 | IFC | 2021-08-14 | 2021-08-28 | 2021-09-07 | 14 | 10 | 24 |  | AFD | 2021-10-03 | 2021-10-06 | 2021-10-26 | 3 | 20 | 23 | [32 empty] | Endorsement Report For Basic Design & Scope of Work
P12-EPC-E1570 | ايستگاه گاز | Process Flow Diagram (PFD) | BK-GCS-PEDCO-120-PR-PF-0001 | IFC | 2021-08-28 | 2021-09-01 | 2021-09-06 | 4 | 5 | 9 |  | IFA | 2021-10-31 | 2021-11-28 | 2021-11-14 | 28 | -14 | 14 | 14 روز زودتر از تاریخ کامنت نیسوک، ای میل شده است | IFA | 2021-12-14 | 2021-12-30 | 2022-01-02 | 16 | 3 | 19 |  | IFA | 2022-01-22 | 2022-02-12 | 2022-02-22 | 21 | 10 | 31 |  | IFA | 2022-03-26 | 2022-04-21 | 2022-04-30 | 26 | 9 | 35 |  | 0 | [6 empty] | Process Flow Diagram (PFD)
P12-EPC-E1540 | ايستگاه گاز | Process Data Sheets For Gas Compressors Packages | BK-GCS-PEDCO-120-PR-DT-0030 | IFC | 2021-11-21 | 2021-11-18 | 2021-11-27 | -3 | 9 | 6 |  | IFA | 2022-01-15 | 2022-01-22 | 2022-01-29 | 7 | 7 | 14 |  | IFA | 2022-04-09 | 2022-05-04 | 2022-05-08 | 25 | 4 | 29 | [8 empty] | 24 روز هست که ویرایش جدید تولید نشده است | [15 empty] | Process Data Sheets For Gas Compressors Packages
P12-EPC-E2480 | ايستگاه گاز | Mechanical Data Sheets For Gas Compressors Packages | BK-GCS-PEDCO-120-ME-DT-0031 | IFC | 2021-09-26 | 2021-10-07 | 2021-10-11 | 11 | 4 | 15 |  | IFA | 2021-10-31 | 2021-11-04 | 2021-11-08 | 4 | 4 | 8 |  | IFA | 2021-11-28 | 2021-12-14 | 2021-12-20 | 16 | 6 | 22 |  | IFA | 2022-01-26 | 2022-02-22 | 2022-02-22 | 27 | 0 | 27 |  | IFA | 2022-03-19 | 2022-03-23 | 2022-03-26 | 4 | 3 | 7 |  | AFC | 2022-05-04 | 2022-04-28 | 2022-05-01 | -6 | 3 | -3 | Mechanical Data Sheets For Gas Compressors Packages
P12-EPC-E7980 | ايستگاه گاز | TBE For Gas Compressors | BK-GCS-PEDCO-120-ME-TB-0001 | IFI | 2022-02-16 | 2022-02-23 | 2022-02-27 | 7 | 4 | 11 |  | IFI | 2022-03-19 | 2022-05-01 | 2022-05-07 | 43 | 6 | 49 | [8 empty] | 25 روز هست که ویرایش جدید تولید نشده است | [23 empty] | TBE For Gas Compressors
P12-EPC-E7970 | ايستگاه گاز | PMR For Gas Compressors | BK-GCS-PEDCO-120-ME-MR-0001 | IFC | 2021-12-12 | 2021-12-13 | 2021-12-15 | 1 | 2 | 3 |  | IFI | 2022-01-18 | 2021-01-15 | 2022-01-30 | -368 | 380 | 12 | تاریخ کامنت نیسوک یک سال قبل از ارسال است | IFI | 2022-02-27 | 2022-03-01 | 2022-03-05 | 2 | 4 | 6 | [24 empty] | PMR For Gas Compressors
P01-EPC-E1060 | چاه شماره 18 | Process Flow Diagram - W018S | BK-W018S-PEDCO-110-PR-PF-0001 | IFC | 2021-08-18 | 2021-08-30 | 2021-09-07 | 12 | 8 | 20 |  | IFC | 2021-11-16 | 0 | 0 |  |  |  | از آبان ماه پارسال کامنت دریافت نشده است | [31 empty] | Process Flow Diagram - W018S
P01-EPC-E1370 | چاه شماره 18 | Plot Plan Drawing - W018S | BK-W018S-PEDCO-110-PI-PY-0001 | IFC | 2021-09-05 | 2021-09-26 | 2021-09-29 | 21 | 3 | 24 |  | IFA | 2021-11-29 | 2021-12-08 | 2021-12-12 | 9 | 4 | 13 |  | IFA | 2022-02-14 | 2022-02-26 | 2022-03-05 | 12 | 7 | 19 | [8 empty] | 88 روز هست که ویرایش جدید تولید نشده است | [15 empty] | Plot Plan Drawing - W018S
P01-EPC-E1860 | چاه شماره 18 | Specification For WHCP/HPU-W018S | BK-SSGRL-PEDCO-110-IN-SP-0001 | IFC | 2021-08-22 | 2021-09-18 | 2021-09-14 | 27 | -4 | 23 | 4 روز زودتر از تاریخ کامنت نیسوک، ای میل شده است | IFA | 2021-10-24 | 2021-12-30 | 2022-01-02 | 67 | 3 | 70 |  | IFA | 2022-01-24 | 2022-01-29 | 2022-01-30 | 5 | 1 | 6 |  | AFD | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | [16 empty] | Specification For WHCP/HPU-W018S
P01-EPC-E2470 | چاه شماره 18 | Rough Grading Plans -W018S | BK-W018S-PEDCO-110-CV-DW-0001 | IFC | 2021-08-11 | 2021-08-03 | 2021-08-07 | -8 | 4 | -4 |  | IFC | 2021-11-13 | 2021-11-02 | 2021-11-06 | -11 | 4 | -7 |  | IFA | 2022-01-29 | 2022-01-20 | 2022-01-22 | -9 | 2 | -7 |  | IFA | 2022-03-12 | 2022-03-02 | 2022-03-05 | -10 | 3 | -7 |  | AFC | 2022-03-27 | 2022-03-16 | 2022-03-27 | -11 | 11 | 0 |  | 0 | [6 empty] | Rough Grading Plans -W018S
P01-EPC-E1070 | چاه شماره 18 | P&ID - W018S | BK-W018S-PEDCO-110-PR-PI-0001 | IFC | 2021-08-23 | 2021-08-30 | 2021-09-06 | 7 | 7 | 14 |  | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 |  | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 |  | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 |  | 0 | [6 empty] | 31 روز هست که ویرایش جدید تولید نشده است | [7 empty] | P&ID - W018S
P01-EPC-E1300 | چاه شماره 18 | Piping Material Specification-W018S | BK-GNRAL-PEDCO-000-PI-SP-0017 | IFC | 2021-09-07 | 2021-09-12 | 2021-09-14 | 5 | 2 | 7 |  | IFA | 2021-10-18 | 2021-12-04 | 2021-11-08 | 47 | -26 | 21 | 26 روز زودتر از تاریخ کامنت نیسوک، ای میل شده است | AFD | 2021-12-29 | 0 | 0 |  |  |  | تایید روی AFD از کارفرما دریافت نشده است | [23 empty] | Piping Material Specification-W018S
P01-EPC-E1870 | چاه شماره 18 | Data Sheets For WHCP/HPU - Wellheads-W018S | BK-SSGRL-PEDCO-110-IN-DT-0001 | IFC | 2021-09-05 | 2021-09-15 | 2021-09-20 | 10 | 5 | 15 |  | IFA | 2021-11-23 | 2021-11-21 | 2021-11-27 | -2 | 6 | 4 |  | IFA | 2022-01-04 | 2022-01-06 | 2022-01-08 | 2 | 2 | 4 | [8 empty] | 144 روز هست که ویرایش جدید تولید نشده است | [15 empty] | Data Sheets For WHCP/HPU - Wellheads-W018S
P01-EPC-E2460 | چاه شماره 18 | Civil and Structural drawings - W018S | BK-W018S-PEDCO-110-CV-PY-0002 | IFC | 2021-08-11 | 2021-08-03 | 2021-08-07 | -8 | 4 | -4 |  | IFA | 2022-01-18 | 2022-01-08 | 2022-01-11 | -10 | 3 | -7 |  | AFC | 2022-03-19 | 0 | 0 | -44639 | 0 | -44639 | تایید روی AFC از کارفرما دریافت نشده است | [23 empty] | Civil and Structural drawings - W018S
P01-EPC-E2450 | چاه شماره 18 | General Civil Layout - W018S | BK-W018S-PEDCO-110-CV-PY-0001 | IFC | 2021-08-11 | 2021-08-03 | 2021-08-07 | -8 | 4 | -4 |  | IFA | 2021-09-11 | 2021-08-29 | 2021-09-04 | -13 | 6 | -7 |  | IFA | 2021-09-27 | 2021-09-18 | 2021-09-18 | -9 | 0 | -9 |  | IFA | 2021-11-06 | 2021-10-29 | 2021-11-02 | -8 | 4 | -4 |  | AFC | 2021-12-04 | 2021-11-23 | 2021-11-27 | -11 | 4 | -7 |  | AFC | 2022-01-10 | 2021-12-30 | 2022-01-02 | -11 | 3 | -8 | General Civil Layout - W018S
P01-EPC-E1810 | چاه شماره 18 | Pipeline Corrosion Study & Material Selection Report-W018S | BK-SSGRL-PEDCO-110-PL-RT-0001 | IFC | 2021-11-10 | 2021-11-16 | 2021-11-21 | 6 | 5 | 11 |  | IFA | 2021-12-18 | 0 | 0 | -44548 | 0 | -44548 | تاریخی بابت کامنت نیسوک ثبت نشده است (ویرایش بعدی ارسال شده است) | IFA | 2022-03-14 | 2022-03-16 | 2022-04-01 | 2 | 16 | 18 |  | 0 | [6 empty] | 61 روز هست که ویرایش جدید تولید نشده است | [15 empty] | Pipeline Corrosion Study & Material Selection Report-W018S
P01-EPC-E3590 | چاه شماره 18 | PMR For WHCP/HPU - W018S | BK-W018S-PEDCO-110-IN-MR-0001 | IFI | 2021-11-29 | 2021-12-17 | 2021-12-07 | 18 | -10 | 8 | 10 روز زودتر از تاریخ کامنت نیسوک، ای میل شده است | IFI | 2022-01-30 | 2022-01-31 | 2022-02-01 | 1 | 1 | 2 | [32 empty] | PMR For WHCP/HPU - W018S
P01-EPC-E3560 | چاه شماره 18 | PMR For Line pipes - W018S | BK-W018S-PEDCO-110-PL-MR-0001 | IFI | 2021-12-20 | 2021-12-13 | 2021-12-15 | -7 | 2 | -5 | [40 empty] | PMR For Line pipes - W018S
P02-EPC-E1060 | چاه شماره 28 | Process Flow Diagram - W028 | BK-W028-PEDCO-110-PR-PF-0001 | IFC | 2021-08-28 | 2021-08-30 | 2021-09-06 | 2 | 7 | 9 |  | IFC | 2021-11-16 | 0 | 0 | -44516 | 0 | -44516 | از آبان ماه پارسال کامنت دریافت نشده است | [31 empty] | Process Flow Diagram - W028
P02-EPC-E1380 | چاه شماره 28 | Plot Plan Drawing - W028 | BK-W028-PEDCO-110-PI-DW-0001 | IFC | 2022-02-16 | 2022-04-16 | 2022-04-25 | 59 | 9 | 68 |  | 0 | [6 empty] | نسخه جدیدی از مدرک از فرودین ماه ارسال نشده است | [31 empty] | Plot Plan Drawing - W028
P02-EPC-E1860 | چاه شماره 28 | Specification For WHCP/HPU - W028 | BK-SSGRL-PEDCO-110-IN-SP-0001 | IFC | 2021-08-22 | 2021-09-18 | 2021-09-14 | 27 | -4 | 23 | 4 روز زودتر از تاریخ کامنت نیسوک، ای میل شده است | IFA | 2021-10-24 | 2021-12-30 | 2022-01-02 | 67 | 3 | 70 |  | IFA | 2022-01-24 | 2022-01-29 | 2022-01-30 | 5 | 1 | 6 |  | AFD | 2022-04-10 | 2022-04-17 | 2022-04-25 | 7 | 8 | 15 | [8 empty] | 37 روز هست که ویرایش جدید تولید نشده است | [7 empty] | Specification For WHCP/HPU - W028
P02-EPC-E2460 | چاه شماره 28 | General Civil Layout -W028 | BK-W028-PEDCO-110-CV-PY-0001 | IFC | 2021-11-02 | 2021-10-25 | 2021-11-22 | -8 | 28 | 20 |  | IFA | 2022-03-26 | 2022-03-15 | 2022-03-25 | -11 | 10 | -1 |  | 0 | [6 empty] | 68 روز است ویرایش جدید ارسال نشده است | [23 empty] | General Civil Layout -W028
P02-EPC-E2470 | چاه شماره 28 | Civil and Structural drawings -W028 | BK-W028-PEDCO-110-CV-PY-0002 | IFC | 2021-11-02 | 0 | 0 | -44502 | 0 | -44502 | تاریخی بابت کامنت نیسوک ثبت نشده است (ویرایش بعدی ارسال شده است) | IFA | 2021-12-04 | 2021-11-29 | 2021-12-01 | -5 | 2 | -3 |  | IFA | 2022-03-28 | 2022-03-30 | 2022-04-03 | 2 | 4 | 6 | 59 روز است ویرایش جدید ارسال نشده است | [23 empty] | Civil and Structural drawings -W028
P02-EPC-E2480 | چاه شماره 28 | Rough Grading Plans -W028 | BK-W028-PEDCO-110-CV-DW-0001 | IFC | 2021-10-25 | 2021-10-16 | 2021-10-18 | -9 | 2 | -7 |  | IFA | 2022-02-20 | 2022-02-19 | 2022-02-12 | -1 | -7 | -8 |  | IFA | 2022-03-28 | 2022-03-30 | 2022-04-03 | 2 | 4 | 6 |  | AFC | 2022-04-24 | 0 | 0 | -44675 | 0 | -44675 | تایید روی AFC از کارفرما دریافت نشده است | [15 empty] | Rough Grading Plans -W028
P02-EPC-E3530 | چاه شماره 28 | PMR For Line Pipes - W028 | BK-W028-PEDCO-110-PL-MR-0001 | IFI | 2021-12-20 | 2021-12-13 | 2021-12-15 | -7 | 2 | -5 | [8 empty] | نسخه جدیدی از مدرک از آذر ماه پارسال ارسال نشده است | [31 empty] | PMR For Line Pipes - W028
P02-EPC-E1070 | چاه شماره 28 | P&ID - W028 | BK-W028-PEDCO-110-PR-PI-0001 | IFC | 2021-09-05 | 2021-08-31 | 2021-09-08 | -5 | 8 | 3 |  | IFC | 2021-11-15 | 2021-11-16 | 2021-11-27 | 1 | 11 | 12 |  | IFA | 2021-12-29 | 2021-12-30 | 2022-01-03 | 1 | 4 | 5 |  | IFA | 2022-03-14 | 2022-04-28 | 2022-05-01 | 45 | 3 | 48 |  | 0 | [6 empty] | 31 روز هست که ویرایش جدید تولید نشده است | [7 empty] | P&ID - W028
P02-EPC-E1880 | چاه شماره 28 | Data Sheets For WHCP/HPU - Wellheads - W028 | BK-SSGRL-PEDCO-110-IN-DT-0001 | IFC | 2021-09-05 | 2021-09-15 | 2021-09-20 | 10 | 5 | 15 |  | IFA | 2021-11-23 | 2021-11-21 | 2021-11-27 | -2 | 6 | 4 |  | IFA | 2022-01-04 | 2022-01-06 | 2022-01-08 | 2 | 2 | 4 |  | 0 | [6 empty] | 144 روز هست که ویرایش جدید تولید نشده است | 0 | [14 empty] | Data Sheets For WHCP/HPU - Wellheads - W028
P02-EPC-E1820 | چاه شماره 28 | Pipeline Corrosion Study & Material Selection Report - W028 | BK-SSGRL-PEDCO-110-PL-RT-0001 | IFC | 2021-11-10 | 2021-11-16 | 2021-11-21 | 6 | 5 | 11 |  | IFA | 2021-12-18 | 0 | 0 | -44548 | 0 | -44548 | تاریخی بابت کامنت نیسوک ثبت نشده است (ویرایش بعدی ارسال شده است) | IFA | 2022-03-14 | 2022-03-16 | 2022-04-01 | 2 | 16 | 18 |  | 0 | [6 empty] | 61 روز هست که ویرایش جدید تولید نشده است | 0 | [14 empty] | Pipeline Corrosion Study & Material Selection Report - W028
P02-EPC-E3590 | چاه شماره 28 | PMR For WHCP/HPU - W028 | BK-W028-PEDCO-110-IN-MR-0001 | IFI | 2021-11-29 | 2021-12-17 | 2021-12-07 | 18 | -10 | 8 | 10 روز زودتر از تاریخ کامنت نیسوک، ای میل شده است | IFI | 2022-01-30 | 2022-01-31 | 2022-02-01 | 1 | 1 | 2 | [32 empty] | PMR For WHCP/HPU - W028
P02-EPC-E1180 | چاه شماره 28 | Piping Material Specification - W028 | BK-SSGRL-PEDCO-110-PI-SP-0001 | IFC | 2021-12-12 | 2021-12-22 | 2021-12-26 | 10 | 4 | 14 |  | IFA | 2022-04-13 | 0 | 0 | -44664 | 0 | -44664 | تاریخی بابت کامنت نیسوک ثبت نشده است (50 روز گذشته است) | [31 empty] | Piping Material Specification - W028

## Gas (hidden)
Activity ID | P | A | BK Document Number | Total Float | Activity Name | Original Duration | Start | Finish | Budgeted Nonlabor Units | Actual Start | Actual Finish | % |  | Actual Start | Actual Finish | doc No.
P12-EPC-E1000 | P12-EPC-E1000P | P12-EPC-E1000A | BK-GNRAL-PEDCO-000-PM-RT-0001 | 0 | Endorsement Report For Basic Design & Scope of Work | 30 | 2021-06-23 | 2021-07-22 | 98017 | 2021-07-31 | 2021-07-31 | 100% | BK-GNRAL-PEDCO-000-PM-RT-0001Endorsement Report For Basic Design & Scope of Work | 2021-07-31 | 2021-09-19 | BK-GNRAL-PEDCO-000-PM-RT-0001
P12-EPC-E1570 | P12-EPC-E1570P | P12-EPC-E1570A | BK-GCS-PEDCO-120-PR-PF-0001 | 0 | Process Flow Diagram (PFD) | 54 | 2021-07-04 | 2021-08-26 | 2203 | 2021-08-14 | 2021-11-30 | 80% | BK-GCS-PEDCO-120-PR-PF-0001Process Flow Diagram (PFD) | 2021-08-14 | 2022-05-25 | BK-GCS-PEDCO-120-PR-PF-0001
P12-EPC-E1050 | P12-EPC-E1050P | P12-EPC-E1050A | BK-GNRAL-PEDCO-000-PR-DC-0001 | 0 | Process Design Criteria | 35 | 2021-07-23 | 2021-08-26 | 103 | 2021-07-27 | 2021-07-27 | 80% | BK-GNRAL-PEDCO-000-PR-DC-0001Process Design Criteria | 2021-07-27 | 2022-01-01 | BK-GNRAL-PEDCO-000-PR-DC-0001
P12-EPC-E1540 | P12-EPC-E1540P | P12-EPC-E1540A | BK-GCS-PEDCO-120-PR-DT-0030 | 0 | Process Data Sheets For Gas Compressors Packages | 44 | 2021-07-31 | 2021-09-12 | 2757 | 2021-11-07 | 2022-03-26 | 60% | BK-GCS-PEDCO-120-PR-DT-0030Process Data Sheets For Gas Compressors Packages | 2021-11-07 | 2022-05-25 | BK-GCS-PEDCO-120-PR-DT-0030
P12-EPC-P1000 | P12-EPC-P1000P | P12-EPC-P1000A |  | 0 | Tendering & Selection For Gas Compressors | 60 | 2021-08-11 | 2021-10-09 | 555269 | 1400/12/07 | 1400/12/25 | 0% | Tendering & Selection For Gas Compressors | 2022-02-26 | 2022-03-16 | 0
P12-EPC-E2480 | P12-EPC-E2480P | P12-EPC-E2480A | BK-GCS-PEDCO-120-ME-DT-0031 | 0 | Mechanical Data Sheets For Gas Compressors Packages | 49 | 2021-08-12 | 2021-09-29 | 1829 | 2021-09-12 | 2021-09-12 | 80% | BK-GCS-PEDCO-120-ME-DT-0031Mechanical Data Sheets For Gas Compressors Packages | 2021-09-12 | 2022-05-08 | BK-GCS-PEDCO-120-ME-DT-0031
P12-EPC-E7980 | P12-EPC-E7980P | P12-EPC-E7980A | BK-GCS-PEDCO-120-ME-TB-0001 | 0 | TBE For Gas Compressors | 45 | 2021-08-16 | 2021-09-29 | 2638 | 2022-02-02 | 2022-03-05 | 0% | BK-GCS-PEDCO-120-ME-TB-0001TBE For Gas Compressors | 2022-02-02 | 2022-03-05 | BK-GCS-PEDCO-120-ME-TB-0001
P12-EPC-E7970 | P12-EPC-E7970P | P12-EPC-E7970A | BK-GCS-PEDCO-120-ME-MR-0001 | 0 | PMR For Gas Compressors | 10 | 2021-09-03 | 2021-09-13 | 1759 | 2021-11-28 | 2022-02-13 | 100% | BK-GCS-PEDCO-120-ME-MR-0001PMR For Gas Compressors | 2021-11-28 | 2022-02-13 | BK-GCS-PEDCO-120-ME-MR-0001
P12-EPC-P1010 | P12-EPC-P1010P | P12-EPC-P1010A |  | 0 | Contract Effectiveness / PO For Gas Compressors | 30 | 2021-10-10 | 2021-11-08 | 832903 |  |  | 0% | Contract Effectiveness / PO For Gas Compressors
P12-EPC-P1020 | P12-EPC-P1020P | P12-EPC-P1020A |  | 0 | Manufacturing / Fabrication / Supply For Gas Compressors | 420 | 2021-11-09 | 2023-01-02 | 12493543 |  |  | 0% | Manufacturing / Fabrication / Supply For Gas Compressors
Formulas:
Actual Start = VLOOKUP([BK Document Number],'S&F'!$B:$E,3,0)
Actual Finish = VLOOKUP([BK Document Number],'S&F'!$B:$E,4,0)

## Well-18 (hidden)
Activity ID | P | A | BK Document Number | Total Float | Activity Name | Original Duration | Start | Finish | Budgeted Nonlabor Units | Actual Start | Actual Finish | % |  | Actual Start | Actual Finish | doc No. | 2022-05-25
P01-EPC-E1000 | P01-EPC-E1000P | P01-EPC-E1000A | BK-GNRAL-PEDCO-000-PM-RT-0001 | 0 | Endorsement Report For Basic Design & Scope of Work -W018S | 30 | 2021-06-23 | 2021-07-22 | 1131 | 2021-07-31 | 2021-07-31 | 100% | BK-GNRAL-PEDCO-000-PM-RT-0001Endorsement Report For Basic Design & Scope of Work -W018S | 2021-07-31 | 2021-09-19 | BK-GNRAL-PEDCO-000-PM-RT-0001
P01-EPC-E1060 | P01-EPC-E1060P | P01-EPC-E1060A | BK-W018S-PEDCO-110-PR-PF-0001 | 39 | Process Flow Diagram - W018S | 45 | 2021-07-23 | 2021-09-05 | 193 | 2021-11-02 | 0 | 60% | BK-W018S-PEDCO-110-PR-PF-0001Process Flow Diagram - W018S | 2021-08-04 | 2022-05-25 | BK-W018S-PEDCO-110-PR-PF-0001
P01-EPC-E1370 | P01-EPC-E1370P | P01-EPC-E1370A | BK-W018S-PEDCO-110-PI-PY-0001 | 14 | Plot Plan Drawing - W018S | 40 | 2021-07-23 | 2021-08-31 | 172 | 2021-08-22 | 2022-01-31 | 80% | BK-W018S-PEDCO-110-PI-PY-0001Plot Plan Drawing - W018S | 2021-08-22 | 2022-05-25 | BK-W018S-PEDCO-110-PI-PY-0001
P01-EPC-E1860 | P01-EPC-E1860P | P01-EPC-E1860A | BK-SSGRL-PEDCO-110-IN-SP-0001 | 22 | Specification For WHCP/HPU-W018S | 38 | 2021-07-23 | 2021-08-29 | 147 | 2021-08-08 | 2021-08-08 | 80% | BK-SSGRL-PEDCO-110-IN-SP-0001Specification For WHCP/HPU-W018S | 2021-08-08 | 2022-03-27 | BK-SSGRL-PEDCO-110-IN-SP-0001
P01-EPC-E2470 | P01-EPC-E2470P | P01-EPC-E2470A | BK-W018S-PEDCO-110-CV-DW-0001 | 9 | Rough Grading Plans -W018S | 40 | 2021-07-28 | 2021-09-05 | 232 | 2021-10-30 | 2021-07-28 | 60% | BK-W018S-PEDCO-110-CV-DW-0001Rough Grading Plans -W018S | 2021-07-28 | 2022-03-13 | BK-W018S-PEDCO-110-CV-DW-0001
P01-EPC-E1070 | P01-EPC-E1070P | P01-EPC-E1070A | BK-W018S-PEDCO-110-PR-PI-0001 | 39 | P&ID - W018S | 45 | 2021-08-02 | 2021-09-15 | 103 | 2021-11-01 | 2021-12-15 | 80% | BK-W018S-PEDCO-110-PR-PI-0001P&ID - W018S | 2021-08-09 | 2022-05-25 | BK-W018S-PEDCO-110-PR-PI-0001
P01-EPC-E1300 | P01-EPC-E1300P | P01-EPC-E1300A | BK-GNRAL-PEDCO-000-PI-SP-0017 | 153 | Piping Material Specification-W018S | 30 | 2021-08-02 | 2021-08-31 | 84 | 2021-08-24 | 2021-08-24 | 100% | BK-GNRAL-PEDCO-000-PI-SP-0017Piping Material Specification-W018S | 2021-08-24 | 2021-12-15 | BK-GNRAL-PEDCO-000-PI-SP-0017
P01-EPC-E1870 | P01-EPC-E1870P | P01-EPC-E1870A | BK-SSGRL-PEDCO-110-IN-DT-0001 | 22 | Data Sheets For WHCP/HPU - Wellheads-W018S | 30 | 2021-08-02 | 2021-08-31 | 28 | 2021-08-22 | 2021-12-21 | 80% | BK-SSGRL-PEDCO-110-IN-DT-0001Data Sheets For WHCP/HPU - Wellheads-W018S | 2021-08-22 | 2022-05-25 | BK-SSGRL-PEDCO-110-IN-DT-0001
P01-EPC-E2460 | P01-EPC-E2460P | P01-EPC-E2460A | BK-W018S-PEDCO-110-CV-PY-0002 | 16 | Civil and Structural drawings - W018S | 40 | 2021-08-07 | 2021-09-15 | 358 | 2021-07-28 | 2021-07-28 | 60% | BK-W018S-PEDCO-110-CV-PY-0002Civil and Structural drawings - W018S | 2021-07-28 | 2022-03-05 | BK-W018S-PEDCO-110-CV-PY-0002
P01-EPC-E2450 | P01-EPC-E2450P | P01-EPC-E2450A | BK-W018S-PEDCO-110-CV-PY-0001 | 14 | General Civil Layout - W018S | 20 | 2021-08-12 | 2021-08-31 | 358 | 2021-07-28 | 2021-07-28 | 100% | BK-W018S-PEDCO-110-CV-PY-0001General Civil Layout - W018S | 2021-07-28 | 2021-12-27 | BK-W018S-PEDCO-110-CV-PY-0001
P01-EPC-E1810 | P01-EPC-E1810P | P01-EPC-E1810A | BK-SSGRL-PEDCO-110-PL-RT-0001 | 192 | Pipeline Corrosion Study & Material Selection Report-W018S | 44 | 2021-08-22 | 2021-10-04 | 59 | 2021-10-27 | 2022-02-28 | 0% | BK-SSGRL-PEDCO-110-PL-RT-0001Pipeline Corrosion Study & Material Selection Report-W018S | 2021-10-27 | 44706 | BK-SSGRL-PEDCO-110-PL-RT-0001
P01-EPC-C1060 | P01-EPC-C1060P | P01-EPC-C1060A |  | 9 | Site Preparation W018S | 10 | 2021-08-27 | 2021-09-05 | 9358 | 1400/05/15 | 1400/06/25 | 92.96% | Site Preparation W018S | 2021-08-06 | 2021-09-16 | 0
P01-EPC-E3590 | P01-EPC-E3590P | P01-EPC-E3590A | BK-W018S-PEDCO-110-IN-MR-0001 | 22 | PMR For WHCP/HPU - W018S | 7 | 2021-08-30 | 2021-09-05 | 27 | 2021-11-15 | 2022-01-16 | 100% | BK-W018S-PEDCO-110-IN-MR-0001PMR For WHCP/HPU - W018S | 2021-11-15 | 2022-01-16 | BK-W018S-PEDCO-110-IN-MR-0001
P01-EPC-E3560 | P01-EPC-E3560P | P01-EPC-E3560A | BK-W018S-PEDCO-110-PL-MR-0001 | 40 | PMR For Line pipes - W018S | 5 | 2021-10-06 | 2021-10-10 | 7 | 0 | 0 | 100% | BK-W018S-PEDCO-110-PL-MR-0001PMR For Line pipes - W018S | 2021-12-06 | 2021-12-15 | BK-W018S-PEDCO-110-PL-MR-0001
P01-EPC-P1670 | P01-EPC-P1670P | P01-EPC-P1670A |  | 22 | Tendering & Selection- W018S-WHCP | 10 | 2021-09-23 | 2021-10-02 | 1814 | 1400/12/24 | #N/A | 0% | Tendering & Selection- W018S-WHCP | 2022-03-15 | 2022-05-25 | 0
P01-EPC-P1550 | P01-EPC-P1550P | P01-EPC-P1550A |  | 26 | Tendering & Selection- W018S- Line pipe | 7 | 2021-10-01 | 2021-10-07 | 7555 | #N/A | #N/A | 0% | Tendering & Selection- W018S- Line pipe |  |  | 0
P01-EPC-P1680 | P01-EPC-P1680P | P01-EPC-P1680A |  | 22 | Contract Effectiveness / PO- W018S- WHCP | 5 | 2021-10-03 | 2021-10-07 | 2722 | #N/A | #N/A | 0% | Contract Effectiveness / PO- W018S- WHCP |  |  | 0
P01-EPC-P1560 | P01-EPC-P1560P | P01-EPC-P1560A |  | 26 | Contract Effectiveness / PO- W018S-Line pipe | 5 | 2021-10-08 | 2021-10-12 | 11332 | #N/A | #N/A | 0% | Contract Effectiveness / PO- W018S-Line pipe |  |  | 0
P01-EPC-P1690 | P01-EPC-P1690P | P01-EPC-P1690A |  | 22 | Manufacturing / Fabrication / Supply- W018S-WHCP | 90 | 2021-10-08 | 2022-01-05 | 22680 | #N/A | #N/A | 0% | Manufacturing / Fabrication / Supply- W018S-WHCP |  |  | 0
P01-EPC-C1330 | P01-EPC-C1330P | P01-EPC-C1330A |  | 94 | Construction of Right of Way- W018S | 20 | 2021-10-09 | 2021-10-28 | 23368 |  |  | 0% | Construction of Right of Way- W018S |  |  | 0
P01-EPC-P1570 | P01-EPC-P1570P | P01-EPC-P1570A |  | 26 | Manufacturing / Fabrication / Supply- W018S-Line pipe | 70 | 2021-10-13 | 2021-12-21 | 94436 | #N/A | #N/A | 0% | Manufacturing / Fabrication / Supply- W018S-Line pipe |  |  | 0
P01-EPC-C1340 | P01-EPC-C1340P | P01-EPC-C1340A |  | 57 | Construction of Steel Works(Wellhead Facilities)- W018S | 15 | 2021-12-05 | 2021-12-19 | 5297 |  |  | 0% | Construction of Steel Works(Wellhead Facilities)- W018S |  |  | 0
P01-EPC-P1580 | P01-EPC-P1580P | P01-EPC-P1580A |  | 26 | Final Inspection- W018S-Line pipe | 7 | 2021-12-22 | 2021-12-28 | 18887 | #N/A | #N/A | 0% | Final Inspection- W018S-Line pipe |  |  | 0
P01-EPC-C1150 | P01-EPC-C1150P | P01-EPC-C1150A |  | 12 | Supply & Installation sealling Layer of Mud pit- W018S | 12 | 2021-09-20 | 2021-09-27 | 34529 | 1400/05/29 | 1400/09/18 |  |  | 2021-08-20 | 2021-12-09 | 0
P01-EPC-C1330 | P01-EPC-C1330P | P01-EPC-C1330A |  | 94 | Right of Way-W018S | 94 | 2021-10-09 | 2021-10-28 | 23368 | [6 empty] | 0
P01-EPC-C1350 | P01-EPC-C1350P | P01-EPC-C1350A |  | 57 | Construction & Installation of Shelter for Wellhead Control Panel-W018S | 57 | 2021-12-20 | 2022-01-03 | 1558 | [6 empty] | 0
Formulas:
Actual Start = VLOOKUP([BK Document Number],'S&F'!$B:$E,3,0)
Actual Finish = VLOOKUP([BK Document Number],'S&F'!$B:$E,4,0)

## Well-28 (hidden)
Activity ID | P | A | BK Document Number | Total Float | Activity Name | Original Duration | Start | Finish | Budgeted Nonlabor Units | Actual Start | Actual Finish | % |  | Actual Start | Actual Finish | doc No. | 2022-05-25
P02-EPC-C1170 | P02-EPC-C1170P | P02-EPC-C1170A |  | 0 | Site Preparation W028 | 20 | 2021-08-17 | 2021-09-05 | 104403 | 1400/06/24 |  | 53% |  | 2021-09-15 |  | 0
P02-EPC-E1060 | P02-EPC-E1060P | P02-EPC-E1060A | BK-W028-PEDCO-110-PR-PF-0001 | 44 | Process Flow Diagram - W028 | 40 | 2021-07-23 | 2021-08-31 | 192 | 2021-11-02 | 0 | 60% | BK-W028-PEDCO-110-PR-PF-0001Process Flow Diagram - W028 | 2021-08-14 | 2022-05-25 | BK-W028-PEDCO-110-PR-PF-0001
P02-EPC-E1070 | P02-EPC-E1070P | P02-EPC-E1070A | BK-W028-PEDCO-110-PR-PI-0001 | 44 | P&ID - W028 | 40 | 2021-08-02 | 2021-09-10 | 102 | 2021-11-01 | 2021-12-15 | 80% | BK-W028-PEDCO-110-PR-PI-0001P&ID - W028 | 2021-08-22 | 2022-05-25 | BK-W028-PEDCO-110-PR-PI-0001
P02-EPC-E1180 | P02-EPC-E1180P | P02-EPC-E1180A | BK-SSGRL-PEDCO-110-PI-SP-0001 | 111 | Piping Material Specification - W028 | 64 | 2021-10-22 | 2021-12-24 | 85 | 2021-11-28 | 0 | 60% | BK-SSGRL-PEDCO-110-PI-SP-0001Piping Material Specification - W028 | 2021-11-28 | 2022-05-25 | BK-SSGRL-PEDCO-110-PI-SP-0001
P02-EPC-E1380 | P02-EPC-E1380P | P02-EPC-E1380A | BK-W028-PEDCO-110-PI-DW-0001 | 44 | Plot Plan Drawing - W028 | 30 | 2021-07-23 | 2021-08-21 | 173 | 2022-02-02 | 0 | 0% | BK-W028-PEDCO-110-PI-DW-0001Plot Plan Drawing - W028 | 2022-02-02 | 2022-05-25 | BK-W028-PEDCO-110-PI-DW-0001
P02-EPC-E1860 | P02-EPC-E1860P | P02-EPC-E1860A | BK-SSGRL-PEDCO-110-IN-SP-0001 | 197 | Specification For WHCP/HPU - W028 | 38 | 2021-07-23 | 2021-08-29 | 148 | 2021-08-08 | 2021-08-08 | 80% | BK-SSGRL-PEDCO-110-IN-SP-0001Specification For WHCP/HPU - W028 | 2021-08-08 | 2022-03-27 | BK-SSGRL-PEDCO-110-IN-SP-0001
P02-EPC-E1880 | P02-EPC-E1880P | P02-EPC-E1880A | BK-SSGRL-PEDCO-110-IN-DT-0001 | 197 | Data Sheets For WHCP/HPU - Wellheads - W028 | 49 | 2021-08-12 | 2021-09-29 | 28 | 2021-08-22 | 2021-12-21 | 80% | BK-SSGRL-PEDCO-110-IN-DT-0001Data Sheets For WHCP/HPU - Wellheads - W028 | 2021-08-22 | 2022-05-25 | BK-SSGRL-PEDCO-110-IN-DT-0001
P02-EPC-E2460 | P02-EPC-E2460P | P02-EPC-E2460A | BK-W028-PEDCO-110-CV-PY-0001 | 0 | General Civil Layout -W028 | 25 | 2021-07-23 | 2021-08-16 | 393 | 2021-10-19 | 0 | 60% | BK-W028-PEDCO-110-CV-PY-0001General Civil Layout -W028 | 2021-10-19 | 2022-05-25 | BK-W028-PEDCO-110-CV-PY-0001
P02-EPC-E2470 | P02-EPC-E2470P | P02-EPC-E2470A | BK-W028-PEDCO-110-CV-PY-0002 | 181 | Civil and Structural drawings -W028 | 45 | 2021-07-23 | 2021-09-05 | 393 | 2021-10-19 | 2022-03-14 | 80% | BK-W028-PEDCO-110-CV-PY-0002Civil and Structural drawings -W028 | 2021-10-19 | 2022-05-25 | BK-W028-PEDCO-110-CV-PY-0002
P02-EPC-E2480 | P02-EPC-E2480P | P02-EPC-E2480A | BK-W028-PEDCO-110-CV-DW-0001 | 0 | Rough Grading Plans -W028 | 25 | 2021-07-23 | 2021-08-16 | 261 | 2021-10-11 | 2021-10-11 | 60% | BK-W028-PEDCO-110-CV-DW-0001Rough Grading Plans -W028 | 2021-10-11 | 2022-04-10 | BK-W028-PEDCO-110-CV-DW-0001
P02-EPC-E3530 | P02-EPC-E3530P | P02-EPC-E3530A | BK-W028-PEDCO-110-PL-MR-0001 | 50 | PMR For Line Pipes - W028 | 10 | 2021-07-30 | 2021-08-08 | 7 | 2021-12-06 | 0 | 100% | BK-W028-PEDCO-110-PL-MR-0001PMR For Line Pipes - W028 | 2021-12-06 | 2021-12-15 | BK-W028-PEDCO-110-PL-MR-0001
P02-EPC-E3590 | P02-EPC-E3590P | P02-EPC-E3590A | BK-W028-PEDCO-110-IN-MR-0001 | 45 | PMR For WHCP/HPU - W028 | 10 | 2021-09-01 | 2021-09-10 | 27 | 2021-11-15 | 2022-01-16 | 100% | BK-W028-PEDCO-110-IN-MR-0001PMR For WHCP/HPU - W028 | 2021-11-15 | 2022-01-16 | BK-W028-PEDCO-110-IN-MR-0001
P02-EPC-P1550 | P02-EPC-P1550P | P02-EPC-P1550A |  | 50 | Tendering & Selection- W028 - Line pipe | 7 | 2021-08-19 | 2021-08-25 | 11460 | #N/A | #N/A | 0% |  | 2022-03-15 | 2022-05-25 | 0
P02-EPC-P1560 | P02-EPC-P1560P | P02-EPC-P1560A |  | 50 | Contract Effectiveness / PO- W028 - Line pipe | 5 | 2021-08-26 | 2021-08-30 | 17189 | #N/A | #N/A | 0% |  |  |  | 0
P02-EPC-P1570 | P02-EPC-P1570P | P02-EPC-P1570A |  | 50 | Manufacturing / Fabrication / Supply- W028 - Line pipe | 110 | 2021-08-31 | 2021-12-18 | 143244 | #N/A | #N/A | 0% |  |  |  | 0
P02-EPC-P1580 | P02-EPC-P1580P | P02-EPC-P1580A |  | 50 | Final Inspection- W028 - Line pipe | 7 | 2021-12-19 | 2021-12-25 | 28649 | #N/A | #N/A | 0% |  |  |  | 0
P02-EPC-P1670 | P02-EPC-P1670P | P02-EPC-P1670A |  | 45 | Tendering & Selection- W028 - WHCP | 10 | 2021-09-23 | 2021-10-02 | 2359 | 1400/12/24 | #N/A | 0% |  | 2022-03-15 | 2022-05-25 | 0
P02-EPC-P1680 | P02-EPC-P1680P | P02-EPC-P1680A |  | 45 | Contract Effectiveness / PO- W028 - WHCP | 5 | 2021-10-03 | 2021-10-07 | 3538 | #N/A | #N/A | 0% |  |  |  | 0
P02-EPC-P1690 | P02-EPC-P1690P | P02-EPC-P1690A |  | 45 | Manufacturing / Fabrication / Supply- W028 - WHCP | 90 | 2021-10-08 | 2022-01-05 | 29486 | #N/A | #N/A | 0% |  |  |  | 0
P02-EPC-C1440 | P02-EPC-C1440P | P02-EPC-C1440A |  | 131 | Construction of Right of Way - W028 | 15 | 2021-10-11 | 2021-10-25 | 37246 |  |  | 0% |  |  |  | 0
P02-EPC-C1450 | P02-EPC-C1450P | P02-EPC-C1450A |  | 131 | Construction of Steel Works(Wellhead Facilities) - W028 | 10 | 2021-10-26 | 2021-11-04 | 8442 |  |  | 0% |  |  |  | 0
P02-EPC-E1000 | P02-EPC-E1000P | P02-EPC-E1000A | BK-GNRAL-PEDCO-000-PM-RT-0001 | 0 | Endorsement Report For Basic Design & Scope of Work - W028 | 30 | 2021-06-23 | 2021-07-22 | 1131 | 2021-07-31 | 2021-07-31 | 100% | BK-GNRAL-PEDCO-000-PM-RT-0001Endorsement Report For Basic Design & Scope of Work - W028 | 2021-07-31 | 2021-09-19 | BK-GNRAL-PEDCO-000-PM-RT-0001
P02-EPC-E1820 | P02-EPC-E1820P | P02-EPC-E1820A | BK-SSGRL-PEDCO-110-PL-RT-0001 | 192 | Pipeline Corrosion Study & Material Selection Report - W028 | 44 | 2021-08-22 | 2021-10-04 | 59 | 2021-10-27 | 2022-02-28 | 0% | BK-SSGRL-PEDCO-110-PL-RT-0001Pipeline Corrosion Study & Material Selection Report - W028 | 2021-10-27 | 2022-05-25 | BK-SSGRL-PEDCO-110-PL-RT-0001
P02-EPC-C1240 | P02-EPC-C1240P | P02-EPC-C1240A |  | 25 | Excavation of Mud Channel- W028 | 7 | 2021-08-30 | 2021-09-05 | 1790 |  |  |  | Excavation of Mud Channel- W028 |  |  | 0
P02-EPC-C1310 | P02-EPC-C1310P | P02-EPC-C1310A |  | 37 | Installation sealling Layer of Mud Pit- W028 | 6 | 2021-08-29 | 2021-09-04 | 13423 | 1401/02/10 |  |  | Installation sealling Layer of Mud Pit- W028 | 2022-04-30 | 2022-05-25 | 0
P02-EPC-C1460 | P02-EPC-C1460P | P02-EPC-C1460A |  | 131 | Construction & Installation of Shelter for Wellhead Control Panel- W028 | 5 | 2021-11-05 | 2021-11-09 | 2483 |  |  |  | Construction & Installation of Shelter for Wellhead Control Panel- W028 |  |  | 0
Formulas:
Actual Start = VLOOKUP([BK Document Number],'S&F'!$B:$E,3,0)
Actual Finish = VLOOKUP([BK Document Number],'S&F'!$B:$E,4,0)