## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W008N-PEDCO-110-IN-MR-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0470 |  |  | Transmital Date: 16 Jan 2022
Document Title: BK-W008N-PEDCO-110-IN-MR-0001 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0008-IN-TR-0470 |  |  | Transmital Date: 16 Jan 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W008N-PEDCO-110-IN-MR-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | موارد 1و2و3و4 نظر خاصی مطرح نمی باشد. |  | 00/2294/390765 | 1400/11/11 | -
2 | قسمت 5.1.1 صفحه 7 ، کلمه CLIENT جایگزین PURCHASER گردد. |  | 00/2294/390765 | 1400/11/11 | مدرک مطابق خواست کارفرمای محترم اصلاح گردید.
3 | قسمت 5.1.1 خط آخر عبارت by CLIENT به آخر جمله اضافه گردد. |  | 00/2294/390765 | 1400/11/11 | مدرک مطابق خواست کارفرمای محترم اصلاح گردید.
4 | عبارت IF ANY از مدرک حذف گردد. |  | 00/2294/390765 | 1400/11/11 | مدرک مطابق خواست کارفرمای محترم اصلاح گردید.
5 | صفحه 10 قسمت 10، کلمه CLIENT جایگزین PURCHASER گردد. |  | 00/2294/390765 | 1400/11/11 | مدرک مطابق خواست کارفرمای محترم اصلاح گردید.
6 | صفحه 11 قسمت 11 ، عبارت OTHER FEE حذف گردد. |  | 00/2294/390765 | 1400/11/11 | مدرک مطابق خواست کارفرمای محترم اصلاح گردید.
7 | ویرایش نهایی مدارک پیوست ها در نظر گرفته شود. |  | 00/2294/390765 | 1400/11/11 | ویرایش نهایی مدارک پیوست در مدرک ذکر گردید و به ضمیمه مدرک ارسال شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: