## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0003_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0401 |  |  | Transmital Date: 08/DeC/2021
Document Title: Mechanical Data Sheets For 1st Stage Gas Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-ME-TR-0401 |  |  | Transmital Date: 08/DeC/2021
[5 empty] | CRS No: NISOC-CRS-BK-GCS-BK-GCS-PEDCO-120-ME-DT-0003_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اطلاعات فرآیندی مطابق با اسنادپایه و آخرین تغییرات فرآیندی پروژه در نظر گرفته شود. |  | 00/2294/372926 | 30/10/1400 | نظر کارفرمای محترم اعمال گردید.
2 | استاندارد طراحی IPS مربوطه در مدرک ذکر گردد. |  | 00/2294/372926 | 30/10/1400 | استاندارد IPS-G-ME-245 در بخش Basic Design Data در قسمت Local standard ذکر شده است.
3 | اطلاعات مربوط به تبادل حرارت مطابق با اسناد پایه اصلاح گردد. |  | 00/2294/372926 | 30/10/1400 | اطلاعات فرآیندی بر اساس تغییرات مدارک فرآیندی اصلاح گردید.
4 | مبنای درج اطلاعات مکانیکی مدرک مشخص نمی باشد. |  | 00/2294/372926 | 30/10/1400 | مطابق نظر کارفرما اطلاعات اضافی حذف شد.
5 | میزان کالای یدکی مطابق با پیوست 11 کتابچه پیمان در نظر گرفته شود. |  | 00/2294/372926 | 30/10/1400 | نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.BAVARSAD | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date: 1/29/2022 |  |  |  |  | Date: 6/18/2022