## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-RT-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0434 |  |  | Transmital Date:1/5/2022
Document Title: Flare Network Study Report |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0434 |  |  | Transmital Date: 1/5/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | شیر XV-2134 بعد از V-2105 در سناریو طراحی شبکه در نظر گرفته نشده است |  | 1400-2294-405516 | 1400/11/23 | اعمال گردید.
2 | شیر PCV-2110 بعد از AC-2102A/B/C در سناریو طراحی شبکه در نظر گرفته نشده است. |  | 1400-2294-405516 | 1400/11/23 | اعمال گردید.
3 | شیر BDV-2132 B,C بعد از AC-2102B,C در سناریو طراحی شبکه در نظر گرفته نشده است. |  | 1400-2294-405516 | 1400/11/23 | اعمال گردید.
4 | شیر BDV-2151 بعد از سیستم نمزدا در سناریو طراحی شبکه در نظر گرفته نشده است. |  | 1400-2294-405516 | 1400/11/23 | اعمال گردید.
5 | با توجه به تغییرات زیاد مدارک P&ID نسبت به مدارک مندرج در پیمان و حذف بسیاری از شیرآلات مربوط به شبکه مزبور این مدرک می بایست پس از تعیین تکلیف موضوع مورد بازنگری قرار گیرد. |  | 1400-2294-405516 | 1400/11/23 | بازگشت به جلسه مورخ 1401/02/28 در مقطع کنونی طراحی این پیمانکار مورد تایید می باشد و پس از جلسه HAZOP تغیرات احتمالی بر روی مدرک فوق اعمال خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021