## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-RT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0431 |  |  | Transmital Date: 1/5/2022
Document Title: Flare Radiation & Dispersion Study Report |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0431 |  |  | Transmital Date: 1/5/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق فايل ارسالي ميزان ماكزيمم تشعشع داخل محوطه استريل 18 kw/m2 مي باشد كه بسيار بيشتر از ميزان استاندارد است لذا لازم است محاسبات مجددا مورد بازنگري كلي قرار گيرد. |  | BK-SUR-ENG-PCS-00-02802 | 2022-01-24 | اصلاح گردید
2 | ميزان افت فشار Seal لحاظ نشده است. |  | BK-SUR-ENG-PCS-00-02802 | 2022-01-24 | اعمال گردید
3 | ميزان هواي مورد نياز در صورت Smokless بودن فلر در محاسبات تشعشع لحاظ گردد. |  | BK-SUR-ENG-PCS-00-02802 | 2022-01-24 | اعمال گردید
4 | فايل محاسباتي بخش DISPERSION در ويرايش بعدي ارسال گردد. |  | BK-SUR-ENG-PCS-00-02802 | 2022-01-24 | اعمال گردید.
5 | محاسبات بخش DISPERSION در سرعت باد صفر نيز انجام پذيرد. |  | BK-SUR-ENG-PCS-00-02802 | 2022-01-24 | لازم به توضیح است نرم افزار PHAST قابلیت انجام مطالعات ِDispersion در سرعت صفر را ندارد.
6 | عليرغم درج در مدرك درخصوص استفاده از 4- Generic Pipe Method اين موضوع در شبيه سازي اعمال نشده است و لازم است در ويرايش بعدي اعمال گردد. |  | BK-SUR-ENG-PCS-00-02802 | 2022-01-24 | اعمال گردید
7 | در محاسبات DISPERSION كانتور هاي LFL-50% نيز نمايش داده شود. |  | BK-SUR-ENG-PCS-00-02802 | 2022-01-24 | با توجه به معیارهای طراحی ارائه شده در TOTAL SPEC GS- SAF-253 در مطالعات صرفا معیار 100%LFL مورد نیاز میباشد.
8 | نقطه نظرات ارئه شده در خصوص شبكه فلر در صورت مرتبط بودن در اين مدرك نيز اعمال گردد. |  | BK-SUR-ENG-PCS-00-02802 | 2022-01-24 | اعمال گردید
9 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-00-02802 | 2022-01-24 | اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021