## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-ME-DC-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0015 |  |  | Transmital Date: 28/JUL/2021
Document Title: Mechanical Design Criteria |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-ME-0103-TR-0015 |  |  | Transmital Date: 28/JUL/2021
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-ME-DC-0001_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | The followings shall be added to refference list: 1-1-IPS-M-PI-130, “Material and Equipment Standard for Pig Launching and Receiving Traps |  | BK-SUR-ENG-FXE-00-01277 | 8/8/2021 | This standard has been added to the document.
| 1-2-ASME B30.11 “Monorails and under hung Cranes” |  | BK-SUR-ENG-FXE-00-01277 | 8/8/2021 | This code has been added to the document.
| 1-3-ASME B30.17 “Overhead and Gantry Cranes (Top-Running Bridge, Single Girder, under hung Hoist) |  | BK-SUR-ENG-FXE-00-01277 | 8/8/2021 | This code has been added to the document.
| 1-4-API Std. 537, “Flare Details for General Refinery and Petrochemical Service” |  | BK-SUR-ENG-FXE-00-01277 | 8/8/2021 | This standard has been added to the document.
| 1-5-ISO 1940-1/2, “Mechanical Vibration - Balance Quality Requirements of Rigid” |  | BK-SUR-ENG-FXE-00-01277 | 8/8/2021 | This standard has been added to the document.
| 1-6-ISO 1940-1/2, “Mechanical Vibration - Balance Quality Requirements of Rigid” |  | BK-SUR-ENG-FXE-00-01277 | 8/8/2021 | This standard has been added to the document.
| 1-7-ISO 10440-2 “Petroleum and Natural Gas Industries – Rotary-Type Positive-Displacement Compressors – Part 2: Packaged Air Compressors (Oil-Free) |  | BK-SUR-ENG-FXE-00-01277 | 8/8/2021 | This standard has been added to the document.
| 1-8-ISO 1217 “Displacement Compressors – Acceptance Tests” |  | BK-SUR-ENG-FXE-00-01277 | 8/8/2021 | This standard has been added to the document.
| 1-9-ISO 12500 “Filters for Compressed Air - Test Methods |  | BK-SUR-ENG-FXE-00-01277 | 8/8/2021 | This standard has been added to the document.
| 1-10-ISO 8573-1 “Compressed Air —Part 1: Contaminants and Purity Classes” |  | BK-SUR-ENG-FXE-00-01277 | 8/8/2021 | This standard has been added to the document.
| 1-11-ISO 10816-6 “Mechanical Vibration -- Evaluation of Machine Vibration by Measurements on Non-Rotating Parts |  | BK-SUR-ENG-FXE-00-01277 | 8/8/2021 | This standard has been added to the document.
2 | The following shall be added to clause " 6.6.2" -Spare pumps in critical services shall be equipped with automatic start facilities -All pumps shall be directly coupled to their drivers. All pumps and their drive train shall be mounted on common bases of rigid construction |  | BK-SUR-ENG-FXE-00-01277 | 8/8/2021 | The mentioned parts have been added to caluse 7.6.2. (As Ordere of precedence section is added, numbering is changed)
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature | M.Fakharian
| Date: 8/8/2021 |  |  |  |  | Date: 06/20/2021