## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W028-PEDCO-110-CV-MR-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0989 |  |  | Transmital Date: 22/May/2022
Document Title: PMR For Geomembrane - W028 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-0989 |  |  | Transmital Date: 22/May/2022
[5 empty] | CRS No: NISOC-CRS-BK-W028-PEDCO-110-CV-MR-0001_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص گارانتی محصولات ژئوممبرین، به صراحت در شرح قرارداد به آن اشاره شده است. |  | 01/2294/85267 | 1401/03/10 | اصلاحات مقتضی اعمال گردید.
2 | در مرحله صحه گذاری اسناد و مدارک پروژه (Endorsement) هیچگونه ابهامی توسط شرکت پتروایران بابت ارائه گارانتی حداقل 10 ساله ی این عایق، مطرح نشده است. بنابراین توضیحات آن شرکت در Reply Sheet مورد قبول این امور نمی باشد. |  | 01/2294/85267 | 1401/03/10
3 | ملاک عمل مراجعه به شرح قرارداد-تسهیلات احداث و تعمیر چاهها-عملیات سیویل و جاده های دسترسی 10-4-1- خدمات اجرایی سیویل-ارائه گارانتی حداقل 10 ساله عایق ژئوممبرین است. |  | 01/2294/85267 | 1401/03/10
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature | M.Fakharian
Date:10/04/2022