## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-ME-DT-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0338 |  |  | Transmital Date:12/13/2021
Document Title: Data Sheets For Pig Traps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0010-ME-TR-0338 |  |  | Transmital Date: 12/13/2021
[5 empty] | CRS No: NISOC-PEDCO-CRS-BK-GCS-BK-PPL-PEDCO-320-ME-DT-0001_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | کد طراحی استاندارد IPS در مدرک درج گردد. |  | 00/2294/329500 | 1400/09/30 | نظرات کارفرمای محترم اعمال شد.
2 | همانگونه که پیشتر گفته شده است نقشه S4L6516 تنها راهنمای ساخت تجهیز STONE TRAP می باشد لذا الزام سازنده به ساخت این تجهیز مطابق با این استاندارد موضوعیت ندارد. |  | 00/2294/329500 | 1400/09/30 | پیرو مذاکرات تلفنی، موضوع مورد اشاره مرتفع گردید.
3 | فشار طراحی مطابق با اسناد پایه اصلاح گردد. |  | 00/2294/329500 | 1400/09/30 | فشار طراحی مطابق با مدرک P&ID در نظر گرفته شده است.
4 | فشارتست هیدرو استاتیک در مدرک درج گردد. |  | 00/2294/329500 | 1400/09/30 | نظرات کارفرمای محترم اعمال شد.
5 | منظور از CLIENT درمتن مدرک مشخص نمی باشد. |  | 00/2294/329500 | 1400/09/30 | منظور از CLIENT شرکت محترم NISOC می باشد.
6 | میزان کالای یدکی مطابق با پیوست 11 کتابچه پیمان در نظر گرفته شود. |  | 00/2294/329500 | 1400/09/30 | نظرات کارفرمای محترم اعمال شد.
7 | با توجه به اینکه محاسبات طراحی ارسال نشده است، ملاک تعیین مشخصات طراحی(به عنوان نمونه ضخامت ) چه بوده است. |  | 00/2294/329500 | 1400/09/30 | ضخامت تجهیزات از مدارک حذف گردید.
8 | میزان خوردگی مجاز بر اساس مطالعات خوردگی و یا اسناد پایه می بایست در نظر گرفته شود. |  | 00/2294/329500 | 1400/09/30 | میزان خوردگی مجاز مطابق با مدرک مطالعات خوردگی به شماره مدرک BK-PPL-PEDCO-320-PI-RT-0001 و همچنین دیتاشیت اسناد پایه، 3.2 میلیمتر ذکر شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.BAVARSAD | Signature | H.naserizadeh |  |  | Clarified By: | H.Ghadyani | M.Fakharian
Date:01/03/2022