## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-MR-0004_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0738 |  |  | Transmital Date: 26 Mar 2022
Document Title:PMR For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold |  |  |  |  | NISOC Tr. No.: BK-PEDCO-NISOC-0012-IN-TR-0738 |  |  | Transmital Date: 26 Mar 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0004_D00 |  |  | CRS Status:
Item |  |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ضرورت دارد پس از نهایی شدن مدارک مرجع ، ویرایش نهایی آنها درج گردد. |  | 01/2294/16060 | 1401/01/20 | آخرین نسخه ارسالی از مدارک مرجع در بخش Reference list ذکر شده است و پس از نهایی شدن مدارک مرجع ، ویرایش نهایی آنها درج می گردد.
2 | در خصوص shipping اطلاعات مورد نیاز اضافه گردد. |  | 01/2294/16060 | 1401/01/20 | این مورد مطابق خواست کارفرمای محترم به مدرک اضافه گردید.
3 | مدرک Specification For On-off/Shut Down Valves(ESDV/MOV) به جدول مربوط به مدارک مرجع اضافه گردد. |  | 01/2294/16060 | 1401/01/20 | این مورد مطابق خواست کارفرمای محترم به مدرک اضافه گردید.
4 | با توجه به اینکه پروژه در مرحله تفصیلی و مدرک مربوط به خرید تجهیز می باشد، استفاده از قیدهای if any و if required به معنایی ندارد و می بایست حذف گردند. |  | 01/2294/16060 | 1401/01/20 | مدرک مطابق خواست کارفرمای محترم اصلاح گردید.
5 | در بندی جدا گانه در خصوص به وجود آمدن Deviation های احتمالی در مرحله Purchase Order ، ساخت و تست توضیحات لازم ارائه گردد. |  | 01/2294/16060 | 1401/01/20 | این مورد در قسمت 11 مدرک، مطابق خواست کارفرمای محترم به مدرک اضافه گردید.
6 | قسمت 10 ، مغایرت ها بایستی به تایید CLIENT برسد. |  | 01/2294/16060 | 1401/01/20 | مدرک مطابق خواست کارفرمای محترم اصلاح گردید.
7 | قسمت 11، بند مربوط به OTHER FEE حذف گردد. |  | 01/2294/16060 | 1401/01/20 | مدرک مطابق خواست کارفرمای محترم اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and inculpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: