## S-Curve-Weekly
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 171
| Project | Index | time axis 2021-06-19 to 2024-06-22
Binak Oil Field Development-EPC | time axis 2021-06-19 to 2024-06-22
| BINAK-Total (EPCC) | 3 | Plan Rev00 -Cumulative | 0.06748% | 0.2656% | 0.3449% | 0.4451% | 0.5551% | 0.6757% | 0.7473% | 0.8526% | 1.112% | 1.499% | 1.975% | 2.578% | 3.217% | 3.913% | 4.606% | 5.326% | 6.18% | 7.079% | 8.018% | 8.98% | 10.04% | 11.19% | 12.17% | 13.4% | 14.9% | 16.27% | 17.71% | 19.09% | 20.5% | 22.06% | 23.82% | 25.54% | 27.02% | 28.5% | 29.96% | 31.49% | 33.06% | 34.68% | 36.34% | 37.94% | 39.17% | 40.38% | 41.69% | 43% | 44.35% | 45.57% | 46.85% | 48.07% | 49.29% | 50.75% | 52.15% | 53.65% | 55.07% | 56.54% | 58.05% | 59.58% | 61.13% | 62.77% | 64.65% | 66.35% | 67.68% | 69.06% | 70.47% | 71.8% | 73.07% | 74.4% | 75.69% | 76.89% | 77.94% | 79.03% | 80.27% | 81.25% | 82.13% | 83.1% | 84.01% | 85.13% | 86.49% | 87.42% | 88.41% | 89.85% | 91.33% | 92.95% | 93.43% | 93.78% | 95.67% | 96.08% | 96.53% | 96.9% | 97.26% | 97.58% | 97.9% | 98.12% | 98.3% | 98.51% | 98.76% | 98.86% | 98.94% | 99.01% | 99.08% | 99.19% | 99.37% | 99.65% | 99.85% | 99.96% | 100%
|  |  | Plan Rev01 -Cumulative | 0.0002033% | 0.0007022% | 0.001305% | 0.002572% | 0.003935% | 0.02172% | 0.0466% | 0.07168% | 0.09748% | 0.1256% | 0.1545% | 0.1848% | 0.2185% | 0.2551% | 0.2927% | 0.3304% | 0.3682% | 0.4069% | 0.4463% | 0.4859% | 0.5261% | 0.5672% | 0.6141% | 0.6721% | 0.7334% | 0.8011% | 0.8715% | 0.9429% | 1.015% | 1.088% | 1.164% | 1.247% | 1.348% | 1.491% | 1.642% | 1.819% | 2.004% | 2.193% | 2.386% | 2.53% | 3.71% | 3.936% | 4.379% | 4.579% | 4.784% | 5.171% | 5.471% | 5.837% | 6.21% | 6.597% | 7.185% | 7.706% | 8.235% | 9.014% | 10.11% | 11.42% | 12.55% | 13.37% | 14.12% | 14.87% | 15.63% | 16.35% | 17.13% | 18.03% | 19.32% | 20.38% | 21.42% | 22.57% | 23.86% | 25.19% | 26.63% | 28.12% | 29.54% | 30.99% | 32.46% | 33.88% | 35.37% | 36.79% | 38.17% | 39.55% | 41.03% | 42.42% | 43.85% | 45.27% | 46.66% | 48.1% | 49.5% | 50.85% | 52.19% | 53.48% | 54.86% | 56.6% | 58.46% | 60.06% | 61.69% | 63.19% | 64.63% | 65.9% | 67.12% | 68.34% | 69.47% | 70.64% | 71.72% | 72.79% | 73.91% | 74.94% | 75.99% | 77.1% | 77.97% | 78.8% | 79.65% | 80.31% | 80.95% | 81.61% | 82.3% | 83.08% | 83.9% | 85.26% | 86.11% | 86.97% | 87.57% | 88.11% | 88.89% | 89.44% | 89.88% | 90.63% | 91.34% | 91.82% | 92.25% | 93.66% | 94.39% | 94.59% | 94.75% | 94.87% | 96.53% | 96.82% | 97.1% | 97.36% | 97.61% | 97.86% | 98.08% | 98.29% | 98.5% | 98.68% | 98.83% | 98.91% | 98.99% | 99.04% | 99.07% | 99.11% | 99.15% | 99.23% | 99.37% | 99.64% | 99.84% | 99.95% | 100% | 100%
Azar Oil Field Development |  |  | Plan Rev01-Period | 0.0002033% | 0.0004989% | 0.0006028% | 0.001267% | 0.001362% | 0.01778% | 0.02488% | 0.02508% | 0.0258% | 0.02809% | 0.02896% | 0.03024% | 0.03371% | 0.03664% | 0.03756% | 0.03767% | 0.03785% | 0.03869% | 0.03937% | 0.03965% | 0.04015% | 0.04112% | 0.04687% | 0.05809% | 0.06124% | 0.06768% | 0.07045% | 0.07136% | 0.07238% | 0.07314% | 0.07542% | 0.08306% | 0.1008% | 0.143% | 0.1518% | 0.1764% | 0.1853% | 0.1887% | 0.1933% | 0.1439% | 1.18% | 0.2254% | 0.443% | 0.2008% | 0.2043% | 0.3873% | 0.3002% | 0.3661% | 0.373% | 0.3867% | 0.5877% | 0.5212% | 0.5291% | 0.779% | 1.101% | 1.307% | 1.131% | 0.816% | 0.7523% | 0.7448% | 0.7594% | 0.7236% | 0.7819% | 0.8988% | 1.293% | 1.052% | 1.046% | 1.15% | 1.286% | 1.328% | 1.447% | 1.486% | 1.42% | 1.453% | 1.463% | 1.424% | 1.487% | 1.424% | 1.383% | 1.374% | 1.486% | 1.388% | 1.429% | 1.418% | 1.394% | 1.434% | 1.409% | 1.348% | 1.334% | 1.294% | 1.383% | 1.738% | 1.863% | 1.592% | 1.629% | 1.501% | 1.446% | 1.268% | 1.219% | 1.223% | 1.132% | 1.166% | 1.079% | 1.067% | 1.127% | 1.026% | 1.056% | 1.108% | 0.8706% | 0.8258% | 0.8543% | 0.654% | 0.6437% | 0.6542% | 0.6966% | 0.7783% | 0.8168% | 1.361% | 0.8514% | 0.8606% | 0.5948% | 0.5406% | 0.7839% | 0.5533% | 0.4375% | 0.7505% | 0.712% | 0.4798% | 0.4256% | 1.413% | 0.724% | 0.2007% | 0.1592% | 0.1236% | 1.66% | 0.292% | 0.2752% | 0.2617% | 0.2515% | 0.249% | 0.2237% | 0.212% | 0.2096% | 0.1778% | 0.1439% | 0.08239% | 0.0816% | 0.0451% | 0.03922% | 0.03545% | 0.04126% | 0.0745% | 0.1431% | 0.2671% | 0.2054% | 0.1112% | 0.04764% | 0%
Actual
Surface
FEED Package |  |  | Binak Oil Field Development-EPC
Geotechnical Survey
Topographical Survey
Geophysical Survey |  |  | BINAK-Total (EPCC)
Comprehensive surface survey
Main Oil Pipeline
Main Oil Transfer Pumps
Gas Compressors
Wellhead Control Panel
HIPPS
Flow lines’ Pipes
Well Pads, Access Roads Re-Construction
Water Supply
Wellhead Facilities,Flowlines
Oil & Gas Export Pipe Lines
CPF Civil Works
Central Process Facilities (CPF)
Modified Early Production
Final Production
Operator's Residential Facility
Electrical Power Supply Substation
Soil, Concrete and Asphalt Laboratory
Surface Technical Site Supervision
Third Party Inspection on vendor’s premises
Other Pproject
Subsurface
Drilling
Drilling of 10 wells-GPTK
Drilling of 7 wells-NIDC
Drilling of 2 Wells-Persia
Acid Fracture / High Volume Acid
Procurement of Tubing 5 1/2" , 4 1/2" , 3 1/2"( for 10 wells)
Procurement of Completion (for 19 Wells)
Technical Site supervision (drilling)
Third Party Inspection on sub surface vendor’s premises
Subsurface Studies
Full Field Reservoir Study
Fluid Sampling and Analysis
Other Projects
[163 empty] | 0.02439 | 0.04878 | 0.073171 | 0.097561 | 0.12195 | 0.14634 | 0.17073 | 0.19512 | 0.21951 | 0.2439 | 0.26829 | 0.29268 | 0.31707 | 0.34146 | 0.36585 | 0.39024 | 0.41463 | 0.43902 | 0.46341 | 0.4878 | 0.5122 | 0.53659 | 0.56098 | 0.58537 | 0.60976 | 0.63415 | 0.65854 | 0.68293 | 0.70732 | 0.73171 | 0.7561 | 0.78049 | 0.80488 | 0.82927 | 0.85366 | 0.87805 | 0.90244 | 0.92683 | 0.95122 | 0.97561 | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[165 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## S-Curve-Monthly
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Project | Index |  | 1: 2021; 7: 2022; 19: 2023; 31: 2024
Binak Oil Field Development-EPC |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
BINAK-Total (EPCC) | 3 |  | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2023-01-31 | 2023-02-28 | 2023-03-31 | 2023-04-30 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-28 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30
|  | Plan Rev00 -Cumulative | 0.1988% | 0.7767% | 1.804% | 3.836% | 7.14% | 12.17% | 18.53% | 25.55% | 33% | 39.97% | 47.22% | 54.7% | 62.39% | 69.37% | 74.65% | 78.74% | 82.17% | 87.07% | 93.25% | 96.48% | 98.1% | 98.51% | 99.35% | 100%
|  | Plan Rev01 -Cumulative | 0.02526% | 0.1419% | 0.2873% | 0.4576% | 0.6471% | 0.9429% | 1.289% | 1.898% | 3.684% | 4.815% | 6.428% | 8.895% | 13.59% | 16.9% | 21.42% | 27.28% | 33.47% | 39.75% | 46.06% | 51.62% | 58.46% | 64.97% | 70.3% | 74.94% | 79.15% | 82.19% | 86.25% | 89.26% | 91.76% | 94.64% | 97.02% | 98.05% | 98.85% | 99.09% | 99.64% | 100%
|  | Plan Rev01-Period | 0.02526% | 0.1166% | 0.1454% | 0.1703% | 0.1895% | 0.2958% | 0.3461% | 0.6092% | 1.786% | 1.131% | 1.614% | 2.467% | 4.694% | 3.312% | 4.521% | 5.857% | 6.189% | 6.284% | 6.311% | 5.554% | 6.849% | 6.503% | 5.334% | 4.636% | 4.211% | 3.041% | 4.061% | 3.005% | 2.501% | 2.886% | 2.374% | 1.034% | 0.7977% | 0.2447% | 0.5415% | 0.3643%
Actual
Binak Oil Field Development-EPC
BINAK-Total (EPCC)
[39 empty] | 0.02439 | 0.04878 | 0.073171 | 0.097561 | 0.12195 | 0.14634 | 0.17073 | 0.19512 | 0.21951 | 0.2439 | 0.26829 | 0.29268 | 0.31707 | 0.34146 | 0.36585 | 0.39024 | 0.41463 | 0.43902 | 0.46341 | 0.4878 | 0.5122 | 0.53659 | 0.56098 | 0.58537 | 0.60976 | 0.63415 | 0.65854 | 0.68293 | 0.70732 | 0.73171 | 0.7561 | 0.78049 | 0.80488 | 0.82927 | 0.85366 | 0.87805 | 0.90244 | 0.92683 | 0.95122 | 0.97561 | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[41 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Data-Base-Monthly
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WBS | Activity ID | Original Duration | Start | Finish | Budgeted Labor Units | Spreadsheet Field | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01
3 | BINAK-Total (EPCC) | 1095 | 23-Jun-21 A | 2024-06-21 | 10000000 | 3 | 55.03 | 2526.48 | 14191.47 | 28731.42 | 45758.23 | 64710.5 | 94288.42 | 128896.82 | 189820.29 | 368430.56 | 481490.6 | 642843.08 | 889515.51 | 1358936.34 | 1690103.67 | 2142198.34 | 2727886.32 | 3346807.26 | 3975173.34 | 4606252.05 | 5161614.98 | 5846491.78 | 6496829.15 | 7030230.78 | 7493856.03 | 7914949.69 | 8219093.05 | 8625213.58 | 8925701.71 | 9175777.33 | 9464374.21 | 9701821.95 | 9805186.85 | 9884955.61 | 9909421.28 | 9963574.99 | 10000000 | 0.0005503% | 0.02526% | 0.1419% | 0.2873% | 0.4576% | 0.6471% | 0.9429% | 1.289% | 1.898% | 3.684% | 4.815% | 6.428% | 8.895% | 13.59% | 16.9% | 21.42% | 27.28% | 33.47% | 39.75% | 46.06% | 51.62% | 58.46% | 64.97% | 70.3% | 74.94% | 79.15% | 82.19% | 86.25% | 89.26% | 91.76% | 94.64% | 97.02% | 98.05% | 98.85% | 99.09% | 99.64% | 100%
4 | GENERAL | 720 | 23-Jun-21 A | 2024-03-08 | 532432.82 | 4 | 55.03 | 2394.53 | 11179.72 | 19696.66 | 28516.34 | 37585 | 49563.54 | 63191.16 | 97538.01 | 229079.94 | 269391.52 | 312464.83 | 373450.58 | 406071.36 | 417155.59 | 457814.48 | 462634.41 | 467160.97 | 472046.05 | 476931.13 | 481353.29 | 486542.96 | 491273.73 | 496158.81 | 500889.59 | 505673.14 | 510456.69 | 515390.52 | 519736.07 | 523426.65 | 526964.06 | 530148.48 | 532187.51 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 0.01034% | 0.4497% | 2.1% | 3.699% | 5.356% | 7.059% | 9.309% | 11.87% | 18.32% | 43.03% | 50.6% | 58.69% | 70.14% | 76.27% | 78.35% | 85.99% | 86.89% | 87.74% | 88.66% | 89.58% | 90.41% | 91.38% | 92.27% | 93.19% | 94.08% | 94.97% | 95.87% | 96.8% | 97.62% | 98.31% | 98.97% | 99.57% | 99.95% | 100% | 100% | 100% | 100%
5 | SUB-Surface DEVELOPMENT | 929 | 24-Jul-21 A | 2024-03-17 | 1818441.13 | 5 |  | 28.06 | 878.07 | 4399.82 | 9503.8 | 15765.63 | 27587.06 | 41167.68 | 58054.63 | 84683.07 | 135630.91 | 219594.88 | 358464.16 | 672913.8 | 828123.51 | 976766.2 | 1162153.98 | 1320651.35 | 1444017.4 | 1552086.06 | 1616994.73 | 1670006.15 | 1738314.11 | 1767075.35 | 1782589.62 | 1788207.67 | 1792845.43 | 1795261.58 | 1797665.4 | 1808608.13 | 1817475.88 | 1818121.36 | 1818266.21 | 1818441.13 | 1818441.13 | 1818441.13 | 1818441.13 | 0% | 0.001543% | 0.04829% | 0.242% | 0.5226% | 0.867% | 1.517% | 2.264% | 3.193% | 4.657% | 7.459% | 12.08% | 19.71% | 37% | 45.54% | 53.71% | 63.91% | 72.63% | 79.41% | 85.35% | 88.92% | 91.84% | 95.59% | 97.18% | 98.03% | 98.34% | 98.59% | 98.73% | 98.86% | 99.46% | 99.95% | 99.98% | 99.99% | 100% | 100% | 100% | 100%
6 | Package 01-New Well # W018S | 649 | 24-Jul-21 A | 2023-04-13 | 88589.59 | 6 |  | 2.59 | 441.31 | 2264.01 | 4748.81 | 7363.39 | 11758.13 | 16994.6 | 21807.64 | 25372.94 | 26855.86 | 33955.21 | 42380.08 | 56444.94 | 62549.67 | 65578.73 | 71793.92 | 76995.91 | 82183.16 | 86447.82 | 87919.82 | 88558.06 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 0% | 0.002924% | 0.4982% | 2.556% | 5.36% | 8.312% | 13.27% | 19.18% | 24.62% | 28.64% | 30.31% | 38.33% | 47.84% | 63.72% | 70.61% | 74.03% | 81.04% | 86.91% | 92.77% | 97.58% | 99.24% | 99.96% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | Package 02-New Well # W028 (Bangestan) | 449 | 24-Jul-21 A | 2023-05-08 | 128827.09 | 7 |  | 1.38 | 35.87 | 1073.01 | 2845.35 | 4893.22 | 8512.39 | 12931.94 | 17519.67 | 23801.25 | 34544.33 | 49503.84 | 62039.93 | 84126.7 | 98741.82 | 103718.33 | 111541.62 | 117595.11 | 121452.31 | 125407.78 | 127842.54 | 128622 | 128796.33 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 0% | 0.001071% | 0.02784% | 0.8329% | 2.209% | 3.798% | 6.608% | 10.04% | 13.6% | 18.48% | 26.81% | 38.43% | 48.16% | 65.3% | 76.65% | 80.51% | 86.58% | 91.28% | 94.28% | 97.35% | 99.24% | 99.84% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | Package 03-New Well # W046S (Bangestan) | 475 | 24-Jul-21 A | 2023-06-29 | 592707.12 | 8 |  | 3.33 | 57.14 | 123.06 | 195.79 | 296.79 | 436.02 | 597.67 | 4203.13 | 16391 | 44832.14 | 85375.25 | 140324.97 | 319561.1 | 363360.58 | 397367.07 | 466837.45 | 504981.08 | 523583.78 | 538367.61 | 549859.62 | 563002.81 | 584863.55 | 591653.6 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 0% | 0.0005618% | 0.009641% | 0.02076% | 0.03303% | 0.05007% | 0.07356% | 0.1008% | 0.7091% | 2.765% | 7.564% | 14.4% | 23.68% | 53.92% | 61.31% | 67.04% | 78.76% | 85.2% | 88.34% | 90.83% | 92.77% | 94.99% | 98.68% | 99.82% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | Package 04-New Well # W035 (Bangestan) | 613.75 | 24-Jul-21 A | 2023-11-23 | 156733.57 | 9 |  | 1.49 | 28.68 | 285.79 | 686.84 | 1714.49 | 4559.45 | 7420.87 | 10042.42 | 12212.78 | 18934.22 | 24303.09 | 32276.31 | 40724.1 | 49997.27 | 72281.81 | 96601.52 | 123878.22 | 128650.45 | 135791.07 | 141248.69 | 145913.19 | 150274.92 | 152020.33 | 152036.38 | 153304.59 | 155777.42 | 156349.74 | 156540.51 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 0% | 0.0009507% | 0.0183% | 0.1823% | 0.4382% | 1.094% | 2.909% | 4.735% | 6.407% | 7.792% | 12.08% | 15.51% | 20.59% | 25.98% | 31.9% | 46.12% | 61.63% | 79.04% | 82.08% | 86.64% | 90.12% | 93.1% | 95.88% | 96.99% | 97% | 97.81% | 99.39% | 99.76% | 99.88% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Package 05-New Well # W008N | 692.75 | 24-Jul-21 A | 2024-02-10 | 69431.14 | 10 |  | 1.48 | 28.45 | 62.17 | 98.91 | 154.98 | 479.05 | 823.63 | 1161.2 | 1524.59 | 2163.3 | 3635.73 | 5756.36 | 7934.62 | 10132.62 | 12428 | 16211.48 | 20003.3 | 28373.61 | 32936.06 | 41033.37 | 51819.74 | 57236.89 | 60597.99 | 62233.06 | 63483.95 | 65232.84 | 66821.02 | 68323.9 | 68979.98 | 69267.64 | 69401.25 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 0% | 0.002132% | 0.04098% | 0.08954% | 0.1425% | 0.2232% | 0.69% | 1.186% | 1.672% | 2.196% | 3.116% | 5.236% | 8.291% | 11.43% | 14.59% | 17.9% | 23.35% | 28.81% | 40.87% | 47.44% | 59.1% | 74.63% | 82.44% | 87.28% | 89.63% | 91.43% | 93.95% | 96.24% | 98.41% | 99.35% | 99.76% | 99.96% | 100% | 100% | 100% | 100% | 100%
11 | Package 06-New Well # W007S/Manifold Extension (Bangestan) | 729 | 24-Jul-21 A | 2024-03-17 | 236214.84 | 11 |  | 3.78 | 75.85 | 158.28 | 250.8 | 384.34 | 547.27 | 729.26 | 935.66 | 1514.35 | 2564.96 | 4875.79 | 13697.24 | 24027.48 | 43189.54 | 59189.83 | 81533.97 | 114455.86 | 141854.99 | 169003.79 | 180497.02 | 190131.71 | 197711.19 | 205499.98 | 213930.92 | 215750.32 | 215892.06 | 216029.24 | 216739.41 | 226833 | 235413.08 | 235924.96 | 236039.92 | 236214.84 | 236214.84 | 236214.84 | 236214.84 | 0% | 0.0016% | 0.03211% | 0.06701% | 0.1062% | 0.1627% | 0.2317% | 0.3087% | 0.3961% | 0.6411% | 1.086% | 2.064% | 5.799% | 10.17% | 18.28% | 25.06% | 34.52% | 48.45% | 60.05% | 71.55% | 76.41% | 80.49% | 83.7% | 87% | 90.57% | 91.34% | 91.4% | 91.45% | 91.76% | 96.03% | 99.66% | 99.88% | 99.93% | 100% | 100% | 100% | 100%
12 | Package 07-Workover # 14 | 532 | 24-Jul-21 A | 2023-09-02 | 140256.49 | 12 |  | 3.49 | 52.65 | 108.32 | 169.25 | 242.69 | 331.26 | 429.49 | 617.82 | 1053.68 | 1559.57 | 4528.87 | 23353.53 | 54860.13 | 73326.57 | 95431.74 | 111647.83 | 118861.83 | 125069.28 | 134683.04 | 135303.86 | 135961.04 | 137101.93 | 138897.12 | 139838.7 | 140090.32 | 140249.42 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 0% | 0.002488% | 0.03754% | 0.07723% | 0.1207% | 0.173% | 0.2362% | 0.3062% | 0.4405% | 0.7513% | 1.112% | 3.229% | 16.65% | 39.11% | 52.28% | 68.04% | 79.6% | 84.75% | 89.17% | 96.03% | 96.47% | 96.94% | 97.75% | 99.03% | 99.7% | 99.88% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
13 | Package 08-Workover # 12 | 512.75 | 24-Jul-21 A | 2023-08-14 | 113892.3 | 13 |  | 3.51 | 52.71 | 108.4 | 169.35 | 239.2 | 322.72 | 415.88 | 592.34 | 971.68 | 1719.34 | 9939.13 | 23445.1 | 49322.77 | 64479.08 | 71183.94 | 76447.56 | 78958.98 | 98237.11 | 105911.73 | 107794.95 | 108460.05 | 112587.12 | 113416.32 | 113722.91 | 113851.36 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 0% | 0.003082% | 0.04628% | 0.09518% | 0.1487% | 0.21% | 0.2834% | 0.3652% | 0.5201% | 0.8532% | 1.51% | 8.727% | 20.59% | 43.31% | 56.61% | 62.5% | 67.12% | 69.33% | 86.25% | 92.99% | 94.65% | 95.23% | 98.85% | 99.58% | 99.85% | 99.96% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
14 | Package 09-Workover # 15 | 499 | 24-Jul-21 A | 2023-07-31 | 170781.35 | 14 |  | 3.51 | 52.71 | 108.4 | 169.35 | 237.32 | 318.06 | 408.45 | 582.4 | 881.46 | 1085.23 | 1901.96 | 11814.1 | 25676.36 | 43668.43 | 71594.56 | 88898.01 | 106840.59 | 122973.34 | 138212.31 | 156252.1 | 161765.07 | 169466.75 | 170272.18 | 170584.46 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 0% | 0.002055% | 0.03086% | 0.06347% | 0.09916% | 0.139% | 0.1862% | 0.2392% | 0.341% | 0.5161% | 0.6354% | 1.114% | 6.918% | 15.03% | 25.57% | 41.92% | 52.05% | 62.56% | 72.01% | 80.93% | 91.49% | 94.72% | 99.23% | 99.7% | 99.88% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | Package 10-Workover # 05 | 551.5 | 24-Jul-21 A | 2023-09-22 | 121007.64 | 15 |  | 3.51 | 52.71 | 108.4 | 169.35 | 239.2 | 322.72 | 415.88 | 592.34 | 959.34 | 1371.95 | 1576.01 | 3376.54 | 10235.61 | 18677.94 | 27992.18 | 40640.64 | 58080.46 | 71639.37 | 85324.83 | 89242.75 | 95772.49 | 111685.85 | 117301.16 | 120119.39 | 120821.97 | 120896.24 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 0% | 0.002901% | 0.04356% | 0.08958% | 0.1399% | 0.1977% | 0.2667% | 0.3437% | 0.4895% | 0.7928% | 1.134% | 1.302% | 2.79% | 8.459% | 15.44% | 23.13% | 33.59% | 48% | 59.2% | 70.51% | 73.75% | 79.15% | 92.3% | 96.94% | 99.27% | 99.85% | 99.91% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
16 | SURFACE DEVELOPMENT | 825 | 24-Jul-21 A | 2024-06-21 | 7649126.04 | 16 |  | 103.9 | 2133.68 | 4634.94 | 7738.09 | 11359.88 | 17137.82 | 24537.97 | 34227.65 | 54667.54 | 76468.17 | 110783.38 | 157600.77 | 279951.18 | 444824.57 | 707617.67 | 1103097.92 | 1558994.94 | 2059109.89 | 2577234.85 | 3063266.96 | 3689942.67 | 4267241.31 | 4766996.61 | 5210376.82 | 5621068.88 | 5915790.93 | 6314561.47 | 6608300.24 | 6843742.55 | 7119934.27 | 7353552.1 | 7454733.13 | 7534081.65 | 7558547.32 | 7612701.03 | 7649126.04 | 0% | 0.001358% | 0.02789% | 0.06059% | 0.1012% | 0.1485% | 0.224% | 0.3208% | 0.4475% | 0.7147% | 0.9997% | 1.448% | 2.06% | 3.66% | 5.815% | 9.251% | 14.42% | 20.38% | 26.92% | 33.69% | 40.05% | 48.24% | 55.79% | 62.32% | 68.12% | 73.49% | 77.34% | 82.55% | 86.39% | 89.47% | 93.08% | 96.14% | 97.46% | 98.5% | 98.82% | 99.52% | 100%
17 | Package 11- EPC Pipeline 8" & 4" | 625 | 24-Jul-21 A | 2023-12-04 | 1535354.68 | 17 |  | 28.46 | 441.73 | 964.27 | 1524.82 | 2161.32 | 3189.32 | 4450.83 | 6151.91 | 9772.29 | 14233.35 | 17249.28 | 19382.7 | 22398.82 | 27594.07 | 69147.01 | 183510.57 | 340033.63 | 506580.26 | 669242.92 | 851589.46 | 1119763.4 | 1214266.66 | 1295447.33 | 1378350.92 | 1468465.65 | 1496029.23 | 1516381.98 | 1524825.57 | 1535003.8 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 0% | 0.001854% | 0.02877% | 0.0628% | 0.09931% | 0.1408% | 0.2077% | 0.2899% | 0.4007% | 0.6365% | 0.927% | 1.123% | 1.262% | 1.459% | 1.797% | 4.504% | 11.95% | 22.15% | 32.99% | 43.59% | 55.47% | 72.93% | 79.09% | 84.37% | 89.77% | 95.64% | 97.44% | 98.76% | 99.31% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
18 | Package 12- EPC # Compressor Station | 825 | 24-Jul-21 A | 2024-06-21 | 6113771.36 | 18 |  | 75.44 | 1691.94 | 3670.68 | 6213.27 | 9198.57 | 13948.5 | 20087.15 | 28075.74 | 44895.25 | 62234.82 | 93534.09 | 138218.08 | 257552.35 | 417230.5 | 638470.67 | 919587.35 | 1218961.31 | 1552529.63 | 1907991.93 | 2211677.5 | 2570179.27 | 3052974.64 | 3471549.28 | 3832025.9 | 4152603.23 | 4419761.7 | 4798179.5 | 5083474.67 | 5308738.76 | 5584579.59 | 5818197.42 | 5919378.45 | 5998726.97 | 6023192.64 | 6077346.35 | 6113771.36 | 0% | 0.001234% | 0.02767% | 0.06004% | 0.1016% | 0.1505% | 0.2281% | 0.3286% | 0.4592% | 0.7343% | 1.018% | 1.53% | 2.261% | 4.213% | 6.824% | 10.44% | 15.04% | 19.94% | 25.39% | 31.21% | 36.18% | 42.04% | 49.94% | 56.78% | 62.68% | 67.92% | 72.29% | 78.48% | 83.15% | 86.83% | 91.34% | 95.17% | 96.82% | 98.12% | 98.52% | 99.4% | 100%
EPCC | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
|  | Original Duration | Start | Finish | Budgeted Labor Units | Spreadsheet Field | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01
22 | General | 720 | 23-Jun-21 A | 2024-03-08 | 532432.82 | 22 | 55.03 | 2394.53 | 11179.72 | 19696.66 | 28516.34 | 37585 | 49563.54 | 63191.16 | 97538.01 | 229079.94 | 269391.52 | 312464.83 | 373450.58 | 406071.36 | 417155.59 | 457814.48 | 462634.41 | 467160.97 | 472046.05 | 476931.13 | 481353.29 | 486542.96 | 491273.73 | 496158.81 | 500889.59 | 505673.14 | 510456.69 | 515390.52 | 519736.07 | 523426.65 | 526964.06 | 530148.48 | 532187.51 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 0.01034% | 0.4497% | 2.1% | 3.699% | 5.356% | 7.059% | 9.309% | 11.87% | 18.32% | 43.03% | 50.6% | 58.69% | 70.14% | 76.27% | 78.35% | 85.99% | 86.89% | 87.74% | 88.66% | 89.58% | 90.41% | 91.38% | 92.27% | 93.19% | 94.08% | 94.97% | 95.87% | 96.8% | 97.62% | 98.31% | 98.97% | 99.57% | 99.95% | 100% | 100% | 100% | 100%
23 | Engineering | 784 | 24-Jul-21 A | 2024-05-11 | 272905.62 | 23 |  | 131.95 | 2601.38 | 5619.99 | 9300.2 | 13696.64 | 20484.45 | 29044.18 | 40408.41 | 64336.63 | 90216 | 107177.42 | 123927.03 | 145132.62 | 166909.8 | 174762.92 | 190063.65 | 200310.75 | 208490.58 | 214852.91 | 219634.85 | 222526.64 | 224311.85 | 225798.15 | 227397.45 | 228349.08 | 228733.53 | 232393.13 | 235265.44 | 236433.52 | 237815.38 | 238468.83 | 238599.52 | 254638.73 | 268004.75 | 272905.62 | 272905.62 | 0% | 0.04835% | 0.9532% | 2.059% | 3.408% | 5.019% | 7.506% | 10.64% | 14.81% | 23.57% | 33.06% | 39.27% | 45.41% | 53.18% | 61.16% | 64.04% | 69.64% | 73.4% | 76.4% | 78.73% | 80.48% | 81.54% | 82.19% | 82.74% | 83.32% | 83.67% | 83.81% | 85.16% | 86.21% | 86.64% | 87.14% | 87.38% | 87.43% | 93.31% | 98.2% | 100% | 100%
24 | Procurement | 670 | 01-Feb-22 A | 2024-01-18 | 7033236.09 | 24 | [9 empty] | 7171.34 | 49198.14 | 140606.64 | 283999.87 | 562207.53 | 818947.15 | 1181847.98 | 1669881.22 | 2187249.24 | 2720159.16 | 3266118.35 | 3735094.99 | 4328571.58 | 4798453.28 | 5161414.6 | 5478027.86 | 5799709.48 | 6047514.1 | 6330799.33 | 6515853.04 | 6655946.64 | 6872661.95 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.102% | 0.6995% | 1.999% | 4.038% | 7.994% | 11.64% | 16.8% | 23.74% | 31.1% | 38.68% | 46.44% | 53.11% | 61.54% | 68.23% | 73.39% | 77.89% | 82.46% | 85.98% | 90.01% | 92.64% | 94.64% | 97.72% | 100% | 100% | 100% | 100% | 100% | 100%
25 | Construction | 950 | 20-Aug-21 A | 2024-04-07 | 2016255.2 | 25 |  |  | 410.37 | 3414.77 | 7941.69 | 13428.86 | 24240.43 | 36661.48 | 51873.87 | 67842.65 | 72684.92 | 82594.19 | 108138.03 | 245524.82 | 287091.13 | 327772.97 | 405307.03 | 492086.3 | 574477.55 | 647599.32 | 723910.69 | 806836.32 | 977178.94 | 1137286.25 | 1276069.57 | 1368834.02 | 1419292.56 | 1526130.94 | 1628578.45 | 1723813.67 | 1788696.48 | 1861086.72 | 1962137.07 | 2016143.66 | 2016255.2 | 2016255.2 | 2016255.2 | 0% | 0% | 0.02035% | 0.1694% | 0.3939% | 0.666% | 1.202% | 1.818% | 2.573% | 3.365% | 3.605% | 4.096% | 5.363% | 12.18% | 14.24% | 16.26% | 20.1% | 24.41% | 28.49% | 32.12% | 35.9% | 40.02% | 48.47% | 56.41% | 63.29% | 67.89% | 70.39% | 75.69% | 80.77% | 85.5% | 88.71% | 92.3% | 97.32% | 99.99% | 100% | 100% | 100%
26 | Commissioning | 527.25 | 2023-01-11 | 2024-06-21 | 145170.26 | 26 | 2023-01-01: 750.34; 2023-02-01: 1621.15; 2023-03-01: 2014.29; 2023-04-01: 5611.35; 2023-05-01: 9572.96; 2023-06-01: 11471.56; 2023-07-01: 12383.98; 2023-08-01: 13096.18; 2023-09-01: 20499.65; 2023-10-01: 26268.71; 2023-11-01: 36156.86; 2023-12-01: 38236.33; 2024-01-01: 38881.82; 2024-02-01: 39026.66; 2024-03-01: 48504.3; 2024-04-01: 59492.41; 2024-05-01: 108745.25; 2024-06-01: 145170.26 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5169% | 1.117% | 1.388% | 3.865% | 6.594% | 7.902% | 8.531% | 9.021% | 14.12% | 18.1% | 24.91% | 26.34% | 26.78% | 26.88% | 33.41% | 40.98% | 74.91% | 100%

## Data-Base-Weekly
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158
WBS | Activity ID | Original Duration | Start | Finish | Budgeted Labor Units | Spreadsheet Field | [158 empty] | 2021-06-19 | 2021-06-26 | 2021-07-03 | 2021-07-10 | 2021-07-17 | 2021-07-24 | 2021-07-31 | 2021-08-07 | 2021-08-14 | 2021-08-21 | 2021-08-28 | 2021-09-04 | 2021-09-11 | 2021-09-18 | 2021-09-25 | 2021-10-02 | 2021-10-09 | 2021-10-16 | 2021-10-23 | 2021-10-30 | 2021-11-06 | 2021-11-13 | 2021-11-20 | 2021-11-27 | 2021-12-04 | 2021-12-11 | 2021-12-18 | 2021-12-25 | 2022-01-01 | 2022-01-08 | 2022-01-15 | 2022-01-22 | 2022-01-29 | 2022-02-05 | 2022-02-12 | 2022-02-19 | 2022-02-26 | 2022-03-05 | 2022-03-12 | 2022-03-19 | 2022-03-26 | 2022-04-02 | 2022-04-09 | 2022-04-16 | 2022-04-23 | 2022-04-30 | 2022-05-07 | 2022-05-14 | 2022-05-21 | 2022-05-28 | 2022-06-04 | 2022-06-11 | 2022-06-18 | 2022-06-25 | 2022-07-02 | 2022-07-09 | 2022-07-16 | 2022-07-23 | 2022-07-30 | 2022-08-06 | 2022-08-13 | 2022-08-20 | 2022-08-27 | 2022-09-03 | 2022-09-10 | 2022-09-17 | 2022-09-24 | 2022-10-01 | 2022-10-08 | 2022-10-15 | 2022-10-22 | 2022-10-29 | 2022-11-05 | 2022-11-12 | 2022-11-19 | 2022-11-26 | 2022-12-03 | 2022-12-10 | 2022-12-17 | 2022-12-24 | 2022-12-31 | 2023-01-07 | 2023-01-14 | 2023-01-21 | 2023-01-28 | 2023-02-04 | 2023-02-11 | 2023-02-18 | 2023-02-25 | 2023-03-04 | 2023-03-11 | 2023-03-18 | 2023-03-25 | 2023-04-01 | 2023-04-08 | 2023-04-15 | 2023-04-22 | 2023-04-29 | 2023-05-06 | 2023-05-13 | 2023-05-20 | 2023-05-27 | 2023-06-03 | 2023-06-10 | 2023-06-17 | 2023-06-24 | 2023-07-01 | 2023-07-08 | 2023-07-15 | 2023-07-22 | 2023-07-29 | 2023-08-05 | 2023-08-12 | 2023-08-19 | 2023-08-26 | 2023-09-02 | 2023-09-09 | 2023-09-16 | 2023-09-23 | 2023-09-30 | 2023-10-07 | 2023-10-14 | 2023-10-21 | 2023-10-28 | 2023-11-04 | 2023-11-11 | 2023-11-18 | 2023-11-25 | 2023-12-02 | 2023-12-09 | 2023-12-16 | 2023-12-23 | 2023-12-30 | 2024-01-06 | 2024-01-13 | 2024-01-20 | 2024-01-27 | 2024-02-03 | 2024-02-10 | 2024-02-17 | 2024-02-24 | 2024-03-02 | 2024-03-09 | 2024-03-16 | 2024-03-23 | 2024-03-30 | 2024-04-06 | 2024-04-13 | 2024-04-20 | 2024-04-27 | 2024-05-04 | 2024-05-11 | 2024-05-18 | 2024-05-25 | 2024-06-01 | 2024-06-08 | 2024-06-15 | 2024-06-22 | time axis 2021-06-19 to 2024-06-22
3 | BINAK-Total (EPCC) | 1095 | 23-Jun-21 A | 2024-06-21 | 10000000 | 3 | 20.33 | 70.22 | 130.5 | 257.25 | 393.49 | 2171.66 | 4659.78 | 7167.84 | 9748.06 | 12557.44 | 15453.76 | 18477.7 | 21848.75 | 25512.96 | 29269.1 | 33035.67 | 36820.86 | 40689.93 | 44627.04 | 48591.92 | 52606.53 | 56718.85 | 61405.44 | 67214.53 | 73338.2 | 80106.7 | 87152.02 | 94288.42 | 101526.46 | 108840.26 | 116382.75 | 124689.12 | 134771.02 | 149072.7 | 164248.5 | 181887.69 | 200420.81 | 219294.31 | 238622.77 | 253012.49 | 371014.23 | 393554.45 | 437854.11 | 457932.44 | 478365.6 | 517092.92 | 547114.97 | 583725.29 | 621022.04 | 659695.9 | 718461.27 | 770578.42 | 823483.66 | 901384.14 | 1011497.2 | 1142231.58 | 1255330.52 | 1336933.52 | 1412166.13 | 1486641.26 | 1562585.11 | 1634941.94 | 1713132.31 | 1803017.28 | 1932350.02 | 2037592.51 | 2142198.34 | 2257231.4 | 2385837.65 | 2518665.86 | 2663333.89 | 2811918.46 | 2953947.56 | 3099237.55 | 3245542.39 | 3387939.32 | 3536622.61 | 3679023.49 | 3817276.02 | 3954646.82 | 4103268.4 | 4242030.38 | 4384963.51 | 4526721.31 | 4666167.3 | 4809574.57 | 4950497.62 | 5085315.72 | 5218677.44 | 5348119.32 | 5486381.3 | 5660150.13 | 5846491.78 | 6005725.43 | 6168631.47 | 6318681.6 | 6463250.75 | 6590038.52 | 6711979.44 | 6834269.49 | 6947449.1 | 7064023.39 | 7171903.95 | 7278570.46 | 7391303.15 | 7493856.03 | 7599456.42 | 7710300.8 | 7797361.82 | 7879945.98 | 7965374.29 | 8030779.08 | 8095153.57 | 8160573.26 | 8230229.77 | 8308064.35 | 8389744.02 | 8525868.19 | 8611004.04 | 8697065.68 | 8756547.95 | 8810609.69 | 8889002.39 | 8944335.06 | 8988081.01 | 9063132.62 | 9134335.46 | 9182310.68 | 9224874.73 | 9366167.07 | 9438563.22 | 9458631.64 | 9474550.73 | 9486913.5 | 9652958.41 | 9682162.8 | 9709682.07 | 9735855.93 | 9761003.34 | 9785907.3 | 9808275.23 | 9829472.97 | 9850429.95 | 9868213.68 | 9882601.48 | 9890840.92 | 9899000.67 | 9903510.84 | 9907432.53 | 9910977.41 | 9915103.42 | 9922553.9 | 9936860.67 | 9963574.99 | 9984112.28 | 9995236.29 | 10000000 | 10000000 | 0.0002033% | 0.0007022% | 0.001305% | 0.002572% | 0.003935% | 0.02172% | 0.0466% | 0.07168% | 0.09748% | 0.1256% | 0.1545% | 0.1848% | 0.2185% | 0.2551% | 0.2927% | 0.3304% | 0.3682% | 0.4069% | 0.4463% | 0.4859% | 0.5261% | 0.5672% | 0.6141% | 0.6721% | 0.7334% | 0.8011% | 0.8715% | 0.9429% | 1.015% | 1.088% | 1.164% | 1.247% | 1.348% | 1.491% | 1.642% | 1.819% | 2.004% | 2.193% | 2.386% | 2.53% | 3.71% | 3.936% | 4.379% | 4.579% | 4.784% | 5.171% | 5.471% | 5.837% | 6.21% | 6.597% | 7.185% | 7.706% | 8.235% | 9.014% | 10.11% | 11.42% | 12.55% | 13.37% | 14.12% | 14.87% | 15.63% | 16.35% | 17.13% | 18.03% | 19.32% | 20.38% | 21.42% | 22.57% | 23.86% | 25.19% | 26.63% | 28.12% | 29.54% | 30.99% | 32.46% | 33.88% | 35.37% | 36.79% | 38.17% | 39.55% | 41.03% | 42.42% | 43.85% | 45.27% | 46.66% | 48.1% | 49.5% | 50.85% | 52.19% | 53.48% | 54.86% | 56.6% | 58.46% | 60.06% | 61.69% | 63.19% | 64.63% | 65.9% | 67.12% | 68.34% | 69.47% | 70.64% | 71.72% | 72.79% | 73.91% | 74.94% | 75.99% | 77.1% | 77.97% | 78.8% | 79.65% | 80.31% | 80.95% | 81.61% | 82.3% | 83.08% | 83.9% | 85.26% | 86.11% | 86.97% | 87.57% | 88.11% | 88.89% | 89.44% | 89.88% | 90.63% | 91.34% | 91.82% | 92.25% | 93.66% | 94.39% | 94.59% | 94.75% | 94.87% | 96.53% | 96.82% | 97.1% | 97.36% | 97.61% | 97.86% | 98.08% | 98.29% | 98.5% | 98.68% | 98.83% | 98.91% | 98.99% | 99.04% | 99.07% | 99.11% | 99.15% | 99.23% | 99.37% | 99.64% | 99.84% | 99.95% | 100% | 100%
4 | GENERAL | 720 | 23-Jun-21 A | 2024-03-08 | 532432.82 | 4 | 20.33 | 70.22 | 130.5 | 257.25 | 393.49 | 2111.44 | 4093.02 | 6075.97 | 8060.77 | 10045.56 | 12030.35 | 14015.14 | 16003.67 | 17992.2 | 19980.74 | 21969.27 | 23960.97 | 25953.95 | 27946.92 | 29939.9 | 31934.44 | 33954.94 | 36073.13 | 38718.9 | 41393.33 | 44113.17 | 46833 | 49563.54 | 52302.09 | 55046.62 | 57795.63 | 61131.99 | 65936.72 | 74659.23 | 84055.63 | 93488.96 | 102936.73 | 112384.5 | 121919.3 | 133590.53 | 229683.85 | 233885.71 | 262060.28 | 265519.93 | 268920.85 | 287393.85 | 294244.91 | 301335.78 | 308407.04 | 315593.59 | 340509.38 | 353296.06 | 362162.51 | 374298.08 | 380340.56 | 398924.9 | 402386.05 | 405252.4 | 408411.83 | 411113.87 | 413509.42 | 415751.48 | 417717.23 | 419784.52 | 455354.81 | 456740.26 | 457814.48 | 458888.18 | 460063.4 | 461137.1 | 462192.53 | 463214.51 | 464331.22 | 465346.4 | 466389.43 | 467469.59 | 468651.27 | 469731.43 | 470811.59 | 471891.74 | 473073.43 | 474153.59 | 475233.74 | 476313.9 | 477394.06 | 478575.74 | 479655.9 | 480736.06 | 481816.22 | 482997.9 | 484382.64 | 485462.8 | 486542.96 | 487724.64 | 488804.8 | 489884.96 | 490965.12 | 492045.27 | 493226.96 | 494307.12 | 495387.27 | 496467.43 | 497649.12 | 498729.27 | 499809.43 | 500889.59 | 501969.74 | 503049.9 | 504130.06 | 505210.22 | 506290.37 | 507370.53 | 508450.69 | 509530.85 | 510611 | 511691.16 | 513075.9 | 514156.06 | 515236.22 | 516316.37 | 517396.53 | 518339.81 | 519228.34 | 520116.86 | 521004.54 | 521853.19 | 522700.44 | 523547.68 | 524385.82 | 525172.87 | 525956.52 | 526740.16 | 527523.81 | 528231.72 | 529046.56 | 529708.56 | 530320.91 | 530924.42 | 531527.93 | 531890.28 | 532237.05 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 0.003818% | 0.01319% | 0.02451% | 0.04832% | 0.0739% | 0.3966% | 0.7687% | 1.141% | 1.514% | 1.887% | 2.26% | 2.632% | 3.006% | 3.379% | 3.753% | 4.126% | 4.5% | 4.875% | 5.249% | 5.623% | 5.998% | 6.377% | 6.775% | 7.272% | 7.774% | 8.285% | 8.796% | 9.309% | 9.823% | 10.34% | 10.86% | 11.48% | 12.38% | 14.02% | 15.79% | 17.56% | 19.33% | 21.11% | 22.9% | 25.09% | 43.14% | 43.93% | 49.22% | 49.87% | 50.51% | 53.98% | 55.26% | 56.6% | 57.92% | 59.27% | 63.95% | 66.36% | 68.02% | 70.3% | 71.43% | 74.92% | 75.57% | 76.11% | 76.71% | 77.21% | 77.66% | 78.09% | 78.45% | 78.84% | 85.52% | 85.78% | 85.99% | 86.19% | 86.41% | 86.61% | 86.81% | 87% | 87.21% | 87.4% | 87.6% | 87.8% | 88.02% | 88.22% | 88.43% | 88.63% | 88.85% | 89.05% | 89.26% | 89.46% | 89.66% | 89.88% | 90.09% | 90.29% | 90.49% | 90.72% | 90.98% | 91.18% | 91.38% | 91.6% | 91.81% | 92.01% | 92.21% | 92.41% | 92.64% | 92.84% | 93.04% | 93.25% | 93.47% | 93.67% | 93.87% | 94.08% | 94.28% | 94.48% | 94.68% | 94.89% | 95.09% | 95.29% | 95.5% | 95.7% | 95.9% | 96.1% | 96.36% | 96.57% | 96.77% | 96.97% | 97.18% | 97.35% | 97.52% | 97.69% | 97.85% | 98.01% | 98.17% | 98.33% | 98.49% | 98.64% | 98.78% | 98.93% | 99.08% | 99.21% | 99.36% | 99.49% | 99.6% | 99.72% | 99.83% | 99.9% | 99.96% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
5 | SUB-Surface DEVELOPMENT | 929 | 24-Jul-21 A | 2024-03-17 | 1818441.13 | 5 | [5 empty] | 16.35 | 100.24 | 193.24 | 327.05 | 670.94 | 1066.14 | 1566.34 | 2365.4 | 3441.21 | 4559.58 | 5677.96 | 6797.91 | 7960.86 | 9158.22 | 10373.42 | 11600.52 | 12851.87 | 14522.67 | 16720.74 | 19083.98 | 21831.7 | 24700.91 | 27587.06 | 30498.63 | 33449.64 | 36555.07 | 39779.96 | 43055.72 | 46387.5 | 49743.68 | 55318.26 | 61709.06 | 68172.63 | 74700.72 | 75726.45 | 85914.54 | 99008.37 | 109886.36 | 121495.86 | 133664.07 | 150069.7 | 169842.07 | 188791.25 | 208035.73 | 228703.03 | 251748.8 | 280042.86 | 313461.75 | 366990.74 | 452822.5 | 538074.5 | 613832.55 | 660979.33 | 700645.16 | 739299.98 | 775940.4 | 806101.85 | 837221.87 | 868687.55 | 901615.57 | 940849.04 | 976766.2 | 1011807.53 | 1053561.93 | 1097799.22 | 1141954.21 | 1186996.22 | 1224562.76 | 1263596.19 | 1298678.85 | 1329583.38 | 1365275.41 | 1395500.67 | 1419911.71 | 1440522.59 | 1469155.89 | 1492706.85 | 1515636.27 | 1539212.37 | 1562258.67 | 1579192.52 | 1593143.66 | 1608878.07 | 1622898.93 | 1632149.3 | 1642295.86 | 1654297.61 | 1670006.15 | 1685304.19 | 1706980.8 | 1723707.56 | 1736547.37 | 1742193.12 | 1750817.56 | 1757737.41 | 1761902.53 | 1768847.96 | 1773053.08 | 1776090.17 | 1779817.53 | 1782589.62 | 1784197.57 | 1785120.22 | 1786215.5 | 1787490.57 | 1789442.69 | 1790751.72 | 1791635.53 | 1792372.4 | 1792935.64 | 1793568.01 | 1794083.09 | 1794457.22 | 1795090.71 | 1795825.49 | 1796277.04 | 1797053.29 | 1797509.94 | 1797736.07 | 1798124.55 | 1799443.89 | 1804287.32 | 1809029.64 | 1811669.72 | 1814638.01 | 1817269.88 | 1817467.93 | 1817495.22 | 1817715.4 | 1817737.32 | 1818083.82 | 1818136.38 | 1818188.94 | 1818217.48 | 1818243.72 | 1818316.19 | 1818396.15 | 1818431.14 | 1818441.13 | 1818441.13 | 1818441.13 | 1818441.13 | 1818441.13 | 1818441.13 | 1818441.13 | 1818441.13 | 1818441.13 | 1818441.13 | 1818441.13 | 1818441.13 | 1818441.13 | 1818441.13 | 1818441.13 | 0% | 0% | 0% | 0% | 0% | 0.0008991% | 0.005512% | 0.01063% | 0.01799% | 0.0369% | 0.05863% | 0.08614% | 0.1301% | 0.1892% | 0.2507% | 0.3122% | 0.3738% | 0.4378% | 0.5036% | 0.5705% | 0.6379% | 0.7068% | 0.7986% | 0.9195% | 1.049% | 1.201% | 1.358% | 1.517% | 1.677% | 1.839% | 2.01% | 2.188% | 2.368% | 2.551% | 2.736% | 3.042% | 3.394% | 3.749% | 4.108% | 4.164% | 4.725% | 5.445% | 6.043% | 6.681% | 7.35% | 8.253% | 9.34% | 10.38% | 11.44% | 12.58% | 13.84% | 15.4% | 17.24% | 20.18% | 24.9% | 29.59% | 33.76% | 36.35% | 38.53% | 40.66% | 42.67% | 44.33% | 46.04% | 47.77% | 49.58% | 51.74% | 53.71% | 55.64% | 57.94% | 60.37% | 62.8% | 65.28% | 67.34% | 69.49% | 71.42% | 73.12% | 75.08% | 76.74% | 78.08% | 79.22% | 80.79% | 82.09% | 83.35% | 84.64% | 85.91% | 86.84% | 87.61% | 88.48% | 89.25% | 89.76% | 90.31% | 90.97% | 91.84% | 92.68% | 93.87% | 94.79% | 95.5% | 95.81% | 96.28% | 96.66% | 96.89% | 97.27% | 97.5% | 97.67% | 97.88% | 98.03% | 98.12% | 98.17% | 98.23% | 98.3% | 98.41% | 98.48% | 98.53% | 98.57% | 98.6% | 98.63% | 98.66% | 98.68% | 98.72% | 98.76% | 98.78% | 98.82% | 98.85% | 98.86% | 98.88% | 98.96% | 99.22% | 99.48% | 99.63% | 99.79% | 99.94% | 99.95% | 99.95% | 99.96% | 99.96% | 99.98% | 99.98% | 99.99% | 99.99% | 99.99% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | Package 01-New Well # W018S | 649 | 24-Jul-21 A | 2023-04-13 | 88589.59 | 6 | [5 empty] | 1.65 | 8.37 | 15.87 | 56.35 | 301.17 | 560.48 | 897.61 | 1318.1 | 1808.65 | 2339.9 | 2871.15 | 3402.4 | 3974.04 | 4576.1 | 5181.2 | 5787.69 | 6396.99 | 7006.86 | 7636.65 | 8381.35 | 9466.46 | 10611.76 | 11758.13 | 12921.24 | 14108.45 | 15296.18 | 16484.92 | 17676.92 | 18872.04 | 20068.82 | 21271.67 | 22522.28 | 23773.8 | 25035.19 | 25232.4 | 25377.82 | 25412.7 | 25448.68 | 25662.71 | 26644.53 | 28502.27 | 30032.6 | 31494.53 | 33036.41 | 34627.7 | 36361.75 | 38936.45 | 40726.72 | 42619.98 | 44310.86 | 46184.58 | 49422.3 | 55170.06 | 58110.32 | 59625.59 | 61180.84 | 62043.46 | 62779.98 | 63496.93 | 64119.08 | 64773.64 | 65578.73 | 66390.18 | 67335.06 | 68864.34 | 70846.03 | 72624.98 | 74488.13 | 75943.99 | 76603.2 | 77132.55 | 78165.82 | 79473.34 | 80767.53 | 81998.96 | 83352.28 | 84304.36 | 85438.92 | 86199.19 | 86585.48 | 86906.66 | 87220.32 | 87632.01 | 88092.06 | 88358.98 | 88472.64 | 88495.17 | 88558.06 | 88576.08 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 88589.59 | 0% | 0% | 0% | 0% | 0% | 0.001863% | 0.009448% | 0.01791% | 0.06361% | 0.34% | 0.6327% | 1.013% | 1.488% | 2.042% | 2.641% | 3.241% | 3.841% | 4.486% | 5.166% | 5.849% | 6.533% | 7.221% | 7.909% | 8.62% | 9.461% | 10.69% | 11.98% | 13.27% | 14.59% | 15.93% | 17.27% | 18.61% | 19.95% | 21.3% | 22.65% | 24.01% | 25.42% | 26.84% | 28.26% | 28.48% | 28.65% | 28.69% | 28.73% | 28.97% | 30.08% | 32.17% | 33.9% | 35.55% | 37.29% | 39.09% | 41.05% | 43.95% | 45.97% | 48.11% | 50.02% | 52.13% | 55.79% | 62.28% | 65.59% | 67.31% | 69.06% | 70.03% | 70.87% | 71.68% | 72.38% | 73.12% | 74.03% | 74.94% | 76.01% | 77.73% | 79.97% | 81.98% | 84.08% | 85.73% | 86.47% | 87.07% | 88.23% | 89.71% | 91.17% | 92.56% | 94.09% | 95.16% | 96.44% | 97.3% | 97.74% | 98.1% | 98.45% | 98.92% | 99.44% | 99.74% | 99.87% | 99.89% | 99.96% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | Package 02-New Well # W028 (Bangestan) | 449 | 24-Jul-21 A | 2023-05-08 | 128827.09 | 7 | [5 empty] | 0.74 | 5.38 | 10.84 | 16.98 | 23.8 | 62.98 | 126.69 | 333.61 | 731.65 | 1129.9 | 1528.15 | 1927.06 | 2327.88 | 2730.08 | 3134.16 | 3539.66 | 3947.61 | 4457.15 | 5220.46 | 5986.16 | 6789.05 | 7643.56 | 8512.39 | 9387.47 | 10273.56 | 11304.11 | 12443.42 | 13585.64 | 14731.05 | 15877.98 | 17025.88 | 18178.06 | 19367.82 | 20566.37 | 20737.65 | 23971.86 | 25262.29 | 27131.13 | 31023.69 | 34063.72 | 36955.56 | 39680.22 | 44302.18 | 47861.95 | 50841.92 | 53340.67 | 56114.56 | 59135.21 | 62475.57 | 66436.05 | 71084.33 | 75257.89 | 81659.06 | 88379.52 | 91558.24 | 96015.55 | 97854.16 | 99058.33 | 100165.55 | 101251.29 | 102507.46 | 103718.33 | 104866.28 | 106119.41 | 108031.84 | 110435.7 | 112745.66 | 115039.88 | 116440.18 | 117145.53 | 117778.75 | 118671.38 | 119444.86 | 120993.24 | 121396.22 | 121771.3 | 122274.25 | 123320.93 | 124806.62 | 125991.25 | 126425.77 | 126842.73 | 127457.29 | 128036.1 | 128254.01 | 128545.05 | 128585.01 | 128622 | 128643.53 | 128665.07 | 128716.34 | 128788.13 | 128816.84 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 128827.09 | 0% | 0% | 0% | 0% | 0% | 0.0005744% | 0.004176% | 0.008414% | 0.01318% | 0.01847% | 0.04889% | 0.09834% | 0.259% | 0.5679% | 0.8771% | 1.186% | 1.496% | 1.807% | 2.119% | 2.433% | 2.748% | 3.064% | 3.46% | 4.052% | 4.647% | 5.27% | 5.933% | 6.608% | 7.287% | 7.975% | 8.775% | 9.659% | 10.55% | 11.43% | 12.33% | 13.22% | 14.11% | 15.03% | 15.96% | 16.1% | 18.61% | 19.61% | 21.06% | 24.08% | 26.44% | 28.69% | 30.8% | 34.39% | 37.15% | 39.47% | 41.4% | 43.56% | 45.9% | 48.5% | 51.57% | 55.18% | 58.42% | 63.39% | 68.6% | 71.07% | 74.53% | 75.96% | 76.89% | 77.75% | 78.59% | 79.57% | 80.51% | 81.4% | 82.37% | 83.86% | 85.72% | 87.52% | 89.3% | 90.38% | 90.93% | 91.42% | 92.12% | 92.72% | 93.92% | 94.23% | 94.52% | 94.91% | 95.73% | 96.88% | 97.8% | 98.14% | 98.46% | 98.94% | 99.39% | 99.56% | 99.78% | 99.81% | 99.84% | 99.86% | 99.87% | 99.91% | 99.97% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | Package 03-New Well # W046S (Bangestan) | 475 | 24-Jul-21 A | 2023-06-29 | 592707.12 | 8 | [5 empty] | 1.93 | 12.22 | 23.56 | 35.92 | 49.14 | 63.23 | 78.22 | 93.51 | 109.28 | 125.35 | 141.43 | 157.62 | 173.9 | 190.47 | 210.19 | 232.22 | 256.58 | 281.7 | 308.24 | 336.38 | 367.06 | 401.42 | 436.02 | 470.88 | 506.53 | 543.07 | 580.85 | 623.26 | 670.46 | 719.67 | 2937.85 | 5890.54 | 8846.35 | 11808.89 | 12234.83 | 17196.33 | 27152.39 | 32641.51 | 38131.53 | 43908.64 | 52109.05 | 63226.72 | 71962.83 | 80428.05 | 89041.17 | 98007.72 | 107629.22 | 118168.94 | 145471.2 | 205522.61 | 257588.94 | 301256.52 | 316728.62 | 327474.8 | 341271.67 | 350033.13 | 357749.3 | 365612.74 | 373411.18 | 381250.17 | 388780.93 | 397367.07 | 411922.51 | 436329.97 | 452231.29 | 462384.06 | 472944.51 | 483628.28 | 493048.03 | 500276.57 | 506759.98 | 513213.15 | 517551.81 | 520484.79 | 523173.38 | 526160.62 | 529431.73 | 533302.38 | 536413.99 | 539802.62 | 543045.96 | 545583.88 | 548043.14 | 551425.89 | 553983.17 | 555211.12 | 557976.43 | 563002.81 | 567916.32 | 576440.59 | 582434.31 | 584738.27 | 585213.15 | 586617.07 | 588488.49 | 590024.55 | 591750.57 | 592122.28 | 592480.39 | 592602.48 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 592707.12 | 0% | 0% | 0% | 0% | 0% | 0.0003256% | 0.002062% | 0.003975% | 0.00606% | 0.008291% | 0.01067% | 0.0132% | 0.01578% | 0.01844% | 0.02115% | 0.02386% | 0.02659% | 0.02934% | 0.03214% | 0.03546% | 0.03918% | 0.04329% | 0.04753% | 0.05201% | 0.05675% | 0.06193% | 0.06773% | 0.07356% | 0.07945% | 0.08546% | 0.09163% | 0.098% | 0.1052% | 0.1131% | 0.1214% | 0.4957% | 0.9938% | 1.493% | 1.992% | 2.064% | 2.901% | 4.581% | 5.507% | 6.433% | 7.408% | 8.792% | 10.67% | 12.14% | 13.57% | 15.02% | 16.54% | 18.16% | 19.94% | 24.54% | 34.68% | 43.46% | 50.83% | 53.44% | 55.25% | 57.58% | 59.06% | 60.36% | 61.69% | 63% | 64.32% | 65.59% | 67.04% | 69.5% | 73.62% | 76.3% | 78.01% | 79.79% | 81.6% | 83.19% | 84.41% | 85.5% | 86.59% | 87.32% | 87.81% | 88.27% | 88.77% | 89.32% | 89.98% | 90.5% | 91.07% | 91.62% | 92.05% | 92.46% | 93.04% | 93.47% | 93.67% | 94.14% | 94.99% | 95.82% | 97.26% | 98.27% | 98.66% | 98.74% | 98.97% | 99.29% | 99.55% | 99.84% | 99.9% | 99.96% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | Package 04-New Well # W035 (Bangestan) | 613.75 | 24-Jul-21 A | 2023-11-23 | 156733.57 | 9 | [5 empty] | 0.84 | 5.56 | 11.17 | 17.49 | 24.49 | 31.84 | 39.67 | 118.01 | 208.25 | 298.71 | 389.16 | 479.62 | 570.07 | 660.63 | 753 | 846.77 | 943 | 1349.33 | 1988.52 | 2628.88 | 3270.69 | 3914.91 | 4559.45 | 5204.29 | 5849.84 | 6495.97 | 7143.2 | 7794.07 | 8448.21 | 9103.36 | 9759.41 | 10419.77 | 11080.89 | 11744.67 | 11839.55 | 12371.17 | 13480.46 | 16199.57 | 17448.9 | 18768.36 | 19930.59 | 21088.88 | 22250.37 | 23521.54 | 24871.01 | 26383.34 | 28178.5 | 30319.09 | 32545.41 | 34430.73 | 36332.47 | 38261.62 | 40171.23 | 42108.65 | 44096.97 | 46022.19 | 48140.3 | 50967.46 | 53844.07 | 58244.54 | 67910.59 | 72281.81 | 74306.52 | 76903.82 | 84344.19 | 92901.44 | 100548.19 | 105917.34 | 113665.48 | 121124.8 | 124387.38 | 125719.19 | 126597.78 | 127358.67 | 128455.27 | 129807.53 | 131345 | 133431.54 | 135054.65 | 136331.86 | 137516.91 | 138643.9 | 140176.18 | 142072.84 | 143427.51 | 144072.72 | 145063.38 | 145913.19 | 146729.61 | 147495.51 | 148521.55 | 150052.99 | 150924.95 | 151527.52 | 151852.77 | 152016.75 | 152021.76 | 152026.77 | 152030.58 | 152033.48 | 152036.38 | 152039.27 | 152042.17 | 152359.19 | 153027.3 | 154246.69 | 155043.09 | 155361.9 | 155685.23 | 155789.98 | 155877.94 | 156138.84 | 156144.68 | 156260.73 | 156439.86 | 156471.01 | 156499.2 | 156525.49 | 156551.77 | 156669.73 | 156704.78 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 156733.57 | 0% | 0% | 0% | 0% | 0% | 0.0005359% | 0.003547% | 0.007127% | 0.01116% | 0.01563% | 0.02031% | 0.02531% | 0.07529% | 0.1329% | 0.1906% | 0.2483% | 0.306% | 0.3637% | 0.4215% | 0.4804% | 0.5403% | 0.6017% | 0.8609% | 1.269% | 1.677% | 2.087% | 2.498% | 2.909% | 3.32% | 3.732% | 4.145% | 4.558% | 4.973% | 5.39% | 5.808% | 6.227% | 6.648% | 7.07% | 7.493% | 7.554% | 7.893% | 8.601% | 10.34% | 11.13% | 11.97% | 12.72% | 13.46% | 14.2% | 15.01% | 15.87% | 16.83% | 17.98% | 19.34% | 20.76% | 21.97% | 23.18% | 24.41% | 25.63% | 26.87% | 28.13% | 29.36% | 30.71% | 32.52% | 34.35% | 37.16% | 43.33% | 46.12% | 47.41% | 49.07% | 53.81% | 59.27% | 64.15% | 67.58% | 72.52% | 77.28% | 79.36% | 80.21% | 80.77% | 81.26% | 81.96% | 82.82% | 83.8% | 85.13% | 86.17% | 86.98% | 87.74% | 88.46% | 89.44% | 90.65% | 91.51% | 91.92% | 92.55% | 93.1% | 93.62% | 94.11% | 94.76% | 95.74% | 96.29% | 96.68% | 96.89% | 96.99% | 96.99% | 97% | 97% | 97% | 97% | 97% | 97.01% | 97.21% | 97.64% | 98.41% | 98.92% | 99.12% | 99.33% | 99.4% | 99.45% | 99.62% | 99.62% | 99.7% | 99.81% | 99.83% | 99.85% | 99.87% | 99.88% | 99.96% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Package 05-New Well # W008N | 692.75 | 24-Jul-21 A | 2024-02-10 | 69431.14 | 10 | [5 empty] | 0.82 | 5.53 | 11.12 | 17.39 | 24.31 | 31.58 | 39.33 | 47.15 | 55.15 | 63.34 | 71.53 | 79.72 | 87.91 | 96.2 | 106.31 | 117.83 | 131.8 | 146.35 | 177.92 | 251.93 | 326.65 | 402.69 | 479.05 | 555.71 | 633.05 | 710.95 | 789.66 | 870.59 | 953.76 | 1037.91 | 1122.93 | 1212.24 | 1302.24 | 1394.71 | 1407.98 | 1533.65 | 1639.84 | 1801.62 | 1969.09 | 2139.3 | 2387.96 | 2978.98 | 3200.56 | 3465.53 | 3756.72 | 4108.16 | 4637.96 | 5204.35 | 5825.8 | 6307.57 | 6793.16 | 7300.27 | 7791.92 | 8290.63 | 8806.92 | 9297.31 | 9782.16 | 10273.41 | 10765.75 | 11270.7 | 11824.94 | 12428 | 13013.12 | 13679.22 | 14681.59 | 15790.71 | 16841.4 | 17884.02 | 18635.84 | 19256.19 | 20301.53 | 21530.96 | 22998.17 | 25770.82 | 28168.41 | 29497.22 | 30427.66 | 31420.34 | 32426.63 | 33224.81 | 34211.16 | 37336.49 | 39781.68 | 41978.47 | 44098.74 | 46894.84 | 49744.97 | 51819.74 | 53771.13 | 55996.09 | 57008.14 | 57200 | 57329.12 | 58752.28 | 60017.38 | 60334.14 | 60732.74 | 61200.17 | 61659.28 | 61976 | 62233.06 | 62335.94 | 62456.73 | 62879.71 | 63302.68 | 63725.65 | 64148.62 | 64572.43 | 64913.83 | 65300.17 | 65739.42 | 65941.07 | 66258.3 | 66743.73 | 67265.69 | 67580.81 | 68190.92 | 68322.09 | 68325.25 | 68417.11 | 68685.4 | 68848.66 | 69029.03 | 69069.01 | 69072.58 | 69243.11 | 69262.19 | 69280.73 | 69296.82 | 69312.92 | 69385.92 | 69407.38 | 69428.84 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 69431.14 | 0% | 0% | 0% | 0% | 0% | 0.001181% | 0.007965% | 0.01602% | 0.02505% | 0.03501% | 0.04548% | 0.05665% | 0.06791% | 0.07943% | 0.09123% | 0.103% | 0.1148% | 0.1266% | 0.1386% | 0.1531% | 0.1697% | 0.1898% | 0.2108% | 0.2563% | 0.3628% | 0.4705% | 0.58% | 0.69% | 0.8004% | 0.9118% | 1.024% | 1.137% | 1.254% | 1.374% | 1.495% | 1.617% | 1.746% | 1.876% | 2.009% | 2.028% | 2.209% | 2.362% | 2.595% | 2.836% | 3.081% | 3.439% | 4.291% | 4.61% | 4.991% | 5.411% | 5.917% | 6.68% | 7.496% | 8.391% | 9.085% | 9.784% | 10.51% | 11.22% | 11.94% | 12.68% | 13.39% | 14.09% | 14.8% | 15.51% | 16.23% | 17.03% | 17.9% | 18.74% | 19.7% | 21.15% | 22.74% | 24.26% | 25.76% | 26.84% | 27.73% | 29.24% | 31.01% | 33.12% | 37.12% | 40.57% | 42.48% | 43.82% | 45.25% | 46.7% | 47.85% | 49.27% | 53.77% | 57.3% | 60.46% | 63.51% | 67.54% | 71.65% | 74.63% | 77.45% | 80.65% | 82.11% | 82.38% | 82.57% | 84.62% | 86.44% | 86.9% | 87.47% | 88.15% | 88.81% | 89.26% | 89.63% | 89.78% | 89.95% | 90.56% | 91.17% | 91.78% | 92.39% | 93% | 93.49% | 94.05% | 94.68% | 94.97% | 95.43% | 96.13% | 96.88% | 97.34% | 98.21% | 98.4% | 98.41% | 98.54% | 98.93% | 99.16% | 99.42% | 99.48% | 99.48% | 99.73% | 99.76% | 99.78% | 99.81% | 99.83% | 99.93% | 99.97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Package 06-New Well # W007S/Manifold Extension (Bangestan) | 729 | 24-Jul-21 A | 2024-03-17 | 236214.84 | 11 | [5 empty] | 1.76 | 16.12 | 31.44 | 48.03 | 65.46 | 83.84 | 102.63 | 121.58 | 141.19 | 161.12 | 181.05 | 201.06 | 221.12 | 243.3 | 271.12 | 301.06 | 332.47 | 365.03 | 398.91 | 434.88 | 471.98 | 509.53 | 547.27 | 586.13 | 625.54 | 667.2 | 710.28 | 755.62 | 804 | 854.35 | 909.62 | 971.45 | 1047.12 | 1149.13 | 1195.15 | 1548.45 | 1788.63 | 2029.37 | 2273.02 | 2525.14 | 2991.54 | 3219.79 | 3569.24 | 4389.41 | 5278.79 | 6548.47 | 8253.62 | 11348.5 | 14006.03 | 16119.73 | 18194.34 | 20270.79 | 23003.97 | 27572.49 | 31959.22 | 36276.9 | 40441.45 | 44307.38 | 48179.7 | 51924.41 | 55764.4 | 59189.83 | 62983.79 | 67207.55 | 72415.08 | 78892.92 | 86109.89 | 94583.5 | 103085.3 | 111285.18 | 115576.66 | 121847.18 | 128136.76 | 134166.43 | 140903.76 | 151149.89 | 159410.27 | 164127.23 | 167404.6 | 170176.14 | 172923.82 | 175928.33 | 178916.12 | 181592.07 | 183034.93 | 185645.75 | 188075.27 | 190131.71 | 191171.7 | 192804.61 | 195090.98 | 197139.03 | 199055.65 | 201637.05 | 203619.67 | 204604.15 | 205878.72 | 207365.62 | 209393.52 | 211822.01 | 213930.92 | 215217.81 | 215487.61 | 215619.14 | 215725.39 | 215768.61 | 215800.62 | 215832.62 | 215864.63 | 215896.64 | 215928.64 | 215960.65 | 215992.66 | 216024.66 | 216058.36 | 216163.63 | 216301.57 | 216600.77 | 216797.46 | 216976.12 | 217992.12 | 222643.51 | 227205.46 | 229805.56 | 232770.27 | 235231.61 | 235410.59 | 235419.33 | 235623.42 | 235629.25 | 235902.75 | 235933.85 | 235964.95 | 235991.19 | 236017.43 | 236089.9 | 236169.86 | 236204.85 | 236214.84 | 236214.84 | 236214.84 | 236214.84 | 236214.84 | 236214.84 | 236214.84 | 236214.84 | 236214.84 | 236214.84 | 236214.84 | 236214.84 | 236214.84 | 236214.84 | 236214.84 | 0% | 0% | 0% | 0% | 0% | 0.0007451% | 0.006824% | 0.01331% | 0.02033% | 0.02771% | 0.03549% | 0.04345% | 0.05147% | 0.05977% | 0.06821% | 0.07665% | 0.08512% | 0.09361% | 0.103% | 0.1148% | 0.1275% | 0.1407% | 0.1545% | 0.1689% | 0.1841% | 0.1998% | 0.2157% | 0.2317% | 0.2481% | 0.2648% | 0.2825% | 0.3007% | 0.3199% | 0.3404% | 0.3617% | 0.3851% | 0.4113% | 0.4433% | 0.4865% | 0.506% | 0.6555% | 0.7572% | 0.8591% | 0.9623% | 1.069% | 1.266% | 1.363% | 1.511% | 1.858% | 2.235% | 2.772% | 3.494% | 4.804% | 5.929% | 6.824% | 7.702% | 8.582% | 9.739% | 11.67% | 13.53% | 15.36% | 17.12% | 18.76% | 20.4% | 21.98% | 23.61% | 25.06% | 26.66% | 28.45% | 30.66% | 33.4% | 36.45% | 40.04% | 43.64% | 47.11% | 48.93% | 51.58% | 54.25% | 56.8% | 59.65% | 63.99% | 67.49% | 69.48% | 70.87% | 72.04% | 73.21% | 74.48% | 75.74% | 76.88% | 77.49% | 78.59% | 79.62% | 80.49% | 80.93% | 81.62% | 82.59% | 83.46% | 84.27% | 85.36% | 86.2% | 86.62% | 87.16% | 87.79% | 88.65% | 89.67% | 90.57% | 91.11% | 91.23% | 91.28% | 91.33% | 91.34% | 91.36% | 91.37% | 91.38% | 91.4% | 91.41% | 91.43% | 91.44% | 91.45% | 91.47% | 91.51% | 91.57% | 91.7% | 91.78% | 91.86% | 92.29% | 94.25% | 96.19% | 97.29% | 98.54% | 99.58% | 99.66% | 99.66% | 99.75% | 99.75% | 99.87% | 99.88% | 99.89% | 99.91% | 99.92% | 99.95% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
12 | Package 07-Workover # 14 | 532 | 24-Jul-21 A | 2023-09-02 | 140256.49 | 12 | [5 empty] | 2.14 | 11.74 | 22.28 | 33.69 | 45.6 | 58.01 | 70.5 | 83.31 | 96.7 | 110.25 | 123.81 | 137.54 | 151.41 | 165.28 | 179.28 | 194.3 | 212.35 | 231.57 | 251.03 | 270.63 | 290.5 | 310.82 | 331.26 | 351.81 | 372.77 | 395.01 | 418.53 | 450.05 | 490.65 | 535.06 | 591.83 | 653.59 | 719.32 | 786.97 | 807.08 | 1070.73 | 1194.36 | 1320.34 | 1435.41 | 1544.17 | 1640.27 | 1688.69 | 2074.08 | 3300.49 | 5667.84 | 8785.19 | 12183.84 | 16734.88 | 24207.92 | 30730.65 | 41364.86 | 49366.8 | 53722.57 | 56841.42 | 59188.76 | 64312.16 | 69444.09 | 74796.67 | 79484.82 | 83780 | 87629.9 | 95431.74 | 100317.13 | 101592.95 | 103088.34 | 108572.05 | 114059.85 | 114476.71 | 115851.59 | 117898.46 | 119169.67 | 120752.98 | 121828.65 | 122710 | 124034.93 | 131140.07 | 134320.72 | 134394.49 | 134513.07 | 134989.14 | 135282.9 | 135283.75 | 135284.56 | 135332.48 | 135451.69 | 135627.23 | 135794.14 | 135961.04 | 136127.94 | 136294.84 | 136461.74 | 136878.99 | 137730.57 | 138384.55 | 138388.72 | 138392.89 | 139232.47 | 139673.12 | 139688.44 | 139764.45 | 139838.7 | 139842.83 | 140038.86 | 140060.86 | 140082.37 | 140100.93 | 140119.49 | 140203.46 | 140228.21 | 140252.96 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 140256.49 | 0% | 0% | 0% | 0% | 0% | 0.001526% | 0.00837% | 0.01589% | 0.02402% | 0.03251% | 0.04136% | 0.05027% | 0.0594% | 0.06895% | 0.07861% | 0.08827% | 0.09806% | 0.108% | 0.1178% | 0.1278% | 0.1385% | 0.1514% | 0.1651% | 0.179% | 0.193% | 0.2071% | 0.2216% | 0.2362% | 0.2508% | 0.2658% | 0.2816% | 0.2984% | 0.3209% | 0.3498% | 0.3815% | 0.422% | 0.466% | 0.5129% | 0.5611% | 0.5754% | 0.7634% | 0.8516% | 0.9414% | 1.023% | 1.101% | 1.169% | 1.204% | 1.479% | 2.353% | 4.041% | 6.264% | 8.687% | 11.93% | 17.26% | 21.91% | 29.49% | 35.2% | 38.3% | 40.53% | 42.2% | 45.85% | 49.51% | 53.33% | 56.67% | 59.73% | 62.48% | 68.04% | 71.52% | 72.43% | 73.5% | 77.41% | 81.32% | 81.62% | 82.6% | 84.06% | 84.97% | 86.09% | 86.86% | 87.49% | 88.43% | 93.5% | 95.77% | 95.82% | 95.91% | 96.24% | 96.45% | 96.45% | 96.46% | 96.49% | 96.57% | 96.7% | 96.82% | 96.94% | 97.06% | 97.18% | 97.29% | 97.59% | 98.2% | 98.67% | 98.67% | 98.67% | 99.27% | 99.58% | 99.59% | 99.65% | 99.7% | 99.71% | 99.84% | 99.86% | 99.88% | 99.89% | 99.9% | 99.96% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
13 | Package 08-Workover # 12 | 512.75 | 24-Jul-21 A | 2023-08-14 | 113892.3 | 13 | [5 empty] | 2.16 | 11.77 | 22.32 | 33.73 | 45.65 | 58.06 | 70.56 | 83.38 | 96.78 | 110.33 | 123.89 | 137.63 | 151.51 | 165.39 | 179.39 | 193.75 | 210.66 | 228.74 | 247.06 | 265.52 | 284.24 | 303.42 | 322.72 | 342.13 | 361.94 | 383.04 | 405.42 | 435.79 | 475.25 | 518.52 | 569.58 | 623.81 | 682 | 742.11 | 761.15 | 984.29 | 1077.58 | 1172.65 | 1268.63 | 1637.96 | 2952 | 5189.93 | 7065.59 | 8894.53 | 10742.62 | 12650.26 | 16195.94 | 20230.61 | 24054.72 | 29095.23 | 35573.44 | 43037.28 | 48230.1 | 52053.57 | 56701.86 | 60894.51 | 63376.86 | 64934.22 | 66221.69 | 67369.64 | 68703.1 | 71183.94 | 73194.66 | 73870.35 | 74906.06 | 75947.43 | 77039.69 | 77612.44 | 78059.33 | 78586.4 | 80582.48 | 85399.07 | 91909.99 | 96411.29 | 98140.46 | 99058.06 | 100149.19 | 101719.08 | 103829.02 | 106929.12 | 107267.53 | 107476.25 | 107686.03 | 107857.58 | 108003.72 | 108149.87 | 108296.01 | 108460.05 | 108841.81 | 111133.48 | 112582.64 | 112586.12 | 112589.6 | 112593.08 | 113217.63 | 113412.6 | 113417.81 | 113539.58 | 113543.05 | 113704.38 | 113722.91 | 113741.44 | 113757.38 | 113773.01 | 113795.53 | 113863.27 | 113884.11 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 0% | 0% | 0% | 0% | 0% | 0.001897% | 0.01033% | 0.0196% | 0.02962% | 0.04008% | 0.05098% | 0.06195% | 0.07321% | 0.08498% | 0.09687% | 0.1088% | 0.1208% | 0.133% | 0.1452% | 0.1575% | 0.1701% | 0.185% | 0.2008% | 0.2169% | 0.2331% | 0.2496% | 0.2664% | 0.2834% | 0.3004% | 0.3178% | 0.3363% | 0.356% | 0.3826% | 0.4173% | 0.4553% | 0.5001% | 0.5477% | 0.5988% | 0.6516% | 0.6683% | 0.8642% | 0.9461% | 1.03% | 1.114% | 1.438% | 2.592% | 4.557% | 6.204% | 7.81% | 9.432% | 11.11% | 14.22% | 17.76% | 21.12% | 25.55% | 31.23% | 37.79% | 42.35% | 45.7% | 49.79% | 53.47% | 55.65% | 57.01% | 58.14% | 59.15% | 60.32% | 62.5% | 64.27% | 64.86% | 65.77% | 66.68% | 67.64% | 68.15% | 68.54% | 69% | 70.75% | 74.98% | 80.7% | 84.65% | 86.17% | 86.98% | 87.93% | 89.31% | 91.16% | 93.89% | 94.18% | 94.37% | 94.55% | 94.7% | 94.83% | 94.96% | 95.09% | 95.23% | 95.57% | 97.58% | 98.85% | 98.85% | 98.86% | 98.86% | 99.41% | 99.58% | 99.58% | 99.69% | 99.69% | 99.84% | 99.85% | 99.87% | 99.88% | 99.9% | 99.92% | 99.97% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
14 | Package 09-Workover # 15 | 499 | 24-Jul-21 A | 2023-07-31 | 170781.35 | 14 | [5 empty] | 2.16 | 11.77 | 22.32 | 33.73 | 45.65 | 58.06 | 70.56 | 83.38 | 96.78 | 110.33 | 123.89 | 137.63 | 151.51 | 165.39 | 179.39 | 193.48 | 209.77 | 227.22 | 244.91 | 262.74 | 280.84 | 299.39 | 318.06 | 336.85 | 356.03 | 376.5 | 398.26 | 428 | 466.83 | 509.48 | 559.91 | 613.51 | 671.08 | 730.57 | 749.51 | 887.95 | 935 | 982.7 | 1030.4 | 1078.13 | 1168.27 | 1273.52 | 1373.25 | 1599.21 | 2261.8 | 3824.2 | 5892.23 | 9067.79 | 12241.26 | 15176.42 | 18151.05 | 21275.61 | 24688.59 | 28513.53 | 33217.88 | 37339.54 | 40665.9 | 45251.33 | 52158.56 | 59776.3 | 67245.86 | 71594.56 | 74481.35 | 77438.41 | 82985.62 | 86661.06 | 91942.65 | 96091.53 | 100531.55 | 104254.99 | 108059.45 | 116339.8 | 121613.12 | 122396.05 | 122901.9 | 123432.57 | 124146.94 | 124863.88 | 133459.95 | 142722.2 | 149526.14 | 151716.42 | 155378.28 | 156931.1 | 157391.3 | 159266.87 | 160238.74 | 161765.07 | 162520.74 | 163001.42 | 164418.58 | 169119.26 | 169687.49 | 170083.94 | 170091.52 | 170268.57 | 170273.62 | 170507.29 | 170534.21 | 170561.14 | 170584.46 | 170607.17 | 170629.89 | 170738.07 | 170768.37 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 0% | 0% | 0% | 0% | 0% | 0.001265% | 0.006892% | 0.01307% | 0.01975% | 0.02673% | 0.034% | 0.04132% | 0.04882% | 0.05667% | 0.0646% | 0.07254% | 0.08059% | 0.08872% | 0.09684% | 0.105% | 0.1133% | 0.1228% | 0.133% | 0.1434% | 0.1538% | 0.1644% | 0.1753% | 0.1862% | 0.1972% | 0.2085% | 0.2205% | 0.2332% | 0.2506% | 0.2733% | 0.2983% | 0.3279% | 0.3592% | 0.3929% | 0.4278% | 0.4389% | 0.5199% | 0.5475% | 0.5754% | 0.6033% | 0.6313% | 0.6841% | 0.7457% | 0.8041% | 0.9364% | 1.324% | 2.239% | 3.45% | 5.31% | 7.168% | 8.886% | 10.63% | 12.46% | 14.46% | 16.7% | 19.45% | 21.86% | 23.81% | 26.5% | 30.54% | 35% | 39.38% | 41.92% | 43.61% | 45.34% | 48.59% | 50.74% | 53.84% | 56.27% | 58.87% | 61.05% | 63.27% | 68.12% | 71.21% | 71.67% | 71.96% | 72.28% | 72.69% | 73.11% | 78.15% | 83.57% | 87.55% | 88.84% | 90.98% | 91.89% | 92.16% | 93.26% | 93.83% | 94.72% | 95.16% | 95.44% | 96.27% | 99.03% | 99.36% | 99.59% | 99.6% | 99.7% | 99.7% | 99.84% | 99.86% | 99.87% | 99.88% | 99.9% | 99.91% | 99.97% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | Package 10-Workover # 05 | 551.5 | 24-Jul-21 A | 2023-09-22 | 121007.64 | 15 | [5 empty] | 2.16 | 11.77 | 22.32 | 33.73 | 45.65 | 58.06 | 70.56 | 83.38 | 96.78 | 110.33 | 123.89 | 137.63 | 151.51 | 165.39 | 179.39 | 193.75 | 210.66 | 228.74 | 247.06 | 265.52 | 284.24 | 303.42 | 322.72 | 342.13 | 361.94 | 383.04 | 405.42 | 435.79 | 475.25 | 518.52 | 569.58 | 623.81 | 682 | 742.11 | 761.15 | 972.29 | 1065.11 | 1158.79 | 1252.46 | 1354.1 | 1432.19 | 1462.74 | 1498.62 | 1538.61 | 1613.48 | 1739.05 | 2020.55 | 2525.65 | 3542.85 | 4692.64 | 6807.32 | 8383.46 | 9813.23 | 11300.22 | 12872.87 | 14568.27 | 16604.16 | 19240.33 | 20959.3 | 22629.43 | 25708.22 | 27992.18 | 30331.98 | 33085.18 | 36250.88 | 39522.82 | 42139.38 | 44840.93 | 48334.91 | 52247.52 | 59834.92 | 63635.88 | 65946.19 | 68852.89 | 71349.31 | 73786.35 | 76896.73 | 83617.47 | 85104.65 | 85506.06 | 86085.67 | 87111.58 | 88522.8 | 89580.34 | 90145.25 | 90409.77 | 92028.49 | 95772.49 | 101005.33 | 106559.6 | 109883.67 | 111454.99 | 112256.15 | 113805.38 | 114644.55 | 115432.19 | 118123.58 | 119201.57 | 119344.01 | 119936.91 | 120119.39 | 120289.3 | 120583.76 | 120661.71 | 120665.13 | 120832.39 | 120850.63 | 120867.65 | 120883.04 | 120898.43 | 120968.06 | 120988.58 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 0% | 0% | 0% | 0% | 0% | 0.001785% | 0.009727% | 0.01845% | 0.02787% | 0.03772% | 0.04798% | 0.05831% | 0.0689% | 0.07998% | 0.09118% | 0.1024% | 0.1137% | 0.1252% | 0.1367% | 0.1482% | 0.1601% | 0.1741% | 0.189% | 0.2042% | 0.2194% | 0.2349% | 0.2507% | 0.2667% | 0.2827% | 0.2991% | 0.3165% | 0.335% | 0.3601% | 0.3927% | 0.4285% | 0.4707% | 0.5155% | 0.5636% | 0.6133% | 0.629% | 0.8035% | 0.8802% | 0.9576% | 1.035% | 1.119% | 1.184% | 1.209% | 1.238% | 1.271% | 1.333% | 1.437% | 1.67% | 2.087% | 2.928% | 3.878% | 5.626% | 6.928% | 8.11% | 9.338% | 10.64% | 12.04% | 13.72% | 15.9% | 17.32% | 18.7% | 21.25% | 23.13% | 25.07% | 27.34% | 29.96% | 32.66% | 34.82% | 37.06% | 39.94% | 43.18% | 49.45% | 52.59% | 54.5% | 56.9% | 58.96% | 60.98% | 63.55% | 69.1% | 70.33% | 70.66% | 71.14% | 71.99% | 73.15% | 74.03% | 74.5% | 74.71% | 76.05% | 79.15% | 83.47% | 88.06% | 90.81% | 92.11% | 92.77% | 94.05% | 94.74% | 95.39% | 97.62% | 98.51% | 98.63% | 99.12% | 99.27% | 99.41% | 99.65% | 99.71% | 99.72% | 99.86% | 99.87% | 99.88% | 99.9% | 99.91% | 99.97% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
16 | SURFACE DEVELOPMENT | 825 | 24-Jul-21 A | 2024-06-21 | 7649126.04 | 16 | [5 empty] | 43.87 | 466.52 | 898.63 | 1360.24 | 1840.94 | 2357.27 | 2896.23 | 3479.68 | 4079.55 | 4728.78 | 5388.44 | 6061.98 | 6775.12 | 7521.89 | 8278.6 | 9071.57 | 9912.04 | 10809.63 | 11774.89 | 12860.88 | 14161.83 | 15618.11 | 17137.82 | 18725.74 | 20344 | 22032.05 | 23777.17 | 25778.57 | 28025.98 | 30449.19 | 33080.46 | 35775.02 | 38737.18 | 42002.75 | 43695.5 | 55415.84 | 60660.37 | 65907.47 | 70916.65 | 75780.69 | 79629.36 | 83027.98 | 93598.26 | 104579.27 | 115399.27 | 126203.08 | 137239.5 | 147859.41 | 160095.33 | 178334.15 | 205232.18 | 239111.92 | 270701.78 | 303109.15 | 336227.41 | 373135.28 | 413088.61 | 458193.21 | 514545.21 | 575379.64 | 640003.2 | 707617.67 | 786535.69 | 872212.31 | 959729.54 | 1059187.15 | 1161707.73 | 1265053.59 | 1370294.96 | 1480474.12 | 1590886.36 | 1702695.93 | 1813791.38 | 1926552.72 | 2042232.49 | 2161039.07 | 2275169.94 | 2394093.49 | 2511195.05 | 2626514.57 | 2751806.31 | 2877698.06 | 2995701.59 | 3113962.3 | 3232972.12 | 3359702.79 | 3520389.71 | 3689942.67 | 3832696.6 | 3972845.87 | 4105089.08 | 4235738.27 | 4355800.13 | 4467934.92 | 4582224.96 | 4690159.3 | 4798708.01 | 4901201.75 | 5003751.02 | 5111676.19 | 5210376.82 | 5313289.11 | 5422130.68 | 5507016.26 | 5587245.19 | 5669641.22 | 5732656.83 | 5795067.36 | 5858670.01 | 5926683.13 | 6002805.17 | 6082585.03 | 6217254.91 | 6300677.11 | 6384923.81 | 6442874.38 | 6495216.6 | 6572264.12 | 6626482.13 | 6668951.92 | 6741835.54 | 6807347.7 | 6849733.35 | 6888819.19 | 7026356.19 | 7095336.83 | 7114423.55 | 7129531.7 | 7140966.39 | 7306174.53 | 7334370.41 | 7361224.77 | 7386742.57 | 7411257.94 | 7435773.31 | 7457721.99 | 7478643.99 | 7499565.99 | 7517339.72 | 7531727.52 | 7539966.96 | 7548126.71 | 7552636.88 | 7556558.57 | 7560103.45 | 7564229.46 | 7571679.94 | 7585986.71 | 7612701.03 | 7633238.32 | 7644362.33 | 7649126.04 | 7649126.04 | 0% | 0% | 0% | 0% | 0% | 0.0005735% | 0.006099% | 0.01175% | 0.01778% | 0.02407% | 0.03082% | 0.03786% | 0.04549% | 0.05333% | 0.06182% | 0.07045% | 0.07925% | 0.08857% | 0.09834% | 0.1082% | 0.1186% | 0.1296% | 0.1413% | 0.1539% | 0.1681% | 0.1851% | 0.2042% | 0.224% | 0.2448% | 0.266% | 0.288% | 0.3108% | 0.337% | 0.3664% | 0.3981% | 0.4325% | 0.4677% | 0.5064% | 0.5491% | 0.5712% | 0.7245% | 0.793% | 0.8616% | 0.9271% | 0.9907% | 1.041% | 1.085% | 1.224% | 1.367% | 1.509% | 1.65% | 1.794% | 1.933% | 2.093% | 2.331% | 2.683% | 3.126% | 3.539% | 3.963% | 4.396% | 4.878% | 5.4% | 5.99% | 6.727% | 7.522% | 8.367% | 9.251% | 10.28% | 11.4% | 12.55% | 13.85% | 15.19% | 16.54% | 17.91% | 19.35% | 20.8% | 22.26% | 23.71% | 25.19% | 26.7% | 28.25% | 29.74% | 31.3% | 32.83% | 34.34% | 35.98% | 37.62% | 39.16% | 40.71% | 42.27% | 43.92% | 46.02% | 48.24% | 50.11% | 51.94% | 53.67% | 55.38% | 56.95% | 58.41% | 59.91% | 61.32% | 62.74% | 64.08% | 65.42% | 66.83% | 68.12% | 69.46% | 70.89% | 72% | 73.04% | 74.12% | 74.95% | 75.76% | 76.59% | 77.48% | 78.48% | 79.52% | 81.28% | 82.37% | 83.47% | 84.23% | 84.91% | 85.92% | 86.63% | 87.19% | 88.14% | 89% | 89.55% | 90.06% | 91.86% | 92.76% | 93.01% | 93.21% | 93.36% | 95.52% | 95.89% | 96.24% | 96.57% | 96.89% | 97.21% | 97.5% | 97.77% | 98.04% | 98.28% | 98.47% | 98.57% | 98.68% | 98.74% | 98.79% | 98.84% | 98.89% | 98.99% | 99.17% | 99.52% | 99.79% | 99.94% | 100% | 100%
17 | Package 11- EPC Pipeline 8" & 4" | 625 | 24-Jul-21 A | 2023-12-04 | 1535354.68 | 17 | [5 empty] | 16.83 | 98.72 | 186.41 | 281.03 | 378.89 | 490.03 | 610.85 | 732.35 | 856.99 | 982.15 | 1107.3 | 1232.46 | 1357.61 | 1487.27 | 1618.72 | 1750.17 | 1897.48 | 2065.25 | 2233.4 | 2403.46 | 2652.85 | 2918.61 | 3189.32 | 3468.75 | 3750.64 | 4033.43 | 4324.05 | 4667.68 | 5061.81 | 5472.67 | 5947.76 | 6424.1 | 6901.56 | 7382.83 | 7451.67 | 9917.69 | 10935.48 | 11953.28 | 12971.07 | 14077.18 | 15011.29 | 15635.37 | 16275.93 | 16945.92 | 17469.73 | 17917.79 | 18504.77 | 18938.37 | 19438.8 | 19920.64 | 20637.02 | 21370.25 | 22147.82 | 23034.97 | 24145.22 | 25733.47 | 26930.24 | 27975.79 | 36321.9 | 45054.79 | 56963.63 | 69147.01 | 87732.04 | 109783.04 | 132607.21 | 167616.51 | 204283.42 | 240637.19 | 277127.29 | 313720.38 | 350537.15 | 387369.6 | 424552.04 | 462712.53 | 501108.19 | 538606.21 | 573923.37 | 610390.67 | 647816.84 | 685382.69 | 733488.48 | 781391.46 | 826123.43 | 870723.76 | 917034.87 | 965535.14 | 1040529.63 | 1119763.4 | 1144700.52 | 1182123.54 | 1198943.58 | 1211003.04 | 1224009.68 | 1242969.57 | 1261313.39 | 1281653.61 | 1301158.45 | 1321458.2 | 1342863.09 | 1363125.76 | 1378350.92 | 1397647.1 | 1431408.69 | 1447438.82 | 1462688.48 | 1475438.25 | 1482335.21 | 1487110.14 | 1491885.06 | 1496719.92 | 1501469.8 | 1506219.69 | 1511483.82 | 1515849.43 | 1517386.38 | 1518364.23 | 1519142.81 | 1522028.17 | 1527017.37 | 1530097.26 | 1532110.95 | 1533892.66 | 1535091.52 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 0% | 0% | 0% | 0% | 0% | 0.001096% | 0.00643% | 0.01214% | 0.0183% | 0.02468% | 0.03192% | 0.03979% | 0.0477% | 0.05582% | 0.06397% | 0.07212% | 0.08027% | 0.08842% | 0.09687% | 0.1054% | 0.114% | 0.1236% | 0.1345% | 0.1455% | 0.1565% | 0.1728% | 0.1901% | 0.2077% | 0.2259% | 0.2443% | 0.2627% | 0.2816% | 0.304% | 0.3297% | 0.3564% | 0.3874% | 0.4184% | 0.4495% | 0.4809% | 0.4853% | 0.646% | 0.7122% | 0.7785% | 0.8448% | 0.9169% | 0.9777% | 1.018% | 1.06% | 1.104% | 1.138% | 1.167% | 1.205% | 1.233% | 1.266% | 1.297% | 1.344% | 1.392% | 1.443% | 1.5% | 1.573% | 1.676% | 1.754% | 1.822% | 2.366% | 2.934% | 3.71% | 4.504% | 5.714% | 7.15% | 8.637% | 10.92% | 13.31% | 15.67% | 18.05% | 20.43% | 22.83% | 25.23% | 27.65% | 30.14% | 32.64% | 35.08% | 37.38% | 39.76% | 42.19% | 44.64% | 47.77% | 50.89% | 53.81% | 56.71% | 59.73% | 62.89% | 67.77% | 72.93% | 74.56% | 76.99% | 78.09% | 78.87% | 79.72% | 80.96% | 82.15% | 83.48% | 84.75% | 86.07% | 87.46% | 88.78% | 89.77% | 91.03% | 93.23% | 94.27% | 95.27% | 96.1% | 96.55% | 96.86% | 97.17% | 97.48% | 97.79% | 98.1% | 98.45% | 98.73% | 98.83% | 98.89% | 98.94% | 99.13% | 99.46% | 99.66% | 99.79% | 99.9% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
18 | Package 12- EPC # Compressor Station | 825 | 24-Jul-21 A | 2024-06-21 | 6113771.36 | 18 | [5 empty] | 27.04 | 367.79 | 712.23 | 1079.22 | 1462.04 | 1867.24 | 2285.37 | 2747.33 | 3222.56 | 3746.63 | 4281.14 | 4829.52 | 5417.51 | 6034.62 | 6659.88 | 7321.39 | 8014.57 | 8744.38 | 9541.49 | 10457.42 | 11508.99 | 12699.49 | 13948.5 | 15256.99 | 16593.36 | 17998.63 | 19453.12 | 21110.89 | 22964.16 | 24976.52 | 27132.7 | 29350.92 | 31835.62 | 34619.92 | 36243.83 | 45498.15 | 49724.88 | 53954.19 | 57945.57 | 61703.51 | 64618.07 | 67392.61 | 77322.33 | 87633.35 | 97929.54 | 108285.29 | 118734.73 | 128921.03 | 140656.52 | 158413.51 | 184595.16 | 217741.67 | 248553.96 | 280074.18 | 312082.2 | 347401.8 | 386158.37 | 430217.42 | 478223.31 | 530324.85 | 583039.58 | 638470.67 | 698803.65 | 762429.27 | 827122.33 | 891570.64 | 957424.32 | 1024416.39 | 1093167.67 | 1166753.73 | 1240349.21 | 1315326.33 | 1389239.34 | 1463840.19 | 1541124.3 | 1622432.86 | 1701246.57 | 1783702.82 | 1863378.21 | 1941131.87 | 2018317.83 | 2096306.61 | 2169578.16 | 2243238.54 | 2315937.24 | 2394167.65 | 2479860.08 | 2570179.27 | 2687996.08 | 2790722.33 | 2906145.5 | 3024735.23 | 3131790.45 | 3224965.36 | 3320911.57 | 3408505.69 | 3497549.55 | 3579743.55 | 3660887.93 | 3748550.43 | 3832025.9 | 3915642.01 | 3990721.99 | 4059577.44 | 4124556.72 | 4194202.97 | 4250321.62 | 4307957.22 | 4366784.95 | 4429963.21 | 4501335.37 | 4576365.34 | 4705771.1 | 4784827.68 | 4867537.43 | 4924510.16 | 4976073.78 | 5050235.95 | 5099464.76 | 5138854.66 | 5209724.59 | 5273455.03 | 5314641.83 | 5353464.51 | 5491001.51 | 5559982.15 | 5579068.86 | 5594177.02 | 5605611.71 | 5770819.85 | 5799015.73 | 5825870.09 | 5851387.89 | 5875903.26 | 5900418.63 | 5922367.31 | 5943289.31 | 5964211.31 | 5981985.04 | 5996372.84 | 6004612.27 | 6012772.03 | 6017282.2 | 6021203.88 | 6024748.77 | 6028874.78 | 6036325.26 | 6050632.03 | 6077346.35 | 6097883.64 | 6109007.65 | 6113771.36 | 6113771.36 | 0% | 0% | 0% | 0% | 0% | 0.0004423% | 0.006016% | 0.01165% | 0.01765% | 0.02391% | 0.03054% | 0.03738% | 0.04494% | 0.05271% | 0.06128% | 0.07002% | 0.07899% | 0.08861% | 0.09871% | 0.1089% | 0.1198% | 0.1311% | 0.143% | 0.1561% | 0.171% | 0.1882% | 0.2077% | 0.2281% | 0.2496% | 0.2714% | 0.2944% | 0.3182% | 0.3453% | 0.3756% | 0.4085% | 0.4438% | 0.4801% | 0.5207% | 0.5663% | 0.5928% | 0.7442% | 0.8133% | 0.8825% | 0.9478% | 1.009% | 1.057% | 1.102% | 1.265% | 1.433% | 1.602% | 1.771% | 1.942% | 2.109% | 2.301% | 2.591% | 3.019% | 3.561% | 4.065% | 4.581% | 5.105% | 5.682% | 6.316% | 7.037% | 7.822% | 8.674% | 9.536% | 10.44% | 11.43% | 12.47% | 13.53% | 14.58% | 15.66% | 16.76% | 17.88% | 19.08% | 20.29% | 21.51% | 22.72% | 23.94% | 25.21% | 26.54% | 27.83% | 29.18% | 30.48% | 31.75% | 33.01% | 34.29% | 35.49% | 36.69% | 37.88% | 39.16% | 40.56% | 42.04% | 43.97% | 45.65% | 47.53% | 49.47% | 51.23% | 52.75% | 54.32% | 55.75% | 57.21% | 58.55% | 59.88% | 61.31% | 62.68% | 64.05% | 65.27% | 66.4% | 67.46% | 68.6% | 69.52% | 70.46% | 71.43% | 72.46% | 73.63% | 74.85% | 76.97% | 78.26% | 79.62% | 80.55% | 81.39% | 82.6% | 83.41% | 84.05% | 85.21% | 86.26% | 86.93% | 87.56% | 89.81% | 90.94% | 91.25% | 91.5% | 91.69% | 94.39% | 94.85% | 95.29% | 95.71% | 96.11% | 96.51% | 96.87% | 97.21% | 97.55% | 97.84% | 98.08% | 98.21% | 98.35% | 98.42% | 98.49% | 98.54% | 98.61% | 98.73% | 98.97% | 99.4% | 99.74% | 99.92% | 100% | 100%
EPCC | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158
| Activity ID | Original Duration | Start | Finish | Budgeted Labor Units | Spreadsheet Field | [158 empty] | 2021-06-19 | 2021-06-26 | 2021-07-03 | 2021-07-10 | 2021-07-17 | 2021-07-24 | 2021-07-31 | 2021-08-07 | 2021-08-14 | 2021-08-21 | 2021-08-28 | 2021-09-04 | 2021-09-11 | 2021-09-18 | 2021-09-25 | 2021-10-02 | 2021-10-09 | 2021-10-16 | 2021-10-23 | 2021-10-30 | 2021-11-06 | 2021-11-13 | 2021-11-20 | 2021-11-27 | 2021-12-04 | 2021-12-11 | 2021-12-18 | 2021-12-25 | 2022-01-01 | 2022-01-08 | 2022-01-15 | 2022-01-22 | 2022-01-29 | 2022-02-05 | 2022-02-12 | 2022-02-19 | 2022-02-26 | 2022-03-05 | 2022-03-12 | 2022-03-19 | 2022-03-26 | 2022-04-02 | 2022-04-09 | 2022-04-16 | 2022-04-23 | 2022-04-30 | 2022-05-07 | 2022-05-14 | 2022-05-21 | 2022-05-28 | 2022-06-04 | 2022-06-11 | 2022-06-18 | 2022-06-25 | 2022-07-02 | 2022-07-09 | 2022-07-16 | 2022-07-23 | 2022-07-30 | 2022-08-06 | 2022-08-13 | 2022-08-20 | 2022-08-27 | 2022-09-03 | 2022-09-10 | 2022-09-17 | 2022-09-24 | 2022-10-01 | 2022-10-08 | 2022-10-15 | 2022-10-22 | 2022-10-29 | 2022-11-05 | 2022-11-12 | 2022-11-19 | 2022-11-26 | 2022-12-03 | 2022-12-10 | 2022-12-17 | 2022-12-24 | 2022-12-31 | 2023-01-07 | 2023-01-14 | 2023-01-21 | 2023-01-28 | 2023-02-04 | 2023-02-11 | 2023-02-18 | 2023-02-25 | 2023-03-04 | 2023-03-11 | 2023-03-18 | 2023-03-25 | 2023-04-01 | 2023-04-08 | 2023-04-15 | 2023-04-22 | 2023-04-29 | 2023-05-06 | 2023-05-13 | 2023-05-20 | 2023-05-27 | 2023-06-03 | 2023-06-10 | 2023-06-17 | 2023-06-24 | 2023-07-01 | 2023-07-08 | 2023-07-15 | 2023-07-22 | 2023-07-29 | 2023-08-05 | 2023-08-12 | 2023-08-19 | 2023-08-26 | 2023-09-02 | 2023-09-09 | 2023-09-16 | 2023-09-23 | 2023-09-30 | 2023-10-07 | 2023-10-14 | 2023-10-21 | 2023-10-28 | 2023-11-04 | 2023-11-11 | 2023-11-18 | 2023-11-25 | 2023-12-02 | 2023-12-09 | 2023-12-16 | 2023-12-23 | 2023-12-30 | 2024-01-06 | 2024-01-13 | 2024-01-20 | 2024-01-27 | 2024-02-03 | 2024-02-10 | 2024-02-17 | 2024-02-24 | 2024-03-02 | 2024-03-09 | 2024-03-16 | 2024-03-23 | 2024-03-30 | 2024-04-06 | 2024-04-13 | 2024-04-20 | 2024-04-27 | 2024-05-04 | 2024-05-11 | 2024-05-18 | 2024-05-25 | 2024-06-01 | 2024-06-08 | 2024-06-15 | 2024-06-22 | time axis 2021-06-19 to 2024-06-22
22 | General | 720 | 23-Jun-21 A | 2024-03-08 | 532432.82 | 22 | 20.33 | 70.22 | 130.5 | 257.25 | 393.49 | 2111.44 | 4093.02 | 6075.97 | 8060.77 | 10045.56 | 12030.35 | 14015.14 | 16003.67 | 17992.2 | 19980.74 | 21969.27 | 23960.97 | 25953.95 | 27946.92 | 29939.9 | 31934.44 | 33954.94 | 36073.13 | 38718.9 | 41393.33 | 44113.17 | 46833 | 49563.54 | 52302.09 | 55046.62 | 57795.63 | 61131.99 | 65936.72 | 74659.23 | 84055.63 | 93488.96 | 102936.73 | 112384.5 | 121919.3 | 133590.53 | 229683.85 | 233885.71 | 262060.28 | 265519.93 | 268920.85 | 287393.85 | 294244.91 | 301335.78 | 308407.04 | 315593.59 | 340509.38 | 353296.06 | 362162.51 | 374298.08 | 380340.56 | 398924.9 | 402386.05 | 405252.4 | 408411.83 | 411113.87 | 413509.42 | 415751.48 | 417717.23 | 419784.52 | 455354.81 | 456740.26 | 457814.48 | 458888.18 | 460063.4 | 461137.1 | 462192.53 | 463214.51 | 464331.22 | 465346.4 | 466389.43 | 467469.59 | 468651.27 | 469731.43 | 470811.59 | 471891.74 | 473073.43 | 474153.59 | 475233.74 | 476313.9 | 477394.06 | 478575.74 | 479655.9 | 480736.06 | 481816.22 | 482997.9 | 484382.64 | 485462.8 | 486542.96 | 487724.64 | 488804.8 | 489884.96 | 490965.12 | 492045.27 | 493226.96 | 494307.12 | 495387.27 | 496467.43 | 497649.12 | 498729.27 | 499809.43 | 500889.59 | 501969.74 | 503049.9 | 504130.06 | 505210.22 | 506290.37 | 507370.53 | 508450.69 | 509530.85 | 510611 | 511691.16 | 513075.9 | 514156.06 | 515236.22 | 516316.37 | 517396.53 | 518339.81 | 519228.34 | 520116.86 | 521004.54 | 521853.19 | 522700.44 | 523547.68 | 524385.82 | 525172.87 | 525956.52 | 526740.16 | 527523.81 | 528231.72 | 529046.56 | 529708.56 | 530320.91 | 530924.42 | 531527.93 | 531890.28 | 532237.05 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 532432.82 | 0.003818% | 0.01319% | 0.02451% | 0.04832% | 0.0739% | 0.3966% | 0.7687% | 1.141% | 1.514% | 1.887% | 2.26% | 2.632% | 3.006% | 3.379% | 3.753% | 4.126% | 4.5% | 4.875% | 5.249% | 5.623% | 5.998% | 6.377% | 6.775% | 7.272% | 7.774% | 8.285% | 8.796% | 9.309% | 9.823% | 10.34% | 10.86% | 11.48% | 12.38% | 14.02% | 15.79% | 17.56% | 19.33% | 21.11% | 22.9% | 25.09% | 43.14% | 43.93% | 49.22% | 49.87% | 50.51% | 53.98% | 55.26% | 56.6% | 57.92% | 59.27% | 63.95% | 66.36% | 68.02% | 70.3% | 71.43% | 74.92% | 75.57% | 76.11% | 76.71% | 77.21% | 77.66% | 78.09% | 78.45% | 78.84% | 85.52% | 85.78% | 85.99% | 86.19% | 86.41% | 86.61% | 86.81% | 87% | 87.21% | 87.4% | 87.6% | 87.8% | 88.02% | 88.22% | 88.43% | 88.63% | 88.85% | 89.05% | 89.26% | 89.46% | 89.66% | 89.88% | 90.09% | 90.29% | 90.49% | 90.72% | 90.98% | 91.18% | 91.38% | 91.6% | 91.81% | 92.01% | 92.21% | 92.41% | 92.64% | 92.84% | 93.04% | 93.25% | 93.47% | 93.67% | 93.87% | 94.08% | 94.28% | 94.48% | 94.68% | 94.89% | 95.09% | 95.29% | 95.5% | 95.7% | 95.9% | 96.1% | 96.36% | 96.57% | 96.77% | 96.97% | 97.18% | 97.35% | 97.52% | 97.69% | 97.85% | 98.01% | 98.17% | 98.33% | 98.49% | 98.64% | 98.78% | 98.93% | 99.08% | 99.21% | 99.36% | 99.49% | 99.6% | 99.72% | 99.83% | 99.9% | 99.96% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
23 | Engineering | 784 | 24-Jul-21 A | 2024-05-11 | 272905.62 | 23 | [5 empty] | 60.22 | 566.76 | 1091.87 | 1654.98 | 2244.08 | 2874.04 | 3530.33 | 4233.18 | 4956.76 | 5731.8 | 6517.27 | 7318.18 | 8161.32 | 9042.21 | 9950.87 | 10907.69 | 11936.28 | 13030.59 | 14199.41 | 15500.35 | 17024.94 | 18721.09 | 20484.45 | 22318.98 | 24189.61 | 26140.56 | 28160.13 | 30486.85 | 33115.59 | 35944.54 | 39032.68 | 42266.45 | 45803.78 | 49702.9 | 51579.31 | 65209.64 | 71347.83 | 77529.34 | 83532.24 | 89388.16 | 93933.72 | 96682.7 | 100502.42 | 104783.54 | 108889.77 | 112797.67 | 116826.77 | 120621.24 | 124517.99 | 128582.78 | 133396.73 | 138611.74 | 143677.16 | 148641.94 | 153433.04 | 159129.8 | 164320.25 | 167380 | 168922.16 | 170186.56 | 172078.58 | 174762.92 | 178280.33 | 181720.55 | 185132.99 | 189083.87 | 191252.38 | 193902.3 | 195951.89 | 198546.27 | 200985.73 | 203152.58 | 205018.06 | 206831.68 | 208311.77 | 209591.36 | 210541.77 | 212538.17 | 214151.54 | 215382.52 | 216907.84 | 218093.88 | 219209.44 | 219800.48 | 220395.36 | 220925.44 | 221656.76 | 222526.64 | 223175.16 | 223422.1 | 223781.51 | 224225.14 | 224538.05 | 225033.8 | 225326.99 | 225573.29 | 226027.08 | 226804.89 | 227154.73 | 227267.02 | 227397.45 | 227558.94 | 227806.35 | 228321.96 | 228332.81 | 228370.77 | 228408.72 | 228514.56 | 228665.65 | 228744.84 | 228824.03 | 228880.6 | 231015.71 | 232300.47 | 232949.06 | 233597.64 | 234246.23 | 234894.82 | 235546.49 | 236050.91 | 236176.9 | 236336.84 | 236439.69 | 236464.4 | 236888.99 | 237660.98 | 237815.38 | 237815.38 | 237972.21 | 238155.17 | 238338.14 | 238521.1 | 238599.52 | 238599.52 | 238599.52 | 238599.52 | 238599.52 | 238599.52 | 244480.56 | 253747.67 | 256866.4 | 259985.14 | 263103.88 | 266222.61 | 269341.35 | 272460.09 | 272905.62 | 272905.62 | 272905.62 | 272905.62 | 272905.62 | 272905.62 | 272905.62 | 0% | 0% | 0% | 0% | 0% | 0.02207% | 0.2077% | 0.4001% | 0.6064% | 0.8223% | 1.053% | 1.294% | 1.551% | 1.816% | 2.1% | 2.388% | 2.682% | 2.991% | 3.313% | 3.646% | 3.997% | 4.374% | 4.775% | 5.203% | 5.68% | 6.238% | 6.86% | 7.506% | 8.178% | 8.864% | 9.579% | 10.32% | 11.17% | 12.13% | 13.17% | 14.3% | 15.49% | 16.78% | 18.21% | 18.9% | 23.89% | 26.14% | 28.41% | 30.61% | 32.75% | 34.42% | 35.43% | 36.83% | 38.4% | 39.9% | 41.33% | 42.81% | 44.2% | 45.63% | 47.12% | 48.88% | 50.79% | 52.65% | 54.47% | 56.22% | 58.31% | 60.21% | 61.33% | 61.9% | 62.36% | 63.05% | 64.04% | 65.33% | 66.59% | 67.84% | 69.29% | 70.08% | 71.05% | 71.8% | 72.75% | 73.65% | 74.44% | 75.12% | 75.79% | 76.33% | 76.8% | 77.15% | 77.88% | 78.47% | 78.92% | 79.48% | 79.92% | 80.32% | 80.54% | 80.76% | 80.95% | 81.22% | 81.54% | 81.78% | 81.87% | 82% | 82.16% | 82.28% | 82.46% | 82.57% | 82.66% | 82.82% | 83.11% | 83.24% | 83.28% | 83.32% | 83.38% | 83.47% | 83.66% | 83.67% | 83.68% | 83.7% | 83.73% | 83.79% | 83.82% | 83.85% | 83.87% | 84.65% | 85.12% | 85.36% | 85.6% | 85.83% | 86.07% | 86.31% | 86.5% | 86.54% | 86.6% | 86.64% | 86.65% | 86.8% | 87.09% | 87.14% | 87.14% | 87.2% | 87.27% | 87.33% | 87.4% | 87.43% | 87.43% | 87.43% | 87.43% | 87.43% | 87.43% | 89.58% | 92.98% | 94.12% | 95.27% | 96.41% | 97.55% | 98.69% | 99.84% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
24 | Procurement | 670 | 01-Feb-22 A | 2024-01-18 | 7033236.09 | 24 | [40 empty] | 8278.1 | 20478.26 | 29854.54 | 37977.66 | 47607.63 | 61982.57 | 80987.73 | 102932.12 | 126282.26 | 151729.3 | 180384.36 | 212990.48 | 249430.99 | 289575.92 | 333334.17 | 399659.49 | 482315.33 | 544924.21 | 603333.86 | 661621.84 | 718718.99 | 774125.25 | 838157.77 | 914610.52 | 997833.03 | 1090549.94 | 1181847.98 | 1280328.74 | 1391614.26 | 1500176.41 | 1618056.54 | 1738381.97 | 1860035.86 | 1979738.33 | 2102288.44 | 2221426.58 | 2345799.79 | 2465435.09 | 2583412.38 | 2703400.55 | 2826521.99 | 2949144.91 | 3078565.02 | 3198971.99 | 3316577.04 | 3435552.59 | 3555728.77 | 3669526.72 | 3784220.96 | 3897357.98 | 4015743.34 | 4165984.16 | 4328571.58 | 4452929.97 | 4570923.29 | 4674001.27 | 4774938.24 | 4866012.15 | 4943271.3 | 5027589.46 | 5106899.71 | 5184000.07 | 5255325.6 | 5326002.7 | 5403395.02 | 5478027.86 | 5561289.14 | 5646165.24 | 5710431.1 | 5772939.53 | 5839036.23 | 5891089.32 | 5944942.95 | 5999616.38 | 6056729.99 | 6120915.49 | 6181861.36 | 6277339.21 | 6323132.25 | 6369973.41 | 6397676.14 | 6430061.31 | 6490488.64 | 6526554.74 | 6551337.67 | 6600244.48 | 6639606.71 | 6658669.96 | 6677733.21 | 6800694.42 | 6859659.16 | 6869727.81 | 6880140.76 | 6889965.55 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 7033236.09 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1177% | 0.2912% | 0.4245% | 0.54% | 0.6769% | 0.8813% | 1.152% | 1.464% | 1.796% | 2.157% | 2.565% | 3.028% | 3.546% | 4.117% | 4.739% | 5.682% | 6.858% | 7.748% | 8.578% | 9.407% | 10.22% | 11.01% | 11.92% | 13% | 14.19% | 15.51% | 16.8% | 18.2% | 19.79% | 21.33% | 23.01% | 24.72% | 26.45% | 28.15% | 29.89% | 31.58% | 33.35% | 35.05% | 36.73% | 38.44% | 40.19% | 41.93% | 43.77% | 45.48% | 47.16% | 48.85% | 50.56% | 52.17% | 53.8% | 55.41% | 57.1% | 59.23% | 61.54% | 63.31% | 64.99% | 66.46% | 67.89% | 69.19% | 70.28% | 71.48% | 72.61% | 73.71% | 74.72% | 75.73% | 76.83% | 77.89% | 79.07% | 80.28% | 81.19% | 82.08% | 83.02% | 83.76% | 84.53% | 85.3% | 86.12% | 87.03% | 87.89% | 89.25% | 89.9% | 90.57% | 90.96% | 91.42% | 92.28% | 92.8% | 93.15% | 93.84% | 94.4% | 94.67% | 94.95% | 96.69% | 97.53% | 97.68% | 97.82% | 97.96% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
25 | Construction | 950 | 20-Aug-21 A | 2024-04-07 | 2016255.2 | 25 | [8 empty] | 32.31 | 267.79 | 549.37 | 932.24 | 1611.9 | 2564 | 3556.57 | 4549.14 | 5541.7 | 6574.66 | 7637.9 | 8701.15 | 9764.39 | 10827.63 | 12301.71 | 14296.22 | 16444.51 | 18968.59 | 21597.93 | 24240.43 | 26905.39 | 29604.04 | 32446.57 | 35397 | 38347.44 | 41297.88 | 44248.32 | 49366.05 | 55217.63 | 61106.03 | 67000.57 | 67842.65 | 67842.65 | 67842.65 | 68409.95 | 70902.61 | 72448.97 | 73782.77 | 75199.63 | 78954.97 | 81549.2 | 83483.23 | 84769.86 | 87465.11 | 91268.92 | 112992.16 | 169239.7 | 210250.46 | 232017.39 | 243079.75 | 251778.5 | 260472.51 | 271226.89 | 280744.96 | 289877.31 | 299700.08 | 308975.61 | 318223.72 | 327772.97 | 339734.15 | 352439.43 | 372219.36 | 394000.95 | 419069.6 | 435678.18 | 458200.93 | 478318.26 | 498057.43 | 519018.97 | 538838.9 | 556220.37 | 571042.76 | 594081.62 | 608145.8 | 618357.6 | 636827.02 | 655598.7 | 677260.11 | 695671.55 | 714288.24 | 731209.72 | 745718.55 | 763443.04 | 785120.53 | 806836.32 | 839841.82 | 882973.97 | 928060.04 | 967877.18 | 1001568.49 | 1044025.15 | 1080042.84 | 1112015.73 | 1147727.27 | 1181892.09 | 1216364.25 | 1249639.05 | 1276069.57 | 1297093.89 | 1321355.9 | 1342406.06 | 1361313.04 | 1379260 | 1391435.94 | 1400542.15 | 1409806.83 | 1421026.79 | 1433336.7 | 1452306.46 | 1486583.6 | 1520364.57 | 1556787.23 | 1586476.04 | 1606400.97 | 1620564.59 | 1633922.48 | 1648702.25 | 1671674.17 | 1700686.56 | 1727359.71 | 1749694.53 | 1766629.2 | 1777101.83 | 1786119.9 | 1790815.11 | 1792268.18 | 1814022.81 | 1842035.73 | 1868707.12 | 1894146.5 | 1918661.87 | 1943177.25 | 1965125.93 | 1986047.93 | 2006969.93 | 2016000.24 | 2016111.79 | 2016223.33 | 2016255.2 | 2016255.2 | 2016255.2 | 2016255.2 | 2016255.2 | 2016255.2 | 2016255.2 | 2016255.2 | 2016255.2 | 2016255.2 | 2016255.2 | 2016255.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.001602% | 0.01328% | 0.02725% | 0.04624% | 0.07995% | 0.1272% | 0.1764% | 0.2256% | 0.2749% | 0.3261% | 0.3788% | 0.4316% | 0.4843% | 0.537% | 0.6101% | 0.709% | 0.8156% | 0.9408% | 1.071% | 1.202% | 1.334% | 1.468% | 1.609% | 1.756% | 1.902% | 2.048% | 2.195% | 2.448% | 2.739% | 3.031% | 3.323% | 3.365% | 3.365% | 3.365% | 3.393% | 3.517% | 3.593% | 3.659% | 3.73% | 3.916% | 4.045% | 4.141% | 4.204% | 4.338% | 4.527% | 5.604% | 8.394% | 10.43% | 11.51% | 12.06% | 12.49% | 12.92% | 13.45% | 13.92% | 14.38% | 14.86% | 15.32% | 15.78% | 16.26% | 16.85% | 17.48% | 18.46% | 19.54% | 20.78% | 21.61% | 22.73% | 23.72% | 24.7% | 25.74% | 26.72% | 27.59% | 28.32% | 29.46% | 30.16% | 30.67% | 31.58% | 32.52% | 33.59% | 34.5% | 35.43% | 36.27% | 36.99% | 37.86% | 38.94% | 40.02% | 41.65% | 43.79% | 46.03% | 48% | 49.67% | 51.78% | 53.57% | 55.15% | 56.92% | 58.62% | 60.33% | 61.98% | 63.29% | 64.33% | 65.54% | 66.58% | 67.52% | 68.41% | 69.01% | 69.46% | 69.92% | 70.48% | 71.09% | 72.03% | 73.73% | 75.41% | 77.21% | 78.68% | 79.67% | 80.37% | 81.04% | 81.77% | 82.91% | 84.35% | 85.67% | 86.78% | 87.62% | 88.14% | 88.59% | 88.82% | 88.89% | 89.97% | 91.36% | 92.68% | 93.94% | 95.16% | 96.38% | 97.46% | 98.5% | 99.54% | 99.99% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
26 | Commissioning | 527.25 | 2023-01-11 | 2024-06-21 | 145170.26 | 26 | 2023-01-07: 44.32; 2023-01-14: 268.98; 2023-01-21: 456.86; 2023-01-28: 1214.99; 2023-02-04: 1278.29; 2023-02-11: 1347.52; 2023-02-18: 1555.26; 2023-02-25: 1630.07; 2023-03-04: 1649.53; 2023-03-11: 1886.83; 2023-03-18: 1925.87; 2023-03-25: 2014.29; 2023-04-01: 2053.84; 2023-04-08: 2507.3; 2023-04-15: 2953.82; 2023-04-22: 5245.09; 2023-04-29: 5874.56; 2023-05-06: 6422.23; 2023-05-13: 7003.08; 2023-05-20: 7573.11; 2023-05-27: 9801.54; 2023-06-03: 10232.26; 2023-06-10: 10319.5; 2023-06-17: 11192.62; 2023-06-24: 11471.56; 2023-07-01: 11544.71; 2023-07-08: 11923.4; 2023-07-15: 12072.64; 2023-07-22: 12150.38; 2023-07-29: 12416.92; 2023-08-05: 12474.56; 2023-08-12: 12703.22; 2023-08-19: 12953.56; 2023-08-26: 13117.15; 2023-09-02: 13296.96; 2023-09-09: 13619.71; 2023-09-16: 16773.62; 2023-09-23: 19970.53; 2023-09-30: 21039.6; 2023-10-07: 21401.59; 2023-10-14: 21561.37; 2023-10-21: 23826.01; 2023-10-28: 28194.49; 2023-11-04: 30985.65; 2023-11-11: 33183.88; 2023-11-18: 35004.92; 2023-11-25: 36293.63; 2023-12-02: 36596.78; 2023-12-09: 36781.6; 2023-12-16: 38184.74; 2023-12-23: 38228.38; 2023-12-30: 38255.67; 2024-01-06: 38475.85; 2024-01-13: 38497.78; 2024-01-20: 38844.28; 2024-01-27: 38896.84; 2024-02-03: 38949.4; 2024-02-10: 38977.93; 2024-02-17: 39004.17; 2024-02-24: 39076.64; 2024-03-02: 39156.61; 2024-03-09: 39191.6; 2024-03-16: 42063.96; 2024-03-23: 47073.11; 2024-03-30: 52082.26; 2024-04-06: 57091.42; 2024-04-13: 58482.85; 2024-04-20: 59285.79; 2024-04-27: 59711.95; 2024-05-04: 60719.21; 2024-05-11: 67724.16; 2024-05-18: 82030.93; 2024-05-25: 108745.25; 2024-06-01: 129282.54; 2024-06-08: 140406.55; 2024-06-15: 145170.26; 2024-06-22: 145170.26 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.03053% | 0.1853% | 0.3147% | 0.8369% | 0.8805% | 0.9282% | 1.071% | 1.123% | 1.136% | 1.3% | 1.327% | 1.388% | 1.415% | 1.727% | 2.035% | 3.613% | 4.047% | 4.424% | 4.824% | 5.217% | 6.752% | 7.048% | 7.109% | 7.71% | 7.902% | 7.953% | 8.213% | 8.316% | 8.37% | 8.553% | 8.593% | 8.751% | 8.923% | 9.036% | 9.16% | 9.382% | 11.55% | 13.76% | 14.49% | 14.74% | 14.85% | 16.41% | 19.42% | 21.34% | 22.86% | 24.11% | 25% | 25.21% | 25.34% | 26.3% | 26.33% | 26.35% | 26.5% | 26.52% | 26.76% | 26.79% | 26.83% | 26.85% | 26.87% | 26.92% | 26.97% | 27% | 28.98% | 32.43% | 35.88% | 39.33% | 40.29% | 40.84% | 41.13% | 41.83% | 46.65% | 56.51% | 74.91% | 89.06% | 96.72% | 100% | 100%