## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-DT-0012_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0749 |  |  | Transmital Date: 27 Mar 2022
Document Title: Data Sheets For LBV |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR- 0749 |  |  | Transmital Date: 27 Mar 2022
[5 empty] | CRS No: NISCO-CRS-BK-PPL-PEDCO-320-IN-DT-0012_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument Comments
| فهرست مدارک مرجع به مدرک اضافه گردد. |  | 1401-2294-27269 | 1401/01/28 | اعمال شد.
| به نام و شماره مدرک مرجع برای Environmental Conditions اشاره گردد. |  | 1401-2294-27269 | 1401/01/28 | اعمال شد.
| ردیف 46 جدول به11 Note اشاره گردیده در حالیکه Note11 در زیر جدول موجود نمی باشد . |  | 1401-2294-27269 | 1401/01/28 | در زیر جدول در Note11 آورده شده است.
| با توجه به اینکه در ردیف 43 جدول ،آیتم Hand wheel به Note 10 اشاره گردیده ، ارتباط این Note با آیتم مربوطه تشریح گردد. |  | 1401-2294-27269 | 1401/01/28 | در نت 17 در قسمت general note آورده شده است.
| بخشی در خصوص Line pressure loss detection system به مدرک اضافه گردد و اطلاعات مربوط به نوع سیستم ، Rate of pressure drop و ....... در آن درج گردد. |  | 1401-2294-27269 | 1401/01/28 | در ردیف 50 اعمال شد.
| ردیف مربوط به Speed controller اضافه گردد. |  | 1401-2294-27269 | 1401/01/28 | در ردیف 51 اعمال شد.
| پس از نهایی شدن مطالعات خوردگی و مدرک PMS پروژه در خصوص متریال شیر آلات بازنگری صورت گیرد. |  | 1401-2294-27269 | 1401/01/28 | ملاحظه و بررسی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 16 Apr 2022 |  |  |  |  | Date: