## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-TE-PY-0005_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0912 |  |  | Transmital Date: May-08nd-2022
Document Title: Telecom Equipment Layout For Area |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0102-TE-TR-0912 |  |  | Transmital Date: May-08nd-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0005_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | یک دستگاه تلفن ضد انفجار درمحوطه کمپرسور میانی اضافه گردد |  | 1401-2294-78843 | 1401-03-08 | اضافه گردید
3 | تعریف دستگاه های تلفن به عنوان هاتلاین می بایست با هماهنگی بهره برداری در زمان راه اندازی انجام و اصلاح گردد. |  | 1401-2294-78843 | 1401-03-08 | این مشاور بر اساس شرح کار بخش تکمیلی نسبت به چیدمان تلفن های بدون شماره گیر قرمز بعنوان هاتلاین در محوطه سایت اقدام نمود که میتواند با تعریف فیزیکی و نرم افزاری بصورت مستقیم با ساختمان کنترل در ارتباط باشند
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: AP.Golrang | Signature |  |  |  | Clarified By: | Signature
| Date: May-10th-2022 |  |  |  |  | Date: