## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-ME-SP-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0015 |  |  | Transmital Date: 28/JUL/2021
Document Title: Specification for Pressure Vessels |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0104-ME-TR-0015 |  |  | Transmital Date: 28/JUL/2021
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-000-ME-SP-0001_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بند 1: بازرس شخص ثالث می بایست توسط پیمانکار اصلی تعیین گردد، از این رو تعریف بر این اساس اصلاح گردد. |  | 00/2294/162504 | 1400/05/21 | نظر کارفرمای محترم اعمال گردید.
2 | بندی در ارتباط با Conflict Requirement به مدرک اضافه و مندرجات زیر این بخش نوشته شود " در صورت وجود تناقض در مندرجات این مدرک و یا وجود تناقض بین مندرجات این مدرک با دیگر مدارک پروژه و یا استانداردهای مرجع این موضوع می بایست به کارفرما منعکس گردد. تصمیم گیری در این شرایط با کارفرما خواهد بود." |  | 00/2294/162504 | 1400/05/21 | نظر کارفرمای محترم اعمال گردید.
3 | در مدرک درج شود هر جا به ویرایش استانداردی اشاره نشده است، منظور آخرین ویرایش موجود می باشد. |  | 00/2294/162504 | 1400/05/21 | نظر کارفرمای محترم اعمال گردید.
4 | بند 2: مطابق فرمت IPS مربوطه تعاربف ADD, SUB,... اصلاح گردد، به عنوان مثال بخش SUB مطابق شرح ذیل اصلاح گردد. |  | 00/2294/162504 | 1400/05/21 | نظر کارفرمای محترم اعمال گردید.
Sub. (Substitution): The clause in IPS-G-ME-150(2) shall be deleted and replaced by the new clause in this specification.
5 | بند 2: این مدرک می بایست بر اساس آخرین ویرایش استاندارد IPS-G-ME-150 تهیه گردد. و ویرایش Jan 2010 ویرایش قدیم بوده و مورد پذیرش نیست از این رو ضرروریست مدرک بر اساس آخرین ویرایش استاندارد مرجع بازنگری گردد. |  | 00/2294/162504 | 1400/05/21 | نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature | M.Fakharian
| Date: 8/8/2021 |  |  |  |  | Date: 07/05/2022