## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-GE-RT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0785 |  |  | Transmital Date:10-APR-2022
Document Title: Value Engineering Study Report |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GE-TR-0785 |  |  | Transmital Date:10-APR-2022
[5 empty] | CRS No: CRS-BK-SSGRL-PEDCO-110-GE-RT-0002-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بتزگشت به مامه BK-PEDCO-NISOC-0101-PR-LT-1036 مورخ 21/01/1401 (شماره سیستمی 964) با موضوع صدرالذکر ، به اطلاع می رساند که نقطه نظرات کارفرما برروی مدارک مزبور در جلسه مورخ 28/02/1401 و با حضور نمایندگان طذفین به پیمانکار ابلاغ و مقرر گردید اصلاحات لازم حداکثر تا تاریخ 02/03/1401 انجام و مئارک مزبور مجددا ارائه گردد. |  | 1401-2294-68426 | 1401/02/31 | اعمال گردید
2 | ضمنا نظرات تکمیلی برروی مدارک محاسبات هیدرولیک گاز گلخاری مربوط به مطالعات مورئ اشاره ارسالی طی BK-PEDCO-NISOC-0101-GE-LT-2274 مورخ 1401/02/04 (شماره سیستمی 2330) نیز به پیوست سوابق (شماره نامه 1401/478/67462) جهت اطلاع واقدام مقتضی ارسال می گردد. |  | 1401-2294-68426 | 1401/02/31 | اعمال گردید و درقالب گزارش جداگانه قبلا ارسال و به تایید آن کارفرمای محترم رسیده است.
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: