## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PR-PH-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0520 |  |  | Transmital Date:1/29/2022
Document Title:Drainage Philosophy |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0520 |  |  | Transmital Date:1/29/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PH-0001 _D01 |  |  | CRS Status: | C
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | شدت بارندگی می بایست از اطلاعات هواشناسی استان بوشهر استعلام و در این مدرک و سایر مدارک مرتبط ملاک قرار گیرد. |  | 1400-2294-436900 | 1400/12/15 | میزان بارش باتوجه به مدارک طراحی پایه (According to the meteorological data in Khozestan province)، در نظر گرفته شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: