## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PR-PH-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0520 |  |  | Transmital Date:1/29/2022
Document Title:Drainage Philosophy |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0520 |  |  | Transmital Date:1/29/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-PH-0001 _D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در آیتم 4.4 نام تمامی تجهیزات قید گردد ( به عنوان مثال رسیور گلخاری) |  | BK-SUR-ENG-PCS-00-03179 | 2022-02-22 | اعمال گردید.
2 | آیتم 4.4.3 بر اساس مشخصات مندرج در طراحی پایه تصحیح گردد. |  | BK-SUR-ENG-PCS-00-03179 | 2022-02-22 | در مدرک آیتم 4.4.3 موجود نمی باشد.
3 | محاسبات ارائه شده در آیتم 6.2 با توجه به طراحی تفضیلی می بایست بازنگری گردد (سطح پوشش غیر جذبی و...) |  | BK-SUR-ENG-PCS-00-03179 | 2022-02-22 | باتوجه به عدم تغییر ابعاد پلنت و فرآیند مورد بررسی در پروژه فوق، از منظر این پیمانکار، محاسبات مربوط به میزان دبی OILY WATER FROM OILY WATER SEWER طراحی پایه مورد تایید و استناد می باشد.
4 | لازم است نقطه نظرات ذینفع اصلی اعمال گردد. |  | BK-SUR-ENG-PCS-00-03179 | 2022-02-22 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: