## S-Curve-Weekly
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 171
| Project | Index | time axis 2021-06-19 to 2024-06-22
Binak Oil Field Development-EPC | time axis 2021-06-19 to 2024-06-22
| BINAK-Total (EPC) | 3 | Plan Rev00 -Cumulative | 0.06748% | 0.2656% | 0.3449% | 0.4451% | 0.5551% | 0.6757% | 0.7473% | 0.8526% | 1.112% | 1.499% | 1.975% | 2.578% | 3.217% | 3.913% | 4.606% | 5.326% | 6.18% | 7.079% | 8.018% | 8.98% | 10.04% | 11.19% | 12.17% | 13.4% | 14.9% | 16.27% | 17.71% | 19.09% | 20.5% | 22.06% | 23.82% | 25.54% | 27.02% | 28.5% | 29.96% | 31.49% | 33.06% | 34.68% | 36.34% | 37.94% | 39.17% | 40.38% | 41.69% | 43% | 44.35% | 45.57% | 46.85% | 48.07% | 49.29% | 50.75% | 52.15% | 53.65% | 55.07% | 56.54% | 58.05% | 59.58% | 61.13% | 62.77% | 64.65% | 66.35% | 67.68% | 69.06% | 70.47% | 71.8% | 73.07% | 74.4% | 75.69% | 76.89% | 77.94% | 79.03% | 80.27% | 81.25% | 82.13% | 83.1% | 84.01% | 85.13% | 86.49% | 87.42% | 88.41% | 89.85% | 91.33% | 92.95% | 93.43% | 93.78% | 95.67% | 96.08% | 96.53% | 96.9% | 97.26% | 97.58% | 97.9% | 98.12% | 98.3% | 98.51% | 98.76% | 98.86% | 98.94% | 99.01% | 99.08% | 99.19% | 99.37% | 99.65% | 99.85% | 99.96% | 100%
|  |  | Plan Rev01 -Cumulative | 0.0002033% | 0.0007022% | 0.001339% | 0.003698% | 0.005136% | 0.05154% | 0.1213% | 0.1912% | 0.261% | 0.3614% | 0.4538% | 0.5331% | 0.6239% | 0.6921% | 0.7512% | 0.7788% | 0.8004% | 0.8276% | 0.8576% | 0.8781% | 0.9% | 0.9219% | 0.9564% | 1.024% | 1.098% | 1.19% | 1.254% | 1.305% | 1.352% | 1.401% | 1.455% | 1.515% | 1.59% | 1.705% | 1.828% | 1.976% | 2.129% | 2.304% | 2.51% | 2.53% | 4.332% | 5.065% | 5.535% | 5.859% | 6.186% | 6.627% | 7.096% | 7.577% | 8.103% | 8.636% | 9.23% | 9.802% | 10.41% | 11.1% | 11.86% | 13.16% | 14.64% | 15.7% | 16.59% | 17.39% | 18.2% | 19.09% | 20% | 20.91% | 21.87% | 22.91% | 23.86% | 24.88% | 26.04% | 27.17% | 28.28% | 29.4% | 30.56% | 31.87% | 33% | 34.12% | 35.21% | 36.32% | 37.45% | 38.57% | 39.73% | 40.87% | 42.04% | 43.16% | 44.31% | 45.44% | 46.58% | 47.73% | 48.89% | 49.98% | 51.19% | 52.48% | 53.78% | 55.04% | 56.46% | 58.07% | 59.45% | 60.72% | 62.06% | 63.36% | 64.52% | 65.67% | 66.84% | 68% | 69.17% | 70.32% | 71.51% | 72.65% | 73.78% | 74.83% | 75.85% | 77.03% | 78.2% | 79.16% | 80.11% | 80.97% | 81.82% | 82.66% | 83.6% | 84.52% | 85.33% | 86.19% | 87.3% | 88.36% | 89.51% | 90.73% | 92.22% | 93.07% | 93.47% | 93.84% | 94.33% | 95.92% | 96.23% | 96.59% | 96.94% | 97.24% | 97.52% | 97.83% | 98.13% | 98.38% | 98.56% | 98.69% | 98.79% | 98.88% | 98.95% | 99.01% | 99.07% | 99.1% | 99.12% | 99.18% | 99.26% | 99.33% | 99.56% | 99.78% | 99.87% | 99.94% | 99.99% | 100%
Azar Oil Field Development |  |  | Plan Rev01-Period | 0.0002033% | 0.0004989% | 0.0006364% | 0.002359% | 0.001438% | 0.0464% | 0.06978% | 0.06983% | 0.06987% | 0.1003% | 0.09243% | 0.07929% | 0.09084% | 0.06823% | 0.05909% | 0.02752% | 0.02164% | 0.02722% | 0.03% | 0.02049% | 0.02193% | 0.0219% | 0.03449% | 0.06745% | 0.07388% | 0.09185% | 0.06471% | 0.05084% | 0.0469% | 0.04934% | 0.05363% | 0.06032% | 0.07447% | 0.1147% | 0.1236% | 0.1475% | 0.1537% | 0.1741% | 0.2062% | 0.02017% | 1.802% | 0.7326% | 0.4706% | 0.3238% | 0.3273% | 0.4404% | 0.4691% | 0.4812% | 0.5264% | 0.5323% | 0.5942% | 0.5727% | 0.6124% | 0.6852% | 0.7592% | 1.296% | 1.484% | 1.059% | 0.887% | 0.8044% | 0.8087% | 0.8926% | 0.9134% | 0.9099% | 0.9519% | 1.042% | 0.9481% | 1.028% | 1.158% | 1.126% | 1.11% | 1.118% | 1.167% | 1.302% | 1.136% | 1.121% | 1.088% | 1.114% | 1.123% | 1.121% | 1.158% | 1.144% | 1.173% | 1.116% | 1.146% | 1.139% | 1.135% | 1.147% | 1.164% | 1.083% | 1.213% | 1.291% | 1.306% | 1.256% | 1.42% | 1.613% | 1.378% | 1.268% | 1.342% | 1.299% | 1.157% | 1.149% | 1.173% | 1.161% | 1.163% | 1.154% | 1.189% | 1.138% | 1.131% | 1.052% | 1.02% | 1.176% | 1.173% | 0.9585% | 0.9526% | 0.8581% | 0.8479% | 0.8411% | 0.9391% | 0.9279% | 0.8014% | 0.8607% | 1.111% | 1.061% | 1.151% | 1.218% | 1.489% | 0.8538% | 0.3994% | 0.369% | 0.4871% | 1.589% | 0.3182% | 0.3578% | 0.3447% | 0.308% | 0.276% | 0.3096% | 0.3042% | 0.2467% | 0.1755% | 0.1314% | 0.09963% | 0.09187% | 0.07208% | 0.06278% | 0.05535% | 0.03144% | 0.01694% | 0.06583% | 0.07276% | 0.06938% | 0.2369% | 0.2174% | 0.09384% | 0.06344% | 0.05269% | 0.01033%
Actual
Surface
FEED Package |  |  | Binak Oil Field Development-EPC
Geotechnical Survey
Topographical Survey
Geophysical Survey |  |  | BINAK-Total (EPC)
Comprehensive surface survey
Main Oil Pipeline
Main Oil Transfer Pumps
Gas Compressors
Wellhead Control Panel
HIPPS
Flow lines’ Pipes
Well Pads, Access Roads Re-Construction
Water Supply
Wellhead Facilities,Flowlines
Oil & Gas Export Pipe Lines
CPF Civil Works
Central Process Facilities (CPF)
Modified Early Production
Final Production
Operator's Residential Facility
Electrical Power Supply Substation
Soil, Concrete and Asphalt Laboratory
Surface Technical Site Supervision
Third Party Inspection on vendor’s premises
Other Pproject
Subsurface
Drilling
Drilling of 10 wells-GPTK
Drilling of 7 wells-NIDC
Drilling of 2 Wells-Persia
Acid Fracture / High Volume Acid
Procurement of Tubing 5 1/2" , 4 1/2" , 3 1/2"( for 10 wells)
Procurement of Completion (for 19 Wells)
Technical Site supervision (drilling)
Third Party Inspection on sub surface vendor’s premises
Subsurface Studies
Full Field Reservoir Study
Fluid Sampling and Analysis
Other Projects
[163 empty] | 0.02439 | 0.04878 | 0.073171 | 0.097561 | 0.12195 | 0.14634 | 0.17073 | 0.19512 | 0.21951 | 0.2439 | 0.26829 | 0.29268 | 0.31707 | 0.34146 | 0.36585 | 0.39024 | 0.41463 | 0.43902 | 0.46341 | 0.4878 | 0.5122 | 0.53659 | 0.56098 | 0.58537 | 0.60976 | 0.63415 | 0.65854 | 0.68293 | 0.70732 | 0.73171 | 0.7561 | 0.78049 | 0.80488 | 0.82927 | 0.85366 | 0.87805 | 0.90244 | 0.92683 | 0.95122 | 0.97561 | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[165 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## S-Curve-Monthly
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Project | Index |  | 1: 2021; 7: 2022; 19: 2023; 31: 2024
Binak Oil Field Development-EPC |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Commissioning | 26 |  | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2023-01-31 | 2023-02-28 | 2023-03-31 | 2023-04-30 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-28 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30
|  | Plan Rev00 -Cumulative | 0.1988% | 0.7767% | 1.804% | 3.836% | 7.14% | 12.17% | 18.53% | 25.55% | 33% | 39.97% | 47.22% | 54.7% | 62.39% | 69.37% | 74.65% | 78.74% | 82.17% | 87.07% | 93.25% | 96.48% | 98.1% | 98.51% | 99.35% | 100%
|  | Plan Rev01 -Cumulative | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1155% | 0.3017% | 0.7776% | 0.9695% | 1.608% | 4.532% | 5.308% | 5.859% | 6.179% | 6.527% | 6.768% | 7.031% | 7.153% | 7.491% | 13.28% | 22.45% | 79.86% | 100%
|  | Plan Rev01-Period | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1155% | 0.1862% | 0.4759% | 0.192% | 0.6387% | 2.924% | 0.7763% | 0.551% | 0.3197% | 0.3477% | 0.2414% | 0.2629% | 0.1221% | 0.338% | 5.791% | 9.165% | 57.42% | 20.14%
Actual
Binak Oil Field Development-EPC
Commissioning
[39 empty] | 0.02439 | 0.04878 | 0.073171 | 0.097561 | 0.12195 | 0.14634 | 0.17073 | 0.19512 | 0.21951 | 0.2439 | 0.26829 | 0.29268 | 0.31707 | 0.34146 | 0.36585 | 0.39024 | 0.41463 | 0.43902 | 0.46341 | 0.4878 | 0.5122 | 0.53659 | 0.56098 | 0.58537 | 0.60976 | 0.63415 | 0.65854 | 0.68293 | 0.70732 | 0.73171 | 0.7561 | 0.78049 | 0.80488 | 0.82927 | 0.85366 | 0.87805 | 0.90244 | 0.92683 | 0.95122 | 0.97561 | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[41 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Data-Base-Monthly
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WBS | Activity ID | Original Duration | Start | Finish | Budgeted Labor Units | Spreadsheet Field | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01
3 | BINAK-Total (EPC) | 1097 | 23-Jun-21 A | 2024-06-23 | 10000000.07 | 3 | 55.03 | 6139.74 | 41438.74 | 74282.73 | 86343.71 | 99303.42 | 130511.04 | 154676.5 | 204159.77 | 252985.18 | 623644.81 | 841026 | 1099961.2 | 1596132.58 | 1973927 | 2385578.44 | 2875670.68 | 3380290.76 | 3872549.98 | 4381591.5 | 4839755.63 | 5378337.74 | 5981706.51 | 6533534.53 | 7031778.65 | 7527436.13 | 7996939.52 | 8374976.84 | 8789071.6 | 9298866.64 | 9600607.81 | 9743744.88 | 9852699.74 | 9896699.88 | 9914893.6 | 9977707.48 | 9999736.98 | 0.0005503% | 0.0614% | 0.4144% | 0.7428% | 0.8635% | 0.9931% | 1.305% | 1.547% | 2.042% | 2.53% | 6.237% | 8.41% | 11% | 15.96% | 19.74% | 23.86% | 28.76% | 33.8% | 38.73% | 43.82% | 48.4% | 53.78% | 59.82% | 65.34% | 70.32% | 75.28% | 79.97% | 83.75% | 87.89% | 92.99% | 96.01% | 97.44% | 98.53% | 98.97% | 99.15% | 99.78% | 100%
4 | GENERAL | 720 | 23-Jun-21 A | 2024-03-08 | 532432.82 | 4 | 55.03 | 5401.38 | 25616.42 | 42062.69 | 47610.84 | 52774.59 | 60997.08 | 70655.27 | 103152.63 | 133590.53 | 365642.61 | 399917.69 | 423247.21 | 449644.15 | 456467.33 | 461969.46 | 469337.41 | 474068.18 | 478953.26 | 483838.34 | 488260.5 | 493450.17 | 498180.94 | 503066.02 | 507769.57 | 512342.1 | 516370.58 | 520223.17 | 523674.86 | 526518.17 | 528759.26 | 530433.88 | 531895.02 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 0.01034% | 1.015% | 4.814% | 7.904% | 8.947% | 9.917% | 11.46% | 13.28% | 19.38% | 25.1% | 68.71% | 75.15% | 79.54% | 84.5% | 85.78% | 86.81% | 88.2% | 89.09% | 90.01% | 90.92% | 91.75% | 92.73% | 93.62% | 94.54% | 95.42% | 96.28% | 97.04% | 97.76% | 98.41% | 98.94% | 99.36% | 99.68% | 99.95% | 100% | 100% | 100% | 100%
5 | SUB-Surface DEVELOPMENT | 1011 | 24-Jul-21 A | 2024-06-07 | 1818441.18 | 5 |  | 317.76 | 7235.33 | 17932.8 | 22571.14 | 28222.68 | 45933.31 | 54293.02 | 63535.22 | 75699.15 | 148161.78 | 254728.52 | 397627.59 | 725751.89 | 886582.1 | 1019080.18 | 1200702.45 | 1361872.17 | 1463720.71 | 1563871.39 | 1632365.76 | 1690233.61 | 1734307.61 | 1752605.7 | 1772102.37 | 1788028.16 | 1793451.82 | 1796516.66 | 1797809.93 | 1798676 | 1799028.05 | 1799434.63 | 1812557.99 | 1817876.67 | 1818216.26 | 1818435.61 | 1818470.6 | 0% | 0.01747% | 0.3979% | 0.9861% | 1.241% | 1.552% | 2.526% | 2.986% | 3.494% | 4.163% | 8.148% | 14.01% | 21.87% | 39.91% | 48.75% | 56.04% | 66.03% | 74.89% | 80.49% | 86% | 89.77% | 92.95% | 95.37% | 96.38% | 97.45% | 98.33% | 98.62% | 98.79% | 98.86% | 98.91% | 98.93% | 98.95% | 99.67% | 99.97% | 99.99% | 100% | 100%
6 | Package 01-New Well # W018S | 649 | 24-Jul-21 A | 2023-04-21 | 88589.59 | 6 |  | 4.95 | 5498 | 14004.6 | 16159.84 | 16408.89 | 24052.17 | 24740.17 | 24960.12 | 25232.4 | 31246.89 | 38773.76 | 46337.42 | 60918.29 | 65640.54 | 68618.73 | 74249.91 | 79372.04 | 83506.67 | 86684.62 | 87929.74 | 88568.31 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 0% | 0.005588% | 6.206% | 15.81% | 18.24% | 18.52% | 27.15% | 27.93% | 28.17% | 28.48% | 35.27% | 43.77% | 52.31% | 68.76% | 74.09% | 77.46% | 83.81% | 89.59% | 94.26% | 97.85% | 99.25% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | Package 02-New Well # W028 (Bangestan) | 449 | 24-Jul-21 A | 2023-05-22 | 128827.1 | 7 |  | 3.37 | 112.56 | 1187.51 | 2956.68 | 7015.36 | 13537.43 | 17579.27 | 19433.22 | 20737.65 | 39796.62 | 54706.37 | 68397.98 | 87404.85 | 103193.79 | 108062.6 | 114416.22 | 118680.3 | 120212.85 | 123993.42 | 127486.47 | 128573.97 | 128674.25 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 0% | 0.002616% | 0.08737% | 0.9218% | 2.295% | 5.445% | 10.51% | 13.65% | 15.08% | 16.1% | 30.89% | 42.46% | 53.09% | 67.85% | 80.1% | 83.88% | 88.81% | 92.12% | 93.31% | 96.25% | 98.96% | 99.8% | 99.88% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | Package 03-New Well # W046S (Bangestan) | 514.25 | 24-Jul-21 A | 2023-08-16 | 592707.13 | 8 |  | 18.43 | 216.13 | 355.86 | 419.32 | 484.94 | 595.42 | 723.9 | 4262.96 | 12234.83 | 45309.12 | 102816.06 | 153315.79 | 325524.91 | 362708.34 | 400037.26 | 474518.32 | 515641.74 | 540218.84 | 551601.93 | 559244.75 | 572511.76 | 583135.85 | 583163.75 | 587133.83 | 592441.66 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 0% | 0.003109% | 0.03646% | 0.06004% | 0.07075% | 0.08182% | 0.1005% | 0.1221% | 0.7192% | 2.064% | 7.644% | 17.35% | 25.87% | 54.92% | 61.19% | 67.49% | 80.06% | 87% | 91.14% | 93.06% | 94.35% | 96.59% | 98.38% | 98.39% | 99.06% | 99.95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | Package 04-New Well # W035 (Bangestan) | 616.75 | 24-Jul-21 A | 2023-11-26 | 156733.57 | 9 |  | 3.54 | 105.65 | 400.8 | 798.89 | 1814.23 | 4653.52 | 7495.43 | 10080.33 | 11839.55 | 19189.22 | 25270.34 | 33460.78 | 41952.62 | 52228.54 | 75457.84 | 103739.26 | 128356.02 | 132479.82 | 140515.65 | 145512.65 | 149004.85 | 151443.4 | 152027.29 | 152039.71 | 153459.65 | 155741.23 | 156158.4 | 156538.79 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 0% | 0.002258% | 0.0674% | 0.2557% | 0.5097% | 1.157% | 2.969% | 4.782% | 6.431% | 7.553% | 12.24% | 16.12% | 21.35% | 26.77% | 33.32% | 48.14% | 66.18% | 81.89% | 84.52% | 89.65% | 92.84% | 95.06% | 96.62% | 96.99% | 97% | 97.91% | 99.36% | 99.63% | 99.87% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Package 05-New Well # W008N | 692.75 | 24-Jul-21 A | 2024-02-10 | 69431.13 | 10 |  | 3.52 | 104.45 | 176.29 | 210.01 | 253.89 | 572.67 | 897.69 | 1198.4 | 1407.97 | 2526.04 | 4041.74 | 6175.62 | 8350.63 | 10585.58 | 13453.5 | 19552.2 | 25210.7 | 39221.98 | 51204.23 | 57404.39 | 60797.34 | 62016.33 | 63647.14 | 65022.86 | 66108.1 | 66549.78 | 67668.98 | 68328.93 | 68982.99 | 69270.65 | 69404.26 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 0% | 0.00507% | 0.1504% | 0.2539% | 0.3025% | 0.3657% | 0.8248% | 1.293% | 1.726% | 2.028% | 3.638% | 5.821% | 8.894% | 12.03% | 15.25% | 19.38% | 28.16% | 36.31% | 56.49% | 73.75% | 82.67% | 87.56% | 89.32% | 91.67% | 93.65% | 95.21% | 95.85% | 97.46% | 98.41% | 99.35% | 99.76% | 99.96% | 100% | 100% | 100% | 100% | 100%
11 | Package 06-New Well # W007S/Manifold Extension (Bangestan) | 811 | 24-Jul-21 A | 2024-06-07 | 236214.84 | 11 |  | 16.25 | 310.63 | 502.39 | 561.35 | 640.28 | 742.56 | 865.43 | 998.32 | 1167.84 | 4423.28 | 9530.9 | 17936.97 | 28302.4 | 47591.52 | 63388.93 | 84588.38 | 122178.26 | 135935.06 | 154634.05 | 173933.34 | 187915.02 | 193817.7 | 197207.86 | 206147.94 | 213102.02 | 215196.97 | 216611.84 | 216864.77 | 216872.46 | 216936.84 | 217209.82 | 230303.3 | 235621.98 | 235961.56 | 236180.92 | 236215.9 | 0% | 0.006879% | 0.1315% | 0.2127% | 0.2376% | 0.2711% | 0.3144% | 0.3664% | 0.4226% | 0.4944% | 1.873% | 4.035% | 7.593% | 11.98% | 20.15% | 26.84% | 35.81% | 51.72% | 57.55% | 65.46% | 73.63% | 79.55% | 82.05% | 83.49% | 87.27% | 90.21% | 91.1% | 91.7% | 91.81% | 91.81% | 91.84% | 91.95% | 97.5% | 99.75% | 99.89% | 99.99% | 100%
12 | Package 07-Workover # 14 | 497 | 24-Jul-21 A | 2023-07-29 | 140256.51 | 12 |  | 66.9 | 221.91 | 326.22 | 366.11 | 404.25 | 452.33 | 509.77 | 672.03 | 807.09 | 1471.76 | 4575.79 | 28758.64 | 75643.88 | 95379.31 | 98858.9 | 102679.97 | 116746.96 | 123951.84 | 135383.15 | 136056.42 | 137730.58 | 139406.38 | 139841.66 | 140100.94 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 0% | 0.0477% | 0.1582% | 0.2326% | 0.261% | 0.2882% | 0.3225% | 0.3635% | 0.4791% | 0.5754% | 1.049% | 3.262% | 20.5% | 53.93% | 68% | 70.48% | 73.21% | 83.24% | 88.38% | 96.53% | 97.01% | 98.2% | 99.39% | 99.7% | 99.89% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
13 | Package 08-Workover # 12 | 477.75 | 24-Jul-21 A | 2023-07-10 | 113892.31 | 13 |  | 66.93 | 222 | 326.37 | 366.31 | 400.9 | 443.95 | 496.27 | 646.59 | 761.15 | 1724.51 | 11475.46 | 27868.04 | 54557.07 | 71434.81 | 73876.44 | 77339.33 | 80726.26 | 92254.47 | 107855.36 | 108662.86 | 112589.6 | 113492.81 | 113736.14 | 113863.27 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 0% | 0.05877% | 0.1949% | 0.2866% | 0.3216% | 0.352% | 0.3898% | 0.4357% | 0.5677% | 0.6683% | 1.514% | 10.08% | 24.47% | 47.9% | 62.72% | 64.87% | 67.91% | 70.88% | 81% | 94.7% | 95.41% | 98.86% | 99.65% | 99.86% | 99.97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
14 | Package 09-Workover # 15 | 524 | 24-Jul-21 A | 2023-08-25 | 170781.36 | 14 |  | 66.93 | 222 | 326.37 | 366.31 | 399.03 | 439.3 | 488.84 | 636.66 | 749.52 | 1097.21 | 1937.84 | 11939.95 | 32751.87 | 58811.39 | 88841.35 | 108551.35 | 116275.42 | 123398.15 | 125388.29 | 145989.29 | 157383.87 | 162410.73 | 169744.34 | 170275.78 | 170603.93 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 0% | 0.03919% | 0.13% | 0.1911% | 0.2145% | 0.2336% | 0.2572% | 0.2862% | 0.3728% | 0.4389% | 0.6425% | 1.135% | 6.991% | 19.18% | 34.44% | 52.02% | 63.56% | 68.08% | 72.26% | 73.42% | 85.48% | 92.16% | 95.1% | 99.39% | 99.7% | 99.9% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | Package 10-Workover # 05 | 552.5 | 24-Jul-21 A | 2023-09-23 | 121007.65 | 15 |  | 66.93 | 222 | 326.37 | 366.31 | 400.9 | 443.95 | 496.27 | 646.59 | 761.15 | 1377.12 | 1600.26 | 3436.39 | 10345.36 | 19008.27 | 28484.64 | 41067.52 | 58684.48 | 72541.03 | 86610.7 | 90145.86 | 95158.31 | 111320.08 | 115817.32 | 120097.83 | 120743.8 | 120894.04 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 0% | 0.05531% | 0.1835% | 0.2697% | 0.3027% | 0.3313% | 0.3669% | 0.4101% | 0.5343% | 0.629% | 1.138% | 1.322% | 2.84% | 8.549% | 15.71% | 23.54% | 33.94% | 48.5% | 59.95% | 71.57% | 74.5% | 78.64% | 91.99% | 95.71% | 99.25% | 99.78% | 99.91% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
16 | SURFACE DEVELOPMENT | 827 | 24-Jul-21 A | 2024-06-23 | 7649126.06 | 16 |  | 420.6 | 8586.99 | 14287.24 | 16161.73 | 18306.15 | 23580.65 | 29728.21 | 37471.93 | 43695.5 | 109840.41 | 186379.79 | 279086.4 | 420736.55 | 630877.56 | 904528.8 | 1205630.82 | 1544350.41 | 1929876.02 | 2333881.77 | 2719129.36 | 3194653.96 | 3749217.96 | 4277862.81 | 4751906.71 | 5227065.87 | 5687117.12 | 6058237 | 6467586.81 | 6973672.47 | 7272820.5 | 7413876.38 | 7508246.72 | 7546682.87 | 7564537 | 7627131.54 | 7649126.05 | 0% | 0.005499% | 0.1123% | 0.1868% | 0.2113% | 0.2393% | 0.3083% | 0.3886% | 0.4899% | 0.5712% | 1.436% | 2.437% | 3.649% | 5.5% | 8.248% | 11.83% | 15.76% | 20.19% | 25.23% | 30.51% | 35.55% | 41.76% | 49.01% | 55.93% | 62.12% | 68.34% | 74.35% | 79.2% | 84.55% | 91.17% | 95.08% | 96.92% | 98.16% | 98.66% | 98.89% | 99.71% | 100%
17 | Package 11- EPC Pipeline 8" & 4" | 805 | 24-Jul-21 A | 2024-06-01 | 1535354.69 | 17 |  | 132.64 | 1723.45 | 2894.66 | 3338.74 | 3690.24 | 4462.4 | 5279.2 | 6542.88 | 7451.67 | 14096.77 | 35517.55 | 58084.79 | 81266.74 | 139645.43 | 234020 | 334283.29 | 442709.83 | 559370.39 | 680188.76 | 785537.51 | 921401.88 | 1022684.15 | 1078100.33 | 1134235.6 | 1191171.62 | 1272090.99 | 1360998.08 | 1417405.63 | 1472797.06 | 1499440.66 | 1517699.82 | 1520889.54 | 1527170.3 | 1531833.3 | 1535266.96 | 1535354.68 | 0% | 0.008639% | 0.1123% | 0.1885% | 0.2175% | 0.2404% | 0.2906% | 0.3438% | 0.4261% | 0.4853% | 0.9181% | 2.313% | 3.783% | 5.293% | 9.095% | 15.24% | 21.77% | 28.83% | 36.43% | 44.3% | 51.16% | 60.01% | 66.61% | 70.22% | 73.87% | 77.58% | 82.85% | 88.64% | 92.32% | 95.93% | 97.66% | 98.85% | 99.06% | 99.47% | 99.77% | 99.99% | 100%
18 | Package 12- EPC # Compressor Station | 827 | 24-Jul-21 A | 2024-06-23 | 6113771.37 | 18 |  | 287.96 | 6863.54 | 11392.58 | 12822.99 | 14615.91 | 19118.25 | 24449.01 | 30929.05 | 36243.83 | 95743.64 | 150862.24 | 221001.61 | 339469.8 | 491232.14 | 670508.8 | 871347.53 | 1101640.58 | 1370505.62 | 1653693 | 1933591.85 | 2273252.09 | 2726533.81 | 3199762.49 | 3617671.11 | 4035894.26 | 4415026.13 | 4697238.92 | 5050181.18 | 5500875.41 | 5773379.84 | 5896176.56 | 5987357.18 | 6019512.57 | 6032703.7 | 6091864.58 | 6113771.37 | 0% | 0.00471% | 0.1123% | 0.1863% | 0.2097% | 0.2391% | 0.3127% | 0.3999% | 0.5059% | 0.5928% | 1.566% | 2.468% | 3.615% | 5.553% | 8.035% | 10.97% | 14.25% | 18.02% | 22.42% | 27.05% | 31.63% | 37.18% | 44.6% | 52.34% | 59.17% | 66.01% | 72.21% | 76.83% | 82.6% | 89.98% | 94.43% | 96.44% | 97.93% | 98.46% | 98.67% | 99.64% | 100%
EPCC | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
|  | Original Duration | Start | Finish | Budgeted Labor Units | Spreadsheet Field | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01
22 | General | 720 | 23-Jun-21 A | 2024-03-08 | 532432.82 | 22 | 55.03 | 5401.38 | 25616.42 | 42062.69 | 47610.84 | 52774.59 | 60997.08 | 70655.27 | 103152.63 | 133590.53 | 365642.61 | 399917.69 | 423247.21 | 449644.15 | 456467.33 | 461969.46 | 469337.41 | 474068.18 | 478953.26 | 483838.34 | 488260.5 | 493450.17 | 498180.94 | 503066.02 | 507769.57 | 512342.1 | 516370.58 | 520223.17 | 523674.86 | 526518.17 | 528759.26 | 530433.88 | 531895.02 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 0.01034% | 1.015% | 4.814% | 7.904% | 8.947% | 9.917% | 11.46% | 13.28% | 19.38% | 25.1% | 68.71% | 75.15% | 79.54% | 84.5% | 85.78% | 86.81% | 88.2% | 89.09% | 90.01% | 90.92% | 91.75% | 92.73% | 93.62% | 94.54% | 95.42% | 96.28% | 97.04% | 97.76% | 98.41% | 98.94% | 99.36% | 99.68% | 99.95% | 100% | 100% | 100% | 100%
23 | Engineering | 759 | 24-Jul-21 A | 2024-04-16 | 272905.67 | 23 |  | 738.36 | 10437.45 | 17187.65 | 19503.18 | 22148.38 | 28248.4 | 35180.11 | 44183.47 | 51552 | 91269.8 | 109988.97 | 126368.29 | 147766 | 167205.25 | 177378.34 | 187320.51 | 198974.86 | 206585.58 | 213289 | 217923.82 | 221504.6 | 224476.57 | 225728.07 | 226452.64 | 228308.76 | 228566.38 | 228751.73 | 228816.39 | 229219.58 | 229376.83 | 233916.08 | 247384.97 | 265806.54 | 272935.08 | 272935.08 | 272935.08 | 0% | 0.2705% | 3.824% | 6.297% | 7.146% | 8.115% | 10.35% | 12.89% | 16.19% | 18.89% | 33.44% | 40.3% | 46.3% | 54.14% | 61.26% | 64.99% | 68.63% | 72.9% | 75.69% | 78.15% | 79.84% | 81.16% | 82.25% | 82.7% | 82.97% | 83.65% | 83.74% | 83.81% | 83.84% | 83.98% | 84.04% | 85.7% | 90.64% | 97.39% | 100% | 100% | 100%
24 | Procurement | 672 | 01-Feb-22 A | 2024-01-20 | 7033236.1 | 24 | [10 empty] | 89553.95 | 229628.76 | 429557.98 | 755887.57 | 1071621.78 | 1430364.78 | 1844550.6 | 2250854.64 | 2654808.05 | 3067474.11 | 3455220.34 | 3924771.06 | 4381961.61 | 4808180.27 | 5202551.53 | 5619961.14 | 6013550.6 | 6264578.99 | 6508716.59 | 6828324.44 | 7030753.14 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.273% | 3.265% | 6.108% | 10.75% | 15.24% | 20.34% | 26.23% | 32% | 37.75% | 43.61% | 49.13% | 55.8% | 62.3% | 68.36% | 73.97% | 79.91% | 85.5% | 89.07% | 92.54% | 97.09% | 99.96% | 100% | 100% | 100% | 100% | 100% | 100%
25 | Construction | 950 | 20-Aug-21 A | 2024-04-07 | 2052025.78 | 25 |  |  | 5384.87 | 15032.39 | 19229.69 | 24380.45 | 41265.56 | 48841.12 | 56823.68 | 67842.65 | 77178.45 | 101490.58 | 120787.72 | 242834.86 | 278632.64 | 315865.87 | 374462.17 | 456393.08 | 532203.1 | 616863.74 | 678020.91 | 737761.23 | 876026.72 | 994800.8 | 1090047 | 1161016.97 | 1232041.97 | 1354663.19 | 1520723.63 | 1707400.22 | 1804026.68 | 1938333.32 | 2031988.33 | 2050986.61 | 2052025.78 | 2052025.78 | 2052025.78 | 0% | 0% | 0.2624% | 0.7326% | 0.9371% | 1.188% | 2.011% | 2.38% | 2.769% | 3.306% | 3.761% | 4.946% | 5.886% | 11.83% | 13.58% | 15.39% | 18.25% | 22.24% | 25.94% | 30.06% | 33.04% | 35.95% | 42.69% | 48.48% | 53.12% | 56.58% | 60.04% | 66.02% | 74.11% | 83.21% | 87.91% | 94.46% | 99.02% | 99.95% | 100% | 100% | 100%
26 | Commissioning | 537.25 | 2023-01-03 | 2024-06-23 | 109399.69 | 26 | 2023-01-01: 126.31; 2023-02-01: 330.05; 2023-03-01: 850.67; 2023-04-01: 1060.67; 2023-05-01: 1759.36; 2023-06-01: 4957.91; 2023-07-01: 5807.16; 2023-08-01: 6409.99; 2023-09-01: 6759.75; 2023-10-01: 7140.14; 2023-11-01: 7404.24; 2023-12-01: 7691.9; 2024-01-01: 7825.51; 2024-02-01: 8195.32; 2024-03-01: 14530.29; 2024-04-01: 24556.3; 2024-05-01: 87370.19; 2024-06-01: 109399.69 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1155% | 0.3017% | 0.7776% | 0.9695% | 1.608% | 4.532% | 5.308% | 5.859% | 6.179% | 6.527% | 6.768% | 7.031% | 7.153% | 7.491% | 13.28% | 22.45% | 79.86% | 100%
[7 empty] | 55.03 | 6139.74 | 41438.74 | 74282.73 | 86343.71 | 99303.42 | 130511.04 | 154676.5 | 204159.78 | 252985.18 | 623644.81 | 841026 | 1099961.2 | 1596132.58 | 1973927 | 2385578.45 | 2875670.69 | 3380290.76 | 3872549.99 | 4381591.5 | 4839755.62 | 5378337.73 | 5981706.51 | 6533534.52 | 7031778.65 | 7527436.13 | 7996939.52 | 8374976.83 | 8789071.61 | 9298866.65 | 9600607.81 | 9743744.89 | 9852699.74 | 9896699.87 | 9914893.59 | 9977707.48 | 9999736.98
[7 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE

## Data-Base-Weekly
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158
WBS | Activity ID | Original Duration | Start | Finish | Budgeted Labor Units | Spreadsheet Field | [158 empty] | 2021-06-19 | 2021-06-26 | 2021-07-03 | 2021-07-10 | 2021-07-17 | 2021-07-24 | 2021-07-31 | 2021-08-07 | 2021-08-14 | 2021-08-21 | 2021-08-28 | 2021-09-04 | 2021-09-11 | 2021-09-18 | 2021-09-25 | 2021-10-02 | 2021-10-09 | 2021-10-16 | 2021-10-23 | 2021-10-30 | 2021-11-06 | 2021-11-13 | 2021-11-20 | 2021-11-27 | 2021-12-04 | 2021-12-11 | 2021-12-18 | 2021-12-25 | 2022-01-01 | 2022-01-08 | 2022-01-15 | 2022-01-22 | 2022-01-29 | 2022-02-05 | 2022-02-12 | 2022-02-19 | 2022-02-26 | 2022-03-05 | 2022-03-12 | 2022-03-19 | 2022-03-26 | 2022-04-02 | 2022-04-09 | 2022-04-16 | 2022-04-23 | 2022-04-30 | 2022-05-07 | 2022-05-14 | 2022-05-21 | 2022-05-28 | 2022-06-04 | 2022-06-11 | 2022-06-18 | 2022-06-25 | 2022-07-02 | 2022-07-09 | 2022-07-16 | 2022-07-23 | 2022-07-30 | 2022-08-06 | 2022-08-13 | 2022-08-20 | 2022-08-27 | 2022-09-03 | 2022-09-10 | 2022-09-17 | 2022-09-24 | 2022-10-01 | 2022-10-08 | 2022-10-15 | 2022-10-22 | 2022-10-29 | 2022-11-05 | 2022-11-12 | 2022-11-19 | 2022-11-26 | 2022-12-03 | 2022-12-10 | 2022-12-17 | 2022-12-24 | 2022-12-31 | 2023-01-07 | 2023-01-14 | 2023-01-21 | 2023-01-28 | 2023-02-04 | 2023-02-11 | 2023-02-18 | 2023-02-25 | 2023-03-04 | 2023-03-11 | 2023-03-18 | 2023-03-25 | 2023-04-01 | 2023-04-08 | 2023-04-15 | 2023-04-22 | 2023-04-29 | 2023-05-06 | 2023-05-13 | 2023-05-20 | 2023-05-27 | 2023-06-03 | 2023-06-10 | 2023-06-17 | 2023-06-24 | 2023-07-01 | 2023-07-08 | 2023-07-15 | 2023-07-22 | 2023-07-29 | 2023-08-05 | 2023-08-12 | 2023-08-19 | 2023-08-26 | 2023-09-02 | 2023-09-09 | 2023-09-16 | 2023-09-23 | 2023-09-30 | 2023-10-07 | 2023-10-14 | 2023-10-21 | 2023-10-28 | 2023-11-04 | 2023-11-11 | 2023-11-18 | 2023-11-25 | 2023-12-02 | 2023-12-09 | 2023-12-16 | 2023-12-23 | 2023-12-30 | 2024-01-06 | 2024-01-13 | 2024-01-20 | 2024-01-27 | 2024-02-03 | 2024-02-10 | 2024-02-17 | 2024-02-24 | 2024-03-02 | 2024-03-09 | 2024-03-16 | 2024-03-23 | 2024-03-30 | 2024-04-06 | 2024-04-13 | 2024-04-20 | 2024-04-27 | 2024-05-04 | 2024-05-11 | 2024-05-18 | 2024-05-25 | 2024-06-01 | 2024-06-08 | 2024-06-15 | 2024-06-22 | time axis 2021-06-19 to 2024-06-22
3 | BINAK-Total (EPC) | 1097 | 23-Jun-21 A | 2024-06-23 | 10000000.07 | 3 | 20.33 | 70.22 | 133.86 | 369.75 | 513.55 | 5153.68 | 12131.71 | 19114.62 | 26101.19 | 36135.44 | 45378.29 | 53306.64 | 62390.21 | 69212.55 | 75121.36 | 77873.69 | 80037.17 | 82759.15 | 85758.99 | 87807.83 | 90001.06 | 92190.6 | 95639.43 | 102384.39 | 109772.06 | 118956.55 | 125427.2 | 130511.04 | 135201.05 | 140134.8 | 145497.91 | 151530.01 | 158976.6 | 170447.8 | 182809.41 | 197560.79 | 212933.91 | 230346.3 | 250968.64 | 252985.18 | 433175.7 | 506438.3 | 553493.54 | 585875.7 | 618603.61 | 662637.83 | 709547.82 | 757663.56 | 810302.08 | 863535.29 | 922949.38 | 980221.02 | 1041459.61 | 1109982.66 | 1185898.01 | 1315485.42 | 1463926.68 | 1569784.87 | 1658484.6 | 1738919.26 | 1819791.56 | 1909049.32 | 2000384.29 | 2091374.44 | 2186563.42 | 2290772.63 | 2385578.44 | 2488353.97 | 2604181.35 | 2716778.6 | 2827747.99 | 2939592.38 | 3056312.73 | 3186524.09 | 3300083.18 | 3412192.08 | 3520942.52 | 3632361.54 | 3744642.03 | 3856730.77 | 3972499.59 | 4086886.41 | 4204148.81 | 4315794.95 | 4430421.26 | 4544358.83 | 4657893.15 | 4772622.99 | 4889064.81 | 4997371.06 | 5118650.63 | 5247710.55 | 5378337.74 | 5503978.29 | 5645974.54 | 5807284.5 | 5945084.58 | 6071891.66 | 6206094.13 | 6336018.12 | 6451756.93 | 6566673.66 | 6684018.32 | 6800109.34 | 6916427.5 | 7031778.65 | 7150652.28 | 7264498.27 | 7377611.75 | 7482773.38 | 7584731.62 | 7702342.23 | 7819664.16 | 7915516.47 | 8010769.79 | 8096574.84 | 8181367.3 | 8265478.55 | 8359385.1 | 8452173.62 | 8532313.57 | 8618383.04 | 8729521.21 | 8835651.44 | 8950795.24 | 9072593.44 | 9221471.75 | 9306845.7 | 9346784.42 | 9383687.02 | 9432396.4 | 9591251.22 | 9623071.79 | 9658854.69 | 9693320.86 | 9724122.98 | 9751727.21 | 9782686.83 | 9813109.19 | 9837781.83 | 9855326.57 | 9868467.51 | 9878430.71 | 9887617.96 | 9894826.01 | 9901103.83 | 9906638.25 | 9909782.48 | 9911476.07 | 9918058.64 | 9925334.85 | 9932272.43 | 9955964.83 | 9977707.48 | 9987090.98 | 9993435.11 | 9998703.89 | 9999736.98 | 0.0002033% | 0.0007022% | 0.001339% | 0.003698% | 0.005136% | 0.05154% | 0.1213% | 0.1912% | 0.261% | 0.3614% | 0.4538% | 0.5331% | 0.6239% | 0.6921% | 0.7512% | 0.7788% | 0.8004% | 0.8276% | 0.8576% | 0.8781% | 0.9% | 0.9219% | 0.9564% | 1.024% | 1.098% | 1.19% | 1.254% | 1.305% | 1.352% | 1.401% | 1.455% | 1.515% | 1.59% | 1.705% | 1.828% | 1.976% | 2.129% | 2.304% | 2.51% | 2.53% | 4.332% | 5.065% | 5.535% | 5.859% | 6.186% | 6.627% | 7.096% | 7.577% | 8.103% | 8.636% | 9.23% | 9.802% | 10.41% | 11.1% | 11.86% | 13.16% | 14.64% | 15.7% | 16.59% | 17.39% | 18.2% | 19.09% | 20% | 20.91% | 21.87% | 22.91% | 23.86% | 24.88% | 26.04% | 27.17% | 28.28% | 29.4% | 30.56% | 31.87% | 33% | 34.12% | 35.21% | 36.32% | 37.45% | 38.57% | 39.73% | 40.87% | 42.04% | 43.16% | 44.31% | 45.44% | 46.58% | 47.73% | 48.89% | 49.98% | 51.19% | 52.48% | 53.78% | 55.04% | 56.46% | 58.07% | 59.45% | 60.72% | 62.06% | 63.36% | 64.52% | 65.67% | 66.84% | 68% | 69.17% | 70.32% | 71.51% | 72.65% | 73.78% | 74.83% | 75.85% | 77.03% | 78.2% | 79.16% | 80.11% | 80.97% | 81.82% | 82.66% | 83.6% | 84.52% | 85.33% | 86.19% | 87.3% | 88.36% | 89.51% | 90.73% | 92.22% | 93.07% | 93.47% | 93.84% | 94.33% | 95.92% | 96.23% | 96.59% | 96.94% | 97.24% | 97.52% | 97.83% | 98.13% | 98.38% | 98.56% | 98.69% | 98.79% | 98.88% | 98.95% | 99.01% | 99.07% | 99.1% | 99.12% | 99.18% | 99.26% | 99.33% | 99.56% | 99.78% | 99.87% | 99.94% | 99.99% | 100%
4 | GENERAL | 720 | 23-Jun-21 A | 2024-03-08 | 532432.82 | 4 | 20.33 | 70.22 | 133.86 | 369.75 | 513.55 | 4706.1 | 9573.07 | 14474.49 | 18846.41 | 23154.6 | 27387.11 | 31165.57 | 35045.55 | 38824.01 | 42602.47 | 44045.78 | 45201.43 | 46255.55 | 47309.67 | 48363.79 | 49519.44 | 50595.57 | 51789.35 | 53757.17 | 55515.67 | 57418.18 | 59219.16 | 60997.08 | 62746.18 | 64596.8 | 66345.9 | 68819.26 | 73103.28 | 81403.86 | 90345.63 | 99315.18 | 108236.73 | 118814.41 | 132556.82 | 133590.53 | 277452.22 | 322590.14 | 345934.83 | 355761.59 | 364501.41 | 374833.13 | 382591.6 | 389660.52 | 396471.69 | 402229.14 | 411988.8 | 416023.01 | 420155.69 | 423692.89 | 426812.63 | 446008.23 | 447688.38 | 449230.51 | 450988.59 | 452537.82 | 453985.54 | 455433.25 | 456880.96 | 458405.83 | 459504.56 | 460889.3 | 461969.46 | 465532.48 | 466714.17 | 467794.32 | 468874.48 | 469954.64 | 471136.32 | 472216.48 | 473296.64 | 474376.8 | 475558.48 | 476638.64 | 477718.8 | 478798.95 | 479980.64 | 481060.8 | 482140.95 | 483221.11 | 484301.27 | 485482.95 | 486563.11 | 487643.27 | 488723.43 | 489905.11 | 491289.85 | 492370.01 | 493450.17 | 494631.85 | 495712.01 | 496792.17 | 497872.32 | 498952.48 | 500134.17 | 501214.32 | 502294.48 | 503374.64 | 504556.32 | 505636.48 | 506716.64 | 507769.57 | 508802.07 | 509834.58 | 510867.09 | 511899.6 | 512878.1 | 513784.6 | 514691.1 | 515597.61 | 516499.28 | 517400.15 | 518605.6 | 519443.9 | 520125.76 | 520807.63 | 521520.72 | 522358.45 | 523196.17 | 524033.89 | 524843.76 | 525545.38 | 526069.19 | 526593 | 527107.69 | 527615.55 | 528123.4 | 528631.26 | 529036.52 | 529424.68 | 529812.84 | 530180.61 | 530535.18 | 530889.76 | 531244.33 | 531597.79 | 531944.56 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 0.00382% | 0.0132% | 0.02516% | 0.06948% | 0.09651% | 0.8844% | 1.799% | 2.72% | 3.542% | 4.351% | 5.147% | 5.857% | 6.586% | 7.296% | 8.006% | 8.277% | 8.494% | 8.692% | 8.89% | 9.089% | 9.306% | 9.508% | 9.732% | 10.1% | 10.43% | 10.79% | 11.13% | 11.46% | 11.79% | 12.14% | 12.47% | 12.93% | 13.74% | 15.3% | 16.98% | 18.66% | 20.34% | 22.33% | 24.91% | 25.1% | 52.14% | 60.62% | 65.01% | 66.85% | 68.5% | 70.44% | 71.9% | 73.23% | 74.51% | 75.59% | 77.42% | 78.18% | 78.96% | 79.62% | 80.21% | 83.81% | 84.13% | 84.42% | 84.75% | 85.04% | 85.31% | 85.59% | 85.86% | 86.14% | 86.35% | 86.61% | 86.81% | 87.48% | 87.71% | 87.91% | 88.11% | 88.31% | 88.54% | 88.74% | 88.94% | 89.15% | 89.37% | 89.57% | 89.77% | 89.98% | 90.2% | 90.4% | 90.6% | 90.81% | 91.01% | 91.23% | 91.44% | 91.64% | 91.84% | 92.06% | 92.32% | 92.53% | 92.73% | 92.95% | 93.15% | 93.36% | 93.56% | 93.76% | 93.99% | 94.19% | 94.39% | 94.59% | 94.82% | 95.02% | 95.22% | 95.42% | 95.61% | 95.81% | 96% | 96.2% | 96.38% | 96.55% | 96.72% | 96.89% | 97.06% | 97.23% | 97.46% | 97.61% | 97.74% | 97.87% | 98% | 98.16% | 98.32% | 98.48% | 98.63% | 98.76% | 98.86% | 98.96% | 99.05% | 99.15% | 99.25% | 99.34% | 99.42% | 99.49% | 99.56% | 99.63% | 99.7% | 99.76% | 99.83% | 99.9% | 99.96% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
5 | SUB-Surface DEVELOPMENT | 1011 | 24-Jul-21 A | 2024-06-07 | 1818441.18 | 5 | [5 empty] | 277.75 | 595.97 | 898.84 | 1696.53 | 5467.66 | 8593.16 | 10795.74 | 14001.46 | 16445.51 | 18175.52 | 19088.78 | 19687.69 | 20902.81 | 22405.48 | 22989.2 | 23581.85 | 24205.14 | 25916.99 | 30032.3 | 34875.49 | 41004.29 | 44350.26 | 45933.31 | 47427.14 | 49042.04 | 51286.59 | 53542.37 | 55155.91 | 56542.84 | 57945.71 | 61656.09 | 66043.75 | 70517.06 | 75051.64 | 75699.15 | 93715.27 | 110144.44 | 122160.22 | 133258.78 | 145864.36 | 166707.93 | 190856.7 | 213621.46 | 239928.6 | 265629.54 | 293690.61 | 325267.82 | 360881.4 | 403287.23 | 448189.08 | 528484.16 | 643373.42 | 711152.21 | 759367.78 | 800078.62 | 832947.78 | 863553.88 | 895792.21 | 925787.43 | 955411.79 | 991212.65 | 1019080.18 | 1051669.86 | 1099638.62 | 1144191.49 | 1184389.11 | 1222089.17 | 1262285.43 | 1310379.3 | 1342911.42 | 1368622.86 | 1389613.93 | 1413610.7 | 1437023.67 | 1460524.03 | 1487462.01 | 1512914.59 | 1539033.22 | 1554609.5 | 1569950.67 | 1584485.88 | 1600707.84 | 1619676.62 | 1641285.53 | 1652968.96 | 1665722.34 | 1678731.65 | 1690233.61 | 1699991.38 | 1713857.09 | 1727379.54 | 1733277.62 | 1736359.16 | 1739548.82 | 1746579.92 | 1750342.16 | 1753926.98 | 1759357.89 | 1762998.53 | 1767365.13 | 1772102.37 | 1776599.3 | 1779655.49 | 1782809.9 | 1786427.22 | 1789902.84 | 1790915.64 | 1791766.93 | 1792682.77 | 1793582.18 | 1794393.6 | 1795011.58 | 1795834.78 | 1796383.81 | 1797574.11 | 1797685.4 | 1797726.26 | 1797768.28 | 1797822.64 | 1798007.88 | 1798334.28 | 1798534.39 | 1798725.31 | 1798766.83 | 1798770.4 | 1798942.62 | 1799009.06 | 1799074.97 | 1799138.43 | 1799179.9 | 1799291.02 | 1799636.48 | 1803875.63 | 1808568.11 | 1811140.55 | 1812927.43 | 1816150.7 | 1817650.1 | 1817668.84 | 1817875.01 | 1817880.84 | 1817886.67 | 1818167.39 | 1818198.49 | 1818228.2 | 1818254.44 | 1818280.68 | 1818400.63 | 1818435.61 | 1818470.6 | 1818470.6 | 1818470.6 | 1818470.6 | 0% | 0% | 0% | 0% | 0% | 0.01527% | 0.03277% | 0.04943% | 0.09329% | 0.3007% | 0.4725% | 0.5937% | 0.77% | 0.9044% | 0.9995% | 1.05% | 1.083% | 1.149% | 1.232% | 1.264% | 1.297% | 1.331% | 1.425% | 1.652% | 1.918% | 2.255% | 2.439% | 2.526% | 2.608% | 2.697% | 2.82% | 2.944% | 3.033% | 3.109% | 3.187% | 3.391% | 3.632% | 3.878% | 4.127% | 4.163% | 5.154% | 6.057% | 6.718% | 7.328% | 8.021% | 9.167% | 10.5% | 11.75% | 13.19% | 14.61% | 16.15% | 17.89% | 19.85% | 22.18% | 24.65% | 29.06% | 35.38% | 39.11% | 41.76% | 44% | 45.8% | 47.49% | 49.26% | 50.91% | 52.54% | 54.51% | 56.04% | 57.83% | 60.47% | 62.92% | 65.13% | 67.2% | 69.41% | 72.06% | 73.85% | 75.26% | 76.42% | 77.74% | 79.02% | 80.32% | 81.8% | 83.2% | 84.63% | 85.49% | 86.33% | 87.13% | 88.02% | 89.07% | 90.26% | 90.9% | 91.6% | 92.32% | 92.95% | 93.48% | 94.25% | 94.99% | 95.32% | 95.48% | 95.66% | 96.05% | 96.25% | 96.45% | 96.75% | 96.95% | 97.19% | 97.45% | 97.7% | 97.87% | 98.04% | 98.24% | 98.43% | 98.48% | 98.53% | 98.58% | 98.63% | 98.68% | 98.71% | 98.76% | 98.79% | 98.85% | 98.86% | 98.86% | 98.86% | 98.86% | 98.87% | 98.89% | 98.9% | 98.91% | 98.92% | 98.92% | 98.93% | 98.93% | 98.93% | 98.94% | 98.94% | 98.95% | 98.96% | 99.2% | 99.46% | 99.6% | 99.7% | 99.87% | 99.95% | 99.96% | 99.97% | 99.97% | 99.97% | 99.98% | 99.99% | 99.99% | 99.99% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100%
6 | Package 01-New Well # W018S | 649 | 24-Jul-21 A | 2023-04-21 | 88589.59 | 6 | [5 empty] | 2.11 | 26.62 | 48.57 | 552.77 | 3941.47 | 6700.54 | 8532.1 | 11150.24 | 13001.4 | 14166.65 | 14515.14 | 14549.31 | 15197.34 | 16150.39 | 16184.1 | 16219.22 | 16262.01 | 16301.59 | 16552.72 | 17853.56 | 22148.48 | 23709.87 | 24052.17 | 24300.83 | 24636.13 | 24685.35 | 24723.54 | 24769.69 | 24815.72 | 24864.99 | 24918.23 | 25015.52 | 25112.25 | 25218.34 | 25232.4 | 27570.82 | 28833.82 | 29424.24 | 30029.52 | 31054.05 | 32833.62 | 34451.36 | 36653.79 | 38000.74 | 39340.34 | 40874.74 | 42682.59 | 44481.1 | 46603.41 | 48708.38 | 51373.51 | 54608.65 | 59824.38 | 62243.68 | 63062.75 | 63969.55 | 64938.93 | 65938.12 | 66884.66 | 67434.61 | 67976.1 | 68618.73 | 69233.22 | 69995.53 | 71501.39 | 73382.56 | 74889.77 | 76570.25 | 78246.99 | 78629.11 | 79552.42 | 80634.86 | 81794.79 | 82741.08 | 83423.46 | 83983.93 | 84801.41 | 85785.9 | 86494.54 | 86797.81 | 87091.19 | 87312.7 | 87647.17 | 88100.92 | 88353.21 | 88500.75 | 88550.29 | 88568.31 | 88580.54 | 88584.83 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 88590.08 | 0% | 0% | 0% | 0% | 0% | 0.002382% | 0.03005% | 0.05483% | 0.624% | 4.449% | 7.564% | 9.631% | 12.59% | 14.68% | 15.99% | 16.38% | 16.42% | 17.15% | 18.23% | 18.27% | 18.31% | 18.36% | 18.4% | 18.68% | 20.15% | 25% | 26.76% | 27.15% | 27.43% | 27.81% | 27.86% | 27.91% | 27.96% | 28.01% | 28.07% | 28.13% | 28.24% | 28.35% | 28.47% | 28.48% | 31.12% | 32.55% | 33.21% | 33.9% | 35.05% | 37.06% | 38.89% | 41.37% | 42.9% | 44.41% | 46.14% | 48.18% | 50.21% | 52.61% | 54.98% | 57.99% | 61.64% | 67.53% | 70.26% | 71.18% | 72.21% | 73.3% | 74.43% | 75.5% | 76.12% | 76.73% | 77.46% | 78.15% | 79.01% | 80.71% | 82.83% | 84.54% | 86.43% | 88.32% | 88.76% | 89.8% | 91.02% | 92.33% | 93.4% | 94.17% | 94.8% | 95.72% | 96.83% | 97.63% | 97.98% | 98.31% | 98.56% | 98.94% | 99.45% | 99.73% | 99.9% | 99.96% | 99.98% | 99.99% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | Package 02-New Well # W028 (Bangestan) | 449 | 24-Jul-21 A | 2023-05-22 | 128827.1 | 7 | [5 empty] | 0.92 | 22.32 | 41.55 | 61.49 | 92.67 | 145.55 | 224.26 | 446.38 | 846.17 | 1244.41 | 1642.64 | 2041.53 | 2442.33 | 2842.47 | 3242.85 | 3644.64 | 4050.22 | 5231.83 | 8353.24 | 11106.37 | 12137.74 | 13111.94 | 13537.43 | 13967.56 | 14411.15 | 15792.23 | 17196.4 | 17901.77 | 18347.05 | 18794.55 | 19241.23 | 19688.92 | 20173.97 | 20667.14 | 20737.65 | 29316.16 | 32304.42 | 34348.45 | 36910.71 | 39438.52 | 42429.89 | 45890.33 | 49202.6 | 52708 | 55876.89 | 59118.93 | 62943.69 | 65947.75 | 68772.15 | 71788.55 | 75341.06 | 79372.96 | 85156.26 | 90794.52 | 92535.96 | 95959.08 | 100997.27 | 103758.64 | 105232.88 | 106317.17 | 107228.29 | 108062.6 | 108848.13 | 109805.02 | 111437.25 | 113486.13 | 115204.25 | 116977.49 | 117964.49 | 118444.08 | 118774.28 | 119103.36 | 119434.81 | 119788.56 | 120160.34 | 120510.33 | 120969.78 | 121768.62 | 122708.39 | 124359.14 | 125387.47 | 126505.44 | 127071.44 | 127748.93 | 128184.06 | 128319.5 | 128338.72 | 128573.97 | 128599.5 | 128625.02 | 128646.56 | 128668.09 | 128719.37 | 128791.15 | 128819.87 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 128830.12 | 0% | 0% | 0% | 0% | 0% | 0.0007141% | 0.01733% | 0.03225% | 0.04773% | 0.07193% | 0.113% | 0.1741% | 0.3465% | 0.6568% | 0.9659% | 1.275% | 1.585% | 1.896% | 2.206% | 2.517% | 2.829% | 3.144% | 4.061% | 6.484% | 8.621% | 9.422% | 10.18% | 10.51% | 10.84% | 11.19% | 12.26% | 13.35% | 13.9% | 14.24% | 14.59% | 14.94% | 15.28% | 15.66% | 16.04% | 16.1% | 22.76% | 25.08% | 26.66% | 28.65% | 30.61% | 32.93% | 35.62% | 38.19% | 40.91% | 43.37% | 45.89% | 48.86% | 51.19% | 53.38% | 55.72% | 58.48% | 61.61% | 66.1% | 70.48% | 71.83% | 74.48% | 78.4% | 80.54% | 81.68% | 82.53% | 83.23% | 83.88% | 84.49% | 85.23% | 86.5% | 88.09% | 89.42% | 90.8% | 91.57% | 91.94% | 92.19% | 92.45% | 92.71% | 92.98% | 93.27% | 93.54% | 93.9% | 94.52% | 95.25% | 96.53% | 97.33% | 98.2% | 98.63% | 99.16% | 99.5% | 99.6% | 99.62% | 99.8% | 99.82% | 99.84% | 99.86% | 99.87% | 99.91% | 99.97% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | Package 03-New Well # W046S (Bangestan) | 514.25 | 24-Jul-21 A | 2023-08-16 | 592707.13 | 8 | [5 empty] | 13.41 | 54.57 | 92.89 | 132.55 | 188.63 | 234.02 | 278.64 | 323.91 | 342.75 | 358.05 | 373.35 | 388.65 | 404.02 | 416.08 | 428.35 | 442.67 | 458.63 | 474.97 | 492.53 | 511.49 | 535.5 | 564.42 | 595.42 | 623.26 | 656.67 | 684.3 | 713.47 | 744.07 | 773.53 | 804.05 | 3006.47 | 5938.61 | 8873.89 | 11814.52 | 12234.83 | 17278.66 | 27293.89 | 32862.89 | 38456.75 | 44367.5 | 54959.61 | 69343.32 | 81392.12 | 95524.09 | 108039.74 | 120226.62 | 131215.96 | 142501.53 | 155040.75 | 170017.18 | 212672.06 | 290837.76 | 321556.19 | 332566.46 | 343278.34 | 350010.16 | 356497.36 | 365131.35 | 373633.99 | 382149.24 | 390847.29 | 400037.26 | 413936.98 | 437448.96 | 454700.14 | 468599.33 | 482462.9 | 495130.06 | 504274.01 | 511171.16 | 517379.79 | 522924.8 | 529687.5 | 536655.23 | 539837.94 | 541762.17 | 543670.76 | 546725.81 | 549736.66 | 552715.4 | 554985.22 | 556560.74 | 558139.32 | 559927.06 | 560655.62 | 564719.14 | 570685.13 | 572511.76 | 573540.03 | 576831.7 | 583127.71 | 583134.04 | 583140.38 | 583159.39 | 583159.39 | 583159.39 | 583169.56 | 583891.4 | 585054.69 | 585616.72 | 587133.83 | 588955.16 | 590607.03 | 591847.73 | 592247.72 | 592523.22 | 592645.31 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 592719.43 | 0% | 0% | 0% | 0% | 0% | 0.002262% | 0.009207% | 0.01567% | 0.02236% | 0.03182% | 0.03948% | 0.04701% | 0.05465% | 0.05783% | 0.06041% | 0.06299% | 0.06557% | 0.06816% | 0.0702% | 0.07227% | 0.07468% | 0.07738% | 0.08013% | 0.0831% | 0.0863% | 0.09035% | 0.09523% | 0.1005% | 0.1052% | 0.1108% | 0.1155% | 0.1204% | 0.1255% | 0.1305% | 0.1357% | 0.5072% | 1.002% | 1.497% | 1.993% | 2.064% | 2.915% | 4.605% | 5.544% | 6.488% | 7.485% | 9.272% | 11.7% | 13.73% | 16.12% | 18.23% | 20.28% | 22.14% | 24.04% | 26.16% | 28.68% | 35.88% | 49.07% | 54.25% | 56.11% | 57.92% | 59.05% | 60.15% | 61.6% | 63.04% | 64.47% | 65.94% | 67.49% | 69.84% | 73.8% | 76.71% | 79.06% | 81.4% | 83.54% | 85.08% | 86.24% | 87.29% | 88.22% | 89.37% | 90.54% | 91.08% | 91.4% | 91.72% | 92.24% | 92.75% | 93.25% | 93.63% | 93.9% | 94.17% | 94.47% | 94.59% | 95.28% | 96.28% | 96.59% | 96.76% | 97.32% | 98.38% | 98.38% | 98.38% | 98.39% | 98.39% | 98.39% | 98.39% | 98.51% | 98.71% | 98.8% | 99.06% | 99.36% | 99.64% | 99.85% | 99.92% | 99.97% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | Package 04-New Well # W035 (Bangestan) | 616.75 | 24-Jul-21 A | 2023-11-26 | 156733.57 | 9 | [5 empty] | 1.07 | 22.61 | 42.03 | 62.19 | 93.61 | 114.72 | 137.6 | 231.2 | 323.24 | 413.73 | 504.21 | 594.7 | 685.19 | 773.72 | 862.44 | 952.53 | 1046.39 | 1450.41 | 2087.3 | 2725.43 | 3367.35 | 4009.79 | 4653.52 | 5295.9 | 5941.45 | 6582.08 | 7221.2 | 7867.56 | 8512.43 | 9156.55 | 9802.84 | 10449.86 | 11097.29 | 11746.72 | 11839.55 | 12448.96 | 13600.13 | 16371.19 | 17660.66 | 19019.02 | 20211.04 | 21403.56 | 22763.28 | 24395.4 | 25901.7 | 27573.97 | 29561.97 | 31497 | 33733.51 | 35637.92 | 37541.54 | 39445.15 | 41352.91 | 43461.15 | 45815.54 | 47958.26 | 50257.17 | 53248.03 | 56320.06 | 60935.36 | 70872.63 | 75457.84 | 76798.3 | 82726.07 | 91214.1 | 100354.88 | 107222.09 | 115308.1 | 123756.64 | 127257.26 | 128693.4 | 129542.66 | 130282.56 | 131046.73 | 132301.97 | 133526.76 | 135033.8 | 137413.07 | 139562.16 | 141167.25 | 142204.44 | 143314.25 | 144625.19 | 146031.92 | 146768.6 | 147542.62 | 148313.46 | 149004.85 | 149680.62 | 150307.89 | 151037.62 | 151356.61 | 151569.95 | 151719.13 | 152022.32 | 152025.22 | 152028.12 | 152031.02 | 152033.91 | 152036.81 | 152039.71 | 152042.61 | 152045.51 | 152333.5 | 153001.6 | 154552.37 | 154916.22 | 155228.57 | 155576.41 | 155756.72 | 155849.79 | 156085.13 | 156151.72 | 156157.57 | 156436.06 | 156467.21 | 156497.49 | 156523.77 | 156550.06 | 156642.99 | 156699.31 | 156734.35 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 156743.11 | 0% | 0% | 0% | 0% | 0% | 0.0006826% | 0.01442% | 0.02681% | 0.03968% | 0.05972% | 0.07319% | 0.08779% | 0.1475% | 0.2062% | 0.264% | 0.3217% | 0.3794% | 0.4371% | 0.4936% | 0.5502% | 0.6077% | 0.6676% | 0.9253% | 1.332% | 1.739% | 2.148% | 2.558% | 2.969% | 3.379% | 3.791% | 4.199% | 4.607% | 5.019% | 5.431% | 5.842% | 6.254% | 6.667% | 7.08% | 7.494% | 7.553% | 7.942% | 8.677% | 10.44% | 11.27% | 12.13% | 12.89% | 13.66% | 14.52% | 15.56% | 16.52% | 17.59% | 18.86% | 20.09% | 21.52% | 22.74% | 23.95% | 25.17% | 26.38% | 27.73% | 29.23% | 30.6% | 32.06% | 33.97% | 35.93% | 38.88% | 45.22% | 48.14% | 49% | 52.78% | 58.19% | 64.03% | 68.41% | 73.57% | 78.96% | 81.19% | 82.1% | 82.65% | 83.12% | 83.61% | 84.41% | 85.19% | 86.15% | 87.67% | 89.04% | 90.06% | 90.72% | 91.43% | 92.27% | 93.17% | 93.64% | 94.13% | 94.62% | 95.06% | 95.49% | 95.89% | 96.36% | 96.56% | 96.7% | 96.79% | 96.99% | 96.99% | 96.99% | 96.99% | 97% | 97% | 97% | 97% | 97% | 97.19% | 97.61% | 98.6% | 98.83% | 99.03% | 99.26% | 99.37% | 99.43% | 99.58% | 99.62% | 99.63% | 99.8% | 99.82% | 99.84% | 99.86% | 99.88% | 99.94% | 99.97% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Package 05-New Well # W008N | 692.75 | 24-Jul-21 A | 2024-02-10 | 69431.13 | 10 | [5 empty] | 1.05 | 22.91 | 41.62 | 61.74 | 92.45 | 113.5 | 136.33 | 159.44 | 169.25 | 177.46 | 185.67 | 193.88 | 202.09 | 208.35 | 214.79 | 222.61 | 234.25 | 246.54 | 275.9 | 347.77 | 422.69 | 497.04 | 572.67 | 646.97 | 724.05 | 796.6 | 867.2 | 943.55 | 1017.39 | 1090.44 | 1165.63 | 1241.76 | 1318.34 | 1396.72 | 1407.97 | 1588.86 | 1757.65 | 1929.19 | 2102.67 | 2391.04 | 3010.69 | 3213.98 | 3485.4 | 3848.13 | 4173.29 | 4553.1 | 5119.12 | 5630.75 | 6246.23 | 6734.8 | 7222.92 | 7715.68 | 8207.94 | 8707.3 | 9228.64 | 9726.17 | 10225.77 | 10732.22 | 11240.63 | 11771.89 | 12346.95 | 13453.5 | 14629.71 | 15897.48 | 17378.3 | 18882.93 | 20422.49 | 21917.62 | 23062.4 | 24197.45 | 25653.26 | 27253.82 | 32281.89 | 36409.61 | 38835.34 | 41403.26 | 44235.51 | 47700.01 | 50293.09 | 52019.04 | 54662.79 | 56126.71 | 56631.84 | 58095.47 | 59614.31 | 59959.3 | 60337.06 | 60797.34 | 61256.94 | 61598.8 | 61878.09 | 61991.72 | 62077.85 | 62490.32 | 62915.11 | 63341.26 | 63771.88 | 64201.97 | 64519.74 | 64749.62 | 65022.86 | 65230.97 | 65263.69 | 65636.88 | 65974.69 | 66246.18 | 66278.9 | 66323.94 | 66399.77 | 66588.96 | 66798.16 | 66927.22 | 67271.87 | 67566.58 | 68299.7 | 68324.86 | 68326.44 | 68328.03 | 68329.61 | 68420.13 | 68688.41 | 68851.68 | 69032.04 | 69072.02 | 69075.6 | 69246.13 | 69265.2 | 69283.74 | 69299.84 | 69315.93 | 69388.93 | 69410.39 | 69431.85 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 69434.15 | 0% | 0% | 0% | 0% | 0% | 0.001512% | 0.033% | 0.05994% | 0.08892% | 0.1331% | 0.1635% | 0.1963% | 0.2296% | 0.2438% | 0.2556% | 0.2674% | 0.2792% | 0.2911% | 0.3001% | 0.3093% | 0.3206% | 0.3374% | 0.3551% | 0.3974% | 0.5009% | 0.6088% | 0.7158% | 0.8248% | 0.9318% | 1.043% | 1.147% | 1.249% | 1.359% | 1.465% | 1.57% | 1.679% | 1.788% | 1.899% | 2.012% | 2.028% | 2.288% | 2.531% | 2.778% | 3.028% | 3.444% | 4.336% | 4.629% | 5.02% | 5.542% | 6.01% | 6.557% | 7.373% | 8.109% | 8.996% | 9.7% | 10.4% | 11.11% | 11.82% | 12.54% | 13.29% | 14.01% | 14.73% | 15.46% | 16.19% | 16.95% | 17.78% | 19.38% | 21.07% | 22.9% | 25.03% | 27.2% | 29.41% | 31.57% | 33.21% | 34.85% | 36.95% | 39.25% | 46.49% | 52.44% | 55.93% | 59.63% | 63.71% | 68.7% | 72.43% | 74.92% | 78.73% | 80.83% | 81.56% | 83.67% | 85.86% | 86.35% | 86.9% | 87.56% | 88.22% | 88.72% | 89.12% | 89.28% | 89.41% | 90% | 90.61% | 91.22% | 91.85% | 92.46% | 92.92% | 93.25% | 93.65% | 93.95% | 93.99% | 94.53% | 95.02% | 95.41% | 95.46% | 95.52% | 95.63% | 95.9% | 96.2% | 96.39% | 96.89% | 97.31% | 98.37% | 98.4% | 98.4% | 98.41% | 98.41% | 98.54% | 98.93% | 99.16% | 99.42% | 99.48% | 99.48% | 99.73% | 99.76% | 99.78% | 99.81% | 99.83% | 99.93% | 99.97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Package 06-New Well # W007S/Manifold Extension (Bangestan) | 811 | 24-Jul-21 A | 2024-06-07 | 236214.84 | 11 | [5 empty] | 8.09 | 69.53 | 129.78 | 192.47 | 271.21 | 338.49 | 404.13 | 470.01 | 490.61 | 504.35 | 518.1 | 531.67 | 545.25 | 557.26 | 573 | 590.65 | 609.26 | 628.6 | 649.12 | 671.16 | 694.18 | 717.69 | 742.56 | 772.92 | 800.15 | 828.72 | 854.01 | 881.52 | 911.85 | 943.62 | 980.7 | 1021.81 | 1081.99 | 1156.87 | 1167.84 | 1642.96 | 2150.45 | 2678.51 | 3206.27 | 4049.41 | 6095.93 | 6883.11 | 7739.13 | 8870.28 | 10053.99 | 11630.4 | 13651.98 | 15561.93 | 18251.02 | 20371.87 | 22458.53 | 24529.65 | 27276.51 | 31854.61 | 36261.13 | 40601.44 | 44838.07 | 48726.74 | 52639.83 | 56400.45 | 60153.4 | 63388.93 | 67035.2 | 71225.77 | 76431.65 | 82201.96 | 89218.34 | 97674.27 | 111525.23 | 119732.2 | 123019.43 | 125935.63 | 128945.33 | 131808.22 | 135352.64 | 139368.09 | 143800.52 | 147986.35 | 151379.03 | 156957.25 | 162629.31 | 167316.89 | 171740.5 | 175565.02 | 178151.32 | 181643.66 | 185102.56 | 187915.02 | 189414.29 | 190832.93 | 192704.16 | 193620.98 | 194330.64 | 195083.47 | 195731.07 | 196427.92 | 197540.25 | 198791.03 | 200567.72 | 203485.3 | 206147.94 | 208164.18 | 209165.51 | 210218.37 | 212378.88 | 213565.36 | 213937.42 | 214309.47 | 214755.95 | 215270.48 | 215710.72 | 215943.78 | 216335.22 | 216582.22 | 216760.93 | 216815.9 | 216824.9 | 216839.04 | 216865.54 | 216867.34 | 216869.13 | 216870.92 | 216872.72 | 216874.26 | 216874.26 | 216875.95 | 216923.31 | 216970.68 | 217018.04 | 217043.42 | 217081.53 | 217405.54 | 221623.23 | 226313.41 | 228885.85 | 230672.74 | 233896 | 235395.4 | 235414.14 | 235620.31 | 235626.14 | 235631.97 | 235912.69 | 235943.79 | 235973.5 | 235999.74 | 236025.98 | 236145.93 | 236180.92 | 236215.9 | 236215.9 | 236215.9 | 236215.9 | 0% | 0% | 0% | 0% | 0% | 0.003425% | 0.02943% | 0.05494% | 0.08148% | 0.1148% | 0.1433% | 0.1711% | 0.199% | 0.2077% | 0.2135% | 0.2193% | 0.2251% | 0.2308% | 0.2359% | 0.2426% | 0.25% | 0.2579% | 0.2661% | 0.2748% | 0.2841% | 0.2939% | 0.3038% | 0.3144% | 0.3272% | 0.3387% | 0.3508% | 0.3615% | 0.3732% | 0.386% | 0.3995% | 0.4152% | 0.4326% | 0.4581% | 0.4898% | 0.4944% | 0.6955% | 0.9104% | 1.134% | 1.357% | 1.714% | 2.581% | 2.914% | 3.276% | 3.755% | 4.256% | 4.924% | 5.779% | 6.588% | 7.726% | 8.624% | 9.508% | 10.38% | 11.55% | 13.49% | 15.35% | 17.19% | 18.98% | 20.63% | 22.28% | 23.88% | 25.47% | 26.84% | 28.38% | 30.15% | 32.36% | 34.8% | 37.77% | 41.35% | 47.21% | 50.69% | 52.08% | 53.31% | 54.59% | 55.8% | 57.3% | 59% | 60.88% | 62.65% | 64.09% | 66.45% | 68.85% | 70.83% | 72.7% | 74.32% | 75.42% | 76.9% | 78.36% | 79.55% | 80.19% | 80.79% | 81.58% | 81.97% | 82.27% | 82.59% | 82.86% | 83.16% | 83.63% | 84.16% | 84.91% | 86.14% | 87.27% | 88.12% | 88.55% | 88.99% | 89.91% | 90.41% | 90.57% | 90.73% | 90.92% | 91.13% | 91.32% | 91.42% | 91.58% | 91.69% | 91.76% | 91.79% | 91.79% | 91.8% | 91.81% | 91.81% | 91.81% | 91.81% | 91.81% | 91.81% | 91.81% | 91.81% | 91.83% | 91.85% | 91.87% | 91.88% | 91.9% | 92.04% | 93.82% | 95.81% | 96.9% | 97.65% | 99.02% | 99.65% | 99.66% | 99.75% | 99.75% | 99.75% | 99.87% | 99.88% | 99.9% | 99.91% | 99.92% | 99.97% | 99.99% | 100% | 100% | 100% | 100%
12 | Package 07-Workover # 14 | 497 | 24-Jul-21 A | 2023-07-29 | 140256.51 | 12 | [5 empty] | 62.76 | 94.32 | 125.56 | 158.28 | 196.84 | 236.51 | 270.59 | 304.97 | 317.92 | 327.61 | 337.29 | 346.86 | 356.5 | 364.15 | 370.75 | 377.77 | 387.49 | 398.17 | 408.78 | 419.35 | 430.02 | 441.32 | 452.33 | 463.39 | 477.61 | 489.84 | 503.18 | 524.51 | 554.81 | 587.49 | 654.32 | 696.71 | 745.54 | 799.36 | 807.09 | 1022.52 | 1120.14 | 1220.28 | 1324.27 | 1453.08 | 1576.35 | 1673.35 | 2093.7 | 3341.4 | 5720.02 | 8884.58 | 12647.12 | 19357.89 | 30120.44 | 40195.96 | 54387 | 65908.14 | 73571.89 | 83084.5 | 89409.65 | 92333.71 | 94022.46 | 95842.19 | 96989.14 | 97739.71 | 98317.17 | 98858.9 | 100530.51 | 101678.41 | 102260.62 | 102647.85 | 102711.67 | 104490.31 | 111996.34 | 116072.69 | 117079.45 | 118175.01 | 119950.49 | 121234.02 | 123605.85 | 130369.62 | 134596.77 | 134788.42 | 135232.07 | 135451.7 | 135627.24 | 135794.14 | 135961.04 | 136127.95 | 136294.85 | 136461.75 | 136879 | 137730.58 | 138384.55 | 138388.73 | 138392.9 | 139232.48 | 139673.12 | 139688.44 | 139764.46 | 139838.71 | 139842.83 | 140038.87 | 140060.87 | 140082.38 | 140100.94 | 140119.5 | 140203.47 | 140228.22 | 140252.97 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 140256.5 | 0% | 0% | 0% | 0% | 0% | 0.04475% | 0.06725% | 0.08952% | 0.1129% | 0.1403% | 0.1686% | 0.1929% | 0.2174% | 0.2267% | 0.2336% | 0.2405% | 0.2473% | 0.2542% | 0.2596% | 0.2643% | 0.2693% | 0.2763% | 0.2839% | 0.2915% | 0.299% | 0.3066% | 0.3147% | 0.3225% | 0.3304% | 0.3405% | 0.3492% | 0.3588% | 0.374% | 0.3956% | 0.4189% | 0.4665% | 0.4967% | 0.5316% | 0.5699% | 0.5754% | 0.729% | 0.7986% | 0.87% | 0.9442% | 1.036% | 1.124% | 1.193% | 1.493% | 2.382% | 4.078% | 6.335% | 9.017% | 13.8% | 21.48% | 28.66% | 38.78% | 46.99% | 52.46% | 59.24% | 63.75% | 65.83% | 67.04% | 68.33% | 69.15% | 69.69% | 70.1% | 70.48% | 71.68% | 72.49% | 72.91% | 73.19% | 73.23% | 74.5% | 79.85% | 82.76% | 83.48% | 84.26% | 85.52% | 86.44% | 88.13% | 92.95% | 95.96% | 96.1% | 96.42% | 96.57% | 96.7% | 96.82% | 96.94% | 97.06% | 97.18% | 97.29% | 97.59% | 98.2% | 98.67% | 98.67% | 98.67% | 99.27% | 99.58% | 99.59% | 99.65% | 99.7% | 99.71% | 99.84% | 99.86% | 99.88% | 99.89% | 99.9% | 99.96% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
13 | Package 08-Workover # 12 | 477.75 | 24-Jul-21 A | 2023-07-10 | 113892.31 | 13 | [5 empty] | 62.79 | 94.36 | 125.62 | 158.35 | 196.93 | 236.61 | 270.7 | 305.1 | 318.06 | 327.76 | 337.46 | 347.03 | 356.69 | 364.35 | 370.97 | 377.34 | 385.93 | 395.47 | 404.95 | 414.38 | 423.91 | 434.08 | 443.95 | 453.86 | 466.92 | 478 | 490.18 | 510.35 | 539.49 | 571.02 | 632.12 | 666.95 | 708.23 | 754.51 | 761.15 | 985.08 | 1079.36 | 1175.51 | 1272.57 | 1642.98 | 2969.84 | 5228.97 | 7375.61 | 10048.51 | 12567.56 | 15148.86 | 19395.73 | 24159.11 | 28539.65 | 34029.92 | 40274.79 | 46505.87 | 53048.67 | 58360.62 | 64000.98 | 68205.09 | 70343.39 | 71929.36 | 72795.11 | 73291.1 | 73587.74 | 73876.44 | 74206.46 | 74699.17 | 75804.05 | 76843.14 | 77952.61 | 78759.17 | 79479.51 | 80198.89 | 80938.56 | 81676.34 | 82767.11 | 85128.06 | 91442.5 | 97984.78 | 103612.57 | 107421.29 | 107753.21 | 108003.72 | 108149.87 | 108296.01 | 108460.05 | 108841.81 | 111133.48 | 112582.65 | 112586.12 | 112589.6 | 112593.08 | 113217.63 | 113412.6 | 113417.81 | 113539.58 | 113543.05 | 113704.38 | 113722.91 | 113741.44 | 113757.38 | 113773.01 | 113795.53 | 113863.27 | 113884.11 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 113892.3 | 0% | 0% | 0% | 0% | 0% | 0.05513% | 0.08285% | 0.1103% | 0.139% | 0.1729% | 0.2077% | 0.2377% | 0.2679% | 0.2793% | 0.2878% | 0.2963% | 0.3047% | 0.3132% | 0.3199% | 0.3257% | 0.3313% | 0.3389% | 0.3472% | 0.3556% | 0.3638% | 0.3722% | 0.3811% | 0.3898% | 0.3985% | 0.41% | 0.4197% | 0.4304% | 0.4481% | 0.4737% | 0.5014% | 0.555% | 0.5856% | 0.6218% | 0.6625% | 0.6683% | 0.8649% | 0.9477% | 1.032% | 1.117% | 1.443% | 2.608% | 4.591% | 6.476% | 8.823% | 11.03% | 13.3% | 17.03% | 21.21% | 25.06% | 29.88% | 35.36% | 40.83% | 46.58% | 51.24% | 56.19% | 59.89% | 61.76% | 63.16% | 63.92% | 64.35% | 64.61% | 64.87% | 65.15% | 65.59% | 66.56% | 67.47% | 68.44% | 69.15% | 69.78% | 70.42% | 71.07% | 71.71% | 72.67% | 74.74% | 80.29% | 86.03% | 90.97% | 94.32% | 94.61% | 94.83% | 94.96% | 95.09% | 95.23% | 95.57% | 97.58% | 98.85% | 98.85% | 98.86% | 98.86% | 99.41% | 99.58% | 99.58% | 99.69% | 99.69% | 99.84% | 99.85% | 99.87% | 99.88% | 99.9% | 99.92% | 99.97% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
14 | Package 09-Workover # 15 | 524 | 24-Jul-21 A | 2023-08-25 | 170781.36 | 14 | [5 empty] | 62.79 | 94.36 | 125.62 | 158.35 | 196.93 | 236.61 | 270.7 | 305.1 | 318.06 | 327.76 | 337.46 | 347.03 | 356.69 | 364.35 | 370.97 | 377.08 | 385.03 | 393.95 | 402.8 | 411.6 | 420.51 | 430.05 | 439.3 | 448.58 | 461.01 | 471.47 | 483.01 | 502.56 | 531.08 | 561.98 | 622.45 | 656.66 | 697.31 | 742.96 | 749.52 | 888.15 | 937.68 | 988.31 | 1038.95 | 1089.65 | 1182.85 | 1295.17 | 1401.04 | 1632.15 | 2314.01 | 3902.07 | 5980.65 | 9162.88 | 12376.71 | 15944.29 | 20322.53 | 25971.75 | 31237.88 | 36880.23 | 43407.69 | 49362.74 | 54530.48 | 60902.26 | 68710.42 | 76317.9 | 83707.72 | 88841.35 | 95611.4 | 102650.52 | 106787.74 | 108046.07 | 109435.36 | 110181.07 | 111236.03 | 114389.5 | 117079.63 | 120110.86 | 121845.68 | 122666.28 | 123327.61 | 123797.03 | 124234.01 | 124670.99 | 125107.97 | 125667.42 | 126351.87 | 131158.45 | 139891.81 | 150297.67 | 152577.36 | 154415.78 | 156249.09 | 157383.87 | 158099.4 | 159690.35 | 160693.33 | 162253.71 | 162829.98 | 163168.89 | 167553.17 | 169510.9 | 169858.02 | 170087.19 | 170265.69 | 170270.74 | 170275.78 | 170518.83 | 170545.75 | 170571.48 | 170594.19 | 170616.91 | 170720.77 | 170751.06 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 170781.35 | 0% | 0% | 0% | 0% | 0% | 0.03677% | 0.05525% | 0.07356% | 0.09272% | 0.1153% | 0.1385% | 0.1585% | 0.1786% | 0.1862% | 0.1919% | 0.1976% | 0.2032% | 0.2089% | 0.2133% | 0.2172% | 0.2208% | 0.2255% | 0.2307% | 0.2359% | 0.241% | 0.2462% | 0.2518% | 0.2572% | 0.2627% | 0.2699% | 0.2761% | 0.2828% | 0.2943% | 0.311% | 0.3291% | 0.3645% | 0.3845% | 0.4083% | 0.435% | 0.4389% | 0.5201% | 0.5491% | 0.5787% | 0.6084% | 0.638% | 0.6926% | 0.7584% | 0.8204% | 0.9557% | 1.355% | 2.285% | 3.502% | 5.365% | 7.247% | 9.336% | 11.9% | 15.21% | 18.29% | 21.59% | 25.42% | 28.9% | 31.93% | 35.66% | 40.23% | 44.69% | 49.01% | 52.02% | 55.98% | 60.11% | 62.53% | 63.27% | 64.08% | 64.52% | 65.13% | 66.98% | 68.56% | 70.33% | 71.35% | 71.83% | 72.21% | 72.49% | 72.74% | 73% | 73.26% | 73.58% | 73.98% | 76.8% | 81.91% | 88.01% | 89.34% | 90.42% | 91.49% | 92.16% | 92.57% | 93.51% | 94.09% | 95.01% | 95.34% | 95.54% | 98.11% | 99.26% | 99.46% | 99.59% | 99.7% | 99.7% | 99.7% | 99.85% | 99.86% | 99.88% | 99.89% | 99.9% | 99.96% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | Package 10-Workover # 05 | 552.5 | 24-Jul-21 A | 2023-09-23 | 121007.65 | 15 | [5 empty] | 62.79 | 94.36 | 125.62 | 158.35 | 196.93 | 236.61 | 270.7 | 305.1 | 318.06 | 327.76 | 337.46 | 347.03 | 356.69 | 364.35 | 370.97 | 377.34 | 385.93 | 395.47 | 404.95 | 414.38 | 423.91 | 434.08 | 443.95 | 453.86 | 466.92 | 478 | 490.18 | 510.35 | 539.49 | 571.02 | 632.12 | 666.95 | 708.23 | 754.51 | 761.15 | 973.09 | 1066.89 | 1161.65 | 1256.4 | 1359.12 | 1438.1 | 1473.55 | 1514.78 | 1559.91 | 1642.01 | 1777.33 | 2069.01 | 2581.46 | 3603.36 | 4760.2 | 6890.22 | 8477.82 | 9919.56 | 11414.7 | 13077.95 | 14821.59 | 16902.99 | 19583.31 | 21340.7 | 23054.36 | 26175.36 | 28484.64 | 30839.97 | 33511.69 | 36676.25 | 39944.27 | 42569.67 | 45277.07 | 48837.67 | 52819.08 | 60452.64 | 64256.56 | 66620.55 | 69545.86 | 72236.37 | 74756.05 | 77959.47 | 84772.77 | 86342.37 | 86811.94 | 87396.47 | 88322.53 | 89508.25 | 90548.8 | 91236.14 | 91577.19 | 91690.23 | 95158.31 | 99842.42 | 105779.21 | 108896.49 | 111012.1 | 111888.21 | 113314.9 | 114320.07 | 114895.64 | 116554.67 | 119138.83 | 119302.69 | 119907.84 | 120097.83 | 120263.73 | 120512.02 | 120661.23 | 120664.65 | 120829.79 | 120848.03 | 120865.46 | 120880.85 | 120896.24 | 120965.13 | 120985.65 | 121006.18 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 121007.64 | 0% | 0% | 0% | 0% | 0% | 0.05189% | 0.07798% | 0.1038% | 0.1309% | 0.1627% | 0.1955% | 0.2237% | 0.2521% | 0.2628% | 0.2709% | 0.2789% | 0.2868% | 0.2948% | 0.3011% | 0.3066% | 0.3118% | 0.3189% | 0.3268% | 0.3346% | 0.3424% | 0.3503% | 0.3587% | 0.3669% | 0.3751% | 0.3859% | 0.395% | 0.4051% | 0.4218% | 0.4458% | 0.4719% | 0.5224% | 0.5512% | 0.5853% | 0.6235% | 0.629% | 0.8042% | 0.8817% | 0.96% | 1.038% | 1.123% | 1.188% | 1.218% | 1.252% | 1.289% | 1.357% | 1.469% | 1.71% | 2.133% | 2.978% | 3.934% | 5.694% | 7.006% | 8.197% | 9.433% | 10.81% | 12.25% | 13.97% | 16.18% | 17.64% | 19.05% | 21.63% | 23.54% | 25.49% | 27.69% | 30.31% | 33.01% | 35.18% | 37.42% | 40.36% | 43.65% | 49.96% | 53.1% | 55.05% | 57.47% | 59.7% | 61.78% | 64.43% | 70.06% | 71.35% | 71.74% | 72.22% | 72.99% | 73.97% | 74.83% | 75.4% | 75.68% | 75.77% | 78.64% | 82.51% | 87.42% | 89.99% | 91.74% | 92.46% | 93.64% | 94.47% | 94.95% | 96.32% | 98.46% | 98.59% | 99.09% | 99.25% | 99.39% | 99.59% | 99.71% | 99.72% | 99.85% | 99.87% | 99.88% | 99.9% | 99.91% | 99.96% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
16 | SURFACE DEVELOPMENT | 827 | 24-Jul-21 A | 2024-06-23 | 7649126.06 | 16 | [5 empty] | 169.84 | 1962.66 | 3741.28 | 5558.25 | 7513.18 | 9398.02 | 11345.33 | 13343.2 | 13943.03 | 14343.37 | 14739.13 | 15148.05 | 15600.8 | 16043.85 | 16454.84 | 16899.77 | 17389.9 | 17933.08 | 18594.92 | 19380.9 | 20534.08 | 21857.78 | 23580.65 | 25027.73 | 26495.95 | 27865.43 | 29168.37 | 30717.41 | 32501.1 | 34518.07 | 36589.52 | 38653.43 | 41014.83 | 43360.18 | 43695.5 | 62008.21 | 73703.73 | 85398.49 | 96855.33 | 108237.84 | 121096.77 | 136099.53 | 154381.59 | 173901.79 | 195676.61 | 217269.97 | 238930.2 | 260422.52 | 283002.55 | 310896.31 | 340993.03 | 372864.88 | 409402.15 | 448128.23 | 486302.81 | 532858.24 | 590062.19 | 647711.12 | 707181.18 | 771647.07 | 838670.69 | 904528.8 | 971151.63 | 1037828.56 | 1104792.79 | 1174484.4 | 1247548.58 | 1322890.97 | 1403928.31 | 1483875.12 | 1569192.42 | 1655770.11 | 1742112.21 | 1829899.57 | 1917407.79 | 2005056.93 | 2092911.02 | 2182974.63 | 2277964.34 | 2376169.33 | 2474390 | 2570622.2 | 2665303.11 | 2759055.85 | 2854496.99 | 2961638.44 | 3076608.88 | 3194653.96 | 3309355.05 | 3436405.44 | 3583112.8 | 3713934.64 | 3836580.02 | 3966411.14 | 4088223.87 | 4199120.29 | 4309372.04 | 4420104.11 | 4531474.32 | 4642345.72 | 4751906.71 | 4865250.9 | 4975008.19 | 5083934.76 | 5184446.57 | 5281950.67 | 5397641.98 | 5513206.13 | 5607236.09 | 5700688.32 | 5784781.09 | 5867750.12 | 5950199.88 | 6042875.53 | 6133791.88 | 6213107.44 | 6298298.34 | 6408556.76 | 6513794.91 | 6627943.6 | 6748713.78 | 6896868.17 | 6981527.39 | 7020909.9 | 7057301.07 | 7105330.38 | 7263610.9 | 7294960.3 | 7330291.58 | 7364328.12 | 7394651.35 | 7421555.55 | 7447921.45 | 7473296.75 | 7495043.49 | 7510454.57 | 7520176.48 | 7528640.29 | 7537808.79 | 7544810.67 | 7551082.66 | 7556611.25 | 7559474.76 | 7561137.25 | 7567690.11 | 7574940.08 | 7581851.42 | 7605423.87 | 7627131.54 | 7636480.05 | 7642824.18 | 7648092.96 | 7649126.05 | 0% | 0% | 0% | 0% | 0% | 0.00222% | 0.02566% | 0.04891% | 0.07267% | 0.09822% | 0.1229% | 0.1483% | 0.1744% | 0.1823% | 0.1875% | 0.1927% | 0.198% | 0.204% | 0.2097% | 0.2151% | 0.2209% | 0.2273% | 0.2344% | 0.2431% | 0.2534% | 0.2685% | 0.2858% | 0.3083% | 0.3272% | 0.3464% | 0.3643% | 0.3813% | 0.4016% | 0.4249% | 0.4513% | 0.4783% | 0.5053% | 0.5362% | 0.5669% | 0.5712% | 0.8107% | 0.9636% | 1.116% | 1.266% | 1.415% | 1.583% | 1.779% | 2.018% | 2.273% | 2.558% | 2.84% | 3.124% | 3.405% | 3.7% | 4.064% | 4.458% | 4.875% | 5.352% | 5.859% | 6.358% | 6.966% | 7.714% | 8.468% | 9.245% | 10.09% | 10.96% | 11.83% | 12.7% | 13.57% | 14.44% | 15.35% | 16.31% | 17.29% | 18.35% | 19.4% | 20.51% | 21.65% | 22.78% | 23.92% | 25.07% | 26.21% | 27.36% | 28.54% | 29.78% | 31.06% | 32.35% | 33.61% | 34.84% | 36.07% | 37.32% | 38.72% | 40.22% | 41.76% | 43.26% | 44.93% | 46.84% | 48.55% | 50.16% | 51.85% | 53.45% | 54.9% | 56.34% | 57.79% | 59.24% | 60.69% | 62.12% | 63.61% | 65.04% | 66.46% | 67.78% | 69.05% | 70.57% | 72.08% | 73.31% | 74.53% | 75.63% | 76.71% | 77.79% | 79% | 80.19% | 81.23% | 82.34% | 83.78% | 85.16% | 86.65% | 88.23% | 90.17% | 91.27% | 91.79% | 92.26% | 92.89% | 94.96% | 95.37% | 95.83% | 96.28% | 96.67% | 97.02% | 97.37% | 97.7% | 97.99% | 98.19% | 98.31% | 98.42% | 98.54% | 98.64% | 98.72% | 98.79% | 98.83% | 98.85% | 98.94% | 99.03% | 99.12% | 99.43% | 99.71% | 99.83% | 99.92% | 99.99% | 100%
17 | Package 11- EPC Pipeline 8" & 4" | 805 | 24-Jul-21 A | 2024-06-01 | 1535354.69 | 17 | [5 empty] | 88.2 | 405.62 | 732.33 | 1076.27 | 1517.37 | 1879.67 | 2264.77 | 2652.4 | 2800.86 | 2910.29 | 3019.72 | 3127.73 | 3235.5 | 3319.48 | 3386.19 | 3452.35 | 3533.66 | 3633.5 | 3732.8 | 3838.81 | 3999.3 | 4177.88 | 4462.4 | 4642.2 | 4829.26 | 5008.71 | 5196.88 | 5433.54 | 5716.89 | 6031.8 | 6395.07 | 6734.7 | 7068.96 | 7403.75 | 7451.67 | 9724.16 | 10755.7 | 11787.24 | 12818.77 | 13938.63 | 17048.31 | 22220.67 | 27409.87 | 32620.93 | 37682.95 | 42669.22 | 47794.42 | 53300.56 | 58864.13 | 64131.29 | 69357.34 | 74589.75 | 79788.38 | 84990.26 | 90255.93 | 102561.69 | 124311.73 | 145870.93 | 168017.08 | 190026.14 | 212021.85 | 234020 | 256302.3 | 278399.06 | 300454.36 | 323588.11 | 348504.73 | 373378.68 | 398484.12 | 423751.89 | 450362.77 | 477084.45 | 503212.97 | 529419.78 | 555626.14 | 581837.39 | 608192.57 | 635527.38 | 663868.11 | 692537.44 | 721178.25 | 747243.34 | 771630.39 | 796051.28 | 820466.52 | 849625.47 | 885144.72 | 921401.88 | 949525.61 | 975714.22 | 1007480.44 | 1019303.44 | 1031109.89 | 1042940.95 | 1055567.09 | 1068672.48 | 1081885.36 | 1094825.88 | 1107952.51 | 1121212.5 | 1134235.6 | 1148732.32 | 1162018.96 | 1174441.93 | 1186451.99 | 1196622.17 | 1218215.86 | 1241339.26 | 1256852.82 | 1274705.47 | 1291799.18 | 1308920.58 | 1325905.07 | 1355173.69 | 1378484.76 | 1391249.01 | 1402836.66 | 1412905.92 | 1423148.82 | 1436431.53 | 1449820.65 | 1462958.96 | 1473723.29 | 1480206.85 | 1486568.69 | 1492200.24 | 1497831.79 | 1503462.84 | 1508941 | 1514091.9 | 1516835.71 | 1518034.62 | 1518695.22 | 1519391.91 | 1520181.46 | 1521014.87 | 1521282.74 | 1522341.97 | 1524105.9 | 1526486.07 | 1528600.15 | 1530454.83 | 1531045.48 | 1531636.14 | 1532016.26 | 1532770.67 | 1533337.09 | 1534442.38 | 1535266.96 | 1535354.68 | 1535354.68 | 1535354.68 | 1535354.68 | 0% | 0% | 0% | 0% | 0% | 0.005745% | 0.02642% | 0.0477% | 0.0701% | 0.09883% | 0.1224% | 0.1475% | 0.1728% | 0.1824% | 0.1896% | 0.1967% | 0.2037% | 0.2107% | 0.2162% | 0.2205% | 0.2249% | 0.2302% | 0.2367% | 0.2431% | 0.25% | 0.2605% | 0.2721% | 0.2906% | 0.3024% | 0.3145% | 0.3262% | 0.3385% | 0.3539% | 0.3723% | 0.3929% | 0.4165% | 0.4386% | 0.4604% | 0.4822% | 0.4853% | 0.6333% | 0.7005% | 0.7677% | 0.8349% | 0.9078% | 1.11% | 1.447% | 1.785% | 2.125% | 2.454% | 2.779% | 3.113% | 3.472% | 3.834% | 4.177% | 4.517% | 4.858% | 5.197% | 5.536% | 5.879% | 6.68% | 8.097% | 9.501% | 10.94% | 12.38% | 13.81% | 15.24% | 16.69% | 18.13% | 19.57% | 21.08% | 22.7% | 24.32% | 25.95% | 27.6% | 29.33% | 31.07% | 32.78% | 34.48% | 36.19% | 37.9% | 39.61% | 41.39% | 43.24% | 45.11% | 46.97% | 48.67% | 50.26% | 51.85% | 53.44% | 55.34% | 57.65% | 60.01% | 61.84% | 63.55% | 65.62% | 66.39% | 67.16% | 67.93% | 68.75% | 69.6% | 70.46% | 71.31% | 72.16% | 73.03% | 73.87% | 74.82% | 75.68% | 76.49% | 77.28% | 77.94% | 79.34% | 80.85% | 81.86% | 83.02% | 84.14% | 85.25% | 86.36% | 88.26% | 89.78% | 90.61% | 91.37% | 92.02% | 92.69% | 93.56% | 94.43% | 95.28% | 95.99% | 96.41% | 96.82% | 97.19% | 97.56% | 97.92% | 98.28% | 98.62% | 98.79% | 98.87% | 98.91% | 98.96% | 99.01% | 99.07% | 99.08% | 99.15% | 99.27% | 99.42% | 99.56% | 99.68% | 99.72% | 99.76% | 99.78% | 99.83% | 99.87% | 99.94% | 99.99% | 100% | 100% | 100% | 100%
18 | Package 12- EPC # Compressor Station | 827 | 24-Jul-21 A | 2024-06-23 | 6113771.37 | 18 | [5 empty] | 81.64 | 1557.05 | 3008.96 | 4481.98 | 5995.81 | 7518.35 | 9080.56 | 10690.8 | 11142.17 | 11433.08 | 11719.4 | 12020.32 | 12365.3 | 12724.36 | 13068.65 | 13447.42 | 13856.24 | 14299.59 | 14862.12 | 15542.09 | 16534.77 | 17679.9 | 19118.25 | 20385.53 | 21666.7 | 22856.72 | 23971.5 | 25283.87 | 26784.21 | 28486.27 | 30194.45 | 31918.73 | 33945.87 | 35956.43 | 36243.83 | 52284.05 | 62948.03 | 73611.25 | 84036.56 | 94299.21 | 104048.45 | 113878.86 | 126971.72 | 141280.86 | 157993.66 | 174600.75 | 191135.78 | 207121.96 | 224138.42 | 246765.02 | 271635.69 | 298275.13 | 329613.77 | 363137.98 | 396046.89 | 430296.56 | 465750.46 | 501840.19 | 539164.1 | 581620.93 | 626648.84 | 670508.8 | 714849.33 | 759429.5 | 804338.44 | 850896.28 | 899043.85 | 949512.3 | 1005444.18 | 1060123.23 | 1118829.65 | 1178685.66 | 1238899.24 | 1300479.79 | 1361781.65 | 1423219.55 | 1484718.45 | 1547447.25 | 1614096.23 | 1683631.88 | 1753211.74 | 1823378.85 | 1893672.72 | 1963004.57 | 2034030.47 | 2112012.97 | 2191464.16 | 2273252.09 | 2359829.44 | 2460691.22 | 2575632.35 | 2694631.19 | 2805470.13 | 2923470.19 | 3032656.79 | 3130447.81 | 3227486.68 | 3325278.23 | 3423521.82 | 3521133.22 | 3617671.11 | 3716518.58 | 3812989.24 | 3909492.83 | 3997994.58 | 4085328.51 | 4179426.13 | 4271866.86 | 4350383.27 | 4425982.85 | 4492981.91 | 4558829.54 | 4624294.8 | 4687701.84 | 4755307.12 | 4821858.44 | 4895461.68 | 4995650.85 | 5090646.09 | 5191512.07 | 5298893.13 | 5433909.21 | 5507804.11 | 5540703.05 | 5570732.38 | 5613130.14 | 5765779.11 | 5791497.46 | 5821350.58 | 5850236.22 | 5877815.64 | 5903520.93 | 5929226.23 | 5953904.85 | 5974862.03 | 5989439.7 | 5998893.74 | 6006298.31 | 6013702.89 | 6018324.6 | 6022482.5 | 6026156.42 | 6028429.28 | 6029501.11 | 6035673.84 | 6042169.41 | 6048514.33 | 6070981.49 | 6091864.58 | 6101125.37 | 6107469.5 | 6112738.28 | 6113771.37 | 0% | 0% | 0% | 0% | 0% | 0.001335% | 0.02547% | 0.04922% | 0.07331% | 0.09807% | 0.123% | 0.1485% | 0.1749% | 0.1822% | 0.187% | 0.1917% | 0.1966% | 0.2023% | 0.2081% | 0.2138% | 0.22% | 0.2266% | 0.2339% | 0.2431% | 0.2542% | 0.2705% | 0.2892% | 0.3127% | 0.3334% | 0.3544% | 0.3739% | 0.3921% | 0.4136% | 0.4381% | 0.4659% | 0.4939% | 0.5221% | 0.5552% | 0.5881% | 0.5928% | 0.8552% | 1.03% | 1.204% | 1.375% | 1.542% | 1.702% | 1.863% | 2.077% | 2.311% | 2.584% | 2.856% | 3.126% | 3.388% | 3.666% | 4.036% | 4.443% | 4.879% | 5.391% | 5.94% | 6.478% | 7.038% | 7.618% | 8.208% | 8.819% | 9.513% | 10.25% | 10.97% | 11.69% | 12.42% | 13.16% | 13.92% | 14.71% | 15.53% | 16.45% | 17.34% | 18.3% | 19.28% | 20.26% | 21.27% | 22.27% | 23.28% | 24.28% | 25.31% | 26.4% | 27.54% | 28.68% | 29.82% | 30.97% | 32.11% | 33.27% | 34.55% | 35.84% | 37.18% | 38.6% | 40.25% | 42.13% | 44.07% | 45.89% | 47.82% | 49.6% | 51.2% | 52.79% | 54.39% | 56% | 57.59% | 59.17% | 60.79% | 62.37% | 63.95% | 65.39% | 66.82% | 68.36% | 69.87% | 71.16% | 72.39% | 73.49% | 74.57% | 75.64% | 76.67% | 77.78% | 78.87% | 80.07% | 81.71% | 83.27% | 84.92% | 86.67% | 88.88% | 90.09% | 90.63% | 91.12% | 91.81% | 94.31% | 94.73% | 95.22% | 95.69% | 96.14% | 96.56% | 96.98% | 97.39% | 97.73% | 97.97% | 98.12% | 98.24% | 98.36% | 98.44% | 98.51% | 98.57% | 98.6% | 98.62% | 98.72% | 98.83% | 98.93% | 99.3% | 99.64% | 99.79% | 99.9% | 99.98% | 100%
EPCC | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158
| Activity ID | Original Duration | Start | Finish | Budgeted Labor Units | Spreadsheet Field | [158 empty] | 2021-06-19 | 2021-06-26 | 2021-07-03 | 2021-07-10 | 2021-07-17 | 2021-07-24 | 2021-07-31 | 2021-08-07 | 2021-08-14 | 2021-08-21 | 2021-08-28 | 2021-09-04 | 2021-09-11 | 2021-09-18 | 2021-09-25 | 2021-10-02 | 2021-10-09 | 2021-10-16 | 2021-10-23 | 2021-10-30 | 2021-11-06 | 2021-11-13 | 2021-11-20 | 2021-11-27 | 2021-12-04 | 2021-12-11 | 2021-12-18 | 2021-12-25 | 2022-01-01 | 2022-01-08 | 2022-01-15 | 2022-01-22 | 2022-01-29 | 2022-02-05 | 2022-02-12 | 2022-02-19 | 2022-02-26 | 2022-03-05 | 2022-03-12 | 2022-03-19 | 2022-03-26 | 2022-04-02 | 2022-04-09 | 2022-04-16 | 2022-04-23 | 2022-04-30 | 2022-05-07 | 2022-05-14 | 2022-05-21 | 2022-05-28 | 2022-06-04 | 2022-06-11 | 2022-06-18 | 2022-06-25 | 2022-07-02 | 2022-07-09 | 2022-07-16 | 2022-07-23 | 2022-07-30 | 2022-08-06 | 2022-08-13 | 2022-08-20 | 2022-08-27 | 2022-09-03 | 2022-09-10 | 2022-09-17 | 2022-09-24 | 2022-10-01 | 2022-10-08 | 2022-10-15 | 2022-10-22 | 2022-10-29 | 2022-11-05 | 2022-11-12 | 2022-11-19 | 2022-11-26 | 2022-12-03 | 2022-12-10 | 2022-12-17 | 2022-12-24 | 2022-12-31 | 2023-01-07 | 2023-01-14 | 2023-01-21 | 2023-01-28 | 2023-02-04 | 2023-02-11 | 2023-02-18 | 2023-02-25 | 2023-03-04 | 2023-03-11 | 2023-03-18 | 2023-03-25 | 2023-04-01 | 2023-04-08 | 2023-04-15 | 2023-04-22 | 2023-04-29 | 2023-05-06 | 2023-05-13 | 2023-05-20 | 2023-05-27 | 2023-06-03 | 2023-06-10 | 2023-06-17 | 2023-06-24 | 2023-07-01 | 2023-07-08 | 2023-07-15 | 2023-07-22 | 2023-07-29 | 2023-08-05 | 2023-08-12 | 2023-08-19 | 2023-08-26 | 2023-09-02 | 2023-09-09 | 2023-09-16 | 2023-09-23 | 2023-09-30 | 2023-10-07 | 2023-10-14 | 2023-10-21 | 2023-10-28 | 2023-11-04 | 2023-11-11 | 2023-11-18 | 2023-11-25 | 2023-12-02 | 2023-12-09 | 2023-12-16 | 2023-12-23 | 2023-12-30 | 2024-01-06 | 2024-01-13 | 2024-01-20 | 2024-01-27 | 2024-02-03 | 2024-02-10 | 2024-02-17 | 2024-02-24 | 2024-03-02 | 2024-03-09 | 2024-03-16 | 2024-03-23 | 2024-03-30 | 2024-04-06 | 2024-04-13 | 2024-04-20 | 2024-04-27 | 2024-05-04 | 2024-05-11 | 2024-05-18 | 2024-05-25 | 2024-06-01 | 2024-06-08 | 2024-06-15 | 2024-06-22 | time axis 2021-06-19 to 2024-06-22
22 | General | 720 | 23-Jun-21 A | 2024-03-08 | 532432.82 | 22 | 20.33 | 70.22 | 133.86 | 369.75 | 513.55 | 4706.1 | 9573.07 | 14474.49 | 18846.41 | 23154.6 | 27387.11 | 31165.57 | 35045.55 | 38824.01 | 42602.47 | 44045.78 | 45201.43 | 46255.55 | 47309.67 | 48363.79 | 49519.44 | 50595.57 | 51789.35 | 53757.17 | 55515.67 | 57418.18 | 59219.16 | 60997.08 | 62746.18 | 64596.8 | 66345.9 | 68819.26 | 73103.28 | 81403.86 | 90345.63 | 99315.18 | 108236.73 | 118814.41 | 132556.82 | 133590.53 | 277452.22 | 322590.14 | 345934.83 | 355761.59 | 364501.41 | 374833.13 | 382591.6 | 389660.52 | 396471.69 | 402229.14 | 411988.8 | 416023.01 | 420155.69 | 423692.89 | 426812.63 | 446008.23 | 447688.38 | 449230.51 | 450988.59 | 452537.82 | 453985.54 | 455433.25 | 456880.96 | 458405.83 | 459504.56 | 460889.3 | 461969.46 | 465532.48 | 466714.17 | 467794.32 | 468874.48 | 469954.64 | 471136.32 | 472216.48 | 473296.64 | 474376.8 | 475558.48 | 476638.64 | 477718.8 | 478798.95 | 479980.64 | 481060.8 | 482140.95 | 483221.11 | 484301.27 | 485482.95 | 486563.11 | 487643.27 | 488723.43 | 489905.11 | 491289.85 | 492370.01 | 493450.17 | 494631.85 | 495712.01 | 496792.17 | 497872.32 | 498952.48 | 500134.17 | 501214.32 | 502294.48 | 503374.64 | 504556.32 | 505636.48 | 506716.64 | 507769.57 | 508802.07 | 509834.58 | 510867.09 | 511899.6 | 512878.1 | 513784.6 | 514691.1 | 515597.61 | 516499.28 | 517400.15 | 518605.6 | 519443.9 | 520125.76 | 520807.63 | 521520.72 | 522358.45 | 523196.17 | 524033.89 | 524843.76 | 525545.38 | 526069.19 | 526593 | 527107.69 | 527615.55 | 528123.4 | 528631.26 | 529036.52 | 529424.68 | 529812.84 | 530180.61 | 530535.18 | 530889.76 | 531244.33 | 531597.79 | 531944.56 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 532140.33 | 0.00382% | 0.0132% | 0.02516% | 0.06948% | 0.09651% | 0.8844% | 1.799% | 2.72% | 3.542% | 4.351% | 5.147% | 5.857% | 6.586% | 7.296% | 8.006% | 8.277% | 8.494% | 8.692% | 8.89% | 9.089% | 9.306% | 9.508% | 9.732% | 10.1% | 10.43% | 10.79% | 11.13% | 11.46% | 11.79% | 12.14% | 12.47% | 12.93% | 13.74% | 15.3% | 16.98% | 18.66% | 20.34% | 22.33% | 24.91% | 25.1% | 52.14% | 60.62% | 65.01% | 66.85% | 68.5% | 70.44% | 71.9% | 73.23% | 74.51% | 75.59% | 77.42% | 78.18% | 78.96% | 79.62% | 80.21% | 83.81% | 84.13% | 84.42% | 84.75% | 85.04% | 85.31% | 85.59% | 85.86% | 86.14% | 86.35% | 86.61% | 86.81% | 87.48% | 87.71% | 87.91% | 88.11% | 88.31% | 88.54% | 88.74% | 88.94% | 89.15% | 89.37% | 89.57% | 89.77% | 89.98% | 90.2% | 90.4% | 90.6% | 90.81% | 91.01% | 91.23% | 91.44% | 91.64% | 91.84% | 92.06% | 92.32% | 92.53% | 92.73% | 92.95% | 93.15% | 93.36% | 93.56% | 93.76% | 93.99% | 94.19% | 94.39% | 94.59% | 94.82% | 95.02% | 95.22% | 95.42% | 95.61% | 95.81% | 96% | 96.2% | 96.38% | 96.55% | 96.72% | 96.89% | 97.06% | 97.23% | 97.46% | 97.61% | 97.74% | 97.87% | 98% | 98.16% | 98.32% | 98.48% | 98.63% | 98.76% | 98.86% | 98.96% | 99.05% | 99.15% | 99.25% | 99.34% | 99.42% | 99.49% | 99.56% | 99.63% | 99.7% | 99.76% | 99.83% | 99.9% | 99.96% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
23 | Engineering | 759 | 24-Jul-21 A | 2024-04-16 | 272905.67 | 23 | [5 empty] | 447.59 | 2558.63 | 4640.12 | 6773.18 | 9146.74 | 11390.11 | 13678.39 | 16020.56 | 16754.16 | 17258.66 | 17758.57 | 18271.63 | 18830.84 | 19361 | 19860.93 | 20403.73 | 21022.36 | 21697.38 | 22496.48 | 23460.54 | 24778.64 | 26348.13 | 28248.4 | 29869.42 | 31539.26 | 33078.31 | 34546.44 | 36323.67 | 38367.47 | 40660.49 | 43148.21 | 45571.8 | 48341.73 | 51150.73 | 51552 | 64947.24 | 71403.48 | 77895.92 | 84187.02 | 90398.15 | 95452.73 | 98997.51 | 103111.52 | 107532.6 | 111731.4 | 115686.1 | 119737.34 | 123472.31 | 126879.76 | 130518.15 | 135221.47 | 140231.26 | 146010.9 | 151135.45 | 155581.64 | 160136.16 | 164684.46 | 167819.37 | 169945.2 | 172629.63 | 175844.33 | 177378.34 | 179349.3 | 181454.52 | 183740.44 | 186239.69 | 188745.92 | 191700.49 | 195130.15 | 197190.28 | 199656.12 | 201763.4 | 203435.18 | 205019.08 | 206389.1 | 207595.5 | 208629.89 | 210556.38 | 212223.74 | 214125.36 | 215356.73 | 216432.1 | 217416.39 | 218254.69 | 218835.84 | 219578.89 | 220328.64 | 221504.6 | 222675.62 | 223285.01 | 223707.19 | 224279.99 | 224776.23 | 224917.64 | 225117.09 | 225468.01 | 225854.11 | 226224.58 | 226228.06 | 226322.21 | 226452.64 | 226628.19 | 226926.31 | 227648.58 | 228075.08 | 228351.43 | 228351.43 | 228368.4 | 228487.18 | 228577.69 | 228656.88 | 228736.07 | 228747.39 | 228750.47 | 228759.26 | 228768.05 | 228776.84 | 228790.78 | 228817.06 | 228852.13 | 228970.92 | 229123.65 | 229225 | 229262.96 | 229300.91 | 229338.87 | 229376.83 | 229376.83 | 230596.89 | 232519.42 | 233323.25 | 234153.21 | 234983.18 | 235813.15 | 238008.83 | 249005.56 | 254903.07 | 258678 | 261796.74 | 264915.47 | 268034.21 | 271152.95 | 272935.08 | 272935.08 | 272935.08 | 272935.08 | 272935.08 | 272935.08 | 272935.08 | 272935.08 | 272935.08 | 272935.08 | 272935.08 | 0% | 0% | 0% | 0% | 0% | 0.164% | 0.9375% | 1.7% | 2.482% | 3.351% | 4.173% | 5.012% | 5.87% | 6.139% | 6.323% | 6.507% | 6.694% | 6.899% | 7.094% | 7.277% | 7.476% | 7.702% | 7.95% | 8.242% | 8.596% | 9.079% | 9.654% | 10.35% | 10.94% | 11.56% | 12.12% | 12.66% | 13.31% | 14.06% | 14.9% | 15.81% | 16.7% | 17.71% | 18.74% | 18.89% | 23.8% | 26.16% | 28.54% | 30.85% | 33.12% | 34.97% | 36.27% | 37.78% | 39.4% | 40.94% | 42.39% | 43.87% | 45.24% | 46.49% | 47.82% | 49.54% | 51.38% | 53.5% | 55.37% | 57% | 58.67% | 60.34% | 61.49% | 62.27% | 63.25% | 64.43% | 64.99% | 65.71% | 66.48% | 67.32% | 68.24% | 69.15% | 70.24% | 71.49% | 72.25% | 73.15% | 73.92% | 74.54% | 75.12% | 75.62% | 76.06% | 76.44% | 77.15% | 77.76% | 78.45% | 78.9% | 79.3% | 79.66% | 79.97% | 80.18% | 80.45% | 80.73% | 81.16% | 81.59% | 81.81% | 81.96% | 82.17% | 82.36% | 82.41% | 82.48% | 82.61% | 82.75% | 82.89% | 82.89% | 82.92% | 82.97% | 83.03% | 83.14% | 83.41% | 83.56% | 83.67% | 83.67% | 83.67% | 83.71% | 83.75% | 83.78% | 83.81% | 83.81% | 83.81% | 83.81% | 83.82% | 83.82% | 83.83% | 83.84% | 83.85% | 83.89% | 83.95% | 83.99% | 84% | 84.01% | 84.03% | 84.04% | 84.04% | 84.49% | 85.19% | 85.49% | 85.79% | 86.09% | 86.4% | 87.2% | 91.23% | 93.39% | 94.78% | 95.92% | 97.06% | 98.2% | 99.35% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
24 | Procurement | 672 | 01-Feb-22 A | 2024-01-20 | 7033236.1 | 24 | [40 empty] | 17191.28 | 37203.43 | 54112.3 | 69581.51 | 86632.91 | 111864.08 | 142590.34 | 174350.61 | 208224.73 | 246057.83 | 287249.49 | 332147.85 | 381666.53 | 437329.09 | 496943.24 | 573862.07 | 662580.63 | 735224.07 | 808945.83 | 879443.29 | 946385.19 | 1018482.46 | 1093825.39 | 1170667.96 | 1252543.9 | 1345269.38 | 1430364.78 | 1520199.49 | 1620991.44 | 1712983.33 | 1804699.01 | 1897478.3 | 1993000.95 | 2093487.54 | 2186649.96 | 2276436.35 | 2365838.16 | 2457553.22 | 2550865.94 | 2641818.93 | 2731653.94 | 2822357.07 | 2920615.85 | 3013150.12 | 3108543.66 | 3204880.24 | 3301611.68 | 3399456.65 | 3496111.21 | 3591951.89 | 3697004.47 | 3810084.21 | 3924771.06 | 4028975.88 | 4135857.42 | 4255138.36 | 4354823.61 | 4449743.49 | 4551311.39 | 4649335.44 | 4741434.54 | 4834907.43 | 4925536.69 | 5017811.39 | 5110514.93 | 5202551.53 | 5300053.07 | 5394475.63 | 5490121.18 | 5581831.41 | 5670053.19 | 5778481.55 | 5877474.24 | 5952412.18 | 6023894.4 | 6087345.32 | 6142127.94 | 6193417.32 | 6253957.08 | 6314267.6 | 6365189.81 | 6407856.61 | 6473670.01 | 6533522.74 | 6595420.88 | 6670913.81 | 6779455.2 | 6832538.56 | 6850778.27 | 6870977.28 | 6902898.34 | 7030418.9 | 7031718.27 | 7032551.5 | 7033183.85 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 7033236.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2444% | 0.529% | 0.7694% | 0.9893% | 1.232% | 1.591% | 2.027% | 2.479% | 2.961% | 3.499% | 4.084% | 4.723% | 5.427% | 6.218% | 7.066% | 8.159% | 9.421% | 10.45% | 11.5% | 12.5% | 13.46% | 14.48% | 15.55% | 16.64% | 17.81% | 19.13% | 20.34% | 21.61% | 23.05% | 24.36% | 25.66% | 26.98% | 28.34% | 29.77% | 31.09% | 32.37% | 33.64% | 34.94% | 36.27% | 37.56% | 38.84% | 40.13% | 41.53% | 42.84% | 44.2% | 45.57% | 46.94% | 48.33% | 49.71% | 51.07% | 52.56% | 54.17% | 55.8% | 57.28% | 58.8% | 60.5% | 61.92% | 63.27% | 64.71% | 66.11% | 67.41% | 68.74% | 70.03% | 71.34% | 72.66% | 73.97% | 75.36% | 76.7% | 78.06% | 79.36% | 80.62% | 82.16% | 83.57% | 84.63% | 85.65% | 86.55% | 87.33% | 88.06% | 88.92% | 89.78% | 90.5% | 91.11% | 92.04% | 92.89% | 93.78% | 94.85% | 96.39% | 97.15% | 97.41% | 97.69% | 98.15% | 99.96% | 99.98% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
25 | Construction | 950 | 20-Aug-21 A | 2024-04-07 | 2052025.78 | 25 | [8 empty] | 481.6 | 3834.11 | 6601.07 | 8462.68 | 11324.1 | 13634.38 | 15260.23 | 16069.34 | 16564.12 | 17672.76 | 19088.33 | 19583.11 | 20077.89 | 20572.68 | 22152.7 | 26130.73 | 30795.85 | 36759.73 | 39859.91 | 41265.56 | 42585.45 | 43998.74 | 46073.7 | 48164.3 | 49549.65 | 50676.47 | 51803.3 | 55097.41 | 59125.38 | 63190.16 | 67261.09 | 67842.65 | 73584.96 | 75241.25 | 75550.49 | 76345.58 | 77071.14 | 80487.89 | 85368.38 | 90540.92 | 98073.06 | 103516.92 | 108024.99 | 112312.83 | 116165.08 | 122080.93 | 131624 | 160393.65 | 213426.41 | 239319.39 | 247414.74 | 251356.51 | 259284.67 | 270449.16 | 281858.57 | 292355.45 | 301885.32 | 308769.63 | 315865.87 | 323272.7 | 335021.22 | 352260.51 | 367934.81 | 383413.52 | 400474.96 | 425689.91 | 442946.3 | 461722.81 | 477782.49 | 494734.51 | 511038.22 | 529723.79 | 553263.93 | 574823.22 | 590775.15 | 607075.38 | 623323.38 | 638371.26 | 653002.6 | 667793.34 | 685636.57 | 696211.27 | 710220.3 | 724318.82 | 737761.23 | 756812.95 | 790211.97 | 830699.36 | 867129.72 | 897259.54 | 928432.61 | 958785.52 | 980852.82 | 1000756.54 | 1024962.46 | 1046309.07 | 1068273.88 | 1090047 | 1109822.31 | 1127698.2 | 1143311.05 | 1155252.56 | 1167477.37 | 1175508.94 | 1192792.87 | 1212636.26 | 1235382.05 | 1256673.35 | 1285221.88 | 1317118.34 | 1349792.86 | 1381301.72 | 1409766.42 | 1452292.31 | 1496739.13 | 1542126.34 | 1594434.13 | 1639854.24 | 1679469.04 | 1711035.85 | 1732142.22 | 1748296.42 | 1764368.41 | 1795137.78 | 1825235.19 | 1858560.52 | 1890067.57 | 1919572.84 | 1945971.08 | 1975724.7 | 2004916.36 | 2026897.31 | 2032912.13 | 2039784.34 | 2044900.89 | 2049186.73 | 2050689.71 | 2051728.88 | 2052025.78 | 2052025.78 | 2052025.78 | 2052025.78 | 2052025.78 | 2052025.78 | 2052025.78 | 2052025.78 | 2052025.78 | 2052025.78 | 2052025.78 | 2052025.78 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.02347% | 0.1868% | 0.3217% | 0.4124% | 0.5518% | 0.6644% | 0.7437% | 0.7831% | 0.8072% | 0.8612% | 0.9302% | 0.9543% | 0.9784% | 1.003% | 1.08% | 1.273% | 1.501% | 1.791% | 1.942% | 2.011% | 2.075% | 2.144% | 2.245% | 2.347% | 2.415% | 2.47% | 2.524% | 2.685% | 2.881% | 3.079% | 3.278% | 3.306% | 3.586% | 3.667% | 3.682% | 3.72% | 3.756% | 3.922% | 4.16% | 4.412% | 4.779% | 5.045% | 5.264% | 5.473% | 5.661% | 5.949% | 6.414% | 7.816% | 10.4% | 11.66% | 12.06% | 12.25% | 12.64% | 13.18% | 13.74% | 14.25% | 14.71% | 15.05% | 15.39% | 15.75% | 16.33% | 17.17% | 17.93% | 18.68% | 19.52% | 20.74% | 21.59% | 22.5% | 23.28% | 24.11% | 24.9% | 25.81% | 26.96% | 28.01% | 28.79% | 29.58% | 30.38% | 31.11% | 31.82% | 32.54% | 33.41% | 33.93% | 34.61% | 35.3% | 35.95% | 36.88% | 38.51% | 40.48% | 42.26% | 43.73% | 45.24% | 46.72% | 47.8% | 48.77% | 49.95% | 50.99% | 52.06% | 53.12% | 54.08% | 54.96% | 55.72% | 56.3% | 56.89% | 57.29% | 58.13% | 59.09% | 60.2% | 61.24% | 62.63% | 64.19% | 65.78% | 67.31% | 68.7% | 70.77% | 72.94% | 75.15% | 77.7% | 79.91% | 81.84% | 83.38% | 84.41% | 85.2% | 85.98% | 87.48% | 88.95% | 90.57% | 92.11% | 93.55% | 94.83% | 96.28% | 97.7% | 98.78% | 99.07% | 99.4% | 99.65% | 99.86% | 99.93% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
26 | Commissioning | 537.25 | 2023-01-03 | 2024-06-23 | 109399.69 | 26 | 2022-12-31: 5.57; 2023-01-07: 15.44; 2023-01-14: 60.47; 2023-01-21: 124.6; 2023-01-28: 127.6; 2023-02-04: 267.65; 2023-02-11: 283.66; 2023-02-18: 313.35; 2023-02-25: 338.92; 2023-03-04: 466.95; 2023-03-11: 557.11; 2023-03-18: 608.86; 2023-03-25: 850.67; 2023-04-01: 881.99; 2023-04-08: 908.13; 2023-04-15: 947.43; 2023-04-22: 978.93; 2023-04-29: 1159.92; 2023-05-06: 1298.32; 2023-05-13: 1565.75; 2023-05-20: 1707.08; 2023-05-27: 1780.94; 2023-06-03: 2738.27; 2023-06-10: 4124.34; 2023-06-17: 4599.83; 2023-06-24: 4957.91; 2023-07-01: 5346.63; 2023-07-08: 5563.55; 2023-07-15: 5663.85; 2023-07-22: 5714.74; 2023-07-29: 5971.53; 2023-08-05: 6215.71; 2023-08-12: 6337.55; 2023-08-19: 6383.24; 2023-08-26: 6416.37; 2023-09-02: 6499.14; 2023-09-09: 6675.8; 2023-09-16: 6751.61; 2023-09-23: 6758.92; 2023-09-30: 7037.41; 2023-10-07: 7068.56; 2023-10-14: 7098.84; 2023-10-21: 7125.12; 2023-10-28: 7151.41; 2023-11-04: 7244.34; 2023-11-11: 7309.09; 2023-11-18: 7354.67; 2023-11-25: 7453.29; 2023-12-02: 7493.27; 2023-12-09: 7496.85; 2023-12-16: 7667.38; 2023-12-23: 7686.45; 2023-12-30: 7704.99; 2024-01-06: 7721.09; 2024-01-13: 7737.18; 2024-01-20: 7810.18; 2024-01-27: 7831.64; 2024-02-03: 7853.1; 2024-02-10: 7899.26; 2024-02-17: 8041.81; 2024-02-24: 8228.22; 2024-03-02: 8403.66; 2024-03-09: 9475.39; 2024-03-16: 11258.06; 2024-03-23: 13844.4; 2024-03-30: 15964.31; 2024-04-06: 18083.09; 2024-04-13: 19445.19; 2024-04-20: 21138.78; 2024-04-27: 27721.35; 2024-05-04: 34997.56; 2024-05-11: 41935.14; 2024-05-18: 65627.54; 2024-05-25: 87370.19; 2024-06-01: 96753.69; 2024-06-08: 103097.82; 2024-06-15: 108366.59; 2024-06-22: 109399.69 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.005091% | 0.01411% | 0.05527% | 0.1139% | 0.1166% | 0.2447% | 0.2593% | 0.2864% | 0.3098% | 0.4268% | 0.5092% | 0.5565% | 0.7776% | 0.8062% | 0.8301% | 0.866% | 0.8948% | 1.06% | 1.187% | 1.431% | 1.56% | 1.628% | 2.503% | 3.77% | 4.205% | 4.532% | 4.887% | 5.086% | 5.177% | 5.224% | 5.458% | 5.682% | 5.793% | 5.835% | 5.865% | 5.941% | 6.102% | 6.172% | 6.178% | 6.433% | 6.461% | 6.489% | 6.513% | 6.537% | 6.622% | 6.681% | 6.723% | 6.813% | 6.849% | 6.853% | 7.009% | 7.026% | 7.043% | 7.058% | 7.072% | 7.139% | 7.159% | 7.178% | 7.221% | 7.351% | 7.521% | 7.682% | 8.661% | 10.29% | 12.65% | 14.59% | 16.53% | 17.77% | 19.32% | 25.34% | 31.99% | 38.33% | 59.99% | 79.86% | 88.44% | 94.24% | 99.06% | 100%
[7 empty] | 20.33 | 70.22 | 133.86 | 369.75 | 513.55 | 5153.69 | 12131.7 | 19114.61 | 26101.19 | 36135.45 | 45378.29 | 53306.64 | 62390.21 | 69212.55 | 75121.36 | 77873.69 | 80037.18 | 82759.15 | 85759 | 87807.83 | 90001.06 | 92190.61 | 95639.43 | 102384.38 | 109772.06 | 118956.55 | 125427.2 | 130511.04 | 135201.05 | 140134.8 | 145497.91 | 151530 | 158976.6 | 170447.8 | 182809.42 | 197560.8 | 212933.91 | 230346.3 | 250968.64 | 252985.18 | 433175.7 | 506438.3 | 553493.54 | 585875.7 | 618603.61 | 662637.83 | 709547.83 | 757663.57 | 810302.08 | 863535.29 | 922949.38 | 980221.03 | 1041459.61 | 1109982.67 | 1185898.02 | 1315485.42 | 1463926.68 | 1569784.87 | 1658484.61 | 1738919.26 | 1819791.56 | 1909049.33 | 2000384.29 | 2091374.44 | 2186563.41 | 2290772.64 | 2385578.45 | 2488353.97 | 2604181.35 | 2716778.6 | 2827747.99 | 2939592.38 | 3056312.72 | 3186524.08 | 3300083.18 | 3412192.08 | 3520942.53 | 3632361.55 | 3744642.04 | 3856730.77 | 3972499.58 | 4086886.42 | 4204148.8 | 4315794.95 | 4430421.27 | 4544358.83 | 4657893.15 | 4772623 | 4889064.82 | 4997371.06 | 5118650.62 | 5247710.54 | 5378337.73 | 5503978.29 | 5645974.54 | 5807284.51 | 5945084.57 | 6071891.66 | 6206094.13 | 6336018.12 | 6451756.93 | 6566673.66 | 6684018.32 | 6800109.34 | 6916427.49 | 7031778.65 | 7150652.27 | 7264498.27 | 7377611.75 | 7482773.39 | 7584731.62 | 7702342.23 | 7819664.16 | 7915516.47 | 8010769.79 | 8096574.84 | 8181367.29 | 8265478.56 | 8359385.09 | 8452173.62 | 8532313.56 | 8618383.05 | 8729521.21 | 8835651.44 | 8950795.24 | 9072593.44 | 9221471.75 | 9306845.7 | 9346784.41 | 9383687.01 | 9432396.4 | 9591251.22 | 9623071.8 | 9658854.68 | 9693320.86 | 9724122.98 | 9751727.21 | 9782686.84 | 9813109.2 | 9837781.84 | 9855326.57 | 9868467.5 | 9878430.71 | 9887617.96 | 9894826.01 | 9901103.83 | 9906638.25 | 9909782.48 | 9911476.07 | 9918058.64 | 9925334.85 | 9932272.43 | 9955964.83 | 9977707.48 | 9987090.98 | 9993435.11 | 9998703.88 | 9999736.98
[7 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE