## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-CV-PY-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-0783 |  |  | Transmital Date: 6-Apr-22
Document Title: BINAK Oil Field Project Overall Well Location/Facilities Layout |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-0783 |  |  | Transmital Date: 6-Apr-22
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-CV-PY-0001-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | صحت و انطباق اطلاعات مختصاتی و طولی مربوط به: Above Ground Flow Line-Well Location-Gas pipeline 8" -Condensate Pipeline 4"- Power line & Site با توجه به شرح پیمان بر عهده پیمانکار مجری است. |  | 01/2294/19624 | 1401/01/23 | مورد قبول است.
2 | در خصوص نمایش خطوط انتقال برق چاهها و برای مشخصات نقاط شروع این خطوط - برای مثال در نقطه مبدا خط انتقال مربوط به چاههای BK:5&12&15 - عبارت T-off Existing OHL GCS to DU قید گردد. |  | 01/2294/19624 | 1401/01/23 | اعمال شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: