## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-CV-DW-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0560 |  |  | Transmital Date: 02/07/2022
Document Title: Standard Drawing For Civil Underground Crossings |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0011-CV-TR-0560 |  |  | Transmital Date: 02/07/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0008_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | شیب های درج شده در پلان و مقلطع به صورت درصد قید گردند. |  | 1400-2294-407467 | 1400/11/24 | اعمال شد.
2 | در قسمت مقاطع،ضمن معرفی لایه ها، مشخصات آنها در نقشه درج گردد. |  | 1400-2294-407467 | 1400/11/24 | اعمال شد.
3 | حداقل ضخامت Cable Trench Cover در مقاطع قید گردد. |  | 1400-2294-407467 | 1400/11/24 | اعمال شد.
4 | جزئیات کانال ها و ترنچ ها قید شود. همچنین در مقطع Pipe & Street Crossing Type C کانال ها به صورت غیر مسلح ترسیم شده است، کلیه ی سازه های بتنی می بایست به صورت مسلح طراحی گردد. |  | 1400-2294-407467 | 1400/11/24 | اعمال شد.
5 | مشخصات و جزئیات واتر استاپ و سایر درز های اجرایی در مدرک قید گردد. |  | 1400-2294-407467 | 1400/11/24 | اعمال شد.
6 | ضخامت و مشخصات تمامی لایه ها در پلان و مقاطع درج گردد. |  | 1400-2294-407467 | 1400/11/24 | اعمال شد.
7 | جدول خم و برش آرماتوربندی تهیه و در نقشه درج گردد.(برای 1 متر طول) |  | 1400-2294-407467 | 1400/11/24 | با توجه به پارامتری بودن ابعاد کانال (وابستگی به سایز لوله)امکان تهیه لیستوفر وجود ندارد.
8 | مقطع اجرایی ساخت مارکر و نحوه اجرا و فواصل ارائه گردد. |  | 1400-2294-407467 | 1400/11/24 | اعمال شد.
9 | جزئیات و مشخصات شامل نوع بتن، ضخامت و ... مربوط به اسلب های خطر درج گردد. |  | 1400-2294-407467 | 1400/11/24 | به مدرک مربوطه ارجاع داده شد.
10 | در صورت استفاده از نقشه های استاندارد در بخش مراجع شماره نقشه درج گردد. |  | 1400-2294-407467 | 1400/11/24 | ذکر شد.
11 | استفاده از Water Proof Primer برای سطوح بتنی درگیر با خاک قید شود. |  | 1400-2294-407467 | 1400/11/24 | به مدرک مربوطه Standard Details of Miscellaneous Items ارجاع داده شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: