## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-HV-DG-0001-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1056 |  |  | Transmital Date: 11/Jun/2022
Document Title: HVAC Flow Diagram For Control Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-HV-TR-1056 |  |  | Transmital Date: 11/Jun/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-HV-DG-0001-D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بررسی مدرک فوق منوط به نهایی شدن فایل محاسبات ترانسیتال 767 مربوط به آن است. قبلا طی نامه شماره 01/2294/27253 مورخ 1401/01/28 نقطه نظرات این امور به پیمانکار اعلام شده است. |  | 01/2294/122267 | 08/04/1401 | با توجه به تغییرات اساسی در نقشه معماری ساختمان کنترل، تغییرات اساسی در نقشه HVAC Flow Diagram For Control Building صورت گرفت ضمنا محاسبات با توجه به معماری جدید و کامنتهای مربوطه اصلاح شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H.ADINEH | Signature
| Date: 4/11/2022 |  |  |  |  | Date: 20/07/2022