## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PL-DW-0013 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0373 |  |  | Transmital Date:12/21/2021
Document Title: Pipeline Standard Drawing For Cover Slabs And Set-On-Weight |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0013-PL-TR-0373 |  |  | Transmital Date:12/21/2021
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0013_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به محتوای متفاوت مدارک ، تغییر نام این مدرک مورد پذیرش نمی باشد . |  | 00/2294/341839 | 1400/10/08 | اعمال گردید .
2 | در صورتی که این مدرک از نقشه های استاندارد استخراج شده است ، نسبت به درج شماره استاندارد اقدام گردد . |  | 00/2294/341839 | 1400/10/08 | اعمال گردید .
3 | آرماتور مصرفی از نوع A3 عنوان شده و مشخصات آن در قسمت NOTE قید گردد . |  | 00/2294/341839 | 1400/10/08 | اعمال گردید .
4 | کاراکتر مشخص کننده قطر آرماتور و فاصله بین آنها تصحیح گردد . |  | 00/2294/341839 | 1400/10/08 | اعمال گردید .
5 | قسمت مراجع تکمیل گردد . |  | 00/2294/341839 | 1400/10/08 | اعمال گردید .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: