## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-CV-CN-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-0460 |  |  | Transmital Date: 15-Jan-2021
Document Title: Calculation Note For Flood Control |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-0460 |  |  | Transmital Date: 15-Jan-2021
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | BK-SUR-ENG-CIV-00-02816 | 2022-01-26 | بر اساس طرح مدیریت پسماند بازنگری کلی شد.
1 |  |  | BK-SUR-ENG-CIV-00-02816 | 2022-01-26 | اعمال شد
1 |  |  | BK-SUR-ENG-CIV-00-02816 | 2022-01-26 | اعمال شد
1 |  |  | BK-SUR-ENG-CIV-00-02816 | 2022-01-26 | اعمال شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: